## Decision Log
ID | Date raised | Name of raiser | Decision Description | Related topic area | Status | DA change required? | Approval Mechanism (if applicable) | Approved Decision (if applicable) | Agreed by | Date Agreed | Comments | Delivery event | Consistency Check
CDD-01 |  | Mark De Souza Wilson | Such as with theft and Long Term Vacant. Do we want BSCP for Suppliers? |  | Closed | N/A | Weekly decisions meeting | Transactional interfaces between the supplier and their services will be included in the BSCP for Data Services. The supplier identification of theft or long term vacant sites is out of scope for MHHS programme | Kevin Spencer Mark DeSouza Wilson Derek Weaving Andrew Margan | 2023-02-02 |  |  | Complete
CDD-02 |  | Mark De Souza Wilson | Lloading of ISD, Registration Data, Load Shapes are implicit in the Method Statement. Should Data Service BSCP explicity outline this process/activity? |  | Closed |  | Internal Programme | Embedded within the BSCPs |  |  |  |  | Complete
CDD-03 |  | Mark De Souza Wilson | Disconnection/deregistration - should sit in BSCP501? |  | Closed |  | Internal Programme | This will sit within REC and DCUSA |  |  |  |  | Complete
CDD-04 |  | Mark De Souza Wilson | Do we need a process to cater for changes in switched-load status? |  | Closed |  | Weekly decisions meeting | If something is required it would need to follow the CR process | Kevin Spencer Derek Weaving Mark deSouza Wilson Matt McKeon | 2023-02-21 |  |  | Complete
CDD-05 |  | Mark De Souza Wilson | How do we handle incorrect register mapping? |  | Closed |  | Weekly decisions meeting | Where MHHS Design doesn't specify a process, the exisiting process will be used as a drafting principle. Principle: BSC will cover Data inconsistencies and REC will cover Metering inconsistencies |  |  |  |  | Complete
CDD-06 |  | Mark De Souza Wilson | Do we want a process for investigating inconsistencies in metered data and fault investigation? |  | Closed |  | Weekly decisions meeting | Design is not proposing to change the Fault process. Where MHHS Design doesn't specify a process, the existing process will be used as a drafting principle. Principle: BSC will cover Data inconsistencies and REC will cover Metering inconsistencies | Kevin Spencer Derek Weaving Mark deSouza Wilson Matt McKeon | 25/05/23 | Review consultation comments from BSCP701 before formally closing |  | Complete
CDD-07 |  | Mark De Souza Wilson | On notification of a problem with the data submitted to MDS, should the SDS process sit in this BSCP or in the MDS BSCP? |  | Closed |  | Internal Programme | MDS BSCP will publish the requirement for the interface with the error/rejection reason code. SDS BSCP will receive the published interface and act upon the reason code |  |  |  |  | Complete
CDD-08 |  | Mark De Souza Wilson | Should all the change of data service, change of service appointment details, change of market segment/connection type, processes sit within BSCP501 as SMRS will be the main actor in these processes? | Data Services | Closed |  | Weekly decisions meeting | initially, the first 4 steps of an appointment will go into BSCP700 and if required in BSCP501 it will be linked into BSCP700 | Kevin Spencer Derek Weaving Mark deSouza Wilson Matt McKeon |  | Review consultation comments |  | Complete
CDD-09 |  | Mark De Souza Wilson | Should all the change of data service, change of service appointment details, change of market segment/connection type, processes sit within BSCP501 as SMRS will be the main actor in these processes? | Data Services | Closed |  | Weekly decisions meeting | initially, the first 4 steps of an appointment will go into BSCP700 and if required in BSCP501 it will be linked into BSCP701 | Kevin Spencer Derek Weaving Mark deSouza Wilson Matt McKeon |  | Review consultation comments |  | Complete
CDD-10 |  | Mark De Souza Wilson | Where should change of energisation status and change of meter processes sit? These are metering processes and SDS only plays a small part. |  | Closed |  | Weekly decisions meeting | Changes are published through the DIP interfaces from REC for smart and advanced - process driven by REC | Kevin Spencer Derek Weaving Mark deSouza Wilson Matt McKeon |  | Review consultation comments |  | Complete
CDD-11 |  | Mark De Souza Wilson | Do we need to redefine what we mean by Complex Sites to decouple it from D0268 and clarify whether sites with Smart Metering should be in scope? |  | Closed |  | Internal Programme | There is a formal definition for Complex Sites, no changes will be made under MHHS |  |  |  |  | Complete
CDD-12 |  | Mark De Souza Wilson | We have requirements, for example to delete data when an appointment has been rejected. Should this form part of the appointments process or as part of the SDS general/overall requirements? |  | Closed | No | CDWG | Link with CDD16 Agreed at CDWG this doesn't need to be written into code because there are already legal requirements around ICO data retention/data proection legislation that parties must follow. | Mark DeSouza Wilson, Kevin Spencer, Seth Chapman | 2023-05-01 | Think it is closed - but need MD to confirm. PSL100 covers this - but there are other data rentetion requirements. |  | Complete
CDD-13 |  | Mark De Souza Wilson | How/where should we incorporate processes around related MPANs? Related to the appointment rules | Registrations | Closed | no | Weekly decisions meeting | Reg will reflect rules re related meter point. Where the code sits (stand alone or part of Reg rules is to be confirmed. BSCP 550 to be put into code during Mop-up | Matt McKeon | 2023-11-05 | Review in registrations drafting REC has included a clause around related metering points. BSC to review and confirm the approach with REC | Mop-up | Complete
CDD-14 | 16/1/23 | Sarah Jones | Currently the use of DTN messages is optional and bilateral arrangements can be agreed. Can we confirm that this is not the case with DIP messages and these are all mandatory within the business processes as set out in the design artefacts. | Metering | Closed | Yes | External | DIP messages are mandatory | Sarah Jones Matt McKeon | 2023-11-05 |  | Data/Meter Services | Complete
CDD-15 | 16/1/23 | Sarah Jones | The MO Schedule has a section on non communicating NHH meters – we have amended to reference use of the D0268. However there is a statement that the D0313 is also sent when a transient issue but not when it’s a permanent removal. How will this work now the D0313 is not being sent – will this need a change or market segment | Metering | Closed | No | Weekly decisions meeting | Remove from REC code drafting - clause 18, 4, 5 & 6 | Kevin Spencer Mark DeSouza Wilson Matt McKeon Derek Weaving Andrew Margan Andrew Wallace Sarah Jones |  | Validate with Design - how is this process expected to work? |  | Complete
CDD-16 | 16/1/23 | Sarah Jones | The DIP interface catalogue references primary / secondary / always recipients. How is this being documented in the BSC - will it be in the schedules or in the data spec |  | Closed |  | Internal Programme | BSC won't introduce primary and secondary particpants in the drafting. It will be included in the data specification | Kevin Spencer Mark DeSouza Wilson Matt McKeon Derek Weaving Andrew Margan Andrew Wallace Sarah Jones | 2023-01-17 |  |  | Complete
CDD-17 | 23/1/23 | Sarah Jones | To discuss the approach to documenting customer direct appointments. There has been some debate about whether anyone can notify a customer direct appointment or just the appointed agent | Metering | Closed |  | DAG | Programme confirmed only incumbent can set the flag | DAG | 2023-02-01 | Matt to clarify the outcome within the workoff items with Design - wait until after DAG for clarity |  | Complete
CDD-18 | 23/1/24 | Sarah Jones | To discuss the approach to documenting customer direct appointments. There has been some debate about whether anyone can notify a customer direct appointment or just the appointed agent | Metering | Closed |  | DAG | Programme confirmed only incumbent can set the flag | DAG | 2023-03-03 | Matt to clarify the outcome within the workoff items with Design - wait until after DAG for clarity |  | Complete
CDD-19 | 26/1/23 | Kevin Spencer | How does the UMSO inform the LDSO updates to the MPL address | N/A | Closed | No | Weekly decisions meeting | Not specifying the process/mechanism by which the UMSO interfaces with the LDSO | Kevin Spencer Mark DeSouza Wilson Matt McKeon Derek Weaving Andrew Margan Andrew Wallace Sarah Jones | 26/1/23 | Linked with CDD-22 |  | Complete
CDD-20 | 2023-01-27 | Sarah Jones | Are we still using the term HH Metered Data or should we used Settlement period Metered Data? | N/A | Closed | No | Weekly decisions meeting | Not using Settlement period metered data. REC continuing to use HH Metered Data | Kevin Spencer Mark DeSouza Wilson Derek Weaving Andrew Margan Andrew Wallace Sarah Jones |  |  |  | Complete
CDD-21 | 23/3/2023 | Sarah Jones | Definition of Cumulative Meter Reads - we have a couple of consultation comments querying this and it doesn't appear to be in the programme glossary. Please could we agree the definition and whether it should be referred to as Total Cumulative Reads | Metering | Closed | No | Internal | Definition Cumulative Register Reading - Meter register reading taken from the Total Cumulative Register of a Smart Meter | "Sarah Jones Matt McKeon" | 2023-05-11 |  |  | Complete
CDD-22 | 23/3/2023 | Sarah Jones | Definition of Complex Sites - the REC definition currently points to the BSC but this is not included in section X. Should this be added to section X or should it be defined in the REC going forward given the metering requirements are now governed there | Metering | Closed | No | Internal | Definition provided by Mark to Sarah Jones | Mark DeSouza Wilson Sarah Jones | 2023-06-15 | To agree a definition between both BSC and REC. MMc to confirm definition | interfaces | Complete
CDD-23 | 2023-02-05 | Andrew Margan | The BSC and Design doesn't cover the Supplier CoS Transfer process in sufficient detail. The design covers the exchange of CoS reads but does not specify the SLAs or timings. We are unsure whether to assume that timings from BSCP504 still apply. There is a second issue where we don't have a destination document (BSCP) identified to hold the obligations on Suppliers. Data Service BSCPs do not contain Supplier to Supplier steps. This may require a Design CR or agreeing SLAs through the code process. A potential solution is to code the process/SLAs and agree later which Code Artefact to include it in. | Metering | Closed | No | CDWG | Delivered as part of Tranche 3 | Andrew Wallace, Matt McKeon, Paul Saker | 2023-11-05 | Paul Saker has raised the DIN items for the Operational Choreography is updated with the correct SLAs, which can then be codified. Design pointed to Design which provides information - need to investigate if this is complete to draft code - eg which meter registers to use maybe unclear | Tranche 3 | Complete
CDD-24 | 2023-02-05 | Andrew Margan | The Code drafting for the Smart Meter Data Retriever (SMDR) role and MDR obligations needs to defined to ensure drafting separates Service and Party providing the Service. | Metering | Closed | No | CDWG | Not to make any reference to MDR specific obligations in the BSC. Omit any specific MDR exchanges. | Matt McKeon Mark DeSouza Wilson | 20/04/23 |  | Mop-up | Complete
CDD-25 | 2023-09-05 | Andrew Margan | The Long Term Vacancy process for Suppliers is not explicit in the Design and the Supplier SLAs can't be created by the Code drafters - may need Elexon input - therefore how will these obligations be drafted into code? When can the Supplier instruct a data service to estimate zero consumption | Metering | Closed | Yes | CDWG | Text drafted and consulted - T4 Consultation | Derek Weaving Matt McKeon | 13/07/2023 | Meeting with Colin Berry Elexon had on 17/05. Articulate the problem to performance assurance PAWG. David Morley has now raised this into the DIN process as it is a Design gap. Approach to be presented to CDWG on 08/08/23 | Tranche 4 | Complete
CDD-26 | 25/05/2023 | Mark De Souza Wilson | Service vs service provider termonology and when to use which term and being consistent across all artefacts. Need to be consistent across artefacts | Registrations | Closed | No | Weekly decisions meeting | Agreed to use Data Service or Data Service Agent as applicable. 13/07/23 - Obligations should sit on the Agents and that is outside the BSCPs and the BSCPs can be purely focused on the processes carried out by the Services. | Matt McKeon Sarah Jones Mark DeSouza Wilson | 15/06/23 | legal advise to call them Service Provider Section J states provider! Others eg Section J is Supplier Agents 05/07/23 - MM to email Nick following meeting with Tom Chevalier | Mop-up | Complete
CDD-27 | 2023-08-06 | Mark De Souza Wilson | HHDC VS ADS - The terms were both considered - decision is that HHDC used in code drafting only | Registrations | Closed | No | Weekly decisions meeting |  | Mark Kevin | 2023-08-06 | Not related to consequential code change | BSC Central Services | Complete
CDD-28 | 29/06/2023 | Matt McKeon | Progression and approval of ECS Reports delivered over the DTN | Interfaces | Closed | No | DAG | 13/07/23 - Due to timeframe required agreed to progress through Programme Governance and DAG approval. | Matt McKeon Derek Weaving | 13/07/23 | 13/07/23 - Need to speak to programme (Fraser) about how best to progress via DAG | Interfaces | Complete
CDD-29 | 29/06/2023 | Andrew Margan | Following approval of CR018 we are expecting updated Operational Choreography artefact that will need to be reflected in Code | Data Services Metering Registration | Closed | Yes | Internal Programme | CR18 text being drafted as part of Mop-Up 1 | Matt McKeom Sarah Jones | 13/07/23 | Agreed to let due process run and see what DAG output is. | Interfaces (BSCP706) Mop-Up (All other relevant BCSPs) | Complete
CDD-30 | 27/07/23 | Kevin Spencer | Use of IF-013 - Design only say send with RF run, Drafting currently says sending with every settlement run | Interfaces | Closed | Yes | TBC | Design changed - DES 138 correct | Design | N/a | Design have approached Nigel at Helix for a view on the way they are intepreting the design. 03/08/23 - Elexon have responded it is going with every run, but suggestion is, as a minimun, it should not go with the II Run. Discussions ongoing. | IR7 | Complete
CDD-31 | 27/07/23 | Matt McKeon | Import/Export Linkage - Disconnection Issue. Are there requirements for LDSO around management that need to input into a BSCP? | Registration | Closed | No | N/A | Under the Licence review - the action is placed on Ofegm to deleiver solution | Programme | 2024-04-24 | CW to send licence review letter to Ofgem |  | Complete
CDD-32 | 2023-03-08 | Kevin Spencer | What is the process for updating ISD following DIP onboarding? (Entities 1, 16 and 45) | Governance | Closed | TBC | TBC | Part of DIP Gov - Parties will get updated on the back of PAB Qual | n/a |  | Out of Programme scope |  | Complete
CDD-33 | 2023-03-08 | Kevin Spencer | How do we ensure Metering Services are updated in Entity M8 when a new meter type is required? | Governance | Closed | N/A | Elexon | Add to Apendix 2 - Where Metering Service is qualified add to M8. Elexon need to own the BAU change process, when a new meter type is raised and updates ISD. | Kevin Spencer Mark DeSouza Wilson | 2023-03-08 | AM engaged with Chris Day, Lawrence to confirm Elexon need to own the process | Governance - TBC | Complete
CDD-34 | 14/09/2023 | Andrew Margan | How will old Code be terminated? | N/A | Closed | N/A | Elexon | Old text eg BSCP 500 series will be removed after M16 by house keeping change | Chirs Day, Colin Berry, Kevein Spencer, Mark DeSouza | 14/06/2023 |  |  | Complete
CDD-35 | 25/09/2023 | Andrew Margan | Perminent home for the Change Of Supplier (Cos) Transfer Read text | Mop-up 2 | Closed | N/A | CDWG/CCAG | Part of Tranche 4 | CDWG | 2024-10-10 | Approved | Tranche 4 | Complete
CDD-36 | 25/09/2024 | Andrew Margan | Perminent home for the Long Term Vacant (LTV) text | Mup-up 2 | Closed |  | CDWG/CCAG | Part of Tranche 5 | CDWG | 2024-10-11 | Approved | Tranche 4 | Complete
CDD-37
CDD-38
CDD-39
CDD-40
Code Decision and Issues Log
Code Decision and Issues Log

## Sheet2
Principles
BSC will cover Data inconsistencies and REC will cover Metering inconsistencies
Not knowingly duplicate processes between codes or documents

## Sheet1 (hidden)
Open
Closed
Internal
External