## Change Control Log
*Change Control Reference | *Topic Area | *Code Body | *Artefact Reference Number (DELxxx) | *Artefact Name | *Artefact version number post change | *Category (Major, Minor, Cosmetic) | *Document Section where the change is applied | *Description of the actual change applied | *Reason for the change | Associated DIN / CR | *Owner | *Status | *Change applied date | Comments
CCR-0001 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration | MHHS 0.4 | Minor | 22.9.10 (MO Schedule) 2.7.10 (Migration Schedule) | From column should be Gaining Supplier rather than Electricity Supplier | Error in original text, amending for consistency |  | Sarah Jones | Closed | 2023-12-18
CCR-0002 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration | MHHS 0.4 | Minor | Section 24 (MO Schedule) Section 4 (Migration Schedule) | Numbering in the table to be corrected and additional step added to cover receipt of the IF036 relating to the data service appointment. | Alignment to BP003 |  | Sarah Jones | Closed | 2023-12-18
CCR-0003 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration | MHHS 0.4 | Cosmetic | Various | Add the words 'unless otherwise stated' to the sentence ahead of the interface tables. | To improve clarity in the document. |  | Sarah Jones | Closed | 2023-12-18
CCR-0004 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration | MHHS 0.4 | Minor | Various | Amend references to sending MTDs for all Related Metering Points to say 'send MTDs for the Metering Point and Secondary Related Metering Points | To improve clarity in the document. |  | Sarah Jones | Closed | 2023-12-18
CCR-0005 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule | MHHS 0.4 | Minor | Section 26 | Update section for clarity | DIN 86 was seeking clarity on the change of market segment process. This has resulted in proposed changes to the relevant section of the schedule. | DIN86 | Sarah Jones | Closed | 2023-12-18
CCR-0006 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule | MHHS 0.4 | Minor | Various | Update cross references to the BSC to include the specific BSCP | To address consultation responses received in the registration tranche and ensure consistent approach across all REC schedules. |  | Sarah Jones | Closed | 2023-12-19
CCR-0007 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule | MHHS 0.4 | Minor | Section 2 | Add requirement for MEMs to retain data for 24 months to support trading disputes | To reflect requirements in section 6 of the operational choreography |  | Sarah Jones | Closed | 2023-12-19
CCR-0008 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule | MHHS 0.4 | Minor | Section 22 | Add statement that de-appointment is based on receipt of the IF037 and not the earlier IF035 (which is just issued for traditional and advanced metering assets to trigger the losing MEM to send the MTDs) | DIN 88 raised to understand why the Losing MEM would not receive notiifcation of lapsed appointments. Confirmation from the programme that notifications of lapsed appointments will not be sent to the Losing MEM and they should assume they are appointed until they receive the IF037 | DIN88 | Sarah Jones | Closed | 2023-12-19
CCR-0009 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule | MHHS 0.4 | Minor | Section 23.5 | Add information on auto appointment / de-appointment for a subsidiary metering point where a new metering point is created and a related MP relationship or import / export association put in place then the MEM | DIN 90 raised to understand the approach for the initial appointment of agents for export metering points. Confirmation from the programme that where a relationship is in place the registration service will carry out a daily review of appointments and auto appoint the relevant agent to the export / secondary metering point | DIN90 | Sarah Jones | Closed | 2023-12-19
CCR-0010 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 2.19 | Placeholder - to confirm whether data is deleted or obfuscated | N/A | DIN89 | Sarah Jones | Closed | 2023-12-19 | DIN closed with a statement that it is for each participant to determine its position with regards to GDPR. Statement to obfuscate or delete remains
CCR-0011 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 21.5.2 | Clarify the approach for changing energisation at the same time as metering asset removal / installation | DIN87 raised to understand the interaction between meter installation / removal processes and change of energisation | DIN87 | Sarah Jones | Closed | 2023-12-19
CCR-0012 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | 15.6.5 | Placeholder - to confirm the cross reference to section L of the BSC | N/A |  | Sarah Jones | Closed | 2023-12-19 | Confirmed no change to the section numbering so no change required to the cross reference.
CCR-0013 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | Various | Remove reference to 21:00hr SLA for confirming MEM appointment and replace with reference to BSCP706 | Avoid dual governance issues |  | Sarah Jones | Closed | 2023-12-19
CCR-0014 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 22.9 and 22.11 | Add DNO, Losing Supplier and EES as recipients of the IF037 de-appointment | Alignment to BP002 |  | Sarah Jones | Closed | 2023-12-19
CCR-0015 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 21.5 | Add DNO and Supplier as recipient of the IF041 and D0010 following change of energisation status | Alignment to BP008 |  | Sarah Jones | Closed | 2023-12-19
CCR-0016 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | Section 22 and 23 (MO Schedule) Section 2 (Migration Schedule) | Reflect 90% sending replacement IF031 following rejection and 90% responding to appointment request by MEM | Design change | DIN202 IR2 | Sarah Jones | Closed | 2023-12-19
CCR-0017 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | Section 22 (MO Schedule) Section 2.7 (Migration Schedule) | Reflect 60 min SLA for IF035 to be sent following CSS cancellation. Note that this was updated in a later release to clarify the IF035 is only sent after the IF034 has been received | Design change | DIN369 IR2 DIN605 IR5 | Sarah Jones | Closed | 2023-12-19
CCR-0018 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 22.9.27 and 22.11.27 | Add DNO as recipient of the MTDs following change of MEM | Design change | IR2 | Sarah Jones | Closed | 2023-12-19
CCR-0019 | Metering | RECCo |  | EES Service Definition |  | Minor | 9.6 | Transitional volumetrics to be applied during the migration period to be added once defined | Design gap recognised prior to CCAG initial approval |  | Sarah Jones | Closed | 2023-05-12
CCR-0020 | Data Services | BSC | DEL1042 | BSCP702 (and any artefacts that the same errors are identified in) |  | Cosmetic | Header and 3.5.1/3.5.2 | Errors in version number and table column headings resulting from exporting to PDF - original Word versions are correct | To ensure accuracy of artefact | N/A | Simon Chidwick | Closed | 2023-01-11
CCR-0021 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 22.9.26 / 22.11.26 | Amend the 'when' to say following receipt of the notifications in 22.9.14 / 22.9.16 and 22.9.18 / 22.9.25. Same change to 22.11 | To reflect the steps applicable to retrospective appointments | N/A | Sarah Jones | Closed | 2023-12-19
CCR-0022 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | Section 22 (MO Schedule) Section 2 (Migration Schedule) | Change 'if data is accepted' to 'if Appointment is accepted' | Clarity | N/A | Sarah Jones | Closed | 2023-12-19
CCR-0023 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 24.1 | Remove reference to Gaining MEM - should just be MEM | Clarity | N/A | Sarah Jones | Closed | 2023-12-19
CCR-0024 | Data Services | BSC | DEL978 | Unmetered Supplies Operations |  | Minor | 3.2.2 3.2.3 3.2.5 3.6.2 3.9.2 3.9.3 3.9.4 3.9.5 3.9.6 3.12 | Missing section. Renumbering required References 3.1.19 and 3.1.10 invalid – amend to 3.2.4 or 3.2.5 Reference 3.1.7 invalid – amend to 3.2.1 Reference 3.8.3 invalid – amend to 3.6.3 Reference 3.7.1 invalid – amend to 3.9.1 Reference 3.7.2 invalid – amend to 3.9.2 Missing section. Renumbering required Reference 3.7.3 invalid – amend to 3.9.3 Reference 3.7.5 invalid – amend to 3.9.5 Reference 3.6 incorrect – amend to 3.8 | To ensure accuracy of artefact | N/A | Kevin Spencer | Closed | 20/10/2023
CCR-0025 | Other | BSC | DEL1526 DEL1728 | CoS Transfer of Reads Long Term Vacant |  | Minor | N/A | Find permanent home for these documents within the BSC - either within other BSCPs or with the creation of a Supplier BSCP. | To ensure permenant home for what are currently standalone documents | N/A | Code Team | Open |  | Supplier Requirements (BSCP709)
CCR-0026 | Other | BSC |  | Section V or Annex X-2 |  | Minor |  | Amendments may be required regarding measurement class | Clarity | CR-032 | Code Team | Open
CCR-0027 | Governance | BSC | DEL1530 | BSCP65 - Registration of Parties and Exit Procedures |  | Minor | 1.5.3 | Update route map to reflect new 700 BSCPs | Clarity/Accuracy | N/A | Derek Weaving | Open
CCR-0028 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 20.1.5, 25.1.3 | Addition of Supplier as recipient of IF006 rejection | Design change | DIN 094, IR3 | Sarah Jones | Closed | 2023-12-19
CCR-0029 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | Various | Review schedule for used of capitalised de-appointment. This is not a defined term | Definition review based on Schedule 1 update |  | Sarah Jones | Closed | 2023-12-19
CCR-0030 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 2.1 | Make Metering Related Services lower case | Definition review based on Schedule 1 update |  | Sarah Jones | Closed | 2023-12-19
CCR-0031 | Various | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | General | Update references from Data Service and amend to Data Service Agent where necessary | Alignment with BSC drafting and Schedule 1 |  | Sarah Jones | Closed | 2023-12-19
CCR-0032 | Various | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | General | Update referenced from Cumulative Meter Reading and amend to Cumulative Register Reading | Consistency check |  | Sarah Jones | Closed | 2023-12-19
CCR-0033 | Various | RECCo |  | Schedule 14 Metering Operations Schedule Related Metering Point Schedule |  | Minor | General | Update references from DIP Interface to DIP Market Message | Definition review based on Schedule 1 update |  | Sarah Jones | Closed | 2023-12-19
CCR-0034 | Registration | RECCo |  | RMP Lifecycle Schedule |  | Minor | Section 5 | Amend drafting to reflect that SMDRs are not Supplier Agents | Definition review based on Schedule 1 update |  | Sarah Jones | Closed | 2023-05-12
CCR-0035 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Related Metering Point Schedule |  | Minor | Section 23.5 (MO Schedule) 2.4.5 and 3.3.5 (Related Metering Point Schedule) | Add steps for losing MEM to send MTDs where de-appointed following an auto alignment due to new import / export or related metering point linkage | Design change | DIN560 IR4 | Sarah Jones | Closed | 2023-12-19
CCR-0036 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | Section 20 | Add reference to IF004 being sent if comms hub info is updated as a result of meter works. Note this is optional | Design change | DIN335 IR4 | Sarah Jones | Closed | 2023-12-20
CCR-0037 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | Section 23.2 - 23.4 | Update Customer Direct Contract process to reflect new BP in BP010 | Design change | DIN554 IR5 | Sarah Jones | Closed | 2023-12-20
CCR-0038 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | Section 22 | Add DNO as recipient of the MTDs following appointment | Design change | DIN630 IR5 | Sarah Jones | Closed | 2023-12-19
CCR-0039 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration |  | Minor | N/A - text reviewed but change not required in the REC | Clarify that IF001 is sent to both the import and export suppliers | Design change | DIN339 IR5 | Sarah Jones | Closed | 2023-12-19 | No change required as the sending of the IF001 is not included in Schedule 14 - this is covered in BSCP706
CCR-0040 | Data Services | BSC | DEL978 | Unmetered Supplies Operations |  | Minor | Section 2.3.2.1 – Send notification of a customer direct contract | unclear what this refers to – the MA/UMDS would have direct contracts to operate outside of a standard UMSDS function | Clarity |  | Kevin Spencer | Closed |  | This is in the design there is the following footnote in Section 3:This is unlikely to be used by UMSOs, given they are a role contracted by the LDSO.
CCR-0041 | Data Services | BSC | DEL978 | Unmetered Supplies Operations |  | Minor | Section 3.4 – Change of UMSDS | No timeframe on change of UMSDS, BSCP520 has a 10WD window for a change of NHH Data Collector for which the UMSDS will be | Clarity |  | Kevin Spencer | Closed |  | Added 10 WD
CCR-0042 | Data Services | BSC | DEL978 | Unmetered Supplies Operations |  | Minor | Section 3.6.3 | "within 2 hrs of accepting and processing an update from the customer send a D0388 to the UMSDS "– clarity required as to why a timeframe has been specified to send the D0388 once an update has been processed | Clarity |  | Kevin Spencer | Closed |  | There is a new section on Service Availability which reflects the these timescale only appy during standard Working Days.
CCR-0043 | Data Services | BSC | DEL978 | Unmetered Supplies Operations |  | Minor | 3.11.2 CMS Fault reporting | Comments have been passed back previously as CMS is a customer operator system for which the UMSO has no dealings, only the Customer and their appointed MA/UMSDS have access to the CMS files and they have the relationship not the UMSO | Accuracy |  | Kevin Spencer | Closed |  | The UMSO may need to submit a revised D0388 which is why they are in this step
CCR-0044 | Data Services | BSC | DEL978 | Unmetered Supplies Operations |  | Minor | 3.6.4 – | Validate Inventory against OID and ISD and respond to 95% of inventory items by end of the next working day”. Concern raised around the removal of the “5 WDs” which was in the Draft v0.2. Even though it is indicating 95% will be returned by the end of the next working day, 5 WDs should remain as currently it is open ended which makes 4.7.1 impossible as it will never actually know when a D0389 should be received by. | Clarity/Accuracy |  | Kevin Spencer | Closed |  | added:Responses on all inventory item shall be completed by 5 WD.
CCR-0045 | Governance | RECCo |  | Data Access Matrix |  | Minor |  | Remove data item Associated Import / Export Supplier Id as the EES design does not reflect this as a distinct data item. It is simply the Supplier Id applied against the associated MPAN | Alignment with EES design |  | Sarah Jones | Closed | 2024-01-02 | No change required as the DAM has been amended to a Cat 3 doc and will be updated outside the SCR modification
CCR-0046 | Governance | RECCo |  | Data Access Matrix |  | Minor |  | Add MDR MPID alongside MDR DIP Id | Alignment with EES design |  | Sarah Jones | Closed | 2024-01-02 | No change required as the DAM has been amended to a Cat 3 doc and will be updated outside the SCR modification
CCR-0047 | Governance | RECCo |  | Data Access Matrix |  | Minor |  | Amend references to MOA to be Metering Service which covers MOA and UMSO | Alignment with EES design |  | Sarah Jones | Closed | 2024-01-02 | No change required as the DAM has been amended to a Cat 3 doc and will be updated outside the SCR modification
CCR-0048 | Governance | RECCo |  | Migration Schedule |  | Minor | 2.1 | Amend reference to Migration Plan as this term is used to define the overall Migraton Plan agreed by the programme rather than the individual Supplier agreed plans | Alignment with REC CP R0093 drafting |  | Sarah Jones | Closed | 2023-12-19
CCR-0049 | Interface | RECCo |  | Message Catalogue |  | Minor |  | BSC recorded as default owners for all DIP flows. Consider if some (e.g. linked to Metering) should be REC owned. |  |  | Andrew Wallace | Open |  | Outside MHHS design - to be discussed via the Issue 101 DIP Governance consultation
CCR-0050 | General | RECCo |  | Schedule 14 Metering Operations Schedule Schedule X Migration Related Metering Point Schedule |  | Minor | General | Review for use of Data Service and amend to Smart / Advanced to avoid scope extending to UMSDS. |  |  | Sarah Jones | Closed | 2023-12-19
CCR-0051 | Registration | RECCo |  | ERDS Service Definition |  | Minor | 7.3A and B | New paragraphs added to reflect timescale for sending appointment data to CSS as set out in the operational choreography |  | CR018 | Sarah Jones | Closed | 2023-12-05
CCR-0052 | General | RECCo |  | General |  | Minor | General | Review for use of Non-MHHS Migrated Metering Points and amend to Non-MHHS Metering Points |  |  | Sarah Jones | Closed | 2023-12-19
CCR-0053 | Data Services | BSC | DEL1042 | BSCP702 |  | Minor | 3.2.3 Notification to ADS following a Change of SVA MOA: | Correction of IF reference from IF-035 to IF-036 | Alignment with Design | N/A | Matt McKeon | Closed | 2023-01-11
CCR-0054 | Data Services | BSC | DEL1042 | BSCP702 |  | Minor | 2.6 Requirements for Processing UTC Period Consumption Data | Correct data item reference to Meter Reading Status (J0045) | Aligned with DTN change documentation | N/A | Matt McKeon | Closed | 2023-01-11
CCR-0055 | Data Services | BSC | DEL1042 | BSCP702 |  | Minor | Section 3 | Removed references to redundant flows (D0022 and D0036) | Alignment with Design | N/A | Matt McKeon | Closed | 2023-01-11
CCR-0056 | Data Services | BSC | DEL1042 | BSCP702 |  | Minor | Appendix 4 | Consolidated text on Meter Advance Reconcilations | Aligning METH002 with existing BSCP502 | N/A | Matt McKeon | Closed | 2023-01-11
CCR-0057 | General | RECCo |  | General |  | Minor |  | Review for interface names to reflect CR025 |  | CR - 025 | Sarah Jones | Closed | 2023-12-20
CCR-0058 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | 2.7 | Revert to legacy drafting and remove reference to the requirement in the BSC to set up an import / export association | The BSC is not requiring Import and Export Metering Points that share a meter to become associated. Therefore the requirement to have the same MEM has been de-linked from the Import / Export Association provisions |  | Sarah Jones | Closed | 19/12/23
CCR-0059 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | Section 22.9.14, 22.9.16, 22.9.27, 22.11.14, 22.11.16, 22.11.27 | Added clarity that MTD steps via the DTN are only applicable to Advanced and Traditional Metering Assets | Clarity |  | Sarah Jones | Closed | 19/12/23
CCR-0060 | Governance | RECCo |  | Schedule 1 Interpretations and Definitions |  | Minor | General | Add a definition for Customer Direct Contract | Missing definition |  | Sarah Jones | Closed | 2023-12-20
CCR-0061 | Metering | RECCo |  | Schedule 14 Metering Operations Schedule |  | Minor | Section 20 | Removal of D0383 and D0384 being issued to the ADS - only sent to supplier and DNO. | Alignment with Design | DIN682, IR6 | Sarah Jones | Closed | 2023-12-20
CCR-0062 | Governance | RECCo |  | Schedule 1 Interpretations and Definitions |  | Minor | General | Add a statment to the definition of Meter Configuration Table to clarify that it is part of the Data Specification | Clarity |  | Sarah Jones | Closed | 2023-12-20
CCR-0063 | Governance | RECCo |  | Schedule 1 Interpretations and Definitions |  | Minor | General | Remove definition of Migration Plan as this is not being used in the REC MHHS drafting | Definition not required |  | Sarah Jones | Closed | 2024-09-01
CCR-0064 | Governance | RECCo |  | Schedule 1 Interpretations and Definitions |  | Minor | General | Removal of reference to the MHHS Transition Schedule based on CDWG agreed position that transition provisions will be included within the wider schedules rather than a standalone artefact. | Definition not required |  | Sarah Jones | Closed | 2024-09-01
CCR-0065 | Various | RECCo |  | Various |  | Major | Various | Inclusion of transitional text (re-inserting legacy provisions applicable to Non MHHS Metering Points) based on CDWG agreed position that transition provisions will be included within the wider schedules rather than a standalone artefact. | CDWG decision on REC transition drafting approach |  | Sarah Jones | Closed | 2024-09-01
CCR-0066 | Registration | RECCo |  | Schedule 24 Switching Data Management Schedule |  | Minor | 4.8.7 | Addition of a statement that where a new Market Participant is a MEM, the Code Manger will convert the Market Role Code for Smart Metering Equipment Managers (S) and / or Advanced Metering Equipment Managers (T) and provide this to CSS as the legacy Meter Operator value (M). | New code manager requirement based on final position regarding market role codes |  | Sarah Jones | Closed | 15/1/24
CCR-0067 | Registration | RECCo |  | RMP Lifecycle Schedule |  | Minor | 4.1.8 | Note to reflect the new Registration Service requirement to issue a notification to the Supplier and EES if the Metering Point is re-connected | Design change | IR7 | Sarah Jones | Closed | 2024-01-02
CCR-0068 | Interfaces | RECCo |  | Standards Definition Document |  | Minor | 2.6 | Added reference to MHHS Data Types being defined in Swagger Hub | Query raised through Tranche 4 - response provided against DIN851 | DIN851 | Sarah Jones | Closed | 2024-02-09
CCR-0069 | Interfaces | RECCo |  | Standards Definition Document |  | Minor | 2.14 | Removed market data service column. | To avoid confusion - addressing comment raised against the ECS report consultation |  | Sarah Jones | Closed | 2024-02-09
CCR-0070 | Interfaces | RECCo |  | Standards Definition Document |  | Minor | 2.14 | Addition of MDR to the list of market participants | Design change | CR023, IR7 | Sarah Jones | Closed | 2024-02-09
CCR-0071 | Interfaces | RECCo |  | Standards Definition Document |  | Minor | 2.14 | Addition of Incoming Supplier to the list of market participants | Missing market participant |  | Sarah Jones | Closed | 2024-02-09
CCR-0072
CCR-0073
CCR-0074
CCR-0075
CCR-0076
CCR-0077
CCR-0078
CCR-0079
CCR-0080
CCR-0081
CCR-0082
CCR-0083
CCR-0084
CCR-0085
CCR-0086
CCR-0087
CCR-0088
CCR-0089
CCR-0090
CCR-0091
CCR-0092
CCR-0093
CCR-0094
CCR-0095
CCR-0096
CCR-0097
CCR-0098
CCR-0099
CCR-0100
MHHS Code Workstream - Change Control Log

## Chg Ctrl Log Post-Mop Ups
[11 empty] | Materiality Key | Definition of Material Change = Change that will have an impact on Participants, Systems and/or Processes
M = Material change
N = Non-Material Change
*Change Control Reference | *Topic Area | *Code Body | *Artefact Reference Number (DELxxx) | *Artefact Name | *Artefact version number post change | *Category (Major, Minor, Cosmetic) | *Document Section where the change is applied | *Description of the actual change applied | *Reason for the change | Associated DIN / CR | Materiality | *Owner | *Status | *Reviewed by | *Change applied date | Comments
MHHS Code Workstream - Change Control Log Post-Mop Ups

## Interim Release Tracker
Lookup Reference | BSC Code Artefact | Lead Author | Published Version | Topic Area | Tranche | IR1 | IR2 | IR3 | IR4 | IR5 | IR6 | IR7
BSCP128 | BSCP128 - Production, Submission, Audit and Approval of Line Loss Factors | Derek Weaving | v11.3 | Governance | 3
BSCP38 | BSCP38 - Authorisations | Derek Weaving | v25.1 | Governance | 3
BSCP601 | BSCP601 - Metering Protocol Approved and Compliance Testing | Derek Weaving | v23.5 | Metering Services | 1
BSCP65 | BSCP65 - Registration of Parties and Exit Procedures | Derek Weaving | v22.3 | Governance | 3
BSCP68 | BSCP68 - Transfer of Registration of Metering Systems between CMRS and SMRS | Derek Weaving | v18.4 | Registration Service | 2
BSCP700 | BSCP700 - Unmetered Supplies Data Services | Kevin Spencer | v0.7 | Data Services | 1 | No changes for UMSDS | Minor changes for unused data item | Minor changes relating to processing the IF-014 | New table for SPQI and Estimation Reason Codes. | Minor changes for UMSDS | Minor change for UMSDS | Minor changes for UMSDS
BSCP701 | BSCP701 - Data Retrieval and Processing for Smart Segment Metering Systems Registered in SMRS | Mark DeSouza-Wilson | v0.5 | Data Services | 1 | No Change | Added message to inform MOA of prospecttive SDS appt (Advanced, Trad). Minor update to Change of SDS process. Updated tables on P42-43 | off peak declaration from supplier. E7/E10 for smart meters | Minor update re. LDSO 60-minute response tiime | IF-36 to import & export suppliers, Customer Direct update every 3 years | No changes | De-appointment timing and splitting of reads
BSCP702 | BSCP702 - Advanced Data Service | Matthew McKeon | v0.7 | Data Services | 1 | No changes | Method Statement Change | No changes | Method Statement Change | No changes | No changes | Method Statement Change and IF/PUB names (CR-025)
BSCP703 | BSCP703 - BSC Central Services for Market-wide Metering Systems | Kevin Spencer | v0.8 | BSC Central Services | 2 | No changes for SVAA | Minor changes for data flow and trading Disputes. | No changes for SVAA | Minor changes | Minor changes | No changes for BSCP703 | Change to name and updated flow names#
BSCP703 | BSC Central Services - Service Description | Kevin Spencer | v0.8 | BSC Central Services | 2 | No changes | No changes | No Changes | No changes | No changes | No changes | Numbering and requirement when data is missing
BSCP704 | BSCP704 - Unmeterd Supplies Operations | Kevin Spencer | v0.8 | Metering Services | 1 | No changes for UMS | Minor Update [DIN 93] | No changes for UMS | Minor update to reflect CR18 response times | Minor changes | No changes for UMSOs | Numbering changes
BSCP705 | BSCP705 - Supplier Metering Registration Service for MHHS Metering Systems | Mark DeSouza-Wilson | v0.4 | Registration Service | 2 | added disconnection notification to EES | Minor change for registration deactivation notification | LDSO update connection type update in SMRS 2WD->3WD | Minor update re. LDSO 60-minute response tiime | IF-43 to LDSO | No changes
BSCP706 | BSCP706 - Supplier Meter Registration Service for MHHS Metering Systems | Matthew McKeon | v0.8 | Registration Service / Interfaces | 2 4 | Captured in T2 | Captured in T2 | Captured in T4 | Captured in T4 | No changes | No changes | Restrospectivity rules and IF/PUB names (CR-025)
BSCP707 | BSCP707 - ISD | Kevin Spencer | v0.8 | Governance | 3 | No changes | Minor Changes | Serveral changes | Minor change | Minor changes | Minor changes | New tables added
BSCP707 | BSCP707 - Appendix 1 - ISD Change Request Form | Kevin Spencer | v0.8 | Governance | 3 | No changes | Minor Changes | Serveral changes | Several changes plus New Table for consent granularity. | Multiple changes including new entities | No changes | New tables and data item changes
BSCP707 | BSCP707 - Appendix 2 - ISD Change Request Entity Validation | Kevin Spencer | v0.8 | Governance | 3 | No changes | Minor Changes | Several Changes | Several Changes plus New Table for consent granularity. | Multiple changes including new entities | Several Minor changes | New tables and data item changes
BSCP708 | BSCP708 - Migration | Mark DeSouza-Wilson | v0.3 | Migration | 3 | BPM002 and BPM003 not in IR1 final documents | Incoming MOA needs to send MTDs to LDSO | No changes | Minor update re. LDSO 60-minute response tiime | No changes | No changes | Minor changes for appointments and import/export MSIDs
BSCP709 | BSCP709 - Supplier Requirements for MHHS | Matthew McKeon | v0.1 | Other | 4 | Captured in v0.1 | Captured in v0.1 | Captured in v0.1 | Captured in v0.1 | Captured in v0.1 | New document | Added requirement to receive notification of MSID reconnection
BSCPX | BSCP - CoS Transfer of Reads | Mark DeSouza-Wilson | v0.3 | Other | 3 | No changes | No changes | No changes | No changes | No changes | No changes | Superseded by BSCP709
BSCPY | Long Term Vacant | Derek Weaving | v0.3 | Other | 4 | IR7: Superseded by BSCP709
COP1 | BSC Code of Practice 1 - Metering of Circuits with a rated capactity exceeding 100MVA for Settlement Purposes | Derek Weaving | v15.5 | Metering Services | 1
COP10 | BSC Code of Practice 10 - Metering of Energy via Low Voltage Circuits for Settlement Purposes | Derek Weaving | v14.4 | Metering Services | 1
COP2 | BSC Code of Practice 2 - Metering of Circuits with a rated capacity not exceeding 100MVA for Settlement Purposes | Derek Weaving | v17.5 | Metering Services | 1
COP3 | BSC Code of Practice 3 - Metering of Circuites with a rated capactity not exceeding 100MVA for Settlement Purposes | Derek Weaving | v17.5 | Metering Services | 1
COP4 | BSC Code of Practice 4 - Calibration, Testing and Commissioning Requirements of Metering Equipment for Settlement Purposes | Derek Weaving | v16.5 | Metering Services | 1
COP5 | BSC Code of Practice 5 - Metering of Energy Transfers with a Maximum Demand of up to (and including) 1MW for Settlment Purposes | Derek Weaving | v18.4 | Metering Services | 1
COP6 | BSC Code of Practice 6 - Metering of Energy Imports via Low Voltage Circuits Fused at 100 Amps or Less per Phase for Settlement Purposes | Derek Weaving | v9.5 | Metering Services | 1
COP7 | BSC Code of Practice 7 - Metering of Energy Imports via Low Voltage Circuits Fused at 100 Amps or Less per Phase for Settlement Purposes | Derek Weaving | v7.5 | Metering Services | 1
P-Flows | MHHS P-Flows Part 1 - Interfaces | Derek Weaving | v0.3 | Interfaces/Data Specifications | 4
P-Flows | MHHS P-Flows Part 2 - Data Items | Derek Weaving | v0.3 | Interfaces/Data Specifications | 4
Section J | Section J - Party Agents and Qualificaton Under the Code | Matthew McKeon | v20.5 | Data Services | 1 | IR7: Merged with BSC Assurance legal text
Section K | Section K - Classification and Registration of Metering Systems and BM Units | Derek Weaving | v48,4 | Metering Services | 1
Section L | Section L - Metering | Mark DeSouza-Wilson | v25.3 | Data Services | 1 | No changes | No changes | No changes | No changes | No changes | No changes
Section S | Annex S-3 - Supplier Volume Allocation Rules for Migrated MHHS Metering Systems | Kevin Spencer | v0.8 | BSC Central Services | 2 | No changes | No changes | No changes | Minor changes to Ann Cons calculations | No changes | No changes | Terminology and numbering changes
Section S | Annex S-4 - Supplier Volume Allocation Rules for Metering Systems During Transition | Kevin Spencer | v0.5 | Transition Text | 4 | No changes | No changes | No changes | No changes | No changes | No changes | Minor changes
Section S | Section S - Supplier Volume Allocation | Kevin Spencer | v44.5 | BSC Central Services | 2 | No changes | No changes | No changes | No changes | No changes | No changes | Minor changes to include UMSO functions.
MHHS Code Workstream - Change Control Log

## Design to Code (hidden)
Reference | Artefact Name / Description | BSC Location | BSC Comments
BP001 | Change of Supplier | BSCP706 | Switch and Registration elements only
BP002 | Change of Service - Metering Service | BSCP706
BP003 | Change of Service - Data Service | BSCP700, BSCP701, BSCP702, BSCP706 | Includes reading exchange
BP003A | CSS and DCC Update | BSCP706
BP003B | Change of Existing Service Appointment Details | BSCP700, BSCP701, BSCP702, BSCP706 | Appointments process managed by SMRS
BP003C | Transfer of Reads - Change of Data Service | BSCP701, BSCP702
BP004 | Data Collection | BSCP700, BSCP701, BSCP702
BP005 | Data Processing | BSCP700, BSCP701, BSCP702, BSCP703
BP007 | Disconnection | BSCP706, BSCP705
BP008 | Change of Energisation Status | BSCP700, BSCP701, BSCP702, BSCP705
BP009 | Change of Meter | BSCP701, BSCP702
BP010 | Change of Registration Data | BSCP706
BP011 | Change of Market Segment and/or Connection Type | BSCP701, BSCP702
BP013 | Demand Disconnection Events | BSCP703, BSCP705
BP016 | Consumption Amendment | BSCP701, BSCP702
BP018 | Load Shaping Service (ECS) | BSCP703
BP019 | Market-wide Data Service (ECS) | BSCP703
BP020 | Volume Allocation Service (ECS) | BSCP703
BP021 | Industry Standing Data (ECS) | BSCP707
BPD001 | Change of Supplier | BSCP706
BPD002 | Change of Service- Metering Service | BSCP706
BPD003 | Change of Service- Data Service | BSCP700, BSCP701, BSCP702, BSCP706
BPD003A | CSS and DCC updates | BSCP706
BPD003B | Change of Existing Service Appointment Details | BSCP700, BSCP701, BSCP702, BSCP706
BPD003C | Transfer of read | BSCP701, BSCP702
BPD004 | Data Collection | BSCP700, BSCP701, BSCP702
BPD005 | Data Processing | BSCP700, BSCP701, BSCP702, BSCP705
BPD007 | Disconnection | BSCP706, BSCP705
BPD008 | Change of Energisation Status | BSCP700, BSCP701, BSCP702, BSCP705
BPD009 | Change of Meter | BSCP701, BSCP702
BPD010 | Change of Registration Data | BSCP706
BPD011 | Change of Market Segment and/or Connection Type | BSCP706
BPD013 | Demand Disconnection Events | BSCP703, BSCP705
BPD016 | Consumption Amendment | BSCP701, BSCP702
BPD018 | Load Shaping Service (ECS) | BSCP703
BPD019 | Market-wide Data Service (ECS) | BSCP703
BPD020 | Volume Allocation Service (ECS) | BSCP703
BPD021 | Industry Standing Data (ECS) | BSCP707
BRS013 | Demand Disconnection Events Requirements (ECS) | BSCP703
BRS001 | Data Services Requirements | BSCP700, BSCP701, BSCP702
BRS002 | Metering Services Requirements | BSCP700
BRS003 | Registration Service Requirements | BSCP706
BRS004 | Supplier Requirements Overview | TBD
BRS005 | LDSO Requirements Overview | BSCP700, BSCP705, BSCP706
BRS006 | EES & SDEP Requirements | N/A
BRS007 | Load Shaping Service Requirements (ECS) | BSCP703
BRS008 | Market-wide Data Service Requirements (ECS) | BSCP703
BRS009 | Volume Allocation Service Requirements (ECS) | BSCP703
BRS010 | Industry Standing Data Requirements (ECS) | BSCP707
BRS012 | Annual Consumption Requirements | BSCP703
BRS014 | ECS Registration Data Archive Requirements | BSCP703
METH001 | SDS Validation & Estimation | BSCP701
METH002 | ADS Validation & Estimation | BSCP702
METH004 | UMSDS- EM Functions | BSCP700
METH005 | LSS Method Statement | BSCP703
METH006 | VAS Method Statement | BSCP703
METH007 | MDS Method Statement | BSCP703
METH008 | DDE Method Statement | BSCP703, BSCP705
METH009 | UMSO Method Statement | BSCP700
METH010 | Annual Consumption | BSCP703
ERI011A | ECS Reports- Internal | BSCP703
ERI011B | ECS Reports- External | BSCP703
EDI021 | ISD Entities | BSCP707
EM021 | ISD Entity Map | BSCP707
DES138 | Interface Catalogue | N/A
OPC001 | Operational Choreography | BSCP700, BSCP701, BACP702, BSCP703, BSCP705, BSCP706
BPM002 | Change of Service - Metering Service - Forward Migration | BSCP708
BPM003 | Change of Service - Data Service - Forward Migration | BSCP708

## Impacted BSC Artefacts
BSC Artefact | Reference | Artefact Name / Description | IR1 | IR2 | IR3 | IR4 | IR5 | IR6 | IR7
BSCP700 | BP003 | Change of Service - Data Service | BP003 | BP003 | BP003 |  |  | BP003 | BP003
BSCP700 | BP003B | Change of Existing Service Appointment Details
BSCP700 | BP004 | Data Collection | IR3: BP004
BSCP700 | BP005 | Data Processing | IR1: BP005
BSCP700 | BP008 | Change of Energisation Status | IR3: BP008
BSCP700 | BPD003 | Change of Service- Data Service | IR2: BPD003
BSCP700 | BPD003B | Change of Existing Service Appointment Details
BSCP700 | BPD004 | Data Collection
BSCP700 | BPD005 | Data Processing
BSCP700 | BPD008 | Change of Energisation Status
BSCP700 | BRS001 | Data Services Requirements | IR1: BRS001; IR2: BRS001; IR3: BRS001; IR7: BRS001
BSCP700 | METH004 | UMSDS Method Statement | IR2: METH004; IR4: METH004; IR6: METH004
BSCP700 | OPC001 | Operational Choreography | IR2: OPC001; IR3: OPC001; IR4: OPC001
BSCP701 | BP003 | Change of Service - Data Service | BP003 | BP003 | BP003 |  |  | BP003 | BP003
BSCP701 | BP003B | Change of Existing Service Appointment Details
BSCP701 | BP003C | Transfer of Reads - Change of Data Service | IR2: BP003C; IR7: BP003C
BSCP701 | BP004 | Data Collection | IR3: BP004
BSCP701 | BP005 | Data Processing | IR1: BP005
BSCP701 | BP008 | Change of Energisation Status | IR3: BP008
BSCP701 | BP009 | Change of Meter | IR2: BP009; IR3: BP009; IR4: BP009; IR6: BP009
BSCP701 | BP011 | Change of Market Segment and/or Connection Type | IR1: BP011; IR2: BP011; IR3: BP011
BSCP701 | BP016 | Consumption Amendment
BSCP701 | BPD003 | Change of Service- Data Service | IR2: BPD003
BSCP701 | BPD003B | Change of Existing Service Appointment Details
BSCP701 | BPD003C | Transfer of read | IR2: BPD003C
BSCP701 | BPD004 | Data Collection
BSCP701 | BPD005 | Data Processing
BSCP701 | BPD008 | Change of Energisation Status
BSCP701 | BPD009 | Change of Meter | IR3: BPD009; IR4: BPD009
BSCP701 | BPD016 | Consumption Amendment
BSCP701 | BRS001 | Data Services Requirements | IR1: BRS001; IR2: BRS001; IR3: BRS001; IR7: BRS001
BSCP701 | METH001 | SDS Validation & Estimation | IR2: METH001; IR3: METH001
BSCP701 | OPC001 | Operational Choreography | IR2: OPC001; IR3: OPC001; IR4: OPC001
BSCP702 | BP003 | Change of Service - Data Service | BP003 | BP003 | BP003 |  |  | BP003 | BP003
BSCP702 | BP003B | Change of Existing Service Appointment Details
BSCP702 | BP003C | Transfer of Reads - Change of Data Service | IR2: BP003C; IR7: BP003C
BSCP702 | BP004 | Data Collection | IR3: BP004
BSCP702 | BP005 | Data Processing | IR1: BP005
BSCP702 | BP008 | Change of Energisation Status | IR3: BP008
BSCP702 | BP009 | Change of Meter | IR2: BP009; IR3: BP009; IR4: BP009; IR6: BP009
BSCP702 | BP011 | Change of Market Segment and/or Connection Type | IR1: BP011; IR2: BP011; IR3: BP011
BSCP702 | BP016 | Consumption Amendment
BSCP702 | BPD003 | Change of Service- Data Service | IR2: BPD003
BSCP702 | BPD003B | Change of Existing Service Appointment Details
BSCP702 | BPD003C | Transfer of read | IR2: BPD003C
BSCP702 | BPD004 | Data Collection
BSCP702 | BPD005 | Data Processing
BSCP702 | BPD008 | Change of Energisation Status
BSCP702 | BPD009 | Change of Meter | IR3: BPD009; IR4: BPD009
BSCP702 | BPD016 | Consumption Amendment
BSCP702 | BRS001 | Data Services Requirements | IR1: BRS001; IR2: BRS001; IR3: BRS001; IR7: BRS001
BSCP702 | METH002 | ADS Validation & Estimation | IR2: METH002; IR4: METH002; IR7: METH002
BSCP703 | BP005 | Data Processing | IR1: BP005
BSCP703 | BP013 | Demand Disconnection Events
BSCP703 | BP018 | Load Shaping Service (ECS)
BSCP703 | BP019 | Market-wide Data Service (ECS)
BSCP703 | BP020 | Volume Allocation Service (ECS) | IR2: BP020; IR7: BP020
BSCP703 | BPD013 | Demand Disconnection Events
BSCP703 | BPD018 | Load Shaping Service (ECS)
BSCP703 | BPD019 | Market-wide Data Service (ECS)
BSCP703 | BPD020 | Volume Allocation Service (ECS) | IR2: BPD020; IR7: BPD020
BSCP703 | BRS013 | Demand Disconnection Events Requirements (ECS)
BSCP703 | BRS007 | Load Shaping Service Requirements (ECS)
BSCP703 | BRS008 | Market-wide Data Service Requirements (ECS)
BSCP703 | BRS009 | Volume Allocation Service Requirements (ECS)
BSCP703 | BRS012 | Annual Consumption Requirements
BSCP703 | BRS014 | ECS Registration Data Archive Requirements
BSCP703 | METH005 | LSS Method Statement | IR7: METH005
BSCP703 | METH006 | VAS Method Statement | IR4: METH006; IR7: METH006
BSCP703 | METH007 | MDS Method Statement | IR4: METH007; IR7: METH007
BSCP703 | METH008 | DDE Method Statement
BSCP703 | METH010 | Annual Consumption | IR4: METH010
BSCP703 | ERI011A | ECS Reports- Internal | IR1: ERI011A; IR3: ERI011A; IR4: ERI011A; IR6: ERI011A
BSCP703 | ERI011B | ECS Reports- External | ERI011B |  | ERI011B | ERI011B |  | ERI011B | ERI011B
BSCP703 | OPC001 | Operational Choreography | IR2: OPC001; IR3: OPC001; IR4: OPC001
BSCP704 | BRS002 | Metering Services Requirements | BRS002 |  | BRS002 | BRS002 |  | BRS002 | BRS002
BSCP704 | BRS005 | LDSO Requirements Overview | IR1: BRS005; IR3: BRS005
BSCP704 | METH009 | UMSO Method Statement | IR2: METH009
BSCP704 | OPC001 | Operational Choreography | IR2: OPC001; IR3: OPC001; IR4: OPC001
BSCP705 | BP007 | Disconnection | IR1: BP007; IR2: BP007; IR7: BP007
BSCP705 | BP008 | Change of Energisation Status | IR3: BP008
BSCP705 | BP013 | Demand Disconnection Events
BSCP705 | BPD005 | Data Processing
BSCP705 | BPD007 | Disconnection | IR1: BPD007; IR2: BPD007
BSCP705 | BPD008 | Change of Energisation Status
BSCP705 | BPD013 | Demand Disconnection Events
BSCP705 | BRS005 | LDSO Requirements Overview | IR1: BRS005; IR3: BRS005
BSCP705 | METH008 | DDE Method Statement
BSCP705 | OPC001 | Operational Choreography | IR2: OPC001; IR3: OPC001; IR4: OPC001
BSCP706 | BP001 | Change of Supplier
BSCP706 | BP002 | Change of Service - Metering Service | IR1: BP002; IR2: BP002; IR6: BP002
BSCP706 | BP003 | Change of Service - Data Service | BP003 | BP003 | BP003 |  |  | BP003 | BP003
BSCP706 | BP003A | CSS and DCC Update
BSCP706 | BP003B | Change of Existing Service Appointment Details
BSCP706 | BP007 | Disconnection | IR1: BP007; IR2: BP007; IR7: BP007
BSCP706 | BP010 | Change of Registration Data | IR1: BP010; IR3: BP010; IR4: BP010
BSCP706 | BPD001 | Change of Supplier | IR7: BPD001
BSCP706 | BPD002 | Change of Service- Metering Service | IR1: BPD002; IR2: BPD002
BSCP706 | BPD003 | Change of Service- Data Service | IR2: BPD003
BSCP706 | BPD003A | CSS and DCC updates
BSCP706 | BPD003B | Change of Existing Service Appointment Details
BSCP706 | BPD007 | Disconnection | IR1: BPD007; IR2: BPD007
BSCP706 | BPD010 | Change of Registration Data | IR1: BPD010; IR4: BPD010
BSCP706 | BPD011 | Change of Market Segment and/or Connection Type | IR2: BPD011
BSCP706 | BRS003 | Registration Service Requirements | IR1: BRS003; IR3: BRS003; IR6: BRS003; IR7: BRS003
BSCP706 | BRS005 | LDSO Requirements Overview | IR1: BRS005; IR3: BRS005
BSCP706 | OPC001 | Operational Choreography | IR2: OPC001; IR3: OPC001; IR4: OPC001
BSCP707 | BP021 | Industry Standing Data (ECS) | IR4: BP021
BSCP707 | BPD021 | Industry Standing Data (ECS) | IR4: BPD021
BSCP707 | BRS010 | Industry Standing Data Requirements (ECS) | IR7: BRS010
BSCP707 | EDI021 | ISD Entities | IR2: EDI021; IR3: EDI021; IR6: EDI021; IR7: EDI021
BSCP707 | EM021 | ISD Entity Map
BSCP708 | BPM002 | Change of Service - Metering Service - Forward Migration | IR1: BPM002; IR2: BPM002; IR7: BPM002
BSCP708 | BPM003 | Change of Service - Data Service - Forward Migration | IR1: BPM003; IR2: BPM003; IR3: BPM003; IR7: BPM003
BSCP709 | BP001 | Change of Supplier
BSCP709 | BP003 | Change of Service - Data Service | IR7: BP003
BSCP709 | BP003B | Change of Existing Service Appointment Details
BSCP709 | BP003C | Transfer of Reads - Change of Data Service | IR7: BP003C
BSCP709 | BP010 | Change of Registration Data
BSCP709 | BP016 | Consumption Amendment
BSCP709 | BRS004 | Supplier Overview | IR7: BRS004

## IR Overview
Reference | Artefact Name / Description | IR1 | IR2 | IR3 | IR4 | IR5 | IR6 | IR7
BP002 | Change of Service - Metering Service | bar: IR1 to IR2; IR6
BP003 | Change of Service - Data Service | bar: IR1 to IR3; IR6 to IR7
BP003C | Transfer of Reads - Change of Data Service | bar: IR2; IR7
BP004 | Data Collection | bar: IR3
BP005 | Data Processing | bar: IR1
BP007 | Disconnection | bar: IR1 to IR2; IR7
BP008 | Change of Energisation Status | bar: IR3
BP009 | Change of Meter | bar: IR2 to IR4; IR6
BP010 | Change of Registration Data | bar: IR1; IR3 to IR4
BP011 | Change of Market Segment and/or Connection Type | bar: IR1 to IR3
BP020 | Volume Allocation Service (ECS) | bar: IR2; IR7
BP021 | Industry Standing Data (ECS) | bar: IR4
BPD002 | Change of Service - Metering Service | bar: IR1 to IR2
BPD002 | Change of Service - Metering Service (Forward Migration) | bar: IR1 to IR2
BPD003 | Change of Service - Data Service | bar: IR2
BPD003 | Change of Service - Data Service (Forward Migration) | bar: IR2
BPD003C | Transfer of readings | bar: IR2
BPD007 | Disconnection | bar: IR1 to IR2
BPD009 | Change of Meter | bar: IR3 to IR4
BPD010 | Change of Registration Data | bar: IR1; IR4
BPD011 | Change of Market Segment and/or Connection Type | bar: IR2
BPD020 | Volume Allocation Service (ECS) | bar: IR2; IR7
BPD021 | Industry Standing Data (ECS) | bar: IR4
BPM002 | Change of Service - Metering Service - Forward Migration | bar: IR1 to IR2; IR7
BPM003 | Change of Service - Data Service - Forward Migration | bar: IR1 to IR3; IR7
BRS001 | Data Services Requirements | bar: IR1 to IR3; IR7
BRS002 | Metering Services Requirements | bar: IR1; IR3 to IR4; IR6 to IR7
BRS003 | Registration Service Requirements | bar: IR1; IR3; IR6 to IR7
BRS004 | Supplier Requirements Overview | bar: IR3; IR7
BRS005 | LDSO Requirements Overview | bar: IR1; IR3
DES138 | Interface Catalogue | bar: IR1 to IR7
DES229 | IF005 Use Case Guide | bar: IR1 to IR3
E2E001 | End to End Solution Architecture | bar: IR1 to IR4; IR7
E2E002 | Requirements | bar: IR1
EDI021 | ISD Entities | bar: IR2 to IR3; IR6 to IR7
ERI011A | ECS Reports- Internal | bar: IR1; IR3 to IR4; IR6
ERI011B | ECS Reports- External | bar: IR1; IR3 to IR4; IR6 to IR7
Swagger | JSON/YAMLfiles | bar: IR1 to IR5
METH001 | SDS Method Statement | bar: IR2 to IR3
METH002 | ADS Method Statement | bar: IR2; IR4; IR7
METH004 | UMSDS Method Statement | bar: IR2; IR4; IR6
METH005 | LSS Method Statement | bar: IR7
METH006 | VAS Method Statement | bar: IR4; IR7
METH007 | MDS Method Statement | bar: IR4; IR7
METH009 | UMSO Method Statement | bar: IR2
METH010 | Annual Consumption | bar: IR4
OPC001 | Operational Choreography | bar: IR2 to IR4
Traceability Matrix | bar: IR1

## IR1
Reference | Artefact Name / Description | Version Number | Theme | Impact
BP002 | Change of Service - Metering Service | V5.1 | MPAN Ownership | Process correction
BP003 | Change of Service - Data Service | V5.1 | MPAN Ownership | Process correction
BP005 | Data Processing | V5.1 | Meter to Bank | Process correction
BP007 | Disconnection | V5.1.1 | Metering Changes | Process correction
BP010 | Change of Registration Data | V5.1.1 | MPAN Ownership | Process correction
BP011 | Change of Market Segment and/or Connection Type | V5.1.1 | Metering Changes | Process correction
BPD002 | Change of Service - Metering Service | V5.1 | MPAN Ownership | Process correction
BPD002 | Change of Service - Metering Service (Forward Migration) | V1.1 | Migration Design | Process Correction
BPD007 | Disconnection | V5.1.1 | Metering Changes | Process correction
BPD010 | Change of Registration Data | V5.1.1 | MPAN Ownership | Process correction
BPM002 | Change of Service - Metering Service - Forward Migration | V1.1 | Migration Design | Process Correction
BPM003 | Change of Service - Data Service - Forward Migration | V1.1 | Migration Design | Process Correction
BRS001 | Data Services Requirements | V5.1 | Supporting Documents | Requirement corrections
BRS002 | Metering Services Requirements | V5.1 | Supporting Documents | Requirement corrections
BRS003 | Registration Service Requirements | V5.1.2 | Supporting Documents | Requirement corrections
BRS005 | LDSO Requirements Overview | V5.1 | Supporting Documents | Requirement corrections
DES138 | Interface Catalogue | V5.1.2 | Meter to Bank, Metering Changes, MPAN Ownership | Null fields and other Interface corrections
DES229 | IF005 Use Case Guide | V1.1.2 | Supporting Documents | IF005 corrections
E2E001 | End to End Solution Architecture | V3.1.1 | Supporting Documents | Additional Solution Design Details
E2E002 | Requirements | V3.1 | Supporting Documents | Requirement corrections
ERI011A | ECS Reports- Internal | V5.1.1 | Supporting Documents | Report corrections
ERI011B | ECS Reports- External | V5.1 | Supporting Documents | Report corrections
| JSON/YAMLfiles | V1.1 | Supporting Documents | Updated Swagger definitions
| Traceability Matrix | V5.1 | Supporting Documents | Requirement traceability corrections
MHHS DEL1275 Design Interim Release 1 Note v1.0.docx

## IR2
Reference | Artefact Name / Description | Version Number | Theme | Impact
BP002 | Change of Service - Metering Service | V5.2 | MPAN Ownership | Process Correction
BP003 | Change of Service - Data Service | V5.2 | MPAN Ownership | Process Correction
BP003C | Transfer of Reads - Change of Data Service | V5.1 | MPAN Ownership | Process Correction
BP007 | Disconnection | V5.2 | Metering Changes | Process Correction
BP009 | Change of Meter | V5.1 | Metering Changes | Process Correction
BP011 | Change of Market Segment and/or Connection Type | V5.2 | Metering Changes | Process Correction
BP020 | Volume Allocation Service (ECS) | V5.1 | Meter to Bank | Process Correction
BPD002 | Change of Service - Metering Service | V5.2 | MPAN Ownership | Process Correction
BPD002 | Change of Service - Metering Service (Forward Migration) | V1.2 | Migration Design | Process correction
BPD003 | Change of Service - Data Service | V5.1 | MPAN Ownership | Process Correction
BPD003 | Change of Service - Data Service (Forward Migration) | v1.1 | Migration Design | Process correction
BPD003C | Transfer of readings | V5.1 | MPAN Ownership | Process Correction
BPD007 | Disconnection | V5.2 | Metering Changes | Process Correction
BPD011 | Change of Market Segment and/or Connection Type | V5.1 | Metering Changes | Process Correction
BPD020 | Volume Allocation Service (ECS) | V5.1.1 | Meter to Bank | Process Correction
BPM002 | Change of Service - Metering Service - Forward Migration | v1.2 | Migration Design | Process correction
BPM003 | Change of Service - Data Service - Forward Migration | v1.2 | Migration Design | Process correction
BRS001 | Data Services Requirements | V5.2 | Supporting Documents | Requirement Correction
DES138 | Interface Catalogue | V5.2.1 | Meter to Bank, Metering Changes, MPAN Ownership | Routing rules and other Interface corrections
DES229 | IF005 Use Case Guide | V1.2 | Supporting Documents | IF005 corrections
E2E001 | End to End Solution Architecture | V3.2 | Supporting Documents | Additional Solution Design Details
EDI021 | ISD Entities | V5.1 | Supporting Documents | Data Correction
| JSON/YAMLfiles | V1.2 | Supporting Documents | Updated Swagger definitions
METH001 | SDS Method Statement | V5.1 | Supporting Documents | Statement Correction
METH002 | ADS Method Statement | V5.1 | Supporting Documents | Statement Correction
METH004 | UMSDS Method Statement | V5.1 | Supporting Documents | Statement Correction
METH009 | UMSO Method Statement | V5.1 | Supporting Documents | Statement Correction
OPC001 | Operational Choreography | V5.1 | Supporting Documents | Design Clarification
MHHS DEL1275 Design Interim Release 2 Note v1.0.docx

## IR3
Reference | Artefact Name / Description | Version Number | Theme | Impact
BP003 | Change of Service - Data Service | V5.3 | MPAN Ownership | Process Correction
BP004 | Data Collection | V5.1 | MPAN Ownership | Process Correction
BP008 | Change of Energisation Status | V5.1 | Metering Changes | Process Correction
BP009 | Change of Meter | V5.2 | Metering Changes | Process Correction
BP010 | Change of Registration Data | V5.2 | Metering Changes | Process Correction
BP011 | Change of Market Segment and/or Connection Type | V5.3 | Metering Changes | Process Correction
BPD009 | Change of Meter | V5.1 | Business Process Description | Process Correction
BPM003 | Change of Service - Data Service - Forward Migration | V1.3 | Migration Design | Process correction
BRS001 | Data Services Requirements | V5.3 | Supporting Documents | Requirement Correction
BRS002 | Metering Services Requirements | V5.2 | Supporting Documents | Requirement Correction
BRS003 | Registration Service Requirements | V5.2 | Supporting Documents | Requirement Correction
BRS004 | Supplier Requirements Overview | V5.1 | Supporting Documents | Requirement Correction
BRS005 | LDSO Requirements Overview | V5.2 | Supporting Documents | Requirement Correction
DES138 | Interface Catalogue | V5.3.2 | Meter to Bank, Metering Changes, MPAN Ownership | Interface corrections
DES229 | IF005 Use Case Guide | V1.3 | Supporting Documents | IF005 corrections
E2E001 | End to End Solution Architecture | V3.3 | Supporting Documents | Additional Solution Design Details
EDI021 | ISD Entities | V5.2 | Supporting Documents | Data Correction
ERI011A | ECS Reports- Internal | V5.2 | Supporting Documents | Data Correction
ERI011B | ECS Reports- External | V5.2 | Supporting Documents | Data Correction
| JSON/YAMLfiles | V1.3 | Supporting Documents | Updated Swagger definitions
METH001 | SDS Method Statement | V5.2 | Supporting Documents | Statement Correction
OPC001 | Operational Choreography | V5.2.6 | Supporting Documents | Statement correction
MHHS DEL1275 Design Interim Release 3 Note v1.0.docx

## IR4
Reference | Artefact Name / Description | Version Number | Theme | Impact
BP009 | Change of Meter | V5.3 | Metering Changes | Process Correction
BP010 | Change of Registration Data | V5.3 | MPAN Ownership | Process Correction
BP021 | Industry Standing Data (ECS) | V5.1 | Meter to Bank | Process Correction
BPD009 | Change of Meter | V5.3 | Business Process Description | Process Correction
BPD010 | Change of Registration Data | V5.2 | Business Process Description | Process Correction
BPD021 | Industry Standing Data (ECS) | V5.1 | Business Process Description | Process Correction
BRS002 | Metering Services Requirements | V5.3 | Supporting Documents | Requirement Correction
DES138 | Interface Catalogue | V5.4.1 | Meter to Bank, Metering Changes, MPAN Ownership | Interface corrections
E2E001 | End to End Solution Architecture | V3.4 | Supporting Documents | Solution Design Correction
ERI011A | ECS Reports- Internal | V5.3 | Supporting Documents | Data Correction
ERI011B | ECS Reports- External | V5.3 | Supporting Documents | Data Correction
| JSON/YAMLfiles | V1.4 | Supporting Documents | Updated Swagger definitions
METH002 | ADS Method Statement | V5.2 | Supporting Documents | Statement correction
METH004 | UMSDS Method Statement | V5.2 | Supporting Documents | Statement correction
METH006 | VAS Method Statement | V5.1 | Meter to Bank | Statement correction
METH007 | MDS Method Statement | V5.1 | Meter to Bank | Statement correction
METH010 | Annual Consumption | V5.1 | Supporting Documents | Statement correction
OPC001 | Operational Choreography | V5.3 | Supporting Documents | Statement correction
MHHS DEL1275 Design Interim Release 4 Note v1.0.docx

## IR5
Reference | Artefact Name / Description | Version Number | Theme | Impact
DES138 | Interface Catalogue | V5.5.3 | Meter to Bank, Metering Changes, MPAN Ownership | Interface corrections
| DataCatalogue-1.5.1-domain.json | V1.5.1 | Supporting Documents | Updated Swagger definitions
| DataCatalogue-1.5.1-domain.yaml | V1.5.1 | Supporting Documents | Updated Swagger definitions
| DataTypes-1.5.1-domain.json | V1.5.1 | Supporting Documents | Updated Swagger definitions
| DataTypes-1.5.1-domain.yaml | V1.5.1 | Supporting Documents | Updated Swagger definitions
| Interfaces-EventCodes-1.5.1-domain.json | V1.5.1 | Supporting Documents | Updated Swagger definitions
| Interfaces-EventCodes-1.5.1-domain.yaml | V1.5.1 | Supporting Documents | Updated Swagger definitions
| RealCommonBlocks-1.5.1-domain.json | V1.5.1 | Supporting Documents | Updated Swagger definitions
| RealCommonBlocks-1.5.1-domain.yaml | V1.5.1 | Supporting Documents | Updated Swagger definitions
| SubmitEvents-1..1-resolved.json | V1.5.1 | Supporting Documents | Updated Swagger definitions
| SubmitEvents-1.5.1-resolved.yaml | V1.5.1 | Supporting Documents | Updated Swagger definitions
| SubmitEvents-1.5.1-swagger.json | V1.5.1 | Supporting Documents | Updated Swagger definitions
| SubmitEvents-1.5.1-swagger. yaml | V1.5.1 | Supporting Documents | Updated Swagger definitions
| Examples-0.3-domain.json | V0.3 | Supporting Documents | Updated Swagger definitions
| Examples-0.3-domain.yaml | V0.3 | Supporting Documents | Updated Swagger definitions
MHHS DEL1275 Design Interim Release 5.1 Note v0.1 .docx

## IR6
Reference | Artefact Name / Description | Version Number | Theme | Impact
BP002 | Change of Service - Metering Service | V5.4 | MPAN Ownership | Process Correction
BP003 | Change of Service - Data Service | V5.5 | MPAN Ownership | Process Correction
BP009 | Change of Meter | V5.4 | Metering Changes | Process Correction
BRS002 | Metering Service requirements | V5.5 | Supporting Documents | Requirement Correction
BRS003 | Registration Service requirements | V5.4 | Supporting Documents | Requirement Correction
DEL961 | Migration Design Document | V1.1 | Migration Documents | Requirement Correction
DES138 | Interface Catalogue | V5.6.1 | Meter to Bank, Metering Changes, MPAN Ownership | Interface corrections
EDI021 | ISD Entities | V5.4 | Supporting Documents | Data Correction
ERI011A | ECS Reports - Internal | V5.5 | Supporting Documents | Data Correction
ERI011B | ECS Reports - External | V5.5 | Supporting Documents | Data Correction
METH004 | UMSDS Method Statement | V5.3 | Supporting Documents | Statement correction
| JSON/YAML files | V1.6 | Supporting Documents | Updated Swagger definitions
| Examples-0.4-domain.json | V0.4 | Supporting Documents | Updated Swagger definitions
| Examples-0.4-domain.yaml | V0.4 | Supporting Documents | Updated Swagger definitions
MHHS DEL1275 Design Interim Release 6 Note v1.0.docx

## IR7
Reference | Artefact Name / Description | Version Number | Theme | Impact
E2E001 | End-to-End Solution Architecture | V3.6 | Supporting Documents | Solution Design Correction
DEL961 | Migration Design Document | V1.2 | Migration Design | Statement correction
BPM001 | Change Of Supply - Reverse Migration | V1.1 | Migration Design | Process Correction
BPM002 | Change of Service - Metering Service - Forward Migration | V1.3 | Migration Design | Process Correction
BPM003 | Change of Service - Data Service - Reverse Migration | V1.1 | Migration Design | Process Correction
BPD001 | Change Of Supply - Reverse Migration | V1.1 | Migration Design | Requirement Correction
DIP051 | IF-015/016 Design Note | V0.2 | Supporting Documents | Solution Design Correction
ERI011B | ECS Reports - External | V5.6 | Supporting Documents | Data Correction
EDI021 | ISD - Entities | V5.5 | Supporting Documents | Data Correction
BP003 | Change of Service - Data Service - Reverse Migration | V5.6.1 | MPAN Ownership | Process Correction
BP003C | Transfer of Reads - Change of Data Service | V5.2 | MPAN Ownership | Process Correction
BP007 | Disconnection | V5.3 | Metering Changes | Process Correction
BP017 | Optional_SDS_MDR_Interactions | V1.0 | Supporting Documents | Process Correction
BP020 | Volume Allocation Service (ECS) | V5.2 | Meter to Bank | Process Correction
BPD020 | Volume Allocation Service Business Process Descriptions | V5.2 | Meter to Bank | Process Correction
BRS001 | Data Service Requirements | V5.5 | Supporting Documents | Requirement Correction
BRS002 | Metering Service requirements | V5.6 | Supporting Documents | Requirement Correction
BRS003 | Registration Service requirements | V5.5 | Supporting Documents | Requirement Correction
BRS004 | Supplier Overview | V5.3 | Supporting Documents | Requirement Correction
BRS010 | Industry Standing Data Requirements (ECS) | V5.1 | Supporting Documents | Requirement Correction
BRS017 | Optional SDS_MDR Standard Interactions Requirements | V1.0 | Supporting Documents | Requirement Correction
DES138 | DES138-Interface Catalogue | V5.7.1 | Meter to Bank, Metering Changes, MPAN Ownership | Interface corrections
METH002 | METH002_ADS_Validation_Estimation | V5.4 | Supporting Documents | Statement correction
METH005 | METH005 LSS_Method_Statement | V5.1 | Supporting Documents | Statement correction
METH006 | METH006_VAS_Method Statement | V5.3 | Meter to Bank | Statement correction
METH007 | METH007_MDS_Method_Statement | V5.3 | Meter to Bank | Statement correction
TRANS - BRS001 | Transition Approach and Parallel Running Requirements | V4.0 | Transition Design | Requirement Correction
MHHS DEL1275 Design Interim Release 7 Note v1.0.docx