## Transition Design Tranche 2
Comment ID (to be assigned by the Code Team) | Code Artefact Name | Document Section | Comments | Suggested Change e.g. proposed wording | Comment Owner | Organisation | Constituency | Submitted | Triage Status | Programme Response e.g.clarification or update on the change
TDC-001 |  |  | SPEN have reviewed the attached MHHS Transition Design Tranche 2 documents and have no further comments to add. |  | Kerryann O'Neill | SPEN | DNO | 2023-10-16 | Accepted ​​ | Thank you for reviewing and confirming SPEN have no further comments.
TDC-002 | Transition to New Settlement Timetable Proposal | Section 3.2 - The Settlement Timetable and Operational Choreography | Confirmation required. 1. Will the settlement timetable be published on the ISD website and will this be downloadable. 2. Confirm the format of the downloadable version of the ISD Settlement Calendar. (And specifically whether this has changed compared to the MDD instance of the calendar). | Confirmation of the points made in the previous cell. | Andrew Dudkowsky | ESO | ESO - Central Services | 2023-10-23 | Clarification Provided​​ | The Master Settlement Timetable will be in ISD. Notification of new Versions are sent out on the IF-047 which provides the URL. The timetable will be in .csv format.
TDC-003 | Transition to New Settlement Timetable Proposal | Section 3.2 - The Settlement Timetable and Operational Choreography | The migration to the new settlement timetable by replacing R2/R3 runs with RF and ending the settlement timetable early is a new process. Are there any plans to test the migration to the new settlement timetable? | Include the test plan for the migration to the settlement timetable. | Andrew Dudkowsky | ESO | ESO - Central Services | 2023-10-23 | Acknowledge​​ | The Settlement Timtable is only a schedule of when Settlement Runs occur. As such there are no processes to test other than the ISD Publish which is on scope.
TDC-004 | Transition to New Settlement Timetable Proposal | Section 4. Proposed Approach for cut-over to New Settlement Timetable | For a given settlement date there may be more than one RF run. Will the files for each RF run have different version numbers to indicate that they are a different RF and not a duplicate file? | Reference that files from RF runs will include a version number based on the date they were produced and the later file has a later version number to earlier files. | Andrew Dudkowsky | ESO | ESO - Central Services | 2023-10-23 | Rejected​​ | There will only be a single RF Run for each Settlement Date.
TDC-005 |  |  | After having reviewed the documentation supporting this consultation with stakeholders in relevant roles, we have no specific feedback to add. |  | Martin Stewart | Opus Energy | I&C Supplier | 2023-10-25 | Accepted ​​ | Thank you for reviewing and confirming Opus have no further comments.
TDC-006 | Transition to New Settlement Timetable Proposal | Overall | Can confirmation please be provided on whether the settlement run will only be reduced post completion of migration of all MPANs? |  | Sophie Horne | Utilita | Medium Supplier | 2023-10-25 | Clarification Provided​​ | The RF Runs will start to reduce to 7 months around September 2026 for Settlement Dates from March 2026. However, this will only occur if the Migration is on track to complete by the 5 October 2026.
TDC-007 | Transition to New Settlement Timetable Proposal | Overall | Related to the above, if there is a risk that the migrations will not be fully completed before the time the settlement timetable proposal is implemented and the window reduced, how can participants be assured that only migrated MPANs (for which we will receive PUB-41s) will be the MPANs subject to the shorter, settlement timetable |  | Sophie Horne | Utilita | Medium Supplier | 2023-10-25 | Clarification Provided​​ | All MPANs will be subject to any reduced timetable as Settlement Runs have to cover all energy on a Settlement Dates. The IF-041 will only be sent for Migrated MPANs as they are sent by MHHS Services.
TDC-008 | Transition to New Settlement Timetable Proposal | 4.1 | Can clarification be provided on what would inform a Go decision and a No Go decision please? |  | Sophie Horne | Utilita | Medium Supplier | 2023-10-25 | Clarification Provided​​ | We have defined some monitoring to be undertaken to collect data to inform any decision. It has been agreed that the criteria be set nearer the time when we know more.
TDC-009 | Transition to New Settlement Timetable Proposal | 3.1 Background and other sections | This section states that decisions related to the reduction of the Post Final Settlement timeline is out of Programme scope despite other sections of the document referring to Post Settlement Timeline specifically | The document should provide information about the Post Final Settlement timeline runs or not mention them at all. Ideally this document should have clear visualisation of DF reconciliation runs providing clear and transparent information on how this run fits together with other Settlement runs. | Aga Medley | UK Power Networks | LDSO | 2023-10-25 | Acknowledge​​ | The Disputes process is under Review by Elexon and it is the process that is out of scope. The document states that the current DF timescales will be reduced for the current 28 Months to 20 Month at the M16 Milestone. We believe this statement is clear enough for parties to understand the intent. ELEXON will have to create the DF timetable once the Master Settlemet Timetable has been agreed ensuring the numer of runs per day is smoothed.
TDC-010 | Transition to New Settlement Timetable Proposal | 3.4 Other Consideration | Bullet point 3 - It has been suggested that once populated in Market Participant Systems make retrospective changes e.g. making the R3 Run the Final Reconciliation Run (RF) once the R3 Run has completed". | Our understanding is that the Programme has moved on from suggesting any retrospective changes to already processed data in industry systems. Please rephrase the sentence to make it clear that no retrospective system changes are required | Aga Medley | UK Power Networks | LDSO | 2023-10-25 | Accepted ​​ | The word cannot was accidently deleted and has now been added back in. This was a consideration which results in the outcome that no retrospective changes occur in the proposed approach.
TDC-011 | Transition to New Settlement Timetable Proposal | 4.2 Detailed Steps | Step 6 "If the M16 date is not confirmed in Step 4 as the 7/12/2026 then a calendar shall be produced that moves the RF adjustments in relation to the revised M16 date. E.G. If the milestone move 3 months then the RF Runs would only be reduced where they were greater than 31 July 2027." In the example given, shouldn't the RF runs be reduced where they are greater than 30/06/2027 (i.e. three months from 31/03/2027) rather than 31/07/2027 (which is four months from 31/03/2027)? | Please revise the example date if applicable. | Aga Medley | UK Power Networks | LDSO | 2023-10-25 | Accepted ​​ | Change to 30 June 2027.
TDC-012 | Transition to New Settlement Timetable Proposal | 4.2 Detailed Steps | "The Post Final Settlement Runs will be brought into 20 Months at the M16 Cut-over date. It should be noted that once the RF dates are completed, for pre M16 Settlement Dates, revised data will not be available for non-migrated MPANs. Hence, the data for these MPANs will be crystallised at RF. Migrated MPANs can have revised data submitted for Pre-M16 Settlement Dates for Post Final Settlement Runs up to 28 Months." Unclear from the paragraph above how migrated and non-migrated pre-M16 MPANs will be treated for RF and DF settlement runs and migrated and non-migrated MPANs post M16. | Please clearly state in the document the definition of non-migrated MPANs. Our understanding is that the M16 milestone is achieved when all MPANs are migrated (excluding 'Created'/'Terminated' MPANs). Please enhance this sestion to also clearly state what happens to migrated and non-migrated MPANs both before and after M16 for the Post Final Settlement Run. It would be beneficial to plot this into the published Excel spreadsheet (MHHS-DEL1593-Replacement RF Settlement Timetable RF Illustration) or issue a seperate spreadsheet just for the DF run visualisation for clarity. | Aga Medley | UK Power Networks | LDSO | 2023-10-25 | Accepted ​​ | Wording amended to recognise some Supplier may keep Das stood up to process DF data.
TDC-013 | Transition to New Settlement Timetable Proposal |  | Monthly terminology is used, however the settement runs are defined in working days rather than months. With with the far more compact settlement timetable, greater accuracy and granularisation is needed. | Any references to timescales expressed in months should be expressed in working days instead. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Rejected​​ | It is easier for parties to undestand the proposal using months rather than say X Working Days. The example spreadsheets provide this level of detail for those parties that are interested in understanding the detail at Settlement Date/ Settlement Run level.
TDC-014 | Transition to New Settlement Timetable Proposal | Page 4 | Disputes after DF are currently not within scope, which leaves parties unclear of the process and timetables that will be in place for such disputes. Further detail is required regarding the change to a 20 month period compared to the 28 month period today. It is understandable why it is not considered core however it a consequential part of the settlement calendar. We are assuming that Extra Settlement Detrimentation (ESD) (where dispute not resolved within 28 months) will be incorporated into the changes. | Clarity is required where as to where the DF disputes process sits within the new settlement timetable. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Acknowledge​​ | The Disputes process is under Review by Elexon and it is the process that is out of scope. The document states that the current DF timescales will be reduced for the current 28 Months to 20 Month at the M16 Milestone. We believe this statement is clear enough for parties to understand the intent. ELEXON will have to create the DF timetable once the Master Settlemet Timetable has been agreed ensuring the numer of runs per day is smoothed.
TDC-015 | Transition to New Settlement Timetable Proposal |  | There are concerns over the impact on credit cover requirements and payment “spikes” as a result of reducing the overall settlement timetable from 14 months to 4 months. More Mpans are now in each of the run pots due to the reduction in the number of runs, so there is a higher payment value for each run compared to the status quo. This could subsequently increase the likelihood of a SoLR occurring even more than currently in the midst of the energy crisis. A specific example of where payment values will increase; BSUoS invoicing (triggered by RF settlement run) will see a minimum of 3 RF runs in January 2027 covering at least 3 different settlement dates. | Clarity is needed to understand how shortening the settlement timetable in the transition timetables will impact credit cover requirements. The settlement days in each run pot should stay consistent with the status quo leaving no impact on payment value spike and credit cover. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Acknowledge​​ | The issue you are raising is inherent in reducing the Settlement Timetable from 14 Months to 4 Months. As such any proposal will have this impact. The number of MPANs in each Settlement Run does not change as all energised MPANs will be processed. The approach proposed reduce the numer of payment dates for example where a RF Run replaces an R3 run (reduces the number of payment dates by 1. Likewise credit cover is driven by the SF Run which is being moved to 7 WD which can only reduce the amount of credit cover required.
TDC-016 | Transition to New Settlement Timetable Proposal |  | It is unclear how the programme will incorporate the new timetable(s) into ISD and notify stakeholders. For example via IF47. | Clarity is needed on the expectations and subsequent impact to parties who need to embed the timetable into processes. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Clarification Provided​​ | The Master Settlement Timetable will be in ISD. Notification of new Versions are sent out on the IF-047 which provides the URL. The timetable will be in .csv format.The draft version of BSCP707 Industry Standing Data is available on the Collaboration Base.
TDC-017 | Transition to New Settlement Timetable Proposal |  | It is unclear how any late invoices relating to old settlement runs that may have now disappeared, for example R2 & R3, will be treated in the new world due to the omission of payment date. Could this increase the risk of double payment and late payment? | Clarity on the process for late payment is needed. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Rejected​​ | The Runs are replaced so would never have occurred so how can there be invoices for Runs that have not occurred?
TDC-018 | Transition to New Settlement Timetable Proposal |  | The current document only shows the new settlement timings, leading to a lack of illustration of legacy settlement runs. | Also show legacy settlement in addition to the new so that there is an appreciation for the “multi” runs at any one time. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Rejected​​ | The proposal covers legacy and revised Settlement timings. The accompanying spreadsheets also cover the detail at Settlement date/ Settlement Run granularity. Currently, there are up to 14 Settlement Runs per Day. This is likely to reduce as there are less Settlement Runs in the Target State.
TDC-019 | Transition to New Settlement Timetable Proposal |  | To support more concrete understanding, broader scope of the time horizon would be helpful. | The illustration should extend beyond the current highlighted time horizon by starting in January 2024, and also split across the 5 different proposed transition timetables including the current timetable. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Rejected​​ | The example speadsheet cover the Settlement Timetable as if it would occur at Go-live. The timings do not change until 2026 so there is no benefot in extrapolating the illustratioon backwards.
TDC-020 | Transition to New Settlement Timetable Proposal |  | As in line 6 above, the illustration uses monthly values rather than working day values. | Working day granularity of settlement runs rather than current monthly level. | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Rejected​​ | It is easier for parties to undestand the proposal using months rather than say X Working Days. The example spreadsheets provide this level of detail for those parties that are interestin in understanding the detail at Settlement Date/ Settlement Run level.
TDC-021 | Transition to New Settlement Timetable Proposal |  | To support understanding, the documented examples in 1591 and 1592 should include the projection of the new timetable / calendar rather than simply changing the existing timetable. |  | Andrew Eisenberg | E.ON Group | Large Supplier | 2023-10-25 | Rejected​​ | It is very complex to produce the Settlement Timetable for future date. The examples use the current Settlemet Timetable to demonstrate the proposal.
TDC-022 | Transition to New Settlement Timetable Proposal | 4.2 | It will be important to understand who is responsible for each of the detailed steps outlined in the transition design section 4.2. It is important to understand who is responsible and who will be involved from Helix and Elexon BAU. We would like a RACI for each step which is probably made up of: MHHS, Helix/Elexon BAU/PAB. |  | Anna Millar | Elexon | Code Body | 2023-10-25 | Acknowledge​​ | We need to set up the discussions you are proposing.
TDC-023 | Transition to New Settlement Timetable Proposal | 4.2 | It will be important to understand who is expected to take action off the back of any reporting concerns picked up in the steps within 4.2- MHHSP or Elexon/PAB as dual governance may be confusing. Taking action to address issues is not an action step- should it be? |  | Anna Millar | Elexon | Code Body | 2023-10-25 | Acknowledge​​ | This can be picked up in discussions between the MHHSP and Elexon.
TDC-024 | Transition to New Settlement Timetable Proposal | 4.2 | The criteria for the go/no go on M16 not yet clear. It may need to be decided nearer the time but it would be good to agree when this will happen and how and it is important that Helix and any appropriate Elexon BAU staff area involved in these decisions. |  | Anna Millar | Elexon | Code Body | 2023-10-25 | Acknowledge​​ | It has been agreed that the go/no go criteria needs to be set nearer the time when more is understood. We can disuss this in our discussions.
TDC-025 | Transition to New Settlement Timetable Proposal | 4.2 | We believe considering the number of disputes open and likely to be opened as part of this criteria is important.- should this be an additional action step? |  | Anna Millar | Elexon | Code Body | 2023-10-25 | Accepted ​​ | Added this to the document.
TDC-026 | Transition to New Settlement Timetable Proposal | 4.2 | Our assumption is that it will be up to Elexon and Helix to ensure that the new DF run dates are agreed and fed into the Settlement Timetable but it would be good to agree with MHHSP: a- If this assumption is correct; and b- When the decision is required by how this change should be incorporated within the Settlement Calendar |  | Anna Millar | Elexon | Code Body | 2023-10-25 | Acknowledge​​ | This detail will need to be discussed but we assume that ELEXON will create the DF Calendar once the Master Settlement Timetable has been agreed.
TDC-027 | Transition to New Settlement Timetable Proposal | 4.2 | It is important for the Participant Readiness assessments to ask what performance participants expect to be so that this can be considered as part of the criteria. This should be discussed with Elexon’s assurance team and only plans over a certain performance at RF acceptable to take a “Go” cutover decision. |  | Anna Millar | Elexon | Code Body | 2023-10-25 | Acknowledge​​ | This needs to be discussed.
TDC-028 | Replacement RF Settlement Timetable Illustration |  | The illustration shows that in some months there will be multiple months reaching RF that are not in a logical order, such as in Jan 27 where RF runs will be issued for Dec 25, Jul 26 and Oct 26. This will put a huge resource issue on settlement teams and could resut in large reconciliations and use of system bills for some suppliers. Credit cover requirements could also be massively increased for outstanding months after more recent months have reached RF. | Please see 'Alternative' attached spredsheet tab. | Mark Jones | SSE Energy Supply | I&C Supplier | 2023-10-25 | Acknowledge​​ | The proposal in you illustration does not reslove the issue you identify as earlier date will still have the RF Runs for earlier Settlement Dates occuring after the Settlement Dates where RF has been moved. The proposal also creates issues with the volumes of RF Runs occuring in the same period. This is likely to impact cashflow even more that the proposal we a putting forward
TDC-029 | Replacement RF Settlement Timetable Illustration |  | The illustration shows that some later settlement months will be settled on RF before earlier settled months are settled on RF. An example of this is Dec 25 which will have RF in Jan 27 , whereas May 26 will have its RF in Nov 26. This could cause issues for settlement processes and systems. | Please see 'Alternative' attached spredsheet tab. | Mark Jones | SSE Energy Supply | I&C Supplier | 2023-10-25 | Acknowledge​​ | See Response above.
TDC-030 | Replacement RF Settlement Timetable Illustration |  | There is a statement in the diagram that RF for settlements months from March 26 onwards will be shortened to 7 months. This seems to be based on a big assumption that a majority of electricity will be being settled in the new MHHS regime by that point. However, some suppliers may decide to migrate their customers later on in the migration window which could lead to big discrepancies and potential disputes as a large amount of NHH settled electricity will have a 7 month cut-off. | Please see 'Alternative' attached spredsheet tab. | Mark Jones | SSE Energy Supply | I&C Supplier | 2023-10-25 | Acknowledge​​ | The assumption may not be correct but that is why the monitoring proposed will be put in place to inform the decsion to move the RF Runs to 7 Months.
TDC-031 | Transition to New Settlement Timetable Proposal | General Comment | It is our view that changing the settlement timetables for settlement dates prior to M16 will add further complexity and overhead for all industry particpants at a time when there will already be heightened activity to support the MHHS changes. We therefore see limited benefits, if any, in changing the settlement calendar for any pre-M16 settlement days at a time when industry resources should be fully focused on the effective management of the migration activity. | 14 month settlement window should be retained for all pre-M16 settlement days. | Stephen McLaughlin | ScottishPower Energy Retail | Supplier | 2023-10-25 | Acknowledge​​ | The proposal is designed to limit the Run off for leagacy Settlement Dates. If the RF Runs is still at 14 Months on the day prior to M16 then the Run Off will complete 14 Months later requireing Suppliers to keep redundant sytems stood up to provide data for those Settlement Runs
TDC-032 | Transition to New Settlement Timetable Proposal | 4.2 | "It should be noted that once the RF dates are completed, for pre M16 Settlement Dates, revised data will not be available for non-migrated MPANs. Hence, the data for these MPANs will be crystallised at RF." In our view it's not acceptable to restrict the ability to correct data post the RF run to just those sites that have been migrated by the settlement date. We believe that this presents a disproportionate financial risk, particularly for Suppliers unable to participate in SIT, and it should be left to each Supplier to determine if they wish to retain their legacy systems to support the correction of data for non-migrated sites up to the DF run for each pre-M16 settlement day. | To support the equitable treatment of migrated and non-migrated MPANs prior to the M16 date, the ability to correct the data for all MPANs up to the DF run date should be possible. | Stephen McLaughlin | ScottishPower Energy Retail | Supplier | 2023-10-25 | Accepted ​​ | The wording has been ameneded to note that some Suppliers may wish to keep systems stood up for this purpose.
TDC-033 | Transition to New Settlement Timetable Proposal | 5 | Step 3 - M16 Monitoring Checkpoint - If the decision is taken to progress with these changes to the settlement calendar then, in addition to considering the volume of actual consumption data that is being submitted to settlements, this monitoring process also needs to consider if the proportional split of MPANs and meter types that have been migrated (smart, legacy and advanced meters) accurately reflects the deployed metering estate. | Clarity needs to be provided on when, and how, the monitoring criteria will be agreed by Industry. | Stephen McLaughlin | ScottishPower Energy Retail | Supplier | 2023-10-25 | Acknowledge​​ | The monitoring will look at how the migration is progressing. It has been agreed that the go/ no go criteria be set nearer the time when more is understood.
MHHS-DEL1843-Transition Design Tranche 2 Consultation Comments Log

## Control Sheet (hidden)
Aretfact Name
Transition to New Settlement Timetable Proposal
Replacement RF Settlement Timetable Illustration
Master Settlement Timetable Example
Master Settlement Timetable Example Replacements

## Sheet1
Triage status​ | Description​​
Accepted ​​ | Comment has been accepted and change has been made to Transition Design
Rejected​​ | Comment reject - No change will be made to Transition Design
Acknowledge​​ | Comment is not related to the Transition Design artefacts but may be picked up in other workstreams or further clarification, will be provided to the comment raiser.​​​
Requires further clarification with PP​​ | Comment is not fully understood by the Transition Design team and requires clarification with the comment raiser.​​​
Clarification Provided​​ | No change made - clarification is provided to respond to reviewers comment​​
Triage response​ reason​ | Triage clarification response​​
Out of Scope ​​ | Outside of Design and/or Programme Scope
Minor Change relating to code ​​ | Small change required to the code drafting content​
Major Change relating to code ​​ | Large change required to the code drafting content​

## Guidance (hidden)
Guidance Sheet
MHHS-DELXXX Consolidated Code Artefacts Consultation Log

## Control (hidden)
Status
Submitted
Accepted
Rejected
Action
Requires Further Clarification
Provide comment owner with clarification
Cosmetic | Formatting and typos
Minor | Minor change relating to code
Major | Major change relating to code
Change request | change request to MHHS Design
Documents
BSCP700 - Unmetered Suppliers Data Services / UMSDS
BSCP701 - Smart Data Collection / SDS
BSCP702 - Advanced Data Collection / ADS
BSCP70x - Unmetered Supplies Operations (UMSO)
BSCP601
BSC Section K
BSC Section J - Party Agents and Qualification under the Code
BSC Section L - Metering
BSC Code of Practice 1
BSC Code of Practice 2
BSC Code of Practice 3
BSC Code of Practice 4
BSC Code of Practice 5
BSC Code of Practice 6
BSC Code of Practice 7
BSC Code of Practice 8
BSC Code of Practice 9
BSC Code of Practice 10
REC - Schedule 13 Transfer of Consumer Data
REC - Schedule 14 Metering Operations
REC - Consolidated Metering Code of Practice
Constituency
Central Party
Code Body
DNO
I&C Supplier
iDNO
In-House Supplier Agent
Independent Agent
Large Supplier
Medium Supplier
Small Supplier
Other MHHS Participant
Software Provider