## Introduction
MHHS-DEL1165 MHHS Participant Checklist
The Programme has created this Participant Checklist to provide participants with information on Programme requests for review and engagement. The checklist includes information on: · Consultations · Assurance activities · Programme Participant Information Requests (PPIR) · Artefact releases · Key deadlines and dates
This checklist is frequently reviewed to provide the latest view of Programme requests, although there will be some occasions where an item is added at short notice.
All items in this checklist will be communicated in our weekly Programme newsletter (The Clock) and in the majority of cases, via email to the Programme Principal Contacts and/or relevant participant groups (e.g., Advisory or Working Groups).
If you have any questions about this document, please get in touch with the PMO team by emailing PMO@mhhsprogramme.co.uk

## Participant Checklist
Workstream | Document / Artefacts | Version | Target Audience | Working Group | Approval Forum | Estimated Consultation Start Date | Consultation Timeline | Due Date | Status | Location: MHHS Website | Location: Collaboration Base | Note
Ofgem PPIR | Ofgem PPIR: MHHS Cost Analysis | n/a | All PPs | n/a | n/a | 2024-05-24 | 6 Working Weeks | 2024-07-05 | Open | Planning --> Ofgem PPIR | Planning --> Ofgem PPIR
CR45 PPIR | CR45 PPIR | n/a | All PPs | n/a | CB | 2024-06-11 | 10 Working Days | 2024-06-24 | Open | Programme Change Control --> PPIR | Programme Change Control --> PPIR
Transition: Elexon PPIR | Elexon PPIR: DTN File Numbering during Transition | n/a | All PPs | TORWG | n/a | 2024-06-13 | 4 Weeks | 2024-07-11 | Open | Transition --> Elexon Programme Participant Information Request: DTN File Numbering during Transition | Transition --> Elexon Programme Participant Information Request: DTN File Numbering during Transition
Migration | Migration Framework Consultation 2 | 0.1 | All PPs, particularly SIT PPs | MWG | MCAG | 2024-06-13 | 10 Working Days | 2024-06-27 | Open | Migration --> MHHS Migration Framework | Migration --> MHHS Migration Framework
Non-SIT LDSO | Non-SIT LDSO Non-Functional and Operational Pre-Integration Testing (PIT) Approach and Plan | n/a | Non-SIT LDSOs | QWG | QAG | 2024-06-14 | 10 Working Days | 2024-07-01 | Open | PIT | PIT
Qualification | End-to-End Sandbox Guidance | TBC | All PPs | QWG | QAG | 2024-06-21 | 10 Working Days | 2024-07-05 | Open | Qualification --> End-to-End Sandbox Guidance | Qualification --> End-to-End Sandbox Guidance
Transition | Test Population Activity: Population of Meter Location and Number of Displayed Register Digits | n/a | MEMs | DCWG | MCAG | 2024-06-21 | 10 Working Days | 2024-07-05 | Open | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Migration | Migration Contact Nominations Request | n/a | Suppliers | MWG | MCAG | 2024-06-21 | 10 Working Days | 2024-07-05 | Open | MHHS Migration Contact Nomination Form | MHHS Migration Contact Nomination Form
Code | Consistency Check Consultation (All Codes) | n/a | All PPs | CDWG | CCAG | 2024-06-24 | 10 Working Days | 2024-07-12 | Open | Code --> Code Artefacts --> Code Artefacts Consistency Check | Code --> Code Artefacts --> Code Artefacts Consistency Check
DIP | Code of Connection Consultation | TBC | All PPs | SDWG | DAG | 2024-07-01 | 10 Working Days | 2024-07-12 | Open | Not yet available | Not yet available
Testing | SIT Operational Test Scenario and Test Case Delivery Theme 3 | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-07-15 | 10 Working Days | 2024-07-22 | Upcoming | Not yet available | Not yet available
Qualification | Qualification Approach & Plan Consultation | v3.0 | All PPs | QWG | QAG | 2024-07-08 | 10 Working Days | 2024-07-19 | Upcoming | Not yet available | Not yet available | Dependent on SIT Non-Functional artefacts
Qualification | Qualfication Approach & Plan: Annex 1 Non-SIT LDSOs Consultation | TBC | Non-SIT LDSOs | QWG | QAG | 2024-07-08 | 10 Working Days | 2024-07-19 | Upcoming | Not yet available | Not yet available | Dependent on SIT Non-Functional artefacts
Qualification | Qualfication Approach & Plan: Annex 2 Non-SIT Supplier & Agents Consultation | TBC | Non-SIT Suppliers & Agents | QWG | QAG | 2024-07-08 | 10 Working Days | 2024-07-19 | Upcoming | Not yet available | Not yet available | Dependent on SIT Non-Functional artefacts
Qualfication | LDSO Test Data Plan Consultation | TBC | All PPs | QWG | QAG | 2024-07-08 | 10 Working Days | 2024-07-19 | Upcoming | Not yet available | Not yet available
Qualfication | Qualification Assessment Document Consultation | TBC | All PPs | QWG | QAG | 2024-07-08 | 10 Working Days | 2024-07-19 | Upcoming | Not yet available | Not yet available
Qualification | Self Qualification AssesSment Document | TBC | New Entrant Data Services | QWG | QAG | 2024-07-08 | 10 Working Days | 2024-07-19 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Approach and Plan (Non-functional and Operational) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-07-01 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Requirements to Test Traceability Matrix (Non-functional and Operational) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-07-12 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Test Scenarios (Non-functional and Operational) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-07-12 | Upcoming | Not yet available | Not yet available
Migration | Migration Framework Consultation 2 Assurance Review | 0.1 | All PPs | MWG | MCAG | 2024-07-18 | 5 Working Days | 2024-07-25 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | Programme participants issue draft-PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-07-26 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | QT Test Plan including draft QT RTTM submission – Non-Functional and Operational | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-08-16 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Execution (Functional and Migration) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-08-30 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | Programme participants issue final PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-08-30 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | PIT Requirements to Test Traceability Matrix (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-09-27 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | PIT Test Scenarios (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-09-27 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | PIT Requirements to Test Traceability Matrix (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-09-27 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | PIT Test Scenarios (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-09-27 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Execution (Non-functional and Operational) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-09-30 | Upcoming | Not yet available | Not yet available
Non-SIT LDSO QT | Programme participants issue final PIT Test Completion Report (Non-functional and Operational) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-09-30 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | PIT Requirements to Test Traceability Matrix (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-11-29 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | PIT Test Scenarios (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-11-29 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | PIT Requirements to Test Traceability Matrix (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-11-29 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | PIT Test Scenarios (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-11-29 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | Programme participants issue draft-PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-11-29 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | PIT Execution (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-12-20 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | PIT Execution (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-12-20 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | Programme participants issue final PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-12-20 | Upcoming | Not yet available | Not yet available
Wave 1 Qualification | Programme participants issue final PIT Test Completion Report (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-12-20 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | PIT Requirements to Test Traceability Matrix (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-01-31 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | PIT Test Scenarios (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-01-31 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | PIT Requirements to Test Traceability Matrix (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-01-31 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | PIT Test Scenarios (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-01-31 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | Programme participants issue draft-PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-01-31 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | PIT Execution (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-02-21 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | PIT Execution (Non-funcitonal and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-02-21 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | Programme participants issue final PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-02-21 | Upcoming | Not yet available | Not yet available
Wave 2 Qualification | Programme participants issue final PIT Test Completion Report (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-02-21 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | PIT Requirements to Test Traceability Matrix (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-03-31 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | PIT Test Scenarios (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-03-31 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | PIT Requirements to Test Traceability Matrix (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-03-31 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | PIT Test Scenarios (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-03-31 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | Programme participants issue draft-PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-03-31 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | PIT Execution (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-04-18 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | PIT Execution (Non-funcitonal and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-04-18 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | Programme participants issue final PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-04-18 | Upcoming | Not yet available | Not yet available
Wave 3 Qualification | Programme participants issue final PIT Test Completion Report (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-04-18 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | Programme participants issue draft-PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-05-30 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | PIT Execution (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-06-20 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | PIT Execution (Non-funcitonal and Operational) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2025-06-20 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | Programme participants issue final PIT Test Completion Report (Functional and Migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-06-20 | Upcoming | Not yet available | Not yet available
Wave 4 Qualification | Programme participants issue final PIT Test Completion Report (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2025-06-20 | Upcoming | Not yet available | Not yet available
Testing | E2E Test Strategy Refresh Assurance Review | TBC | All PPs | SITWG, QWG, NFWG | SITAG | TBC | TBC | TBC | Upcoming | Not yet available | Not yet available
Qualification | Non-SIT LDSO Qualification Testing Approach and Plan Template completion | n/a | Non-SIT LDSOs | QWG | QAG | 2024-05-24 | n/a | 2024-06-28 | Closed | Qualification | Qualification
Qualification | Non-SIT Supplier Meter Point Administration Number (MPAN) Data Request for Qualification Testing | n/a | Non-SIT Suppliers | QWG | QAG | 2024-06-19 | 7 Working Days | 2024-06-28 | Closed | Qualification --> MPAN Data Request | Qualification --> MPAN Data Request
DIP | Data Integration Platform (DIP) Simulator updates for Interim Releases 8 & 8.1 | 8 & 8.1 | All PPs | SDWG | DAG | 2024-06-28 | n/a | 2024-06-28 | Closed | Not yet available | Not yet available
Qualification | Wave Allocation | n/a | All PPs | QWG | QAG | 2024-06-28 | n/a | 2024-06-28 | Closed | Not yet available | Not yet available
Non-SIT LDSO QT | QT Test Plan including draft QT RTTM submission (functional and migration) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-06-28 | Closed | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Test Scenarios (functional and migration) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-06-03 | Closed | Not yet available | Not yet available
Non-SIT LDSO QT | PIT Requirements to Test Traceability Matrix (functional and migration) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-06-03 | Closed | Not yet available | Not yet available
Testing | Non-SIT Supplier and Agent Qualification Test Data Approach and Plan | 0.5 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-06-06 | 10 Working Days | 2024-06-21 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data and Approach | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data and Approach
Qualification | Non-SIT Supplier & Agent Qualification Testing Test Data Approach | TBC | Non-SIT Suppliers & Agents | QWG / SAQTSG | QAG | 2024-06-10 | 10 Working Days | 2024-06-17 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data Approach | Qualification --> Non-SIT Suppliers & Agents Qualification Test Data Approach
Testing | SIT Non-Functional Test Scenario and Test Cases Delivery Theme 3 | n/a | SIT PPs | NFTWG | SITAG | 2024-06-10 | 5 Working Days | 2024-06-17 | Closed | Testing --> SIT --> SIT Non-Functional | Testing --> SIT --> SIT Non-Functional
Qualification | Non-SIT Supplier & Agent Qualification Testing Migration Test Scenarios and Test Cases | v0.1 | Non-SIT Suppliers & Agents | QWG / SAQTSG | QAG | 2024-06-03 | 10 Working Days | 2024-06-14 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios
Design | Design Interim Release 8.1 Artefacts | IR8.1 | All PPs | n/a | n/a | 2024-06-12 | n/a | 2024-06-12 | Closed | Design --> Baselined Design Artefacts --> Baselined Design Artefacts Interim Release 8.1 | Design --> Baselined Design Artefacts --> Baselined Design Artefacts Interim Release 8.1
Testing | SIT Functional Cycle 2 Test Scenarios and Cases – Alignment with Interim Release 7 (IR7) | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-05-20 | 15 Working Days | 2024-06-10 | Closed | Testing --> SIT Functional --> SIT Functional Test Scenarios and Test Cases ---> SIT Functional Test Scenarios Cycle 2 | Testing --> SIT Functional --> SIT Functional Test Scenarios and Test Cases ---> SIT Functional Test Scenarios Cycle 2
Testing | SIT Operational Test Scenario and Test Cases Theme 2 Industry Review | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-06-04 | 5 Working Days | 2024-06-11 | Closed | Testing --> SIT --> SIT Operational | Testing --> SIT --> SIT Operational
Testing | Environments Approach & Plan assurance review | v2.15 | All PPs | EWG | SITAG | 2024-05-28 | 9 Working Days | 2024-06-07 | Closed | Testing --> Environment Approach & Plan | Testing Overview --> Environment Approach & Plan
Testing | SIT Operational Test Scenario and Test Cases Theme 1 Industry Review | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-05-28 | 5 Working Days | 2024-06-04 | Closed | SIT --> Operational | SIT --> Operational
Testing | SIT Non-Functional Test Scenarios and Test Cases Theme 2 Industry Review | n/a | SIT PPs | NFTWG | SITAG | 2024-05-20 | 5 Working Days | 2024-05-29 | Closed | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases
Testing | SIT Non-Functional Test Tooling Queries - Theme 2 | n/a | SIT PPs | NFTWG and SITWG | SITAG | 2024-05-22 | 3 Working Days | 2024-05-24 | Closed | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases | Testing --> SIT --> SIT Non-Functional --> Test Scenarios and Test Cases
CR44 PPIR | CR44 PPIR | n/a | All PPS | n/a | CB | 2024-05-17 | 5 Working Days | 2024-05-24 | Closed | Change Control Documents | Change Control Documents
Qualification | Qualification Assessment Document Guidance Informal Consultation | v1.1 | All PPs | QWG | QAG | 2024-05-07 | 10 Working Days | 2024-05-21 | Closed | Qualification --> Qualification Assessment Document | Qualification --> Qualification Assessment Document
Non-SIT LDSO Qualification | Confirm whether placing reliance on Non-Functional and/or Operational Testing | n/a | Non-SIT LDSOs | QWG | QAG | 2024-05-01 | n/a | 2024-05-17 | Closed | N/A | N/A
Testing | SIT Migration Participant Readiness Reporting | n/a | SIT PPs | SITWG | SITAG | 2024-05-07 | 5 Working Days | 2024-05-15 | Closed | SIT --> SIT Migration --> SIT Migration Participant Readiness Reporting | SIT --> SIT Migration --> SIT Migration Participant Readiness Reporting
Testing | SIT Non-Functional Test Scenario and Test Cases Delivery Theme 1 | n/a | SIT PPs | NFTWG | SITAG | 2024-05-02 | 5 Working Days | 2024-05-10 | Closed | Testing --> SIT --> SIT Functional test scenarios and test cases --> SIT Non-Functional theme 1 | Testing --> SIT Non-Functional -- > SIT Non-Functional test scenarios and test cases --> SIT Non-Functional Theme 1 - DIP and Helix
Transition | M10 M11 Cutover Plan Consultation | v0.1 | All PPs | TORWG | MCAG | 2024-04-23 | 10 Working Days | 2024-05-07 | Closed | Transition --> M10 / M11 Cutover Plan | Transition --> M10 / M11 Cutover Plan
Qualification | Qualification Approach & Plan: Annex 1 Non-Functional and Operational Testing Updates Consultation | v1.1 | Non-SIT LDSOs | QWG | QAG | 2024-04-23 | 10 Working Days | 2024-05-03 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Non-Systems Integration Testing (SIT) Licensed Distribution System Operators (LDSOs) Migration Test Scenarios & Test Cases Consultation | n/a | Non-SIT LDSOs | QWG | QAG | 2024-04-22 | 10 Working Days | 2024-05-03 | Closed | Qualification --> Non-SIT LDSO Test Cases and Test Scenarios | Qualification --> Non-SIT LDSO Test Cases and Test Scenarios
Migration | Migration Framework Assurance Meeting | n/a | All PPs | MWG | MCAG | 2024-04-19 | 10 Working Days | 2024-04-26 | Closed | N/A | N/A
Data Cleanse Activities | LDSOs issue a self-declaration to the Programme that they have completed population activities set out within section “6.2.1.4 Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’” | n/a | LDSOs | n/a | n/a | 2024-04-08 | n/a | 2024-04-29 | Closed | N/A | N/A
Qualification | Pre-Qualification Submission | n/a | Non-SIT Suppliers & Agents | QWG | QAG | 2024-02-05 | 60 Working Days | 2024-04-26 | Closed | Qualification --> Pre-Qualification Submission | Qualification --> Pre-Qualification Submission
Non-SIT LDSO Qualification | PIT Approach and Plan (functional and migration) | n/a | Non-SIT LDSOs | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 1 Qualification | PIT Approach and Plan (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 2 Qualification | PIT Approach and Plan (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 3 Qualification | PIT Approach and Plan (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 4 Qualification | PIT Approach and Plan (functional and migration) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 1 Qualification | PIT Approach and Plan (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 2 Qualification | PIT Approach and Plan (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 3 Qualification | PIT Approach and Plan (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Wave 4 Qualification | PIT Approach and Plan (Non-functional and Operational) | n/a | Non-SIT Suppliers & Agents | QWG | QAG | n/a | n/a | 2024-04-26 | Closed | Pre-Integration Testing (PIT) | Pre-Integration Testing (PIT)
Data | 6.2.1.4 Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’” | n/a | LDSOs | DWG | SITAG | 2024-04-08 | n/a | 2024-04-29 | Closed | Transition --> Data Cleanse Plan | Transition --> Data Cleanse Plan
Code | Topic Area Mop-up 2 (All Codes) Assurance Review | n/a | All PPs | CDWG | CCAG | 2024-04-10 | 8 Working Days | 2024-04-22 | Closed | Code --> Code artefacts --> Mop Up 2 | Code --> Code Artefacts --> Mop Up 2
Qualification | Qualification Non-SIT Suppliers & Agents Test Cases & Test Scenarios Batch 2 | v0.2 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-04-05 | 10 Working Days | 2024-04-19 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios
Testing | SIT Operational Test Approach & Plan Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-15 | 5 Working Days | 2024-04-19 | Closed | Testing --> SIT --> SIT Operational | Not yet available
Testing | SIT Operational Test Data Approach & Plan Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-15 | 5 Working Days | 2024-04-19 | Closed | Testing --> SIT --> SIT Operational | Not yet available
Testing | SIT Non-Functional Test Data Approach and Plan Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-11 | 5 Working Days | 2024-04-17 | Closed | Testing --> SIT --> SIT Non-Functional --> Test Data A&P | Testing --> SIT --> SIT Non-Functional --> Test Data A&P
Testing | SIT Non-Functional Test Approach and Plan Industry Assurance Review | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-04-11 | 5 Working Days | 2024-04-17 | Closed
Testing | Non-SIT LDSO Test Data Approach and Plan Consultation | v0.8 | Non-SIT LDSOs | QWG | QAG | 2024-03-28 | 10 Working Days | 2024-04-15 | Closed | Qualification --> Non-SIT LDSO Approach & Plan | Qualification --> Non-SIT LDSO Approach & Plan
Testing | SIT Operational Test Approach & Plan Industry Consultation | TBC | SIT PPs | SITWG | SITAG | 2024-03-27 | 10 Working Days | 2024-04-09 | Closed | Not yet available | Not yet available
Testing | SIT Operational Test Data Approach & Plan Industry Consultation | TBC | SIT PPs | SITWG | SITAG | 2024-03-27 | 10 Working Days | 2024-04-09 | Closed | Not yet available | Not yet available
Migration | Migration Framework Consultation 1 | TBC | All PPs, particularly SIT PPs | MWG | MCAG | 2024-03-18 | 13 Working Days | 2024-04-08 | Closed | Migration & Transition --> MHHS Migration Framework | Migration & Transition --> MHHS Migration Framework
Testing | SIT Non-Functional Test Data Approach and Plan Industry Consultation | 0.2 | SIT PPs | SITWG, NFWG | SITAG | 2024-03-26 | 5 Working Days | 2024-04-05 | Closed | Not yet available | Not yet available
Qualification | Annex 2: Qualification Approach & Plan: Non-SIT Supplier & Agent MHHS Qualification Testing Approach Consultation | v0.5 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-03-18 | 10 Working Days | 2024-04-05 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Qualification | Non-SIT Supplier & Agent Qualification Testing Test Scenarios Batch 1 | v0.2 | Non-SIT Suppliers & Agents | QWG | QAG | 2024-03-18 | 10 Working Days | 2024-04-05 | Closed | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios | Qualification --> Non-SIT Suppliers & Agents Qualification Testing Test Scenarios
Design | Design Interim Release 8 published | IR8 | All PPs | n/a | n/a | n/a | n/a | 2024-04-03 | Closed | Not yet available | Not yet available
Testing | SIT Non-Functional Test Approach and Plan Industry Consultation | TBC | SIT PPs | SITWG, NFWG | SITAG | 2024-03-18 | 10 Working Days | 2024-04-02 | Closed | Timeline adjusted as agreed at SITAG on 21-Feb-24 | Not yet available
Testing | Environment Approach & Plan Industry Consultation | 2.12 | All PPs | EWG | SITAG | 2024-03-14 | 5 Working Days | 2024-03-21 | Closed | Testing --> Environment Approach & Plan | Testing --> Environment Approach & Plan
Testing | SIT Migration Theme 3 - Import/Export MPANs & Exception Handling | TBC | SIT PPs | SITWG | SITAG | 2024-03-13 | 5 Working Days | 2024-03-20 | Closed | Testing --> SIT | Testing --> SIT --> SIT Migration Test Scenarios & Test Cases --> SIT Migration Theme 3
N/A | MHHS PPIR: Use of MDR Function - Supporting Assumptions for DCC Capacity Planning | N/A | All Suppliers | n/a | n/a | 2024-03-06 | 10 Working Days | 2024-03-19 | Closed | Not on the website | Not on the Collaboration Base
N/A | MHHS Licence Review Consultation | n/a | All PPs | N/A | CCAG | 2024-01-31 | 30 Working Days | 2024-03-13 | Closed | Code --> MHHS Supply, Distribution and Transmission Licence Review | Code Homepage --> MHHS Supply, Distribution and Transmission Licence Review
Code | Topic Area Mop-up 2 (All Codes) Consultation | n/a | All PPs | CDWG | CCAG | 2024-02-19 | 10 Working Days | 2024-03-11 | Closed | Code --> Code artefacts --> Mop Up 2 | Code --> Code artefacts --> Mop Up 2
Qualification | Non-SIT LDSO Test Scenarios & Test Cases Review | Multiple | Non-SIT LDSOs | QWG | QAG | 2024-02-26 | 9 Working Days | 2024-03-08 | Closed | Not on the website | Qualification --> Non-SIT LDSO Qualification
Qualification | Qualification Assessment Document Consultation | TBC | All PPs | QWG | QAG | 2024-02-16 | 10 Working Days | 2024-03-01 | Closed | Testing --> Qualification | Testing --> Qualification --> Qualification Assessment Document
Testing | SIT Functional Defect Management Approach and Plan released to participants | n/a | SIT PPs | SITWG | SITAG | 2024-02-29 | n/a | n/a | Closed | n/a | n/a
Testing | SIT Migration Theme 1 Test Scenarios and Cases – Further Uplifts | TBC | SIT PPs | SITWG | SITAG | 2024-02-13 | 10 Working Days | 2024-02-28 | Closed | Testing --> SIT--> SIT Migration | Testing --> SIT --> SIT Migration Test Scenarios & Test Cases --> SIT Migration Theme 1
Testing | SIT Functional Readiness Report Template | n/a | SIT PPs | SITWG | SITAG | 2024-02-05 | 7 Working Days | 2024-02-14 | Closed | Testing --> SIT | Testing --> SIT--> SIT Functional Participant Readiness Report
Qualification | Qualification Approach & Plan | v1.1 | All PPs | QWG | QAG | 2024-01-31 | 10 Working Days | 2024-02-14 | Closed | Qualification --> Qualification Approach & Plan | Qualification --> Qualification Approach & Plan
Testing | CIT Test Completion Report Template - for completion | n/a | SIT PPs | SITWG | SITAG | 2024-02-06 | 5 Working Days | 2024-02-13 | Closed | Not yet available | Not yet available
Testing | SIT Migration Theme 1 Test Scenarios and Cases - Industry Review | n/a | SIT PPs | SITWG | SITAG | 2024-02-05 | 5 Working Days | 2024-02-12 | Closed | Not yet available | Not yet available
Migration | Data Cleanse Plan Consultation | v1.1 | All PPs | DCWG | MCAG | 2024-01-29 | 10 Working Days | 2024-02-09 | Closed | Migration --> Data Cleanse Plan | Migration --> Data Cleanse Plan
Design | Design Interim Release 5.4 published | n/a | All PPs | n/a | n/a | 2024-02-07 | n/a | n/a | Closed | Design --> Red-lined Design Artefacts --> Interim Release 5.4 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 5.4 (Red-lined versions)
Testing | SIT Functional Test Scheduling / Prioritisation released to participants | n/a | SIT PPs | SITWG | SITAG | 2024-02-09 | n/a | n/a | Closed | Not yet available | Not yet available
Testing | SIT Functional Readiness Report Template - released to participants | v1.0 | SIT PPs | SITWG | SITAG | 2024-02-05 | n/a | n/a | Closed | Not yet available | Not yet available
Design | Design Interim Release 7 published | n/a | All PPs | n/a | n/a | 2024-01-31 | n/a | 2024-01-31 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 7 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 7 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions)
Code | Topic Area Mop-up 1 (All Codes) Assurance Review | n/a | All PPs | CDWG | CCAG | 2024-01-17 | 10 Working Days | 2024-01-31 | Closed | Code --> Code Artefacts | Code --> Code Artefacts
Transition and Operational Readiness | MHHS Service Management Strategy Consultation | v0.1 | All PPs | TORWG | TMAG | 2024-01-15 | 10 Working Days | 2024-01-26 | Closed | Migration --> Migration Overview --> MHHS Service Management Strategy Consultation --> MHHS Service Management Strategy / MHHS Service Management Strategy Comments Log | Migration --> Service Management Strategy --> MHHS Service Management Strategy v0.1 / MHHS Service Management Strategy Comments Log
Governance - Change Request | CR040: Change to NFR E2E1009 for DNO and iDNO roles | n/a | All PPs | n/a | DAG | 2024-01-10 | n/a | 2024-01-24 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG for Impact Assessment
Governance - Change Request | CR041: Change the format of Market Participant Code from Char(1) to Char(2) | n/a | All PPs | n/a | DAG | 2024-01-10 | n/a | 2024-01-24 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG for Impact Assessment
Qualification | Placing Reliance Form Submission | n/a | Non-SIT LDSOs | QWG | TMAG | n/a | n/a | 2023-01-05 | Closed | Qualification | Qualification
Design | MHHS Impacts to Data Transfer Network (DTN) flows Consultation | Multiple | All PPs | n/a | DAG | 2023-12-13 | 15 Working Days | 2023-01-05 | Closed | Design --> Baselined Design Artefacts --> MHHS Impacts to DTN Flows | Design --> Baselined Design Artefacts --> MHHS Impacts to DTN Flows
Code | Topic Area Mop-up (All Codes) | n/a | All PPs | CDWG | CCAG | 2023-11-30 | 23 Working Days | 2024-01-02 | Closed | Code --> Code artefacts --> Mop Up 1 | Code --> Code artefacts --> Mop Up 1
Code | Transition Text (REC & BSC) and Interfaces / Data Spec (REC & BSC) Assurance Review | Multiple | All PPs | CDWG | CCAG | 2023-11-22 | 10 Working Days | 2023-12-13 | Closed | Code --> Code artefacts --> Tranche 4 | Code --> Code artefacts --> Tranche 4
Migration | M15 Acceptance Criteria | 0.1 | All PPs | MWG | TMAG | 2023-11-22 | 10 Working Days | 2023-12-06 | Closed | Migration | Migration
Testing | CIT Test Cases, Batch 3 (Interval 5 & 6) Assurance Review | TBC | SIT PPs | SITWG | TMAG | 2023-11-27 | 5 Working Days | 2023-12-01 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Migration Test and Test Data Approach & Plan Assurance Review | TBC | SIT PPs | SITWG | TMAG | 2023-11-21 | 5 Working Days | 2023-11-27 | Closed | Testing --> SIT--> SIT Migration | Testing --> SIT--> SIT Migration
Testing | CIT Test Cases, Batch 3 (Interval 5 & 6) Consultation | n/a | SIT PPs | SITWG | TMAG | 2023-11-09 | 12 Working Days | 2023-11-21 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Migration Test and Test Data Approach & Plan Industry Consultation | v0.2 | SIT PPs | SITWG | TMAG | 2023-11-02 | 10 Working Days | 2023-11-15 | Closed | Testing --> SIT | Testing --> SIT
Design | Interim Release 6 Release | IR6 | All PPs | n/a | n/a | n/a | n/a | 2023-11-01 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 6 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 6 (Red-lined versions)
Code | Interfaces / Data Spec (REC & BSC) Consultation | n/a | All PPs | CDWG | CCAG | 2023-10-11 | 15 Working Days | 2023-11-01 | Closed | Code --> Code artefacts --> Tranche 4 | Code --> Code artefacts --> Tranche 4
Code | Transition Text (REC & BSC) Consultation | n/a | All PPs | CDWG | CCAG | 2023-10-11 | 15 Working Days | 2023-11-01 | Closed | Code --> Code artefacts --> Tranche 4 | Code --> Code artefacts --> Tranche 4
Governance - Change Request | CR032: Change to interface MHHS-IF-165 P0210 TUoS reporting | n/a | All PPs | n/a | DAG | 2023-10-13 | n/a | 2023-10-30 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG for Impact Assessment
Testing | CIT Test Cases, Batch 2 (Interval 3 & 4) Assurance Review | n/a | SIT PPs | SITWG | TMAG | 2023-10-23 | 5 Working Days | 2023-10-27 | Closed | Testing --> SIT | Testing --> SIT
Design | Programme Participant Information Request: UTC vs Clock | n/a | All PPs | DRG | DAG | 2023-10-16 | 10 Working Days | 2023-10-30 | Closed | N/A | N/A
Transition Design | Settlement Timetable Transition Solution Consultation | TBC | All PPs | MTDSG | DAG | 2023-10-11 | 10 Working Days | 2023-10-25 | Closed | Design --> Transition Design | Design --> Transition Design
Code | REC & BSC Qualification / Governance and Migration Code Artefacts Assurance Review | n/a | All PPs | CDWG | CCAG | 2023-09-29 | 16 Working Days | 2023-10-20 | Closed | Code --> Code artefacts --> Tranche 3 | Code --> Code artefacts --> Tranche 3
Testing | Environment Approach & Plan Assurance Review | v2.7 | All PPs | EWG | TMAG | 2023-10-16 | 5 Working Days | 2023-10-20 | Closed | Testing Overview --> Environment Approach & Plan | Testing Overview --> Environment Approach & Plan
Governance - Change Request | CR031: Amending Transition Design Milestone Description and Delivery Date | n/a | All PPs | n/a | DAG | n/a | n/a | n/a | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-23. Approved without IA due to low impact T2 milestone. Please view the Master Change Request dashboard tab for more information.
Design | Interim Release 6 Objection Cut-off | IR6 | All PPs | n/a | n/a | n/a | n/a | 2023-10-18 | Closed | n/a | n/a
Migration | Migration Thresholds | v0.1 | All PPs | MWG | TMAG | 2023-09-27 | 10 Working Days | 2023-10-11 | Closed | Migration --> Migration Thresholds | Migration --> Migration Thresholds
Design | Interim Release 5 Release | IR5 | All PPs | n/a | n/a | n/a | n/a | 2023-10-04 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 5 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions) | Design --> Red-lined Design Artefacts --> Interim Release 5 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions)
Planning | Readiness Assessment Three (RA3) | N/a | All PPs | n/a | PSG | 2023-09-05 | 15 Working Days | 2023-09-25 | Closed | Planning --> RA3 | Planning --> RA3
Design | Interim Release 5 Objection Cut-off | IR5 | All PPs | n/a | n/a | 2023-08-30 | n/a | 2023-09-20 | Closed | n/a | n/a
Testing | CIT Test Cases, Batch 1 (Interval 1 & 2) Assurance Review |  | SIT PPs | SITWG | TMAG | 2023-09-18 | 5 Working Days | 2023-09-22 | Closed | Shared via email | Shared via email
Code | Migration (REC & BSC) and Qualification Governance (REC & BSC) | n/a | All PPs | CDWG | CCAG | 2023-08-18 | 15 Working Days | 2023-09-08 | Closed | Code --> Code artefacts --> Tranche 3 | Code --> Code artefacts --> Tranche 3
Testing | SIT Functional Test Scenarios Assurance Review | v5.2.1 | SIT PPs | SITWG | TMAG | 2023-08-21 | 10 Working Days | 2023-09-05 | Closed | Testing --> SIT | Testing --> SIT
Testing | Test Data SFTP Guide | v1.0 | FTIG PPs | FTIG | FTIG | 2023-08-29 | 5 Working Days | 2023-09-05 | Closed | n/a | n/a
Design | Interim Release 4 Release | IR4 | All PPs | n/a | n/a |  | n/a | 2023-08-30 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 4 (Red-lined versions) | Design --> Red-lined Design Artefacts --> Interim Release 4 (Red-lined versions)
Design | MHHS Impacts to BSC Owned Data Flows | v0.5 | All PPs | n/a | DAG | 2023-08-14 | 10 Working Days | 2023-08-29 | Closed | Design --> Design Overview | Design
Code | Balancing and Settlement Code (BSC) Central Services Assurance Review | n/a | All PPs | CDWG | CCAG | n/a |  | 2023-08-25 | Closed | Code --> Code Artefacts --> Tranche 2 | Code --> Code Artefacts --> Tranche 2
Testing | Bilateral Data Sharing Agreement: Review and Signing (FTIG PPs) | v2.3 | FTIG PPs | n/a | n/a | n/a | n/a | 2023-08-25 | Closed | Testing --> Data | Testing --> Data
Testing | SIT CIT Test Scenarios Assurance Review | v5.2.2 | SITWG & TMAG Attendees | SITWG | TMAG | n/a | 5 Working Days | 2023-08-25 | Closed | Testing --> SIT | Testing --> SIT
Governance - Change Request | CR030: Introduction of Compressed Payloads into DIP Messages | n/a | All PPs | n/a | DAG | 2023-08-11 | 11 Working Days | 2023-08-25 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-25. Please view the Master Change Request dashboard tab for more information.
Governance - Change Request | CR029: DIP LDSO Interface Processing | n/a | All PPs | n/a | DAG | 2023-08-10 | 11 Working Days | 2023-08-24 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-24. Please view the Master Change Request dashboard tab for more information.
Governance - Change Request | CR028: Change to interface MHHS-IF-165 P0210 TUoS reporting | n/a | All PPs | n/a | DAG | 2023-08-10 | 11 Working Days | 2023-08-24 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents | Approved by DAG on 13-Sep-23. Please view the Master Change Request dashboard tab for more information.
Design | Interim Release 4 Objection Cut-off | IR4 | All PPs | n/a | n/a | n/a | n/a | 2023-08-16 | Closed | n/a | n/a
Testing | SIT Functional Test Approach & Plan (Assurance) | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-28 | 5 Working Days | 2023-08-04 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Functional Test Data Approach & Plan (Assurance) | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-28 | 5 Working Days | 2023-08-04 | Closed | Testing --> SIT | Testing --> SIT
Design | Interim Release 3 Release | IR3 | All PPs | n/a | n/a | n/a | n/a | 2023-08-02 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 3 (Red-lined versions). Design --> Baselined Design Artefacts (Clean versions) | Design --> Red-lined Design Artefacts --> Interim Release 3 (Red-lined versions). Design --> Baselined Design Artefacts (Clean versions)
Testing | SIT Component Integration Testing (CIT) Test Scenarios (Assurance) | v5.2 | All PPs, particularly SIT PPs | n/a | n/a | 2023-07-21 | 5 Working Days | 2023-07-28 | Closed | Testing --> SIT | Testing --> SIT
Governance - Change Request | CR027: DUoS E-Billing DIP message for MHHS issued for Impact Assessment | n/a | All PPs | n/a | DAG | 2023-07-13 | n/a | 2023-07-27 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Governance - Change Request | CR023: Standardisation of Interfaces within the Smart and Advanced Data Services Roles issued for Impact Assessment | n/a | All PPs | n/a | DAG | 2023-07-06 | n/a | 2023-07-21 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Testing | SIT Functional Test Approach & Plan | v0.2 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-07 | 10 Working Days | 2023-07-21 | closed | Testing --> SIT | Testing --> SIT
Testing | SIT Functional Test Data Approach & Plan | v0.2 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-07-07 | 10 Working Days | 2023-07-21 | Closed | Testing --> SIT | Testing --> SIT
Governance - Change Request | CR024: Data Item Names and Descriptions - Re-Issued for IA | n/a | All PPs | n/a | DAG | 2023-07-13 | n/a | 2023-07-20 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Testing | Environment Approach and Plan - CIT environments | v2.4 | All PPs, particularly SIT PPs | EWG | TMAG | 2023-07-07 | 5 Working Days | 2023-07-13 | Closed | Testing Overview --> Environment Approach & Plan | Testing Overview --> Environment Approach & Plan
Design | Interim Release 3 Objection Cut-off | IR3 | All PPs | n/a | n/a | n/a | n/a | 2023-07-12 | Closed | n/a | n/a
Code | Balancing and Settlement Code (BSC) Central Services Consultation | n/a | All PPs | CDWG | CCAG | 2023-06-21 | 15 Working Days | 2023-07-12 | Closed | Code --> Code Artefacts --> Tranche 2 | Code --> Code Artefacts --> Tranche 2
Testing | SIT Component Integration Testing (CIT) Test Approach & Plan (Assurance) | v0.5 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-30 | 5 Working Days | 2023-07-06 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Component Integration Testing (CIT) Test Data Approach & Plan (Assurance) | v0.5 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-30 | 5 Working Days | 2023-07-06 | Closed | Testing --> SIT | Testing --> SIT
Design | Interim Release 2 Release | IR2 | All PPs | n/a | n/a | n/a | n/a | 2023-07-05 | Closed | Design --> Red-lined Design Artefacts --> Interim Release 2 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions) | Design --> Red-lined Design Artefacts --> Interim Release 2 (Red-lined versions) OR Design --> Baselined Design Artefacts (Clean versions)
FTIG | Delivery Assurance Cohort Two Questionnaire Issued | n/a | All SIT volunteers with an MHHS role under the TOM who were not part of Cohort 1 | FTIG | N/A | 2023-06-16 | 11 Working Days | 2023-06-30 | Closed | Shared via email. Questions can be found Programme Information --> Delivery Assurance | Shared via email. Questions can be found Programme Information --> Delivery Assurance
DIP | Interface Code of Connection & PKI Policy (Assurance) | v0.7 | All PPs | SDWG | DAG | 2023-06-22 | 5 Working Days | 2023-06-28 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Migration | Data Cleanse Plan (Review 2) | v0.1 | All PPs | MWG | TMAG | 2023-06-09 | 10 Working Days | 2023-06-23 | Closed | Migration --> Data Cleanse Plan | Migration --> Data Cleanse Plan
Testing | Overarching Test Data Approach & Plan | v0.6 | All PPs | DWG | TMAG | 2023-06-19 | 5 Working Days | 2023-06-23 | Closed | Testing --> Data | Testing --> Data
Design | Interim Release 2 Objection Cut-off | IR2 | All PPs | n/a | n/a | n/a | n/a | 2023-06-23 | Closed | n/a | n/a
Testing | SIT Component Integration Testing (CIT) Test Approach & Plan | v0.4 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-09 | 10 Working Days | 2023-06-22 | Closed | Testing --> SIT | Testing --> SIT
Testing | SIT Component Integration Testing (CIT) Test Data Approach & Plan | v0.4 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-06-09 | 10 Working Days | 2023-06-22 | Closed | Testing --> SIT | Testing --> SIT
Code | Registration (REC & BSC) | n/a | All PPs | CDWG | CCAG | 2023-05-31 | 15 Working Days | 2023-06-21 | Closed | Code --> Code Artefacts --> Tranche 2 | Code --> Code Artefacts --> Tranche 2
FTIG | Delivery Assurance Cohort One Questionnaire Issued | n/a | Central Parties and Core Capability Providers, and SIT volunteers who are not dependent on the Placing Reliance Policy | FTIG | N/A | 2023-05-31 | 12 Working Days | 2023-06-16 | Closed | Shared via email. Questions can be found: Programme Information --> Delivery Assurance | Shared via email. Questions can be found: Programme Information --> Delivery Assurance
Testing | SIT Functional Test Scenarios | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-05-15 | 10 Working Days | 2023-05-30 | Closed | Testing --> SIT | Testing --> SIT
DIP | Code of Connection & PKI Policy Formal Review | v0.6 | All PPs | n/a | DAG | 2023-05-12 | 10 Working Days | 2023-05-25 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Testing | Overarching Test Data Approach & Plan | v0.5 | All PPs | DWG | TMAG | 2023-05-05 | 10 Working Days | 2023-05-22 | Closed | Testing --> Data | Testing --> Data
Migration | Data Cleanse Plan (Review 1) | n/a | All PPs | MWG | TMAG | 2023-05-04 | 10 Working Days | 2023-05-19 | Closed | Migration --> Data Cleanse Plan | Migration --> Data Cleanse Plan
Migration | Migration, Data Strategy and Cutover | v0.2 | All PPs | MWG | TMAG | 2023-05-04 | 10 Working Days | 2023-05-19 | Closed | Migration --> Migration, Data Strategy and Cutover | Migration --> Migration, Data Strategy and Cutover
DIP | Interface Code of Connection Informal Review | n/a | All PPs | n/a | DAG | 2023-05-03 | 5 Working Days | 2023-05-11 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
DIP | PKI Policy | n/a | All PPs | n/a | DAG | 2023-05-05 | 3 Working Days | 2023-05-11 | Closed | Programme Information --> Data Integration Platform (DIP) | Programme Information --> Data Integration Platform (DIP)
Design | Amended Design Documents | n/a | All PPs | n/a | DAG | 2023-04-14 | 16 Working Days | 2023-05-09 | Closed | n/a | n/a
Testing | SIT Component Integration Testing (CIT) Test Scenarios | v0.3 | All PPs, particularly SIT PPs | SITWG | TMAG | 2023-04-17 | 10 Working Days | 2023-05-02 | Closed | Testing --> SIT | Testing --> SIT
Design | Transition Design | Multiple | All PPs | MTDSG | DAG | 2023-04-14 | 10 Working Days | 2023-04-28 | Closed | Design --> Transition Design | Design --> Transition Design
Planning | CR022 Impact Assessment | n/a | All PPs | n/a | Change Board | 2023-04-06 | 13 Working Days | 2023-04-26 | Closed | Programme Information --> Programme Change Control | Programme Information --> Programme Change Control --> Change Control Documents
Testing | Qualification Approach & Plan | v0.1 | All PPs | QWG | TMAG | 2023-03-28 | 9 Workings Days | 2023-04-11 | Closed | Testing --> Qualification | Testing --> Qualification
Testing | Placing Reliance Policy Part 2 | v0.5 | All PPs | SITWG | TMAG | 2023-03-31 | 7 Working Days | 2023-04-11 | Closed | Testing --> Testing Overview | Testing landing page
Testing | Placing Reliance Policy Part 1 | v0.4 | All PPs | SITWG | TMAG | 2023-03-09 | 4 Working Days | 2023-03-14 | Closed | Testing --> Testing Overview | Testing landing page
Code | Data Services (BSC) and Metering Services (REC) | n/a | All PPs | CDWG | CCAG | 2023-02-14 | 20 Working Days | 2023-03-13 | Closed | Code --> Code Artefacts --> Tranche 1 | Code --> Code Artefacts --> Tranche 1
Design | Migration Design | Multiple | All PPs | MTDSG | DAG | 2023-02-14 | 10 Working Days | 2023-02-24 | Closed | Design --> Migration Design | Design --> Migration Design

## Master Change Request Dashboard
Date Raised | Change Request | CR Name | Advisory Group | Status | IA Issue Date | IA Deadline Date | Advisory Group Approval Decision | Target Implementation Date | Open/Closed | Comments
2024-06-01 | CR053 | ISD Publication Frequency Change |  | Awaiting Change Board validation |  |  |  |  | Open
2024-06-01 | CR052 | Amending the 'M7 SCR powers enabled' Milestone |  | Awaiting Change Board validation |  |  |  |  | Open
2024-06-01 | CR051 | Deferral of MHHSP-037 | PSG | Issued to Impact Assessment | 2024-06-27 | 2024-07-11 |  |  | Open | Industry webinar to be held on 26 June before CR051 is issued to Impact Assessment.
2024-04-01 | CR050 | Amendments to the MHHS Change Control Approach and Form | PSG | Awaiting Ofgem approval decision | 2024-05-14 | 2024-05-29 |  |  | Open | Ofgem decision to be communicated at July PSG.
2024-04-01 | CR049 | Swagger Open API 3.0 to 3.1 Upgrade | PSG | Retracted | N/A | N/A |  |  | Closed | Change request retracted by the Change Raiser.
2024-03-01 | CR048 | Amending Qualification Milestones for Non-SIT Supplier and Agent QT | PSG | Approved | 2024-04-02 | 2024-04-16 | Approved by PSG on 01-May-24 | May-24. | Closed
2024-03-01 | CR047 | Amending Qualification Milestones for non-SIT LDSO QT | PSG | Approved | 2024-04-02 | 2024-04-16 | Approved by PSG on 01-May-24 | May-24. | Closed
2024-03-01 | CR046 | Enabling Metering Point Energy Flow to be changed more than once | DAG | Approved | 2024-03-14 | 2024-03-28 | Approved by DAG on 10-Apr-24 | IR8.1 (Jun-24). | Closed
2024-03-01 | CR045 | Supply Start Date (SSD) Correction Tool | DAG | Issued for PPIR | 2024-03-14 | 2024-03-28 |  |  | Open | Issued for PPIR, response deadline 24 June 2024. Update to be provided at July PSG.
2024-03-01 | CR044 | Implementation of 'Data Refresh' Message IF-051 | DAG | Rejected | 2024-03-14 | 2024-03-28 | Rejected by PSG on 05-Jun-24 |  | Closed | Programme to hand over solution to Code Bodies for post-M10 implementation.
2024-02-01 | CR043 | Supplier Registration of ABMU and MPAN Mapping | DAG | Approved | 2024-02-15 | 2024-02-29 | Approved by DAG on 13-Mar-24 | IR8 (Apr-24). | Closed
2024-01-01 | CR042 | Amending the ‘M16 Methodology Approved’ Milestone | PSG | Approved | N/A | N/A | Approved by PSG on 07-Feb-24 | Feb-24. | Closed | Approved without IA due to low impact T2 milestone.
2024-01-01 | CR041 | Change the format of Market Participant Code from Char(1) to Char(2) | DAG | Rejected | 2024-01-10 | 2024-01-24 | Rejected by DAG on 14-Feb-24 |  | Closed | Rejected on the grounds that it does not meet the requirements of the Change Freeze.
2024-01-01 | CR040 | Change to NFR E2E1009 for DNO and iDNO roles | DAG | Approved | 2024-01-10 | 2024-01-24 | Approved by DAG on 14-Feb-24 | IR8 (Apr-24). | Closed
2024-01-01 | CR039 | Registration Service IF-40 Change | DAG | Approved | 2024-01-17 | 2024-01-31 | Approved by DAG on 14-Feb-24 | IR8 (Apr-24). | Closed
2023-12-01 | CR038 | Amendments to the MHHS Change Board Terms of Reference | N/A - Housekeeping | Approved | N/A | N/A | N/A | Dec-23. | Closed
2023-12-01 | CR037 | Migration Message Processing Choreography Update | TMAG | Approved | 2023-12-20 | 2024-01-11 | Approved by TMAG on 17-Jan-24 | IR8 (Apr-24). | Closed
2023-11-01 | CR036 | Use of Clock Midnight for Appointments and Reads | DAG | Approved | 2023-11-24 | 2023-12-01 | Approved by DAG on 13-Dec-23 | IR7 (Jan-24). | Closed | Decision appeal received from LSC.
2023-11-01 | CR035 | Programme proposal to restructure TMAG in the MHHS Governance Framework and other housekeeping updates | PSG | Approved | 2023-11-14 | 2023-11-28 | Approved by PSG on 06-Dec-23 | Jan-24. | Closed
2023-10-01 | CR034 | Delay to Elexon Level 4 validation response - NFR (1009) | DAG | Approved | 2023-11-09 | 2023-11-23 | Approved by DAG on 13-Dec-23 | IR7 (Jan-24). | Closed
2023-10-01 | CR033 | Remove ELEX REP-005 and include LLF details as part of ISD catalogues | N/A | Issued to DIN log |  |  |  |  | Closed
2023-09-01 | CR032 | Change to interface MHHS-IF-165 P0210 TUoS reporting | DAG | Approved | 2023-11-28 | 2023-12-05 | Approved by DAG on 13-Dec-23 | IR7 (Jan-24). | Closed
2023-08-01 | CR031 | Amending Transition Design Milestone Description and Delivery Date | DAG | Approved | N/A | N/A | Approved by DAG on 13-Sep-23 |  | Closed | Approved without IA due to low impact T2 milestone.
2023-08-01 | CR030 | Introduction of Compressed Payloads into DIP Messages | DAG | Approved | 2023-08-11 | 2023-08-25 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-08-01 | CR029 | DIP LDSO Interface Processing | DAG | Approved | 2023-08-10 | 2023-08-24 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-08-01 | CR028 | EES and SDEP Requirements | DAG | Approved | 2023-08-10 | 2023-08-24 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-07-01 | CR027 | DUoS E-Billing DIP message for MHHS | DAG | Approved | 2023-07-13 | 2023-07-27 | Approved by DAG on 13-Sep-23 | IR5 (Oct-23). | Closed
2023-06-01 | CR026 | Enhancements to the Change Control Approach | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2023-06-01 | CR025 | DIP Interface Name Changes | DAG | Approved | 2023-06-14 | 2023-06-28 | Approved by DAG on 12-Jul-23 | Postponed until post-M10. | Closed
2023-06-01 | CR024 | Data Item Names and Descriptions | DAG | Approved | 2023-07-13 | 2023-07-20 | Approved by DAG on 09-Aug-23 | Postponed until post-M10. | Closed
2023-05-01 | CR023 | Standardisation of Interfaces within the Smart and Advanced Data Services Roles | DAG | Approved | 2023-07-06 | 2023-07-28 | Approved by DAG on 13-Sep-23 | IR7 (Jan-24). | Closed
2023-04-01 | CR022 | MHHS Programme Re-plan | PSG | Approved | 2023-04-05 | 2023-04-26 | Approved by Ofgem on 8-Jun-23 |  | Closed
2023-03-01 | CR021 | Update TMAG Terms of Reference to Reflect Option of Meeting Co-Representation | N/A - Housekeeping | Approved | N/A | N/A | Approved by Change Board on 29-Mar-23 |  | Closed
2023-03-01 | CR020 | Update Interim Plan to Reflect 1 Month Deferment to Replan Times | N/A - Housekeeping | Approved by Change Board | N/A | N/A | Approved by Change Board on 24-Apr-23 |  | Closed
2023-03-01 | CR019 | Replacement of D0242 D0315 for MHHS | DAG | Approved | 2023-03-15 | 2023-03-30 | Scheduled for Design Release 5 |  | Closed
2023-02-01 | CR018 | Registration Service Operating Hours | DAG | Approved | 2023-06-07 | 2023-06-14 | Approved by DAG Chair on 12-Jul-23 |  | Closed | Approval upheld by SRO following LSC objection.
2023-01-01 | CR017 | DSO Registration Service DIP Messages Processing Times | DAG | Rejected | 2023-03-02 | 2023-03-23 | Rejected by DAG Chair on 12-Jul-23 |  | Closed | Rejected as CR018 is mutually exclusive to CR017.
2023-01-01 | CR016 | Changes to the Change Control Approach to Incorporate Design Change Process | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2023-01-01 | CR015 | Differential Settlement for E7E10 Meters for Smart Opt-out Customers | PSG | Approved | 2023-02-02 | 2023-02-16 | Approved by PSG on 1-Mar-23 |  | Closed
2023-01-01 | CR014 | Changes to the Baselined LSS Design | N/A - Housekeeping | Retracted | N/A | N/A | N/A |  | Closed
2022-11-01 | CR013 | Examination of Settlement Impacts resulting from MHHS Programme | PSG | Approved | 2022-12-07 | 2023-01-09 | Approved by PSG on 1-Feb-23 | 2023-10-01 | Closed | Report approved at October PSG.
2022-10-01 | CR012 | Increase in Scope of CCAG ToR and Code Drafting Activities to Include Consequential Change | PSG | Approved | 2022-11-02 | 2022-11-16 | Approved by PGS on 7-Dec-22 |  | Closed
2022-09-01 | CR011 | Update to the Programme Interim Poap to Reflect Decisions made at September 2022 PSG | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2022-07-01 | CR010 | Proposal to Include the Full Plan Review 'PM2' Activity within Programme Governance | PSG | Approved | N/A | N/A | N/A |  | Closed
2022-07-01 | CR009 | M5 and M3 Milestone Date Changes | PSG | Approved | 2022-07-15 | 2022-07-29 | Approved by Ofgem on 1-Sep-22 |  | Closed
2022-05-01 | CR008 | Inclusion of RECCo Membership of Level 2 and 3 Governance Groups | PSG | Approved | 2022-05-11 | 2022-05-25 | Approved by PSG on 8-Jun-22 |  | Closed
2022-05-01 | CR007 | Proposal to Change M3 | PSG | Retracted | N/A | N/A | N/A |  | Closed
2022-04-01 | CR006 | Programme Proposal to Update DAG ToR | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2022-03-01 | CR005 | Adding Cooperation to Governance Framework | PSG | Approved | 2022-03-29 | 2022-04-12 | Approved by CCAG on 4-May-22 |  | Closed
2022-03-01 | CR004 | Programme Proposal to Change TMAG ToR | N/A - Housekeeping | Approved | N/A | N/A | N/A |  | Closed
2022-03-01 | CR003 | CCAG Proposals for M6 and M7 | CCAG | Approved | 2022-03-29 | 2022-04-12 | Approved by Ofgem on 21-Apr-22 |  | Closed
2022-03-01 | CR002 | Supplier Proposal to Delay M5 by 7+ Months | PSG & DAG | Rejected | 2022-03-11 | 2022-03-25 | Rejected by Ofgem on 21-Apr-22 |  | Closed
2022-03-01 | CR001 | Extend the Delivery of Design from the Current 30th April 2022 Baseline to 29th July 2022 | DAG | Approved | 2022-03-11 | 2022-03-25 | Approved by Ofgem on 21-Apr-22 |  | Closed

## Sheet1 (hidden)
List
Live
Closed
Upcoming