## Comments
DEL2295 - Qualification Assessment Document Comments Log v2
Comment I.D | Theme | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | *Comment Owner to be anonymised | Decision | Action Status | Proposed response wording
0 | 0 | Select the Ref # of the area of the document you are commenting on | Succinctly state the comment and the basis for the concern | Provide detail of the change or action required to resolve the comment | Provide a rationale for the change detailing the impact or materiality as a result of not making the recommended change | Provide the name of person providing the comment | Confirm whether your organisation comments should be anonymised in the consolidated comments log | Accept, Reject | Respond, Update Document, No Action Required
1 | Formatting and Layout | Data Management - Question 5.8.2.1 | Border lines missing | Add missing border lines | No major impact, but the change will just make the document structure look harmonised. | Ralph Azagoh-Kouadio |  | Accept | Update | N/A
2 | Formatting and Layout | Customer Direct Contract - Question 5.8.2.2 | Border lines missing | Add missing border lines | No major impact, but the change will just make the document structure look harmonised. | Ralph Azagoh-Kouadio |  | Accept | Update | N/A
3 | Formatting and Layout | Data Management - Question 5.6.2.1 - Estimation Values - Guidance Point 5.6.2.1 B&C | Border lines missing | Add missing border lines | No major impact, but the change will just make the document structure look harmonised. | Ralph Azagoh-Kouadio |  | Accept | Update | N/A
4 | Specific Questions and amendments/ removals | 5.5.1.6 | The Guidance Points references MS responsibilities, what DS responsibilities need to be assured? | Update the guidance points to accurately reflect the audience of the question. | DS respondents will not be sure how to respond to this question to meet requirements | Kristina Leary |  | Accept | Update | Removed reference to MTDs, no requirement exists on the DS to manage MTDs
5 | Specific Questions and amendments/ removals | 5.6.1.9 | The Guidance Points references MS responsibilities, what DS responsibilities need to be assured? | Update the guidance points to accurately reflect the audience of the question. | DS respondents will not be sure how to respond to this question to meet requirements | Kristina Leary |  | Accept | Update | Removed reference to MTDs, no requirement exists on the DS to manage MTDs
6 | Specific Questions and amendments/ removals | 5.5.1.6 | A data service does not share MTDs, they receive MTDs. I do not think this guidances note are relevant to data service, only Metering | Either update the guidance notes to relevant questions to data services or remove the question from data service roles | not applicable to data service roles in their current form | MM - IMServ |  | Accept | Update | Removed reference to MTDs, no requirement exists on the DS to manage MTDs
7 | Specific Questions and amendments/ removals | 5.6.1.7 | Should OPC_320A and B be removed from this list as well? They appear to be Reg Service requirements as per Operational Choreography. | Remove requirements |  | SG - IMServ |  | Accept | Update | OPC_320A/B does not exist in OPs Chor document, updated the QAD to remove requirement , Requirement is to process the IF-09
8 | Specific Questions and amendments/ removals | 5.6.1.7 | Should OPC_580 be included? Appears to be a requirement on ECS not SDS as per Operational Choreography. | Remove requirement |  | SG - IMServ |  | Reject | No Action Required | OPC_580 is still a requirement for SDS to receive and process
9 | Numbering | 5.6.1.9 | This 5.6.1.9 is included within the 5.7 UMSDS section - numbering of questions is out of line | Correct numbering |  | RF - PDA |  | Accept | Update | Updated numbering
10 | Numbering | 5.6.1.9 | This same 5.6.1.9 section in the question then refers to 5.8.1.5 A - also a section out of scope/line with this 5.7 UMSDS section | Correct numbering |  | RF - PDA |  | Accept | Update | Updated numbering
11 | Specific Questions and amendments/ removals | 5.5.1.1.e | MHHS-BR-DS-108, IMServ is uncertain this requirement relates to Appointment/De-appointment at all but rather to energisation change | Move this requirement reference to the appropriate section |  | IH - IMServ |  | Accept | Update | Removed question 5.5.1.1.e as 3rd parties are not used with ADS
12 | Specific Questions and amendments/ removals | 5.5.1.4 | Should OPC_510 be included? This relates to the IF-044 which does not get sent to the ADS | Remove this reference |  | IH - IMServ |  | Reject | No Action Required | Update already made to QAD v3.1
13 | Specific Questions and amendments/ removals | 5.4.1.7 | Guidance Points narrative still contains reference to OPC_320 which is one of the requirement documents that has been removed. | Remove reference to OPC_320 in the Guidance Point narrative | to ensure alignment | Jacqui Neck |  | Accept | Update | Updated guidance note to remove reference to OPC_320
14 | Guidance and clarification | Sections 4.5 and 4.6 | Sections 4.5 and 4.6 do NOT have any guidnance notes which could lead to issues / mislaignment on participant responses | Update guidance notes from the QAD walk through session on 14th Nov and additional guidance into the document and send a communication out with guidance (given v.3.1 will not be signed off until late in Dec) to enable valid responses and evidence | The rest of the document includes additonal questions and guidance notes to help participants and to reduce rework and rereview. Guidance was verally given on 14th - so should be available for update. No update will result in rework and rereview for all parties mpacting resource and timelines | Chris Butterfield |  | Accept | Update | Guidance notes added to section 4.5 and 4.6 (4.6 updates Pending )
15 | Guidance and clarification | Section 5.3 | Please can it be confirmed if this section requires completing by the Supplier or the LDSOs as it is for the SMRA Supplier Meter Registration Agents? | Clarification required |  | Sophie Horne |  | Reject | No Action Required | Section 5.3 only applies to SMRA, therefore should be completed by SMRA only

## Control
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Bar chart
Theme | Count
Formatting and Layout | 3
Specific Questions and amendments/ removals | 8
Numbering | 2
Guidance and clarification | 2
Total | 15

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted