## Comments
DEL2436 - Non-SIT Supplier & Agents QT Test Scenarios Comments Log
*Organisation: |  |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Date:
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | *Comment Owner to be anonymised | Theme | Decision | Action | Code Bodies Response
DEL2205-C1 | Input the Ref # of the area of the document you are commenting on | Succinctly state the comment and the basis for the concern | Provide detail of the change or action required to resolve the comment | Provide a rationale for the change detailing the impact or materiality as a result of not making the recommended change | Provide the name of person providing the comment | Confirm whether your organisation comments should be anonymised in the consolidated comments log
DEL2205-C2 | 5.1.4 table | Row 3 states "ResorEJMeter To Bank" - should be meter to bank | Typo amendment | Update | Chris Butterfield |  | Correction | Accept | Update Document | Thank you for your comment, we have applied a correction to the Document
DEL2205-C3 | 5.2 - last bullet | This bullets state elements that are out of scope for QT and will be evidenced in the QAD and PIT. This also needs to be validated against Placing Reliance and it would be good to outline these against the SIT NFR and Operational tests requirements to outline what is and is not in scope as at present this is a little vague. | Update with reference to SIT tests scenarions (funct/NFR or Operational) to ensure validation of scope, | PPs may misinterpret the elements that are out of scope or valid to PLace Reliance on | Chris Butterfield |  | Additional Information | Reject | Respond | Thank you for your comment. As Placing Reliance is applied to each individual participant, we don’t think that this section is is the best area to articulate the impact of placing reliance. The SIT scope for Operational and NFR is still being finalised and will be reflected in the BSC/REC Assessment Criteria as well as the RTTMs.
DEL2205-C4 | 6.1 last bullet | The outlook on Placing Reliance is very high level and more understanding is required on how palcing reliance will be assessed and how this might impact PIT and QT testing. This is urgent as PIT testing is in progress and QT testing with DCPs could drive huge duplication in testing. | Add more information on the PR assessment and outcomes | No change - no further information will lead to a great deal of test duplications and will leave PPs uncertain on the scope of their PIT and QT testing. This will impact resourcing and planning. | Chris Butterfield |  | Additional Information | Accept | Respond | Thank you for your comment. Additional Clarification has been added to the document. Further detail on the Placing Reliance process including timelines shall be discussed as part of the QWG.
DEL2205-C5 | 6.2.1 | Functional test outlook does not outline whether settlement testing will be in scope | Add whether settlement testing is in scope (as in SIT this was tested seperately to functional testing) | PPs will not know whether settlement testing is part of QT | Chris Butterfield |  | Additional Information | Accept | Respond | Thank you for your comment. A number of settlement related testing from SIT Settlement (Theme 8) were selected by the Code Bodies and included in the Functional Testing scope Batch 1 & 2, we are not expecting to run separate Settlement Testing as part of the QTF.
DEL2205-C6 | 6.2.2 | No mention of placing reliance in the NFR section (in PIT) | Include an outlook on placing reliance | No update will leave PPs without an outlook on placing reliance eligiibility | Chris Butterfield |  | Additional Information | Accept | Update Document | Thank you for your comment. Additional Clarification has been added to the document. Further detail on the Placing Reliance process including timelines shall be discussed as part of the QWG.
DEL2205-C7 | 6.2.4 | Some operational testing can not be performed in PIT as it requires central parties and some elements of this are called out in section 5.2. as out of sope. The text needs to be specific on the elements to be included - against the SIT scenarios | Include more detail on what requires coverage | PPs will not understand what needs to be / can be proved in PIT, which elements through placing reliance and which elements will br in QT. | Chris Butterfield |  | Additional Information | Accept | Update Document | Thank you for your comment. Additional Clarification has been added to the document in section 6.2.2 and 6.2.4. Further detail on the Placing Reliance process including timelines shall be discussed as part of the QWG. Further information is also available in the PIT Guidance document (MHHS-DEL852 v2.6). The SIT Operational scope is still being finalised and any updates will be reflected in the RTTM and Assessment Criteria.
DEL2205-C8 | 9.2.3 | This section does not include the outlook on using CoS to update PPs systems outlined in QWG | Include CoS update in this section | PPs may not be able to progress a data load and may need the CoS business process to update systems | Chris Butterfield |  | Additional Information | Accept | Respond | Thank you for your comment. The Test Data approach will be updated if needed following evaluation of the 'Plan B' approach for loading of test data.
DEL2205-C9 | 9.3 Diagram | Will SDS - MDR updates be tested - as this is not outlined in the diagram but is central to consumtpion / settlement testing | Validate if MDR is part of testing | PPs will not know how to run tests without the MDR role | Chris Butterfield |  | Clarification | Accept | Respond | Thank you for your comment. We will have a QT MDR DIP ID to be able to used in relevant SDS DIP messages so a Supplier will receive a MDR DIP ID associated with the QT SDS. In terms of MDR functionality, (SDS<->MDR) - this is out of scope
DEL2205-C10 | 10.3 | PLacing Reliance assessment needs more detail to validate how this assessment will work and be validated by the code bodies | INclude more detail on PLacing reliance assessment | PPs will not know how this assessment will hapen and so the scope of their QT testing scope. | Chris Butterfield |  | Additional Information | Accept | Respond | Thank you for your comment. Additional Clarification has been added to the document. Further detail on the Placing Reliance process including timelines shall be discussed as part of the QWG.
DEL2205-C11 | 10.4.1 | Placing REliance assessment needs more information | Add more information on how the test plan can be produced against the QT role and the level of Placing Reliance | PPs will not know how to assess their QT scope | Chris Butterfield |  | Additional Information | Accept | Update Document | Thank you for your comment. We have added additional clarification to the document.under section 10.4.2. Further detail on the Placing Reliance process including timelines shall be discussed as part of the QWG.
DEL2205-C12 | 12.1 | Table needs to include the scoping of the QT tests and how this will be assessed including Placing Reliance | Add a section on QT scoping | PPs will not know the RASCI for this scoping task | Chris Butterfield |  | Additional Information | Accept | Update Document | Thank you for your comment. We have added an additional activity to the RASCI.
DEL2205-C13 | 6.2.1 | As Annex 2 is only for Non Sit supplier and agents I had hoped for a more expanded Functional test type information with linked examples. | Have linked examples of the test types you expect participents to ennact | Further confusion to participents due to loosely worded explanations. | Ben Free |  | Clarification | Accept | Respond | Functional Test Cases Batch 1 and 2 have been published and are available on the Programme Collaboration Base for review. The Batches contain the overarching scenarios/cases and the underlying test cases/steps can also be reviewed.
DEL2205-C14 | 6.2.2 | As Annex 2 is only for Non Sit supplier and agents I had hoped for a more expanded non Functional test type information with linked examples. | Have linked examples of the test types you expect participents to ennact | Further confusion to participents due to loosely worded explanations. | Ben Free |  | Clarification | Accept | Respond | The Non-Functional Test Scope for SIT is still being finalised. The QT NFT scope will be confirmed in parallel.
DEL2205-C15 | 9.1.3 Requirements Traceability | When will the QT RTTM be produced | confirm the date of issue | participants lack clarity of QT scope | Neil Archer |  | Clarification | Accept | Respond | Thank you for your comment. An updated RTTM is being published alongside the papers for QWG, however further updates will be required as the QT Test Scope is finalised.
DEL2205-C16 | 9.3.4 Running QT cases | "however, execution of the Test Case will halt where interventions are required by the Non-SIT S&A QT Participant (e.g. capturing of specific evidence)" - When will all the interventions be outlined and available for PPs | confirm the date of issue | It would be good to indicate where evidences are required ahead of entering QT, in order to ensure it is covered in PIT and we have the capability to produce the necessary evidence | Neil Archer |  | Clarification | Accept | Respond | Thank you for your comment. We have added commentary to the document. Currently Intervention steps can be determinable by looking at the SIT/QT Test Scenario Spreadsheets (which are mapped against the Functional Test Cases in Batch 1 & 2) and filtering by your role. We are reviewing to determine if there is a more efficient way to present this information in advance of the QTF being available for use.
DEL2205-C17 | 10.4 Test Deliverables | Will a timeline be available per wave per deliverable to support planning | It would be useful to add in expected delivery plans | Deliverables may not be received on time per QT wave | Neil Archer |  | Clarification | Accept | Respond | Thank you for your comment. We will provide regular updates as part of the QWG/SAQTSG
DEL2205-C18 | 10.2 Env Prep & DIP Onboarding | This section states that test environments do not need to be fully scaled to match production levels. However, in section 6.2.2 Non Functional, it is expected that Non-SIT S&A QT participants will test NFT requirements at production volumes. Is this a contradiction in that you would need a scaled environment to test at these levels? | Confirm the requirement | QT test environment may not be built to run required NFT tests | Sarah Lewis |  | Clarification | Accept | Update Document | Thank you for your comment. Production volume testing is a PIT requirement only. We have added clarification to this section.
DEL2205-C19 | 3 Objectives | This is regarding the non-functional and operational requirement. If due to some reason, we will utilise most of the test data in QT functional testing. Then in this case, what's the contingency planning to utilise the data in QT NFT and OT? | Provide proper contingency planning and use the lesson learnt from MHHS SIT. |  | Unknown |  | Clarification | Accept | Update Document | Thank you for your comment. We have added additional commentary to section 9.2.1. There will be no requirement to hold test data from functional for NFR or operational choreography as each QTC will be supplied with the necessary MPANs. Should the Participant need to request more test data for functional if the existing provision is consumed, this may be requested from the QTF team.
DEL2205-C20 | 3 Objectives | Can we use the leftover functional test data without tweaking them before utilise them in Non-functional and Operational testing? | Provide more clarity on the steps to utilise the functional test data without much effort. |  | Unknown |  | Clarification | Accept | Update Document | Thank you for your comment. As per above, We have added additional commentary to section 9.2.1. There is no need as the QTC team will provision the necessary MPANs specific for NFR and Operational Chroeograph test cases explicitly and this can be replenished if required.

## Sheet1
Theme | Count of Theme
Additional Information | 9
Clarification | 8
Correction | 1
Grand Total | 18

## Control (hidden)
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted