## Comments
DEL2535 - NFT update to Annex 1 of the Qualification Approach & Plan Consultation Comments Log
*Organisation: |  |  | Consolidated feedback log
*Constituency: |  |  | LDSO
*Date: |  |  | 18/07/2024
Comment ID | Organisations | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | Decision | Theme | Action | Response
| SPEN | P35 - 8.6 Test Plan | This section does not reference submitting a QT Test Plan for Functional and Migration QT, then a further submission for NFT and Operational Testing |  |  | Accept |  | Update document | Document update to inculde there are two submissions of the QT test plan, one for functional and migration and one for non-functional and operational testing
| Northern Powergrid | P17 -5.3 Testing types -Non-Functional | As per the document, " Security – NFRs around PKI and levels 1 through to 4 validations" The Level 1 and 2 validation does by the DIP. The LDSOs are not responsible. As LDSO can't validate Level 1 and 2, please review and update statement which will show the true reflection of testing. This creates confusion and may impact to QT. |  |  | Accept |  | Update document | Document update to refer to level 3 and 4 validation