## Sheet1
Organisation: | Various
Constituency: | Various
Date: | 2024-08-05 |  |  | MHHS-DEL2968 QT Non-Functional Test Scenarios Theme 3 Consolidated Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete | [5 empty] | Programme to complete once consultation window has closed.
Ref | Reviewer | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject or Action | Response | Status
1 | UKPN | QT NFT Theme 3 | MHHS-DEL2808 QT Non-Functional Test Scenarios Theme3 v0.1 |  |  | UK Power Networks has reviewed the non-functional test scenarios and we have no further comments. | Accept |  | Closed
2 | SPEN | QT NFT Theme 3 | MHHS-DEL2906 QTNFT-T2-200 | SITNFT-T2-200-040-Smart |  | Operating_Windows – test SITNFT-T2-200-040-Smart - testing the acceptance of a related MPAN removal or its rejection ? • Test Step 25 text states rejection, but Message Input Event Code suggests acceptance as do some of the later steps. • Test Step 65 shows PUB-020 being received by REGS, but Test Step text sates it is the supplier that receives the IF-020 which makes more sense I suspect this step should be removed | Accept | Test cases have been updated to reflect the LDSO rejection with correct message data, and desitinations
3 | SPEN | QT NFT Theme 3 | SITNFT-T2-130 | SITNFT-T2-130-030-Smart |  | There are many places in this test scenario and test case where it is mentioned that PUB-019 with event code [RelatedRemove] is received by LDSO. This is incorrect. If the event code is [RelatedRemove] then it will go to Registration Service system from DIP. | Accept | Test cases have been updated to reflect the LDSO rejection with correct message data, and desitinations
4 | SPEN | QT NFT Theme 3 | SITNFT-T2-130 | SITNFT-T2-130-030-Smart |  | Again, many steps are overlapping with functional test cases. What will be the business benefit to repeat the same steps in NFT? | Reject | The test steps remain the same as functional tests, however, the actual test is to provide assurance that messages are buffered when the DIP is unavailable, and once available, that messages can be successfully processed
5 | SPEN | QT NFT Theme 3 | SITNFT-T2-200 | QTNFT-T2-200-030-Smart | Step No 25, 30 | Step No 25, 30 The CSS simulator won't be used as discussed in the July LQTSA meeting. In this case, these 2 steps will not be able to test. There is no requirement to test with CSS in QT phase. | Accept | CSS files will be created by the programme for testing
6 | SPEN | QT NFT Theme 3 | SITNFT-T2-200 | QTNFT-T2-200-030-Smart SITNFT-T2-200-040-Smart |  | Again, many steps are overlapping with functional test cases. What will be the benefit to repeat the same steps in NFT? | Reject | The test steps remain the same as functional tests, however, the actual test is to provide assurance that messages are buffered when the DIP is unavailable, and once available, that messages can be successfully processed
7 | SPEN | QT NFT Theme 3 | SITNFT-T2-200 | SITNFT-T2-200-040-Smart |  | There are references of PUB-019 with event code [RelatedRemove] receive by LDSO. This is incorrect. If the event code is [RelatedRemove] then it will to Registration Service system. | Reject | Duplicate comment
8 | SPEN | QT NFT Theme 3 | General | General |  | There are no test scenario and test cases for Network Ops system interaction with DIP. Parties are placing reliance with registration service and UMSO on MHHS SIT. If there are similar NFT test cases in MHHS SIT then we are mostly duplicating the testing. | Accept | Now that both cases involving LDSO and IF-020 have been altered, these systems are in in scope as planned
9 | SPEN | QT NFT Theme 3 | QTNFT-T2-200 | QTNFT-T2-200-030-Smart |  | Outside window processing. How to achieve it? | Accept | The supplier is a programme controlled simulator, we will kick off the messages outside of processing windows to validate queuing until the next day
10 | Northern Powergrid | QT NFT Theme 3 | SITNFT-T2-130 | SITNFT-T2-130-030-Smart |  | There are many places in this test scenario and test case where it is mentioned that PUB-019 with event code [RelatedRemove] is received by LDSO. This is incorrect. If the event code is [RelatedRemove] then it will go to Registration Service system from DIP. | Accept | Test cases have been updated to reflect the LDSO rejection with correct message data, and desitinations
11 | Northern Powergrid | QT NFT Theme 3 | SITNFT-T2-130 | SITNFT-T2-130-030-Smart |  | Again, many steps are overlapping with functional test cases. What will be the business benefit to repeat the same steps in NFT? | Reject | The test steps remain the same as functional tests, however, the actual test is to provide assurance that messages are buffered when the DIP is unavailable, and once available, that messages can be successfully processed
12 | Northern Powergrid | QT NFT Theme 3 | QTNFT-T2-200 | QTNFT-T2-200-030-Smart |  | Step No 25, 30 The CSS simulator won't be used as discussed in the July LQTSA meeting. In this case, these 2 steps will not be able to test. There is no requirement to test with CSS in QT phase. | Accept | CSS files will be created by the programme for testing
13 | Northern Powergrid | QT NFT Theme 3 | QTNFT-T2-200 | QTNFT-T2-200-030-Smart SITNFT-T2-200-040-Smart |  | Again, many steps are overlapping with functional test cases. What will be the benefit to repeat the same steps in NFT? | Reject | The test steps remain the same as functional tests, however, the actual test is to provide assurance that messages are buffered when the DIP is unavailable, and once available, that messages can be successfully processed
14 | Northern Powergrid | QT NFT Theme 3 | QTNFT-T2-200 | SITNFT-T2-200-040-Smart |  | There are references of PUB-019 with event code [RelatedRemove] receive by LDSO. This is incorrect. If the event code is [RelatedRemove] then it will to Registration Service system. | Accept | Test cases have been updated to reflect the LDSO rejection with correct message data, and desitinations
15 | Northern Powergrid | QT NFT Theme 3 | General | General |  | There are no test scenario and test cases for Network Ops system interaction with DIP. Parties are placing reliance with registration service and UMSO on MHHS SIT. If there are similar NFT test cases in MHHS SIT then we are mostly duplicating the testing. | Accept | Now that both cases involving LDSO and IF-020 have been altered, these systems are in in scope as planned
16 | Northern Powergrid | QT NFT Theme 3 | QTNFT-T2-200 | QTNFT-T2-200-030-Smart |  | Outside window processing. How to achieve it? | Accept | The supplier is a programme controlled simulator, we will kick off the messages outside of processing windows to validate queuing until the next day
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372

## Sheet2
Theme
Theme 1 - Forward Migration - CoA & CoS
Theme 2 - Reverse Migration - CoS
Theme 3 - Import/Export MPANs & Exception Handling