## Sheet1
DEL3352 - Non-SIT Supplier & Agents QT Test Scenarios Comments Log - Batch 3
*Organisation: | Consolidated |  |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Date:
Comment ID | *Ref # | Batch # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | ST Comment | Decision | Theme | Action | Response
15_01_01_01 | Column B | 3 | Grouping of Scope Theme is misaligned, for example it starts with Theme 7 in rows 3-5, then switches to other Themes, then Theme 7 appears again in rows 17 and 27-30. | To be reordered so that each Scope Theme is grouped together numerically | Less simple to 'lift and shift' into our own test plan | Subhasish Gosh | Spreadsheet is sorted by Column F. The spreadsheet can obviously also be sorted by Column A or B if required. | Acknowledge | Housekeeping | Response | Thanks for revieiwng, the spreadsheet is currently sorted by Column F but can also be sorted by Column A or B if required.
15_01_01_02 | Column F | 3 | QT-245, QT-248 & QT-249 are missing - is this deliberate? | Confirmation whether these are deliberately missing due to being removed from scope or have been omitted in error | Lack of certainty | Subhasish Gosh | Yes, this is due to historical test cases that have been removed. For example because the test case was removed from SIT scope. | Acknowledge | Missing Test Scenarios | Response | Thanks for reviewing. Yes, this is due to historical test cases that have been removed. For example because the test case was removed from SIT scope.
15_01_01_03 | Rows 4 & 5, Columns D and I | 3 | Reconciliation is spelled incorrectly | Change from 'Reconcillation' in Column D and 'Reconcilitation' in column I to 'Reconciliation' | Spelling errors would remain | Subhasish Gosh | Typo - update | Action | Housekeeping | Update Document | Thanks for reviewing, this has been amended in the newest version.
15_01_01_04 | Rows 15 & 25, Column C | 3 | Listed as 'Change of Registration' whereas the other test cases in Theme 2 are listed as 'Change of Registration Data' | Ensure the same naming convention for Theme 2 | Lack of consistency | Subhasish Gosh | Update - Make consistent with SIT - "Change of Registrations" | Action | Housekeeping | Update Document | Thanks for reviewing, this update has been made.
15_01_01_05 | Row 23, Column C | 3 | Listed as 'Change of Metering' whereas the other test cases in Theme 5 are listed as 'Change of Metering Service' | Ensure the same naming convention for Theme 5 | Lack of consistency | Subhasish Gosh | Update - Make consistent with SIT - "Change of Metering Service" | Action | Housekeeping | Update Document | Thanks for reviewing, this update has been made.
15_01_01_06 | Row 29, Column G | 3 | QT-271 has 'TC03' at the beginning of its Test Case Title, whereas no others do as this instead appears in columns J and K | Remove so naming convention is the same | Lack of consistency | Subhasish Gosh | Typo - update to remove "TC03" | Action | Housekeeping | Update Document | Thanks for reviewing, this has been amended in the newest version.
15_01_01_07 | General | 3 | Theme 5, QT-256 is 'no change of supplier' however in column P it shows that Suppliers should complete this test case. Whereas QT-264 is also 'no change of supplier' but is not marked in column P as Suppliers required to complete it. Is this an error? | Confirm if QT-256 is marked as 'Y' in Column P in error or if QT-264 has been missed in error | Lack of certainty | Subhasish Gosh | Neither is an error. These test cases are required to be run by the defined Role in order to meet one or more specific requirements for each Role. | Acknowledge | Clarity of Test Scenario | Response | Thanks for revieiwng, neither is an error. These test cases are required to be run by the defined Role in order to meet one or more specific requirements for each Role.
15_01_02_01 | QT Scenarios batch 3 doc - QT-258 (Row 16) | 3 | Traditional Prepay MS Energisation: Why is this being covered for Pre-payment as opposed to just testing for traditional please? Will this scenario test going from energised to de-energised or vice versa? | More clarity please to justify the test | Lack of clarity / additional test effort | Rachael Stringfellow | MHHS-BR-MS-046.1 for MSS is specific to Traditional Prepayment meters. Other requirements are also being covered in QT-258 that are non prepayment specific. The test case is from De-energised to Energised. | Acknowledge | Clarity of Test Scenario | Response | Thanks for reviewing, MHHS-BR-MS-046.1 for MSS is specific to Traditional Prepayment meters. Other requirements are also being covered in QT-258 that are non prepayment specific. The test case is from De-energised to Energised.
15_01_02_02 | Row 29 & 30 (QT-271 & QT TC03 Smart Pre-RF and Dispute Criteria met Advanced Pre-RF and Dispute Criteria met | 3 | What process is required as part of this please? (PUB_027, PUB_028, PUB_21, PUB_014, PUB_041?) | More clarity please | Lack of clarity | Rachael Stringfellow | PUB-027 Consumption Amendment is the specific process being addressed in QT-271 and QT-272 | Acknowledge | Clarity of Test Scenario | Response | Thanks for reviewing, PUB-027 Consumption Amendment is the specific process being addressed in QT-271 and QT-272.
15_01_03_01 | MHHS-DEL1890/ SITFTS-0845 TC02 Traditional -Meter Removal/De-Energisation/Disconnection during Change of Supply, Metering Service and Data Service (Batch 3) | 3 | Missing requirement MHHS-BR-SU-058 for de-activation | Supplier must receive CSS02370 message for confirmation of registration deactivation. | Missing CSS message and there is no confirmation for deactivation | Narmatha Tamiselvan | CSS messages will be included in the QT test cases as per CSS process flows. CSS02370 is included in this QT test case for example. | Acknowledge | Clarity of Requirement | Response | Thanks for reviewing, the CSS messages will be included in the QT test cases as per CSS process flows. CSS02370 is included in this QT test case for example.
15_01_03_02 | MHHS-DEL1813/SITFTS-0010 TC01 Smart Metered -Change of supplier, no change of DS or MS (Batch 3) | 3 | Input/Trigger column holding incorrect CSS message (CSS01700) for Change of supplier (Note: All the Change of Supplier test cases holding CSS1700 in the Input column) | CSS01800 triggered from Supplier for COS process. Please update all scenarios for a CoS Gain to reflect this CSS message. | Incorrect CSS message added - CSS01700 is used for New connection which is InitialRegistrationRequest - so could cause confusion as the scenario in question is not a new connection. | Narmatha Tamiselvan | CSS messages will be included in the QT test cases as per CSS process flows. CSS01800 and not CSS01700 is included in this QT test case for example. | Acknowledge | Clarity of Requirement | Response | Thanks for reviewing, CSS messages will be included in the QT test cases as per CSS process flows. CSS01800 and not CSS01700 is included in this QT test case for example.
15_01_04_01 | QT -263 | 3 | There is no change of supplier and MS, do DS. | As suppliers and B2B customers can choose whichever agent, shouldn’t there be a test for this scenario? | Pogramme could miss a legitimate scenario | Alex Persse | QT-263 is included to cover a specific Metering Service Smart MSS requirement. | Acknowledge | Clarity of Test Scenario | Response | Thanks for reviewing, QT-263 is included to cover a specific Metering Service Smart MSS requirement.
15_01_05_01 | QT-233 | Migration | The use of 'or' in the wording implies that there is an option to use either 'Import/Export or Related MHHS mpans' but where a supplier chooses to use related mpans, this test becomes the same as QT-238. If the scenario should use mpans that are import/export linked, or mpans that are both import/export linked AND set as related, this should be clarified. | In order to avoid duplication, change the wording to clarify the scenario being tested. | Test undertaken could be a duplicate and full test coverage will not be attained. | Emily Luke | QT-233 is Linked Import/Export, QT-238 is Related. QT-233 to QT-235 to be updated to remove "or Related" from QT Scenario. | Action | Housekeeping | Update Document | Thanks for reviewing, this has been amended in the newest version.
15_01_05_02 | QT-234 | Migration | Same concern as QT-233 above, lack of clarity in the wording re import/export linked or related. | In order to avoid duplication, change the wording to clarify the scenario being tested. | Test undertaken could be a duplicate and full test coverage will not be attained. | Emily Luke | QT-233 is Linked Import/Export, QT-238 is Related. QT-233 to QT-235 to be updated to remove "or Related" from QT Scenario. | Action | Housekeeping | Update Document | Thanks for reviewing, this has been amended in the newest version.
15_01_05_03 | QT-235 | Migration | Same concern as QT-233 above, lack of clarity in the wording re import/export linked or related. | In order to avoid duplication, change the wording to clarify the scenario being tested. | Test undertaken could be a duplicate and full test coverage will not be attained. | Emily Luke | QT-233 is Linked Import/Export, QT-238 is Related. QT-233 to QT-235 to be updated to remove "or Related" from QT Scenario. | Action | Housekeeping | Update Document | Thanks for reviewing, this has been amended in the newest version.
[7 empty] | Housekeeping | 8
[7 empty] | Missing Test Scenarios | 1
[7 empty] | Test Scenario Clarity | 4
[7 empty] | Requirement Clarity | 2