## Summary
Consolidated Comments Log - Sandbox Test Data Approach & Plan
MHHS-DEL3801
Consultation Responses - Review of v0.2 dated 26-May-2025
Sandbox Test Data Approach & Plan (MHHS-DEL3775)
2025-06-09
Version 1.0

## Responses
Organisation: | MHHS-DEL3835
Constituency:
Date: | 2025-06-09
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Comment Reference | Reviewer | Page | Section | Comment | Response | Status
1 | SP Energy Networks (SPEN) | 5 | 5 | Bullet point 2 - Sandbox will use the same ISD - should a second sub-bullet point be added to note that a new ISD will be required if the party is testing a different MPID to QT? | Yes agree. Document has been updated to reflect this point. | CLOSED - Document Updated
OVO01 | OVO | 11 | 7.1 | The document states that priority for testing will be given to the QT testing above that of the UIT testing - can you confirm that additional resource is in place to support data set up and data runs for UIT across the QT and UIT period - as this will be required to support these in parallel (e.g. Wave 3 QT will be happening while Wave 2 UIT is in progress) | As Sandbox testing is optional and use of the environments may be fairly ad-hoc its difficult to determine demand and any potential contentions. Teams are in place to cover the test phase and this will be monitored and reviewed over the duration of the Sandbox testing period. | CLOSED - Query responded to but No Document Update
OVO02 | OVO | 11 | 7.2 & 7.5 | The document states that MPANs will be given for ALL QTCs available to the role in section 7.2, but 7.5 states that MPANs will be given for the specific tests requiring re-run. Can you advise which is true as the former would give more flexibility in scope for participants while the latter would constraint PPs to choosing specific tests and gain specific data sets. | The same approach will be followed for Sandbox as for QT. MPANs for test are allocated against each Test Case (QTC) and these can be used for executing the TC. Test Participants can run ANY QTCs relating to the Market Role for which they are registered to test against based on their qualified market roles. This means that a larger subset of MPANs will be made available to each requesting Sandbox Participant even if they subsequently choose not to run these QTCs. The statements in section 7.5 for the circa 20 MPANs per QTC was added to provide some form of context of how much test data its to be expected. Added some extra words into section 7.2 to clarify. | CLOSED - Document Updated
OVO03 | OVO | 11 | 7.1 | "The Sandbox test environment uses the same UIT environment as is being used for Qualification Testing (QT) over largely the same time period." Can the timelines be accurately stated to align to ALL QT wave completion - as we need to validate the timelines that the UIT environment will be open to? | Accepted - Added reference to section 7 of the E2E Sandbox Guidance document (MHHS-DEL2736) which states the availability dates so that they is only in 1 master set of dates within sandbox documents. | CLOSED - Document Updated
| npower Business Solutions |  |  | nBS have read the required document and have no feedback |  | n/a
1 | Northern Powergrid | 6 | 6.3 Supporting the use of the MHHS Non-SIT LDSO Qualification Test Harness Tool | Please elaborate on the governance mechanism during Sandbox testing. There are still some concerns regarding the following points: - The contact details (Sandbox team email ID). Will the LDSO_QT <ldso_qt@mhhsprogramme.co.uk> continue to be point of contact? - The escalation model if an issue or response is not resolved in a timely manner. | Accepted - Updates made to section 6.3 to clarify that Sandbox Testing will continue to fall under the Qualification governance framework, via QWG and QAG and any required escalations will be to the Programme team. | CLOSED - Document Updated
2 | Northern Powergrid | 6 | 6.3 Supporting the use of the MHHS Non-SIT LDSO Qualification Test Harness Tool | During the QT, we observed close collaboration between the LDSO and MHHS QT team in identifying the correct data, facilitated through offline discussions via the Teams channel or daily stand-up calls. However, we anticipate that no such calls will be arranged for the Sandbox environment. Please suggest the mechanism to address any test data failures that may become a time-consuming process. In cases where urgent intervention is required, delays to the timeline could impact to our goal to complete in due timeline. Will there be any Teams channel or regular catch up call to discuss the issues/defects etc? | Teams channel will be set up for Sandbox. Agree that no formal daily standup calls are expected to occur but if required the Sandbox support team will discuss any issues bi-laterally with participants as required. As per above updates to section 6.3 made will cover any required escalations | CLOSED - Document Updated
3 | Northern Powergrid |  | General | The UIT environment has now become the Sandbox test environment. Simultaneously, other activities are in progress, including a plan to migrate the configuration of UIT to the Production environment as part of DIP On-boarding. Will this have any impact on Sandbox testing? | This activity is not expected to have any impact on Sandbox Testing | CLOSED - Query responded to but No Document Update
4 | Northern Powergrid |  | General | We want to test another MPID which was not part of the QT. Could you please mention the approach for any additional setup or configuration or test data requirement? | Accepted - updates made to section 6.4 to cover this scenario | CLOSED - Document Updated
| Utilita Energy |  |  | Utilita Energy have no comments for return |  | n/a
| Anonymised Supplier | 4 | 4 | Regarding requesting access, what is the expected timeline from request being submitted to access being granted? | Accepted - updates made to section 4 to cover this scenario at circa one weeks lead time. | CLOSED - Document Updated
| Anonymised Supplier | 5 | Figure 2 | Is there a limit on how many additional MPANs can be requested? | No formal set limit. See section 7.5 which sets anticipated standard level of MPANs available for each QTC at the circa 20 MPAN levels. If more or required then please request from the Sandbox support team and each case will be managed on a case by case basis. Large MPAN numbers not anticipated though as generally the approach is similar and in line with qualification testing levels as a design principle. | CLOSED - Query responded to but No Document Update
1 | C&C (on behalf of LDSOs) |  |  | On P5 it has the following statement: Note – For LDSOs, the aim if possible is to try and re-use MPANs from non-SIT QT to reduce data set up and support levels (see section 6.4 below for more details) It's worth noting that for the LDSOs, the testing they want to do is to test their other MPIDs (i.e. the one they didn't use it QT) so reusing MPANs won't even be possible. The test data for Sandbox testing is the bit that concerns me the most | Accepted - Yes agree and in these scenarios it is recognised that new MPAN data will be required and the process does support this upon request as per section 6.4. Have updated the words to reflect this valid scenario where new data would be required as a good example. | CLOSED - Document Updated
2 | C&C (on behalf of LDSOs) |  |  | P5 also states the following: The Sandbox environment will use the same Industry Standing Data (ISD) data set configured for use in the UIT environment and used for Qualification Testing I can't see how this will work, at the very least the additional LDSO MPIDs will have to be flagged as Activated (I'm not sure if this would cause issues for Supplier testing) | Accepted - Comment noted and you are right in what you say. Maybe we need to update the wording to reflect that updates can be made to the ISD but it’s to the same version used for all testing in the UIT environment. Section 5 bullet 2 updated to reflect. | CLOSED - Document Updated
3 | C&C (on behalf of LDSOs) |  |  | On Page 6 it contains the following statement: This tool has been built by the MHHS Programme Sims & Ems Team and has been used by Non-SIT LDSOs as part of Non-SIT LDSO Qualification testing. That isn't true, the LDSOs didn't have access to or use the QT Test Harness. They received messages from it but at no point did they use it. Any Sandbox Testing would require the same team to support it. | Slight wording update in section 6.2 made to clarify This tool has been built by the MHHS Programme Sims & Ems Team and has been used by the Programme to support Non-SIT LDSO Qualification testing. | CLOSED - Document Updated
4 | C&C (on behalf of LDSOs) |  |  | On P7 it makes reference to ignoring ISD (IF-047 messages), we'd have to engineer a way of doing this, the IF-047 is a broadcast message and systems are built to consume whenever it arrives. There may be a way we could tell our Adaptor to not process it fully but out of the box we'd process it and send to every system. | Accepted - additional words added to section 6,.4 to cover. | CLOSED - Document Updated
5 | C&C (on behalf of LDSOs) |  |  | On P8 it makes reference to ignoring HELIX messages, I'm not sure what this is referring to but as for ISD as an Adaptor we can't simply choose to ignore some messages of a specific type. | Link to point 4 above | CLOSED - Document Updated
| Qualification Team |  |  | I think there is one review comment that has been previously missed. I don’t see a note to this effect. Parties cannot do joint testing with the QTF. | Yes agree. Document has been updated to reflect this point at end of section 7.1 'Key Principles'. | CLOSED - Document Updated