## Sheet1
MHHSP - BPRWG Action Log
Action Ref | Meeting Date | Action | Owner | Due Date | Status | Update | Links
1-01 | 2021-11-03 | Ian Smith to arrange a call with Chris Beard to discuss security concerns in more detail | Ian Smith | 2021-12-01 | Closed | Completed
1-02 | 2021-11-03 | Meeting calendar to be shared with the BPRWG members | Claire Silk | Ongoing | Closed | 02/12/21 - In Progress: Meeting calendar for 2021 circulated and available on the MHHS website. Updated calendar for 2022 to be circulated following planning. 05/01/22 - In Progress: Updated meeting calendar to be issued in accordance with the revised Working Group approach. Covered by agenda item. Closed
1-03 | 2021-11-03 | Background documentation to be migrated to new BPRWG MS Teams channels and members added to channels | Claire Silk | Ongoing | Closed | In Progress- Issue with MS Teams channel access now resolved. Work ongoing to migrate background documentation and post all material that has been circulated within the sub-groups 05/01/22 - In Progress- new MS Teams Channel created as part of the MHHS Portal- all documentation is being migrated to the new folder structure. Covered by agenda item. 02/02/22 - In progress- Design Document Library is now live and migration of background documentation is in progress Closed
1-04 | 2021-11-03 | Tom Chevalier to host a session to cover background context for Meter Operator/ Meter Equipment Manager/ Metering Service | Claire Silk | 2021-12-01 | Closed | Meeting took place on 10th Nov.
1-05 | 2021-11-03 | BPRWG members to confirm interest in Registration and Smart sub-groups | All | 2021-12-03 | Closed | Completed
1-06 | 2021-11-03 | BPRWG members to provide feedback on draft Business Process List | All | 2021-12-03 | Closed | Completed
2-01 | 2021-12-01 | Ensure BPRWG members have access to all level 4 working group Team channels where permissible. | Simon Chidwick | 2022-03-02 | Closed | 05/01/22 - In Progress- all Working Group participants will be provided with a user profile to enable access to the MHHS Teams Channel. Log in Details will be communicated by the end of the week. 02/02/22 – Although participants have access to the Portal this action relates specifically to meeting documentation which is not yet on the Portal and so the action remains open 02/03/22 - Enhancements are planned for the MHHS Portal which will include a meeting library for all meeting documentation- in the interim all L4 meeting papers are now available in the Design Document Library
2-02 | 2021-12-01 | TDWG Updates to be included in future BPRWG meetings | Claire Silk | 2022-01-05 | Closed | TDWG updates now part of the standard agenda.
2-03 | 2021-12-01 | Update Sub Group Meeing Invites for those that have been postponed etc | Claire Silk | 2022-01-05 | Closed | Claire has updated the invites accordingly
3-01 | 2021-12-05 | Provide feedback/suggestions on how Teams channel folders and documents can be best managed | All | 2022-02-02 | Closed | Completed
4-01 | 2022-02-02 | CS to provide view of March sub group activity and a view of the activity end to end although it is appreciated it is subject to change. | Claire Silk | Ongoing | Closed | Completed
4-02 | 2022-02-02 | Business Requirements/Business Process Descriptions – CS to ensure UMSO is included in the Metering Services descriptions | Claire Silk | 2022-03-02 | Closed | Actioned
4-03 | 2022-02-02 | A complete list of processes for each service detailing those that remain unchanged and reflecting both target state and transition to be made available | Claire Silk | 2022-04-06 | Open | In progress- activity has commenced to develop signposting which will feed into the Design playback sessions planned throughout August
4-04 | 2022-02-02 | CS to ensure Method Statements are included in the Business Design Progress Update | Claire Silk | 2022-03-02 | Closed | Actioned
4-05 | 2022-02-02 | CS to arrange for summary of TDWG and SDWG activity to be presented at the next BPRWG | Claire Silk | 2022-03-02 | Closed | Included in and took place on BPRWG of 02/03/2022
4-06 | 2022-02-02 | CS to investigate whether certain aspects of the SWDG documentation can be shared with everyone, and which can only be shared amongst the SDWG | Claire Silk | 2022-03-02 | Closed | SDWG update provided in BPRWG of 02/03/2022
4-07 | 2022-02-02 | CS to confirm if the Registration sub group of the 15th is required or not and to ensure the Change of Agent session invite becomes a cross sub-group invite. | Claire Silk | 2022-03-02 | Closed | CS confirmed it was not required
4-08 | 2022-02-02 | Design Issues Log and RAID log to be published to the Design Document Library | Claire Silk | 2022-04-06 | Propose Closed | The Design Artefact Tracker on the MHHS Portal now includes a full list of all baseline design issues and Dependencies along with design specific risks
4-09 | 2022-02-02 | CS to see if an archived artefact section can be made available on the Portal where the previous version of the artefact can be viewed for comparison. | Claire Silk | 2022-04-06 | Open | In progress- requirement is being reviewed as part of the Portal enhancements. Under the new approach, going forward the intention will be to show tracked changes in artefacts
4-10 | 2022-02-02 | Business Process Diagrams to be updated with process timings where applicable | Design Team | 2022-03-02 | Closed | Update: The expectation across all processes is that data will be processed as quickly as possible, timings for specific processes will be covered in the Operational Choreography document
4-11 | 2022-02-02 | Timescales for submission of design artefacts to DAG to be reviewed to ensure adequate time for DAG representatives to seek feedback from their constituencies | Claire Silk | 2022-03-02 | Closed | Closed- following discussions with the DAG it was agreed that design artefacts will be made available to the DAG representatives and published to wider industry at the same time that they are issued to BPRWG for review
4-12 | 2022-02-02 | Change Control process to be published | Claire Silk | 2022-04-02 | Propose Closed | The Change Control process is published on the MHHS Website | MHHS Website/Change Control
5-01 | 2022-03-02 | Confirm that the risk around not including process timings on the Business Process Diagrams is captured on the RAID log | Ian Smith | 2022-04-02 | Closed | Added to the Design Risk Log in the Design Artefact Tracker | Design Artefact Tracker
5-02 | 2022-03-02 | Confirm that Tranche 1 review documents are available to all industry participants on the MHHS Website | Claire Silk | 2022-04-02 | Closed | 07/03/22 - Tranche 1 review documents can be found on the Knowledgebase section of the MHHS Website here: https://www.mhhsprogramme.co.uk/knowledge-base/
5-03 | 2022-03-02 | Review the communication methods for design artefact review periods to ensure all industry parties are made aware | Claire Silk | 2022-04-06 | Closed | Communication directly to BPRWG distribution list at the point that documents are published to the Portal. Weekly update in The Clock to provide detail of dates of Tranche releases and progress updates.
5-04 | 2022-03-02 | Confirm the definition of statuses assigned to review comments in Comment Logs | Claire Silk | 2022-04-06 | Closed | Comment statuses updated: Accepted – comments are agreed and documents have been updated to reflect the changes Rejected- comments have been reviewed and considered and the MHHS programme team have confirmed that changes will not be incorporated into the design. Action - Further discussions at sub group level or future actions are required in order for the changes to be incorporated into the design. Requires further clarification- Further information is required before a decision can be taken to accept the change into the design
5-06 | 2022-03-02 | Initial session to be arranged with St Clements to discuss the approach to the MPAN Enquiry Service requirements | Ian Smith | 2022-04-06 | Closed | Update- Session held
5-07 | 2022-03-02 | Open Working Group sessions to be arranged to cover MPAN Enquiry Service, Operational Choreography and Network Charging requirements | Claire Silk | 2022-04-06 | Closed | Closed- activity included in plan
5-08 | 2022-03-02 | Arrange sessions to discuss material BPRWG review feedback | Claire Silk | 2022-04-06 | Closed | Closed- Tranche Assurance and review of open Design Issues and Dependencies added to BPRWG as a standing agenda item
5-09 | 2022-03-02 | Schedule of activity for April onwards to be published- including placeholder sessions to discuss BPRWG review comments as required | Claire Silk | 2022-04-06 | Closed | Update- Forward view of schedule to June published on Portal: Design Working Group Schedule . Covered in agenda
5-10 | 2022-03-02 | Confirm whether Change of Agent-No Change of Supplier is included within the interfaces | Ian Smith | 2022-04-06 | Closed | Confirmed
5-11 | 2022-03-02 | Discuss feedback on process efficiency in more detail with Chris Bretten | Ian Smith | 2022-04-06 | Open | In progress- request for availability sent
5-12 | 2022-03-02 | Consider whether Technical Design documentation requires wider industry review prior to submission to DAG for approvaL | Ian Smith | 2022-04-06 | Closed | Closed- Technical artefacts are subject to review by the Level 4 Technical Design Working Group. Artefacts are published for wider industry review at the point of submission to DAG
S-13 | 2022-03-02 | Ensure all DAG decisions are cascaded to the Level 4 Working Groups and Sub-groups | Claire Silk | 2022-04-06 | Closed | Closed- covered in agenda
6-01 | 2022-04-06 | Confirm if the potential risk around the scale of data transfer has been considered as part of the technical design | Claire Silk | 2022-05-04 | Closed | The modelling that has been carried out as part of the technical design has shown that whilst the volumes are large for the energy industry they are comparatively small for event driven architectures.
6-02 | 2022-04-06 | Confirm the level of qualification relating to Design Principle 2- Energy Suppliers can choose how they deliver their TOM Data Services (direct or procured). Suppliers may perform any aspect of any service subject to qualification. | Ian Smith | 2022-05-04 | Closed | The Smart Data service as defined in the TOM will be a qualified entity with the MDR element being seperately qualified undert the SEC. The programme will be subsequently defining the qualification process alsongside the code drafting work. The design principle seeks to not place any un-necessary constrains on parties in their resolution of these services noting the optinality in terms of resolving elements to existing systems and / or procuring / outsourcing elements of the service in part or in whole.
6-03 | 2022-04-06 | JA to follow up with MH regarding the identified ‘gaps’ relating to ECS artefacts | Justin Andrews | 2022-05-04 | Closed | Meeting scheduled for w/c 2/05/22
6-04 | 2022-04-06 | Confirm that there are no further design artefacts for the Smart Sub-Group | Claire Silk | 2022-05-04 | Closed | Confirmed
6-05 | 2022-04-06 | Establish a separate sub-working group to cover Distributor requirements | Claire Silk | 2022-05-04 | Closed | Closed- Distributor requirements will be picked up under the new Reporting and Transition Sub-Group (replacing the ECS Sub-group).
6-06 | 2022-04-06 | Confirm the process for updating the BSCP’s- are the MHHS programme or the Code Bodies responsible for the initial drafting | Ian Smith/Andrew Margan | 2022-05-04 | Propose Closed | The MHHS Programme will be providing resource to assist with code drafting. This will be covered by the CCAG activity
6-07 | 2022-04-06 | Update MHHS Design Dashboard to include Meter Faults and Settlement Queries processes under relevant Service | Claire Silk | 2022-04-14 | Closed | Completed
6-08 | 2022-04-06 | Circulate updated MHHS Design Dashboard | Claire Silk | 2022-04-14 | Closed | Completed
6-09 | 2022-04-06 | Document and circulate process for approval of Design Artefacts | Claire Silk | 2022-05-04 | Propose Closed | The revised schedule and approach was communicated on 22nd June | M5 Plan Update
6-10 | 2022-04-06 | Review lead times for submission of Design Artefacts to DAG for approval | Claire Silk | 2022-05-04 | Closed | Completed
6-11 | 2022-04-06 | Confirm the significance of Tranche 1 comments still to be actioned and the impact on the timeline | Claire Silk | 2022-04-14 | Propose Closed | Tranche 1 comments in action status are associated to open design issues or dependencies. Resoluton of design issues and dependencies is refected in the revised schedule.
6-12 | 2022-04-06 | Schedule sub-group sessions to discuss Business Requirements | Claire Silk | 2022-05-04 | Propose Closed | Business Requirements were issued for offline review and drop in sessions provided to enable participants to discuss detail - due to the nature of the documents it was determined that this was the most efficient approach
7-01 | 2022-05-04 | Ensure Jonathan Hawkins is included on the distribution list for the Operational Choreography Working Group | Simon Chidwick | 2022-05-04 | Closed | Completed- email address updated
7-02 | 2022-05-04 | Arrange discussion with Chris Butterfield (Ovo) concerning Smart interactions with MHHS | Ian Smith | 2022-06-01 | Closed | Propose closed- Initial session held Monday 16th May- follow up session held and further session to be scheduled
7-15 | 2022-05-04 | Provide further detail to Ovo around the decision to replace the D0142 flow | Ian Smith | 2022-06-01 | Closed | The decision to replace the D0142 flow has been added to the Dissensus Register for further discussion
7-03 | 2022-05-04 | Design Issue ID and Dependency ID to be added to the slides in the DAG Summary Report to enable cross reference against Consolidated Comments Log | Claire Silk | 2022-05-04 | Closed | Completed- DAG Summary Report slides updated
7-04 | 2022-05-04 | Confirm approach to Interface Specifications | Ian Smith | 2022-06-01 | Closed | Interface specifications will be issued in Tranche 4 including those interfaces that were previously issues in T2. As the interfaces have evolved we wish to ensure that conventions are applied consistently. For precedding Tranches this will not impact the core data attributes that have been presented.
7-05 | 2022-05-04 | Arrange discussion with Mohammad Amin Fuggawala (Centrica) to understand potential gaps in processes in relation to REC timelines | Ian Smith | 2022-06-01 | Open | In Progress- feedback from initial session being processed
7-06 | 2022-05-04 | Confirm whether an additional review and approval cycle will be required once design artefacts are migrated to iServer | Ian Smith/Paul Pettitt | 2022-06-01 | Closed | Update- M5 baseline informed by current artefact set. Assurance of migration to be planned in post M5
7-07 | 2022-05-04 | Provide gap analysis/traceability matrix to demonstrate where there are expected changes. IS to arrange discussion with Blanka Caen (Centrica), Anne-Claire Leydier (UKPD) and Toye Coker (EDW) | Ian Smith | 2022-06-01 | Open | In progress- request for availability sent
7-08 | 2022-05-04 | Provide clarification around the comment resolution process to detail the steps to be followed to raise concerns where participants do not believe that comments have been addressed satisfactorily | Claire Silk | 2022-06-01 | Propose Closed | The revised schedule and approach was communicated on 22nd June | M5 Plan Update
7-09 | 2022-05-04 | Review option to include a list of areas requiring focus from specific constituencies as part of each Tranche review | Claire Silk | 2022-06-01 | Propose Closed | As part of the revised approach we have introduced a Participant Experience Workstream and will be developing tragetted signposting for participants as part of the review process
7-10 | 2022-05-04 | Provide a list of Design related RAID items ahead of programme RAID functionality being made available on the MHHS Portal | Claire Silk | 2022-06-01 | Propose Closed | Design specific risk, open design issues and dependencies are included within the Design Artefact Tracker | Design Artefact Tracker
7-11 | 2022-05-04 | Provide a clear view of the outstanding issues to be discussed in each sub-working group to ensure participants are able to focus resource | Claire Silk | 2022-06-01 | Propose Closed | See agenda item- The revised Working Group Schedule provides a view of Sub-Working Group activity at artefact level
7-12 | 2022-05-04 | Consider the risk that the removal of the second review period for Tranche 2 may result in issues not being identified as participants have not completed a full review of design artefacts | Claire Silk/Ian Smith | 2022-06-01 | Closed | Tranche 2 assurance comments incorporated into open design issues and dependencies logs- Tranche 2 artefacts conditionally approved by DAG on 8th June
7-13 | 2022-05-04 | Review process to ensure that key changes to design artefacts as a result of comments which have not been previously discussed in the sub-working group are fed back for discussion/agreement | Claire Silk | 2022-06-01 | Propose Closed | The revised approach for Tranche 4 has introduced a step in the comment resolution process whereby proposed changes to artefacts will be communicated to participants for review prior to documents being updated. Any objections to proposed changes should be directed to the Design team and will be discussed in the BPRWG meeting
7-14 | 2022-05-04 | Note the risk that participants may not have the necessary resource available to cover sub-working group activity, review activity and resolution of outstanding issues in parallel | Claire Silk | 2022-06-01 | Propose Closed | The revised schedule takes into account participant resource, particularly over the summer period. We also propose to release documents for review as soon as they are ready to enable participants to better manage their resources in completing review activity
08-01 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates)- Assess whether there is an opportunity to discuss non-consensus items in Working Group prior to escalation to DAG | Warren Fulton | 2022-06-08 | Propose Closed | A standing agenda item has been included in BPRWG to review the Dissensus Register and determine actions required to achieve consensus or agreement to escalate to DAG for decision
08-02 | 2022-06-01 | Raised by Robert Langdon (SMS Plc)- Consider whether the questions asked of DAG with regard to Tranche 2 conditional approval should also be retrospectively applied to Tranche 1 artefacts. | Warren Fulton | 2022-06-08 | Propose Closed | Tranche 1 was conditionally approved by DAG on the basis that the open design issues and dependencies were understood. Any required changes to these documents will be picked up as part of the Tranche 4 activity and E2E review
08-03 | 2022-06-01 | Raised by Mohammad Amin Fuggawala (Centrica)- Ensure existing Smart journey relating to Suppliers not being able to communicate with a smart meter is reflected in the process specific to CoS reads and not just the general CoS process. | Ian Smith | 2022-07-06 | Closed | In Progress- covered in Change of Supplier Read Sub-Group
08-05 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates)- Ensure reverse traceability to show which comments are feeding into which design issues and into sub working group discussions. | Ian Smith | 2022-07-06 | Closed | Column ‘P’ in the Consolidated Comments Log references the SNAG_ID or DEP_ID related to a comment. The associated detail for each Design Issue (SNAG_ID) or Dependency (DEP_ID) can be found in the Design Artefact Tracker
08-06 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates)- Ensure that any comments that have been marked as Accepted/Rejected but require further action are reviewed and updated accordingly | Ian Smith | 2022-07-06 | Open | Update- comment review assurance underway and will be completed by the end of July
08-07 | 2022-06-01 | Raised by Jonathan Hawkins (RECCo)- Ensure that MDR ID issue is prioritised as this will need to be resolved prior to Tranche 4 due to CP Impact Assessment occurring later this month. | Ian Smith | 2022-07-06 | Closed | Update- TDWG reached position on participant ID's
08-08 | 2022-06-01 | Raised by Matt Hall (Elexon)- Provide visibility of schedule for Sub-Working Group sessions to discuss specific design issues | Claire Silk | 08/06//22 | Propose Closed | In progress- The Working Group schedule has been published
08-09 | 2022-06-01 | Raised by David Morley (OVO Energy)- arrange follow up session with Ovo to review comments that were ‘rejected’ due to misinterpretation of the original comment | Ian Smith | 2022-07-06 | Open | Update- follow up session held, feedback being processed
08-10 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates)- Confirm whether Change of Supplier Read will cover estimated reads, negative reads and consumption adjustments | Ian Smith | 2022-07-06 | Propose Closed | In Progress- covered in Change of Supplier Read Sub-Group
08-11 | 2022-06-01 | Raised by Mohammad Amin Fuggewala (Centrica)- Confirm whether last released versions of the Change of Supplier Reads process includes the latest updates | Ian Smith | 2022-07-06 | Closed | The latest version did include updates- this artefact is currently under review with the sub-working group and subject to further changes
08-12 | 2022-06-01 | Raised by Steve Thomas (CGI)- issues raised around confusion arising from updates to linked artefacts in different tranches – action to ensure full traceability between related artefacts and clear signposting of changes | Claire Silk | 2022-07-06 | Open | As part of the revised approach we are bringing in dedicated resource to manage change control and traceability across all artefacts. We have also introduced steps to provide clear signposting of changes across all related artefacts
08-13 | 2022-06-01 | Raised by Seth Chapman (Callisto)- Review options to track changes in documents to provide clarity around what has changed since the previous version | Claire Silk | 2022-07-06 | Open | As part of the revised approach we are bringing in dedicated resource to manage change control and traceability across all artefacts. We have also introduced steps to provide clear signposting of changes across all related artefacts
08-14 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates) SNAG_ID 033 – Consumption Validation within MDS - Ensure upstream impacts are captured as well as downstream | Ian Smith | 2022-07-06 | Closed | Accepted
08-15 | 2022-06-01 | Raised by James Murphy (Stark)- DEP-020 – LSS Delivery to non-DIP actors – Update dependency to reflect broader scope- ISD, MDS, VAS etc. | Ian Smith | 2022-07-06 | Closed | Dependency Updated
08-16 | 2022-06-01 | Raised by Stephen Mclaughlin (Scottish Power)- DEP-016 – Consumption Adjustments/Correction – Update to Tranche 4 | Ian Smith | 2022-07-06 | Closed | Dependency updated
08-17 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates)- Update the Dependency Log to include detail of artefact(s) impacted and the planned sub-working group sessions where each dependency will be discussed | Warren Fulton | 2022-07-06 | Open | In Progress- The Design Artefact Tracker and Working Group Schedule are being updated to reflect the revised schedule and incorporate this detail
08-18 | 2022-06-01 | Raised by Matt Hall (Elexon)- Arrange follow up session to discuss Tranche 2 assurance feedback provided by Helix | Ian Smith/Warren Fulton | 2022-06-08 | Closed | Session held
08-19 | 2022-06-01 | Raised by Daniel Tadecicco (St Clements)/ Jonathan Hawkins (RECCo)- arrange discussion to review the issues around R-40 and BP003A and whether CSS changes can be considered or not. | Ian Smith | 2022-07-06 | Open | Update- Dissensus item for discussion at BPRWG 27th July
08-20 | 2022-06-01 | Raised by Joseph Kavanagh (BUUK Infrastructure) Consider different approaches to conditional approval in order to reach M5 baseline | Warren Fulton | 2022-07-06 | Propose Closed | The revised schedule and approach was communicated on 22nd June | M5 Plan Update
08-21 | 2022-06-01 | Raised by Tom Chevalier (Power Data Associates) Ensure typo’s etc. that arose from the review of Tom Chevalier’s assurance comments are updated in the artefacts and consider how these changes will be clearly tracked and visible to Participants | Ian Smith | 2022-07-06 | Closed | Quality checks ongoing and further change control processes to be adopted
08-22 | 2022-06-01 | Raised by Jenny Rawlinson- Based on the unlikeliness distribute the T4 artefacts for Level 4 review by 08/06, amend RAG status for Tranche 4 to Red | Warren Fulton | 2022-07-06 | Propose Closed | RAG status updated on MHHS Dashboard and status updated in Design Artefact Tracker | Design Artefact Tracker
08-23 | 2022-06-01 | Raised by Robert Langdon- Confirm evolution of decision to replace D0142 with DIP flow | Ian Smith | 2022-07-06 | Closed | D0142 will be added to the dissensus log for further discussion
08-24 | 2022-06-01 | Raised by Matt Hall (Elexon)- Review length and frequency of BPRWG meeting to ensure sufficient time to cover all agenda items (e.g. RAID) | Warren Fulton | 2022-07-06 | Propose Closed | Proposal to increase the frequency of the BPRWG meeting to fortnightly to be tabled at the next meeting
08-25 | 2022-06-01 | Raised by David Morley (OVO Energy)- review actions in propose closed status | Warren Fulton | 2022-07-06 | Propose Closed | Full Action Log reviewed and updated- BPRWG asked to review the Log ahead of the meeting on 29th June and raise any objections
08-26 | 2022-06-01 | Raised by James Murphy (Stark)- concerns expressed that the design does not meet the TOM as there are issues around the Level Playing Field Principle with regard to access to Smart metering data | Ian Smith | 2022-07-06 | Closed | The Level Playing Field Principle is covered by the standing agenda item at DAG relating to MP162- superceded by activity in DAG
08-27 | 2022-06-01 | Raised by David Morley (OVO Energy)- concern raised around design ‘moving at pace’ will not allow time to review the e2e before baseline and address outstanding comments | Ian Smith | 2022-07-06 | Closed | The revised schedule and approach was communicated on 22nd June | M5 Plan Update
08-29 | 2022-06-01 | Raised by Matt Hall- issue raised around ability to plan resources to support design activity due to lack of visibility of Working Group schedule | Claire Silk | 2022-07-06 | Propose Closed | Added to the Design Risk Log in the Design Artefact Tracker | Design Artefact Tracker
09-01 | 2022-06-29 | Raised by Mohammad Amin Fuggawala (Centrica)- include target dates for follow up sessions to be arranged against open actions | Ian Smith | 2022-07-13 | Propose Closed | Requests for availability sent to actin owners
09-02 | 2022-06-29 | Raised by Lee Stone (E.on)- Add contingency to Working Group swimlane on the Plan on a Page | Warren Fulton | 2022-07-13 | Open
09-03 | 2022-06-29 | Raised by Mohammad Amin Fuggawala (Centrica)- Provide a breakdown of all reporting interfaces included in Reporting Artefacts | Claire Silk | 2022-07-13 | Open
09-04 | 2022-06-29 | Raised by Seth Chapman (Callisto) - expand the descriptions for open design issues | Ian Smith | 2022-07-13 | Open | In Progress- to be completed by end July
09-05 | 2022-06-29 | Raised by Seth Chapman (Callisto) Update description for SNG_027- COS Reads to reflect evolution of comment responses | Ian Smith | 2022-07-13 | Closed | Updated
09-06 | 2022-06-29 | Raised by Seth Chapman (Callisto)- IS to arrange session with SC, SJ, JB to discuss the wording of the SDS requirements to ensure clarity of requirements for qualification and code drafting against information requirements | Ian Smith | 2022-07-13 | Closed | Update- Session held
09-07 | 2022-06-29 | Raised by Seth Chapman (Callisto)- more detail required for Dissensus items to reflect pro's and con's | Ian Smith | 2022-07-13 | Closed | Update- additional detail included in BPRWG meeting papers
09-08 | 2022-06-29 | Raised by Lee Stone (Eon)- provide more preparation time for participants to review Dissensus material ahead of BPRWG session | Claire Silk | 2022-07-13 | Open
09-09 | 2022-06-29 | Raised by Seth Chapman (Callisto)- confirm the process for SWG review of Registration Service Requirements | Claire Silk | 2022-07-13 | Open
09-10 | 2022-06-29 | Raised by Seth Chapman (Callisto)- provide a view of other working groups and work with PMO to try to avoid meeting clashes | Claire Silk | 2022-07-13 | Open
09-11 | 2022-06-29 | DIS001- discussions to be picked up in the Operational Choreography Sub-Working Group | Ian Smith | 2022-07-13 | Closed | Update- believe agreement reached in Sub-Group
09-12 | 2022-06-29 | DIS002/DIS003- IS to arrange discussion with JH and confirm next steps | Ian Smith | 2022-07-13 | Open | Update- To be arranged
09-13 | 2022-06-29 | DIS004/DIS005/DIS006- Design Team to provide paper for each item to be issued for review | Ian Smith | 2022-07-13 | Closed | Update- additional detail included in BPRWG meeting papers
09-14 | 2022-06-29 | Raised by Seth Chapman (Callisto)- DIS004- amend wording to read 'an Independent Agent' | Claire Silk | 2022-06-29 | Propose Closed | Dissensus Register updated to reflect change