## Cover Page
MHHS M10/M11 Cutover Delivery Plan
Document owner: | Document number: | Version:
MHHS Transition & Operational Readiness Team | MHHS-DEL2522 | 1
Status: | Date: | Classification:
Baselined following MCAG Approval | 2024-06-05 | External

## Introduction
Document Purpose
This document outlines each individual activity that is included within the Cutover plan including when it is due to take place and who is responsible for it. This document is intended to act as the complete list of activities that will need to take place in the lead up to and during the Cutover period.
Objectives
The document aims to: - Establish a clear timeline with milestones for the Cutover period - Identify key dependencies between activities - Serve as a central communication tool that stakeholders can refer to throughout the Cutover period
Delivery Plan
Column Name | Description of the data in each of the columns within Delivery Plan worksheet
Category | Cutover tasks required for completion
Cutover WBS | Hierarchical breakdown of cutover tasks
Cutover Plan Reference | Task reference number from MHHS-DEL2521 - MHHS M10/M11 Cutover Plan
Activity | Cutover tasks required for completion
Responsible Party | Party responsible for executing each sub-activity
Cutover Dependencies | Activities that must be completed before a particular activity can start
Start Date | Planned start date for an activity
Due Date | Planned due date for completing an activity

## Delivery Plan
Days
Category | Cutover WBS | Cutover Plan Reference | Activity | Responsible Parties | Cutover Dependencies | Start Date | Due Date | Baseline Start Date | time axis 2025-01-01 to 2025-04-29
Test Completion | 1.1 | N/A | SIT MVC Test Exit Report Approved | SIT MVC Participants, MHHS Programme |  | 2025-02-07 | 2025-02-07 |  | 2025-02-07: p; 2025-04-29: #REF!
Pre-Requisites for M10 | 2.1.1 | 5.1.1 | SIT MVC Participant Qualification | REC Code Manager, BSC PAB, SIT Participants, MHHS Programme | Qualification of the SIT MVC will be a key dependency for the Programme to progress to and approve M10 | 2024 | 2025-02-21 |  | 2025-01-01: g; 2025-01-02: g; 2025-01-03: g; 2025-01-04: g; 2025-01-05: g; 2025-01-06: g; 2025-01-07: g; 2025-01-08: g; 2025-01-09: g; 2025-01-10: g; 2025-01-11: g; 2025-01-12: g; 2025-01-13: g; 2025-01-14: g; 2025-01-15: g; 2025-01-16: g; 2025-01-17: g; 2025-01-18: g; 2025-01-19: g; 2025-01-20: g; 2025-01-21: g; 2025-01-22: g; 2025-01-23: g; 2025-01-24: g; 2025-01-25: g; 2025-01-26: g; 2025-01-27: g; 2025-01-28: g; 2025-01-29: g; 2025-01-30: g; 2025-01-31: g; 2025-02-01: g; 2025-02-02: g; 2025-02-03: g; 2025-02-04: g; 2025-02-05: g; 2025-02-06: g; 2025-02-07: g; 2025-02-08: g; 2025-02-09: g; 2025-02-10: g; 2025-02-11: g; 2025-02-12: g; 2025-02-13: g; 2025-02-14: g; 2025-02-15: g; 2025-02-16: g; 2025-02-17: g; 2025-02-18: g; 2025-02-19: g; 2025-02-20: g; 2025-02-21: q; 2025-04-29: #REF!
| 2.1.2 | 5.1.2 | Non-SIT LDSO Qualification | REC Code Manager, BSC PAB, Non-SIT LDSOs, MHHS Programme | The qualification of all LDSOs is a key dependency for M10 and for the MHHS Migration period. For it to be possible to migrate or reverse migrate all MPANs following M11, there is a dependency on all LDSOs being qualified | 2024 | 2025-02-21 |  | 2025-01-01: g; 2025-01-02: g; 2025-01-03: g; 2025-01-04: g; 2025-01-05: g; 2025-01-06: g; 2025-01-07: g; 2025-01-08: g; 2025-01-09: g; 2025-01-10: g; 2025-01-11: g; 2025-01-12: g; 2025-01-13: g; 2025-01-14: g; 2025-01-15: g; 2025-01-16: g; 2025-01-17: g; 2025-01-18: g; 2025-01-19: g; 2025-01-20: g; 2025-01-21: g; 2025-01-22: g; 2025-01-23: g; 2025-01-24: g; 2025-01-25: g; 2025-01-26: g; 2025-01-27: g; 2025-01-28: g; 2025-01-29: g; 2025-01-30: g; 2025-01-31: g; 2025-02-01: g; 2025-02-02: g; 2025-02-03: g; 2025-02-04: g; 2025-02-05: g; 2025-02-06: g; 2025-02-07: g; 2025-02-08: g; 2025-02-09: g; 2025-02-10: g; 2025-02-11: g; 2025-02-12: g; 2025-02-13: g; 2025-02-14: g; 2025-02-15: g; 2025-02-16: g; 2025-02-17: g; 2025-02-18: g; 2025-02-19: g; 2025-02-20: g; 2025-02-21: q; 2025-04-29: #REF!
| 2.2 | 5.2 | Completion of the MHHS Data Cleanse | Suppliers, LDSOs, MEMs, DCC, MHHS Programme SI | Programme Participants carrying out the activities that they are responsible for as set out within the Data Cleanse Plan | 2024 | 2025-02-26 | bar: 2025-01-01 to 2025-02-26
| 2.3 | 5.3 | Early Life Support Implemented | MHHS Programme, Elexon, Central Services | Approval of the Early Life Support Model by the MCAG in 2024 | 2024 | 2025-03-07 | bar: 2025-01-01 to 2025-03-07
| 2.4 | 5.4 | MCC Tested and Ready to Operate | MHHS Programme Migration Team | This is a key dependency for the MHHS Migration period as it will allocate migration capacity to participants | 2025-03-07 | 2025-03-07 | bar: 2025-03-07
| 2.5.1 | 5.5 | Market-wide Participant MHHS Supporting Functionality Ready - Confirmation from Code Bodies | Suppliers, MOPs and DCs |  | 2024 | 2025-03-03 |  | 2025-01-01: g; 2025-01-02: g; 2025-01-03: g; 2025-01-04: g; 2025-01-05: g; 2025-01-06: g; 2025-01-07: g; 2025-01-08: g; 2025-01-09: g; 2025-01-10: g; 2025-01-11: g; 2025-01-12: g; 2025-01-13: g; 2025-01-14: g; 2025-01-15: g; 2025-01-16: g; 2025-01-17: g; 2025-01-18: g; 2025-01-19: g; 2025-01-20: g; 2025-01-21: g; 2025-01-22: g; 2025-01-23: g; 2025-01-24: g; 2025-01-25: g; 2025-01-26: g; 2025-01-27: g; 2025-01-28: g; 2025-01-29: g; 2025-01-30: g; 2025-01-31: g; 2025-02-01: g; 2025-02-02: g; 2025-02-03: g; 2025-02-04: g; 2025-02-05: g; 2025-02-06: g; 2025-02-07: g; 2025-02-08: g; 2025-02-09: g; 2025-02-10: g; 2025-02-11: g; 2025-02-12: g; 2025-02-13: g; 2025-02-14: g; 2025-02-15: g; 2025-02-16: g; 2025-02-17: g; 2025-02-18: g; 2025-02-19: g; 2025-02-20: g; 2025-02-21: g; 2025-02-22: g; 2025-02-23: g; 2025-02-24: g; 2025-02-25: g; 2025-02-26: g; 2025-02-27: g; 2025-02-28: g; 2025-03-01: g; 2025-03-02: g; 2025-03-03: q; 2025-04-29: #REF!
| 2.5.2 | 5.5 | Market-wide Participant MHHS Supporting Functionality Ready | Suppliers, MOPs and DCs | The Code Bodies have confirmed on 03/03 that this activity has taken place | 2024 | 2025-03-10 |  | 2025-01-01: g; 2025-01-02: g; 2025-01-03: g; 2025-01-04: g; 2025-01-05: g; 2025-01-06: g; 2025-01-07: g; 2025-01-08: g; 2025-01-09: g; 2025-01-10: g; 2025-01-11: g; 2025-01-12: g; 2025-01-13: g; 2025-01-14: g; 2025-01-15: g; 2025-01-16: g; 2025-01-17: g; 2025-01-18: g; 2025-01-19: g; 2025-01-20: g; 2025-01-21: g; 2025-01-22: g; 2025-01-23: g; 2025-01-24: g; 2025-01-25: g; 2025-01-26: g; 2025-01-27: g; 2025-01-28: g; 2025-01-29: g; 2025-01-30: g; 2025-01-31: g; 2025-02-01: g; 2025-02-02: g; 2025-02-03: g; 2025-02-04: g; 2025-02-05: g; 2025-02-06: g; 2025-02-07: g; 2025-02-08: g; 2025-02-09: g; 2025-02-10: g; 2025-02-11: g; 2025-02-12: g; 2025-02-13: g; 2025-02-14: g; 2025-02-15: g; 2025-02-16: g; 2025-02-17: g; 2025-02-18: g; 2025-02-19: g; 2025-02-20: g; 2025-02-21: g; 2025-02-22: g; 2025-02-23: g; 2025-02-24: g; 2025-02-25: g; 2025-02-26: g; 2025-02-27: g; 2025-02-28: g; 2025-03-01: g; 2025-03-02: g; 2025-03-03: g; 2025-03-04: g; 2025-03-05: g; 2025-03-06: g; 2025-03-07: g; 2025-03-08: g; 2025-03-09: g; 2025-03-10: q; 2025-04-29: #REF!
Code Bodies | 3.1.1 | 7.1.1 | Code Changes Designated | REC Code Manager, BSCCo, Ofgem, MHHS Programme | This activity is dependant on the approval of M10 | 2025-03-10 | 2025-03-10 | bar: 2025-03-10
| 3.1.2 | 7.1.2 | SIT Participant Qualification - The final date by which participant qualification status can be confirmed for participants to be ready for the start of Migration at M11. | REC Code Manager, BSC PAB, SIT Participants |  | 2024 | 2025-03-14 | bar: 2025-01-01 to 2025-03-14
Elexon Services | 4.1.1 | 7.2.1 | Production DIP Portal (DIP Deployment) | DIP Manager, Elexon |  | 2025-02-21 | 2025-02-21 |  | 2025-02-21: p; 2025-04-29: #REF!
| 4.1.2 | 7.2.1 | Production Certificates (DIP Deployment) | DIP Manager, Elexon |  | 2025-02-21 | 2025-02-21 | bar: 2025-02-21
| 4.1.3 | 7.2.2 | Elexon Central Services Deployment | DIP Manager, Elexon | The Production ISD data must have been created and maintained in line with MDD data prior to M10. The PAB on the 21/02/2025 should approve the ISD for release at M10 | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q; 2025-04-29: #REF!
| 4.1.4 | 7.2.3 | Service Management Go-Live | Elexon | The completion of Service Design by Elexon | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q; 2025-04-29: #REF!
Central Services Deployment of New Functionality | 5.1.1 | 7.3.1 | DTS | Electralink, RECCo | RECCo will have provided ElectraLink with the relevant technical specification for the DTS release which will support M10. All Market Participants will be required to have implemented the changes to ensure continued operation of their Legacy processes | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q; 2025-04-29: #REF!
| 5.1.2 | 7.3.2 | EES | RECCo | The EES is a key Central Service and therefore, the completion of this activity is a key dependency for the approval of M10 | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q; 2025-04-29: #REF!
| 5.1.3 | 7.3.3 | DCC (Functionality available June 2024) | DCC | The successful releases of the MHHS supporting versions of the CSS and DSP in June 2024 | 2024-06-01 | 2024-06-30 |  | 2025-04-29: #REF!
LDSOs | 6.1.1 | 7.4.1 | MPRS, UMSO Role, LDSO Role Operational | LDSOs | Each LDSOs DIP Connection Provider will need to have become qualified so that the relevant LDSO can communicate with the DIP | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q; 2025-04-29: #REF!
| 6.1.2 | 7.4.1 | Population of Domestic Premises Indicator | MMHS Programme, DCC, LDSOs | This is dependant on the new MPRS functionality being operational | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q; 2025-04-29: #REF!
| 6.1.3 | 7.4.1 | Population of Market Segment | MHHS Programme, LDSOs | This is dependant on the new MPRS functionality being operational | 2025-03-07 | 2025-03-09 |  | 2025-03-07: p; 2025-03-08: g; 2025-03-09: q
Governance | 7.1 | 4 | TORWG | MHHS Programme |  | 2025-03-05 | 2025-03-05 |  | 2025-03-05: p; 2025-04-29: #REF!
| 7.2 | 4 | MCAG | MHHS Programme |  | 2025-03-07 | 2025-03-07 |  | 2025-03-07: p; 2025-04-29: #REF!
| 7.3 | 4 | Central Systems live and Codes designated at 00:00 (T3) | MHHS Programme |  | 2025-03-10 | 2025-03-10 |  | 2025-03-10: p; 2025-04-29: #REF!
| 7.4 | 4 | TORWG | MHHS Programme |  | 2025-03-11 | 2025-03-11 |  | 2025-03-11: p; 2025-04-29: #REF!
| 7.5 | 4 | PSG | MHHS Programme |  | 2025-03-12 | 2025-03-12 |  | 2025-03-12: p; 2025-04-29: #REF!
| 7.6 | 4 | TORWG | MHHS Programme |  | 2025-03-31 | 2025-03-31 |  | 2025-03-31: p; 2025-04-29: #REF!
| 7.7 | 4 | MCAG | MHHS Programme |  | 2025-04-02 | 2025-04-02 |  | 2025-04-02: p; 2025-04-29: #REF!
| 7.8 | 4 | PSG | MHHS Programme |  | 2025-04-04 | 2025-04-04 |  | 2025-04-04: p; 2025-04-29: #REF!
TORWG 05/03 Inputs | 8.1 | 4 | Confirmation that Pre-migration Data Cleanse Activities have successfully taken place | Suppliers, Agents, LDSOs |  | 2025-02-26 | 2025-02-26 | bar: 2025-02-26
| 8.2 | 4 | Confirmation of Qualification Status for SIT MVC | SIT MVC, Code Bodies |  | 2025-03-03 | 2025-03-03 |  | 2025-03-03: p; 2025-04-29: #REF!
| 8.3 | 4 | Confirmation of Qualification Status for Non-SIT LDSOs | Non-SIT LDSOs, Code Bodies |  | 2025-03-03 | 2025-03-03 |  | 2025-03-03: p; 2025-04-29: #REF!
| 8.4 | 4 | Confirmation of Qualification Status of at least one Supplier and their contracted Agents | Suppliers, MHHS Programme |  | 2025-03-03 | 2025-03-03 |  | 2025-03-03: p; 2025-04-29: #REF!
| 8.5 | 4 | Declaration from all Central Services and LDSOs that they are in a position to move forwards | DIP Manager, Elexon (ECS, ISD, Service Management), Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) |  | 2025-03-03 | 2025-03-03 | bar: 2025-03-03
| 8.6 | 4 | Market-wide Participant MHHS Migration Supporting Functionality is Live | Suppliers, Agents |  | 2025-03-03 | 2025-03-03 |  | 2025-03-03: p; 2025-04-29: #REF!
MCAG 07/03 Inputs | 9.1 | 4 | Recommendation from TORWG that the Programme should enter M10 | TORWG Members, MHHS Transition Team |  | 2025-03-05 | 2025-03-07 |  | 2025-03-05: p; 2025-03-06: g; 2025-03-07: q; 2025-04-29: #REF!
TORWG 11/03 Inputs | 10.1 | 4 | Early Life Support model is in place | MHHS Programme |  | 2025-03-07 | 2025-03-07 |  | 2025-03-07: p; 2025-04-29: #REF!
| 10.2 | 4 | MCC Operational | MHHS Programme |  | 2025-03-07 | 2025-03-07 |  | 2025-03-07: p; 2025-04-29: #REF!
| 10.3 | 4 | Self-Declaration from all Central Services and LDSOs that Cutover activities have been successfully carried out | Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) |  | 2025-03-10 | 2025-03-10 |  | 2025-03-10: p; 2025-04-29: #REF!
| 10.4 | 4 | Confirmation that DIP and ECS have been deployed, Service management is active, ISD has been populated | Elexon (ECS, ISD, Service Management), DIP Manager |  | 2025-03-10 | 2025-03-10 |  | 2025-03-10: p; 2025-04-29: #REF!
| 10.5 | 4 | Self-Declarations against all M10 Data Cleanse Activities | LDSOs |  | 2025-03-10 | 2025-03-10 |  | 2025-03-10: p; 2025-04-29: #REF!
| 10.6 | 4 | IF-047 has been sent | ECS |  | 2025-03-10 | 2025-03-10 | bar: 2025-03-10
PSG 12/03 Inputs | 11.1 | 4 | Recommendation from TORWG that PSG should approve M10 | TORWG Members, MHHS Transition Team, PSG |  | 2025-03-11 | 2025-03-12 |  | 2025-03-11: p; 2025-03-12: q; 2025-04-29: #REF!
TORWG 31/03 Inputs | 12.1 | 4 | Confirmation of Qualified Parties from Code Bodies | Code Bodies, SIT Participants |  | 2025-03-14 | 2025-03-28 |  | 2025-03-14: p; 2025-03-15: g; 2025-03-16: g; 2025-03-17: g; 2025-03-18: g; 2025-03-19: g; 2025-03-20: g; 2025-03-21: g; 2025-03-22: g; 2025-03-23: g; 2025-03-24: g; 2025-03-25: g; 2025-03-26: g; 2025-03-27: g; 2025-03-28: q
| 12.2 | 4 | Self-Declaration that MHHS Functionality will be deployed to Production by Qualified parties | All Qualified Parties |  | 2025-03-28 | 2025-03-28 |  | 2025-03-28: p; 2025-04-29: #REF!
| 12.3 | 4 | Production Service Activation Activities have taken place | All Qualified Parties |  | 2025-03-28 | 2025-03-28 |  | 2025-03-28: p; 2025-04-29: #REF!
MCAG 02/04 Inputs | 13.1 | 4 | Confirmation of Qualified Parties from TORWG | TORWG, MHHS Transition Team |  | 2025-04-02 | 2025-04-02 |  | 2025-04-02: p; 2025-04-29: #REF!
PSG 04/04 Inputs | 14.1 | 4 | Recommendation from MCAG that the Programme can approve M11 | MCAG, MHHS Transition Team |  | 2025-04-02 | 2025-04-02 |  | 2025-04-02: p; 2025-04-29: #REF!
Note on H61: Microsoft Office User: Qualification to be confirmed by 14/03 Confirmation from Code Bodies to be shared by 28/03