## Cover Page
MHHS M10 Acceptance Criteria
Document owner: | Document number: | Version:
MHHS Transition & Operational Readiness Team | MHHS-DEL2537 | 1
Status: | Date: | Classification:
Baselined following MCAG Approval | 2024-06-05 | External

## M10 - Updated
M10 Acceptance Criteria
No. | Milestone | Workstream | Criterion | Owners
1 | M10 | Testing | End of SIT MVC testing | SIT Participants, Programme
2 | M10 | Testing | IPA M10 Assurance Report developed and agreed | IPA
3 | M10 | Qualification | Non-SIT LDSO Qualification Testing complete | Non-SIT LDSOs only, Programme
4 | M10 | Qualification | A minimum of 1 supplier & required contracted agents are qualified and ready to operate under new MHHS arrangements | SIT Participants, Code Bodies
5 | M10 | Qualification | All LDSOs qualified | LDSOs, Code Bodies
6 | M10 | Data | All pre-migration data cleanse activities complete | Programme Participants
7 | M10 | Data | All data migration activities set out in the cutover plan complete | Programme Participants
8 | M10 | Data | ISD fully populated by Elexon | Elexon
9 | M10 | Code | Significant Code Review Powers (SCR) enacted by Ofgem (M7) and updates to regulatory code ready to be implemented at M8 | Ofgem
10 | M10 | Migration | Migration Schedule approved | Programme
11 | M10 | Migration | Migration Framework approved | Programme
12 | M10 | Migration | Migration Control Centre (MCC) delegation of authority approved | Programme
13 | M10 | Migration | Migration incentives implemented | Programme
14 | M10 | Migration | MCC tested and ready to operate | Programme
15 | M10 | Transition | Service Delivery Operating Model in place | Programme
16 | M10 | Transition | Service Delivery Operating Model in place (Self-Certification) | LDSOs, Central Parties
17 | M10 | Transition | Early Life Support Model defined | Programme
18 | M10 | Transition | Early Life Support Model arrangements in place and operational | All SIT Participants, Code Bodies, BSC PAB, REC PAB
19 | M10 | Transition | Early Life Support Model arrangements in place and operational (Self-Certification) | LDSOs, Central Parties, Code Bodies, BSC PAB, REC PAB
20 | M10 | Transition | M10/M11 Cutover Plan in place | Programme
21 | M10 | Transition | Central Programme Party Cutover Plans in place | Central Programme Parties
22 | M10 | Transition | Production environment in place for LDSOs and Central Parties | All SIT Participants
23 | M10 | Transition | Service activation complete to DIP Production environment for Central Parties and LDSOs | All SIT Participants
24 | M10 | Transition | Cutover Plan executed | Programme
25 | M10 | Planning | M10 Risk Assessment undertaken | Programme
26 | M10 | Planning | Roles and responsibilities post-M10 agreed and accepted | Code Bodies, LDSOs, Central Parties
27 | M10 | Planning | M10 Work off plan agreed (if required) | Programme