## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | BP003 Reverse Migration Test cases initial draft for Test scenario TC_BP003_01 | Syed Naveedh |  | 2024-04-03
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP003_TestScenarios
Test Scenario ID | Role (s) | Theme | Business Process | BP Steps | Interface | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Notes
TS_BP003_01 | Registration Service / LDSO | MPAN Ownership | BPM-003 - Change of Service – Data Service – Reverse Migration |  |  | Update Registration Details and process de-appointment notification | For prospective appointments the Registration Service to issue IF-003 to the DIP which informs that the Data Service is being de-appointed. DIP will publish PUB-003 to test harness (Outgoing DS / Outgoing Supplier / EES) and LDSO. | The boundaries for this scenario are as follows Starting point: The starting point for this scenario will be the CSS simulator. For prospective appointments the Registration Service to hold the MPANs in the queue and re-process after receiving from CSS simulator/ an agreed mechanism, until the Metering Service 'eff from date' comes into effect End point: The ending point will be test harness (Outgoing DS / Outgoing Supplier / EES) and LDSO to receive PUB-003 | Segment S (Smart) with prospective appointment Segment S (Traditional) with prospective appointment Segment A (Advanced) with prospective appointment |  | 3 | H | VH | MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 MHHS-RMigration-CoA(DS)-RS-002 MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 MHHS-RMigration-CoA(DS)-LDSO-001 MHHS-RMigration-CoA(DS)-LDSO-002

## TC_BP003_01_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_01_01 | Data service de-appointment and occurance of reverse migration | TS_BP003_01 | Pre req: 1. Registration service should hold already migrated MPAN 2. Switch request from new supplier and agent appointment should be true 3. Single MPAN Segment S (Smart) IF-003 "Notifcation of Reverse Migration & DeAppointment " from Registration service to DIP with the following characteristics. • (DI-999)Event Code = [ReverseMigNotification] • (DI-819)De-Appointment Reason Code = CSUPP = Change of Supply | LDSO receiving PUB-003 "Notifcation of Reverse Migration & DeAppointment" to confirm the Data service de-appointment and occurance of reverse migration
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002-Step 1006 (120)/Step 1007 (125) | MHHS-RMigration-CoA(DS)-RS-002 MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 | Registration service | Registration service | NA | CSS batch will be run automatically (usually every 2 hours or more frequent) or the tester will use the CSS simulator. Previously migrated MPAN to be picked up by the batch.For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N
2 | BP002-Step 1008 (130) | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 | Registration service | DIP | IF-003 | IF-003 "Notifcation of Reverse Migration & DeAppointment " will be sent to the DIP which inforDS that the DS is being de-appointed. Registration Service should include identity of DC in IF-003 if this data was provided in the D0205. | Y | Evidence of IF-003 sent to DIP
3 | BP002-Step 1009/1011 | MHHS-RMigration-CoA(DS)-LDSO-001 MHHS-RMigration-CoA(DS)-LDSO-002 | DIP | LDSO | PUB-003 | LDSO to receive PUB-003 informing of DS de-appointment notification and to confirm the occurance of reverse migraiton | Y | Evidence of LDSO receiving PUB-003 to confirm the Data service de-appointment and occurance of reverse migration
4 | BP002-Step 1009/1013/1012/1010 | NA | DIP | Test harness (Outgoing DS / Outgoing Supplier / EES) | PUB-003 | Test harness (Outgoing DS / Outgoing Supplier / EES) to receive PUB-003 informing of DS de-appointment notification and to confirm the occurance of reverse migraiton | N | NA

## TC_BP003_01_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_01_02 | Data service de-appointment and occurance of reverse migration | TS_BP003_01 | Pre req: 1. Registration service should hold already migrated MPAN 2. Switch request from new supplier and agent appointment should be true 3. Single MPAN Segment S (Traditional) IF-003 "Notifcation of Reverse Migration & DeAppointment " from Registration service to DIP with the following characteristics. • (DI-999)Event Code = [ReverseMigNotification] • (DI-819)De-Appointment Reason Code = CSUPP = Change of Supply | LDSO receiving PUB-003 "Notifcation of Reverse Migration & DeAppointment" to confirm the Data service de-appointment and occurance of reverse migration
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002-Step 1006 (120)/Step 1007 (125) | MHHS-RMigration-CoA(DS)-RS-002 MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 | Registration service | Registration service | NA | CSS batch will be run automatically (usually every 2 hours or more frequent) or the tester will use the CSS simulator. Previously migrated MPAN to be picked up by the batch.For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N
3 | BP002-Step 1008 (130) | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 | Registration service | DIP | IF-003 | IF-003 "Notifcation of Reverse Migration & DeAppointment " will be sent to the DIP which inforDS that the DS is being de-appointed. Registration Service should include identity of MOP in IF-003 if this data was provided in the D0205. | Y | Evidence of IF-003 sent to DIP
4 | BP002-Step 1009/1011 | MHHS-RMigration-CoA(DS)-LDSO-001 MHHS-RMigration-CoA(DS)-LDSO-002 | DIP | LDSO | PUB-003 | LDSO to receive PUB-003 informing of DS de-appointment notification and to confirm the occurance of reverse migraiton | Y | Evidence of LDSO receiving PUB-003 to confirm the Data service de-appointment and occurance of reverse migration
5 | BP002-Step 1009/1013/1012/1010 | NA | DIP | Test harness (Outgoing DS / Outgoing Supplier / EES) | PUB-003 | Test harness (Outgoing DS / Outgoing Supplier / EES) to receive PUB-003 informing of DS de-appointment notification and to confirm the occurance of reverse migraiton | N | NA

## TC_BP003_01_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_01_03 | Data service de-appointment and occurance of reverse migration | TS_BP003_01 | Pre req: 1. Registration service should hold already migrated MPAN 2. Switch request from new supplier and agent appointment should be true 3. Linked MPAN Segment A (Advanced) IF-003 "Notifcation of Reverse Migration & DeAppointment " from Registration service to DIP with the following characteristics. • (DI-999)Event Code = [ReverseMigNotification] • (DI-819)De-Appointment Reason Code = CSUPP = Change of Supply | LDSO receiving PUB-003 "Notifcation of Reverse Migration & DeAppointment" to confirm the Data service de-appointment and occurance of reverse migration
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002-Step 1006 (120)/Step 1007 (125) | MHHS-RMigration-CoA(DS)-RS-002 MHHS-RMigration-CoA(DS)-RS-003 MHHS-RMigration-CoA(DS)-RS-004 | Registration service | Registration service | NA | CSS batch will be run automatically (usually every 2 hours or more frequent) or the tester will use the CSS simulator. Previously migrated MPAN to be picked up by the batch.For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N
3 | BP002-Step 1008 (130) | MHHS-RMigration-CoA(DS)-RS-005 MHHS-RMigration-CoA(DS)-RS-007 | Registration service | DIP | IF-003 | IF-003 "Notifcation of Reverse Migration & DeAppointment " will be sent to the DIP which inforDS that the DS is being de-appointed. Registration Service should include identity of MOP in IF-003 if this data was provided in the D0205. | Y | Evidence of IF-003 sent to DIP
4 | BP002-Step 1009/1011 | MHHS-RMigration-CoA(DS)-LDSO-001 MHHS-RMigration-CoA(DS)-LDSO-002 | DIP | LDSO | PUB-003 | LDSO to receive PUB-003 informing of DS de-appointment notification and to confirm the occurance of reverse migraiton | Y | Evidence of LDSO receiving PUB-003 to confirm the Data service de-appointment and occurance of reverse migration
5 | BP002-Step 1009/1013/1012/1010 | NA | DIP | Test harness (Outgoing DS / Outgoing Supplier / EES) | PUB-003 | Test harness (Outgoing DS / Outgoing Supplier / EES) to receive PUB-003 informing of DS de-appointment notification and to confirm the occurance of reverse migraiton | N | NA

## Requirement coverage
Req. ID | Requirement description | Comments
MHHS-RMigration-CoA(MS)-RS-004 | D0205 batch processing to occur within the Registration Service on a frequent basis with batch processing running every 2 hours or more frequently, in the majority of cases.
MHHS-RMigration-CoA(MS)-RS-003 | Although the Registration Service can process multiple D0205's, it will only use information from the last accepted D0205 before Secured Active processing at 1800 hours to generate an IF-003 at Secured Active acceptance.
MHHS-RMigration-CoA(MS)-RS-001 | In the case of Smart Meters only, Registration Service to include new Supplier details as part of IF-003 which is sent to outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). | Not covered as Outgoing MS is out of scope of QT
MHHS-RMigration-CoA(MS)-RS-005 | Registration Service to include identity of MOP in IF-003 if this data was provided in the D0205.
MHHS-RMigration-CoA(MS)-MS-003 | If outgoing MS is requested to transfer MTDs manually to incoming MOP and DC (due to D0205 not being sent to the Registration Service before the IF-003 was issued and MTDs now needing to be transferred manually), they must action this within 5 working days of receiving a valid request from the MOP. | Not covered as Outgoing MS is out of scope of QT
MHHS-RMigration-CoA(MS)-RS-007 | As soon as an IF-003 is sent, marking the completion of a Reverse Migration, Registration Service to add MPAN back into the Legacy EES Extract. | Need clarification
MHHS-RMigration-CoA(MS)-LDSO-001 | LDSO to receive PUB-003 from Registration Service (via the DIP), informing of MS de-appointment notification.
MHHS-RMigration-CoA(MS)-LDSO-002 | The receipt of a PUB-003 will serve as the definitive statement to each service that a Reverse Migration has occurred.