## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TS_BPM1&BPM2&BPM3_FM_02_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TS_BPM1&BPM2&BPM3_FM_02_01 | Successful migration of DS and MS (Using MCS) for Segment S, Single MPAN via prospective processing route | TS_BPM1&BPM2&BPM3_FM_02 | Pre requisites The Tester will pick a legacy Mpan for which they want to initiate the COS process and forward migration for. Whereby the initiating Suppler of the COS process (The supplier making the COS request) is not the supplier held in the Registration Services that is supplying the meter point currently This test The Tester will start at step 1 of this script where the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The Supplier will then trigger the IF-031 for both DS and MS appointments using scenario code MCS. Note Use the same MPAN and same appointment effective dates on both DS and MS appointments (IF-031), choose an appointment effective dates in the future (2-3 days). We want the appointments to go through the prospective processing route in RS. They will enter the prospective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved either by CSS simulator or tester manual action in RS) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manual actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service (Test Harness) - creation of the IF-034 in the Metering Service (Test Harness) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCS (Migration Change of Supplier) - Appointment is for a single MPAN - Appointment is for a Segment S (traditional meter) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCS (Migration Change of Supplier) - Appointment is for a single MPAN - Appointment is for a Segment S (traditional meter) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS | In this scenario the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The tester will then use the Supplier (a test harness) to initiate the migration of a Data service and Metering Service (by triggering the IF-031 with scenario code MCS). The migration of both will be successful (defined by the sending of the IF-036 notification for DS and MS). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in to their a real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP001 70 | MHHS-BR-RS-005 | CSS | Registration Services | CSS flow (CSS2800) | Registration Service has received notification from CSS (Simulator) via the CSS flow (CSS2800) after the new supplier submitting the request to CSS (Simulator). The notification will be a pending request. | N | To ensure that the Registration Services has received the pending supplier request.
2 | BP001 70 to 75 75 to 80 | MHHS-BR-RS-005 MHHS-BR-RS-006 MHHS-Migration-CoS-RS-001 MHHS-Migration-CoS-RS-002 MHHS-Migration-CoS-RS-003 | Registration Services | DIP | IF-002 | Once it has been confirmed that the switch from the Legacy MPAN to a MHSS Qualified Supplier has been achieved, Registration Services will send the IF-002 to the incoming Supplier via DIP | Y | To ensure that the information required has been sent to DIP and also the acceptance criteria/requirement has been met
3 | BP001 80 to 85 85 to 190 | N/A | DIP | Incoming Supplier (Test Harness) | PUB-002 | DIP has received IF-002 from Registration Services and will send PUB-002 to the incoming Supplier. | N | Not required
4 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
5 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
6 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
7 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
8 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
9 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
10 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
11 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
12 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
13 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
14 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
15 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
16 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
17 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
18 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
19 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
20 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
21 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
22 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
23 | BPM002_FM - Step 80 to Step 85 to Step 100, 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
24 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
25 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
26 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
27 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 281 (MS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
28 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
29 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
30 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
31 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)

## TS_BPM1&BPM2&BPM3_FM_02_02
s | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TS_BPM1&BPM2&BPM3_FM_02_02 | Successful migration of DS (Using MCS) for Segment U, single mpan via the prospective processing route | TS_BPM1&BPM2&BPM3_FM_02 | Pre requisites The Tester will pick a legacy Mpan for which they want to initiate the COS process and forward migration for. Whereby the initiating Suppler of the COS process (The supplier making the COS request) is not the supplier held in the Registration Services that is supplying the meter point currently This test The Tester will start at step 1 of this script where the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The Supplier will then trigger the IF-031 for both DS and MS appointments using scenario code MCS. Note Use the same MPAN and same appointment effective dates on both DS and MS appointments (IF-031), choose an appointment effective dates in the future (2-3 days). We want the appointments to go through the prospective processing route in RS. They will enter the prospective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved either by CSS simulator or tester manual action in RS) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manual actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service test harness - creation of the IF-034 in the Metering Service test harness (unless this is UMSO then this will happen automatically) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCS (Migration Change of Supplier) - Appointment is for a single mpan - Appointment is for a Segment U (Unmetered) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Supplier) - Appointment is for a single mpan - Appointment is for a Segment U (Unmetered) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS | In this scenario the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The tester will then use the Supplier (a test harness) to initiate the migration of a Data service and Metering Service (by triggering the IF-031 with scenario code MCS). The migration of both will be successful (defined by the sending of the IF-036 notification for DS and MS). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in to their a real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP001 70 | MHHS-BR-RS-005 | CSS | Registration Services | CSS flow (CSS2800) | Registration Service has received notification from CSS (Simulator) via the CSS flow (CSS2800) after the new supplier submitting the request to CSS (Simulator). The notification will be a pending request. | N | To ensure that the Registration Services has received the pending supplier request.
2 | BP001 70 to 75 75 to 80 | MHHS-BR-RS-005 MHHS-BR-RS-006 MHHS-Migration-CoS-RS-001 MHHS-Migration-CoS-RS-002 MHHS-Migration-CoS-RS-003 | Registration Services | DIP | IF-002 | Once it has been confirmed that the switch from the Legacy MPAN to a MHSS Qualified Supplier has been achieved, Registration Services will send the IF-002 to the incoming Supplier via DIP | Y | To ensure that the information required has been sent to DIP and also the acceptance criteria/requirement has been met
3 | BP001 80 to 85 85 to 190 | N/A | DIP | Incoming Supplier (Test Harness) | PUB-002 | DIP has received IF-002 from Registration Services and will send PUB-002 to the incoming Supplier. | N | Not required
4 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
5 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
6 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
7 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
8 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
9 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
10 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
11 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
12 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
13 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
14 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
15 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service UMSO | PUB-033 | MS: DIP automatically publishes PUB-033 to UMSO The UMSO will receive, validate and update their records accordingly | Y | DIP automatically publishes PUB-033 to the New Metering Service (UMSO) The UMSO will receive, validate and update their records accordingly
16 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
17 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
18 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
19 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
20 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service UMSO | DIP | MHHS-IF-034 | MS: UMSO will automatically trigger the IF-034 to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
21 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
22 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
23 | BPM002_FM - Step 80 to Step 85 to Step 100, 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
24 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
25 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
26 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
27 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
28 | BPM003FM -Step 255 to 281 (MS) | NA | DIP | UMSO Metering Service | PUB-036 | DS: DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly | Y | DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly
29 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | y | Registration Service automatically send IF-036 to the DIP
30 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
31 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
32 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
33 | BPM002_FM - Step 245 to Step 195 (MS) |  | DIP | UMSO Metering Service | PUB-036 | MS: DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly | y | DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly

## TS_BPM1&BPM2&BPM3_FM_02_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TS_BPM1&BPM2&BPM3_FM_02_03 | Successful migration of DS and MS (Using MCS) for Segment A (NHH meter), Single MPAN via retro/ same day processing route | TS_BPM1&BPM2&BPM3_FM_02 | Pre requisites The Tester will pick a legacy Mpan for which they want to initiate the COS process and forward migration for. Whereby the initiating Suppler of the COS process (The supplier making the COS request) is not the supplier held in the Registration Services that is supplying the meter point currently. This test The Tester will start at step 1 of this script where the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The Supplier will then trigger the IF-031 for both DS and MS appointments using scenario code MCS. Note Use the same MPAN and same appointment effective dates on both DS and MS appointments (IF-031), choose an appointment effective dates in such a way that the retro/ same day processing route is taken Manual actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service (Test Harness) - creation of the IF-034 in the Metering Service (Test Harness) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCS (Migration Change of Supplier) - Appointment is for a single MPAN - Appointment is for a Segment S (traditional meter) Data Service - Effective date of the appointment is such that retro/ same day processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCS (Migration Change of Supplier) - Appointment is for a single MPAN - Appointment is for a Segment S (traditional meter) Metering Service - Effective date of the appointment is such that retro/ same day processing route is taken in RS | In this scenario the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The tester will then use the Supplier (a test harness) to initiate the migration of a Data service and Metering Service (by triggering the IF-031 with scenario code MCS). The migration of both will be successful (defined by the sending of the IF-036 notification for DS and MS). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in to their a real system or a test harness.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP001 70 | MHHS-BR-RS-005 | CSS | Registration Services | CSS flow (CSS2800) | Registration Service has received notification from CSS (Simulator) via the CSS flow (CSS2800) after the new supplier submitting the request to CSS (Simulator). The notification will be a pending request. | N | To ensure that the Registration Services has received the pending supplier request.
2 | BP001 70 to 75 75 to 80 | MHHS-BR-RS-005 MHHS-BR-RS-006 MHHS-Migration-CoS-RS-001 MHHS-Migration-CoS-RS-002 MHHS-Migration-CoS-RS-003 | Registration Services | DIP | IF-002 | Once it has been confirmed that the switch from the Legacy MPAN to a MHSS Qualified Supplier has been achieved, Registration Services will send the IF-002 to the incoming Supplier via DIP | Y | To ensure that the information required has been sent to DIP and also the acceptance criteria/requirement has been met
3 | BP001 80 to 85 85 to 190 | N/A | DIP | Incoming Supplier (Test Harness) | PUB-002 | DIP has received IF-002 from Registration Services and will send PUB-002 to the incoming Supplier. | N | Not required
4 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
5 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
6 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
7 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
8 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
9 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
10 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
11 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
12 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
13 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
14 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
15 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
16 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
17 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
18 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
19 | BPM003FM - Step 80 to 85 to 100 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Retro/ same day" Processing | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
20 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
21 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
22 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
23 | BPM002_FM - Step 80 to Step 85 to Step 100 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Retro/ same day" Processing | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
24 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
25 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
26 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
27 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 281 (MS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
28 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
29 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
30 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
31 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)