## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
v0.5 | changes made after feedback |  |  | 2024-04-26
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM003&002_FM_01_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_01 | Successful migration of DS and MS (Using MCA) for Segment S, Single MPAN via prospective processing route | TS_BPM3AND2_FM_01 | Pre requisites. The Tester will pick a legacy mpan that they are currently supplying, that they wish to carry out forward migration for. The tester will start at step 1 of this script by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for both DS and MS appointments using the scenario code MCA This test Use the same MPAN and same appointment effective dates on both DS and MS appointments, choose a appointment effective dates in the future (2-3 days). We want the appointments to go through the prospective processing route in RS. They will enter the prospective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved by CSS simulator or another manual action by the tester) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manul actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service (Test Harness) - creation of the IF-034 in the Metering Service (Test Harness) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single MPAN - Appointment is for a Segment S (traditional meter) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single MPAN - Appointment is for a Segment S (traditional meter) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS | In this scenario a Supplier (a test harness) will initiate the migration of a Data service and Metering Service (by triggering the IF-031 with scenario code MCA for both DS and MS appointments). The migration of both will be successful (defined by the sending of the IF-036 notification). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in to their a real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS : Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS : DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the DS request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS : Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
4 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS : DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the MS request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
5 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS : Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
6 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS : DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS : Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
8 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS : DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
9 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
10 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS : Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
12 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS : DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
13 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
14 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
15 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
16 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
17 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS : Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
18 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS : Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS : DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 80 to Step 85 to Step 100, 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | MS : DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
21 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
22 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
23 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
24 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 281 (MS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
25 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS : Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
26 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS : DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
27 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS : Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
28 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS : DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)

## TC_BPM003&002_FM_01_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_02 | Successful migration of DS and MS Segment S (Using MCA) for import/export MPAN via prospective processing route | TS_BPM3AND2_FM_01 | Pre requisites. The Tester will pick a legacy import mpan that they are currently supplying, that they wish to carry out forward migration for. As a pre requisite the tester will start by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for the import mpans for both DS and MS ( using scenario code MCA) and validating that migration is completed (the definition of migration completed is when the PUB-036 is published). The tester can follow the steps on TC_BPM003&002_FM_01_01 to achieve this. This Test For this test, the tester will initiate the IF-031 for the export mpans for both DS and MS by following the script. All steps in this script are to do with the migration of the export mpan for the DS and MS Note: Use the same mpan and same appointment effective dates on both DS and MS appointments, choose the same same agents to appoint (meaning that no auto allignment will be needed at the end of this test) choose a appointment effective dates in the future (2-3 days). We want the appointments to go through the perspective processing route in RS. They will enter the perspective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved by CSS simulator or another manual action by the tester) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manul actions required by tester - creation of the IF-031 in the Supplier test harness for the Data Service appointment (for export Mpan) - creation of the IF-031 in the Supplier test harness for the Metering Service appointment (for export Mpan) - creation of the IF-034 in the New Data Service test harness (accept appointment) (for export Mpan) - creation of the IF-034 in the Metering Service test harness The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in the IF-031 is MCA (Migration Change of Agent). - Appointment is for a export mpan (Pre req for migration of import mpan is required) - Appointment is for a Segment S (smart meter) Data Service - Effective date of the appointment is such that perspective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in the IF-031 is MCA (Migration Change of Agent). - Appointment is for a export mpan (Pre req for migration of import mpan is required) - Appointment is for a Segment S (smart meter) Metering Service - Effective date of the appointment is such that perspective processing route is taken in RS Notes Import / Export MPANs will require two IF-031's to be submitted separately for each of the Import and Export pairing to initiate Forward Migration. The import side of this test will be completed in the pre req. Please refer to DEL1058 on how migration works for smart linked import/export mpans | In this scenario a Supplier (a test harness) will initiate the migration of a Data service and Metering Service (by triggering the IF-031 with scenario code MCA for both DS and MS appointments for the export mpan). The migration of both will be successful (defined by the sending of the IF-036 notification). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in to their a real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP. for the export Mpan for DS | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | MHHS-IF-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. for the export Mpan for DS | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP. for the export Mpan for MS | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP.
4 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | MHHS-IF-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. for the export Mpan for MS | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
5 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code for the export Mpan for DS | Y | Registration Service send IF-032 to the DIP with an accepted response code
6 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code for the export Mpan for DS | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code for the export Mpan for MS | Y | Registration Service send IF-032 to the DIP with an accepted response code
8 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code for the export Mpan for MS | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
9 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP for the export Mpan for DS | Y | Registration Service send IF-033 to the DIP
10 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) for the export Mpan for DS | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP for the export Mpan for MS | Y | Registration Service send IF-033 to the DIP
12 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) for the export Mpan for MS | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
13 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code for the export Mpan for DS | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
14 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP for the export Mpan for DS | Y | Registration Service automatically sends IF-035 to the DIP
15 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End for the export Mpan for DS | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
16 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. for the export Mpan for DS | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
17 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code for the export Mpan for MS | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
18 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP for the export Mpan for MS | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End for the export Mpan for MS | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 80 to Step 85 to Step 100 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. for the export Mpan for MS | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
21 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. for the export Mpan for DS | y | Registration Service automatically send IF-036 to the DIP
22 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message for the export Mpan for DS | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
23 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly for the export Mpan for DS | y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
24 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 281 (MS) |  | DIP | EES (Test Harness) End Metering Service (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) for the export Mpan for DS | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness)
25 | BPM003FM - Step 250 to 710 to 770 to 780 | MHHS-Migration-CoA(DS)-RS-016 | Registration Service | DIP | MHHS-IF-036 | DS: This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the IF-036 is sent from RS to the DIp for the export Mpan for DS RS sends IF-036 to DIP | Y | This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the IF-036 is sent from RS to the DIp for the export Mpan RS sends IF-036 to DIP
26 | BPM003FM - Step 780 to 790 (DS) BPM003FM - Step 780 to 750 (Supplier) | NA | DIP | New Data Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the PUB-036 is sent from DIP to the locations below for the export Mpan for DS DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the PUB-036 is sent from DIP o the locations below for the export Mpan DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
27 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. for the export Mpan for MS | Y | Registration Service automatically send IF-036 to the DIP
28 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message for the export Mpan for MS | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
29 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. for the export Mpan for MS | y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
30 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) for the export Mpan for MS | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness)
31 | BPM002_FM - Step 100 to Step 710 to Step 770 to Step 780 | MHHS-Migration-CoA(MS)-RS-016 | Registration Service | DIP | MHHS-IF-036 | MS: This step is mentioned separately because the way the Business Process diagram is drawn - In this step, RS sends IF-036 to DIP for the export Mpan for MS | Y | This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the IF-036 is sent from RS to the DIp for the export Mpan RS sends IF-036 to DIP
32 | BPM002_FM - Step 780 to 790 (MS) BPM002_FM - Step 780 to 750 (Supplier) | NA | DIP | New Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: This step is mentioned separately because the way the Business Process diagram is drawn - In this step, DIP sends PUB-036 for the export Mpan for MS New Metering Service (Test Harness) Supplier (Test Harness) | N | This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the PUB-036 is sent from DIP o the locations below for the export Mpan DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)

## TC_BPM003&002_FM_01_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_03 | Successful migration of DS and MS for Segment A (Using MCA) for single mpan via prospective processing route | TS_BPM3AND2_FM_01 | Pre requisites: The Tester will pick a legacy mpan that they are currently supplying, that they wish to carry out forward migration for. The tester will start at step 1 of this script by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for both DS and MS appointments using the scenario code MCA This test Note: Use the same MPAN and same appointment effective dates on both DS and MS appointments, choose a appointment effective dates in the future (2-3 days). We want the appointments to go through the perspective processing route in RS. They will enter the perspective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved by CSS simulator or another manual action by the tester) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manul actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service (Test Harness) - creation of the IF-034 in the Metering Service (Test Harness) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single MPAN - Appointment is for a Segment A (HH meter) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single MPAN - Appointment is for a Segment A (HH meter) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS | In this scenario a Supplier (a test harness) will initiate the migration of a data service (by triggering the IF-031). The migration will be successful (defined by the sending of the IF-036 notification). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration into either the real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
4 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
5 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
6 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
8 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
9 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
10 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
12 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
13 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
14 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
15 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
16 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
17 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
18 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 80 to Step 85 to Step 100, 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
21 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
22 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
23 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
24 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 281 (MS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
25 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
26 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
27 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
28 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)

## TC_BPM003&002_FM_01_04
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_04 | Successful migration of DS and MS (Using MCA) for Segment A, related mpan via prospective processing route | TS_BPM3AND2_FM_01 | Pre requisites. The Tester will pick a legacy related mpan that they are currently supplying, that they wish to carry out forward migration for. The tester will start at step 1 of this script by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for both DS and MS appointments using the scenario code MCA This Test Related MPANs will automatically migrate together and only require one IF-031 to be submitted (1 IF-031 for the DS primary mpan, and 1 IF-031 for the MS primary mpan) to migrate both sides of the primary and secondary pairing. The outcome will be that both mpans are migrated at the end of this process for MS and DS (denoted by sending of a separate PUB-036 for each mpan to the expected participants). Notes: Use the same MPAN and same appointment effective dates on both DS and MS appointments, choose a appointment effective dates in the future (2-3 days). We want the appointments to go through the prospective processing route in RS. They will enter the prospective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved by CSS simulator or another manual action by the tester) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manual actions required by tester - creation of the IF-031 in the Supplier test harness for primary mpan for DS - creation of the IF-031 in the Supplier test harness for primary mpan for MS - creation of the IF-034 in the New Data Service test harness for primary mpan for DS - creation of the IF-034 in the New Metering Service test harness for primary mpan for MS The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in the IF-031 is MCA (Migration Change of Agent). - Appointment is for a primary mpan of a related group (using primary mpan, and the secondary will automatically migrate with it) - Appointment is for a Segment A (NHH meter) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in the IF-031 is MCA (Migration Change of Agent). - Appointment is for a primary mpan of a related group (using primary mpan, and the secondary will automatically migrate with it) - Appointment is for a Segment A (NHH meter) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS Please refer to DEL1058 on how migration works for related mpans | In this scenario a Supplier (a test harness) will initiate the migration of a DS and MS (by triggering the a IF-031 for the primary mpan of a related group for the DS appointment . And by triggering a IF-031 the primary mpan of a related group for the MS appointment). For related mpans the secondary mpan will automatically migrate along side the primary.. The migration will be successful for both DS and MS (defined by the sending of the IF-036 notification to all participants). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration into either the real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP. An IF-031 will be sent for the Primary MPAN to serve as the instruction to begin Forward Migration and the Secondary MPAN automatically to be migrated alongside the Primary MPAN (without requiring a second IF-031 to be sent) | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP. An IF-031 will be sent for the Primary MPAN to serve as the instruction to begin Forward Migration and the Secondary MPAN automatically to be migrated alongside the Primary MPAN (without requiring a second IF-031 to be sent)
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP.
4 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
5 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | y | Registration Service send IF-032 to the DIP with an accepted response code
6 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
8 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
9 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | y | Registration Service send IF-033 to the DIP
10 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
12 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
13 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
14 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
15 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
16 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
17 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
18 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 80 to Step 85 to Step 100, 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
22 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 MHHS-Migration-CoA(DS)-RS-005 | Registration Service | DIP | MHHS-IF-036 | DS: (RS-18) Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. (RS-05) Following the appointment of the Service Provider, the Registration Service will send an IF-036 for both Primary and Secondary MPANs together. | y | Registration Service automatically send IF-036 to the DIP
23 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
24 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly For related mpans, a PUB-036 will be triggered for each mpan | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly. For related mpans, a PUB-036 will be triggered for each mpan
25 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 281 (MS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End Metering Service (Test Harness) End New Data Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) For related mpans, a PUB-036 will be triggered for each mpan | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) For related mpans, a PUB-036 will be triggered for each mpan
26 | BPM003FM - Step 750 - | MHHS-Migration-CoA(DS)-RS-017 | NA | NA | NA | DS: After the migration of both primary and secondary mpans has completed, check to make sure that both primary and secondary mpans are appointed to the same DS. The DS of the secondary mpan should be aligned with the same DS as the primary mpan. The design team are aware that is might not be @ step 750 on the diagram - "non the less, regardless of the step, the tester will validate this functionality is working" | Y | check to make sure that both primary and secondary mpans are appointed to the same DS
27 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
28 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message. | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
29 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
30 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to New Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to New Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)

## TC_BPM003&002_FM_01_05
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_05 | Successful migration of DS and MS (Using MCA) for Segment U, single mpan via prospective processing route | TS_BPM3AND2_FM_01 | Pre requisites. The Tester will pick a legacy mpan that they are currently supplying, that they wish to carry out forward migration for. The tester will start at step 1 of this script by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for both DS and MS appointments using the scenario code MCA This test Note: Use the same mpan and same appointment effective dates on both DS and MS appointments, choose a appointment effective dates in the future (2-3 days). We want the appointments to go through the perspective processing route in RS. They will enter the perspective processing route in RS after receiving the IF-034 from the Service providers (DS and MS) and will await a CSS secured notification (achieved by CSS simulator or another manual action by the tester) for the appointments to be processed out of the Queue. When the appointments are processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manual actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service test harness - creation of the IF-034 in the Metering Service test harness (unless this is UMSO then this will happen automatically) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single mpan - Appointment is for a Segment U (Unmetered) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single mpan - Appointment is for a Segment U (Unmetered) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS | In this scenario a Supplier (a test harness) will initiate the migration of a data service (by triggering the IF-031). The migration will be successful (defined by the sending of the IF-036 notification). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration into either the real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
4 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
5 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
6 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
8 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
9 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
10 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
12 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | UMSO | PUB-033 | MS: DIP automatically publishes PUB-033 to the UMSO The UMSO will receive, validate and update their records accordingly | Y | DIP automatically publishes PUB-033 to the New Metering Service (UMSO) The UMSO will receive, validate and update their records accordingly
13 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
14 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
15 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
16 | BPM003FM - Step 80 to 85 to 100 > 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
17 | BPM002_FM - Step 75 to Step 80 | NA | UMSO | DIP | MHHS-IF-034 | MS: UMSO will automatically trigger the IF-034 to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
18 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | UMSO End | PUB-035 | MS: DIP automatically sends PUB-035 to UMSO | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 80 to Step 85 to Step 100, 101, 120, 125 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
21 | BPM003FM - Step 250 to2 55 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
22 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
23 | BPM003FM - Step 255 to2 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
24 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
25 | BPM003FM -Step 255 to 281 (MS) | NA | DIP | UMSO | PUB-036 | DS: DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly | Y | DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly
26 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
27 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
28 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
29 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
30 | BPM002_FM - Step 245 to Step 195 (MS) |  | DIP | UMSO | PUB-036 | MS: DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly | Y | DIP sends PUB-036 to UMSO Metering Service The UMSO will receive, validate and update their records accordingly

## TC_BPM003&002_FM_01_06
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_06 | Successful migration of DS and MS (Using MCA) for Segment S, Single MPAN via Retro/Same Day processing route | TS_BPM3AND2_FM_01 | Pre requisites. The Tester will pick a legacy mpan that they are currently supplying, that they wish to carry out forward migration for. The tester will start at step 1 of this script by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for both DS and MS appointments using the scenario code MCA This test Use the same MPAN and same appointment effective dates on both DS and MS appointments, choose a appointment effective dates as Retro/Same Day. We want the appointments to go through the Retro/Same Day processing route in RS. They will enter the retro processing route in RS after receiving the IF-034 from the Service providers (DS and MS). When the appointments are processed, an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful) Manul actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - creation of the IF-034 in the New Data Service (Test Harness) - creation of the IF-034 in the New Metering Service (Test Harness) The data for this test should be as follows: for the Data Service appointment - IF-031 event code = [DSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single MPAN - Appointment is for a Segment S (Traditional Meter) Data Service - Effective date of the appointment is such that Retro/Same Day processing route is taken in RS The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in IF-031 is MCA (Migration Change of Agent) - Appointment is for a single MPAN - Appointment is for a Segment S (Traditional Meter) Metering Service - Effective date of the appointment is such that Retro/Same Day processing route is taken in RS | In this scenario a Supplier (Test Harness) will initiate the migration of a Data service and Metering Service (by triggering the IF-031 with scenario code MCA for both DS and MS appointments). The migration of both will be successful (defined by the sending of the IF-036 notification). The LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in to their a real system or a test harness.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
4 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
5 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
6 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
8 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
9 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
10 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
12 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
13 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
14 | BPM003FM Step 85 to 87 to 90 | NA | Registration Service | DIP | MHHS-IF-035 | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
15 | BPM003FM Step 90 TO 91 (DS) BPM003FM Step 90 TO 95 (SUP) | NA | DIP | Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
16 | BPM003FM - Step 80 to 85 to 100 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed •"Retro/Same Day" Processing | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
17 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP with an accepted response code
18 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 80 to Step 85 to Step 100 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed •"Retro/Same Day" Processing | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
21 | BPM003FM - Step 250 to 255 | MHHS-Migration-CoA(DS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | DS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
22 | BPM003FM - Step 255 to no step mentioned | MHHS-Migration-CoA(DS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | DS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
23 | BPM003FM - Step 255 to 280 | MHHS-Migration-CoA(DS)-LDSO-001 | DIP | LDSO | PUB-036 | DS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification and MTD. And update their record accordingly
24 | BPM003FM -Step 255 to 279 (EES) BPM003FM -Step 255 to 340 (DS) BPM003FM -Step 255 to 281 (MS) BPM003FM -Step 255 to 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | DS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
25 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
26 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
27 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
28 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)

## TC_BPM003&002_FM_01_07
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003&002_FM_01_07 | Successful migration of MS Segment S (smart meter) for import/export MPAN via prospective processing route. Where auto alignment is triggered because export agent does not align with import agent | TS_BPM3AND2_FM_01 | Pre requisites. The Tester will pick a legacy import mpan that they are currently supplying, that they wish to carry out forward migration for. The Tester will start by initiating the migration by triggering the IF-031 from the Supplier (Test Harness) for the import for the MS and validating that migration is completed (the definition of migration completed is when the PUB-036 is published). The tester can follow the steps on TS_BPM3AND2FM_01_01 (only MS steps) to achieve this. At the end of the pre req process the import mpan for the MS will be migrated as follows:- - MS import mpan is migrated and will be appointed to the MSA (advanced Meter Service) This Test For this test, the tester will initiate the IF-031 for the export mpan for the MS by following this script. All steps in this script are to do with the successful migration of the export mpan (the definition of migration completed is when the PUB-036 is published). The tester will make sure of the following to test req -MHHS-Migration-Mis-RS-022 - When migrating the MS Export mpan, to choose a different Advanced Meter Service (MSA) to the import mpan (this will create the mis-alignment of the import and export Metering Services) The above condition will result in the following behaviour:- The Registration Service will perform a daily scan for any Import / Export MPANs where both Import and Export MPANs have been fully migrated, but they have been appointed to different Agents. Where any examples of this occur, the Registration Service will automatically align the Export mpans Meeting Service (MSA) to the import mpans Metering Service (MSA). This happens by de-appointing the incorrect export Metering Service (MSA) and appointing the correct export Metering Service (MSA) to align the export mpans Metering Service to the import mpans Metering Service. Note: For the Export mpan, choose a appointment effective dates in the future (2-3 days). We want the appointment to go through the prospective processing route in RS. It will enter the prospective processing route in RS after receiving the IF-034 from the Metering Service and will await a CSS secured notification (achieved by CSS simulator or another manual action by the tester) for the appointment to be processed out of the queue. When the appointment is processed out of the queue, an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration has been successful). The alignment process will begin when both import and export mpans are migrated. Manul actions required by tester - creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment (for export Mpan) - creation of the IF-034 in the Metering Service (Test Harness) (accepted appointment) (for export Mpan) The data for this test should be as follows: for the Metering Service appointment - IF-031 event code = [MSApp] - Appointment Scenario in the IF-031 is MCA (Migration Change of Agent). - Appointment is for a export mpan (Pre req for migration of import mpan is required) - Appointment is for a Segment S ( Smart meter) Metering Service (MSA) - Effective date of the appointment is such that prospective processing route is taken in RS Notes Import / Export MPANs for the smart segment will require two IF-031's to be submitted separately for the import and Export pairing to initiate Forward Migration. The import side of this test will be completed in the pre req. Please refer to DEL1058 on how migration works for smart linked import/ export mpans. | In this scenario a Supplier (a test harness) will initiate the migration of a Metering Service (by triggering the IF-031 with scenario code MCA for the appointment of the MS export mpan). The migration will be successful albeit that the Import mpan agent will be mis-aligned to the export mpan agent. The Registration Service will perform a daily scan for any Import / Export MPANs where both Import and Export MPANs have been fully migrated, but they have been appointed to different Agents. Where any examples of this occur, the Registration Service will automatically align the Export mpan Metering Service (MSA) to the import Metering Service (MSA). This happens by de-appointing the incorrect export Metering Service (MSA) and appointing the correct export Metering Service (MSA) to align the export mpans Metering Service to the import mpans Metering Service.
Test Step Id | Business Process Steps | Traceability Requirements | The above will | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP. for the export Mpan for MS | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP.
2 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | MHHS-IF-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. for the export Mpan for MS | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
3 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code for the export Mpan for MS | y | Registration Service send IF-032 to the DIP with an accepted response code
4 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code for the export Mpan for MS | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
5 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP for the export Mpan for MS | y | Registration Service send IF-033 to the DIP
6 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) for the export Mpan for MS | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
7 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an accepted response code for the export Mpan for MS | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
8 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 | MS: Registration Service automatically sends IF-035 to the DIP for the export Mpan for MS | Y | Registration Service automatically sends IF-035 to the DIP
9 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | MS: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End for the export Mpan for MS | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
10 | BPM002_FM - Step 80 to Step 85 to Step 100 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the SCC simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. for the export Mpan for MS | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
11 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. for the export Mpan for MS | Y | Registration Service automatically send IF-036 to the DIP
12 | BPM002_FM - Step 245 to no step mentioned | MHHS-Migration-CoA(MS)-RS-006 | DIP | Elexon Central Systems (Helix Test harness) | PUB-036 | MS: DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin. We are testing that only the test harness receives the message for the export Mpan for MS | N | DIP automatically sends an PUB-036 to Elexon Central Systems (Helix) to inform that settlement activities for the MPAN can now begin.
13 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly. for the export Mpan for MS | y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification and MTD. And update their record accordingly.
14 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) for the export Mpan for MS | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness)
15 | BPM002_FM - Step 100 to Step 710 to Step 770 to Step 780 | MHHS-Migration-CoA(MS)-RS-016 | Registration Service | DIP | MHHS-IF-036 | MS: This step is mentioned separately because the way the Business Process diagram is drawn - In this step, RS sends IF-036 to DIP for the export Mpan for MS | y | This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the IF-036 is sent from RS to the DIp for the export Mpan RS sends IF-036 to DIP
16 | BPM002_FM - Step 780 to 790 (MS) BPM002_FM - Step 780 to 750 (Supplier) | NA | DIP | New Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: This step is mentioned separately because the way the Business Process diagram is drawn - In this step, DIP sends PUB-036 for the export Mpan for MS New Metering Service (Test Harness) Supplier (Test Harness) | N | This step is mentioned separately because the way the diagram is drawn. for this step we are just saying the PUB-036 is sent from DIP o the locations below for the export Mpan DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
17 | MS alignment check | MHHS-Migration-Mis-RS-022 | Registration Service (internal processing - MS alignment check) | Registration Service (internal processing - MS alignment check) | NA | Metering Service step At this stage of the test both import and export mpans have been migrated for the MS and have different agents appointed This step explains the scan that the Registration Services performs on the import/export mpan for the MS only, the following steps will show how the incorrect MS is de-appointed and the correct MS is appointed The Registration Service will perform a daily scan for any Import / Export MPANs where both Import and Export MPANs have been fully migrated, but they have been appointed to different Agents. Where any examples of this occur, the Registration Service will automatically align the Export mpan to the Import mpan. This is achieved by de-appointing the export mpans agent and appointing the correct export mpan agent | y | Metering Service step At this stage of the test both import and export mpans have been migrated for the MS and have different agents appointed RS daily scan is performed to check if import MS agent is aligned to the export mpan agent
18 | MS incorrect export agent de-appointment | NA | Registration service | DIP | MHHS-IF-037 | MS: Registration Service will issue a de-appointment of existing metering service notification via MHHS-IF-037 "Notification of Service De-Appointment" | Y | Evidence of Registration service issuing MHHS-IF-037
19 | MS incorrect export agent de-appointment | NA | DIP | Test harness (Supplier, Existing Metering service) | PUB-037 | MS: DIP publishes PUB-037 to Test harness (Supplier, Existing Metering service) | N | NA
20 | MS correct export agent appointment | NA | Registration service | DIP | MHHS-IF-036 | MS: Registrations Service will issue out a confirmed appointment to the DIP via MHHS-IF-036 "Service Provider Notification of Appointment" to align the Metering Service | Y | Evidence of Registration service issuing MHHS-IF-036
21 | MS correct export agent appointment | NA | DIP | Test harness (Supplier, Prospective Metering service) | PUB-036 | MS: DIP publishes PUB-037 to Test harness (Supplier, Prospective Metering service) | N | NA