## 1 Cover Page
<organisation> PIT to Qualification Requirements to Test Traceability Matrix
Document owner | Document number | Version
<name or role> |  | <version number>
Status: | Date | Classification
<status> | <date> | Internal

## 2 Change Control
Programme Participant Name
Programme participants to fill in the table below and include their relevant constituency group and third-party provider if applicable.
Programme Participant Name | Constituency Group | MPID(s) Tested | Third Party Provider
e.g. Generic Electricity Co. Ltd | I&C Supplier | MPID(s) | N/A
Change Record
The table below needs to be updated with details of each amendment and change control.
Date | Author | Version | Change Detail
Document Approval
The table below needs to be updated and the role needs to be defined per person
Reviewer/Approver | Role
References
Reference any documents into the table below along with reference and version number. Programme participants should insert documents wherever possible. Programme participants should insert documents wherever possible.
Reference | Documents | Publisher | Version | Additional Information
REF 001 | PIT Test Approach and Plan
REF 002 | PIT Test Scenarios
Terminology
Reference any terminology used in this document.
Term | Description

## 3 Template Verision Control
Template Change Control
Date | Author | Version | Change Detail
2024-03-27 | Code Bodies | V0.1 | Intial Draft
This template is aligned to following documents
Document | Verision
REC Asssesment Criteria | V1.0
BSC Assesement Criteria | xx
Qualification Assesment Document | V1.0

## 4 Guidance
Purpose of the document |  | The purpose of this document is provide traceability back to requirements across the different stages of qualification (PIT, QT and QAD) and covers functional, migration, non-functional and operational requirements. This document will also support agreement of placing reliance arrangement and act as an agreement of individual participant’s test scope. This document will be assured by the Code Bodies as well as the MHHSP for Non-SIT LDSOs. This document is aligned to REC and BSC assesment critieria and sections maintained by Code Bodies will be updated if the assesement critieria documents are updated. Please note: There is a separate version of the template pre-filled for each role, with the exception of LDSOs where LDSO/UMSO/Registration Services combined into one template
When does this document need to be submitted |  | It is a working document so it is expected that a Programme Participant will update and submit this document multiple times to support its progress through MHHS Qualification. For Programme Participants undertaking Qualification Testing, it is expected that they will submit this document to support PIT entry, PIT exit, QT entry and QT exit.​ For PIT it is expected that participants map their PIT test cases to the requirements, for QT this will be done by MHHSP/Code Bodies. Note, whilst the RTTM goes down to individual requirements, the participant can reference a single test scenario against multiple requirements and provide a single set of test evidence to reflect that test has been passed
Tab name |  | Purpose |  | Participant to update
1 | .Cover Page | To capture the current document status and version number. |  | Yes
2 | Change Control | To capture changes to document made by programme participant. |  | Yes
3 | Template Change Control | To capture changes made to the base template. |  | No
4 | Guidance | This tab. To provide guidance on how programme participant should complete and submit this template. |  | No
5 | Functional Requirements | Functional requirements to test traceability matrix which participants will need to complete and submit at various points within MHHS Qualification process. |  | Yes
6 | Migration Requirements | Migration requirements to test traceability matrix which participants will need to complete and submit at various points within MHHS Qualification process. |  | Yes
7 | Non-functional Requirements | Non- Functional requirements to test traceability matrix which participants will need to complete and submit at various points within MHHS Qualification process. |  | Yes
8 | Operational Requirements | Operational requirements to test traceability matrix which participants will need to complete and submit at various points within MHHS Qualification process. |  | Yes
Column Name within requirement tab |  |  | Description of the data in each of the columns within RTTM worksheet | Participant to complete
B | Reference |  | Requirement MHHS reference | No - prepopulated from the relevant MHHS Design Artefacts.
C | Market Role |  | Market Role e.g. Supplier. | No - prepopulated from the relevant MHHS Design Artefacts.
D | Requirement |  | Title of requirement | No - prepopulated from the relevant MHHS Design Artefacts.
E | Requirement Description |  | Description of requirement | No - prepopulated from the relevant MHHS Design Artefacts.
F | Code |  | Whether the requirement is applicable to both REC and BSC or applicable to only one Code | No – prepopulated by Code Bodies
G | Supporting information/ questions |  | Supporting information on requirement | No - prepopulated from the relevant MHHS Design Artefacts.
H | Process |  | MHHS business process the requirement relates to | No - prepopulated from the relevant MHHS Design Artefacts.
I | Step |  | Step within a MHHS business process the requirement relates to | No - prepopulated from the relevant MHHS Design Artefacts.
J | Interface |  | MHHS interface the requirement relates to | No - prepopulated from the relevant MHHS Design Artefacts.
K | Optionality |  | Whether there is optionality in how a programme participant meets the requirement | No - prepopulated from the relevant MHHS Design Artefacts.
L | PIT Testing Required |  | Whether a programme participant needs to provide evidence that this requirement has been tested via PIT. This is populated based on the BSC and REC MHHS Qualification Assessment Criteria | No – prepopulated by Code Bodies
M | Entry Criteria for QT (Y/N) |  | Whether a programme participant needs to provide evidence of this requirement being tested in PIT to support their QT entry or their QT exit | No – prepopulated by Code Bodies
N | PIT Scenario |  | Title of test scenario that a programme participant will execute to show they have met this requirement . Please note; whilst the RTTM goes down to individual requirements, the participant can reference a single test scenario against multiple requirements and provide a single set of test evidence to reflect that test has been passed. | Yes – submit in line with timeline in PIT Guidance
O | Placing Reliance Applicable (Y/N) |  | Whether programme participant is seeking to place reliance on another party for this requirement | Yes – submit in line with timeline in PIT Guidance
P | Placing Reliance info |  | Information on who a programme participant is placing reliance on for this requirement | Yes – submit in line with timeline in PIT Guidance
Q | PIT Status |  | Status of test execution e.g. Passed, Failed, Not Run, blocked etc | Yes – submit in line with PIT TCR
R | PIT Test Evidence |  | Confirmation of test evidence has been captured and submitted | Yes – submit in line with PIT TCR
S | Work Off Plan |  | Whether programme participant successfully meeting requirement is subject to item in their work off plan | Yes – submit in line with PIT TCR
T | Comments |  | Any comments and if any tests have failed, this field should also include Defect ID and defect details. | Yes – submit in line with PIT TCR
U | SIT/QT Required |  | Whether QT test scenario is required to show that a programme participant can meet this requirement | No – prepopulated by Code Bodies
V | QT Scenario |  | Title of test scenario that a programme participant will execute to show they have met this requirement in QT | No – prepopulated by Code Bodies
W | Placing Reliance Applicable (Y/N) |  | Whether programme participant is seeking to place reliance on another party for this requirement | Yes – submit in line with QT test plan
X | Placing Reliance info |  | Information on who a programme participant is placing reliance on for this requirement | Yes – submit in line with QT test plan
Y | QT Status |  | Status of test execution e.g. Passed, Failed, Not Run, blocked etc | Yes – submit in line with QT TCR
Z | QT Test Evidence |  | Confirmation of test evidence has been captured and submitted | Yes – submit in line with QT TCR
AA | Work Off Plan |  | Whether programme participant successfully meeting requirement is subject to item in their work off plan | Yes – submit in line with QT TCR
AB | Comments |  | Any comments and if any tests have failed, this field should also include Defect ID and defect details. | Yes – submit in line with QT TCR
AC | QAD Question |  | Whether there is QAD question linked to this requirement | No – prepopulated by Code Bodies
AD | QAD Question Number |  | Number of QAD question linked to the requirement | No – prepopulated by Code Bodies
Guidance

## 5 Functional Requirements
Code Bodies to complete. Columns are aligned to REC and BSC assesment critieria and sections maintained by Code Bodies will be updated if the assesement critieria documents are updated.
Programme Participant to complete
Requirement | [9 empty] | PIT | [8 empty] | QT | [8 empty] | QAD
[10 empty] | Prepopulated | Prepopulated | Submit inline with timeline in PIT Guidance |  |  | Submit with PIT TCR |  |  |  | Prepopulated | Prepopulated |  | Submit with QT Test Plan |  | Submit with QT TCR |  |  |  | Prepopulated | Prepopulated
Reference | Market Role | Requirement | Requirement Description | Code | Supporting information/ questions | Process | Step | Interface | Optionality | PIT Testing Required (Y/N) | Entry Criteria for QT (Y/N) If No, participants are expected to have completed by QT exit | PIT Scenario ID - at least one but could be multiple | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should include the organisation conducting the test. This will need to be reviewed by code bodies | PIT Status (Passed, Failed, Not Run) | PIT Test Evidence Captured | Work Off Plan (Y/N) | Comments | SIT / QT Required (Y/N) | SIT/QT Scenario ID - at least one but could be multiple | QT Test Scenario/s to be executed | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | QT Status (Passed, Failed, Not Run) | SIT / QT Test Evidence in ADO (Y/N) | Work Off Plan (Y/N) | Comments | QAD Question (Y/N) | QAD Question Number
MHHS-BR-DS-003 | ADS/SDS | Receive Metering Service appointment notification | ADS/SDS must obtain Registration Service Notification of Service Appointment & Supporting Info updates, confirming a Metering Service appointment and providing MPAN/ Meter Technical details, via the appropriate interface on the Data Integration Platform and maintain records accordingly for all meter types. |  | PUB-036. Note for Smart meters PUB-036 contains all the Meter Technical Detail required ( No additional D-flow as is the case with Trad and Advanced ) | BP002 Change of Metering Service | 270 | PUB-036 | None | Y | [8 empty] | Y | [8 empty] | Y
MHHS-BR-DS-006 | SDS | Receive Meter Technical Details from Smart Metering Service (Change of Metering Service) | SDS must receive Meter Technical Details for Traditional meters via the appropriate interfaces (D0149 and D0150 on DTN), maintain records accordingly and investigate any discrepancies against data received from the Registration Service (PUB-036 via the Data Integration Platform). These details could be received from a prospective incoming Metering Service that does not turn out to be the Metering Service appointed when the Data Service appointment commences. Therefore ADS may wish to consider how to process these MTDs ie they will provide early view of MTDs at site, however further MTDs (which may be revised) could be received from a second subsequent Metering Service. |  |  | BP002 Change of Metering Service | 190 | D0149 D0150 | SDS - Service Traditional meters | Y | [17 empty] | Y
MHHS-BR-DS-006.1 | ADS/SDS | Investigate missing or incorrect Meter Technical Details from Metering Service | ADS/SDS must investigate with the Metering Service where Meter Technical Details are not received for Advanced/ Traditional meters in expected timescales, as outlined in the Operational Choreography, or where they appear to be incorrect. |  |  | BP002 Change of Metering Service | 271 |  | SDS - Service Traditional meters
MHHS-BR-DS-007 | Data Service | Receive proposed appointment service request | Data Service must obtain Registration Service Request for Service Appointments, with Data Service proposed appointment requests, via the appropriate interface on the Data Integration Platform. |  | PUB-033 | BP003 Change of Data Service | 220 | PUB-033 | None | Y | [8 empty] | Y | [5 empty] | Y |  |  | Y
MHHS-BR-DS-008 | Data Service | Validate and respond to proposed appointment service request | Data Service must confirm that they are certified to service the connection type and able to contractually deliver the Data Service based on the information contained in the proposed appointment request and publish a response (acceptance or rejection) on the Data Integration Platform via the appropriate interface. Where the Data Service rejects an appointment request, a rejection reason should be provided in the response. Data Service should be aware that following the initial acceptance the appointment remains "prospective" and there is a possibility that it may need to be lapsed. |  | MHHS-IF-034 to Registration Service | BP003 Change of Data Service | 220/221 | MHHS-IF-034 | None | [18 empty] | Y
MHHS-BR-DS-008.1 | ADS/SDS | Delete data for rejected appointments | ADS/SDS must, for any proposed appointments it rejects, delete any metering details received, as soon as operationally practicable following the rejection. |  |  | BP003 Change of Data Service | 232 |  | None | Y
MHHS-BR-DS-009 | Data Service | Notification of third party providers | Data Service must, where required, make their own arrangements for notifying any third party service providers ( eg Meter Reading Service, Meter Data Retrieval Service ) via a mechanism agreed bilaterally |  |  | BP003 Change of Data Service | 230 (BP003B -230) |  | Use of third party service providers
MHHS-BR-DS-010 | SDS | Engagement of MDR | SDS must notify the MDR nominated by the Supplier, advised in the appointment service request. In cases where no MDR is nominated the SDS should notify the MDR based on whatever rules have been agreed with the Supplier. The SDS must ensure that all DCC enrolled meters always have an MDR notified for each day that the SDS is responsible for the site. |  | PUB-033 from Registration Service MHHS-IF-034 to Registration Service | BP003 Change of Data Service | 230 (BP003B -230) | PUB-033 MHHS-IF-034 | SDS - Service Smart Meters | Y |  |  |  | Y |  |  |  |  | Y | [5 empty] | Y |  |  | Y
MHHS-BR-DS-011 | Data Service | Existing appointment amendment | Data Service must be able to process requests to vary the conditions of an existing appointment received via the appropriate interface. For example change of contract code or change of MDR (SDS only). These should be validated and an outcome returned using the appropriate interface. In the case of rejection, a rejection reason should be provided in the response and the existing appointment will continue unamended. |  | Data Service should note: 1. In the case of Related MPANs, any accepted updates will also be applied to the Secondary MPANs 2. In the case of linked Import/Export MPANs, any accepted updates will also be applied to the Export MPAN (except in the case of Smart Data Service updates where a different SDS can be appointed) PUB-033 from Registration Service MHHS-IF-034 to Registration Service PUB-035 from Registration Service ( For each Updated MPAN ) | BP003B Change of Existing Service Provider details | 220,225,96 | PUB-033 MHHS-IF-034 PUB-035 | None | [18 empty] | Y
MHHS-BR-DS-011.1 | SDS | SDS initiated change of MDR | SDS must be able to , if required, initiate a change of MDR. This would be achieved by the SDS issuing the relevant interface/ event code via the Data Integration Platform to the Registration Service. The Registration Service will respond to these requests using the relevant interface. |  | Data Service should note: 1. In the case of Related MPANs, any accepted updates will also be applied to the Secondary MPANs MHHS-IF-034 [SDS-MDRUpdate] to Registration Service PUB-035 from Registration Service for each updated MPAN | BP003B Change of Existing Service Provider details | 226, 225,96 | MHHS-IF-034 PUB-035 | SDS - Service Smart Meters
MHHS-BR-DS-012.1 | Data Service | Receive Registration notification of Data Service accepted/rejected appointments | Data Service must obtain Registration Service Appointment Status Notification updates, acknowledging the Prospective Data Service accepted/rejected appointments, via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-035 | BP003 Change of Data Service | 91 | PUB-035 | [19 empty] | Y
MHHS-BR-DS-012 | Data Service | Receive Data Service lapsed notification | Data Service must obtain Registration Service Appointment Status Notifications, with Data Service lapsed appointments, via the appropriate interface on the Data Integration Platform and update records accordingly so as to ensure that the appointment does not become effective. ADS/SDS must delete meter technical details received for all lapsed appointments as soon as operationally practicable following receipt of the lapsed notification. |  | PUB-035 | BP003 Change of Data Service | 231/232 | PUB-035 | None | [18 empty] | Y
MHHS-BR-DS-013 | Data Service | Receive Data Service appointment notification | Data Service must obtain Registration Service Notification of Service Appointment & Supporting Info updates, confirming a Data Service appointment, via the appropriate interface on the Data Integration Platform and update records with MPAN and Meter Technical Details (ADS/SDS only). For the avoidance of doubt this is the message that indicates that an appointment will/has taken effect. |  | PUB-036. Note for Smart meters PUB-036 contains all the Meter Technical Detail required ( No additional D-flow as is the case with Trad and Advanced ) | BP003 Change of Data Service | 340 | PUB-036 | None | [18 empty] | Y
MHHS-BR-DS-016 | SDS | Receive Meter Technical Details from Smart Metering Service (Change of Data Service) | SDS must receive Meter Technical Details for Traditional meters via the appropriate interfaces (D0149 and D0150 on DTN), maintain records accordingly and investigate any discrepancies against data received from the Registration Service (PUB-036 via the Data Integration Platform). These details could be received from a prospective incoming Metering Service that does not turn out to be the Metering Service appointed when the Data Service appointment commences. Therefore ADS may wish to consider how to process these MTDs ie they will provide early view of MTDs at site, however further MTDs (which may be revised) could be received from a second subsequent Metering Service. |  |  | BP003 Change of Data Service | 345/346 | D0149 D0150 | SDS - Service Traditional meters
MHHS-BR-DS-018 | Data Service | Receive de-appointment notification | Data Service must obtain Registration Service Notification of Service De-Appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-037 Note, a second notification will be received, if the first notification does not identify the new Data Service. | BP003 Change of Data Service | 96 | PUB-037 | None
MHHS-BR-DS-019 | Data Service | Termination of third party arrangements | Data Service must, where required, make their own arrangements for terminating any third party service providers ( eg Meter Reading Service, Meter Data Retrieval Service ) via a mechanism agreed bilaterally |  |  | BP003 Change of Data Service | 302 |  | Use of third party service providers
MHHS-BR-DS-020 | SDS | Delete any active DSP Schedules | SDS must, via the Meter Data Retrieval Service (MDR), delete any active DSP Schedules, as defined in the Smart Energy Code, in line with the de-appointment date. |  |  | BP003 Change of Data Service | 302 |  | SDS - Service Smart Meters
MHHS-BR-DS-022 | ADS/SDS | Determination of consumption up to de-appointment | ADS/SDS must, on de-appointment, make all reasonable attempts to obtain actual consumption history up to the point of de-appointment, for Advanced and Smart meters, for submission to settlements |  |  | BP003 Change of Data Service | 301 |  | SDS - Service Smart meters
MHHS-BR-DS-029.1 | ADS/SDS | Receive Data Service appointment for linked Related MPAN | ADS/SDS must obtain Related MPAN appointments via the appropriate interface on the Data Integration Platform and update records with registration and metering details. ADS/SDS should note this message will be automatically triggered when a change of Data Service has successfully completed for the Primary Related MPAN. |  | PUB-036 | BP003 Change of Data Service | 790 | PUB-036 | None
MHHS-BR-DS-030.1 | ADS/SDS | Receive Data Service de-appointment for linked Related MPAN | ADS/SDS must obtain Related MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. ADS/SDS should note that this message will be automatically triggered when a change of Data Service has successfully completed for the Primary Related MPAN. |  | PUB-037 | BP003 Change of Data Service | 760 | PUB-037 | None
MHHS-BR-DS-023.1 | SDS | Attempt to recover Smart reads | Data Service must, for Smart meters and following a successful Change of Supplier or Change of Data Service, attempt to download the cumulative and register reads from the Smart meter and maintain records accordingly. |  |  | BP003C Transfer of Reads |  | 45,55 | SDS - Service Smart meters | Y | [17 empty] | Y
MHHS-BR-DS-024.0 | SDS | Receive Customer Own transfer read | Data Service must be able to receive a Customer Own Transfer Read sent by their partner Supplier and use for estimation as required in line with the Smart Validation & Estimation Method statement |  | D0010 on DTN | BP003C Transfer of Reads |  | D0010 | SDS - Service Traditional meters | [18 empty] | Y
MHHS-BR-DS-024 | SDS | Send estimated closing read | Outgoing SDS must, on de-appointment, in the absence of an actual valid read for a Traditional meter, send an estimated read for midnight on the day following the de-appointment ( ie if effective de-appointment is 23:59:59 on 1st Jan then read point should be 00:00:00 on 2nd Jan) to the new SDS, LDSO and old Supplier via the appropriate interface. Estimates will be required for each settlement register and should be determined using the Smart Validation & Estimation Method statement |  | D0010 on DTN | BP003C Transfer of Reads | 270 | D0010 | SDS - Service Traditional meters | [18 empty] | Y
MHHS-BR-DS-024.1 | SDS | Send estimated closing read | Outgoing SDS must, after 5 working days following de-appointment, in the absence of an actual valid read for a Smart meter, send an estimated cumulative read for midnight on the day following the de-appointment ( ie if effective de-appointment is 23:59:59 on 1st Jan then read point should be 00:00:00 on 2nd Jan) to the new SDS and new/old Supplier via the appropriate interface. Estimates should be determined using the Smart Validation & Estimation Method statement |  | MHHS-IF-041 | BP003C Transfer of Reads | 105/110 | MHHS-IF-041 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-024.2 | SDS | Send "hand-shake" actual closing read | Outgoing SDS must, within 5 working days following de-appointment, on retrieving an actual valid read for a Smart meter, send the actual cumulative read and register reads for midnight on the day following the de-appointment to the new SDS and new/old Supplier via the appropriate interface. |  | MHHS-IF-041 | BP003C Transfer of Reads | 100 | MHHS-IF-041 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-025 | SDS | Receive estimated closing read | SDS must be able to receive and process estimated register reads sent by the previous SDS via the appropriate interface and forward the estimated register reads to the incoming Supplier. |  | D0010 on DTN Data processing requirements captured separately | BP003C Transfer of Reads | 290 | D0010 | SDS - Service Traditional meters | [18 empty] | Y
MHHS-BR-DS-025.1 | SDS | Receive estimated cumulative closing read | SDS must be able to receive and process estimated cumulative closing reads sent by the previous SDS via the appropriate interface. Where SDS has retrieved it's own data, SDS could compare data received from the old Data Service to ensure no significant discrepancies. SDS should use the best data available for it's starting position. |  | PUB-041 Data processing requirements captured separately | BP003C Transfer of Reads | 125/130 | PUB-041 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-025.2 | SDS | Send New Supplier Opening cumulative read | Incoming SDS must, for smart meters, send the opening cumulative read and, where available register reads, for midnight on the day of appointment of the new SDS to the new Supplier via the appropriate interface. |  | MHHS-IF-041 | BP003C Transfer of Reads | 130 | MHHS-IF-041 | SDS - Service Smart meters
MHHS-BR-DS-028.1 | SDS | Receive Agreed Register Reads (Incoming) | SDS must be able to receive and process agreed register reads sent by the Incoming Supplier for a traditional meter via the appropriate interface and must use these as the opening register reads for that period of Supply. |  | D0010 on DTN | BP003D Agreed Reads | 75 | D0010 | SDS - Service Traditional meters
MHHS-BR-DS-028.2 | SDS | Receive Smart Agreed Reads (Incoming) | SDS must obtain and process agreed reads, sent on the Data Integration Platform by the Incoming Supplier for a Smart meter, via the appropriate interface and must use these as the opening reads for that period of Supply. |  | PUB-041 | BP003D Agreed Reads | 100 | PUB-041 | SDS - Service Smart meters
MHHS-BR-DS-028.3 | SDS | Receive Agreed Register Reads (Outgoing) | SDS must be able to receive and process agreed register reads sent by the Outgoing Supplier via the appropriate interface and must use these as the closing register reads for that period of Supply. |  | D0010 on DTN | BP003D Agreed Reads | 30 | D0010 | SDS - Service Traditional meters
MHHS-BR-DS-028.4 | SDS | Receive Smart Agreed Reads (Outgoing) | v |  | PUB-041 | BP003D Agreed Reads | 45 | PUB-041 | SDS - Service Smart meters
MHHS-BR-DS-031 | Data Service | Send notification of a customer direct contract | Data Service must publish a Customer Direct Contract Advisory on the Data Integration Platform via the appropriate interface for each MPAN that forms part of the contract, this will also include the contract end date. This can be done only where a contract has been formally agreed with the customer. |  | MHHS-IF-038 to Registration Service Note, for evergreen contracts the flag and end date should be updated every three years | BP003 Change of Data Service | 910 | MHHS-IF-038 | Service Customer Direct contracts | Y | [17 empty] | Y
MHHS-BR-DS-032 | Data Service | Receive customer direct contract response | Data Service must obtain Registration Service Customer Direct Contract Advisory Responses via the appropriate interface on the Data Integration Platform |  | PUB-039 | BP003 Change of Data Service | 950 | PUB-039 | Service Customer Direct contracts | [18 empty] | Y
MHHS-BR-DS-033 | Data Service | Manage acceptance of customer direct contract | Data Service must, for accepted responses, maintain records to show which MPANs have been flagged as a customer direct contract |  |  | BP003 Change of Data Service | 950 |  | Service Customer Direct contracts | [18 empty] | Y
MHHS-BR-DS-034 | Data Service | Coordination of customer direct contract appointments | Data Service must continue to manually coordinate the appointment of MPANs within the contract with other industry participants. |  | Notes: 1. The setting of the customer direct contract flag is simply an indicator held in the registration system and will have no effect in the initiation or blocking of other participants service appointment activities | BP003 Change of Data Service | 900 |  | Service Customer Direct contracts | [18 empty] | Y
MHHS-BR-DS-035 | Data Service | Amendment or termination of customer direct contract | Data Service must have the ability to cancel or change the end date of a customer direct contract using the appropriate interface on the Data Integration platform |  | MHHS-IF-038 to Registration Service | BP003 Change of Data Service | 910 | MHHS-IF-038 | Service Customer Direct contracts | [18 empty] | Y
MHHS-BR-DS-036 | Data Service | Manage rejection of customer direct contract | Data Service must investigate any rejections of customer direct contracts and re-submit as appropriate |  |  | BP003 Change of Data Service | 950 |  | Service Customer Direct contracts | [18 empty] | Y
MHHS-BR-DS-037 | Data Service | Coordination of failed customer direct contract | Data Service must, in the case of rejection for an existing contract, liaise with their customer and other participants to determine why it appears overlapping contracts might exist |  |  | BP003 Change of Data Service | 950 |  | Service Customer Direct contracts | [18 empty] | Y
MHHS-BR-DS-040 | Data Service | Publish timely data | Data Service must process and publish all data in line with timescales set out in the Operational Choreography document |  |  | BP004 Data Collection | 15 |  | None | [18 empty] | Y
MHHS-BR-DS-041 | SDS | Request consumption in line with customer consent | SDS must request meter data retrieval in line with the customers stated consent preference as provided by the Registration Service |  |  | BP004 Data Collection | 60 |  | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-042 | SDS | Request collection of consumption | SDS must, via a Meter Data Retrieval Service (MDR), send the required Service Request(s), as defined in the Smart Energy Code, to the Data Communications Company (DCC) so as to obtain data in line with the customer consent ( Service request(s) may need to cover recovery of period consumption and cumulative reading as per customer consent for both import and export ) |  |  | BP004 Data Collection | 70 |  | SDS - Service Smart Meters | [18 empty] | Y
MHHS-BR-DS-042.1 | SDS | Receive confirmation that DCC is updated with new MDR details | SDS must obtain Registration Service Appointment Status Notifications, with confirmation that DCC has been updated with the new MDR details, via the appropriate interface on the Data Integration Platform, update records accordingly and inform MDR that they can start data collection from the effective start date. |  | PUB-035 | BP003A CSS and DCC update | 120 | PUB-035 | SDS - Service Smart Meters | [18 empty] | Y
MHHS-BR-DS-043 | SDS | Manage meter data request rejections | SDS must, via a MDR, manage meter data request rejections from DCC |  |  | BP004 Data Collection | 84 |  | SDS - Service Smart Meters
MHHS-BR-DS-044 | SDS | Process DCC meter access outcome response | SDS must, via a MDR, receive data recovered from the meter contained in the DCC Service Request response (Service Requests as outlined in the Smart Energy Code) |  |  | BP004 Data Collection | 100 |  | SDS - Service Smart Meters | [18 empty] | Y
MHHS-BR-DS-045 | ADS/SDS | Schedule site visit (non Trad) | ADS/SDS must have the capability to schedule and manage site visits to Smart/ AMR sites where agreed with the Supplier in order to obtain an on-site read |  |  | BP004 Data Collection | 10/110 |  | SDS - Service Smart meters | Y | [17 empty] | Y
MHHS-BR-DS-046 | SDS | Schedule site visit | SDS must, via a third party where required, manage a schedule of site visits for Traditional meters and arrange site visits to enable submission of consumption data for settlements in line with timescales set out in the Operational Choreography document |  |  | BP004 Data Collection | 110 |  | SDS - Service Traditional meters | Y
MHHS-BR-DS-047 | SDS | Attempt meter read | SDS must, via a third party where required, read the meter and maintain reading details accordingly |  |  | BP004 Data Collection | 120/130 |  | SDS - Service Traditional meters | Y | [17 empty] | Y
MHHS-BR-DS-048 | SDS | Attempt meter read | SDS must, via a third party where required, record the reason why a meter cannot be read and maintain records accordingly |  |  | BP004 Data Collection | 120 |  | SDS - Service Traditional meters | Y
MHHS-BR-DS-049 | ADS/SDS | Receive and process Supplier provided register readings | ADS/SDS must be able to receive and process Supplier provided register read(s) for Traditional and Advanced meters (where appropriate), however sourced, via the appropriate interface. |  | D0010 on DTN | BP004 Data Collection | 130 | D0010 | SDS - Service Traditional meters | [18 empty] | Y
MHHS-BR-DS-050 | ADS/SDS | Receive and process Supplier provided cumulative readings | ADS/SDS must be able to receive and process a Supplier provided cumulative read (Smart and Advanced only), actual/customer however sourced, via the appropriate interface on the Data Integration Platform |  | PUB-041 on DIP | BP004 Data Collection | 130 | PUB-041 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-051 | ADS/SDS | Notify supplier unable to read meter | ADS/SDS must provide a notification to the Supplier of a failure to obtain a meter reading arising from a site visit via the appropriate interface |  | D0004 on DTN or as agreed bilaterally | BP004 Data Collection | 16/120 | D0004 | None | [18 empty] | Y
MHHS-BR-DS-052 | SDS | Receive consumption for Smart meters | SDS must record Coordinated Universal Time (UTC) period data consumption for a given MPAN, received from the DCC, on Smart Data Service systems |  |  | BP004 Data Collection | 130 |  | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-053 | SDS | Receive failure response from DCC | SDS must consider how best to deal with a failure response for a given MPAN, received from DCC, on Smart Data Service systems in terms of re-attempting to obtain the data prior to resorting to estimation or escalating to the Supplier |  |  | BP004 Data Collection | 130 |  | SDS - Service Smart meters
MHHS-BR-DS-057 | ADS/SDS | Receive Supplier to DS notification | ADS/SDS must obtain Supplier to DS notification via the appropriate interface on the Data Integration Platform |  | PUB-024 | BP004 Data Collection | 230 | PUB-024 | None | [18 empty] | Y
MHHS-BR-DS-058 | ADS/SDS | Process Supplier to DS notification | ADS/SDS must update their systems with any details from the Supplier notification of vacant sites, no communications, remote disconnection and remote reconnection |  | Note: Long term vacant and disconnection can impact how the Data Service should process data as described in the Method Statements. Remote disconnection and Remote reconnection only utilised for Smart. | BP004 Data Collection | 240 |  | None | [18 empty] | Y
MHHS-BR-DS-060 | ADS/SDS | Expiry of DS notification | ADS/SDS should expire a notification (and the effect of that notification) in line with the data contained within the original notification or any revised expiry date received following the original message via the appropriate interface |  | PUB-024 | BP004 Data Collection | 230 | PUB-024 | None
MHHS-BR-DS-073 | SDS | Prepare UTC Period Level Consumption | SDS must prepare MPAN level UTC Period Level Consumption Data in line with the Smart Validation & Estimation Method statement |  |  | BP005 Data Processing | 70-110 (BP004-160) |  | None | Y | [17 empty] | Y
MHHS-BR-DS-075 | SDS | Historic data | SDS must store and use historic data to enable validation of period reads in line with the Smart Validation & Estimation Method Statement |  |  | BP005 Data Processing | 70-110 (BP004-160) |  | None | [18 empty] | Y
MHHS-BR-DS-077 | SDS | Receive load shaping data | SDS must obtain Load Shape Data and utilise data as described in the Smart Validation & Estimation Method Statement. Load shaping data will be available via the appropriate interfaces on the Data Integration Platform or as static data published to a publically accessible URI. |  | Currently Load Shape Service Period Data (PUB-022) and Load Shape Service Totals Data (PUB-023) | BP005 Data Processing | 120 | PUB-022 PUB-023 | None | [18 empty] | Y
MHHS-BR-DS-080 | SDS | Receive updated load shaping data | SDS must in exceptional circumstances when a new load shape is made available, reprocess previously submitted data following the Smart Validation & Estimation Method Statement |  | Currently Load Shape Service Period Data (PUB-022) and Load Shape Service Totals Data (PUB-023) This is expected to be an extremely rare occurrence. Data Services should consider whether this is automated or managed through their internal support processes | BP005 Data Processing | 120 | PUB-022 PUB-023 | None
MHHS-BR-DS-082 | Data Service | Identify Load Shapes to be used for estimating | Data Service must, where required for estimating, identify (based on MPAN Registration data) the load shapes associated with each MPAN from the Load Shape Category table in Industry Standing Data. Data Service should maintain a record of any load shapes used. |  |  | BP005 Data Processing |  |  | None | Y
MHHS-BR-DS-084 | SDS | Estimate missing/invalid consumption | SDS must estimate consumption for any missing/ invalid periods using the Smart Validation & Estimation Method Statement |  |  | BP005 Data Processing | 130 |  | None | Y | [17 empty] | Y
MHHS-BR-DS-087 | SDS | Validate UTC Period Level Consumption Data | SDS must validate UTC Period Level Consumption Data in line with the Smart Validation & Estimation Method Statement |  |  | BP005 Data Processing |  |  | None | Y | [17 empty] | Y
MHHS-BR-DS-089 | SDS | Estimate missing/invalid consumption | SDS must re-estimate consumption for any estimated UTC periods using the Smart Validation & Estimation Method Statement where further data becomes available to support a more accurate estimate being submitted, in line with the Operational Choreography |  |  | BP005 Data Processing | 130 |  | None | [18 empty] | Y
MHHS-BR-DS-092 | SDS | Validate full period consumption | SDS must validate the full set of UTC Period Level Consumption Data for a given submission, including any estimates, in line with the Smart Validation & Estimation Method Statement |  |  | BP005 Data Processing | 140 |  | None | Y | [17 empty] | Y
MHHS-BR-DS-093 | Data Service | Submit validated UTC Period Level Consumption Data | Data Service must publish/republish validated UTC Period Level Consumption Data ( kWh to 3 decimal places ) on the Data Integration Platform using the appropriate interface for all appointed MPAN's in line with the Operational Choreography document for each day of their appointment |  | MHHS-IF-021 to Central Settlements, Supplier and LDSO | BP005 Data Processing | 50/150 | MHHS-IF-021 | None | [18 empty] | Y
MHHS-BR-DS-094 | Data Service | Submit validated UTC Period Level Consumption Data (updated) | Data Service must republish updated validated UTC Period Level Consumption Data ( kWh to 3 decimal places ) as actual data, improved estimates or revised input data become available. ADS/SDS must re-estimate if new consumption data, meter reads or Meter Technical Details are received. UMSDS must reprocess data on receipt of updated Inventory Data, PECU Array Data or CMS Data, or where there is a change to ISD. |  | MHHS-IF-021 to Central Settlements, Supplier and LDSO | BP005 Data Processing | 50/150 | MHHS-IF-021 | None | [18 empty] | Y
MHHS-BR-DS-094.1 | Data Service | Receive Consumption Data rejections | Data Service must obtain UTC Settlement Period Consumption Data Rejections, sent by Central Settlements on the Data Integration Platform, via the appropriate interface, investigate the validation failures and resubmit as appropriate |  | PUB-014 | BP005 Data Processing | BP016 Step 260 | PUB-014 | None | [18 empty] | Y
MHHS-BR-DS-094.2 | Data Service | Receive Default Consumption | Data Service must obtain Notification of Defaulted UTC Settlement Period Consumption Data provided by Central Settlements via the appropriate interface on the Data Integration Platform and maintain records accordingly. Data Service could choose to use the characteristics data to derive and validate the load shape used for the default consumption values. In the case of ADS/UMSDS it should be noted that the GSP Group ID will not be required to determine the load shape. |  | PUB-013 | BP005 Data Processing |  | PUB-013 | None
MHHS-BR-DS-095 | Data Service | Maintain records of submitted data | Data Service must keep a record of data submitted for audit purposes, as outlined in the Non Functional requirements. |  |  | BP005 Data Processing |  | 50/150 | None | [18 empty] | Y
MHHS-BR-DS-097 | Data Service | Investigate and resolve issues | Data Service must support investigations and resolution of issues highlighted by Central Settlements reporting and feedback from other participants |  |  | BP005 Data Processing |  |  | None
MHHS-BR-DS-098.1 | ADS/SDS | Validate meter reading data | ADS/SDS must validate meter readings received from site visits or Customer Own Reads provided by the Supplier in line with the relevant Method Statement. |  |  | BP005 Data Processing | 175 |  | None
MHHS-BR-DS-098.2 | ADS/SDS | Publish cumulative meter reads | ADS/SDS must, where available for Smart and Advanced meters, publish cumulative meter reads to the Supplier and LDSO via the appropriate interface. |  | IF-041 | BP005 Data Processing | 315 | IF-041 | SDS - Service Smart meters
MHHS-BR-DS-098 | ADS/SDS | Provide meter reading data via D0010 | ADS/SDS must send register meter readings to the Supplier and LDSO via the appropriate interface. Where the readings, pass validation and are used by the Data Service they should have the Meter Reading Status (J0047) set to ‘T’ or where they fail validation set to ‘F’ in the D0010 flow. |  | D0010 on DTN | BP005 Data Processing | 190 | D0010 | SDS - Service Traditional meters | Y | [17 empty] | Y
MHHS-BR-DS-104 | Data Service | Receive de-appointment with reason of CSS deregistration | Data Service must obtain Registration Service Notification of Service De-Appointments, with a de-appointment reason of dereg, via the appropriate interface on the Data Integration Platform and maintain records accordingly. |  | PUB-037 | BP007 Disconnection | 140 | PUB-037 | None | Y | [17 empty] | Y
MHHS-BR-DS-105 | Data Service | Consumption treatment following de-appointment | Data Service must cease submission to settlement for any settlement dates after the effective date of it's de-appointment. For clarity, the Data Service retains responsibility for submitting data for the dates that they were appointed for, even after they have been de-appointed. |  |  | BP007 Disconnection | 140 BP003 - 96 BP003 - 760 |  | None | [18 empty] | Y
MHHS-BR-DS-106 | Data Service | Receive change of energisation notification | Data Service must obtain Registration Service Notification of Change of Energisation Status updates via the appropriate interface on the Data Integration Platform and maintain records accordingly. |  | PUB-008 | BP008 Change of energisation | 155 | PUB-008 | None | Y | [17 empty] | Y
MHHS-BR-DS-107 | Data service | Investigate consumption on de-energised MPAN | Data Service must escalate to the Supplier or UMSO ( UMSDS only) where it is identified that consumption is occurring on a MPAN that is de-energised. However, this should not prevent it's submission into settlements. |  |  | BP008 Change of energisation |  |  | None
MHHS-BR-DS-109 | SDS | Receive register read data for energisation change | SDS must receive register reads from the Metering Service via the appropriate interface for Traditional meters and store for use in estimation processes where no better data is available. Where no reading(s) are provided alongside the change in Energisation Status, the Data Service should, after 5 working days, generate an estimated reading(s) for the Date of the Change of Energisation Status (reflecting the nature of the Energisation Change) using the most appropriate method from the SDS Method Statement. |  | Initial read(s) for energisation, Final read(s) for de-energisation D0010 on DTN | BP008 Change of energisation | 145 | D0010 | SDS - Service Traditional meters | Y | [17 empty] | Y
MHHS-BR-DS-110 | SDS | Provide register meter reading data to Supplier | SDS must send change of energisation register meter readings to the LDSO and Supplier for Traditional meters, where received, via the appropriate interface |  | Initial read(s) for energisation, Final read(s) for de-energisation D0010 on DTN | BP008 Change of energisation | 145 | D0010 | SDS - Service Traditional meters | [18 empty] | Y
MHHS-BR-DS-111 | ADS/SDS | Receive change of energisation cumulative reads | ADS/SDS must, where provided by the Metering Service, obtain Advanced and Smart cumulative reads via the appropriate interface on the Data Integration Platform and store for use in the estimation process where no better data is available |  | Meter Readings (PUB-041) | BP008 Change of energisation | 150 | PUB-041 | SDS - Service Smart meters | Y | [17 empty] | Y
MHHS-BR-DS-115 | ADS/SDS | Process change of energisation reads | ADS/SDS must utilise change of energisation read(s) data for settlement, only where a complete set of validated data is not available from the meter | [24 empty] | Y
MHHS-BR-DS-116 | Data Service | Process change of energisation reads | Data Service must re-process any UTC Period Level Consumption Data previously submitted to settlements, where advised of an energisation status change and no actual consumption has been recorded, particularly where this is back-dated |  | Details in data processing process. Note: only applies to UMSDS if Inventory data is available | BP008 Change of energisation | 185 |  | None
MHHS-BR-DS-117 | ADS/SDS | Receive change of metering notification | ADS/SDS must obtain and process updates to meters and meter technical details via the appropriate interface on the Data Integration Platform |  | PUB-006 | BP009 Change of Metering | 185 | PUB-006 | None | Y | [17 empty] | Y
MHHS-BR-DS-118 | ADS/SDS | Receive change of metering cumulative reads | ADS/SDS must obtain and process cumulative meter reads (Smart and Advanced only) received via the appropriate interface on the Data Integration Platform and store for use in estimation processes where no better data is available |  | Initial reads for Exchange and Install, Final reads for Exchange and Removal Meter Readings (PUB-041) | BP009 Change of Metering | 180 | PUB-041 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-121 | SDS | Receive metering updates | SDS must receive Traditional meter updates via the appropriate interface, maintain records accordingly and investigate any discrepancies with data received from the Registration Service. In the case where Related MPANs or Import/Export linked meters exist, SDS should expect to receive Meter Technical Details for all the MPANs in the Related MPAN or Import/Export group. |  | D0149 and D0150 on DTN | BP009 Change of Metering | 175 | D0149 D0150 | SDS - Service Traditional meters | Y | [17 empty] | Y
MHHS-BR-DS-122 | SDS | Receive change of metering register reads | SDS must receive register reads via the appropriate interface for Traditional meters and store for use in estimation processes where no better data is available. Where no reading(s) are provided alongside the change in metering, the Data Service should, after 5 working days, generate an estimated reading(s) for the Date of the Removal of the previous meter(s) using the most appropriate method from the Method Statement. Any newly installed meter should be assumed to have been installed with an index position of Zero. |  | Initial reads for Exchange and Install, Final reads for Exchange and Removal D0010 on DTN | BP009 Change of Metering | 175 | D0010 | SDS - Service Traditional meters | [18 empty] | Y
MHHS-BR-DS-123 | ADS/SDS | Process change of metering reads | ADS/SDS must utilise change of metering read(s) data for settlement, only where a complete set of validated data is not available from the meter |  | Details in data processing process. | BP009 Change of Metering | 225 |  | None
MHHS-BR-DS-124 | ADS/SDS | Process change of metering reads | ADS/SDS must re-process any UTC Period Level Consumption Data previously submitted to settlements, where advised of any change of metering and no actual consumption has been recorded, particularly where this is back-dated |  | Details in data processing process. | BP009 Change of Metering | 225 |  | None | [18 empty] | Y
MHHS-BR-DS-125 | Data Service | Receive Meter Point Location (MPL) address/GSP Group ID update notification | Data Service must obtain MPL address/ GSP Group ID updates via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-018 | BP010 Change of registration data | 70 | PUB-018 | None | [18 empty] | Y
MHHS-BR-DS-126 | ADS/SDS | Receive domestic premise indicator update notification | ADS/SDS must obtain domestic premise indicator updates via the appropriate interface on the Data Integration Platform, maintain records accordingly and consider impacts to service delivery as required |  | PUB-018 | BP010 Change of registration data | 160 | PUB-018 | None | [18 empty] | Y
MHHS-BR-DS-127 | ADS/SDS | Receive Consent Granularity Indicator update notification | ADS/SDS must obtain Consent Granularity Indicator updates via the appropriate interface on the Data Integration Platform, maintain records accordingly and assess if a change in recovery pattern is required |  | PUB-026 | BP010 Change of registration data | 230 | PUB-026 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-128 | ADS/SDS | Change recovery pattern | ADS/SDS must commence collection of settlement period consumption data (active import) in line with the updated customer consent, from the date that the Consent Granularity Indicator update notification is received, even if the date the change in consent was captured is in the past. There is no requirement to alter data that has been previously captured using the previously consented recovery pattern. |  |  | BP010 Change of registration data | 230 |  | SDS - Service Smart meters | Y | [17 empty] | Y
MHHS-BR-DS-130 | SDS | Update DCC Service Requests | SDS must, via a Meter Data Retrieval Service (MDR), send the required Service Request, as defined in the Smart Energy Code, to the Data Communications Company (DCC) so as to obtain data in line with the updated customer consent, where the change of Consent Granularity Indicator requires this. |  |  | BP010 Change of registration data | 230 |  | SDS - Service Smart Meters | Y | [17 empty] | Y
MHHS-BR-DS-130.1 | ADS/SDS | Receive Related MPAN update notification | ADS/SDS must be able to obtain Related MPAN updates via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-020 | BP010B Change of registration data | 380 | PUB-020 | None | [18 empty] | Y
MHHS-BR-DS-130.2 | Data Service | Receive Energy Direction update notification | Data Service must be able to obtain Energy Direction updates via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-018 | BP010 (BPM2) Change of registration data | 490 | PUB-018 | None | [18 empty] | Y
MHHS-BR-DS-130.3 | Data Service | Receive Metered Status update notification | Data Service must be able to obtain Metered Status updates via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-018 | BP010 (BPM2) Change of registration data | 610 | PUB-018 | None | [18 empty] | Y
MHHS-BR-DS-130.4 | SDS | Receive SMSO update notification | SDS must obtain SMSO updates from Registration Service via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-026 | BP010 (BPM3) Change of registration data | 830 | PUB-026 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-130.5 | Data Service | Receive Import/Export linkage update notification | Data Service must be able to obtain Import/Export linkage updates via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-020 | BP010C Change of registration data | 930 | PUB-020 | None | [18 empty] | Y
MHHS-BR-DS-130.6 | Data Service | Receive Profile Class/SSC update notification | Data Service must obtain legacy data item (Profile Class/SSC) updates from Registration Service via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-026 | BP010D Change of registration data | 1050 | PUB-026 | None | [18 empty] | Y
MHHS-BR-DS-130.7 | SDS | Receive DCC enrolment update notification | SDS must be able to obtain DCC enrolment updates via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | PUB-018 | BP010D Change of registration data | 1120 | PUB-018 | SDS - Service Smart meters | [18 empty] | Y
MHHS-BR-DS-132 | SDS | Qualify to provide a Smart Data Service under the Balancing and Settlement Code | The SDS must be qualified to operate as a Data Service in line with the Qualification Process and the Smart Data Service BSCPs |  | Exact qualification mechanism and BSCP to be confirmed. The BSCPs will be developed post design, but to be reflective of the requirements/design. The new BSCP will cover the non MHHS process requirements for on site activities eg management of tampering/ theft. | Overall |  |  | None | Y | [17 empty] | Y
MHHS-BR-DS-135 | SDS | Engage Meter Reading Service | Where a SDS plans to provide a service to support Traditional Meters, that SDS must, where required, engage with Meter Reading Service(s) and agree bilaterally how data will be shared so that the SDS can provide a service for Traditional meters in line with the Smart Data Service BSCP |  | BSCP to be confirmed. | Overall |  |  | SDS - Service Traditional meters
MHHS-BR-DS-136 | SDS | Engage Meter Data Retrieval Service | SDS must, where required, engage with a qualified Meter Data Retrieval Service(s) for all Smart meters and agree bilaterally how data will be shared so that the SDS can provide a service for Smart meters in line with the Smart Data Service BSCP |  | MDR must be qualified to the SEC to retrieve data for settlements from the DCC BSCP to be confirmed. | Overall |  |  | SDS - Service Smart Meters
MHHS-BR-DS-137 | All Services | Flexible settlement period duration | All services should, where possible, build in the ability to configure the settlement period duration during their solution design, in order to support any future move to a different settlement period duration |  | Currently 30 minutes | Overall |  |  | Advice | Y
MHHS-BR-DS-138 | All Services | Publish data via the Data Integration Platform in agreed ISO8601 date/time format | All services must publish data following ISO8601 format - YYYY-MM-DDTHH:MM:SS±TZH:TZM. |  |  | Overall |  |  | None
MHHS-BR-DS-139 | All Services | Receive Industry Standing Data | All services must obtain Industry Standing Data (ISD) update notifications via the appropriate interface, and if required take necessary steps to obtain refreshed ISD data, maintain their records accordingly and reference/ utilise ISD as appropriate as part of the service delivery. |  | PUB-047 | Overall |  | PUB-047 | None
MHHS-BR-DS-139.1 | All Services | Map DIP ID/ Role to DTN Market Participant ID/ Role | All services must utilise Industry Standing Data to identify the relevant DIP ID/Role or DTN Market Participant ID/Role, as appropriate, to be used when communicating over the DIP/DTN. |  | PUB-047 | Overall |  | PUB-047 | None
MHHS-BR-DS-139.2 | All Services | Message addressing | All services must derive and populate the DIP addressing (primary recipients) for all outbound interfaces in line with the rules described in the interface specification |  | Note, Addressing functionality is described in the End to End Solution Architecture. | Overall |  |  | None
MHHS-BR-DS-141 | Data Service | Data retention and audit | Data services must retain data in line with the Non Functional requirements |  |  | Overall |  |  | None | Y
MHHS-BR-DS-142 | All Services | Process data in a timely manner | All services must process data and share outputs with other parties in line with timescales set out in the Operational Choreography document |  |  | Overall |  |  | None
MHHS-BR-DS-143.2 | All Services | Qualification for Data Integration Platform access | All services must undergo qualification in order to realise operational access to the DIP |  | Exact qualification mechanism to be confirmed. | Overall |  |  | None
MHHS-BR-DS-143 | All Services | Manage Data Integration Platform error messages | All Services must obtain Data Integration Platform error messages in line with the End to End Solution Architecture, review the impacted data and re-issue corrected messages/transactions as required |  |  | Overall |  |  | None
MHHS-BR-DS-143.1 | All Services | Inbound DIP message validation | All services must return Data Integration Platform error messages in line with the End to End Solution Architecture. Unexpected and/or un-processable messages should be returned to the DIP/ originating party |  |  | Overall |  |  | None
MHHS-BR-DS-144 | All Services | Ensure responses received | All services, when transacting via the DIP, must ensure that they implement monitoring so as to identify where expected responses are not received within standard DIP SLA's, as outlined in the Operational Choreography, so that the appropriate investigative/ resolution activity can be undertaken. |  |  | Overall |  |  | None
MHHS-BR-DS-144.1 | All Services | DIP activity/ performance dashboard | All services must have familiarity with and actively monitor any Data Integration Platform tools for tracking messages, as outlined in the End to End Solution Architecture, so that the necessary investigative action can be taken when required. |  |  | Overall |  |  | None
MHHS-BR-DS-145 | All Services | Reporting requirements | All services must provide and receive reports in line with agreed reporting requirements and delivery method as outlined in MHHSP-ERI011B ECS reports and interfaces |  | Service Provider reporting is out of scope of M5 Design Baseline- Performance Assurance requirements to be drafted after M5 | Overall |  |  | None
MHHS-BR-DS-146 | ADS/SDS | Identify related MPANs | ADS/SDS, where required, must be able to identify ( using the appropriate interface ) and appropriately manage related MPANs as described in the relevant BSCP |  | PUB-033, PUB-035, PUB-036 | Overall |  |  | None | Y | [17 empty] | Y
MHHS-BR-DS-147.1 | SDS | Ability to handle faults for Smart and Traditional Meters | SDS must notify any faulty equipment to the Supplier via a D0001 or bilaterally agreed interface as outlined in the relevant BSCP |  | For Smart and Traditional meters the Supplier will take the lead investigating faults. The Supplier will be responsible for notifying the Data Service if they require data to be resubmitted as a result of a fault. New BSCP to be confirmed. | Overall |  |  | None | Y
MHHS-BR-DS-149 | All Services | Ability to use existing DTC flows | Some MHHS processes require the continued use of DTC flows, Services should ensure that if they plan to service customer types that utilise these processes then a mechanism will be required for transmitting/receiving DTC flows. |  |  | Overall |  |  | None
MHHS-BR-DS-150 | Data Service | Most accurate data for each settlement run | Data Service must ensure that its systems and processes operate in such a way as to support the most up to date and accurate data being available to settlements in advance of the cut off for each formal settlement run as outlined in the Operational Choreography. |  |  | Overall |  |  | None
MHHS-BR-DS-152 | All Services | Validate data | All Services should implement data validation steps and techniques that they feel are appropriate to ensure the most accurate and efficient delivery of the service |  |  | Overall |  |  | Advice
MHHS-BR-DS-154.1 | ADS/SDS | Receive customer details | ADS/SDS must receive Notification of Customer Details from the Supplier via the appropriate interface and maintain records accordingly |  | D0302 on the DTN | Overall |  | D0302 | None
MHHS-BR-DS-154.2 | ADS/SDS | Manage previous customer details | ADS/SDS must, on receipt of updated customer details, delete or obfuscate the previously held customer details |  |  | Overall |  |  | None
MHHS-BR-DS-154.3 | ADS/SDS | Receive Priority Service Register (PSR) details | ADS/SDS must receive Priority Service Details from the Supplier via the appropriate interface and maintain records accordingly |  | D0225 on the DTN | Overall |  | D0225 | None
MHHS-BR-DS-154.4 | ADS/SDS | Manage previous Priority Service Register (PSR) details | ADS/SDS must, on receipt of updated PSR details, delete or obfuscate the previously held PSR details |  |  | Overall |  |  | None
MHHS-BR-DS-154.5 | ADS/SDS | Manage Customer/ Priority Service Register (PSR) details on de-appointment | ADS/SDS must, on receipt of a de-appointment notification becoming effective, delete or obfuscate the previously held PSR and customer details |  |  | Overall |  |  | None
MHHS-BR-DS-156 | All Services | Electricity Enquiry Service | All services could choose to take advantage of the Electricity Enquiry Service (EES previously known as ECOES) in order to obtain the current data associated with an MPAN in cases where a query arises around the accuracy of data held. |  |  | Overall |  |  | Advice
MHHS-BR-DS-157 | All Services | Manage data on receipt of interfaces | All Services must maintain and update their records with any data received on interfaces to ensure the most accurate and efficient delivery of the service. |  |  | Overall |  |  | None
MHHS-BR-DS-158 | MHHS-BR-DS-158 | Receive Change of Segment Meter exchange confirmation | ADS/SDS must be able to obtain a Registration Service Change of Segment Meter Exchange confirmation with MTDs and readings via the appropriate interface on the Data Integration Platform, even when it is from a 3rd party Metering Service (ie not the currently appointed Metering Service). |  | PUB-006 | BP011A Change of Connection Type/ Change of Segment | 285 | PUB-006 | None | [18 empty] | Y | Y
MHHS-BR-DS-159 | MHHS-BR-DS-159 | Receive Change of Connection Type notification | ADS/SDS must be able to obtain Registration Service Change of Connection Type notifications via the appropriate interface on the Data Integration Platform and maintain records accordingly. |  | PUB-043 | BP011B Change of Connection Type/ Change of Segment | 544 | PUB-043 | None | [18 empty] | Y | Y
MHHS-BR-DS-159.1 | MHHS-BR-DS-159.1 | Receive Invalid Market Segment advisory | ADS/SDS must obtain Invalid Market Segment Advisory notifications, sent from the Registration Service on the Data Integration Platform, via the appropriate interface. |  | PUB-045 Registration Service will run the Advisory Notification process each processing day to identify MPANs with an Invalid Market Segment - that is to say sites with an Invalid Connection Type-Meter Type Combination. | BP011C Registration Service Monitoring & Notification | 596 | PUB-045 | None | [18 empty] | Y | Y
MHHS-BR-DS-160 | ADS/SDS | Receive Override Read | ADS/SDS must obtain Override Reads, sent by the Supplier on the Data Integration Platform, via the appropriate interface and maintain records accordingly. |  | PUB-041 | BP016 Consumption Amendment | 520 | PUB-041 | None | Y | [17 empty] | Y | Y
MHHS-BR-DS-161 | ADS/SDS | Process Override Read | ADS/SDS must, following consultation with the Supplier if required, use the override read to recalculate any pre-RF consumption and re-issue the consumption data as required. ADS/ SDS should bilaterally agree a process for highlighting and resolving any disagreement in the usage of either Agreed or Override Readings as part of their contractual agreements with the Supplier. |  |  | BP016 Consumption Amendment | 540 |  | None | [18 empty] | Y | Y
MHHS-BR-DS-162 | ADS/SDS | Receive Consumption Amendment Request | ADS/SDS must obtain Consumption Amendment Requests, sent by the Supplier on the Data Integration Platform, via the appropriate interface and maintain records accordingly |  | PUB-027 | BP016 Consumption Amendment | 70 | PUB-027 | None | [18 empty] | Y | Y
MHHS-BR-DS-163 | ADS/SDS | Validate MPAN ownership | ADS/SDS must validate that they were responsible for the MPAN for the Consumption Amendment Period requested |  |  | BP016 Consumption Amendment | 80 |  | None | [18 empty] | Y | Y
MHHS-BR-DS-164 | ADS/SDS | Calculate revised UTC period data | ADS/SDS must calculate the consumption and reactive data, where required, for each UTC period impacted by the Consumption Amendment Request using the relevant Method Statement. |  |  | BP016 Consumption Amendment | 85 |  | None | [18 empty] | Y | Y
MHHS-BR-DS-165 | ADS/SDS | Validate Consumption Amendment | ADS/SDS must validate the UTC period Consumption Amendment data in line with the relevant Method Statement |  |  | BP016 Consumption Amendment | 90 |  | None | [18 empty] | Y | Y
MHHS-BR-DS-166 | ADS/SDS | Reject Consumption Amendment Request | ADS/SDS must publish a Consumption Amendment rejection on the Data Integration Platform via the appropriate interface, where any validation is failed, with the appropriate rejection reason. |  | MHHS-IF-028 | BP016 Consumption Amendment | 90 | MHHS-IF-028 | None | [18 empty] | Y | Y
MHHS-BR-DS-167 | ADS/SDS | Issue revised UTC period data | ADS/SDS must publish validated UTC Period Level Consumption and Reactive Data ( where required ) for the Consumption Amendment on the Data Integration Platform using the appropriate interface |  | MHHS-IF-021 to Central Settlements, Supplier and LDSO | BP016 Consumption Amendment | 120 | MHHS-IF-021 | None | [18 empty] | Y | Y
MHHS-BR-DS-168 | SDS | Receive Supplier to DS notification (Off-Peak Declaration) | SDS must obtain Supplier to DS notification containing Off-peak Declarations via the appropriate interface on the Data Integration Platform |  | PUB-024 | BP004 Data Collection | 230 | PUB-024 | SDS Service Smart Meters
MHHS-BR-DS-169 | SDS | Calculate E7/E10 consumption | SDS must, where a Smart Meter is present and Consent Granularity is not set to Half-Hourly, where provided use the latest Off-peak Declaration Proportions received from the currently appointed Supplier, to calculate/re-calculate E7/E10 consumption for each Off-Peak day provided in the Declaration, in line with the SDS Method Statement. |  |  | BP004 Data Collection | 230 | PUB-024 | SDS Service Smart Meters
MHHS Functional Requirements
Note on Q9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this need blocked?
Note on S9: If yes this should be captured in PIT test completion report and defects added to ADO
Note on AB9: If yes this should be captured in PIT test completion report and defects added to ADO

## 6 Migration Requirements
Code Bodies to complete. Columns are aligned to REC and BSC assesment critieria and sections maintained by Code Bodies will be updated if the assesement critieria documents are updated.
Programme Participant to complete
Requirement | [9 empty] | PIT | [8 empty] | QT | [8 empty] | QAD
[10 empty] | Prepopulated | Prepopulated | Submit inline with timeline in PIT Guidance |  |  | Submit with PIT TCR |  |  |  | Prepopulated | Prepopulated |  | Submit with QT Test Plan |  | Submit with QT TCR |  |  |  | Prepopulated | Prepopulated
Reference | Market Role | Requirement | Requirement Description | Code | Supporting information/ questions | Process | Step | Interface | Optionality | PIT Testing Required (Y/N) | Entry Criteria for QT (Y/N) If No, participants are expected to have completed by QT exit | PIT Scenario ID - at least one but could be multiple | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | PIT Status (Passed, Failed, Not Run) | PIT Test Evidence Captured | Work Off Plan (Y/N) | Comments | SIT / QT Required (Y/N) | SIT/QT Scenario ID - at least one but could be multiple | QT Test Scenario/s to be executed | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | QT Status (Passed, Failed, Not Run) | SIT / QT Test Evidence in ADO (Y/N) | Work Off Plan (Y/N) | Comments | QAD Question (Y/N) | QAD Question Number
MHHS-Migration-CoA(DS)-DS-001 | Change of Agent - Smart | The incoming DS to retrieve a midnight read from the Smart Meter and send an IF-041 to the DIP. No half-hourly profile data (D0036 / D0380) to be sent in the case of half-hourly Smart Meters. | The incoming DS to retrieve a midnight read from the Smart Meter and send an IF-041 to the DIP. No half-hourly profile data (D0036 / D0380) to be sent in the case of half-hourly Smart Meters. |  |  | MHHSP-BPM-003 – Change of Service – Data Service (Forward Migration) | [12 empty] | Y
MHHS-Migration-CoA(DS)-DS-002 | Change of Agent - HH Advanced | In the case of half-hourly Advanced meters, new Data Service to receive a D0036 from the outgoing DC containing 3 months' of data. | In the case of half-hourly Advanced meters, new Data Service to receive a D0036 from the outgoing DC containing 3 months' of data. |  |  | MHHSP-BPM-003 – Change of Service – Data Service (Forward Migration) | [12 empty] | Y
MHHS-Migration-CoA(DS)-DS-003 | Change of Agent - Traditional | In the case of CoA only, incoming DS will receive a D0010 from the incumbent Supplier with specific values. Incoming DS to then use this read as the start read for the new MHHS arrangements. | In the case of CoA only, incoming DS will receive a D0010 from the incumbent Supplier with specific values. Incoming DS to then use this read as the start read for the new MHHS arrangements. |  | The D0010 will be populated with the following values: a. Reading Type = Initial b. Meter Reading Reason Code = 28 (Forward Migration CoA) | MHHSP-BPM-003 – Change of Service – Data Service (Forward Migration) | [12 empty] | Y
Y
MHHS-Migration-Can-DS-001 | Cancellation of a Migration CoA | Registration Service cancels a CoA Migration and follows the BAU de-appointment process. | When a future dated CoA Migration fails to take place, the Data Service needs to be able to process the relevant de-appointment flows (as per MHHS BAU processes) from the Registration Service. | [15 empty] | Y
MHHS-Migration-Can-DS-002 | Cancellation of a Migration CoS | Registration Service cancels a CoS Migration and follows the BAU de-appointment process. | When a CoS Migration is cancelled the Data Service needs to be able to process the relevant de-appointment flows (as per MHHS BAU processes) from the Registration Service. | [15 empty] | Y
MHHS-Migration-UNM-DS-001 | Migration of an Unmetered site | When an Unmetered site is being migrated, the Supplier should liaise with the new and outgoing Agents outside of any messages / interfaces. | When an Unmetered site is being migrated, the Supplier should liaise with the new and outgoing Agents outside of any market messaging / interfaces in order to work out how they will migrate the meter. | [15 empty] | Y
MHHS-Migration-Mis-DS-001 | All | All Agents will need to have made changes to their services and business processes by M11 to support the Migration of MPANs away from their portfolios when a Migration CoS occurs. | All Agents will need to have made changes to their services and business processes by M11 to support the Migration of MPANs away from their portfolios when a Migration CoS occurs. |  | Parties who have not made that change will cause data quality issues impacting consumers and settlement. | [13 empty] | Y
MHHS-Migration-Mis-DS-002 | All | All Agents wishing to operate the Reverse Migration process (to Switch consumers whose MPAN is under the MHHS arrangements) must have made changes to their services and business processes by M11. | All Agents wishing to operate the Reverse Migration process (to Switch consumers whose MPAN is under the MHHS arrangements) must have made changes to their services and business processes by M11. |  | Parties who have not made that change will cause data quality issues impacting consumers and settlement. | [13 empty] | Y
MHHS-Migration-Mis-DS-003 | Change of Agent - HH Smart | New DS will not receive any historical data from the outgoing HHDC. | New DS will not receive any historical data from the outgoing HHDC. | [15 empty] | Y
MHHS-Migration-Mis-DS-004 | Change of Supply | Reverse Migration: DS to adhere to the SLAs specified within the MHHS BAU Design as part of the various read sharing processes, unless explicitly called out. | Reverse Migration: DS to adhere to the SLAs specified within the MHHS BAU Design as part of the various read sharing processes, unless explicitly called out. | [15 empty] | Y
MHHS-Migration-Mis-DS-005 | Change of Agent or Change of Supply | When sending and processing DIP messages, DS's to adhere to the BAU MHHS Design SLAs, which will apply unchanged throughout the Migration period. | When sending and processing DIP messages, DS's to adhere to the BAU MHHS Design SLAs, which will apply unchanged throughout the Migration period. | [15 empty] | Y
MHHS-Migration-Mis-DS-006 | Change of Agent or Change of Supply | DS's to send all Legacy Data Flows via the DTN or via other agreed means. | DS's to send all Legacy Data Flows via the DTN or via other agreed means. | [15 empty] | Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
Y
N
N
N
N
Y
N
N
Y
N
N
Y
Y
N
N
N
N
N
Y
Y
N
N
N
N
N
N
N
Y
N
N
Y
Y
Y
Y
N
N
N
N
N
N
N
N
N
N
N
N
N
Y
N
N
N
N
N
N
N
N
N
Y
N
N
N
N
Y
N
N
N
N
N
N
N
Y
Y
Y
Y
Y
Y
Y
Y
Y
MHHS Migration Requirements
Note on S9: If yes this should be captured in PIT test completion report and defects added to ADO
Note on AB9: If yes this should be captured in PIT test completion report and defects added to ADO

## 7 Non Functional Requirements
Code Bodies to complete. Columns are aligned to REC and BSC assesment critieria and sections maintained by Code Bodies will be updated if the assesement critieria documents are updated.
Programme Participant to complete
Requirement | [9 empty] | PIT | [8 empty] | QT | [8 empty] | QAD
[10 empty] | Prepopulated | Prepopulated | Submit inline with timeline in PIT Guidance |  |  | Submit with PIT TCR |  |  |  | Prepopulated | Prepopulated |  | Submit with QT Test Plan |  | Submit with QT TCR |  |  |  | Prepopulated | Prepopulated
NFR Reference | Market Role | NFR Category | NFR Description | Code | Supporting information/ questions | Process | Step | Interface | Optionality | PIT Testing Required (Y/N) | Entry Criteria for QT (Y/N) If No, participants are expected to have completed by QT exit | PIT Scenario ID - at least one but could be multiple | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | PIT Status (Passed, Failed, Not Run) | PIT Test Evidence Captured | Work Off Plan (Y/N) | Comments | SIT / QT Required (Y/N) | SIT/QT Scenario ID - at least one but could be multiple | QT Test Scenario/s to be executed | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | QT Status (Passed, Failed, Not Run) | SIT / QT Test Evidence in ADO (Y/N) | Work Off Plan (Y/N) | Comments | QAD Question (Y/N) | QAD Question Number
E2E0014 | All | Compatibility | All services shall send and receive messages for all DIP interfaces and publications via the API definitions in the MHHS Swagger documentation (E2E003) | [12 empty] | Y | [8 empty] | Y
E2E0108 | All | Compatibility | All services shall interpret the http response code to determine the outcome of DIP validation level 1 for each message sent referenced by Sender Unique Reference & Transaction Id | [12 empty] | Y | [8 empty] | Y
E2E0109 | All | Compatibility | All services shall connect to the Receive Status Messages webhook DIP to establish the outcome of level 2,3,4 validation with messages referenced by Transaction Id | [12 empty] | Y | [8 empty] | Y
E2E0201 | All | Compatibility | Services shall undertake Level 3 message validation including structure and the format of individual data fields/elements shall be performed against the appropriate message schema definition of all interface interactions. | [12 empty] | Y | [8 empty] | Y
E2E0207 | All | Compatibility | Level 4 validation of the message content shall be established during processing by the Recipient and reported back to the Sender via the Send Status Messages API using the corresponding status code | [12 empty] | Y | [8 empty] | Y
E2E0211 | All | Compatibility | All messages received by DIP Participant systems shall be initially acknowledged as received in the http response of the API transaction | [12 empty] | Y | [8 empty] | Y
E2E1004 | All | Performance Efficiency | All Services (see exceptions) shall have capacity to process the following volumes of messages: - average daily volume of 66,000 - peak daily volume of 300,000 - average hourly volume of 2,750 - peak hourly volume of 35,000 - annual volume of 24M | [12 empty] | Y | [8 empty] | Y
E2E1005 | All | Performance Efficiency | All Services (unless explicitly referenced below) shall have capacity to process the following volumes of messages: - peak daily volume of 300,000 2,100,000 * portfolio coefficient - peak hourly volume of 300,000 2,100,000 * portfolio coefficient - annual volume of 110M * portfolio coefficient | [12 empty] | Y | [8 empty] | Y
E2E1006 | All | Performance Efficiency | All services shall be designed to cope with an increase in message volumes of 25% over 5 years | [12 empty] | Y | [11 empty] | Y
E2E1007 | All | Performance Efficiency | During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore, assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M | [12 empty] | Y | [11 empty] | Y
E2E0208 | All | Performance Efficiency | DIP Participants shall be able to process messages at their own speed, independently to other consumers | [12 empty] | Y | [11 empty] | Y
E2E1008 | All | Performance Efficiency | Services sending messages via the 'Pattern B' model shall provide a publicly available (or using a Federated Identity Management (FIM) capability) URI location that other Services/ Market Participants can access and download content | [12 empty] | Y | [8 empty] | Y
E2E0101 | All | Performance Efficiency | All services shall have the capability to control the number of messages that are sent within a single API call | [12 empty] | Y | [11 empty] | Y
E2E1003 | All | Performance Efficiency | All Services shall provide an initial synchronous response (Level 3 validation) to a message within the following timeframes: - up to average hourly volume, mean response time of 2s or less - up to average hourly volume, 90th percentile response time of 4s or less - from average hourly to peak hourly volume, mean response time of 5s or less - from average hourly to peak hourly volume, 90th percentile response time of 8s or less | [12 empty] | Y | [8 empty] | Y
E2E1009 | All | Performance Efficiency | All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less | [12 empty] | Y | [8 empty] | Y
E2E0105 | All | Reliability | Each service after invoking a DIP API shall implement an exponential backoff and retry with jitter policy in the event of a comms failure with the DIP resulting from a http 429 response | [12 empty] | Y | [8 empty] | Y |  |  | Y
E2E0106 | All | Reliability | In the event of a failure to communicate with the DIP, the Service shall be able to buffer messages for a period of at least 72 hours | [12 empty] | Y | [8 empty] | Y
E2E0206 | All | Reliability | In the event of a failure to communicate with the DIP, Participant systems shall be able to buffer messages for a period of at least 72 hours | [12 empty] | Y | [8 empty] | Y |  |  | Y
E2E0402 | All | Reliability | When participant systems/services are unavailable from both unplanned and planned outages the outage shall be communicated to the DIP via e-mail or via the DIP portal **TBC once DIP governance procedures are available** | [24 empty] | Y
E2E1001 | All | Reliability | All services (those components that physically interface with the DIP, i.e. send and receive messages), unless explicitly defined, shall have an availability of 98% outside planned outage periods | [24 empty] | Y
E2E1009 | All | Reliability | All services (involved in BP affecting the Secured Active process), shall not plan outages within the Secured Active processing window | [12 empty] | Y | [8 empty] | Y
E2E0204 | All | Reliability | Participant systems shall check for duplicate messages with the same SUR under Level 3 or Level 4 validation | [12 empty] | Y | [8 empty] | Y
E2E0205 | All | Reliability | Participant systems shall check for duplicate messages with the same Transaction Id under Level 3 or Level 4 validation | [12 empty] | Y | [8 empty] | Y
E2E0210 | All | Reliability | In terms of handling messages all participant systems shall be idempotent and have mechanism for handling duplicate messages | [12 empty] | Y | [8 empty] | Y
E2E0401 | All | Reliability | Participants shall maintain all DIP facing systems so that all operating system, programming languages and their runtime libraries are at minimum supported versions from their respective vendors | [24 empty] | Y
E2E0404 | All | Reliability | Participants shall maintain all DIP facing systems so that all operating system, programming languages and their runtime libraries are at recommended supported versions from their respective vendors | [24 empty] | Y
E2E0011 | All | Reliability | There shall be no data loss in the event of a single component failing | [12 empty] | Y | [8 empty] | Y |  |  | Y
E2E0403 | All | Reliability | Participant systems shall maintain an archive of all transactional data for 24 months | [24 empty] | Y
E2E1002 | All | Reliability | In the event of an unplanned outage, each service shall be able to resume operation within 1 hour. | [12 empty] | Y | [8 empty] | Y |  |  | Y
E2E0012 | All | Security | DIP Participants shall ensure measures are put in place to ensure separation of production and non-production environments | [24 empty] | Y
E2E0103 | All | Security | All Services shall digitally sign messages | [12 empty] | Y | [8 empty] | Y
E2E0202 | All | Security | All services shall check that messages are digitally signed with the correct certificate from the Sender of the message | [12 empty] | Y | [8 empty] | Y |  |  | Y
E2E0102 | All | Security | All Services shall generate a Sender Unique Reference (SUR) for each message/event | [12 empty] | Y | [8 empty] | Y
E2E0104 | All | Security | All Services shall use DIP generated Transaction Ids returned in the response body of the API transaction to map against messages for audit and tracking purposes | [12 empty] | Y | [8 empty] | Y
E2E0107 | All | Security | When sending messages all services shall use the http response of the API transaction to establish whether a message has been received by the DIP | [12 empty] | Y | [8 empty] | Y
E2E0209 | All | Security | DIP Participants shall put in measures to differentiate the processing of replayed messages c.f. original messages | [12 empty] | Y | [8 empty] | Y
E2E0203 | All | Usability | When Level 3 validation fails, e.g. when payload contents cannot be reconciled (schema validation), a response with the corresponding error code shall be reported back to the DIP via the http response in the webhook call-back | [12 empty] | Y | [8 empty] | Y
E2E0013 | All Services | Maintainability | All newly developed components of services shall align to the current settlement period of 30 min. This may change in the future and therefore these components should be designed such that any change in this value can be accomodated without the need for fundamental system change, i.e. a reduction to 15 mins | [24 empty] | Y
E2E2002 | SDS | Performance Efficiency | SDS shall submit all half-hourly consumpition data (IF-021) so that the maximum number of submissions submitted in an hour is 1/6th of their portfolio size (a lower limit of portfolio size under which where this does not apply shall be maintained) | [12 empty] | Y | [8 empty] | Y
E2E2003 | SDS | Performance Efficiency | SDS shall submit all half-hourly consumpition data (IF-021) so that no more than ½ of their portfolio size can be submitted in a single 6 hour period (a lower limit of portfolio size under which where this does not apply shall be maintained) | [12 empty] | Y | [8 empty] | Y
E2E2004 | SDS | Performance Efficiency | An SDS that submits data with extreme peaks, i.e. where all data submitted is concentrated in short timespans, shall be subject to throttling by the DIP and shall need to buffer and resubmit data | [12 empty] | Y | [8 empty] | Y
MHHS Non Fucntional Requirements
Note on S9: If yes this should be captured in PIT test completion report and defects added to ADO
Note on AB9: If yes this should be captured in PIT test completion report and defects added to ADO

## 8 Operational Requirements
Code Bodies to complete. Columns are aligned to REC and BSC assesment critieria and sections maintained by Code Bodies will be updated if the assesement critieria documents are updated.
Programme Participant to complete
Requirement | [9 empty] | PIT | [9 empty] | QT | [7 empty] | QAD
[10 empty] | Prepopulated | Prepopulated |  | Submit inline with timeline in PIT Guidance |  |  | Submit with PIT TCR |  |  |  | Prepopulated | Prepopulated | Submit with QT Test Plan |  | Submit with QT TCR |  |  |  | Prepopulated | Prepopulated
Reference | Market Role | Requirement | Requirement Description | Code | Supporting information/ questions | Process | Step | Interface | Optionality | PIT Testing Required (Y/N) | Entry Criteria for QT (Y/N) If No, participants are expected to have completed by QT exit | QT Test Scenario/s to be executed | PIT Scenario ID - at least one but could be multiple | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | PIT Status (Passed, Failed, Not Run) | PIT Test Evidence Captured | Work Off Plan (Y/N) | Comments | SIT / QT Required (Y/N) | SIT/QT Scenario ID - at least one but could be multiple | Placing Reliance Applicable (Y/N) | Placing Reliance Info - this should inculde the organisation conducting the test. This will need to be reviewed by code bodies | QT Status (Passed, Failed, Not Run) | SIT / QT Test Evidence in ADO (Y/N) | Work Off Plan (Y/N) | Comments | QAD Question (Y/N) | QAD Question Number
MHHS Operational Requirements
Note on T9: If yes this should be captured in PIT test completion report and defects added to ADO
Note on AB9: If yes this should be captured in PIT test completion report and defects added to ADO