## Summary (hidden)
Theme | Scope Theme | Scenario Details | Equivalent SIT Scenario | Test Case Name | Test cases | Comments | Questions
1 | New Connection | End to end covering: New connection (LDSO only so could start later for non LDSO) Initial Registration (Supplier only so could start later for MOA / DS) Agent appointment (relevant for all roles) Energisation and Meter Install (relevant for all roles) | SITFTS 0050 | SITFTS0050- Advanced SITFTS0050- Traditional | Traditional needed for SDS and Smart MOA Smart to be created for SDS and Smart MOA Advanced needed for ADS and Advanced MOA Supplier could do both | Didn’t suggest Smart Test Case as this covers impact and export. | Are we ok with just a single end to end scenario for this theme? Yes Should supplier test against both? Both to be created Do we need import / export and related or can we just do these for the appointment and CoS scenarios? covered in other scenarios as the link is added after the connection
2 | Change of Registration Data | Change of Customer Appointment MS | SITFTS 0100 |  | Traditional / Smart needed for SDS and Smart MOA Advanced needed for ADS and Advanced MOA Supplier could do both |  | Should supplier test against both? We should create both and then ask if they have separate processes / systems for smart and advanced before determining whether to test both
2 | Change of Registration Data | Change of Customer Appointment DS | SITFTS 0180 |  | Smart needed for SDS and Smart MOA Advanced needed for ADS and Advanced MOA Supplier could do both
2 | Change of Registration Data | DCC Enrolment Update | SITFTS 1020 |  | TC01 - applicable to Supplier and SDS. Not applicable to MOA | There are two test cases and the difference is not clear
2 | Change of Registration Data | Domestic Premises Update | SITFTS 0940 |  | TC01 is Smart - applicable to SDS and Smart MOA TC02 is Advanced - applicable to ADS and Advanced MOA Supplier could do both
2 | Change of Registration Data | Legacy Info Update | SITFTS 1010 |  | TC01 Trad for smart agents and suppliers TC02 Smart for smart agents and suppliers | There are 4 different test cases covering Profile Class and SSC update individually and separately. Just doing the joint scenario
2 | Change of Registration Data | Consent Granularity Update | SITFTS 0930 |  | BSC to confirm which test case
2 | Change of Registration Data | IHD Update | SITFTS 0995 |  | TC01 - smart covers Smart MOA, SDS and Supplier TC02 rejection - Supplier only | No Advanced needed
2 | Change of Registration Data | GSP Group Update | SITFTS 0920 |  | BSC to confirm which test case. TC02 is Traditional, TC03 is Advanced
2 | Change of Registration Data | Address Update | SITFTS 0920 |  | TC01 - smart covers Smart MOA, SDS and Supplier TC01A create new advanced test case for Smart MOA, ADS and Supplier
2 | Change of Registration Data | SMSO Update | SITFTS 0990 |  | TCO1 - covers Smart MOA, SDS and Supplier. | No Advanced needed
2 | Change of Registration Data | SMSO Update | SITFTS 0990 |  | TCO2 - Supplier only covers rejection
2 | Change of Registration Data | Metered Indicator Update | SITFTS 0980 |  | TC01 Smart / TC02 Trad covers Smart MOA and SDS TC03 Advanced covers Advanced MOA and ADS Supplier could do both
2 | Change of Registration Data | Energy Direction Update | SITFTS 0970 |  | TC01 Smart import to export TC02 Advanced export to import Suppliers could do both
2 | Change of Registration Data | Related Metering Point Update | SITFTS 0960 |  | TC01 Smart Related Removal Smart MOA and SDS and Supplier TC01A create new Advanced Related Removal for Advanced MOA, ADS and Supplier TC02 Advanced Related Addition Advanced MOA and ADS and Supplier TC02A create new Smart Related Addition for Smart MOA, SDS and Supplier
2 | Change of Registration Data | Related Metering Point Update Rejection (supplier only) | SITFTS 0965 |  | Supplier only
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 |  | TC01 smart addition single supplier - Smart MOA, SDS and Supplier TC01A create new advanced addition for Advanced MOA, ADS, Supplier TC02 advanced removal single supplier Advanced MOA, ADS and Supplier TC02A create new Smart removal for Smart MOA, SDS and Supplier TC03 covers smart separate supplier linkage creation - should test export only TC03A create new test case for Advanced export only linkage creation
2 | Change of Registration Data | Import / Export Association Update Rejection (supplier only) | SITFTS 1005 |  | Supplier only
3 | Change of Supplier | Single MPAN end to end covering: Switch Request to CSS (Supplier only so could start later for MOA / DS) Agent Appointment (including MTD transfer) Transfer Read Settlement Calender | SITFTS 0035 |  | There is only a single test case covering Smart with estimated read TC02 create new advanced single MPAN test case | BSC question - do we need to check for smart with actual data as this scenario only covers estimated read There are scenarios with change of DS but no change of MS (SITFTS 0020) or scenarios with change of MS but no change of DS (SITFTS0030) - not required for QT
3 | Change of Supplier | Appointment rejection (Supplier only) |  |  |  | There is an appointment update rejection but no appointment rejection that I can see. To be created if no one can find one
3 | Change of Supplier | Appointment lapsed due to secured active not being received | SITFTS 0045 |  | Smart for SDS and Smart MOA Advanced for ADS and Advanced MOA Suppliers could do both
3 | Change of Supplier | Related CoS covering agent appointments | SITFTS 0040 |  | Traditional for SDS, Smart MOA and Supplier Create new test cases for smart and advanced
3 | Change of Supplier | Import / Export CoS covering agent appointments | SITFTS 0040 |  | Advanced for ADS, Advanced MOA and Supplier Create new test cases for smart and trad
3 | Change of Supplier | Import / Export CoS covering agent appointments with different supplier | SITFTS 0025 |  | TC02 smart linked export for Smart MOA, SDS and Supplier. TC02A create advanced linked export for Advanced MOA, ADS and Supplier
4 | Change of Data Service | Single MPAN end to end covering: Agent Appointment (including MTD transfer) Transfer Read - consumption transfer Can we also cover the COS MS DS Change - Settlement
4 | Change of Data Service | Appointment rejection (Supplier only)
4 | Change of Data Service | Related CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced related | No related for Advanced
4 | Change of Data Service | Import / Export CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced linked | No import export for Smart
5 | Change of Metering Service | Single MPAN single covering agent appointment | N/A |  | Use shared steps for smart, trad advanced linked
5 | Change of Metering Service | Appointment rejection (Supplier only) |  |  |  | There is an appointment update rejection but no appointment rejection that I can see
5 | Change of Metering Service | Related CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced related
5 | Change of Metering Service | Import / Export CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced linked
6 | Metering Changes | Meter Update - Install, Remove, Exchange | SITFTS 0900 |  | TC01 covers trad to smart exchange for Smart MOA, Smart DS and Supplier TC03 covers advanced to advanced exchange for Advanced MOA, Smart DS and Supplier | TC02 smart install and TC04 advanced removal not included | We cover install with new connection, remove with de-energisation and exchange with change of market segment. Suggest we just use an exchange scenario as a basic test
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 |  | There are 6 test cases - keep them all and decide which apply later: (1) traditional--> smart SMETS2 exchange (2) smart SMETS1 --> smart SMETS2 exchange (3) Smart SMETS2 installation (4) Advanced installation (5) traditional, removal (6) Advanced, removal
6 | Metering Changes | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | SITFTS 0840 |  | TC01 for smart MOA and Smart DS TC03 for Advanced MOA and Advanced DS Supplier could do both | I dont think we need TC02 which covers trad. TC04 covers unmetered I would like to have had this starting with a de-energisation and meter removal as the equivalent to new connection but this is only available for related (SITFTS 0850) of import / export (SITFTS 0855) to decide if we need this as well
6 | Metering Changes | Related Disconnection | SITFTS 0850 |  | Smart for Smart MOA, SDS and Supplier Advanced for Advanced MOA, ADS and Supplier Traditional for Smart MOA, SDS and Supplier
6 | Metering Changes | Linked Disconnection | SITFTS 0855 |  | Smart for Smart MOA, SDS and Supplier Advanced for Advanced MOA, ADS and Supplier Create new test case for Traditional for Smart MOA, SDS and Supplier
6 | Metering Changes | Change of Energisation Status | SITFTS 280 |  | TC01 Smart credit for Smart MOA, Smart DS and Supplier TC01A create smart Ldso energisation for Smart MOA, SDS and Supplier TC04 Advanced for Advanced MOA, Advanced DS TC04A create Advanced MOA energisation for Advanced MOA and Supplier | No De-energisation scenarios but this is covered for related and linked in SITFTS 0850 and 0855 and also rejections in SITFTS0360 I dont think we need : TC02 smart prepay - I think the proceses are the same with just a different event code TC03 Trad - process the same as smart Unmetered is covered in TC05 These scenarios differ as the TC01 has MOA energisation and TC04 has LDSO energisation. Additional test cases to be created | MAC - SITFTS-ST0015 - Can we also cover the settlement section of the requirements at the end?
6 | Metering Changes | Change of Energisation Status Rejection by Registration Service | SITFTS 0360 |  | TC01 Smart MOA de-energisation for Smart MOA, SDS and Supplier TC01A create smart Ldso de-energisation for Smart MOA, SDS and Supplier TC03 Advanced LDSO de-energisation for Advanced MOA and Supplier TC03A create Advanced MOA de-energisation for Advanced MOA and Supplier | TC02 not needed as just covering a different rejection reason. These scenarios differ as the TC01 have MOA de-energisation and TC03 has LDSO de-energisation. Additional test cases to be created
6 | Metering Changes | Change of Energisation Status Rejection by MOA | SITFTS 0360 |  | TC04 covers this for trad for smart MOA and Supplier TC04A create test case for advanced MOA and Supplier
6 | Metering Changes | Historic Meter Update | SITFTS 0890 |  | TC01 Amend Meter Id for smart MOA, Smart DS TC02 Amend meter Id rejected for smart MOA TC03 Meter Removal for Advanced MOA, Advanced DS TC04 Meter Removal rejected (trad) for smart MOA TC05 Meter Addition for smart MOA and Smart DS TC06 meter addition rejection for smart MOA Supplier could test all | We dont have meter rejection for Advanced but the scenarios is the same for trad and advanced so could just apply to advanced? | Do we need all these scenarios - maybe for MOA but not for DS and Supplier
6 | Metering Changes | MAP Id Update | SITFTS 0910 |  | TC01 Smart for Smart MOA and Supplier TC03 Advanced for Advanced MOA and Supplier | TC02 not needed as just covering a different rejection reason. These scenarios differ as the TC01 have MOA de-energisation and TC02 has LDSO de-energisation. | Do we need to test MOA de-energisation and LDSO de-energisation for both?
6 | Metering Changes | MAP Id Update Failure | SITFTS 0915 |  | Smart MOA and Supplier Create test case for Advance MOA and Supplier
6 | Metering Changes | Change of Market Segment | SITFTS 0860 |  | TC01 Advanced to Smart - Advanced and Smart MOA and Advance and Smart DS TC02 Smart to Advanced - Advanced and Smart MOA and Advanced and Smart DS Supplier could test both | I havent included TC03 which include import / export association or TC04 which is Trad to Advanced I havent seen a straightforward change of connection type to test the IF043 / 44 - will need to check this is covered.
6 | Metering Changes | Change of Market Segment with CoS | SITFTS 0862 |  | Single test case - smart to advanced for all agents |  | This is a very complicated scenario. Most of the complexity comes from the choreography and registraton service processing but it would be a good one to test in QT unless people feel like its an edge case
6 | Metering Changes | Receipt of invalid Market Segment |  |  |  |  | There is a full change of segment scenario covering this (SITFTS0880) but I dont think we need it all so need to understand if theis element is tested as a small send and receive scenario
7 | Consumption | Amend Override Readings | SITFTS 1070
7 | Consumption | Amendment Accepted | SITFTS 10110
7 | Consumption | Amendment Criteria No Met | SITFTS-1080
7 | Consumption | Amendment Rejected | SITFTS-1100 TC01
7 | Consumption | Amendment Invalid Data | SITFTS-1090 TC01
7 | Consumption | Amendment Trading Dispute | SITFTS-1095 TC01
7 | Consumption | COS Transfer Reads | SITFTS0012
7 | Consumption | Invalid | SITFTS-0270
7 | Consumption | LSS IF-021 | SITFTS0530
7 | Consumption | Smart | SITFTS-0260 TC03
7 | Consumption | Unmetered Invalid
7 | Consumption | DS Change of Transfer of Reads | SITFTS0132-
7 | Consumption | Estimated Tra Multi Rates
7 | Consumption | SDS Estimation
7 | Consumption | ADS Meter Adance Reconcillation
7 | Consumption | ADS Import Estimation | SITFTS-0305 TC07
7 | Consumption | ADS Export Estimation
7 | Consumption | ADS Opt-Out Estimation | SITFTS0315- 01 Method 0 O-R
7 | Consumption | UMSDS Estimation
7 | Consumption | Load Shapes in Estimation | Shared Steps
8 | Settlement | BSC

## Overview
Purpose | List of Test Scenarios and Cases for Non-SIT Supplier and Agent Qualification Testing.
Overview | Where systems, interfaces, and hosting to deliver the end-to-end business processes are identical to another Participant, Participants can place full reliance on their PIT and SIT/QT.​
Where systems, interfaces, and hosting are similar to another Participant, but not identical, a Participant may be able to place partial reliance on their SIT/QT; they would still be expected to conduct their own PIT on the areas impacted by the differences.
If a Participant intends to place partial reliance, the extent of PIT/SIT/QT they would need to complete depends on the nature of the similarities and differences between systems, interfaces, and hosting.
For example, if the majority of the systems, interfaces, and hosting were identical to the Participant they wished to place reliance on, but they have a bespoke in-house CRM, the expectation is that they will complete the relevant scope of PIT for business processes impacted by the CRM, and do a proportion of the QT reflected in the QT Test Catalogue.
This document provides a view of the expected test cases for those placing Partial Reliance where the functionality of the automated flow management system has already been tested, however the interfaces between the flow management system and the Participant's systems (e.g. CRM/Billing) have not been tested.​
Participants should always discuss their individual situations with Code Bodies and placing reliance scope isn't considered to be agreed until the Participant PIT/QT RTTM is approved by Code Bodies.
Assumptions | - For each role, Participants are expected to complete at least one relevant E2E test that covers all of the relevant interfaces e.g. between the bespoke part of their system and the systems they are placing reliance on and/or central services.
- When defining the expected test cases, the BSC and REC Code Bodies placed greater emphasis on the areas of high Settlement and Retail risk respectively. Where possible, we have selected E2E test cases which multiple key areas for both codes, supplemented with individual tests e.g. those that focus on the control or management of important exception processes.
- The test cases are focused on functional test cases as this is the area most impacted by the bespoke element between Participants and their Service Provider.
- For Suppliers, where there are similar test cases for the Smart and Advanced segments (e.g. QT-044 and QT-045), and the bespoke element of your systems use the same process for both cases, then you will only need to complete one of the test cases. If bespoke element and/or trigger to your Service Provider is different, you will need to complete both in QT.
- For Migration: We expect this to be mostly unaffected by the bespoke element of your systems, and CoS/CoA triggers are captured by the Functional QT Cases; if there is a further impact you will be required to complete a subset in QT e.g. 1 forward and reverse migration. You should also consider whether you need to complete any migrations to support your other QT testing.
- For Operational: Based on the current BSC and REC Assessment Criteria, we expect this to be mostly unaffected by the bespoke element of your systems, and if there is an impact it would be appropriate to test during PIT and Functional QT.

## QT Partial Reliance Scenarios
Scope Theme | Scenario Details | QT Test Case ID | QT Test Case Title | SMOA | AMOA | SDS | ADS | Supplier | UMSDS | Supplier Linked
Change of Registration Data | Change of Customer Appointment MS | QT-044 | Change of Customer Appointment - Metering Services Smart | Y |  |  |  | Y
Change of Registration Data | Change of Customer Appointment MS | QT-045 | Change of Customer Appointment - Metering Services Advanced |  | Y |  |  | Y
Change of Registration Data | Change of Customer Appointment DS | QT-051 | Change of Customer Appointment - Data Services Smart |  |  | Y |  | Y
Change of Registration Data | Change of Customer Appointment DS | QT-052 | Change of Customer Appointment - Data Services Advanced |  |  |  | Y | Y
Change of Registration Data | Consent Granularity Update | QT-133 | Consent Granularity - Smart Daily to HH Consent |  |  | Y |  | Y
Change of Registration Data | Consent Granularity Update | QT-134 | Consent Granularity - Advanced HH Consent to Monthly Reads Only |  |  |  | Y | Y
Change of Registration Data | Energy Direction Update | QT-142 | Update Energy Direction Advanced - Export > Import |  | Y |  | Y | Y
Change of Registration Data | Import / Export Association Update | QT-198 | Import/Export Linkage Addition - Advanced |  | Y |  | Y | Y
Change of Registration Data | Import / Export Association Update | QT-200 | Import/Export Linkage Addition different suppliers - Advanced |  | Y |  | Y | Y |  | Y
Change of Registration Data | Related Metering Point Update | QT-196 | Related Removal - Advanced |  | Y |  | Y | Y
Change of Registration Data | Related Metering Point Update | QT-197 | Related Addition - Smart | Y |  | Y |  | Y
Change of Supplier | Single MPAN end to end covering: Switch Request to CSS (Supplier only so could start later for MOA / DS), Agent Appointment (including MTD transfer), Transfer Read, Settlement Calender | QT-034 | Change of Supplier and DS, no change of MS - Smart | Y* |  | Y* |  | Y*
Change of Supplier | Single MPAN end to end covering: Switch Request to CSS (Supplier only so could start later for MOA / DS), Agent Appointment (including MTD transfer), Transfer Read, Settlement Calender | QT-177 | Change of Supplier and DS, no change of MS - Advanced |  | Y* |  | Y* | Y*
Metering Changes | Change of Energisation Status | QT-187 | Smart LDSO Energisation | Y |  | Y |  | Y
Metering Changes | Change of Energisation Status | QT-186 | Advanced Credit MS Energisation |  | Y |  | Y | Y
Metering Changes | Change of Market Segment | QT-104 | Advanced to Smart Market Segment Change | Y | Y | Y | Y | Y
Metering Changes | Change of Market Segment | QT-105 | Smart to Advanced Market Segment Change | Y | Y | Y | Y | Y
Metering Changes | Meter Update - Install, Remove, Exchange | QT-116 | Traditional to Smart Meter Exchange | Y |  | Y |  | Y
Metering Changes | Meter Update - Install, Remove, Exchange | QT-117 | Advanced to Advanced Meter Exchange |  | Y |  | Y | Y
Consumption | ADS Meter Adance Reconcillation | QT-073 | Modern Advanced Meter Periodic MAR Check fails |  |  |  | Y
Consumption | ADS Meter Adance Reconcillation | QT-074 | Advanced Meter with Check Meter Periodic MAR Check fails |  |  |  | Y
Consumption | ADS Export Estimation | QT-076 | Advanced Meter where Check Meter data is missing - Export |  |  |  | Y
Consumption | UMSDS Estimation | QT-080 | Unmetered MPAN with Inventory and Load (Dynamic) | [5 empty] | Y
Consumption | ADS Meter Advance Reconciliation | QT-243 | Modern Advanced Meter Periodic MAR Check fails - Export |  |  |  | Y
N/A | UMSDS default consumption data and annual consumption receipt | QT-277 | UMSDS default consumption data and annual consumption receipt | [5 empty] | Y
Consumption | UMSDS Consumption Data Calculation and Estimation | QT-259 | Inventory with Load (Dynamic) using PECU Array Data Unmetered MPAN with Inventory and Load (Dynamic) using PECU Array Data | [5 empty] | Y
Consumption | Amendment Invalid Data | QT-270 | Override Read Submission Advanced |  |  |  | Y | Y
Consumption | Amendment Trading Dispute | QT-272 | Advanced Pre-RF and Dispute Criteria met |  |  |  | Y | Y

## Change Log
Date | Author | Release | Reason for change
2025-02-04 | Code Bodies | v0.1 | Initial Version
2025-05-02 | Code Bodies | v0.2 | Updated to reflect changes in QT Scope
2025-05-12 | Non-SIT S&A QT Team / Code Bodies | V0.3 | Code Bodies Review and Rationalisation of Test Cases

## Batch 2 (hidden)
Theme | Scope Theme | Scenario Details | Equivalent SIT Scenario | Document Id | SIT Scenario Title | Test cases | SIT Test Case Title | SMOA | AMOA | SDS | ADS | Supplier | UMSDS
3 | Change of Supplier | Appointment rejection | [5 empty] | Y | Y | Y | Y | Y
4 | Change of Data Service | Appointment rejection | [7 empty] | Y | Y | Y
5 | Change of Metering Service | Appointment rejection | [5 empty] | Y | Y |  |  | Y
1 | New Connection | End to end covering: New connection (LDSO only so could start later for non LDSO) Initial Registration (Supplier only so could start later for MOA / DS) Agent appointment (relevant for all roles) Energisation and Meter Install (relevant for all roles) | SITFTS 0050 | MHHS-DEL1757 | SITFTS-0050 New Connection | Smart single MPAN to be created |  | Y |  | Y |  | Y
2 | Change of Registration Data | Address Update | SITFTS 0920 | MHHS-DEL1762 | REG UPD MPL Address GSP Group ID | TC01A create new advanced test case |  |  | Y |  | Y | Y
2 | Change of Registration Data | Related Metering Point Update | SITFTS 0960 | MHHS-DEL1766 | SITFTS-0960 REG UPD Related | TC01A create new Advanced Related Removal |  |  | Y |  | Y | Y
2 | Change of Registration Data | Related Metering Point Update | SITFTS 0960 | MHHS-DEL1766 | SITFTS-0960 REG UPD Related | TC02A create new Smart Related Addition |  | Y |  | Y |  | Y
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 | MHHS-DEL1772 | REG UPD Linked | TC01A create new advanced addition single supplier |  |  | Y |  | Y | Y
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 | MHHS-DEL1772 | REG UPD Linked | TC02A create new Smart removal single supplier |  | Y |  | Y |  | Y
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 | MHHS-DEL1772 | REG UPD Linked | TC03A create new test case for Advanced export only linkage creation |  |  | Y |  | Y | Y
3 | Change of Supplier | Single MPAN end to end covering: Switch Request to CSS (Supplier only so could start later for MOA / DS) Agent Appointment (including MTD transfer) Transfer Read Settlement Calender | SITFTS 0035 | MHHS-DEL1817 | COS DS Change Est Read | create new advanced single MPAN test case |  |  | Y |  | Y | Y
3 | Change of Supplier | Related CoS covering agent appointments | SITFTS 0040 | MHHS-DEL1818 | COS MS DS Change | Create new test case for smart |  | Y |  | Y |  | Y
3 | Change of Supplier | Related CoS covering agent appointments | SITFTS 0040 | MHHS-DEL1818 | COS MS DS Change | Create new test case for advanced |  |  | Y |  | Y | Y
3 | Change of Supplier | Import / Export CoS covering agent appointments | SITFTS 0040 | MHHS-DEL1818 | COS MS DS Change | Create new test case for smart |  | Y |  | Y |  | Y
3 | Change of Supplier | Import / Export CoS covering agent appointments | SITFTS 0040 | MHHS-DEL1818 | COS MS DS Change | Create new test case for traditional |  | Y |  | Y |  | Y
3 | Change of Supplier | Import / Export CoS covering agent appointments with different supplier | SITFTS 0025 | MHHS-DEL1815 | COS DS Change Linked Diff Suppliers | TC02A create advanced linked export |  |  | Y |  | Y | Y
6 | Metering Changes | Linked Disconnection | SITFTS 0855 | MHHS-DEL1892 | MET Disconnect Linked | Create new test case for Traditional |  | Y |  | Y |  | Y
6 | Metering Changes | Change of Energisation Status | SITFTS 280 | MHHS-DEL1887 | MET Energisation Change | TC01A create smart Ldso energisation |  | Y |  | Y |  | Y
6 | Metering Changes | Change of Energisation Status | SITFTS 280 | MHHS-DEL1887 | MET Energisation Change | TC04A create Advanced LDSO energisation |  |  | Y |  | Y | Y
6 | Metering Changes | Change of Energisation Status Rejection by Registration Service | SITFTS 0360 | MHHS-DEL1888 | MET Energisation Change Fails | TC01A create smart Ldso de-energisation |  | Y |  | Y |  | Y
6 | Metering Changes | Change of Energisation Status Rejection by Registration Service | SITFTS 0360 | MHHS-DEL1888 | MET Energisation Change Fails | TC03A create Advanced MOA de-energisation |  |  | Y |  | Y | Y
6 | Metering Changes | Change of Energisation Status Rejection by MOA | SITFTS 0360 | MHHS-DEL1888 | MET Energisation Change Fails | TC04A create test case for advanced |  |  | Y |  | Y | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | Create TC04A Meter Removal rejected for Advanced |  |  | Y
6 | Metering Changes | MAP Id Update Failure | SITFTS 0915 | MHHS-DEL1915 | MET Change of MAP update unsuccessful | Create test case for Advanced |  |  | Y |  | Y | Y
6 | Metering Changes | Receipt of invalid Market Segment |  | MHHS-DEL1919 | MET Connect Type Change with missing Services (MS) | Smart to Advanced Connection Type/Market Segment Change |  | Y | Y | Y | Y | Y |  | No Coverage in SIT scenario

## Sheet1 (hidden)
Equivalent SIT Scenario | Document Id | BSC Yes/No
SITFTS 0050 | MHHS-DEL1757 | N
SITFTS 0050 | MHHS-DEL1757 | N
SITFTS 0050 | MHHS-DEL1757 | N
SITFTS 0920 | MHHS-DEL1762 | N
SITFTS 0920 | MHHS-DEL1762 | N
SITFTS 0920 | MHHS-DEL1762 | N
SITFTS 0920 | MHHS-DEL1762 | N
SITFTS 0930 | MHHS-DEL1763 | Y
SITFTS 0930 | MHHS-DEL1763 | Y
SITFTS 0940 | MHHS-DEL1764 | N
SITFTS 0940 | MHHS-DEL1764 | N
SITFTS 0960 | MHHS-DEL1766 | Y
SITFTS 0960 | MHHS-DEL1766 | Y
SITFTS 0960 | MHHS-DEL1766 | Y
SITFTS 0960 | MHHS-DEL1766 | Y
SITFTS 0970 | MHHS-DEL1768 | N
SITFTS 0970 | MHHS-DEL1768 | N
SITFTS 0980 | MHHS-DEL1769 | N
SITFTS 0980 | MHHS-DEL1769 | N
SITFTS 0995 | MHHS-DEL1771 | N
SITFTS 0995 | MHHS-DEL1771 | N
SITFTS 1000 | MHHS-DEL1772 | N
SITFTS 1000 | MHHS-DEL1772 | N
SITFTS 1000 | MHHS-DEL1772 | N
SITFTS 1000 | MHHS-DEL1772 | N
SITFTS 1000 | MHHS-DEL1772 | N
SITFTS 1000 | MHHS-DEL1772 | N
SITFTS 1005 | MHHS-DEL1773 | N
SITFTS 1010 | MHHS-DEL1774 | Y
SITFTS 1010 | MHHS-DEL1774 | Y
SITFTS 1020 | MHHS-DEL1775 | N
SITFTS 0180 | MHHS-DEL1805 | Y
SITFTS 0180 | MHHS-DEL1805 | Y
SITFTS 0100 | MHHS-DEL1806 | N
SITFTS 0100 | MHHS-DEL1806 | N
SITFTS 0025 | MHHS-DEL1815 | N
SITFTS 0025 | MHHS-DEL1815 | N
SITFTS 0035 | MHHS-DEL1817 | Y
SITFTS 0035 | MHHS-DEL1817 | Y
SITFTS 0040 | MHHS-DEL1818 | Y
SITFTS 0040 | MHHS-DEL1818 | Y
SITFTS 0040 | MHHS-DEL1818 | Y
SITFTS 0040 | MHHS-DEL1818 | Y
SITFTS 0040 | MHHS-DEL1818 | Y
SITFTS 0040 | MHHS-DEL1818 | Y
SITFTS 0045 | MHHS-DEL1819 | Y
SITFTS 0045 | MHHS-DEL1819 | Y
N/A | MHHS-DEL1822 | N
N/A | MHHS-DEL1824 | Y
N/A | MHHS-DEL1825 | N
N/A | MHHS-DEL1826 | N
N/A | MHHS-DEL1827 | Y
N/A | MHHS-DEL1828 | N
N/A | MHHS-DEL1829 | N
N/A | MHHS-DEL1830 | Y
N/A | MHHS-DEL1831 | Y
SITFTS 280 | MHHS-DEL1887 | Y
SITFTS 280 | MHHS-DEL1887 | Y
SITFTS 280 | MHHS-DEL1887 | Y
SITFTS 280 | MHHS-DEL1887 | Y
SITFTS 0360 | MHHS-DEL1888
SITFTS 0360 | MHHS-DEL1888
SITFTS 0360 | MHHS-DEL1888
SITFTS 0360 | MHHS-DEL1888
SITFTS 0360 | MHHS-DEL1888
SITFTS 0360 | MHHS-DEL1888
SITFTS 0840 | MHHS-DEL1889
SITFTS 0840 | MHHS-DEL1889
SITFTS 0850 | MHHS-DEL1891
SITFTS 0850 | MHHS-DEL1891
SITFTS 0850 | MHHS-DEL1891
SITFTS 0855 | MHHS-DEL1892
SITFTS 0855 | MHHS-DEL1892
SITFTS 0855 | MHHS-DEL1892
SITFTS 0890 | MHHS-DEL1893
SITFTS 0890 | MHHS-DEL1893
SITFTS 0890 | MHHS-DEL1893
SITFTS 0890 | MHHS-DEL1893
SITFTS 0890 | MHHS-DEL1893
SITFTS 0890 | MHHS-DEL1893
SITFTS 0890 | MHHS-DEL1893
SITFTS 0900 | MHHS-DEL1894
SITFTS 0900 | MHHS-DEL1894
SITFTS 0905 | MHHS-DEL1913
SITFTS 0905 | MHHS-DEL1913
SITFTS 0905 | MHHS-DEL1913
SITFTS 0905 | MHHS-DEL1913
SITFTS 0905 | MHHS-DEL1913
SITFTS 0905 | MHHS-DEL1913
SITFTS 0910 | MHHS-DEL1914
SITFTS 0910 | MHHS-DEL1914
SITFTS 0915 | MHHS-DEL1915
SITFTS 0915 | MHHS-DEL1915
SITFTS 0860 | MHHS-DEL1916
SITFTS 0860 | MHHS-DEL1916
SITFTS 0862 | MHHS-DEL1917
MHHS-DEL1919
MHHS-DEL1919
SITFTS-0012 | MHHS-DEL1937
SITFTS-0012 | MHHS-DEL1937
SITFTS-0012 | MHHS-DEL1937
SITFTS-0012 | MHHS-DEL1937
SITFTS-0132 | MHHS-DEL1938
SITFTS-0132 | MHHS-DEL1938
SITFTS-0132 | MHHS-DEL1938
SITFTS-0132 | MHHS-DEL1938
SITFTS-0260 | MHHS-DEL1939
SITFTS-0260 | MHHS-DEL1939
SITFTS-0260 | MHHS-DEL1939
SITFTS-0270 | MHHS-DEL1940
SITFTS-0270 | MHHS-DEL1940
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0330 | MHHS-DEL1941
SITFTS-0530 | MHHS-DEL1942
SITFTS-0530 | MHHS-DEL1942
SITFTS-1095 | MHHS-DEL1943
SITFTS-1095 | MHHS-DEL1943
SITFTS-0290 | MHHS-DEL1970
SITFTS-0295 | MHHS-DEL1971
SITFTS-0300 | MHHS-DEL1972
SITFTS-0300 | MHHS-DEL1972
SITFTS-0305 | MHHS-DEL1973
SITFTS-0310 | MHHS-DEL1974
SITFTS-0315 | MHHS-DEL1975
SITFTS-0320 | MHHS-DEL1976
SITFTS-1070 | MHHS-DEL1977
SITFTS-1070 | MHHS-DEL1977
SITFTS-1080 | MHHS-DEL1978
SITFTS-1090 | MHHS-DEL1979
SITFTS-1090 | MHHS-DEL1979
SITFTS-1100 | MHHS-DEL1980
SITFTS-1100 | MHHS-DEL1980
SITFTS-1110 | MHHS-DEL1981
SITFTS-1110 | MHHS-DEL1981
Shared Steps | MHHS-DEL1982
Shared Steps | MHHS-DEL1983
Shared Steps | MHHS-DEL1983
Shared Steps | MHHS-DEL1983
Shared Steps | MHHS-DEL1984
Shared Steps | MHHS-DEL1985
N/A | MHHS-DEL2017
N/A | MHHS-DEL2022