## Comments
MHHS-DEL3669 - Initial QAD Submissions Participant Feedback Comments Log
*Organisation: | Consolidated
*Constituency: | SIT & LDSO
*Date: | 2025-04-23
Comment ID | *Comment | Theme | Decision | Response
To be populated by the Code Bodies | Succinctly state the comment and the basis for the concern | To be populated by the Document Owner | Accept, Reject | To be populated by the Document Owner
LDSO - 1 | Portal –Improvement where we had one MPID and the content was the same functionality to copy the content onto the additional MPID would result in one review and less effort all round | Portal functionality | Accept | Thank you for this feedback, for the Final QAD Submissions: Only where submissions are identical across their MPIDs, Participants will be able to submit a QAD for one MPID, complete draft and review, once finalised submit the remaining MPID's QAD​. ​
LDSO - 2 | Portal – Access ensure that the right participants on the contact list for access | Contacts | Accept | Thank you for this feedback, we have factored this into the process for Code Bodies to confirm a Participant's latest view of their QAD Contacts prior to QAD Portal access being granted.
LDSO - 3 | Portal – Opportunity to provide facility in portal to download the full QAD as it stand you can only download sections | Portal functionality | Accept | For Download functionality, there is currently functionality available from “view and download application” button on the QAD Applications dashboard. Use “Print and submit button”. We are progressing functionality to hide download buttons where role does not have access to download the content .i.e. Section Submission pages/Section Review pages to avoid confusion.
LDSO - 4 | Portal – Would be good to understand the improvements based on feedback for the Final QAD | Guidance | Accept | Code Bodies will provide communications on any improvements via the relevant Committees and update guidance documents accordingly.
LDSO - 5 | QAD Feedback – provided the exact same information in both MPIDS however the feedback differed per MPID leading to additional effort all round in reviewing and responding | Review Quality | Accept | Thank you for this feedback, for the Final QAD Submissions: Only where submissions are identical across their MPIDs, Participants will be able to submit a QAD for one MPID, complete draft and review, once finalised submit the remaining MPID's QAD​. ​
LDSO - 6 | QAD Guidance – Webinars were really useful, and provided guidance, opportunity to ask questions this was further enhanced when Code Bodies provided more specific detail on the key question requirements, after feedback | Guidance | Accept | Thank you for this feedback, we will continue to update the guidance provided.
LDSO - 7 | QAD Feedback – a lot of the MPRS detail was already known via SIT duplication of effort in particular for those placing reliance | MPRS | Accept | A dedicated session regarding MPRS with LDSO group was held on 14 April to provide further clarity to provide guidance on the MPRS QAD section. Further guidance will be published as a follow up from this session as a reference.
LDSO - 8 | Portal - The usual Word font options are not available, e.g. Bold, underline, italics, bullet points, therefore any formatting used to add clarity in responses drafted outside of the Portal is immediately lost when copied over. | Portal functionality | Accept | Thank you for your feedback, we are currently progressing Portal enhancements to address this functionality.
LDSO - 9 | Portal - The Portal offers little functionality to set out lengthy responses in a clear manner (for the above reasons). | Portal functionality | Accept | Thank you for your feedback, we are currently progressing Portal enhancements to address this functionality.
LDSO - 10 | Portal - Whilst all download icons on the various screens can be used, some only provide a blank template. It is confusing trying to remember which screen/view provides a fully populated extract. | Portal functionality | Accept | For Download functionality, there is currently functionality Available from “view and download application” button on QAD Applications dashboard. Use “Print and submit button”. We are progressing functionality to hide download buttons where role does not have access to download the content .i.e. Section Submission pages/Section Review pages to avoid confusion.
LDSO - 11 | Process Issues - Email notifications from the onset have not equated to the queries seen within the system. | Portal notifications | Accept | Thank you for your feedback, we are currently progressing Portal enhancements to address this functionality.
LDSO - 12 | Process Issues - No notifications have been received to confirm a section is “Complete” | Portal notifications | Accept | Thank you for your feedback, we are currently progressing Portal enhancements to address this functionality.
LDSO - 13 | Process Issues - Notifications received do not reference the section for which action is required therefore once a participant has a few “sections requiring attention” it isn’t easy to identify the new query. | Portal notifications | Accept | Thank you for your feedback, we have added this to the backlog for future QAD Portal enhancements.
LDSO - 14 | Process Issues - Further questions have been raised on sections which had already been rejected and revised responses uploaded, however notifications were not received regarding the additional questions. | Portal notifications | Accept | Thank you for your feedback, we are currently progressing Portal enhancements to address this functionality.
LDSO - 15 | Process Issues - There are other instances where new queries appear in sections with a date query raised of many weeks earlier – as if they are being drip fed in. | Process | Accept | Thank you for your feedback. Code Bodies workflow are reviewed independently and then once the second Code Body has responded this is fed through to the customer. We appreciate this may be frustrating but it is essential that both Code Bodies are reviewing a 'stable' response.
LDSO - 16 | Process Issues - There have been instances where the image indicating a query is not present, e.g. in SDS there were 3 sections with the comments speech bubble that total 3 questions. There was in fact a total of 15 questions from across 7/8 sections but it only became clear if you opened every section or when you download the extracts and go through them. | Portal functionality | Accept | Thank you for your feedback, we have added this to the backlog for future QAD Portal enhancements.
LDSO - 17 | Process Issues - Some queries are marked as to be responded to in the Final QAD however we have experienced an issue where this was not made clear by the reviewer – this needs to be clearly stated on any such review comment. | Review Quality | Accept | Thank you for your feedback, this is to be added to our internal Code Bodies Review framework.
LDSO - 18 | Process Issues - It is not clear which contact address should be used for QAD queries. I had assumed MHHS Qualification, however have since also been advised that I should be contacting REC direct on any queries for them (and have been advised of various routes into REC). There needs to be a single and agreed contact point. | Support | Accept | Code Bodies to publish escalation route for both Codes and DIP Manager for both technical and process in QAG pack and added to guidance doc.
LDSO - 19 | Process Issues - Establishing an escalation contact point was much more difficult and slower than it should have been – this needs to be immediately available upon request from the MHHS Qualification contact point. | Support | Accept | Code Bodies to publish escalation route for both Codes and DIP Manager for both technical and process in QAG pack and added to guidance doc.
LDSO - 20 | Process Issues - Multiple date commitments were given for review completion and not kept, with no communication as to why. | Response Time | Accept | We welcome this feedback and are taking a number of measures to improve the timeliness of the review by the REC Code Manager. This includes, 1) improvements in QAD Portal reporting to ensure that any outstanding Code Body reviews of Party responses can be identified, this will be particularly beneficial in addressing cases where QAD sections may be submitted in iterations, 2) review of REC Code Manager resourcing to incorporate surge capacity as we now have a better understanding of the QAD review process requirements, 3) introduction of an improved query management process via REC Service Desk to ensure that these are tracked and can be responded to within a 3WD SLA (for avoidance of doubt, this SLA is for responding to Party queries and should not be taken as the turnaround time for a QAD review).
LDSO - 21 | Review - The process is very confusing with the additional information requests being drip-fed by different reviewers. | Process | Accept | Thank you for your feedback. Code Bodies workflow are reviewed independently and then once the second Code Body has responded this is fed through to the customer. We appreciate this may be frustrating but it is essential that both Code Bodies are reviewing a 'stable' response.
LDSO - 22 | Portal - Access isn’t always possible, and it sometimes appears that sections are blocked from view or input. My access has been ‘blocked’ for more than a week whilst some of the additional comments are being reviewed. I am aware that I have additional information to provide but am unable to upload it to the relevant sections. | Portal functionality | Accept | Thank you for your feedback. Code Bodies workflow are reviewed independently and then once the second Code Body has responded this is fed through to the customer. We appreciate this may be frustrating but it is essential that both Code Bodies are reviewing a 'stable' response.
LDSO - 23 | Portal - It would be useful if there was the ability to download all of the QAD sections, including responses so far and Code Body text. We could be working on this whilst the sections are being reviewed to avoid these delays. | Portal functionality | Accept | For Download functionality, there is currently functionality Available from “view and download application” button on QAD Applications dashboard Use “Print and submit button”. We are progressing functionality to hide download buttons where role does not have access to download the content .i.e. Section Submission pages/Section Review pages to avoid confusion.
LDSO - 24 | Portal - The last time I was able to access some of the sections it appeared that some information I had previously provided was no longer there. I had been meticulous about saving my responses and so I don’t believe that it was due to that. Unfortunately, I have not been able to get back in to be able to double check whether the view was glitched in some way. | Portal functionality | Accept | Thank you for your feedback, we are currently progressing Portal enhancements to address this functionality.
LDSO - 25 | Review - Despite there being the option within some of the questions to annotate ‘N/A’, additional requests appear not to support that. One item of additional request asked me to double check my responses and then only annotate N/A if I was certain that was still the case. | Review Quality | Accept | Thank you for your feedback, this is to be added to our internal Code Bodies Review framework.
LDSO - 26 | Review - It was my understanding that, where we have submitted PIT/SIT evidence under the activity of SIT participant, we would not be requested to submit it again. I have been requested to provide PIT evidence, within one of the questions. | Review Quality | Accept | Thank you for your feedback, this is to be added to our internal Code Bodies Review framework.
LDSO - 27 | Review - Some of the additional request for feedback has not been for my role. For example, document the process by which you will allocate your MPANs for migration. As an LDSO I will not be choosing the MPANs. This is a supplier activity. | Review Quality | Accept | Thank you for your feedback, this is to be added to our internal Code Bodies Review framework.
LDSO - 28 | Review - . The Code Bodies have rejected the MPRS responses for 5 (I believe) of the iDNOs. C&C can't provide responses to it as it's MPRS Functionality and St Clements are saying that they don't have time to provide any responses and that it's all been tested during SIT so they shouldn't need to. C&C are not sure where we go with this now. | MPRS | Accept | A dedicated session regarding MPRS with LDSO group was held on 14 April to provide further clarity and provide guidance on the MPRS QAD section. Further guidance will be published as a follow up from this session as a reference.
LDSO - 29 | Portal - There is no way of interacting directly with the question: either asking for clarity on the question, or pointing it a sentence in our answer which we think already addresses the comments. We also can't tell it for instance: we will address this in our Final submission. The only option we have is to edit our answer … | Portal | Accept | Thank you for your feedback, for us to provide direct feedback on this please contact Code Bodies if question is unclear.
LDSO - 30 | Review - A few comments I would argue are actually addressed later on in our answer: is the review too “rigid”? | Review Quality | Accept | Thank you for your feedback, for us to provide direct feedback on this please contact Code Bodies if question is unclear.
LDSO - 31 | Section 5.3 Supplier Meter Registration Service. I understand that as the Programme Participant we have the responsibility to answer these questions, but as you know MPRS, used by every single LDSO, is almost completely automated, and has been developed following all the business rules and requirements and tested rigorously by St Clements and SIT participants. Following initial feedback for Participant I am trying to expand on my answers using the business process and requirements documentation but it still feels like duplication, as the Programme will already have this detailed information through other channels. | Process | Accept | A dedicated session regarding MPRS with LDSO group was held on 14 April to provide further clarity and provide guidance on the MPRS QAD section. Further guidance will be published as a follow up from this session as a reference.
LDSO - 32 | Process - Product specific questions which would be relevant for all DNOs – repetition and functionality already proven in SIT for placing reliance. | Process | Accept | A dedicated session regarding MPRS with LDSO group was held on 14 April to provide further clarity and provide guidance on the MPRS QAD section. Further guidance will be published as a follow up from this session as a reference.
LDSO - 33 | DTN process and BAU activity queried – no changes to processes but questions and comments raised, i.e. Disconnections and MPAN creation. | Review Quality | Accept | Thank you for your feedback, to be added to Code Bodies Review framework.
LDSO - 34 | Communication methods queried but no change of DNO to Supplier, via email or ECOES SDEP. | Review Quality | Accept | Thank you for your feedback, to be added to Code Bodies Review framework.
LDSO - 35 | Only able to respond per section, rather than per question (i.e. all questions in 4.2). | Portal functionality | Reject | Thank you for your feedback, we are not currently looking to add this process to workflow to allow sections and applications to be reviewed as a whole.
LDSO - 36 | Only able to respond to review comments per section, rather than per question. This delays our response until a question set section is ready to reply to all comments. | Portal functionality | Reject | Thank you for your feedback, we are not currently looking to add this process to workflow to allow sections and applications to be reviewed as a whole.
LDSO - 37 | Unable to download the whole QAD in a single simple step- need to select sections, add to download by section and then extract the downloads. Would be good to have a clearer user process to download the full question set, responses and comments as a single document for review. | Portal functionality | Accept | For Download functionality, there is currently functionality Available from “view and download application” button on QAD Applications dashboard. Use “Print and submit button”. We are progressing functionality to hide download buttons where role does not have access to download the content .i.e. Section Submission pages/Section Review pages to avoid confusion.
LDSO - 38 | Repetition for same roles (MPID and MPID) in separate QAD documents, meaning two identical documents completed. | Process | Accept | Thank you for this feedback, for the Final QAD Submissions: Only where submissions are identical across their MPIDs, Participants will be able to submit a QAD for one MPID, complete draft and review, once finalised submit the remaining MPID's QAD​. ​
SIT - 1 | Concerns around the timeliness of the REC Review | Response Time | Accept | We welcome this feedback and are taking a number of measures to improve the timeliness of the review by the REC Code Manager. This includes, 1) improvements in QAD Portal reporting to ensure that any outstanding Code Body reviews of Party responses can be identified, this will be particularly beneficial in addressing cases where QAD sections may be submitted in iterations, 2) review of REC Code Manager resourcing to incorporate surge capacity as we now have a better understanding of the QAD review process requirements, 3) introduction of an improved query management process via REC Service Desk to ensure that these are tracked and can be responded to within a 3WD SLA (for avoidance of doubt, this SLA is for responding to Party queries and should not be taken as the turnaround time for a QAD review).
SIT - 2 | Scrolling in section windows to be improved | Portal functionality | Accept | Thank you for your feedback, we have added this to the backlog for future QAD Portal enhancements.
SIT - 3 | Concerns around receiving feedback after the 6 week deadline for responses | Response Time | Accept | We welcome this feedback and are taking a number of measures to improve the timeliness of the review by the REC Code Manager. This includes, 1) improvements in QAD Portal reporting to ensure that any outstanding Code Body reviews of Party responses can be identified, this will be particularly beneficial in addressing cases where QAD sections may be submitted in iterations, 2) review of REC Code Manager resourcing to incorporate surge capacity as we now have a better understanding of the QAD review process requirements, 3) introduction of an improved query management process via REC Service Desk to ensure that these are tracked and can be responded to within a 3WD SLA (for avoidance of doubt, this SLA is for responding to Party queries and should not be taken as the turnaround time for a QAD review).
SIT - 4 | Additional Guidance (Webinar) on evidence to be provided to support QAD sections, submission of sections, notifications of feedback provided, responding to feedback, timelines for responding to feedback, | Guidance | Accept | Thank you for your feedback we will continue to update the guidance published and summarise any changes or highlights at the Qualification Working Group (QWG) and Qualification Advisory Group (QAG).
SIT - 5 | Scrolling in section windows to be improved | Portal functionality | Accept | Thank you for your feedback, we have added this to the backlog for future QAD Portal enhancements.
SIT - 6 | Improvement in clarity of which Code Body has responded and if accepted | Process | Accept | Thank you for your feedback, we will update the guidance material published to include where to find this information on the QAD Portal platform.

## Control (hidden)
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted