## 1 Cover Page
<organisation> SIT/ Qualification Testing Work Off Plan
Document owner | Document number | Version
<name or role> |  | <version number>
Status: | Date | Classification
<status> | <date> | Internal

## 2 Change Control
Programme Participant Name
Programme participants to fill in the table below and include their relevant constituency group and third-party provider if applicable.
Programme Participant Name | Constituency Group | MPID(s) Tested | Third Party Provider
e.g. Generic Electricity Co. Ltd | I&C Supplier | MPID(s) | N/A
Change Record
The table below needs to be updated with details of each amendment and change control.
Date | Author | Version | Change Detail
Document Approval
The table below needs to be updated and the role needs to be defined per person
Reviewer/Approver | Role
References
Reference any documents into the table below along with reference and version number. Programme participants should insert documents wherever possible. Programme participants should insert documents wherever possible.
Reference | Documents | Publisher | Version | Additional Information
REF 001 | PIT Test Approach and Plan
REF 002 | PIT Test Scenarios
Terminology
Reference any terminology used in this document.
Term | Description

## 3 Template Version Control
Template Change Control
Date | Author | Version | Change Detail
2024-08-16 | Code Bodies | V0.1 | Initial Draft
20/09/2024 | Code Bodies | V0.2 | Updates following internal review
2025-04-04 | Code Bodies | V0.3 | Updates following internal review
2025-04-07 | Code Bodies | V0.4 | Updates following internal review
2025-05-06 | Code Bodies | V1.0 | Baselined verision - publish as part of QWG34 papers

## 4 Guidance
Purpose of the document |  | The purpose document is to capture any work off items and provide sufficient information to Code Bodies and DIP Manager so they are able to assess the impact of proposed items. Work off items should be in line with the QT exit criteria set out in the Qualification Approach and Plan plus associated Annexes. Programme Participants should include work off items where they have placed reliance if there are items that have not been fixed.
When does this document need to be submitted |  | This document should be submitted alongside a programme participant's test completion report. Please note, providing early sight of work off items is highly encouraged.
Sheet number | Sheet name | Purpose |  | Participant to update
1 | Cover Page | To capture the current document status and version number. |  | Yes
2 | Change Control | To capture changes to document made by programme participant. |  | Yes
3 | Template Change Control | To capture changes made to the base template. |  | No
4 | Guidance | This tab is to provide guidance on how programme participant should complete and submit this template. |  | No
5 | Work Off Items | To capture a programme participant's proposed work off plan. |  | Yes
Column | Column Name within Work Off Tab |  | Description of what is expected to be completed for each column | Participant to complete
A | REF |  | Reference number for each work off item listed | Yes
B | Defect Number |  | ADO defect number | Yes
C | Severity |  | Severity of the defect. Please note, only sev 3 and 4 should be listed as a participant can not meet the QT exit criteria with open Sev 1 and/or 2 defect | Yes
D | Defect Status |  | The current defect status e.g. open, ready for retest, closed etc. | Yes
E | Defect Title |  | Title of defect in ADO | Yes
F | Description of defect |  | Description of defect | Yes
G | Role |  | MHHS Role this defect impacts | Yes
H | Placing Reliance Implications |  | This should describe any placing reliance implications e.g. defect is in system/software that a participant has placed reliance on | Yes
I | Test Step Defect Relates to |  | What test step (e.g. SITFTS-0300 TC02) does the defect relate to? | Yes
J | Business Requirement Reference for Defect Non-Compliance |  | What Business Requirement (e.g. MHHS-BR-SU-094) does the defect relate to? | Yes
K | Impact of defect on live operations |  | This should describe the impact of defect on live operations for MSIDs that have been migrated. Include the frequency and likelihood this will be see. Please note: this should refer to current operating size and plans for size over the fix period especially if new entrant. This should also refer to impact of placing reliance. | Yes
L | Impact of defect on migration |  | This should describe the impact of defect, if any, on migration including the frequency and likelihood this will be see. Please note: this should refer to current operating size and plans for size over the fix period especially if new entrant. This should also refer to impact of placing reliance. In particular, this should describe any relevant impact on the processes that deal with the initial MHHS Service Appointments | Yes
M | If Supplier, Impact of defect on Suppliers' migration schedules |  | This should describe the impact of defect, if any, on supplier's migration plan e.g. defect will not be seen during migration and is impacted to only occur on ad hoc basis as such migration plan is not impacted. In particular, this should describe any relevant impact on the processes that deal with the initial MHHS Service Appointments. | Yes
N | Code Body Impacted |  | Does the defect impact the BSC, REC, DIP, or a combination. | Yes
O | Settlement and/or Retail Risk defect maps to |  | Details of the settlement and/or retail risk the defect maps to. BSC/REC Assessment criteria map requirements to a settlement or retail risk. | Yes
P | Workaround description |  | Provide a clear and concise description of the operational processes involved in your workaround. Please include: - What discrete tasks must be performed to work the workaround? (e.g. manually creating and pushing flows to the DIP) - What data will you require to action the workaround? How will you identify affected systems/MSIDs? - Who will be performing these tasks? - How much work have you forecasted this workaround to be? | Yes
Q | Does workaround fully mitigate defect? If not, how will residual risk be mitigated and managed prior to fix being deployed |  | Confirmation if the expected workaround fully mitigates the defect. If not, please explain how residual risk will be mitigated and managed by your organisation. Please note: this should refer to current operating size and plans for size over the fix period especially if new entrant. | Yes
R | How will you know that the workaround is working? What reporting will you have in place to demonstrate this? |  | What reporting will you have in place to monitor that your workaround is working? For example, data monitoring the acceptance or rejection of flows. | Yes
S | Description of proposed fix |  | Description of the proposed fix of the defect. The defect fix is the enduring solution to the defect (e.g. a code fix), as opposed to the workaround that is temporary during the development of the fix. | Yes
T | Does fix fully mitigate defect? If not, how will residual risk be mitigated and managed |  | Confirmation if the expected fix fully fixes the defect. If not, please explain how residual risk will be mitigated and managed by your organisation. | Yes
U | Expected Fix Date |  | Date by which defect is expected to be fixed | Yes
W | Is fix date prior to migration start? If not, please indicate the impact of this on mitigation schedules and how this will be managed |  | Confirmation if the expected fix date is before or after the expected start of migration. If the fix date is post the start of migration, please explain the impact, if any, on migration and how this will be mitigated. | Yes
X | Confidence level on meeting fix date |  | Participant's confidence that the are on track to meet their proposed fix date | Yes
Y | Proposed retest model |  | How this defect fix is expected to be retested to confirm the fix resolves the defect e.g. PIT | Yes
Z | BSC Comments |  | To capture any feedback comments from BSC on work off item | No - BSCCo to complete
AA | REC Comments |  | To capture any feedback comments from REC on work off item | No - RECCo to complete
AB | DIP Manager Comments |  | To capture any feedback comments from DIP Manager on work off item | No - DIP Manager to complete
Guidance

## 5 Work Off Items
REF | Defect Number | Severity | Defect Status | Defect Title | Description of defect | Role | Placing Reliance Implications | Test Step Defect Relates to | Business Requirement Reference for Defect Non-Compliance | Impact of defect on live operations Please note: this should refer to current operating size and plans for size over the fix period especially if new entrant. This should also refer to impact of placing reliance. | Impact of defect on migration This should also refer to impact of placing reliance. | If Supplier, Impact of defect on Suppliers' migration schedules | Code Body Impacted | Settlement and/or Retail Risk defect maps to | Work around description | Does workaround fully mitigate defect? If not, how will residual risk be mitigated and managed prior to fix being deployed | How will you know that the workaround is working? What reporting will you have in place to demonstrate this? | Description of proposed fix | Does fix fully mitigate defect? If not, how will residual risk be mitigated and managed | Expected Fix Date | Expected Resolution Date | Is fix date prior to migration start. If not, please indicate the impact of this on mitigation schedules and how this will be managed | Confidence level on meeting fix date | Proposed retest model | BSC Comments | REC Comments | DIP Manager Comments
SIT/Qualification Testing Work Off Plan