## Sheet1
Test Case Title | Key Journey | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence
| Events | [10 empty] | Required
Settle Advanced DS | Load Shaping | 1 | BP005 | 230 | MHHS-BR-RD-019 | DIP | IF-021 | [ActivePower] & [DI-015] <> W | LSS | LSS receives the PUB-021 | LSS receives PUB-021 [ActivePower] & [DI-015] = W containing UTC Settlement Period Consumption Data. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 2 | BP018 | 15 | MHHSP-04 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LSS | Receive HH Data | Central Systems will need to subscribe to the DIP HH Data Publication. Data will be received as a constant stream. No data validation of the content occurs at this point only validation from approved DIP user | Y
MHHSP-30
|  | 3 | BP018 | 25-65 |  | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LSS | Validate HH Data and calculate Load Shaping Period and Totals data. |  | N
|  | 4 | BP018 | 60 | MHHS-BR-RD-022 | LSS | IF-022 | [LSSPeriodData] | DIP | The Load Shaping Service will generate Load Shape Period Data (IF-022) and Load Shape Totals Data (IF-023) and submit to DIP. | http 202 response from DIP | Y
|  |  |  | 75 | MHHS-BR-RD-023 |  | IF-023 | [LSSTotalsData]
Load Shaping data will require actual IF-021 data to be processed for MPANs within the same Load Shape Category.
|  | 5 |  | 240 |  | DIP | PUB-022 | [LSSPeriodData] | SUPC, ADSC | DIP sends PUB-022 and PUB-023 to Supplier and Data Service |  | N
|  |  |  | 250 |  |  | PUB-023 | [LSSTotalsData]
|  | 6 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-022 | [LSSPeriodData] | SUPC | Supplier receives the PUB-022 | Supplier receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | Y
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 7 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-023 | [LSSTotalsData] | SUPC | Supplier receives the PUB-023 | Supplier receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | Y
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 8 | BP005 | 120 | MHHS-BR-DS-076 | DIP | PUB-022 | [LSSPeriodData] | ADSC | Data Service receives the PUB-022 | Data Service receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. | Y
[5 empty] | MHHS-BR-DS-079 | [5 empty] | Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 9 | BP005 | 120 | MHHS-BR-DS-077 | DIP | PUB-023 | [LSSTotalsData] | ADSC | Data Service receives the PUB-023 | Data Service receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. | Y
[5 empty] | MHHS-BR-DS-080 | [5 empty] | Capture test evidence in the form of logs / screenshots from downstream systems/apps
| LSS Internal Calculations are validated | 10 | BP018 |  |  | Helix |  |  |  | LSS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. | Y
Capture test evidence in the form of logs / screenshots from Helix Tool
| UTC Period Level Consumption Start | 11 | BP005 | 130 | MHHS-BR-DS-083 | DIP | PUB-022 | [LSSPeriodData] | ADSC | If estimation is required the Data service estimates the Consumption based on the LSS Data |  | Y
[5 empty] | MHHS-BR-DS-088 |  | PUB-023 | [LSSTotalsData]
|  | 12 | BP005 | 140 | MHHS-BR-DS-091 | DIP | PUB-022 | [LSSPeriodData] | ADSC | If estimation is required the Data service validates complete set of UTC Settlement Period data |  | Y
[7 empty] | PUB-023 | [LSSTotalsData]
|  | 13 | BP005 | 150 | MHHS-BR-DS-093 | ADSC | IF-021 | [ActivePower] & [DI-015] <> W | DIP | The Data service submits IF-021 (UTC Period Level Consumption Data) to DIP | http 202 response from DIP | Y
MHHS-BR-DS-094.1
MHHS-BR-DS-095
|  | 14 | BP005 | 160 |  | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC, LDSO, LSS, MDS | DIP submits PUB-021 (UTC Period Level Consumption Data) to Supplier , LDSO, LSS and MDS |  | N
200
|  | 15 | BP005 | 280 | MHHS-BR-SU-044 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC | Supplier receives the PUB-021 | Supplier receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. | Y
[5 empty] | MHHS-BR-SU-045 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 16 | BP005 | 270 | MHHS-BR-LD-008 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LDSO | LDSO receives the PUB-021 | LDSO receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. | Y
[5 empty] | MHHS-BR-LD-007 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 17 | BP005 | 290 | MHHS-BR-SU-046 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC | Consumption Reconciliation Processes | Suppliers will follow their own reconciliation processes | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| UTC Period Level Consumption End | 18 | BP005 | 210 | MHHS-BR-RD-019 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LSS, MDS | LSS, MDS receives the PUB-021 | LSS and MDS receive PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| IF-021 Data in queue | 19 | BP005 | 220 | MHHS-BR-RD-019 | ADSC | PUB-021 | [ActivePower] & [DI-015] <> W | MDS | The IF-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | Y
| MDS Run Starts | 20 | BP019 | N/A |  | MDS | Settlement LDSO Base Data Report |  | DIP | MDS generates the Settlement LDSO Base Data Report by MPAN which is designed to assist LDSO in reconciling the test results . | http 202 response from DIP | Y
Test Tool/Artefact:
LDSO Base Data Report
|  | 21 | BP0019 | N/A |  | DIP | Settlement LDSO Base Data Report |  | LDSO | DIP submits Settlement LDSO Base Data Report for Publication to the LDSO |  | N
|  | 22 | BP0019 | N/A |  | DIP | Settlement LDSO Base Data Report |  | LDSO | LDSO receives published Settlement LDSO Base Data Report | LDSO receives Settlement LDSO Base Data Report and confirms report matches expected results. | Y
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| Test Tool/Artefact: | 23 | BP019 | N/A |  | MDS | Settlement Supplier Base Data Report |  | DIP | MDS generates the Settlement Supplier Base Data Report by MPAN which is designed to assist Supplier in reconciling the test results . | http 202 response from DIP | Y
Supplier Base Data Report
|  | 24 | BP0019 | N/A |  | DIP | Settlement Supplier Base Data Report |  | SUPC | DIP submits Settlement Supplier Base Data Report for Publication to the LDSO |  | N
|  | 25 | BP0019 | N/A |  | DIP | Settlement Supplier Base Data Report |  | SUPC | LDSO receives published Settlement Supplier Base Data Report | SUPC receives Settlement Supplier Base Data Report and confirms report matches expected results. | Y
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| MDS Reports are produced | 26 | BP0019 | 105 | MHHSP-14 | MDS | REP-002 |  | DIP | On completion, MDS submits Reports for Publication to DIP | http 202 response from DIP | Y
[5 empty] | MHHSP-23 |  | REP-002A
[5 empty] | MHHSP-27 |  | REP-002B
[5 empty] | MHHSP-30 |  | REP-006
[5 empty] | METH007, ID-9700 |  | REP-009
METH007, ID-9836
|  | 27 | BP0019 | 85 |  | DIP | REP-002 |  | SUPC, LDSO, | DIP submits Reports for Publication to the Supplier and LDSO |  | N
REP-002A
REP-002B
REP-006
REP-009
|  | 28 | BP0019 | N/A |  | DIP | REP-002 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports and confirms reports match expected results. | Y
[7 empty] | REP-006 |  |  |  | Capture test evidence in the form of logs / screenshots from downstream systems/apps
REP-009
|  | 29 | BP0019 | N/A |  | DIP | REP-002A |  | LDSO | LDSO receives published MDS Reports and confirms output is as expected | LDSO receives MDS Reports and confirms reports reconcile with expected results using the Settlement LDSO Base Data Report. | Y
[7 empty] | REP-002B |  |  |  | Capture test evidence in the form of logs / screenshots from downstream systems/apps
| MDS Run Ends | 30 | BP0019 |  |  | Helix |  |  |  | MDS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. | Y
Capture test evidence in the form of logs / screenshots
Internal MDS Calculations are validated
|  | 31 | BP019 | 115 | VAS Requirement | MDS | REP-090 |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | Y
| VAS Run Starts | 32 | BP020 | 75 | MHHSP-42 | VAS | REP-090 |  | DIP | On completion, VAS submits Reports for Publication to the DIP | http 202 response from DIP | Y
MHHSP-43
| VAS Reports are produced |  |  |  | MHHSP-44
MHHSP-45
MHHSP-51
MHHSP-52
MHHSP-55
MHHSP-56
MHHSP-57
| VAS Reports are produced | 33 | BP020 | 80 | REP-003 REP-003A | DIP | REP-090 |  | SUPC | DIP submits Reports for Publication to the Supplier |  | N
REP-004 REP-007
REP-D0081 REP-D0237
REP-D0266 REP-D0276
REP-D0296 REP-D0354
REP-D0369 REP-D0370
REP-D0373 REP-D0374
|  | 34 | BP0020 | N/A | REP-003 REP-003A | DIP | REP-090 |  | SUPC | Supplier receives published VAS Reports and confirms output is as expected | Supplier receives VAS Reports and confirms reports reconcile with expected results using the Settlement Supplier Base Data Report. | Y
[5 empty] | REP-004 REP-007 | [5 empty] | Capture test evidence in the form of logs / screenshots from downstream systems/apps
REP-D0081 REP-D0237
REP-D0266 REP-D0276
REP-D0296 REP-D0354
REP-D0369 REP-D0370
REP-D0373 REP-D0374
| VAS Run Ends | 35 | BP0019 |  |  | Helix |  |  |  | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. | Y
Capture test evidence in the form of logs / screenshots
Internal VAS Calculations are validated

## Settle Advanced DS
Common Shared Steps Process
SITFTC-MPAN Settlement Advanced Data Service
Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
Load Shaping | 10 | BP005 | 230 | MHHS-BR-RD-019 | DIP | IF-021 | [ActivePower] & [DI-015] <> W | LSS | LSS receives the PUB-021 | LSS receives PUB-021 [ActivePower] & [DI-015] = W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| 15 | BP018 | 15 | MHHSP-04 MHHSP-30 | DIP | PUB-021 | [ActivePower] & [DI-015] = W | LSS | Receive HH Data | Central Systems will need to subscribe to the DIP HH Data Publication. Data will be received as a constant stream. No data validation of the content occurs at this point only validation from approved DIP user | Y
| 20 | BP018 | 25-65 |  | DIP | PUB-021 | [ActivePower] & [DI-015] = W | LSS | Validate HH Data and calculate Load Shaping Period and Totals data. |  | N
| 25 | BP018 | 60 75 | MHHS-BR-RD-022 MHHS-BR-RD-023 | LSS | IF-022 IF-023 | [LSSPeriodData] [LSSTotalsData] | DIP | The Load Shaping Service will generate Load Shape Period Data (IF-022) and Load Shape Totals Data (IF-023) and submit to DIP. Load Shaping data will require actual IF-021 data to be processed for MPANs within the same Load Shape Category. | http 202 response from DIP | Y
| 30 |  | 240 250 |  | DIP | PUB-022 PUB-023 | [LSSPeriodData] [LSSTotalsData] | SUPC, ADSC | DIP sends PUB-022 and PUB-023 to Supplier and Data Service |  | N
| 35 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-022 | [LSSPeriodData] | SUPC | Supplier receives the PUB-022 | Supplier receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| 40 | BP005 | 260 | MHHS-BR-SU-043 | DIP | PUB-023 | [LSSTotalsData] | SUPC | Supplier receives the PUB-023 | Supplier receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| 45 | BP005 | 120 | MHHS-BR-DS-076 MHHS-BR-DS-079 | DIP | PUB-022 | [LSSPeriodData] | ADSC | Data Service receives the PUB-022 | Data Service receives PUB-022 [LSSPeriodData]. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| 50 | BP005 | 120 | MHHS-BR-DS-077 MHHS-BR-DS-080 | DIP | PUB-023 | [LSSTotalsData] | ADSC | Data Service receives the PUB-023 | Data Service receives PUB-023 [LSSTotalsData]. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
LSS Internal Calculations are validated | 55 | BP018 |  |  | Heilx |  |  |  | LSS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots from Helix Tool | Y
UTC Period Level Consumption Start | 60 | BP005 | 130 | MHHS-BR-DS-083 MHHS-BR-DS-088 | DIP | PUB-022 PUB-023 | [LSSPeriodData] [LSSTotalsData] | ADSC | If estimation is required the Data service estimates the Consumption based on the LSS Data |  | Y
| 65 | BP005 | 140 | MHHS-BR-DS-091 | DIP | PUB-022 PUB-023 | [LSSPeriodData] [LSSTotalsData] | ADSC | If estimation is required the Data service validates complete set of UTC Settlement Period data |  | Y
| 70 | BP005 | 150 | MHHS-BR-DS-093 MHHS-BR-DS-094.1 MHHS-BR-DS-095 | ADSC | IF-021 | [ActivePower] & [DI-015] <> W | DIP | The Data service submits IF-021 (UTC Period Level Consumption Data) to DIP | http 202 response from DIP | Y
| 75 | BP005 | 160 200 |  | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC, LDSO, LSS, MDS | DIP submits PUB-021 (UTC Period Level Consumption Data) to Supplier , LDSO, LSS and MDS |  | N
| 80 | BP005 | 280 | MHHS-BR-SU-044 MHHS-BR-SU-045 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC | Supplier receives the PUB-021 | Supplier receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| 85 | BP005 | 270 | MHHS-BR-LD-008 MHHS-BR-LD-007 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LDSO | LDSO receives the PUB-021 | LDSO receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
UTC Period Level Consumption End | 90 | BP005 | 210 | MHHS-BR-RD-019 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LSS, MDS | LSS, MDS receives the PUB-021 | LSS and MDS receive PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
IF-021 Data in queue | 95 | BP005 | 220 | MHHS-BR-RD-019 | ADSC | PUB-021 | [ActivePower] & [DI-015] <> W | MDS | The IF-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | Y
MDS Run Starts LDSO Base Data Reports | 100 | BP019 | N/A |  | MDS | Settlement LDSO Base Data Report |  | DIP | MDS generates the Settlement LDSO Base Data Report by MPAN which is designed to assist LDSO in reconciling the test results . | http 202 response from DIP | Y
| 105 | BP0019 | N/A |  | DIP | Settlement LDSO Base Data Report |  | LDSO | DIP submits Settlement LDSO Base Data Report for Publication to the LDSO |  | N
| 110 | BP0019 | N/A |  | DIP | Settlement LDSO Base Data Report |  | LDSO | LDSO receives published Settlement LDSO Base Data Report | LDSO receives Settlement LDSO Base Data Report and confirms report matches expected results. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
Supplier Base Data Reports | 115 | BP019 | N/A |  | MDS | Settlement Supplier Base Data Report |  | DIP | MDS generates the Settlement Supplier Base Data Report by MPAN which is designed to assist Supplier in reconciling the test results . | http 202 response from DIP | Y
| 120 | BP0019 | N/A |  | DIP | Settlement Supplier Base Data Report |  | SUPC | DIP submits Settlement Supplier Base Data Report for Publication to the LDSO |  | N
| 125 | BP0019 | N/A |  | DIP | Settlement Supplier Base Data Report |  | SUPC | LDSO receives published Settlement Supplier Base Data Report | SUPC receives Settlement Supplier Base Data Report and confirms report matches expected results. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MDS Reports are produced | 130 | BP0019 | 105 | MHHSP-14 MHHSP-23 MHHSP-27 MHHSP-30 | MDS | IF-021 | [ActivePower] & [DI-015] <> W | DIP | On completion, MDS submits Reports for Publication to DIP | http 202 response from DIP | Y
| 135 | BP0019 | 85 |  | DIP | REP-002 REP-002A REP-002B REP-006 REP-009 |  | SUPC, LDSO, | DIP submits Reports for Publication to the Supplier and LDSO |  | N
| 140 | BP0019 | N/A |  | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports and confirms reports match expected results. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| 145 | BP0019 | N/A |  | DIP | REP-002A REP-002B |  | LDSO | LDSO receives published MDS Reports and confirms output is as expected | LDSO receives MDS Reports and confirms reports reconcile with expected results using the Settlement LDSO Base Data Report. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MDS Run Ends Internal MDS Calculations are validated | 150 | BP0019 |  |  | Heilx |  |  |  | MDS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
| 155 | BP019 | 115 | VAS Requirement | MDS | REP-090 |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | Y
VAS Run Starts VAS Reports are produced | 160 | BP020 | 75 | MHHSP-42 MHHSP-43 MHHSP-44 MHHSP-45 MHHSP-51 MHHSP-52 MHHSP-55 MHHSP-56 MHHSP-57 | VAS | REP-090 |  | DIP | On completion, VAS submits Reports for Publication to the DIP | http 202 response from DIP | Y
VAS Reports are produced | 165 | BP020 | 80 | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0237 REP-D0266 REP-D0276 REP-D0296 REP-D0354 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-090 |  | SUPC | DIP submits Reports for Publication to the Supplier |  | N
| 170 | BP0020 | N/A | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0237 REP-D0266 REP-D0276 REP-D0296 REP-D0354 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-090 |  | SUPC | Supplier receives published VAS Reports and confirms output is as expected | Supplier receives VAS Reports and confirms reports reconcile with expected results using the Settlement Supplier Base Data Report. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
VAS Run Ends Internal VAS Calculations are validated | 175 | BP0019 |  |  | Heilx |  |  |  | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y