## Sheet1
SITFTS-0040 Change of supplier, MS and DS
Smart Related MPANs, forward-dated Change of Supply, Metering Service and Data Service (as per DES138 data specification)
Test Case Title | Key Journey | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence
| Events | [10 empty] | Required
Case replicated from: SITFTS-0040 TC03S | Change of Supply - Start | 1 | BP001 | 60 | N/A | SUPI | CSS01700 | N/A | CSS | SUPI sends Switch Request to CSS |  | Y
|  | 2 | BP001 | 65 | N/A | SUPI | CSS01700 | N/A | CSS | CSS receives Switch Request from Incoming Supplier and responds to REGS |  | Y
|  | 3 | BP001 | 70 | MHHS-BR-RS-005 | CSS | CSS02800 | N/A | REGS | CSS sends CSS02800 (pending Supplier request via CSS flow) for Primary MPAN. to the REGS. |  | Y
|  | 4 | BP001 | 70 | MHHS-BR-RS-005 | CSS | CSS02800 | N/A | REGS | CSS sends CSS02800 (pending Supplier request via CSS flow) for 1st of the Secondary MPAN'S to the REGS. |  | Y
|  | 5 | BP001 | 70 | MHHS-BR-RS-005 | CSS | CSS02800 | N/A | REGS | CSS sends CSS02800 (pending Supplier request via CSS flow) for 2nd of the Secondary MPAN'S to the REGS. |  | Y
|  | 6 | BP001 | 70 | MHHS-BR-RS-005 | CSS | CSS02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS flow for Primary MPAN. |  | Y
|  | 7 | BP001 | 70 | MHHS-BR-RS-005 | CSS | CSS02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS flow for 1st of the Secondary MPAN's. |  | Y
|  | 8 | BP001 | 70 | MHHS-BR-RS-005 | CSS | CSS02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS flow for 2nd of the Secondary MPAN's. |  | Y
| New Supplier of Site Notification - Primary MPAN | 9 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to the DIP for Primary MPAN | http 202 response from DIP | Y
|  | 10 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPI | DIP sends PUB-002 to the Incoming Supplier | PUB-002 Sent to new Supplier for Primary MPAN in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 11 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPI | Incoming Supplier receives PUB-002 from DIP | Supplier receives PUB-002 GainMPANInfo with all relevant information to set up the site. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| New Supplier of Site Notification - Secondary MPAN 1 | 12 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to the DIP for Secondary MPAN 1 | http 202 response from DIP | Y
|  | 13 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPI | DIP sends PUB-002 to the Incoming Supplier | PUB-002 Sent to new Supplier for Secondary MPAN 1 in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 14 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPI | Incoming Supplier receives PUB-002 from DIP | Supplier receives PUB-002 GainMPANInfo with all relevant information to set up the site. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| New Supplier of Site Notification - Secondary MPAN 2 | 15 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to the DIP for Secondary MPAN 2 | http 202 response from DIP | Y
|  | 16 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPI | DIP sends PUB-002 to the Incoming Supplier | PUB-002 Sent to new Supplier for Secondary MPAN 2 in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 17 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPI | Incoming Supplier receives PUB-002 from DIP | Supplier receives PUB-002 GainMPANInfo with all relevant information to set up the site. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| Change of Metering Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 18 | BP002 | 10 | MHHS-BR-SU-005 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to the DIP for a MS Appointment. | http 202 response from DIP | Y
|  |  |  | 20 | MHHS-BR-SU-006
MHHS-BR-SU-007
|  | 19 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
|  | 20 | BP002 | 40 | MHHS-BR-RS-010 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 21 | BP002 | 45 | MHHS-BR-RS-011 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 22 | BP002 | 50 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 to the Supplier. |  | N
|  | 23 | BP002 | 55 | MHHS-BR-SU-008 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-SU-009
| RS Appointment Request | 24 | BP002 | 60 | MHHS-BR-RS-014.1 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP. | http 202 response from DIP | Y
MHHS-BR-RS-015
|  | 25 | BP002 | 65 |  | DIP | PUB-033 | [MSAppSPRequest] | SMSI | DIP sends PUB-033 to the SMS (Incoming). |  | N
|  | 26 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | SMS (Incoming) receives PUB-033. | SMS incoming receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 27 | BP002 | 75 | MHHS-BR-MS-002 | SMSO | IF-034 | [MSAppSPResponse] | DIP | SMS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
MHHS-BR-MS-003
|  | 28 | BP002 | 80 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 29 | BP002 | 85 | MHHS-BR-RS-016 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-RS-017
| RS Appointment Accepted | 30 | BP002 | 87 | MHHS-BR-RS-018 | REGS | IF-035 | [MSAppAccepted] | DIP | REGS sends IF-035 to the DIP. | http 202 response from DIP | Y
|  | 31 | BP002 | 91 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, SMSI | DIP sends PUB-035 to the Supplier and SMS (Incoming) |  | N
|  | 32 | BP002 | 95 | MHHS-BR-SU-010 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-SU-011
|  | 33 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | SMSI | SMSI receives PUB-035. | SMSI receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 34 | BP002 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 [Prospective Appt] to the DIP. | http 202 response from DIP | Y
|  | 35 | BP002 | 90 |  | DIP | PUB-035 | [IMS-SendMTD] | SMSO | DIP sends PUB-035 [Prospective Appt] to the SMS (Outgoing). |  | N
|  | 36 | BP002 | 160 | MHHS-BR-MS-006 | DIP | PUB-035 | [IMS-SendMTD] | SMSO | SMS (Outgoing) receives PUB-035. | SMS outgoing receives PUB-035 with details of IMS Send MTD from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Change of Data Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 39 | BP003 | 10 | MHHS-BR-SU-019 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP - for a DS Appointment | http 202 response from DIP | Y
|  |  |  | 20 | MHHS-BR-SU-020
MHHS-BR-SU-021
|  | 40 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment |  | N
|  | 41 | BP003 | 40 | MHHS-BR-RS-043 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier. | REGS receives PUB-031 DSApp with details of Data Services Appointment and confirms the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-RS-044
| Supplier Appointment Request Accepted | 42 | BP003 | 45 | MHHS-BR-RS-045 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
MHHS-BR-RS-046
|  | 43 | BP003 | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the DIP. |  | N
|  | 44 | BP003 | 55 | MHHS-BR-SU-022 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-SU-023
| RS Appointment Request | 45 | BP003 | 60 | MHHS-BR-RS-049 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 202 response from DIP | Y
MHHS-BR-RS-048.1
|  | 46 | BP003 | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | SDSI | DIP sends PUB-033 to the SDS (Incoming). |  | N
|  | 47 | BP003 | 220 | MHHS-BR-DS-007 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | SDS (Incoming) receives PUB-033 from the DIP. | SDS receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-DS-011
| RS Appointment Request Accepted | 48 | BP003 | 221 | MHHS-BR-DS-008 | SDSI | IF-034 | [DSAppSPResponse] | DIP | SDS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
MHHS-BR-DS-011
|  | 49 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 50 | BP003 | 85 | MHHS-BR-RS-050 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to determine processing treatment | Y
|  |  |  | 100 | MHHS-BR-RS-051 | [5 empty] | Confirms successful updates on downstream systems.
[5 empty] | MHHS-BR-RS-054 | [5 empty] | Capture test evidence in the form of logs / screenshots from downstream systems/apps
MHHS-BR-RS-056
MHHS-BR-RS-057
| RS Appointment Accepted | 51 | BP003 | 85 | MHHS-BR-RS-050 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to the DIP | http 202 response from DIP | Y
|  |  |  | 87 | MHHS-BR-RS-051
MHHS-BR-RS-052
|  | 52 | BP003 | 91 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC, SDSI | DIP sends PUB-035 to the Supplier and Data Service (Incoming) |  | N
|  | 53 | BP003 | 95 | MHHS-BR-SU-024 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-SU-025
|  | 54 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | SDSI | SDSI receives PUB-035. | SDSI receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 55 | BP003 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 to DIP | http 202 response from DIP | Y
|  | 56 | BP003 | 88 |  | DIP | PUB-035 | [IMS-SendMTD] | SMSO | DIP sends PUB-035 [Prospective Appt] to the SMS (Outgoing). |  | N
|  | 57 | BP003 | 160 | MHHS-BR-MS-006 | DIP | PUB-035 | [IMS-SendMTD] | SMSO | SMS (Outgoing) receives PUB-035 from the DIP | SMS Outgoing receives PUB-035 with details of IMS-SendMTD and confirm REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 60 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPI | CSS Sends Status Change Notification Message to New Supplier for Primary MPAN. | Suppliers will receive notification from CSS that COS has a secured status | Y
MHHS-BR-SU-048
|  | 61 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPI | CSS Sends Status Change Notification Message to New Supplier 1st of the Secondary MPAN's. | Suppliers will receive notification from CSS that COS has a secured status | Y
MHHS-BR-SU-048
|  | 62 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPI | CSS Sends Status Change Notification Message to New Supplier 2nd of the Secondary MPAN's | Suppliers will receive notification from CSS that COS has a secured status | Y
MHHS-BR-SU-048
|  | 63 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPI | SUPI receives CSS02370 Status Change Notification Message from CSS for Primary MPAN. | Suppliers will receive notification from CSS that COS has a secured status | Y
MHHS-BR-SU-048
|  | 64 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPI | SUPI receives CSS02370 Status Change Notification Message from CSS 1st of the Secondary MPAN's. | Suppliers will receive notification from CSS that COS has a secured status | Y
MHHS-BR-SU-048
|  | 65 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPI | SUPI receives CSS02370 Status Change Notification Message from CSS 2nd of the Secondary MPAN's. | Suppliers will receive notification from CSS that COS has a secured status | Y
MHHS-BR-SU-048
|  | 66 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | CSS sends CSS02860 Status Change Sync to REGS for Primary MPAN. | The Registration Service will receive a COS secured notification from CSS. The Registration Service will send IF-001 to confirm to parties the new Supplier information | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 67 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | CSS sends CSS02860 Status Change Sync to REGS 1st of the Secondary MPAN's. | The Registration Service will receive a COS secured notification from CSS. The Registration Service will send IF-001 to confirm to parties the new Supplier information | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 68 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | CSS sends CSS02860 Status Change Sync to REGS 2nd of the Secondary MPAN's. | The Registration Service will receive a COS secured notification from CSS. The Registration Service will send IF-001 to confirm to parties the new Supplier information | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 69 | BP001 | 180 | MHHS BR EES 016.4 | CSS | CSS02460 | N/A | EES | EES receives CSS02460 Status Change Sync for Primary MPAN |  | Y
|  | 70 | BP001 | 180 | MHHS BR EES 016.4 | CSS | CSS02460 | N/A | EES | EES receives CSS02460 Status Change Sync 1st of the Secondary MPAN's. |  | Y
|  | 71 | BP001 | N/A | N/A | CSS | CSS02460 | N/A | EES | EES receives CSS02460 Status Change Sync 2nd of the Secondary MPAN's. |  | Y
|  | 72 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | REGS receives CSS02860 Status Change Sync and outputs IF-001 - CoS Notification for Primary MPAN. | The Registration Service will receive a COS secured notification from CSS. The Registration Service will send IF-001 to confirm to parties the new Supplier information | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 73 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | REGS receives CSS02860 Status Change Sync 1st of the Secondary MPAN's and outputs IF-001 - CoS Notification. |  | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 74 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | REGS receives CSS02860 Status Change Sync 2nd of the Secondary MPAN's and outputs IF-001 - CoS Notification. |  | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
| COS Notification - Primary MPAN | 75 | BP001 | 130 |  | REGS | IF-001 | [ChangeOfSupplier] | DIP | REGS sends IF-001 - CoS Notification to DIP for Primary MPAN | http 202 response from DIP | Y
|  | 76 | BP001 | 135 | MHHS-BR-RS-007 | DIP | PUB-001 | [ChangeOfSupplier] | SUPC, LDSO, MDS | DIP sends PUB-001 - CoS Notification to SUPC, LDSO, MDS. | DIP send PUB-001 ChangeOfSupplier notification for Primary MPAN with relevant information to SUPC, LDSO, MDS.Confirms successful updates on downstream systems. | N
|  |  |  | 150 | MHHS-BR-RS-008 | [5 empty] | Capture test evidence in the form of logs / screenshots from downstream systems/apps
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 77 | BP001 | 165 | MHHS-BR-SU-004 | DIP | PUB-001 | [ChangeOfSupplier] | SUPC | Supplier receives PUB-001 - CoS Notification | Supplier receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
[5 empty] | MHHS-BR-SU-049 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 78 | BP001 | 160 | MHHS-BR-LD-001 | DIP | PUB-001 | [ChangeOfSupplier] | LDSO | LDSO receives PUB-001 - CoS Notification | LDSO receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
[5 empty] | MHHS-BR-LD-012 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 79 | BP001 | 155 | MDS | DIP | PUB-001 | [ChangeOfSupplier] | MDS | MDS receives PUB-001 - CoS Notification | MDS receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| COS Notification - Secondary MPAN 1 | 80 | BP001 | 130 |  | REGS | IF-001 | N/A | DIP | REGS sends IF-001 - CoS Notification to DIP for Secondary MPAN 1 | http 202 response from DIP | Y
|  | 81 | BP001 | 135 | MHHS-BR-RS-007 | DIP | PUB-001 | [ChangeOfSupplier] | SUPC, LDSO, MDS | DIP sends PUB-001 - CoS Notification to SUPC, LDSO, MDS. | DIP send PUB-001 ChangeOfSupplier notification for Secondary MPAN 1 with relevant information to SUPC, LDSO, MDS. | N
|  |  |  | 150 | MHHS-BR-RS-008 | [5 empty] | Confirms successful updates on downstream systems.
[5 empty] | MHHS-BR-RS-094 | [5 empty] | Capture test evidence in the form of logs / screenshots from downstream systems/apps
MHHS-BR-RS-096
|  | 82 | BP001 | 165 | MHHS-BR-SU-004 | DIP | PUB-001 | [ChangeOfSupplier] | SUPC | Supplier receives PUB-001 - CoS Notification | Supplier receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
[5 empty] | MHHS-BR-SU-049 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 83 | BP001 | 160 | MHHS-BR-LD-001 | DIP | PUB-001 | [ChangeOfSupplier] | LDSO | LDSO receives PUB-001 - CoS Notification | LDSO receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
[5 empty] | MHHS-BR-LD-012 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 84 | BP001 | 155 | MDS | DIP | PUB-001 | [ChangeOfSupplier] | MDS | MDS receives PUB-001 - CoS Notification | MDS receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
| COS Notification - Secondary MPAN 2 | 85 | BP001 | 130 | MHHS-BR-RS-007 | REGS | IF-001 | N/A | DIP | REGS sends IF-001 - CoS Notification to DIP for Secondary MPAN 2 | http 202 response from DIP | Y
MHHS-BR-RS-008
MHHS-BR-RS-094
MHHS-BR-RS-096
|  | 86 | BP001 | 135 |  | DIP | PUB-001 | [ChangeOfSupplier] | SUPC, LDSO, MDS | DIP sends PUB-001 - CoS Notification to SUPC, LDSO, MDS. | DIP send PUB-001 ChangeOfSupplier notification for Secondary MPAN 2 with relevant information to SUPC, LDSO, MDS. | N
150
|  | 87 | BP001 | 165 | MHHS-BR-SU-004 | DIP | PUB-001 | [ChangeOfSupplier] | SUPC | Supplier receives PUB-001 - CoS Notification | Supplier receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
[5 empty] | MHHS-BR-SU-049 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 88 | BP001 | 160 | MHHS-BR-LD-001 | DIP | PUB-001 | [ChangeOfSupplier] | LDSO | LDSO receives PUB-001 - CoS Notification | LDSO receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
[5 empty] | MHHS-BR-LD-012 | [5 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 89 | BP001 | 155 | MDS | DIP | PUB-001 | [ChangeOfSupplier] | MDS | MDS receives PUB-001 - CoS Notification | MDS receives PUB-001 ChangeOfSupplier with all relevant information to confirm new supplier. | Y
Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
Change of Metering Service - Accept Appointment
| RS Appointment Queue (If required) / | 90 | BP002 | 100 | MHHS-BR-RS-020 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached and CSS Secured Notifications received |  | Y
| COS Secured Notification |  |  | 101 | MHHS-BR-RS-022
|  |  |  | 120 | MHHS-BR-RS-025
|  | 91 | BP002 | 125 | N/A | CSS | CSS Secured Notification | N/A | REGS | CSS Secured Notification received for Primary MPAN |  | Y
|  | 92 | BP002 | 125 | N/A | CSS | CSS Secured Notification | N/A | REGS | CSS Secured Notification received for Secondary MPAN 1 |  | Y
|  | 93 | BP002 | 125 | N/A | CSS | CSS Secured Notification | N/A | REGS | CSS Secured Notification received for Secondary MPAN 2 |  | Y
| RS Appointment Notification - Primary MPAN | 94 | BP002 | 240 | MHHS-BR-RS-033 | REGS | IF-036 | [MSAppActive] | DIP | REGS sends IF-036 to DIP. | http 202 response from DIP | Y
|  | 95 | BP002 | 245 |  | DIP | PUB-036 | [MSAppActive] | SDSC | DIP sends PUB-036 to SUPC, LDSO, EES, SMSI and SDSC for the Primary MPAN |  | N
|  | 96 | BP002 | 260 | MHHS-BR-SU-013 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 97 | BP002 | 280 | MHHS-BR-LD-003 | DIP | PUB-036 | [MSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 98 | BP002 | 283 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 99 | BP002 | 195 | MHHS-BR-MS-007 | DIP | PUB-036 | [MSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 100 | BP002 | 270 | MHHS-BR-DS-002 | DIP | PUB-036 | [MSAppActive] | SDSC | SDSC receives PUB-036 | SDSC receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-DS-003
| RS De-Appointment Notification - Primary MPAN | 101 | BP002 | 120 +130 | MHHS-BR-RS-024 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 202 response from DIP | Y
MHHS-BR-RS-030
MHHS-BR-RS-031
|  | 102 | BP002 | 140 |  | DIP | PUB-037 | [MSDeApp] | SMSO, SUPO, LDSO, EES | DIP sends PUB-037 to Old Metering Service, Supplier(Outgoing), LDSO & EES for the Primary MPAN |  | N
|  | 103 | BP002 | 231 | MHHS-BR-MS-005 | DIP | PUB-037 | [MSDeApp] | SMSO | Old Metering Service receives PUB-037 confirming MS De-appointment | Old metering service receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 104 | BP002 | 150 | MHHS-BR-SU-012 | DIP | PUB-037 | [MSDeApp] | SUPO | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Outgoing supplier receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 105 | BP002 | 145 | MHHS-BR-LD-002 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 106 | BP002 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Secondary MPAN 1 | 107 | BP002 | 710 | MHHS-BR-RS-037 | REGS |  |  |  | Registration service identifies Related MPANs and processes the Secondary MPAN 1 |  | Y
|  | 108 | BP002 | 770 | MHHS-BR-RS-039 | REGS | IF-036 | [MSAppActive] | DIP | Registration service sends out IF-036 to DIP. | http 202 response from DIP | Y
|  | 109 | BP002 | 780 |  | DIP | PUB-036 | [MSAppActive] | SUPC, SMSI, LDSO, EES | DIP sends PUB-036 to SUPC, SMSI, LDSO, EES confirming MS Appointment for Secondary MPAN 1 |  | N
|  | 110 | BP002 | 750 | MHHS-BR-SU-017 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 111 | BP002 | 790 | MHHS-BR-MS-008.1 | DIP | PUB-036 | [MSAppActive] | SMSI | SMS (Incoming) receives PUB-036 | SMS incoming receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-MS-008
|  | 112 | BP002 | 280 | MHHS-BR-LD-003 | DIP | PUB-036 | [MSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 113 | BP002 | 283 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Secondary MPAN 2 | 114 | BP002 | 710 | MHHS-BR-RS-037 | REGS |  |  |  | Registration service identifies Related MPANs and processes the Secondary MPAN 2 |  | Y
|  | 115 | BP002 | 770 | MHHS-BR-RS-039 | REGS | IF-036 | [MSAppActive] | DIP | Registration service sends out IF-036 to DIP. | http 202 response from DIP | Y
|  | 116 | BP002 | 780 |  | DIP | PUB-036 | [MSAppActive] | SUPC, SMSI, LDSO, EES | DIP sends PUB-036 to SUPC, SMSI, LDSO, EES confirming MS Appointment for Secondary MPAN 2 |  | N
|  | 117 | BP002 | 750 | MHHS-BR-SU-017 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 118 | BP002 | 790 | MHHS-BR-MS-008.1 | DIP | PUB-036 | [MSAppActive] | SMSI | SMS (Incoming) receives PUB-036 | SMS incoming receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-MS-008
|  | 119 | BP002 | 280 | MHHS-BR-LD-003 | DIP | PUB-036 | [MSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 120 | BP002 | 283 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 with details of Metering service appointment active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Secondary MPAN 1 | 127 | BP002 | 720 | MHHS-BR-RS-038 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 202 response from DIP | Y
|  | 128 | BP002 | 740 |  | DIP | PUB-037 | [MSDeApp] | SMSO, SUPO, LDSO, EES | DIP sends PUB-037 to SMSO, Supplier(Outgoing), LDSO AND EES confirming MS De-appointment for Secondary MPAN 1 |  | N
|  | 129 | BP002 | 760 | MHHS-BR-MS-009 | DIP | PUB-037 | [MSDeApp] | SMSO | SMSO receives PUB-037 | SMSO receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-MS-009.1
|  | 130 | BP002 | 755 | MHHS-BR-SU-016 | DIP | PUB-037 | [MSDeApp] | SUPO | Supplier(Outgoing) receives PUB-037 | Supplier Outgoing receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 131 | BP002 | 145 | MHHS-BR-LD-002 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 | LDSO receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 132 | BP002 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 | EES receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Secondary MPAN 2 | 133 | BP002 | 720 | MHHS-BR-RS-038 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 202 response from DIP | Y
|  | 134 | BP002 | 740 |  | DIP | PUB-037 | [MSDeApp] | SMSO, SUPO, LDSO, EES | DIP sends PUB-037 to SMSO, Supplier(Outgoing), LDSO AND EES confirming MS De-appointment for Secondary MPAN 2 |  | N
|  | 135 | BP002 | 760 | MHHS-BR-MS-009 | DIP | PUB-037 | [MSDeApp] | SMSO | SMSO receives PUB-037 | SMSO receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-MS-009.1
|  | 136 | BP002 | 755 | MHHS-BR-SU-016 | DIP | PUB-037 | [MSDeApp] | SUPO | Supplier(Outgoing) receives PUB-037 | Supplier Outgoing receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 137 | BP002 | 145 | MHHS-BR-LD-002 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 | LDSO receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 138 | BP002 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 | EES receives PUB-037 with details of Metering DE appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
Change of Data Service - Accept Appointment
| RS Appointment Queue (If required) / | 139 | BP003 | 100 | MHHS-BR-RS-054 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached and CSS Secured Notifications received | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to hold these in a queue and re-process daily after CSS updates have been received or until the 'eff from date' comes into effect. | Y
| COS Secured Notification |  |  | 101 | MHHS-BR-RS-056 | [5 empty] | Retain accepted responses in the background until the Effective from date when it will reflect as a live appointment.
|  |  |  | 120 | [6 empty] | Confirms successful updates on downstream systems.
Capture test evidence in the form of logs / screenshots from downstream systems/apps
|  | 140 | BP003 | 125 | N/A | CSS | CSS Secured Notification | N/A | REGS | CSS Secured Notification received for Primary MPAN |  | Y
|  | 141 | BP003 | 125 | N/A | CSS | CSS Secured Notification | N/A | REGS | CSS Secured Notification received for Secondary MPAN 1 |  | Y
|  | 142 | BP003 | 125 | N/A | CSS | CSS Secured Notification | N/A | REGS | CSS Secured Notification received for Secondary MPAN 2 |  | Y
| RS Appointment Notification - Primary MPAN | 143 | BP003 | 250 | MHHS-BR-RS-067 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 202 response from DIP | Y
|  | 144 | BP003 | 255 |  | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, LDSO, EES, SDSI, MDS | DIP sends PUB-036 to SUPC, SMSI, LDSO, EES, SDSI and MDS confirming DS Appointment for the Primary MPAN |  | N
|  | 145 | BP003 | 260 | MHHS-BR-SU-027 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 146 | BP003 | 281 | MHHS-BR-MS-030 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 147 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-036 | [DSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 148 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 149 | BP003 | 284 (TBC) | TBC | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 150 | BP003 | 340 | MHHS-BR-DS-013 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Primary MPAN | 151 | BP003 | 130 | MHHS-BR-RS-064 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
MHHS-BR-RS-065
|  | 152 | BP003 | 140 |  | DIP | PUB-037 | [DSDeApp] | SDSO, SUPO, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to SDSO, SUPO, LDSO, EES and MDS for the Primary MPAN |  | N
|  | 153 | BP003 | 96 | MHHS-BR-DS-018 | DIP | PUB-037 | [DSDeApp] | SDSO | Smart Data Service (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | Outgoing Smart Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 154 | BP003 | 150 | MHHS-BR-SU-026 | DIP | PUB-037 | [DSDeApp] | SUPO | SUPO receives PUB-037 confirming DS De-appointment | SUPO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 155 | BP003 | 145 | MHHS-BR-LD-004 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 156 | BP003 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 157 | BP003 | 147 (TBC) | TBC | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Secondary MPAN 1 | 158 | BP003 | 710 | MHHS-BR-RS-072 | REGS |  |  |  | Registration service identifies Related MPANs and processes the Secondary MPAN 1 | Registration services receives PUB-034 DSAppSPResponsep with details of Data Services Appointment PR response and confirms identifying Related MPANs and processes the secondary MPANs successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 159 | BP003 | 770 | MHHS-BR-RS-074 | REGS | IF-036 | [DSAppActive] | DIP | Registration service sends IF-036 to DIP | http 202 response from DIP | Y
|  | 160 | BP003 | 780 | MHHS-BR-RS-074 | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, SDSI, LDSO, EES, MDS | DIP sends PUB-036 to SUPC, SMSI, SDSI, LDSO, EES and MDS confirming DS Appointment for the Secondary MPAN 1 |  | N
|  | 161 | BP003 | 750 | MHHS-BR-SU-029 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 162 | BP003 | 281 | MHHS-BR-MS-030 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 163 | BP003 | 790 | MHHS-BR-DS-029 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-DS-029.1
|  | 164 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-036 | [DSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 165 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 166 | BP003 | 284 (TBC) | TBC | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Secondary MPAN 1 | 167 | BP003 | 720 | MHHS-BR-RS-073 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
|  | 168 | BP003 | 740 |  | DIP | PUB-037 | [DSDeApp] | SDSO, SUPO, LDSO, EES, MDS | DIP sends PUB-037 to SDSO, SUPO, LDSO, EES and MDS confirming DS De-appointment for the Secondary MPAN 1 |  | N
|  | 169 | BP003 | 760 | MHHS-BR-DS-030 | DIP | PUB-037 | [DSDeApp] | SDSO | SDSO receives PUB-037 | SDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-DS-030.1
|  | 170 | BP003 | 150 | MHHS-BR-SU-026 | DIP | PUB-037 | [DSDeApp] | SUPO | SUPO receives PUB-037 confirming DS De-appointment | SUPO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 171 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037 | LDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 172 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037 | EES receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 173 | BP003 | 284 (TBC) | TBC | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037 | MDS receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification - Secondary MPAN 2 | 174 | BP003 | 710 | MHHS-BR-RS-072 | REGS |  |  |  | Registration service identifies Related MPANs and processes the Secondary MPAN 2 | Registration services receives PUB-034 DSAppSPResponsep with details of Data Services Appointment PR response and confirms identifying Related MPANs and processes the secondary MPANs successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 175 | BP003 | 770 | MHHS-BR-RS-074 | REGS | IF-036 | [DSAppActive] | DIP | Registration service sends IF-036 to DIP | http 202 response from DIP | Y
|  | 176 | BP003 | 780 | MHHS-BR-RS-074 | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, SDSI, LDSO, EES, MDS | DIP sends PUB-036 to SUPC, SMSI, SDSI, LDSO, EES and MDS confirming DS Appointment for the Secondary MPAN 2 |  | N
|  | 177 | BP003 | 750 | MHHS-BR-SU-029 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 178 | BP003 | 281 | MHHS-BR-MS-030 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 179 | BP003 | 790 | MHHS-BR-DS-029 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-DS-029.1
|  | 180 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-036 | [DSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 181 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 182 | BP003 | 284 (TBC) | TBC | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS De-Appointment Notification - Secondary MPAN 2 | 183 | BP003 | 720 | MHHS-BR-RS-073 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 202 response from DIP | Y
|  | 184 | BP003 | 720 |  | DIP | PUB-037 | [DSDeApp] | SDSO, SUPO, LDSO, EES, MDS | DIP sends PUB-037 to SDSO, SUPO, LDSO, EES and MDS confirming DS De-appointment for the Secondary MPAN 2 |  | N
|  | 185 | BP003 | 760 | MHHS-BR-DS-030 | DIP | PUB-037 | [DSDeApp] | SDSO | SDSO receives PUB-037 | SDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
MHHS-BR-DS-030.1
|  | 186 | BP003 | 150 | MHHS-BR-SU-026 | DIP | PUB-037 | [DSDeApp] | SUPO | SUPO receives PUB-037 confirming DS De-appointment | SUPO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 187 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037 | LDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 188 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037 | EES receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 189 | BP003 | 284 (TBC) | TBC | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037 | MDS receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| CSS/DCC Updates - Start | 325 | BP003A | 20 | MHHS-BR-RS-078 MHHS-BR-RS-078.1 MHHS-BR-RS-078.2 | REGS | ERDA CSS00200 (Issue MDR Request) | N/A | CSS | REGS issues ERDA CSS00200 for Primary MPAN (Issue MDR Request) to CSS which outputs CSS07000 (Response) |  | Y
|  | 330 | BP003A | 20 | MHHS-BR-RS-078 MHHS-BR-RS-078.1 MHHS-BR-RS-078.2 | REGS | ERDA CSS00200 (Issue MDR Request) | N/A | CSS | REGS issues ERDA CSS00200 for Secondary MPAN 1 (Issue MDR Request) to CSS which outputs CSS07000 (Response) |  | Y
|  | 330 | BP003A | 20 | MHHS-BR-RS-078 MHHS-BR-RS-078.1 MHHS-BR-RS-078.2 | REGS | ERDA CSS00200 (Issue MDR Request) | N/A | CSS | REGS issues ERDA CSS00200 for Secondary MPAN 2 (Issue MDR Request) to CSS which outputs CSS07000 (Response) |  | Y
|  | 335 | N/A | N/A | Existing requirement- REC Schedule 28 | REGS | ERDA CSS00200 (Issue MS appointment notification ) | N/A | CSS | REGS issues ERDA CSS00200 for Primary MPAN (Issue MS appointment notification) to CSS which outputs CSS07000 (Response) |  | Y
|  | 340 | N/A | N/A | Existing requirement- REC Schedule 28 | REGS | ERDA CSS00200 (Issue MS appointment notification ) | N/A | CSS | REGS issues ERDA CSS00200 for Secondary MPAN 1 (Issue MS appointment notification) to CSS which outputs CSS07000 (Response) |  | Y
|  | 340 | N/A | N/A | Existing requirement- REC Schedule 28 | REGS | ERDA CSS00200 (Issue MS appointment notification ) | N/A | CSS | REGS issues ERDA CSS00200 for Secondary MPAN 2 (Issue MS appointment notification) to CSS which outputs CSS07000 (Response) |  | Y
|  | 345 | BP003A | 30 40 | CSS | CSS | DSP of MDR appointment | N/A | DCC | CSS calls CSS-DSP Interface to inform DSP of MDR appointment |  | Y
|  | 350 | N/A | N/A | CSS | CSS | DSP of MS appointment (CSS03200) | N/A | DCC | CSS calls CSS-DSP Interface to inform DSP of MS appointment |  | Y
|  | 355 | BP003A | 50 60 | DCC | DCC | DSP updates MDR appointment | N/A | CSS | DSP updates MDR appointment, and confirms update to CSS over CSS-DSP Interface for Import MPAN |  | Y
|  | 360 | BP003A | 50 60 | DCC | DCC | DSP updates MDR appointment | N/A | CSS | DSP updates MDR appointment, and confirms update to CSS over CSS-DSP Interface for Export MPAN |  | Y
|  | 365 | BP003A | 80 | MHHS-BR-RS-079 | CSS | CSS07000 (Response) | N/A | REGS | REGS receives CSS07000 (Response) from CSS for Primary and outputs IF-035 - (DCC MDR Outcome) to DIP | http 202 response from DIP | Y
|  | 370 | BP003A | 80 | MHHS-BR-RS-079 | CSS | CSS07000 (Response) | N/A | REGS | REGS receives CSS07000 (Response) from CSS for Secondary MPAN 1 |  | Y
|  | 370 | BP003A | 80 | MHHS-BR-RS-079 | CSS | CSS07000 (Response) | N/A | REGS | REGS receives CSS07000 (Response) from CSS for Secondary MPAN 2 |  | Y
|  | 375 | BP003A | 90 | MHHS-BR-RS-080 | REGS | IF-035 | [DCC-MDROutcome] | DIP | REGS sends IF-035 - (DCC MDR Outcome) to DIP for Primary MPAN | http 202 response from DIP | Y
|  | 380 | BP003A | 100 110 |  | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | DIP sends PUB-035 to SDSI |  | N
|  | 385 | BP003A | 120 | MHHS-BR-DS-042.1 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | SDS (Incoming) receives PUB-035 - (DCC MDR Outcome) and manages Service Provider Update (BAU). | SDS incoming receives PUB-035 for Primary MPAN with details of DCC MDR outcome and confirms (DCC MDR Outcome) and manages Service Provider Update (BAU) successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 390 | BP003A | 90 | MHHS-BR-RS-080 | REGS | IF-035 | [DCC-MDROutcome] | DIP | REGS sends IF-035 - (DCC MDR Outcome) to DIP for Secondary MPAN 1 | http 202 response from DIP | Y
|  | 390 | BP003A | 90 | MHHS-BR-RS-080 | REGS | IF-035 | [DCC-MDROutcome] | DIP | REGS sends IF-035 - (DCC MDR Outcome) to DIP for Secondary MPAN 2 | http 202 response from DIP | Y
|  | 395 | BP003A | 100 110 |  | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | DIP sends PUB-035 to SDSI |  | N
| CSS/DCC Updates - Completed | 400 | BP003A | 120 | MHHS-BR-DS-042.1 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | SDS (Incoming) receives PUB-035 for Secondary MPAN 1 - (DCC MDR Outcome) and manages Service Provider Update (BAU). | SDS incoming receives PUB-035 for Export MPAN with details of DCC MDR outcome and confirms (DCC MDR Outcome) and manages Service Provider Update (BAU) successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| CSS/DCC Updates - Completed | 400 | BP003A | 120 | MHHS-BR-DS-042.1 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | SDS (Incoming) receives PUB-035 for Secondary MPAN 2 - (DCC MDR Outcome) and manages Service Provider Update (BAU). | SDS incoming receives PUB-035 for Export MPAN with details of DCC MDR outcome and confirms (DCC MDR Outcome) and manages Service Provider Update (BAU) successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y