## Sheet1
Test Case Title | Key Journey | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence
| Events | [10 empty] | Required
Case replicated from: SITFTS-0050 TC03 | New MPAN Initial Registration - Start | 1 | BP001 | 5 | MHHS-BR-LD-010.1 | LDSO | DB01 | N/A | REGS | LDSO creates MPAN for Import MPAN and issues DB01 REGS | Import Mpan creation and linkage required | Y
MHHS-BR-LD-010.2
|  | 2 | BP001 | 40 | MHHS-BR-RS-089 | REGS | IF-050 | [MPANCreation] | DIP | MPAN is created in the Registration Service and REGS sends IF-050 to DIP | http 202 response from DIP | Y
|  |  |  | 41 | MHHS-BR-RS-090
MHHS-BR-RS-091
MHHS-BR-RS-091.1
MHHS-BR-RS-091.2
MHHS-BR-RS-092
MHHS-BR-RS-093
MHHS-BR-RS-093.1
|  | 3 | BP001 | 42 |  | DIP | PUB-050 | [MPANCreation] | EES | MPAN is created in the Registration Service and DIP sends PUB-050 to EES |  | N
|  | 4 | BP001 | 43 | MHHS-BR-EES-016.3 | DIP | PUB-050 | [MPANCreation] | EES | EES receives PUB-050 and updates its data | EES receives PUB-050 with details of MPAN Creation Notification and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 5 | BP001 | 45 | N/A | REGS | CSS01000 | N/A | CSS | MPAN is created in CSS For Import MPAN | CSS will create the Import MPAN as per the existing process | Y
50
|  | 6 | BP001 | 50 | N/A | SUPC | CSS01700 | N/A | CSS | CSS receives Switch Request for Import MPAN from Supplier and notifies to REGS | Unnumbered "Receive COS Request" in BP001 | Y
|  | 7 | BP001 | 70 | MHHS-BR-RS-094 | CSS | CSS02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS flow for Import MPAN. |  | Y
MHHS-BR-RS-094.1
MHHS-BR-RS-096
| New Supplier Site Info (IF-002) - Import MPAN | 8 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to DIP for Import MPAN | http 202 response from DIP | Y
|  | 9 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPC | DIP Sends PUB-002 to the new supplier | PUB-002 is Sent to new Supplier for Import MPAN in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 10 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPC | PUB-002 received by new supplier | New Supplier receives PUB-002 with details of Gaining MPAN info for Import MPAN and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering Service - Raise Appointment | 11 | BP002 | 10 | MHHS-BR-SU-005 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to DIP | http 202 response from DIP | Y
|  |  |  | 20 | MHHS-BR-SU-006
MHHS-BR-SU-007
MHHS-BR-SU-123.2
|  | 12 | BP002 | 10 |  | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
20
|  | 13 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP | REGS receives PUB-031 with details of Metering Service Appointment and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 14 | BP002 | 40 | MHHS-BR-RS-010 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP | http 202 response from DIP | Y
|  |  |  | 45 | MHHS-BR-RS-011
|  | 15 | BP002 | 40 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the Supplier. |  | N
45
|  | 16 | BP002 | 55 | MHHS-BR-SU-009 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 with details of Metering Service Appointment initial response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 17 | BP002 | 60 | MHHS-BR-RS-014.1 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP | http 202 response from DIP | Y
MHHS-BR-RS-015
|  | 18 | BP002 | 60 | MHHS-BR-RS-014.1 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | DIP sends PUB-033 to the Metering Service (Incoming). |  | N
MHHS-BR-RS-015
|  | 19 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | Metering Service (Incoming) receives PUB-033 from the DIP. | Metering Service receives PUB-033 with details of Metering Service Appointment service provider response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 20 | BP002 | 75 | MHHS-BR-MS-002 | SMSI | IF-034 | [MSAppSPResponse] | DIP | Metering Service (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
MHHS-BR-RS-034
MHHS-BR-DS-71.2
|  | 21 | BP002 | 75 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 22 | BP002 | 85 | MHHS-BR-RS-022 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment REGS Holds in appointment queue until appointment date reached | REGS receives PUB-034 with details of Metering Service Appointment service provider response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  |  |  | 101 | MHHS-BR-RS-016
|  |  |  | 120 | MHHS-BR-RS-017
|  | 23 | BP002 | 87 | MHHS-BR-RS-018 | REGS | IF-035 | [MSAppAccepted] | DIP | For Same day events REGS will process the appointments on the day and sends IF-035 to the DIP | http 202 response from DIP | Y
|  |  |  | 100 | MHHS-BR-RS-020
MHHS-BR-RS-023
|  | 24 | BP002 | 87 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, SMSI | For Same day events REGS will process the appointments on the day and DIP sends PUB-035 to the Supplier & Smart Metering Service. |  | N
100
|  | 25 | BP002 | 95 | MHHS-BR-SU-010 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Registration Service Notification on Appointment Status and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 26 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | SMSI | SMS (Incoming) receives PUB-035. | Metering Service receives PUB-035 with details of Registration Service Notification on Appointment Status and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Data Service - Raise Appointment -Import | 27 | BP003 | 10 | MHHS-BR-SU-019 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP for a DS Appointment for Import MPAN. | http 202 response from DIP | Y
|  |  |  | 20 | MHHS-BR-SU-020
MHHS-BR-SU-021
|  | 28 | BP003 | 10 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment for Import MPAN. |  | N
20
|  | 29 | BP003 | 40 | MHHS-BR-RS-043 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier for Import MPAN. | REGS receives PUB-031 with details of Metering Service Appointment and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MHHS-BR-RS-044
|  | 30 | BP003 | 45 | MHHS-BR-RS-045 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP | http 202 response from DIP | Y
|  | 31 | BP003 | 45 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the Supplier for Import MPAN. |  | N
|  | 32 | BP003 | 55 | MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance for Import MPAN. | Supplier receives PUB-032 with details of Data Service Appointment initial response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 33 | BP003 | 60 | MHHS-BR-RS-049 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to the DIP | http 202 response from DIP | Y
MHHS-BR-RS-048.1
|  | 34 | BP003 | 60 |  | DIP | PUB-033 | [DSAppSPRequest] | SDSI | DIP sends PUB-033 to the SDS (Incoming) for Import MPAN. |  | N
|  | 35 | BP003 | 220 | MHHS-BR-DS-007 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | SDS (Incoming) receives PUB-033 from the DIP for Import MPAN. | Data Service receives PUB-033 with details of Data Service Appointment service provider response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 36 | BP003 | 221 | MHHS-BR-DS-008 | SDSI | IF-034 | [DSAppSPResponse] | DIP | SDS (Incoming) sends IF-034 to the DIP | http 202 response from DIP | Y
|  | 37 | BP003 | 221 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS for Import MPAN. |  | N
|  | 38 | BP003 | 85 | MHHS-BR-RS-050 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment REGS Holds in appointment queue until appointment date reached for Import MPAN. | REGS receives PUB-034 with details of Data Service Appointment service provider response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  |  |  | 100 | MHHS-BR-RS-051
|  |  |  | 101 | MHHS-BR-RS-054
|  |  |  | 120 | MHHS-BR-RS-056
MHHS-BR-RS-057
|  | 39 | BP003 | 85 | MHHS-BR-RS-050 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to the DIP | http 202 response from DIP | Y
|  |  |  | 90 | MHHS-BR-RS-051
MHHS-BR-RS-052
|  | 40 | BP003 | 85 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC, SDSI | DIP sends PUB-035 to the Supplier & Data Service for Import MPAN. |  | N
90
|  | 41 | BP003 | 95 | MHHS-BR-SU-024 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035 for Import MPAN. | Supplier receives PUB-035 with details of Registration Service Notification on Appointment Status and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 42 | BP004 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | SDSI | Smart Data Service (Incoming) receives PUB-035 for Import MPAN.. | Data Service receives PUB-035 with details of Registration Service Notification on Appointment Status and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| New Connection NEW MPAN - COS Secured Notification | 43 | BP001 | 100 | MHHS-BR-SU-003 | CSS | CSS02370 | N/A | SUPC | Supplier receives CSS02370 Status Change Notification for Import MPAN |  | Y
MHHS-BR-SU-048
|  | 44 | BP001 | 180 | MHHS BR EES 016.4 | CSS | CSS02460 | N/A | EES | EES receives CSS02460 Status Change Sync for Import MPAN |  | Y
|  | 45 | BP001 | 130 | MHHS-BR-RS-007 | CSS | CSS02860 | N/A | REGS | REGS receives CSS02860 Status Change Sync for Import MPAN. |  | Y
MHHS-BR-RS-094
| Change of Supplier Notification (IF-001) - Import MPAN | 46 | BP001 | 130 | MHHS-BR-RS-008 | REGS | IF-001 | [InitialRegistration] | DIP | REGS sends IF-001 to DIP for Import MPAN | http 202 response from DIP | Y
MHHS-BR-RS-096
|  | 47 | BP001 | 135 | MHHS-BR-RS-008 | DIP | PUB-001 | [InitialRegistration] | SUPC, SUPL, LDSO & MDS | DIP sends PUB-001 CoS Notification to SUPC, SUPL, LDSO & MDS |  | N
150
|  | 48 | BP001 | 165 | MHHS-BR-SU-004 | DIP | PUB-001 | [InitialRegistration] | SUPC | Supplier receives PUB-001 - CoS Notification | Supplier receives PUB-001 for Import MPAN with details of Initial Registration confirmation and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MHHS-BR-SU-049
|  | 49 | BP001 | 165 | MHHS-BR-SU-004 | DIP | PUB-001 | [InitialRegistration] | SUPL | Supplier (Linked) receives PUB-001 - CoS Notification | Supplier (Linked) receives PUB-001 for Import MPAN with details of Initial Registration confirmation and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MHHS-BR-SU-049
|  | 50 | BP001 | 160 | MHHS-BR-LD-001 | DIP | PUB-001 | [InitialRegistration] | LDSO | LDSO receives PUB-001 - CoS Notification | LDSO receives PUB-001 with details of Initial Registration confirmation for Import MPAN and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MHHS-BR-LD-012
|  | 51 | BP001 | 155 | Central settlements | DIP | PUB-001 | [InitialRegistration] | MDS | MDS receives PUB-001 - CoS Notification | MDS receives PUB-001 with details of Initial Registration confirmation for Import MPAN and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering Service - Accept Appointment (Import) | 52 | BP002 | 240 | MHHS-BR-RS-033 | REGS | IF-036 | [MSAppActive] | DIP | The Registration Service will issue confirmation to the Metering Service their appointment is now active REGS sends IF-036 to DIP | http 202 response from DIP | Y
REGS dependency on Secured Active batch as a step before this.
|  | 53 | BP002 | 240 |  | DIP | PUB-036 | [MSAppActive] | SMSI, SUPC,LDSO,SDSI & EES | The Registration Service will issue confirmation to the Metering Service their appointment is now active. DIP sends PUB-036 to Metering Service (Incoming), Supplier, LDSO, Data Service (Incoming) and EES | REGS dependency on Secured Active batch as a step before this. | N
|  | 54 | BP002 | 260 | MHHS-BR-SU-013 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 with details of Active Metering Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 55 | BP002 | 280 | MHHS-BR-LD-003 | DIP | PUB-036 | [MSAppActive] | LDSO | LDSO receives PUB-036 | LDSO receives PUB-036 with details of Active Metering Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 56 | BP002 | 270 | MHHS-BR-DS-002 | DIP | PUB-036 | [MSAppActive] | SDSI | SDSI receives PUB-036 | Data Service receives PUB-036 with details of Active Metering Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
MHHS-BR-DS-003
|  | 57 | BP002 | 283 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 with details of Active Metering Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Data Service - Accept Appointment for Import MPAN | 58 | BP003 | 250 | MHHS-BR-RS-067 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 202 response from DIP | Y
REGS dependency on Secured Active batch as a step before this.
|  | 59 | BP003 | 250 |  | DIP | PUB-036 | [DSAppActive] | SUPC, LDSO, EES, SDSI, SMSI & MDS | DIP sends PUB-036 to SUPC, LDSO, EES, SDSI and MDS confirming Appointment for Import MPAN | REGS dependency on Secured Active batch as a step before this. | N
|  | 60 | BP003 | 260 | MHHS-BR-SU-027 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 for Import MPAN | Supplier receives PUB-036 for Import MPAN with details of Active Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 61 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-036 | [DSAppActive] | LDSO | LDSO receives PUB-036 for Import MPAN | LDSO receives PUB-036 for Import MPAN with details of Active Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 62 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 for Import MPAN | EES receives PUB-036 for Import MPAN with details of Active Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 63 | BP003 | 284 (TBC) | TBC | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 for Import MPAN | MDS receives PUB-036 for Import MPAN with details of Active Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 64 | BP003 | 340 | MHHS-BR-DS-013 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 for Import MPAN | Data Service receives PUB-036 for Import MPAN with details of Active Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 65 | BP003 | 281 | MHHS-BR-MS-030 | DIP | PUB-036 | [DSAppActive] | SMSI | SMS (Incoming) receives PUB-036 for Import MPAN | Meter Service receives PUB-036 for Import MPAN with details of Active Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Update RMP status | 66 | N/A | N/A | N/A | REGS | CSS07000 | N/A | CSS | REGS sends CSS07000 to CSS To update RMP Status to Operational (Import MPAN) |  | Y
- Start (Import)
|  | 67 | N/A | N/A | N/A | REGS | IF-050 | [MPStatusChange] | DIP | Meter Point status is updated in REGS and IF-050 is sent to DIP (Import MPAN) | http 202 response from DIP | Y
|  | 68 | N/A | N/A | N/A | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES |  | N
| Update RMP status | 69 | BP001 | 42 | MHHS-BR-EES-016.3 | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050 and updates its data | EES receives PUB-050 with details of Meter Point Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| - End (Import) |  |  | 43
| Change of Metering - MS accepts request to Install a Meter | 70 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142 | N/A | SMSC | Supplier issues out D0142 to Metering service via the DTN or the Service Provider Portal requesting Meter installation works to be taken out |  | Y
|  | 71 | BP009 | 30 | MHHS-BR-MS-051 | SMSC | D0142 | N/A | N/A | Metering Service (Currently Appointed) receives D0142 via the DTN or the Service Provider Portal accepts and Metering will complete the required metering works requested by Supplier and update their systems to reflect the changes made once works are complete this will move to change of energisation. |  | Y
|  |  |  | 40 | MHHS-BR-MS-056
| Change of Energisation - Start | 72 | BP008 | 45 | MHHS-BR-MS-057 | SMSC | IF-007 | [EnergisationStatusChange] | DIP | As part of the meter install process energisation starts at this point SMSC sends IF-007 to the DIP for Import MPAN | http 202 response from DIP | Y
|  |  |  | 80 | MHHS-BR-MS-049
85
|  | 73 | BP008 | 80 |  | DIP | PUB-007 | [EnergisationStatusChange] | REGS | DIP sends PUB-007 to the REGS. |  | N
85
|  | 74 | BP008 | 105 | MHHS-BR-RS-104 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | REGS receives PUB-007. | REGS receives PUB-007 with details of Energisation Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  |  |  | 110 | MHHS-BR-RS-105
|  | 75 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to DIP For Import MPAN | http 202 response from DIP | Y
|  | 76 | BP008 | 115 |  | DIP | PUB-008 | [EnergisationStatusChange] | SMSC, SUPC, LDSO, SDSC, MDS and EES | DIP sends PUB-008 to SMSC, SUPC, LDSO, SDSC, MDS and EES. Once energisation process is complete it continues with the meter install process |  | N
|  | 77 | BP008 | 140 | MHHS-BR-MS-050 | DIP | PUB-008 | [EnergisationStatusChange] | SMSC | Metering Service (Currently Appointed) receives PUB-008 | Metering Service receives PUB-007 with details of Energisation Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 78 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | SDSC | SDS (Current) receives PUB-008. | Data Service receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 79 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 80 | BP008 | 160 | central settlements | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008. | MDS receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 81 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 82 | BP008 | 175 | MHHS-BR-SU-064 | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | Supplier receives PUB-008. | Supplier receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. Now that change of energisation has taken place the metering install process continues. | Y
|  | 83 | BP009 | 55 | MHHS-BR-MS-058 | SMSC | IF-005 | [MeterInstall] | DIP | SMSC sends IF-005 to the DIP for Import MPAN | http 202 response from DIP | Y
MHHS-BR-MS-058.3
|  | 84 | BP009 | 55 |  | DIP | PUB-005 | [MeterInstall] | REGS | DIP sends PUB-005 to the REGS |  | N
|  | 85 | BP009 | 95 | MHHS-BR-RS-108 | DIP | PUB-005 | [MeterInstall] | REGS | REGS receives PUB-005 and updates Metering and new registration data passes validation rules will update their systems with the new metering details and update all relevant systems. | REGS receives PUB-005 Updating Meter Install and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  |  |  | 100 | MHHS-BR-RS-108.1
|  |  |  | 125 | MHHS-BR-RS-109
|  | 86 | BP009 | 140 | MHHS-BR-RS-111 | REGS | IF-006 | [MeterInstall] | DIP | REGS sends IF-006 to the DIP for Import MPAN | http 202 response from DIP | Y
|  | 87 | BP009 | 140 |  | DIP | PUB-006 | [MeterInstall] | SUPC, LDSO, EES, SMSC & SDSC | DIP sends PUB-006 to the SUPC, LDSO, EES, SMSC & SDSC. |  | N
|  | 88 | BP009 | 200 | MHHS-BR-SU-069 | DIP | PUB-006 | [MeterInstall] | SUPC | Supplier receives PUB-006 | Supplier receives PUB-006 Notifying Meter Technical information of the back of Meter Install and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 89 | BP009 | 195 | MHHS-BR-LD-030 | DIP | PUB-006 | [MeterInstall] | LDSO | LDSO receives PUB-006 | LDSO receives PUB-006 Notifying Meter Technical information of the back of Meter Install and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 90 | BP009 | 186 | MHHS-BR-EES-016.3 | DIP | PUB-006 | [MeterInstall] | EES | EES receives PUB-006 | EES receives PUB-006 Notifying Meter Technical information of the back of Meter Install and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 91 | BP009 | 160 | MHHS-BR-MS-073.1 | DIP | PUB-006 | [MeterInstall] | SMSC | Metering Service (Currently Appointed) receives PUB-006 | Metering Service receives PUB-006 Notifying Meter Technical information of the back of Meter Install and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  |  |  | 170 | MHHS-BR-MS-059
|  | 92 | BP009 | 185 | MHHS-BR-DS-117 | DIP | PUB-006 | [MeterInstall] | SDSC | SDS (Current) receives PUB-006 | Data Service receives PUB-006 Notifying Meter Technical information of the back of Meter Install and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 93 | BP009 | 60 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingInstl] | DIP | SMSC sends IF-041 to the DIP for Import MPAN | http 202 response from DIP | Y
|  | 94 | BP009 | 60 |  | DIP | PUB-041 | [ReadingInstl] | SUPC, LDSO & SDSC | DIP sends PUB-041 to the SUPC, LDSO & SDSC. |  | N
|  | 95 | BP009 | 220 | MHHS-BR-SU-072 | DIP | PUB-041 | [ReadingInstl] | SUPC | Supplier receives PUB-041 and reconciles Metering/Reading information. | Supplier receives PUB-041 Meter Install Read and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  |  |  | 215 | MHHS-BR-SU-071
|  | 96 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingInstl] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 Meter Install Read and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering - MS completes Installation of the Meter | 97 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingInstl] | SDSC | SDS (Current) receives PUB-041. | Data Service receives PUB-041 Meter Install Read and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| CSS/DCC Updates - Start | 98 | BP003A | 20 | MHHS-BR-RS-078 | REGS | ERDA CSS00200 (Issue MDR Request) | N/A | CSS | REGS issues ERDA CSS00200 for Import (Issue MDR Request) to CSS which outputs CSS07000 (Response) |  | Y
MHHS-BR-RS-078.1
MHHS-BR-RS-078.2
|  | 99 | N/A | N/A | Existing requirement- REC Schedule 28 | REGS | ERDA CSS00200 (Issue MS appointment notification ) | N/A | CSS | REGS issues ERDA CSS00200 for Import (Issue MS appointment notification) to CSS which outputs CSS07000 (Response) |  | Y
|  | 100 | BP003A | 30 | CSS | CSS | DSP of MDR appointment | N/A | DCC | CSS calls CSS-DSP Interface to inform DSP of MDR appointment |  | Y
40
|  | 101 | N/A | N/A | CSS | CSS | DSP of MS appointment (CSS03200) | N/A | DCC | CSS calls CSS-DSP Interface to inform DSP of MS appointment |  | Y
|  | 102 | BP003A | 50 | DCC | DCC | DSP updates MDR appointment | N/A | CSS | DSP updates MDR appointment, and confirms update to CSS over CSS-DSP Interface for Import MPAN |  | Y
60
|  | 103 | BP003A | 80 | MHHS-BR-RS-079 | CSS | CSS07000 (Response) | N/A | REGS | REGS receives CSS07000 (Response) from CSS for Import |  | Y
|  | 104 | BP003A | 90 | MHHS-BR-RS-080 | REGS | IF-035 | [DCC-MDROutcome] | DIP | REGS sends IF-035 - (DCC MDR Outcome) to DIP for Import MPAN | http 202 response from DIP | Y
|  | 105 | BP003A | 100 |  | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | DIP sends PUB-035 to SDSI |  | N
110
| CSS/DCC Updates - Completed | 106 | BP003A | 120 | MHHS-BR-DS-042.1 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | SDS (Incoming) receives PUB-035 for Import MPAN - (DCC MDR Outcome) and manages Service Provider Update (BAU). | SDS incoming receives PUB-035 for Import MPAN with details of DCC MDR outcome and confirms (DCC MDR Outcome) and manages Service Provider Update (BAU) successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Scheduled Meter Access Request for Import MPAN - Start | 107 | BP004A | 60 | MHHS-BR-DS-041 | SDSI | N/A | N/A | MDR | Smart Data Service issues scheduled meter access request reflective of the Customer Consent provided to the MDR for Import MPAN | SDS must request meter data retrieval in line with the customers stated consent preference as provided by the Registration Service for Import MPAN | Y
|  |  |  | 65 | MHHS-BR-DS-042
|  | 108 | BP004A | 70 | MDR | MDR | DCC Service Request SRV 5.1 | N/A | DCC | Send Required Service Request(s) to DCC | SDS will send the appropriate service requests to DCC via the MDR in order to establish a schedule to recover the appropriate data from the meter. | Y
|  | 109 | BP004A | 80 | MDR | DCC | DCC Service Request SRV 5.1 | N/A | DCC | DCC receives and validates Service Request(s) |  | Y
| Scheduled Meter Access Request for Import MPAN - Completed | 110 | BP004A | 81 | MDR | DCC | DCC Service Request SRV 5.1 | N/A | DCC | DCC accepts Service Request(s) | Accepted service requests will be scheduled for Import MPAN | Y