## Control Sheet
MHHS-DEL1140 Programme Milestone Register
The purpose of this document is to provide a register of the activities in the Programme Re-plan that have been assigned a milestone status and therefore, will be reported against and managed via programme governance.
Document Classification: | Public
Version Control
Version | Prepared by | Publication / Baseline Date | Comment
v1.0 | Joe Deal | 2022-08-01 | Published for first round of industry consultation
v2.0 | Joe Deal | 2022-09-12 | Published for second round of industry consultation
v3.0 | Joe Deal | 2022-12-14 | Published for third round of industry consultation
v4.0 | Becca Fox | 2023-04-05 | Published for industry consultation of CR
v4.1 | Becca Fox | 2023-04-14 | Updates to the DEpencies tab
v4.2 | Becca Fox | 2023-05-11 | Updates to the milestone register post CR022 impact assessments received
v5.0 | Becca Fox | 2023-05-26 | Milestone register baselined for approval of CR022 (replan)
v5.1 | Becca Fox | 2023-05-27 | Updates in line with programme plan version 5.1
v5.2 | Becca Fox | 2023-07-04 | Update to Regulatory T2 milestones to reflect CCAG approval of changes on 28/6/23
v5.3 | Lewis Hall | 2023-07-19 | No update - version numbering updated to align to Programme Plan (v5.3)
v5.4 | Chris Holden | 2023-08-02 | T3-MI-0021 - Baseline date changed from 31/8/23 to 20/9/23 following TMAG approval on 19/07/23 T3-DB-0039 - Forecast changed from 15/12/23 to 3/11/23 and name changed from Interim Release 6 to 5 - awaiting approval to formally change from TMAG T2-RE-0400 - Changed date from 13/11/23 to 22/11/2 after approval from CCAG on 28/6/23 Dates to the below milestones have been changed in this document to align to the programme plan and correct misalignment between planning artefacts. Please note no changes have taken plave to baselime dates communicated in the Programme plan: T3-QU-0062/63/64/65/66/68 / T3-DB-0089/91/93 / T2-RE-0350 T3-TE-0073-78 Added T3-TE-0079-82 Added
v5.5 | Chris Holden | 2023-08-16 | T3-TE-0083 to 0103 - New milestones added T3-DB-0098 to 1002 - New milestones added T3-MI-0024 to 0032 - New milestones added T3-MI-0018 & 0019 Milestones removed
v5.6 | Chris Holden | 2023-08-30 | T3-TE-0104 to 0105 - New milestones added
v5.7 | Chris Holden | 2023-09-13 | No Change
v5.8 | Chris Holden | 2023-09-27 | New Milestones Added: T3-TE-0129,T3-TE-0106,T3-TE-0107,T3-TE-0108,T3-TE-0124,T3-TE-0109,T3-TE-0131,T3-TE-0125,T3-TE-0126,T3-TE-0130,T3-TE-0111,T3-TE-0110,T3-TE-0167,T3-TE-0172,T3-TE-0177,T3-TE-0127,T3-TE-0134,T3-TE-0112,T3-TE-0113,T3-TE-0135,T3-TE-0136,T3-TE-0169,T3-TE-0173,T3-TE-0174,T3-TE-0128,T3-TE-0132,T3-TE-0168,T3-TE-0178,T3-TE-0179,T3-TE-0114,T3-TE-0119,T3-TE-0133,T3-TE-0137,T3-TE-0120,T3-TE-0121,T3-TE-0138,T3-TE-0170,T3-TE-0175,T3-TE-0180,T3-TE-0115,T3-TE-0171,T3-TE-0176,T3-TE-0181,T3-TE-0122,T3-TE-0139,T3-TE-0140,T3-TE-0141,T3-TE-0123,T3-TE-0116,T3-TE-0117,T3-TE-0143,T3-TE-0118,T3-TE-0142,T3-TE-0145,T3-TE-0147,T3-TE-0144,T3-TE-0146,T3-TE-0148,T3-TE-0151,T3-TE-0149,T3-TE-0150,T3-TE-0153,T3-TE-0155,T3-TE-0159,T3-TE-0152,T3-TE-0161,T3-TE-0163,T3-TE-0154,T3-TE-0156,T3-TE-0157,T3-TE-0160,T3-TE-0162,T3-TE-0164,T3-TE-0158,T3-TE-0165,T3-TE-0166 Milestones Removed: T3-DB-0080,T3-DB-0080,T3-DB-0082,T3-DB-0084,T3-DB-0092,T3-DB-0092,T3-DB-0090,T3-DB-0086,T3-DB-0094,T3-DB-0094 Milestone Name Changes: T3-DB-0048,T3-DB-0050,T3-DB-0066,T3-DB-0093,T3-DB-0089,T3-DB-0087 Milestone Name and Date Changes: T3-DB-0046,T3-DB-0054,T3-DB-0052,T3-DB-0037,T3-DB-0062,T3-DB-0011,T3-DB-0064,T3-DB-0060,T3-DB-0025,T3-DB-0072,T3-DB-0031,T3-DB-0068,T3-DB-0091,T3-DB-0074,T3-DB-0078,T3-DB-0024 Milestone Date Changes: T3-TE-0096,T3-TE-0084,T3-MI-0021
v5.9 | Chris Holden | 2023-10-11 | Milestones changed from T2 to T3: T3-RE-0300,T3-RE-0350,T3-RE-0400,T3-RE-0450,T3-RE-0500,T3-RE-0550
v5.10 | Chris Holden | 2023-10-25 | Milestones Removed: T3-DB-0013,T3-DB-0015 Milestone Date Changes: T3-TE-0070,T3-TE-0015,T3-TE-0084,T3-DB-0060,T3-DB-0025,T3-DB-0177,T3-DB-0178,T3-DB-0179,T3-MI-0021,T3-QU-0066,T3-TE-0028,T3-DB-0180,T3-TE-0102,T3-DB-0181,T3-TE-0030,T3-TE-0071,T3-TE-0036,T3-TE-0037,T3-TE-0025,T2-TE-0750 Milestone Name Changes: T3-DB-0157, T3-DB-0165
v5.11 | Chris Holden | 2023-11-08 | No Change
v5.12 | Chris Holden | 2023-11-22 | Milestone Date Changes: T3-TE-0096, T3-TE-0095, T3-MI-0022
v5.13 | Chris Holden | 2023-12-06 | No Change
v5.14 | Chris Holden | 2023-12-20 | Milestone Date Changes: T3-DB-0098,T3-DB-0099, T3-BC-0010 Milestones Removed: T3-DB-0100, T3-DB-0101, T3-DB-0102, New Milestones Added: T3-TE-0106, T3-TE-0107, T3-TE-0108, T3-TE-0109, T3-DB-0182, T3-DB-0183 Milestone Name Change: T3-TE-0015, T3-TE-0070, T3-TE-0079, T3-TE-0082 Milestone Name and Date Change: T3-TE-0080, T3-TE-0081
v5.15 | Chris Holden | 2024-01-10 | No Change
v5.16 | Chris Holden | 2024-01-24 | Milestones Removed: T3-TE-0027 Milestone Date Change: T3-BC-0010
v5.17 | Chris Holden | 2024-02-07 | Milestone Date and Level Change: T3-MI-0500
v5.18 | Chris Holden | 2024-02-21 | New Milestones Added: T3-TE-0110, T3-TE-0111, T3-TE-0112, T3-TE-0113 Milestone Date Changes: T3-TE-0092, T3-TE-0103, T3-TE-0079, T3-TE-0026, T3-TE-0028, T3-TE-0036 Milestones Removed: T3-DB-0024, T3-DB-0118, T3-DB-0031, T3-DB-0071, T3-DB-0025
v5.19 | Chris Holden | 2024-03-06 | Milestone Name and Date Change: T3-MI-0023 New Milestones Added: T3-MI-0032, T3-MI-0033
v5.20 | Chris Holden | 2024-03-20 | Milestone Date Change: T3-TE-0092
v5.21 | Chris Holden | 2024-04-03 | Milestone Name and Date Change: T3-TE-0093; T3-TE-0091
v5.22 | Chris Holden | 2024-04-17 | Milestone Date Change: T3-TE-0033, T3-TE-0092, T3-TE-0080 Milestones Removed: T3-TE-0028, T3-TE-0030, T3-TE-0036, T3-TE-0037 Milestone Name Change: T3-TE-0091 New Milestone Added: T3-TE-0114, T3-TE-0115, T3-TE-0116, T3-TE-0117, T3-TE-0118, T3-TE-0119, T3-TE-0120
v5.23 | Chris Holden | 2024-05-01 | No Change
v5.24 | Chris Holden | 2024-05-15 | Milestone Date Change: T3-MI-0023, T3-MI-0033, T3-QU-0011, T3-QU-0007, T3-QU-0008, T3-QU-0009 Milestones Removed: T3-TE-0039, T2-QU-0350, T2-QU-400, T2-QU-0450, T3-QU-0013, T3-QU-0014, T3-QU-0015, T3-QU-0018, T3-QU-0019, T3-QU-0022, T3-QU-0023, T3-QU-0026, T3-QU-0029, T3-QU-0032, T3-QU-0035, T3-QU-0036, T3-QU-0037, T3-QU-0040, T3-QU-0041, T3-QU-0042, T3-QU-0045, T3-QU-0046, T3-QU-0047, T3-QU-0048, T3-QU-0049, T3-QU-0050, T3-QU-0051, T3-QU-0052, T3-QU-0053, T3-QU-0058, T3-QU-0059, T3-QU-0060 New Milestones Added: T2-QU-0550, T3-QU-0069 - T3-QU-0109 Milestone Name and Date Change: T2-QU-0150, T2-QU-0200, T2-QU-0250, T2-QU-0300, T3-QU-0063, T3-QU-0064, T3-QU-0065, T3-QU-0066, T3-QU-0017, T3-QU-0027, T3-QU-0028, T3-QU-0054, T3-QU-0016, T3-QU-0021, T3-QU-0020, T3-QU-0033, T3-QU-0034, T3-QU-0055, T3-QU-0025, T3-QU-0024, T3-QU-0038, T3-QU-0039, T3-QU-0056, T3-QU-0030, T3-QU-0031, T3-QU-0043, T3-QU-0044, T3-QU-0057, T3-QU-0110 - T3-QU-0118
v5.25 | Chris Holden | 2024-05-29 | Milestone Date Change: T3-QU-0065 Milestones added in v5.24 as 'subject to approval' were approved at QAG on 23/05/24
v5.26 | Chris Holden | 2024-06-12 | Milestone Date Change: T3-MI-0032, T3-MI-0500
v5.27 | Chris Holden | 2024-06-26 | Milestone Date Change: T3-TE-0059, T3-QU-0110, T3-QU-0075, T3-QU-0081, T3-QU-0065 New Milestones Added: T3-MI-0034, T3-MI-0035, T3-MI-0036, T3-QU-0119, T3-QU-0120, T3-QU-0121, T3-QU-0122, T3-QU-0123 Milestone Name and Date Change: T3-QU-0077 Milestone Name Change: T3-TE-0035
v5.28 | Chris Holden | 2024-07-10 | New Miletone: T3-QU-0124 Milestone Date Change: T3-TE-0067, T3-TE-0048, T3-TE-0049
v5.29 | Chris Holden | 2024-07-24 | Milestone Date Change: T3-TE-0043, T3-QU-0110, T3-QU-0071, T3-QU-0073, T3-QU-0077 Milestone Name and Date Change: T3-QU-0008 Milestones Removed: T3-QU-0082, T3-QU-0068, T3-QU-0062
v5.30 | Chris Holden | 2024-08-07 | Milestone Name and Date Change: T3-MI-0017 New Milestone Added: T3-MI-0037, T3-MI-0038, T3-MI-0039 Milestone Date Change: T3-TE-0116, T3-TE-0117, T3-TE-0119
v5.31 | Chris Holden |  | Milestone Name and Date Change: T2-RE-0600 Milestones Removed: T3-TE-0041, T3-QU-0123
v6.0 | Will Rosson | 2024-09-20 | Forecast Milestone date changes in line with Programme CR055 where M10 (T1-TE-1000) is delayed and the subsequent milestones have moved to reflect this. T1 Milestones Changed: T1-TE-2000, T1-TE-1000, T1-MI-3000, T1-MI-4000, T1-MI-2000, T1-MI-5000, T1-MI-6000, T1-EL-1000
v6.1 | Will Rosson | 2024-10-15 | Forecast Milestone date changes following the CR055 Impact Assessment window and feedback received from Industry.
v6.11 | Will Rosson | 2024-11-13
v6.12 | Will Rosson | 2024-10-31
v6.13 | Will Rosson | 2024-11-27 | Key updates made in version 6.13 include, but are not limited to:
-Non-Functional Preparation tasks updated to reflect the approach agreed at the NFTWG.
-Operations Manual plan expanded.
v6.14 | Will Rosson | 2024-12-11 | Key updates made in version 6.14 include, but are not limited: -Included IR 8.6 and 8.7 -Updated proposed dates for the Test Case Rationalisation, for agreement by SITAG -Updated proposed dates for Regression testing, for agreement by SITAG -Restructured the All Non-SIT LDSOs Qualification Testing plan, but no change to dates, for agreement with QAG -Updated the Migration plan, which is due to be discussed and agreed at January MCAG.
v6.15 | Will Rosson | 2024-12-20 | Key updates made in version 6.15 include, but are not limited: -Set placeholder dates for IR8.7, which are subject to further updates -Updated PP PIT submission figures -Included the Settlement testing extension after SITAG approved it on 18/12/24 -Updated the Operational and Non-Functional testing and preparation activities to reflect the Settlement testing extension -Made some corrections to the E2E Sandbox dates, although further refinement is required which will be done in early January -Restructured the 'All Non-SIT LDSOs Qualification Testing' section of the plan as per the decision taken by QAG on 19/12/24.
v6.16 | Will Rosson / Will Miller | 2025-01-15 | Key updates made in version 6.16 include, but are not limited: -Confirmed IR8.7 dates -Updated migration and functional rationalisations dates -Updated Operational and NF RTTM dates -Updated Operational and NF Overarching Readiness Report dates -Updated Regression dates
v6.17 | Will Rosson | 2025-01-29 | The plan shows the latest progress of the Programme's activities. Some activities have been amended while other have been newly included, these changes are summarised below: -Expansion of the Knowledge Transfer plan, including new FreshDesk and iServer activities; -Expansion of the Operational PP PIT section, to allow for the tracking of Theme 3 (Batch 1) and Themes 1, 2 and 3 (Batch 2) figures, separately; -Re-baselining of the Rationalisation timeframes in line with the update given to SITAG, this included an update to milestone T3-TE-0141, which was approved by SITAG; -Re-baselining of the Overarching Readiness Report for Non-Functional and Operational plans, as per the update given to SITAG. New milestones created as part of this - T3-TE-0190, T3-TE-0191, T3-TE-0192, and T3-TE-0193; -Re-baselining the Regression timeframes in line with the update given to SITAG, this includes updates to milestones T3-TE-0123 and T3-TE-0122, which were both approved by SITAG; -Inclusion of activities to represent the SIT Scope Traceability doc development and approval; -An updated Migration plan, which was approved by MCAG and included changes to milestones T3-MI-0017 and the creating of new milestones which are T3-MI-0041, T2-MI-7000, T3-MI-0043, T3-MI-7500, T2-MI-8000, T3-MI-0044, T3-MI-0045, and T2-MI-0500; -Correction of the Advanced Migration and Non-Smart Migration end dates, so they line up with M15.
v6.18 | Will Miller | 2025-02-12 | Key updates made in version 6.18 include, but are not limited: -Included new activity to represent IR 8.8 -Minor update to the Design Handover activities -Minor restructuring of the SIT Operational and Non-Functional plan, so that the sequence of activities was more in line with the delivery approach being taken. The activities moved did not have forecasted or baselined dates changed, nor were their titles amended; -Added activities for the Theme 3 (Batch 2) Supplementary Test Cases, which were not approved at December SITAG. -Included activities for the Operational Theme 1, 2 and 3 (Batch 2) DITL; -Included activities for the Operational Theme 1, 2 and 3 (Batch 2) RTTM; -Expanded the Helix Settlement Assurance Testing (SAT) section to include new activities. Existing Helix SAT activities have been struck through and will be removed in version 6.19; -Updated the M10 Checkpoint milestone (T3-MI-0040) date so it takes place on 02/04/25 as per the feedback from Ofgem and an action from the IPA. Also included new activities as part of the Checkpoint, as per the presentation given to FTIG on 31/01/25; -Updated the data load dates for Waves 1 - 4; -Added PAB dates -Expanded the Migration plan, including new activities for Consultation 4, the Migration Schedule, Supplier Commission and MCC; -Included the Migration Sprints, which will replace 'UMS / Advanced Migration' and 'Smart / Non-Smart Migration' -Updated the Readiness Assessment 5 / 6 activity baseline dates so it doesn't take place across Easter, as per a decision approved by PSG on Wednesday 05/02/25.
v6.19 | Will Rosson / Will Miller | 2025-02-26 | Key updates in version 6.19 include, but are not limited to Amended the Regression Core Test Pack plan, to include new activities and forecasted dates. SITAG will be asked to approve re-baselining T3-TE-0122 and associated activities at their March meeting. Minor amendment to activity 'Non-SIT LDSO Participants submit Final QAD' so that it has the correct dependencies. Added new activity and updated dates for both 'ESME ID' and 'Meter Location and Number of Displayed Register Digits'. Added T2-MI-8500 'Non-SIT Participants Migration Start', so there is still an activity to show the start of Non-SIT Participant migration after replacing the migration waves. Minor amendments to the 'Cutover Governance M11' timings. MCAG will be asked to re-baseline T3-MI-0036 and associated activity at their March meeting. Minor amendments to the 'Early Life Support Model' timings. MCAG will be asked to re-baseline T3-MI-0033 and associated activity at their March meeting.
v6.20 | Will Rosson / Will Miller | 2025-03-12 | Key updates in version 6.20 include, but are not limited to: -Minor amendment to the 'SIT Operational Execution Model' plan, which will now be socialised with participants directly, rather than via SITWG. -Update to the Regression Core Test Pack plan, although 'T3-TE-0122 SIT Regression Approval' has not been affected. -Update to the SIT Scope Traceability timeframes. The document will now be going to April SITAG. -Expanded the 'SIT-A Settlement Testing' plan, to include a more detailed breakdown of activities, but no date changes. -Updated the 'Regression Testing' activities to align with the approach which will be taken. -Updated the 'E2E Sandbox Guidance' and 'E2E Sandbox Test Data Approach & Plan' timeframes to align with the presentation given to QWG on 11/03/25. -Corrected the 'Migration Sprint 3' dates.
v6.21 | Will Rosson / Will Miller | 2025-03-26 | Key updates in version 6.21 include, but are not limited to: - Added activity to represent IR 8.9 and 8.10 - Minor amendments to the Regression plan, but T3-TE-0122 unchanged - Updated name of T3-TE-0040 so it now covers both NFT Theme 2 & 3 - New milestones created for UIT Environment and Sandbox Testing: T3-QU-0125, T3-QU-0126, T3-QU-0127, T3-QU-0128, T3-QU-0129 - New milestones created for M8 Code Change Preperation: T3-RE-0600, T3-RE-0650, T3-RE-0700, T3-RE-0750, T3-RE-0800, T3-RE-0850, T3-RE-0900, T3-RE-0950. T3-RE-1000, T3-RE-1050, T3-RE-1100 -Minor amendment to T2-RE-0650 - Code Changes Delivered (M8) as proposed by CR060 and agreed by CCAG on 26/03/25. - Statuses of non-SIT LDSO QT updated and some forecast finished moved, but T3-QU-0010 unchanged - Activities added to Cutover Governance M10. - T3-MI-0036 rebaselined.
v6.22 | Will Rosson / Will Miller | 2025-04-09 | Key updates in version 6.22 include, but are not limited to: - Updated the ordering of SIT Operational Testing, no impact to testing completion date. - Added T3-MI-0046 (M10 Checkpoint 2 Complete) in line with M10 checkpoint approach shared at PSG 02/04. - T3-MI-0033 updated in line with new MCAG April date. - T3-QU-0129 updated in line with regression end dates. - Added additional activity for Connection Type and Meter Type activity. - M10 acceptance criteria listed in plan.
v6.23 | Will Rosson / Will Miller | 2025-04-23 | Key updates in version 6.23 include, but are not limited to: - T3-TE-0050 proposed dates adjusted in line with SIT Operational testing end, decision to be made at May SITAG. - T3-QU-0128 proposed dates adjusted to support early SIT Exit. - T3-QU-0079 updated in line with test end activity. - Development of Cutover Plan requirements with Participants updated with more detailed activities. - Regulatory Governance Incentives Implemented activity updated in line with CR055. - Non-SIT LDSO QT Closure activity updated to reflect emergent post-QT window testing contingency requirement.
v6.24 | Will Rosson / Will Miller | 2025-05-07 | Key updates in version 6.24 include, but are not limited to: -The proposed SIT Exit reporting approach, which was endorsed by SITWG on 01/05 and is going to SITAG on 21/05 for approval, has been added as 'Proposed' activity. As part of this, the forecast dates for T2-TE-0900 & T2-TE-0950 have been moved, as per the SIT Exit approach. T3-TE-0046, T2-TE-0850, T3-TE-0043, T2-TE-0900, T3-TE-0050, T2-TE-0950, T1-TE-2000, T3-TE-0052, T3-TE-0055, T3-TE-0051, T3-TE-0056, T3-TE-0059 have been renamed in line with this approach. - The proposed renaming of 'SIT MVC' to 'SIT' has been included. This is because current testing data shows all SIT PPs are in a position to complete SIT by the end of Regression, meaning the end of Regression is no longer just the target SIT end date for PPs who will be ready for M10, but all PPs. 'SIT non-MVC' will be renamed 'SIT Contingency', to show that SIT will still go on until November, as per the existing plan. This proposed change is going to May SITAG for formal approval. - The 'M10-Ready', 'M11-Ready' and 'Not-M11-Ready' terminology, which has been shared with GLIG, SITWG and QWG, has been added in place of 'MVC' and 'Non-MVC'. The proposed Qualification Pathways have also been added as 'Proposed' activity, as part of this. - Helix's Service Management plan has been included.
v6.25 | Will Rosson / Will Miller | 2025-05-21 | Key updates in version 6.25 include, but are not limited to: -The SIT Exit reporting approach, which was approved by SITAG on 21/05 has been updated to 'Approved' activity and rebaselined. As part of this, the baseline dates for T2-TE-0850, T2-TE-0800, T2-TE-0900 & T2-TE-0950 have been moved, as per the SIT Exit approach. T3-TE-0046, T2-TE-0850, T3-TE-0043, T2-TE-0900, T3-TE-0050, T2-TE-0950, T1-TE-2000, T3-TE-0052, T3-TE-0055, T3-TE-0051, T3-TE-0056, T3-TE-0059 have been renamed in line with this approach. - The naming of 'SIT MVC' to 'SIT' has been updated. This is because current testing data shows all SIT PPs are in a position to complete SIT by the end of Regression, meaning the end of Regression is no longer just the target SIT end date for PPs who will be ready for M10, but all PPs. 'SIT non-MVC' will be renamed 'SIT Contingency', to show that SIT will still go on until November, as per the existing plan. This change was approved in May SITAG. - The 'M10-Ready', 'M11-Ready' and 'Not-M11-Ready' terminology, which has been shared with GLIG, SITWG and QWG, has been added in place of 'MVC' and 'Non-MVC'. The proposed Qualification Pathways have also been added as 'Proposed' activity, as part of this. - Placeholder M11 Readiness activity has been added and will be developed in the coming weeks. - Proposed separation for Sandbox Testing Execution to reflect different start and end dates for different Participant types, updates to the names for T3-QU-0126 & T3-QU-0127, and proposed addition of milestones for LDSO participants for May QAG approval. - Minor updates have been made to the Service Activation plan, with more updates still to come in the next plan version.
v6.251 | Will Rosson / Will Miller | 2025-05-22 | To support Programme Participants' planning, a v6.251 of the plan has been published to reflect the outcomes from May QAG on 22/05. This decision was taken to ensure that the new naming convention to replace MVC / non-MVC is baselined in the plan. Key updates in version 6.251 include, but are not limited to: - The 'M10-Ready', 'M11-Ready' and 'Not-M11-Ready' terminology, which has been shared with GLIG, SITWG and QWG, has been added in place of 'MVC' and 'Non-MVC'. The Qualification Pathways have also been added as 'Approved' activity, as reviewed and approved at May QAG. - Proposed separation for Sandbox Testing Execution to reflect different start and end dates for different Participant types, updates to the names for T3-QU-0126 & T3-QU-0127, and milestones T3-QU-130 & T3-QU-0131 have been added for LDSO participants as approved at May QAG. - Milestone names have been updated for T3-QU-0085 & T3-QU-0086 to reflect updated Qualification pathways terminology.
v6.26 | Will Rosson / Will Miller | 2025-06-04 | Key updates in version 6.26 include, but are not limited to: - As part of CR061 recommended at PSG (04/06) and verbally approved by Ofgem, M10 (T1-MI-1000) and M13 (T1-MI-2000) have been realigned to 22/09. - T3-MI-0047 (M10 Acceptance Criteria Ratification) has been added to reflect the completion of governance approval after the event. - Helix/Elexon M10 Readiness section added to plan, comprising of additional activity to reflect the wider Helix/Elexon M10 Readiness activity as per their planning assumptions. Also moving the existing Service Activation Readiness (M10 Ready) activity within the plan to the Helix/Elexon section for continuity. - Dress rehearsal activity combined with Submission 2 for clarity, as communicated to all Migration contacts. T3-MI-0043 moved in plan as part of this, with no impact to delivery dates.
v6.27 | Will Rosson / Will Miller | 2025-06-18 | Key updates in version 6.27 include, but are not limited to: - T3-QU-0016 current dates revised due to late submission of QT RTTM and as discussed at QAG on 10/06. Proposed date of 15/08/25. - Functional and Migration SIT Exit report dates updated to reflect revised timings. -The Service Activation dates for 'M11-Ready' and 'Not M11-Ready' PPs has been updated. -The Helix Implementation section has had new dependencies added. - Pathway 6 PAB dates updated. Please note that the revised Settlement and Regression testing dates have not been added to the Programme Plan yet. There is an eSITAG due to take place on Thursday 26/06, where a decision will be taken on the Settlement and Regression testing approach. The Programme will take steps to get these dates included in the plan and published as soon as possible.
v6.28 | Will Rosson / Will Miller | 2025-07-02 | Key updates in version 6.28 include, but are not limited to: - Revised timings for SIT Settlement and Regression, as approved at 26/06 eSITAG. - Updates to the SIT Exit Reporting approach, with T2-TE-0900, T2-TE-0800 & T2-TE-0800 moving to 06/08/25, and T2-TE-0950 moving to 15/08/25. Separate Functional and Migration Exit Report and Regression Exit section combined into F&M SIT Exit and F&M (Regression) Exit, respectively. Proposed removal of T3-TE-0046 & T3-TE-0046, pending approval. -Added activity to Helix's Service Management plan -Updates the Service Management plan for 'M10-Ready', 'M11-Ready' and 'Not M11-Ready' PPs and the SOLR Consultation -Minor amendments to the Helix Implementation plan to align with their latest dates - Proposed updates to Sandbox execution to simplify and add clarity, with the proposal to move T3-QU-0128 to 08/08/25 and T3-QU-0129 to 13/11/25, as well as the proposal to separate T3-QU-0125 into LDSO and S&A PPs, with the creation of a complementary milestone proposed.
v6.29 | Will Rosson / Will Miller | 2025-07-16 | Key updates in version 6.29 include, but are not limited to: - Service Activation Wave dates updated inline with the st Helix plan dates. - Minor updates to Helix plan section reflecting current dates. | v6.30
v6.30 | Will Rosson / Will Miller | 2025-07-30 | Key updates in version 6.30 include, but are not limited to: - Updates to the 'Helix / Elexon M10 Readiness' section, to reflect Helix's latest plan. -The Cutover plan section has been expanded following baselining of the Cutover Plan at MCAG, including updated naming for T3-MI-0036. -The Service Activation plan for the Qualification PPs has been updated to reflect Helix's latest plan.
v6.31 | Will Rosson / Will Miller | 2025-08-13 | Key updates in version 6.31 include, but are not limited to: -Adding dates for ServiceNow and UIT Onboarding for SIT PPs -Minor updates to the Migration plan
v6.32 | Will Rosson / Will Miller | 2025-08-27 | Key updates in version 6.32 include, but are not limited to: -Amendments to the 'Helix / Elexon M10 Readiness' section to reflect recent changes Helix have made to their plan -Minor amendments to the Migration section to correct dates -Included activities for the 'Legacy Settlement Run Stability Assessment', which will take place between M10 and M11.
v6.33 | Will Rosson / Will Miller | 2025-09-10 | Key updates in version 6.33 include, but are not limited to: -Amendments to T2-MI-0450 to reflect CR055 date shift, communicated via email to MCAG Participants. -Amendment to T3-MI-0500 in line with updated approach.
v6.34 | Will Rosson / Will Miller | 2025-09-24 | Key updates in version 6.34 include, but are not limited to: -Created a 'Elexon / Helix M10 - M16'workstream, where the activity Elexon and Helix will undertake in the lead up to M16 will sit. Added activity in this section for the SAT Test Cases descoped for M10 / M11. -Minor amendments made to the 'Regulatory Governance' sub-workstream. -Minor amendments to the 'M11 Checkpoint. -Minor updates to the 'Transition to New Settlement Timetable (M16)' and 'M16 Approval Window' workstreams.
v6.35 | Will Rosson / Will Miller | 2025-10-08 | Key updates in version 6.35 include, but are not limited to: -Updates to the Service Activation plan.
v6.36 | Will Rosson / Will Miller | 2025-10-22
v6.37 | Will Rosson / Will Miller | 2025-11-05
v6.38 | Will Rosson / Will Miller | 2025-11-19 | Key updates in version 6.38 include, but are not limited to: - Addition of T3-QU-0134/T3-QU-0135/T3-QU-0136 to reflect the updated Qualification approach with minimum viable and all wave separation, as proposed at QWG and pending approval at QAG. - Updates to activity names for T3-QU-0094, T3-QU-0098, T3-QU-0102, T3-QU-0095, T3-QU-0099, T3-QU-0103 T3-QU-0016, T3-QU-0020, T3-QU-0024, T3-QU-0096, T3-QU-0100, T3-QU-0104T3-QU-0027, T3-QU-0033, T3-QU-0038, T3-QU-0097, T3-QU-0101, T3-QU-0105, T2-QU-0150, T2-QU-0200, T2-QU-0250 to reflect the updated Qualification approach with minimum viable and all wave separation, as proposed at QWG and pending approval at QAG. - Updates to Elexon/Helix M10 - M16 plan activities, inclduing addition of solution build sprints, DAH and VAS/MDS/LSS development activity.
v6.39 | Will Rosson / Will Miller | 2025-12-03 | Key updates in version 6.39 include, but are not limited to: - Revised ELS Phase 2 Exit dates - 2026 PAB dates added
v6.40 | Will Rosson / Will Miller | 2025-12-17
v6.41 | Will Rosson / Will Miller | 2026-01-14
v6.42 | Will Rosson / Dan Crompton | 2026-01-28 | Key updates in version 6.42 include, but are not limited to: - Dates for the Migration exclusion PPIR - Updates on the dates of Offgems approval of migration exemptions - Including milestone ID for M16 checkpoint #1 activity
v6.43 | Will Rosson / Dan Crompton | 2026-02-11 | Key updates in version 6.43 include but are not limited to: - Updates to Qualfication activities to align with the QA&P Consultation agreed at QAG on 28th Jan 26 - New Activities added under Elexon / Helix M10 - M16 (Work Package Development) to reflect Helix's latest Solution Build plan - Migration Sprint Retro actvities added to each Mirgration Sprint (0-8) to reflect latest migration plan - Refreshed Readiness Assessment 7 (Migration checkpoint) activities with latest plan to represent the approach agreed with PSG (previous version of section striked-through, to be removed in next iteration of plan) - Note: includes update to date of Readiness Asessment 7 Milestone - reflected in milestone register
v6.44 | Dan Crompton | 2026-02-25 | Key updates in version 6.44 include but are not limited to: - New activities and updates to timings in-relation to realease management deployment schedule - i.e. DAH, WP2 (LSS, MDS, VAS, OP), ISD Asure, and SAT M16 Test Case Execution - Completion of R2 run as part of M11 Settlement Checks - General updates since last fortnight in relation to key Qualification activities (e.g. Wave 4 test data marked as complete - 24/02/26: ADO / QTF onboarding complete and correct test sets agreed, and status updates to qualification waves 2-4 activities General updates since last fortnight in relation to key Migration activities (e.g. still expecting end of Feb 26 for Ofgem incentives approval, migration sprint activities marked on-track)
6.45 | Dan Crompton | 2026-03-11 | Key updates in version 6.45 include, but are not limited to: - A more detailed and built out plan for M16, superseeding the high-level plan previously stored - which will continue to evolve and be monitored on a regular basis - General updates to Qualification, Migration activities - The addition of new activities, adjustment of dates, and general updates for Helix-associated line items
6.46 | Dan Crompton | 2026-03-25 | Key updates in version 6.46 include, but are not limited to: - Continued review and refinement of the detailed M16 Plan (incl. the removal of the previous M16 Methodology Section). All relevant M16 milestones which have changed as a result of the new plan are kept as proposed until formally approved at MCAG. - General updates to Qualification and Migration activities - The addition of new activities, adjustment of dates, and general updates for Helix-associated line items
6.47 | Kat Keane | 2026-04-08 | Key updates in version 6.47 include, but are not limited to: - Continued review and refinement of the detailed M16 Plan (including updates to the proposed consultation date, which is now due to be issued later in the month). All relevant M16 milestones which have changed as a result of the new plan are kept as proposed until formally approved at MCAG. - General updates to Qualification and Migration activities - The addition of new activities, adjustment of dates, and general updates for Helix-associated line items
6.48 | Kat Keane | 2026-04-22 | Key updates in version 6.48 include, but are not limited to: - Continued review and refinement of the detailed M16 Plan (including updates to the proposed consultation date, which is now due to be issued on 29/04/26). All relevant M16 milestones which have changed as a result of the new plan are kept as proposed and will be formally approved at MCAG on 28/04/26 - General updates to Qualification and Migration activities - The addition of new activities, adjustment of dates, and general updates for Helix-associated line items
6.49 | Kat Keane | 2026-05-06 | Key updates in version 6.49 include, but are not limited to: - Continued review and refinement of the detailed M16 Plan, including the approval of all 6 proposed milestones at the 28/04/26 MCAG as below: - T3-MI-0500: Milestone name changed from ‘M16 Approach Approved at PSG’ to ‘M16 Approach Approved at MCAG’; date changed from 31/07/26 to 23/06/26; decision-making authority changed from PSG to MCAG; party responsible for reporting RAG changed from CPT to SRO - T2-MR-0400: Milestone name changed from ‘M16 Checkpoint 1’ to ‘STEG May - M16 Checkpoint 2’; date changed from 25/06/26 to 17/05/27; decision-making authority changed from CPT to STEG; party responsible for reporting RAG changed from CPT to SRO - T2-MR-0500: New milestone ‘MCAG Endorses Assessment’ added for 17/07/26 - T2-RA-0700: Date changed from 13/10/26 to 14/08/26 - T2-EL-0200: New milestone ‘MCAG Approve Recommendation to Change to RF 7-Month Calendar’ added for 18/09/26 - T2-EL-0100: New milestone ‘MCAG Approve Recommendation - Confirm M16 Date’ added for 18/06/27 - General updates to Qualification and Migration activities - The addition of new activities, adjustment of dates, and general updates for Helix-associated line items

## Milestone Register Guidance
MHHS Programme Milestone Register Guidance
This page provides an explanation of how to interpret the information in the Milestone Register tab
Milestone Register Fields
Column Heading | Milestone Tier | Milestone ID | Milestone Title | Milestone Description | Plan Section | Milestone Date | Critical Path | Critical Thread (Relevant Tier 1 milestone) | Artefact required for milestone approval | Decision-making authority (governance group) | Party responsible for reporting RAG | Party applicability RACI
Description | The tier of the milestone, denoting the activities' Critical Path / Thread relevance and programme governance level responsible for reporting and decision-making. Detail of Milestone Tier Classifications documented below. | Milestone unique identifier | Title of the milestone | Narrative description of the milestone | Section of the MS Project plan that the milestone can be found. | Proposed date for milestone approval at the relevant programme goverance forum | If 'Yes', the milestone is considered to be on the programme's critical path to Go-Live | References the relevant Tier 1 dependent milestone | The associated artefact(s) that are required to support the completion of the milestone | Programme governance forum responsible for reporting on milestone progress and deciding on milestone changes / approval | Organisation responsible for reporting the RAG status of the milestone via the Milestone Status Report and relevant governance group | RACI to identify the applicability of milestones to different organisations engaged in the MHHS programme. [R] Responsible = The party is responsible for completing the activity associated with the milestone approval. [A] Accountable = The party is ultimately accountable for ensuring the completion of the activity associated with the milestone approval. Responsible parties are accountable to this organisation. [C] Consulted = The party is not directly involved in the activity associated with the milestone approval, but may be consulted for input or advice. Consulted parties will also be informed of any output. [I] Informed = The party is not directly involved in the activity associated with the milestone approval, but will be kept informed of progress and outputs.
Column subject to Change Control (Y / N) | Y | Y | Y | Y | N | Y | N | N | Y | Y | N | Y
Milestone Tier Classifications
Milestone Tier | Milestone Tier Description | Milestone Tier Reference | Governance reporting, decision-making and change control
Tier 1 | Milestones that sit on the critical path for Go-Live and / or are under the purview of the Programme Steering Group. This includes milestones for the decision point associated with progressing to the next phase of the programme (i.e. Control Points). Tier 1 milestones are comprised of a number of sub-milestones (Tier 2 and 3) focused on activities and deliverables which will be key inputs into decision-making. | T1-XX-XXXX | Programme Steering Group (PSG)
Tier 2 | Milestones that sit on a critical thread and therefore, are direct dependencies for the delivery of critical path milestones. This includes commencement and completion checkpoints for key stages of activity, such as the stages of SIT. Tier 2 milestones are key input activities or deliverables for Tier 1 milestone decision points. | T2-XX-XXXX | Advisory Groups
Tier 3 | Milestones that are considered key input activities to Tier 2 (Critical Thread) milestones. This includes the approval of key artefacts and the release of test stubs required for a particular stage of PP testing. Working Groups and Sub-groups will be tasked with completing these tasks and reporting progress and completion to the appropriate Advisory Group to inform a decision. | T3-XX-XXXX | Advisory Groups
Milestone ID Convention |  |  | Example
TX-XX-XXXX |  |  | T1-CP-2000
TX | XX | XXXX | T1 | CP | 2000
Milestone Tier | Plan Section | Numerical identifier | Milestone Tier | Plan Section | Numericla Identifier
T1 = Tier 1 | BC = Business Change | Free text to identify the sequencing of activities within the relevant workstream | Tier 1 | Control Point | Second in a series of five Programme Control Points
T2 = Tier 2 | CP = Control Point
T3 = Tier 3 | DB = System Design & Build
EL = Early Live Running
MI = Migration
PC = Programme Closure
PM = Programme Management
QU = Qualification
RA = Readiness Assessment
RE = Regulatory
TE = Systems Integration Testing
MR = Milestone Range Checkpoint

## Milestone Register
| Milestone Tier | Level 1 Approval | Milestone ID | Milestone Name | Milestone Description | Plan Section | Milestone Date | Critical Path | Critical Thread (Relevant Tier 1 milestone) | Artefact ID | Artefact / Deliverable required for milestone approval | Decision-making authority (governance group) | Party responsible for reporting RAG | Ofgem | SRO | LDP | IPA | SRO Function | CPT | PMO | PPC | SI Test | SI DevOps | SI Design | SI Migration | DCC | Elexon Central Systems | DIP | RECCo | Registration Services | Network Operators | UMSOs | Small Suppliers | Medium Suppliers | Large Suppliers | I&C Suppliers | In-House Supplier Agents | Independent Agents | Software Providers | BSC | REC | DCUSA | SEC | CUSC | SRO Code Drafters | IPA | Ofgem | Elexon Board | Notes
| T1 |  | T1-CP-1000 | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | The Programme will deliver an assessment of Programme Health using a set of health criteria to determine that the previous Programme delivery phase - Mobilisation & E2E Design - has been delivered satisfactorily and that the Programme is set up to deliver the next Programme delivery phase - Design, Build and Test - to the required standard. | CP | 2022-12-07 | Yes |  | MHHS-ART059 | Control Point 1 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | Conducts the Control Point Review, approves assessments and actions, provides report to PSG with decision | Prepares the Control Point Review, produces public report based on approved assessments and actions | Assurance over the conclusions and actions from the Control Point Review, to be presented at PSG | A | R | R | C | C | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | I | I
| T1 |  | T1-CP-2000 | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | The Programme will deliver an assessment of Programme Health using a set of health criteria to determine that the previous Programme delivery phase - System Design, Build & Test - has been delivered satisfactorily and that the Programme is set up to deliver the next Programme delivery phase - Integration & Test - to the required standard. | CP | 2023-10-30 | Yes |  | MHHS-ART059 | Control Point 2 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve DAG milestone recommendation and / or manage escalation if required | Provide detailed technical assurance on design artefacts and the overall design | Assurance over the attainment of the milestone, supported by a report | A | C | I | C | I | C | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T1 |  | T1-CP-3000 | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | The Programme will deliver an assessment of Programme Health using a set of health criteria to determine that the previous Programme delivery phase - Integration & Test - has been delivered satisfactorily and that the Programme is set up to deliver the next Programme delivery phase - Readiness for Migration / Qualification - to the required standard. | CP | 2025-09-18 | Yes |  | MHHS-ART059 | Control Point 3 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | Conducts the Control Point Review, approves assessments and actions, provides report to PSG with decision | Prepares the Control Point Review, produces public report based on approved assessments and actions | Assurance over the conclusions and actions from the Control Point Review, to be presented at PSG | C | A | C | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | C
| T1 |  | T1-CP-4000 | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | The Programme will deliver an assessment of Programme Health using a set of health criteria to determine that the previous Programme delivery phase - Migration - has been delivered satisfactorily and that the Programme is set up to deliver the next Programme delivery phase - Cut Over - to the required standard. | CP | 2027-06-23 | Yes |  | MHHS-ART059 | Control Point 5 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | Conducts the Control Point Review, approves assessments and actions, provides report to PSG with decision | Prepares the Control Point Review, produces public report based on approved assessments and actions | Assurance over the conclusions and actions from the Control Point Review, to be presented at PSG | C | A | I | I | R | I | I | I | C | R | C | R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | I | C
| T1 | Yes | T1-DB-1000 | Physical design baselined (M5) | In order for the other parties to commence the DBT phase a complete Physical Baseline, aligning technical, process and regulatory designs, will be delivered. | DB | 2022-10-31 | Yes |  | MHHS-ART001 | Physical design baseline accepted Completion of M5 Milestone Report | PSG | SRO Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve DAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T1 | Yes | T1-EL-1000 | Cut over to new settlement timetable (M16) | The date of the cut over to the new settlement timetable will occur after the end of migration. The decision on when the settlement timetable should be taken nearer the time, and on market monitoring against trigger points. Industry should ensure that the new settlement timetable is introduced as soon as practical after the end of migration. | EL | 2027-07-02 | Yes |  | MHHS-ART012 | Completion of M16 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 | Yes | T1-EL-2000 | Cut over to new settlement timetable (M16*) - Late Exit | This defines the end of the 6-month range for achievement of M16. | EL | 2027-12-23 | Yes |  | MHHS-ART012 | Completion of M16 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 |  | T1-MI-1000 | Central systems ready for migrating MPANs (M10) | Following completion of the testing phase (excluding TE18 Security Testing), the Central Systems (BSC central systems, registration, DCC and communication systems) will be ready to initiate migration of Meter Point Administration Numbers (MPANs) from the current market roles into the new market roles. | MI | 2025-09-22 | Yes |  | MHHS-ART076 | Migration Test Completion Report Completion of M10 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | R | R | R | R | R | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T1 |  | T1-MI-2000 | Load Shaping Service switched on (M13) | The LSS will be switched on after a period used to gather and validate settlement period level data from the smart meter data service. | MI | 2025-09-22 | Yes |  | MHHS-ART012 | Completion of M13 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | C | I | I | C | I | I | C | R | C | C | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T1 | Yes | T1-MI-3000 | Start of 18-month migration for UMS / Advanced (M11) | Start of migration window for suppliers to move all UMS and advanced meter points to be settled in the new arrangements. | MI | 2025-10-22 | Yes |  | MHHS-ART012 | Completion of M11 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 |  | T1-MI-4000 | Start of 18-month migration for Smart / Non-smart (M12) | Start of migration window for suppliers to move all smart and non-smart meter points to be settled in the new arrangements. | MI | 2025-10-22 | Yes |  | MHHS-ART012 | Completion of M10 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | C | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 | Yes | T1-MI-5000 | All suppliers must be able to access MPANs under the new TOM (M14) | Deadline by which all suppliers must have the systems and services in place to accept MPANs under the new TOM. From this point MPANs cannot be moved back into NHH regime on change of supplier and any suppliers who have not put these arrangements in place will not be able to take on new customers | MI | 2026-10-28 | Yes |  | MHHS-ART012 | Completion of M14 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 | Yes | T1-MI-5500 | All suppliers must be able to access MPANs under the new TOM (M14*) - Late Exit | This defines the end of the 3-month range for achievement of M14. | MI | 2027-01-28 | Yes |  | MHHS-ART012 | Completion of M14 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 | Yes | T1-MI-6000 | Full transition complete (M15) | Completion of implementation activities including 18 month migration. | MI | 2027-05-07 | Yes |  | MHHS-ART012 | Completion of M15 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 | Yes | T1-RE-1000 | Code changes baselined (M6) | The CCDG will deliver the recommendations aimed at addressing any outstanding areas of the DWG’s TOM design, and will deliver the recomendations for the changes to the Industry Codes and subsidiary documents necessary to enable the TOM. | RE | 2024-08-23 | Yes |  | MHHS-ART012 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance Completion of M6 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve CCAG milestone recommendation and / or manage escalation if required | Manage governance process | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | A/R | R | A/R | A/R | C | C
| T1 | Yes | T1-TE-1000 | System Integration Testing Start (M9) | System Integration Testing (SIT) will commence in October 2023. This test phase involves the central parties (Elexon, DCC, comms network providers and the registration system providers) along with a small number of agents and suppliers. | TE | 2023-10-30 | Yes |  | MHHS-ART071 | SIT - Component Integration Test Readiness Report Completion of M9 Milestone Report | PSG | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | R | C | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C | C
| T1 |  | T1-TE-2000 | SIT Complete (SIT Test Exit Report Approved) | The approval by PSG of the Test Exit Report for SIT | TE | 2025-08-22 | Yes |  | MHHS-ART081 | SIT Test Exit Report | PSG | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | I | C | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-DB-0100 | Phase 1 - SIT Volunteers (Core Providers) complete | The production and approval of the design assurance findings and recommendations by DAG of SIT Volunteers (Core Providers) design | DB | 2023-10-27 | No | T1-TE-1000 | MHHS-ART002 | Design Assuance Report | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-DB-0150 | Tranche 1 Transition Design approved | The approval by DAG of the Parallel Running and GSP Group Correction, Transitional Interfaces and Transition Approach and Requirements: LLFs and UMS Charge Code and Switch Regimes | MI | 2023-05-17 | No |  |  | MHHS-DES240-Transitional_Scaling_Weights, MHHS-DES242-Transitional_BMU_Aggregated_Data and VMHHSP-TRANS - BRS001 Transition Approach ans Parallel Running Requirements | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | R |  | I | [5 empty] | C | C | C | C | C | C | C | C | C | C | C | C |  |  | C | C | C | C | C | I | I | C | I
| T2 |  | T2-DB-0200 | SIT PPs design assurance (excl Migration/Reverse Migration) complete | The production and approval of the design assurance findings and recommendations by DAG of SIT participants design | DB | 2023-11-22 | No | T1-TE-1000 | MHHS-ART002 | Design Assuance Report | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-DB-0250 | Tranche 2 Transition Design Baselined | The approval by DAG of Transition Approach and Requirementsfor ISD and MDD, ISD population requirements, ISD Originators and Authorisation Routes, requirements for the SVAA, SAA Calendars aligned with the Master Settlement Timetable and Transition to the new Settlement Timetable | MI | 2023-11-15 | No |  |  | Transition Tranche 2 requirements | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | R |  | I | [5 empty] | C | C | C | C | C | C | C | C | C | C | C | C |  |  | C | C | C | C | C | I | I | C | I
| T2 |  | T2-EL-0100 | Confirm M16 Date | Agreement to the date to move to the new settlement timetable (based on meeting yet to be agreed performance criteria) | EL | 2027-04-30 | Yes | T1-EL-1000 |  |  | PSG/BSC PAB | BSC PAB & REC | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required. Provide artefacts and manage any related CRs to support the milestone decision. | Assurance over the attainment of the milestone, supported by a report | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | R | I | I | I | I | I | C | C
| T2 |  | T2-MI-0050 | Migration Design approved | The approval by DAG of the Migration Design | MI | 2023-03-31 | No | T1-TE-2000 |  | Migration Design Artefacts | DAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | R | A | C | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T2 |  | T2-MI-0350 | DCC Capacity Upgrade Operational | DCC implementation of capacity upgrade to support MHHS, as set out in Ofgem direction letter. | MI | 2025-08-29 | No | T1-MI-1000 |  |  | DCC/SEC | DCC | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | C | R, A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |  | C |  |  | C | C
| T2 |  | T2-MI-0450 | Pre-migration data cleanse complete | Completion of the data cleansing and population activities set out within the Data Cleanse Plan. At this point, data should be of the required quality and completeness to correctly enable Migration operations. | MI | 2025-09-22 | No | T1-MI-3000 | - | - | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | Consulted for advice throughout the attainment of this milestone. Also responsible for oversight of this delivery. | Responsible for monitoring and assuring progress of data improvement activities undertaken by MHHS Participants to ultimately enable timely completion of this milestone. | Assurance over the attainment of the milestone | I | A | I | I | I | - | - | A | - | I | - | R | R | R | R | R | R | R | R | R | R | R | - | - | - | - | - | - | I | I | -
| T2 |  | T2-MI-0500 | MCC Operational Complete | MCC Operational is complete. | MI | 2025-08-29 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T1 |  | T2-MI-1500 | Central systems ready for migrating MPANs (M10*) - Late Exit | This defines the end of 3-month range for achievement of M10 | MI | 2025-12-24 | Yes |  | MHHS-ART076 | Migration Test Completion Report Completion of M10 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | R | R | R | R | R | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T1 |  | T2-MI-2500 | Load Shaping Service switched on (M13*) - Late Exit | This defines the end of the 3-month range for the achievement of M13 | MI | 2025-12-24 | Yes |  | MHHS-ART012 | Completion of M13 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | C | I | I | C | I | I | C | R | C | C | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T1 | Yes | T2-MI-3500 | Start of 18-month migration for UMS / Advanced (M11*) - Late Exit | This defines the end of the 3-month range for achievement of M11. | MI | 2026-01-21 | Yes |  | MHHS-ART012 | Completion of M11 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 |  | T2-MI-4500 | Start of 18-month migration for Smart / Non-smart (M12*) - Late Exit | This defines the end of the range for the achievement of M12 | MI | 2026-01-21 | Yes |  | MHHS-ART012 | Completion of M10 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage and approve TMAG milestone recommendation and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | C | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T1 | Yes | T2-MI-6500 | Full transition complete (M15*) - Late Exit | This defines the end of the 3-month range for achievement of M15. | MI | 2027-08-09 | Yes |  | MHHS-ART012 | Completion of M15 Milestone Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | As PSG Chair, manage milestone decision and / or manage escalation if required | Provide artefacts and manage any related CRs to support the milestone decision | Assurance over the attainment of the milestone, supported by a report | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T2 |  | T2-MI-7000 | Framework Baselined at MCAG | The approval by MCAG of the Migration Framework Artefacts which were reviewed by industry during consultation 4. | MI | 2025-04-29 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T2 |  | T2-MI-7500 | V1.0 of Migration Schedule Baseline Approved at MCAG | MCAG approve V1.0 of Migration Schedule Baseline | MI | 2025-07-22 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T2 |  | T2-MI-8000 | Migration Sprint 0 schedule baselined | Migration Sprint 0 schedule is baselined | MI | 2025-10-16 |  | M11 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T2 |  | T2-MI-8500 | Non-SIT Participants Migration Start | Non-SIT Participants Migration Started. | MI | 2026-05-15 |  | M14 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T2 |  | T2-MI-9000 | Sprint Execution End | All Migration Sprints have been completed | MI | 2027-05-05 |  | M16 |  |  | MCAG | Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | I | C | R | C | C | C | C | C | C | R | R | R | R | R | C | C | C | I | I | I | I | I | I | C | C
| T2 |  | T2-MR-0100 | M10, M11, M12, and M13 milestone checkpoint - date approval | Three month date range checkpoint for MHHS to reaffirm whether the planned Tier 1 date remains on schedule and whether the planned date for the milestone will change | MR | 2025-07-31 | No |  |  |  | CPT | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | C | C | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T2 |  | T2-MR-0200 | M14 milestone checkpoint - date approval | Three month date range checkpoint for MHHS to reaffirm whether the planned Tier 1 date remains on schedule and whether the planned date for the milestone will change | MR | 2026-08-06 | No |  |  |  | CPT | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | C | C | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T2 |  | T2-MR-0300 | M15 milestone checkpoint - date approval | Three month date range checkpoint for MHHS to reaffirm whether the planned milestone date remains on schedule and whether the planned date for the milestone will change | MR | 2027-02-15 | No |  |  |  | CPT | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | C | C | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T2 |  | T2-MR-0400 | M16 milestone checkpoint - date approval | Three month date range checkpoint for MHHS to reaffirm whether the planned Tier 1 date remains on schedule and whether the planned date for the milestone will change | MR | 2027-04-12 | No |  |  |  | CPT | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | C | C | C | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T2 |  | T2-QU-0150 | All M14 Critical Wave 1 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB & REC Code Manager approval of the qualification of Wave 1 participants | QU | 2026-04-15 | No | T1-MI-5000 | MHHS-ART073 | Qualification Test Completion Report | BSC PAB & REC Manager | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | C | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T2 |  | T2-QU-0200 | All M14 Critical Wave 2 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB & REC Code Manager approval of the qualification of Wave 2 participants | QU | 2026-05-28 | No | T1-MI-5000 | MHHS-ART073 | Qualification Test Completion Report | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | C | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T2 |  | T2-QU-0250 | All M14 Critical Wave 3 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB & REC Code Manager approval of the qualification of Wave 3 participants | QU | 2026-07-30 | No | T1-MI-5000 | MHHS-ART073 | Qualification Test Completion Report | BSC PAB & REC Manager | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | C | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T2 |  | T2-QU-0300 | Qualification Wave 4 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB & REC Code Manager approval of the qualification of Wave 4 participants | QU | 2026-09-24 | No | T1-MI-5000 | MHHS-ART073 | Qualification Test Completion Report | BSC PAB & REC Manager | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | C | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T2 |  | T2-QU-0500 | BSC PAB & REC Manager approval of Qualification for Non-SIT LDSOs (Start of Migration for Qualification Participants) | Date when REC & BSC PABs are expected to approve successful completion of non-SIT LDSO Qualification Testing | QU | 2025-09-11 | No | T1-MI-1000 |  |  | REC PAB / BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | C | I | A/R | I | A/R | C | C | C | I | I | I | I | I | I | I | R/A | R/A | I | I | I | I | C | C
| T2 |  | T2-QU-0500 | BSC PAB & REC Manager approval of Qualification for Non-SIT LDSOs | BSC PAB & REC Manager have approved Qualification for Non-SIT LDSOs | QU (Non-SIT S&A) | 2025-09-11 |  | M10 |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-QU-0550 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed (Final Test Readiness Review for LDSO) | Final test readiness checks are complete for all LDSOs demonstrating their readiness to start their QT scope | QU (Non-SIT LDSO) | 2024-12-20 | No | M9+12 | TBC | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; I: I; A/R: C; C: C; C: C; C: C; R/A: A; R/A: A |  | Critical Path comment is against the project plan, not overall programme plan
| T2 |  | T2-QU-1100 | Qualification Testing Wave Readiness Confirmed | Readiness for commencement of Qualification Testing Waves confirmed by QAG | QU (Non-SIT S&A) | 2025-08-21 |  | M10 |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-RA-0200 | Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | The Programme will conduct a Readiness Assessment to determine the progress made by Participants in their Design, Build and Pre-Integration Testing (PIT) activities. This will involve a self-assessment survey, assessment of evidence and deep-dive interviews with Participants to understand the extent to which DBT activities have been progressed to a high quality and to the agreed time periods in the MHHS Programme Plan. This Readiness Assessment will be the first of two Design & Build Checkpoints focusing on participants expecting to be involved in SIT. | RA | 2023-11-27 | No | T1-CP-2000 | MHHS-ART024 | Readiness Assessment 3 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | R | C | C | C | C | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | C
| T2 |  | T2-RA-0400 | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check (incl. Readiness Assessment Report approval) Completed | The Programme will conduct a Readiness Assessment to determine the progress made by Participants towards the start of Qualification Testing. This will involve a self-assessment survey, assessment of evidence and deep-dive interviews with Participants to understand the extent to which Qualification Testing preparatory activities have been completed to a high quality and to the agreed time periods in the MHHS Programme Plan. | RA | 2025-07-01 | No | T1-MI-5000 | MHHS-ART024 | Readiness Assessment 5/6 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | R | C | C | C | C | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | R | R | R | C
| T2 |  | T2-RA-0500 | Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | Readiness Assessment 6, covering the start of Migration is reviewed and approved at PSG. | RA | 2025-07-01 | No | M10 |  |  | PSG | PPC | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-RA-0600 | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | The Programme will conduct a Readiness Assessment to determine the progress made by Participantsin their Migration activities. This will involve a self-assessment survey, assessment of evidence and deep-dive interviews with Participants to understand the extent to which Migration activities have been progressed to a high quality and to the agreed time periods in the MHHS Programme Plan. | RA | 2026-04-01 | No | T1-CP-5000 | MHHS-ART024 | Readiness Assessment 7 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | R | C | C | C | C | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | C
| T2 |  | T2-RA-0700 | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | The Programme will conduct a Readiness Assessment to determine the progress made by Participants in their readiness to accept new MPANs under the MHHS arrangements. This will involve a self-assessment survey, assessment of evidence and deep-dive interviews with Participants to understand the extent to which activities required to demonstrate readiness to accept new MPANs have been completed to a high quality and to the agreed time periods in the MHHS Programme Plan. | RA | 2026-10-13 | No | T1-MI-5000 | MHHS-ART024 | Readiness Assessment 8 Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | R | C | C | C | C | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | C
| T2 |  | T2-RA-0800 | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | The Programme will conduct a Readiness Assessment to determine the progress made by Participantsin their readiness for the new Settlement Timetable. This will involve a self-assessment survey, assessment of evidence and deep-dive interviews with Participants to understand the extent to which Migration activities have been progressed to a high quality and to the agreed time periods in the MHHS Programme Plan. | RA | 2027-06-17 | No | T1-EL-1000 |  | Readiness Assessment Report | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | R | C | C | C | C | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | C
| T2 |  | T2-RE-0100 | Code drafting for Data Services topic area approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2023-05-24 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | R | R | R | R | C | C | C | C | C | A/R | C
| T2 |  | T2-RE-0150 | Code drafting for Metering topic area approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2023-05-24 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | R | R | R | R | C | A/R | C | C | C | C | C
| T2 |  | T2-RE-0200 | Code drafting for BSC Central Services topic area approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2023-09-27 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | I
| T2 |  | T2-RE-0250 | Code drafting for Registration topic area approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2023-08-23 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | A/R | C | C | A/R | C
| T2 |  | T2-RE-0600 | Ofgem decisions on M6 baselined code modification proposals (M7) | Ofgem enable their Significant Code Review Powers to facilitate the implementation of all Code documentation at M8 | RE | 2024-12-11 | No | T1-MI-1000 | MHHS-ART012 | Completion of M7 Milestone Report | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [32 empty] | A/R | bar: C C to C C
| T2 |  | T2-RE-0650 | Code changes delivered (M8) | All changes to regulation (licences, industry codes (including BSC, SEC, REC, DCUSA)) have been made setting out the regulatory baseline. | RE | 2025-09-22 | No | T1-MI-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance Completion of M8 Milestone Report | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | R | R | R | R | R | R | C | C
| T2 |  | T2-RE-0700 | Code changes delivered (M8*) late exit | This defines the end of 3-month range for achievement of M8 | RE | 2025-12-24 | No | T1-MI-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance Completion of M8 Milestone Report | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | R | R | R | R | R | R | C | C
| T2 |  | T2-TE-0100 | SIT Participant Volunteers Identified | Following assurance of programme plans by the SI for Programme participant (PP) (PP)(PP)s that registered their interest for being involved in SIT, a cohort of participants that have sufficiently demonstrated their ability to be ready for SIT start will be confirmed. | TE | 2023-02-14 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-0150 | SIT Participants Agreed | Participants who wish to volunteer for SIT MVC or SIT have been accepted as SIT participants based on agreed decision criteria | TE | 2023-05-23 | Yes | T1-TE-2000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | R | I | C | R | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-0250 | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | TMAG approves that all preparation activities required to commence SIT Component Integration have been completed and assured. | TE | 2023-10-27 | Yes | T1-TE-1000 | MHHS-ART071 | SI SIT Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | I | R | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T2 |  | T2-TE-0300 | SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | TMAG approves that all preparation activities required to commence SIT Component Integration have been completed and assured. | TE | 2023-11-06 | Yes | T1-TE-1000 | MHHS-ART071 | SI SIT Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T2 |  | T2-TE-0350 | SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | TMAG approves that all preparation activities required to commence SIT Component Integration have been completed and assured. | TE | 2023-11-20 | Yes | T1-TE-1000 | MHHS-ART071 | SI SIT Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T2 |  | T2-TE-0400 | SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | TMAG approves that all preparation activities required to commence SIT Component Integration have been completed and assured. | TE | 2023-12-04 | Yes | T1-TE-1000 | MHHS-ART071 | SI SIT Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T2 |  | T2-TE-0450 | SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | TMAG approves that all preparation activities required to commence SIT Component Integration have been completed and assured. | TE | 2024-01-08 | Yes | T1-TE-1000 | MHHS-ART071 | SI SIT Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | I | C | C | C | C | R | R | R | R | R | R | C | C | C | C | C | C | C | C | C | C
| T2 |  | T2-TE-0500 | SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | TMAG approves that all preparation activities required to commence SIT Component Integration have been completed and assured. | TE | 2024-01-19 | Yes | T1-TE-1000 | MHHS-ART071 | SI SIT Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | R | C | C | R | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T2 |  | T2-TE-0550 | SIT Functional Testing Preparation Complete | TMAG approves that all preparation activities required to commence SIT Functional have been completed and assured. | TE | 2024-03-01 | Yes | T1-TE-2000 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | C
| T2 |  | T2-TE-0600 | SIT Component Integration Testing Test Completion Report Approved | The approval by TMAG of the Test Completion Report for SIT Component Integration | TE | 2024-03-11 | Yes | T1-TE-2000 | MHHS-ART074 | Component Integration Test Completion Report (formerly Industry Integration Test Completion Report) | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | I | C | C | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C
| T2 |  | T2-TE-0650 | SIT Migration Testing Preparation Complete | TMAG approves that all preparation activities required to commence SIT Migration have been completed and assured. | TE | 2024-06-03 | Yes | T1-TE-2000 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | C | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | C
| T2 |  | T2-TE-0700 | SIT Non-Functional Testing Preparation Complete Theme 1 | TMAG approves that all preparation activities required to commence SIT Non-Functional have been completed and assured. | TE | 2025-02-28 | Yes | T1-TE-2000 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | C
| T2 |  | T2-TE-0750 | SIT Operational Theme 3 (Batch 1) Testing Preparation Complete | TMAG approves that all preparation activities required to commence SIT Operational have been completed and assured. | TE | 2025-01-31 | Yes | T1-TE-2000 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-0800 | SI SIT Migration Testing Test Exit Report Approved | The approval by TMAG of the Test Exit Report for SIT Migration | TE | 2025-08-20 | Yes | T1-TE-2000 | MHHS-ART076 | SIT Migration Test Completion Report | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-0850 | SI SIT Functional Testing Test Exit Report Approved | The production and approval by TMAG of the Test Exit Report for SIT Functional | TE | 2025-08-20 | Yes | T1-TE-2000 | MHHS-ART072 | SIT Functional Test Completion Report (formerly E2E Test Completion Report) | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-0900 | SIT Non-Functional Testing Test Exit Report (all SIT PPs) Approved | The production and approval by TMAG of the Test Exit Report for SIT Non-Functional | TE | 2025-08-06 | Yes | T1-TE-2000 | MHHS-ART079 | SIT Non-Functional Test Completion Report (formerly Non-Functional Test Completion Report) | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-0950 | SIT Operational Testing Test Exit Report (all SIT PPs) Approved | The approval by TMAG of the Test Exit Report for SIT Operational | TE | 2025-08-15 | Yes | T1-TE-2000 | MHHS-ART081 | SIT Operational Test Completion Report | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-1000 | Regression Test Data Load Start | Data Load for Regression can start. | TE | 2025-04-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-1100 | SIT Non-Functional Testing Preparation Complete Theme 2 & 3 | Data preparation for Non-Functional Themes 2 & 3 are complete | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-1150 | SIT Functional Cycle 3 Complete | SIT Functional Cycle 3 sprints have concluded. | TE | 2025-04-28 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-1200 | SIT Migration Cycle 3 Complete | SIT Migration Cycle 3 is complete. | TE | 2025-04-25 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-1250 | Regression Test Execution Start | Regression Test Execution Started. | TE | 2025-06-30 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T2 |  | T2-TE-1300 | SIT Operational Theme 1, 2, 3 (Batch 2) Testing Preparation Complete | SIT Operational Theme 1, 2, 3 (Batch 2) Testing Preparation has been completed. | TE | 2025-04-25 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-BC-0010 | Service Management Strategy approved | The production and approval by DAG of the Service Management Strategy | BC | 2024-02-27 | No |  |  | Service Management Strategy | DAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | I | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0010 | Design Authority ToR approved | Approval by DAG of the Terms of Reference (ToR) document for the Design Authority | DB | 2022-12-14 | No |  |  | Design Authority Terms of Reference | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T3 |  | T3-DB-0011 | All Network Operation test scenarios' submitted to Programme for assurance | Final date by which Network Operation are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-10-05 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C A C C C C C C C C C C C C C C C C C C C C C C: C; A R A A A A A A A A A A A A A A A A A A A A A A: C; I I I I I I I I I I I I I I I I I I I I I I I I: I; C C I I I I I I I C C I I I I I I I I I I I I C: C; R R R R R R R R R R R R R R R R R R R R R R R I: C; I I I I I I I I C I I I I I I I I I I I I I I R: I; I C I I I I I I I I I I I I I I I I I I I I I I: I; I C I I I I I I I I C I C C I I I I I I I I I I: I; C C C C C C R C R I R R C C C C C C C C C C C I: A/R; I I C C C C C C I I I I I I I I I I I I I I I I: I; I I C C C C C C I I I I I I I I I I I I I I I I: I; I I C C C C C C I I I I I I I I I I I I I I I I: I; I I C C C C C C I I I I I I I I I I I I I I I I: I; I I C C C C C C I I I I I I I I I I I I I I I I: I; I I C C C C C C I I I I I I I I I I I I I I I I: I; C C C C C C C C C C C C C C C C C C C C C C C I: I
| T4 |  | T3-DB-0012 | Participant Design Assurance Approach approved |  | DB | 2023-01-11 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0014 | M5 design Work-Off Plan completion approved | SI Design Activities as part of the transition from SRO to SI Design, including the handling of participant queries, configuration and release management. | DB | 2023-02-16 | No |  |  | Design Work-off plan | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A/R | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0016 | Enduring change management process approved | Sign off by DAG / PSG against the design change management process set-up of the Design Authority and associated delegate authority | DB | 2023-02-16 | No |  |  | Enduring Change Management Process | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | I | I | R | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
| T3 |  | T3-DB-0017 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | Final date by which PP’s in CIT Interval 3 are expected to provide their PIT Test Completion Report (excl Migration/Reverse Migration) to the MHHS SI Test Team for review and assurance | DB | 2023-11-03 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C to I; C to C
| T3 |  | T3-DB-0018 | DIP Simulator released | The simulators and emulators team will deliver the Data Integration Platform (DIP) simulator; allowing the simulation of the behaviour of the interface over the Data Integration Platform (DIP) with Load Shaping Service (LSS) and Market-wide Data Service (MDS) - both inbound to the DIP and the outbound “publish” from the DIP. The simulators will be fully tested and corresponding business readiness activities completed prior to release. | DB | 2023-03-29 | No |  |  |  | TMAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0019 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | Final date by which PP’s in CIT Interval 4 are expected to provide their PIT Test Completion Report (excl Migration/Reverse Migration) to the MHHS SI Test Team for review and assurance | DB | 2023-11-17 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C to I; I to I
| T3 |  | T3-DB-0020 | All SIT LDSOs have procured their adapter providers | Where a LDSO is participanting in SIT they need to have completed the procurement of their DIP adaptor provider where required. | DB | 2023-05-23 | No |  |  | Detailed their intention to use a DIP Adaptor provider as part of their response to their design assurance | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | I | I | I | I | I | I | C | I | I | I | C | I | I | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0021 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | Final date by which PP’s in CIT Interval 6 are expected to provide their PIT Test Completion Report (excl Migration/Reverse Migration) to the MHHS SI Test Team for review and assurance | DB | 2023-12-08 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | A/R |  |  | A/R | A/R | [8 empty] | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0022 | Data Generator released | Final date by which the tool developed by the SI team to generate consumption data for Programme participant (PP)' testing is made available to Programme participant (PP) | DB | 2023-05-31 | No |  |  | Evidence that generator code and attendant documentation/training is available on the Collaboration Base and that Programme participant (PP) have been notified in an appropriate manner | TMAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0023 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | Final date by which PP’s in CIT Interval 6 are expected to provide their PIT Test Completion Report (excl Migration/Reverse Migration) to the MHHS SI Test Team for review and assurance | DB | 2024-01-05 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | A/R |  |  | A/R | A/R | [8 empty] | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0025 | All UMSO test scenarios' submitted to Programme for assurance | Final date by which UMSO are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-11-02 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: C; A: C; I: I; C: C; C: C; R: I; C: I; I: I; C: A/R; I: I; I: I; I: I; I: I; I: I; I: I; I: I
| T3 |  | T3-DB-0026 | DIP Test Approach & Plan (PIT) submitted to Programme for assurance | Final date by which the DIP provider are expected provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-07-07 | No |  | MHHS-ART073 | Test Approach & Plan - DIP | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | C | I | C | C | I | I | I | I | I | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0028 | Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | Final date by which the Registration Services are expected provide their PIT Test Approach & Plans to the MHHS SI Test Team for review and assurance | DB | 2023-07-28 | No |  | MHHS-ART073 | Test Approach & Plan - Registration Services' | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | I | I | I | C | C | I | I | I | I | I | I | I | R | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0029 | Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | Final date by which Elexon are expected to provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-07-13 |  |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0030 | Elexon Central Systems RTTM submitted to Programme for assurance | Final date by which Elexon Central Systems are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-08-04 | No |  | MHHS-ART009 | Requirement Traceability Matrix | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0031 | EES test scenarios submitted to Programme for assurance | Final date by which RECCo (EES) are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-11-02 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A I: C; C I: C; I I: I; C C: C; C C: C; I I: I; I I: I; I I: I; I I: A/R; I I: I; I I: I; I I: I; I I: I; I I: I; I I: I; I I: I; I I: I
| T3 |  | T3-DB-0032 | Elexon Central Systems test scenarios submitted to Programme for assurance | Final date by which Elexon Central Systems are expected provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-08-04 | No |  |  | Test Approach & Plan - Elexon Central Systems | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0034 | DIP RTTM submitted to Programme for assurance | Final date by which the DIP provider are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-08-04 | No |  | MHHS-ART009 | Requirement Traceability Matrix | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | C | I | C | C | I | I | I | I | I | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0035 | DIP Simulator uplifted to align with Interim Release 2 | The Simualtors will be reviewed and assessed against Design interim release 2 and uplifted to include any changes that are required. The simulators will be fully tested and corresponding business readiness activities completed prior to release. | DB | 2023-08-11 | No |  |  |  | TMAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0036 | DIP PIT test scenarios submitted to Programme for assurance | Final date by which DIP are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-07-31 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | A/R | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0037 | All SIT Suppliers test scenarios' submitted to Programme for assurance | Final date by which Suppliers are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-10-05 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | [7 empty] | A/R | A/R | A/R | A/R | I | I |  | I | I | I | I | I | I | I
| T3 |  | T3-DB-0038 | All Data Services Test Approach & Plans (PIT) submitted to Programme for assurance | Final date by which Data Services are expected to provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-08-11 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: A C to I I; I I to I I
| T3 |  | T3-DB-0039 | DIP Simulator uplifted to align with Interim Release 5 | The Simualtors will be reviewed and assessed against Design interim release 5 and uplifted to include any changes that are required. The simulators will be fully tested and corresponding business readiness activities completed prior to release. | DB | 2023-11-03 | No |  |  |  | TMAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0040 | All Metering Services Test Approach & Plans (PIT) submitted to Programme for assurance | Final date by which SIT Metering Services are expected provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-08-25 | No |  |  | Test Approach & Plan - SIT Metering Services | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | I | I | I | I | I | I | C | C | C | C | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-DB-0042 | Registration Services RTTM submitted to Programme for assurance | Final date by which the Registration Services are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-09-01 | No |  | MHHS-ART009 | Requirement Traceability Matrix | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | I | I | I | C | C | I | I | I | I | I | I | I | R | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0044 | Registration Services test scenarios submitted to Programme for assurance | Final date by which Registration Services are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-09-01 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | A/R | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0046 | All SIT Suppliers Test Approach & Plans (PIT) submitted to Programme for assurance | Final date by which SIT Suppliers are expected provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-09-15 | No |  |  | Test Approach & Plan - SIT Suppliers | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | I | I | I | I | I | I | R | R | R | R | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0048 | All Metering Services RTTMs submitted to Programme for assurance | Final date by which the SIT Metering Services' are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-09-15 | No |  | MHHS-ART009 | Requirement Traceability Matrix | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | I | C | C | C | C | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-DB-0050 | All Metering Services test scenarios' submitted to Programme for assurance | Final date by which Metering Services are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-09-15 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: I to I; I to I
| T3 |  | T3-DB-0052 | All UMSO Test Approach & Plans (PIT) submitted to Programme for assurance | Final date by which UMSOs are expected provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-10-13 | No |  |  | Test Approach & Plan - UMSO | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | I | I | I | I | I | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0054 | All Network Operation Test Approach & Plans (PIT) submitted to Programme for assurance | Final date by which Network Operation Services are expected provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-09-15 | No |  |  | Test Approach & Plan - Network Operation Services | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | I | I | I | I | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0056 | All Data Services test scenarios' submitted to Programme for assurance | Final date by which Data Services are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-09-20 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: I to I; I to I
| T3 |  | T3-DB-0058 | All Data Services RTTMs submitted to Programme for assurance | Final date by which Data Services are expected to provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-09-20 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: I to I; I to I
| T3 |  | T3-DB-0060 | All UMSO RTTMs submitted to Programme for assurance | Final date by which the UMSOs are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-11-02 | No |  | MHHS-ART009 | Test Approach & Plan - Registration Services' | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0062 | All Network Operation RTTMs submitted to Programme for assurance | Final date by which the Network Operation Services are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-10-05 | No |  | MHHS-ART009 | Test Approach & Plan - Registration Services' | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0064 | All SIT Suppliers RTTMs submitted to Programme for assurance | Final date by which the SIT Suppliers' are expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-10-06 | No |  | MHHS-ART009 | Test Approach & Plan - Registration Services' | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | I | A/R | A/R | A/R | A/R | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0066 | EES Test Approach & Plan (PIT) submitted to Programme for assurance | Final date by which RECCo (EES) is expected to provide their PIT Test Approach & Plan to the MHHS SI Test Team for review and assurance | DB | 2023-10-13 | No |  |  | Test Approach & Plan - RECCo (EES) | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0068 | DCC Test Approach & Plan (PIT) submitted to Programme for assurance | Final date by which DCC is expected to provide their Programme PIT Test Approach and Plan (equivalent to DCC SIT) to the MHHS SI Test Team for review and assurance. | DB | 2023-11-17 | No |  |  | PIT Test Completion Report - DCC (DSP) | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0072 | EES RTTM submitted to Programme for assurance | Final date by which RECCo (EES) is expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-11-02 | No |  | MHHS-ART009 | Requirement Traceability Matrix | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | C | C | C | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0074 | DCC RTTM submitted to Programme for assurance | Final date by which DCC is expected provide their RTM to the MHHS SI Test Team for review and assurance | DB | 2023-12-15 | No |  |  | Testing Heatmap - DCC | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | I: C; I: C; I: I; C: I; C: C; I: I; I: I; I: I; I: A/R
| T3 |  | T3-DB-0078 | DCC test scenarios submitted to Programme for assurance | Final date by which DCC are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-12-15 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0081 | Interim release 4 Go live | Design updates and change requests included in the interim 4 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2023-08-30 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0083 | Interim release 5 Go live | Design updates and change requests included in the interim 5 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2023-10-04 | No | T1-TE-1000 |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0085 | Interim release 6 Go live | Design updates and change requests included in the interim 6 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2023-11-01 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0087 | All SIT Functional PIT Completion Reports submitted to Programme for Assurance | Final date by which SIT Functional (MVC) PPs are expected provide their PIT Test Completion Report for their SIT Functional DBT to the MHHS SI Test Team for review and assurance. | DB | 2024-02-09 | No |  |  | PIT Test Completion Report - SIT Functional (MVC) PPs | tMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0089 | SIT Functional PIT test scenarios submitted to Programme for assurance | Final date by which SIT Functional (MVC) PPs are expected to provide their test scenarios to the MHHS SI Test Team for review and assurance | DB | 2023-12-07 | No |  |  | PIT Test Completion Report - SIT Functional (MVC) PPs | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0091 | SIT Functional PIT RTTM submitted to Programme for assurance | Final date by which SIT Functional (MVC) PPs is expected provide their RTTM to the MHHS SI Test Team for review and assurance | DB | 2023-12-07 | No |  |  | PIT Test Completion Report - SIT Functional (MVC) PPs | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0093 | SIT Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | Final date by which SIT Functional (MVC) PPs are expected provide their PIT Approach & Plan for their SIT Functional DBT to the MHHS SI Test Team for review and assurance | DB | 2023-11-17 | No |  |  | PIT Test Completion Report - SIT Functional (MVC) PPs | tMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | I | I | I | I | I | I | I | I | I | A/R | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-DB-0095 | Interim release 1 Go live | Design updates and change requests included in the interim 1 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2023-06-12 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0096 | Interim release 2 Go live | Design updates and change requests included in the interim 2 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2023-07-05 | No | T1-TE-1000 |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0097 | Interim release 3 Go live | Design updates and change requests included in the interim 3 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2023-08-02 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0098 | Interim release 7 Go live | Design updates and change requests included in the interim 7 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2024-01-31 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0099 | Interim release 8 Go live | Design updates and change requests included in the interim 8 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2024-04-03 | No |  |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0106 | Elexon Central Systems Test approach and plan MHHS Review Completed | SI Test completed document review | DB | 2023-09-22 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0107 | Elexon Central Systems RTTM MHHS Review Completed | SI Test completed document review | DB | 2023-09-22 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0108 | Elexon Central Systems Test scenarios MHHS Review Completed | SI Test completed document review | DB | 2023-09-22 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0109 | Elexon Central Systems PIT Completion Report submitted to Programme for assurance | Document received by Programme | DB | 2023-09-27 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0110 | Elexon Central Systems PIT Completion Report MHHS Review Completed | SI Test completed document review | DB | 2023-10-11 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0111 | DIP PIT Completion Report (Interim Release 1) submitted to Programme for assurance | Document received by Programme | DB | 2023-10-09 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0112 | DIP PIT Completion Report (Interim Release 1) MHHS Review Completed | SI Test completed document review | DB | 2023-10-23 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0113 | DIP PIT Completion Report (Interim Release 2) submitted to Programme for assurance | Document received by Programme | DB | 2023-10-23 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0114 | DIP PIT Completion Report (Interim Release 2) MHHS Review Completed | SI Test completed document review | DB | 2023-11-06 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0115 | DCC Test Approach & Plan (PIT) MHHS Review Completed | SI Test completed document review | DB | 2023-12-15 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0116 | DCC RTTM MHHS Review Completed | SI Test completed document review | DB | 2024-01-26 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0117 | DCC Test Scenarios MHHS Review Completed | SI Test completed document review | DB | 2024-01-26 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0119 | EES Test approach and plan (PIT) MHHS Review Completed | SI Test completed document review | DB | 2023-11-09 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0120 | EES RTTM MHHS Review Completed | SI Test completed document review | DB | 2023-11-30 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0121 | EES Test scenarios MHHS Review Completed | SI Test completed document review | DB | 2023-11-30 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0122 | EES PIT Completion Report submitted to Programme for assurance | Document received by Programme | DB | 2024-01-05 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0123 | EES PIT Completion Report MHHS Review Completed | SI Test completed document review | DB | 2024-01-19 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0124 | Registration Services Test approach and plan MHHS Review Completed | SI Test completed document review | DB | 2023-09-22 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0125 | Registration Services RTTM MHHS Review Completed | SI Test completed document review | DB | 2023-09-29 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0126 | Registration Services Test scenarios MHHS Review Completed | SI Test completed document review | DB | 2023-09-29 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0127 | Registration Services PIT (CIT interval 2) Completion Report submitted to Programme for assurance | Document received by Programme | DB | 2023-10-25 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0128 | Registration Services PIT (CIT interval 2) Completion Report MHHS Review Completed | SI Test completed document review | DB | 2023-11-03 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0129 | All Data Services Test approach and plans MHHS Review Completed | SI Test completed document review | DB | 2023-09-21 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0130 | All Data Services RTTMs MHHS Review Completed | SI Test completed document review | DB | 2023-09-29 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0131 | All Data Services Test scenarios' MHHS Review Completed | SI Test completed document review | DB | 2023-09-28 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0132 | All Data Services PIT Completion Reports submitted to Programme for assurance | Document received by Programme | DB | 2023-11-03 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0133 | All Data Services PIT Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2023-11-17 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0134 | All Metering Services Test approach and plans MHHS Review Completed | SI Test completed document review | DB | 2023-10-20 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0135 | All Metering Services MHHS Reviews Completed | SI Test completed document review | DB | 2023-10-27 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0136 | All Metering Services Test scenarios' MHHS Review Completed | SI Test completed document review | DB | 2023-10-27 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0137 | All Metering Services PIT Completion Reports submitted to Programme for assurance | Document received by Programme | DB | 2023-11-17 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0138 | All Metering Services PIT Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2023-12-01 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0139 | All SIT Functional Test approach and plans MHHS Reviews Completed | SI Test completed document review | DB | 2024-01-11 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0140 | All SIT Functional RTTMs MHHS Reviews Completed | SI Test completed document review | DB | 2024-01-18 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0141 | All SIT Functional Test scenarios' MHHS Reviews Completed | SI Test completed document review | DB | 2024-01-18 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0142 | All SIT Functional PIT Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2024-02-23 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0143 | All SIT Migration PIT Test Approach & Plans submitted to Programme for assurance | Document received by Programme | DB | 2024-02-16 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0144 | All SIT Migration PIT Test approach and plans MHHS Reviews Completed | SI Test completed document review | DB | 2024-04-11 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0145 | All SIT Migration PIT RTTMs submitted to Programme for assurance | Document received by Programme | DB | 2024-03-07 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0146 | All SIT Migration RTTMs MHHS Reviews Completed | SI Test completed document review | DB | 2024-04-18 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0147 | All SIT Migration PIT test scenarios submitted to Programme for assurance | Document received by Programme | DB | 2024-03-07 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0148 | All SIT Migration Test scenarios MHHS Reviews Completed | SI Test completed document review | DB | 2024-04-18 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0149 | All SIT Migration PIT Completion Reports submitted to Programme for assurance | Document received by Programme | DB | 2024-05-10 | Yes |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0150 | All SIT Migration PIT Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2024-05-24 | Yes |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0151 | SIT Non-Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | Document received by Programme | DB | 2024-09-27 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0152 | SIT Non-Functional Test approach and plan MHHS Review Completed | SI Test completed document review | DB | 2024-11-22 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0153 | SIT Non-Functional PIT RTTM submitted to Programme for assurance | Document received by Programme | DB | 2024-11-01 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0154 | SIT Non-Functional RTTM MHHS Review Completed | SI Test completed document review | DB | 2024-11-29 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0155 | SIT Non-Functional PIT test scenarios submitted to Programme for assurance | Document received by Programme | DB | 2024-11-01 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0156 | SIT Non-Functional Test scenarios MHHS Review Completed | SI Test completed document review | DB | 2024-11-29 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0157 | SIT Non-Functional PIT Completion Report submitted to Programme for assurance | Document received by Programme | DB | 2024-11-29 | Yes |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0158 | SIT Non-Functional PIT Completion Report MHHS Review Completed | SI Test completed document review | DB | 2024-12-20 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0159 | SIT Operational PIT Test Approach & Plan (PIT) submitted to Programme for assurance | Document received by Programme | DB | 2024-09-27 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0160 | SIT Operational Test approach and plan MHHS Review Completed | SI Test completed document review | DB | 2024-11-21 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0161 | SIT Operational PIT RTTM submitted to Programme for assurance | Document received by Programme | DB | 2024-11-01 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0162 | SIT Operational RTTM MHHS Review Completed | SI Test completed document review | DB | 2024-11-29 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0163 | SIT Operational PIT test scenarios submitted to Programme for assurance | Document received by Programme | DB | 2024-11-01 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0164 | SIT Operational Test scenarios MHHS Review Completed | SI Test completed document review | DB | 2024-11-29 | 'No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0165 | SIT Operational PIT Completion Report submitted to Programme for assurance | Document received by Programme | DB | 2024-11-29 | Yes |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0166 | SIT Operational PIT Completion Report MHHS Review Completed | SI Test completed document review | DB | 2025-01-31 | Yes |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0167 | All SIT Suppliers Test Approach & Plans MHHS Review Completed | SI Test completed document review | DB | 2023-10-12 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0168 | All SIT Suppliers RTTMs MHHS Review Completed | SI Test completed document review | DB | 2023-11-03 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0169 | All SIT Suppliers Test scenarios' MHHS Review Completed | SI Test completed document review | DB | 2023-11-02 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0170 | All SIT Suppliers PIT Completion Reports submitted to Programme for assurance | Document received by Programme | DB | 2023-12-08 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0171 | All SIT Suppliers PIT Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2023-12-22 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0172 | All Network Operation Test Approach & Plans MHHS Review Completed | SI Test completed document review | DB | 2023-10-12 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0173 | All Network Operation RTTMs MHHS Review Completed | SI Test completed document review | DB | 2023-11-02 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0174 | All Network Operation test scenarios' MHHS Review Completed | SI Test completed document review | DB | 2023-11-02 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0175 | All Network Operation PIT (CIT interval 5) Completion Reports submitted to Programme for assurance | Document received by Programme | DB | 2023-12-08 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0176 | All Network Operation PIT (CIT interval 5) Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2023-12-22 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0177 | All UMSO Test Approach & Plans MHHS Review Completed | SI Test completed document review | DB | 2023-11-09 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0178 | All UMSO RTTMs MHHS Review Completed | SI Test completed document review | DB | 2023-11-30 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0179 | All UMSO Test scenarios' MHHS Review Completed | SI Test completed document review | DB | 2023-11-30 | 'No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0180 | All UMSO PIT (CIT interval 6) Completion Reports submitted to Programme for assurance | Document received by Programme | DB | 2024-01-05 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0181 | All UMSO PIT (CIT interval 6) Completion Reports MHHS Review Completed | SI Test completed document review | DB | 2024-01-19 | Yes |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-DB-0182 | DIP Simulator uplifted to align with Interim Release 7 | The Simualtors will be reviewed and assessed against Design interim release 7 and uplifted to include any changes that are required. The simulators will be fully tested and corresponding business readiness activities completed prior to release. | DB | 2024-03-22 | No |  |  |  | SITAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0183 | DIP Simulator uplifted to align with Interim Release 8 | The Simualtors will be reviewed and assessed against Design interim release 8 and uplifted to include any changes that are required. The simulators will be fully tested and corresponding business readiness activities completed prior to release. | DB | 2024-06-28 | No |  |  |  | SITAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0184 | Interim Release 8.4 Published | Design updates and change requests included in the interim 8.4 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2024-10-16 | No | M10 |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0185 | Interim Release 8.5 Published | Design updates and change requests included in the interim 8.5 Design Artefact release will be published to the collaboration base and the DIN log will be updated to reflect the published artefact | DB | 2024-11-06 | No | M10 |  |  | DAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-DB-0186 | SIT Non-Functional PIT Completion Report Theme 2 & 3 MHHS Review Completed | SI Test completed document review | DB | 2025-02-21 | No | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0010 | Migration Approach approved | The approval by PSG of the recommended Migration option | MI | 2022-12-07 | No |  | MHHS-DEL770 | Migration Option Analysis | PSG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | C | I | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C | C
| T3 |  | T3-MI-0011 | Migration design artefacts issued for consultation | The Migration Design artefacts are issued to Programme participant (PP) for feedback and review | MI | 2023-02-13 | No |  |  | Migration Design Artefacts | DAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | C | I | I | C | I | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-MI-0012 | Data Assessment Report approved | The approval by TMAG of the Data Assessment Report | MI | 2023-02-28 | No |  | MHHS-ART013 | Data Assessment Report | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | C | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-MI-0013 | Updated Migration Design artefacts issued to PPs for assurance review | Following review and integration of PP consultation feedback, the updated Migration Design artefacts will be issued to Programme participant (PP) for assurance review | MI | 2023-03-03 | No |  |  | Migration Design Artefacts | DAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | A | C | I | I | C | I | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-MI-0014 | Migration, Cutover & Data Strategy approved | The Migration, Cutover and Data Strategy will be approved, reflecting the programme approach to migration preparation activities, the criteria to formally "cutover" and start the migration period, and the process by which the migration period will be managed and governed | MI | 2023-04-28 | No |  | MHHS-ART055 | Migration, Cutover & Data Strategy | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | C | I | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-MI-0017 | MCAG Approval of Consultation 3 | The approval by MCAG of the Migration Framework Artefacts which were reviewed by industry during consultation 3. | MI | 2025-02-25 | No |  |  | Migration Processes & Procedures | SITAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | C | I | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-MI-0020 | Data Cleanse Plan approved | The Data Cleanse Plan will set-out the data population and cleansing activities that are required to uplift data to the completeness and quality required to support System Integration Testing, Migration and ongoing live operations. | MI | 2023-07-19 | No |  |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | C | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-MI-0021 | Threshold volumes approved at TMAG | The approval of the migration threshold volumes at TMAG | MI | 2023-11-20 | No |  |  |  | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | I | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-MI-0022 | Acceptance criteria for M15 agreed at TMAG | The approval of M15 acceptance criteria at TMAG | MI | 2023-12-20 | No |  |  |  | TMAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | I | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-MI-0023 | MCAG Approval of M10/M11 Cut-over Plan | The approval of the cut-over plan at TMAG | MI | 2024-06-04 | No |  |  |  | MCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | I | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-MI-0024 | DCC to extract ESME ID and share with LDSO | The migration of ESME ID from DCC to LDSOs completed | MI | 2024-08-16 | Yes | T1-MI-1000 |  |  | SITAG | PPs in SDS Market Role | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0025 | LDSO ‘full refresh’ between their Registration Service and the EES (ESME ID) | Data has been synced between each LDSO and the EES | MI | 2024-11-11 | No |  |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0026 | LDSO ‘full refresh’ between their Registration Service and the EES (Meter Location and Number of Displayed Register Digits) | The migration of MTD data from each MEM to the relevant registration service completed | MI | 2024-11-18 | Yes | T1-MI-1000 |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0027 | Automated Population of Connection Type for Measurement Classes ‘B’, ‘D’, ‘F’ & ‘G’ | Each LDSO has completed population of connection type data | MI | 2024-10-04 | No |  |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0028 | BAU Population of Connection Type for Site Specific LLFCs within Measurement Classes ‘C’ & ‘E’ | Each LDSO has completed population of connection type data | MI | 2024-10-04 | No |  |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0029 | Automated Population of Connection Type for Smart Meters within Measurement Class ‘A’ | Each LDSO has completed population of connection type data | MI | 2024-10-04 | No |  |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0030 | Automated Population of Null Connection Type | Each LDSO has identified any null conntaction type values and populated with a default value | MI | 2024-10-04 | Yes | T1-MI-1000 |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0031 | Each LDSO has linked al relevant import/export MPANS | Industry has completed the linking of import/export MPANS | MI | 2024-10-18 | No |  |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | C | I | I | A | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0033 | MCAG Approval of Early Life Support Model | MCAG sign-off of Early Life Support Model | MI | 2025-04-29 | No |  | N/A | N/A | MCAG | SI Transition | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | i | I | I | I | I | I | I | I | I
| T3 |  | T3-MI-0034 | Central Systems live and Codes designated at 00:00 | DIP Manager, Elexon (ECS, ISD, Service Management), Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) new systems and processes, and Code Bodies go live | MI | 2025-09-22 | Yes | M10/M11 | N/A | N/A | NA | SI Transition | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C A C A C C C C C C C C C C C C C C C: C; I I I I I I I C C C C C C C C C C C I: I; I I I I I I I I I I C C C C C C C C I: I; R R R R R R R R R R A A A A A A A A I: A; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; I I I I I I I I I I I I I I I I I I I: R; I I I I I I I I I I I I I I I I I I I: R
| T3 |  | T3-MI-0035 | MCAG (Confirm that the Programme can Enter M10) | All Participants have completed pre-M10 Cutover activities | MI | 2025-09-19 | Yes | M10/M11 | N/A | N/A | MCAG | SI Transition | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C A C A C C C C C C C C C C C C C C C: C; I I I I I I I C C C C C C C C C C C I: I; I I I I I I I I I I C C C C C C C C I: I; R R R R R R R R R R A A A A A A A A I: A; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; I I I I I I I I I I I I I I I I I I I: R; I I I I I I I I I I I I I I I I I I I: R
| T3 |  | T3-MI-0036 | Recommendation from MCAG that the Programme can approve M11 / M12 | All Qualified Parties have completed their service activation activities and are in a position to deploy MHHS Functionality to Production | MI | 2025-10-20 | Yes | M11 | N/A | N/A | MCAG | SI Transition | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C A C A C C C C C C C C C C C C C C C: C; I I I I I I I C C C C C C C C C C C I: I; I I I I I I I I I I C C C C C C C C I: I; R R R R R R R R R R A A A A A A A A I: A; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; C C C C C C C C C C C C C C C C C C I: R; I I I I I I I I I I I I I I I I I I I: R; I I I I I I I I I I I I I I I I I I I: R
| T3 |  | T3-MI-0037 | Consultation 2 - Control - MCAG Approval of Interim Artefacts | All Participants have completed pre-M10 Cutover activities | MI | 2024-07-25 | No |  |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C A C A C C C C C C C C C C C C C C C
| T3 |  | T3-MI-0040 | M10 Checkpoint | The progress towards M10 is reviewed 6-months out from the planned due date. | MI | 2025-04-02 | No | M10 |  |  | PSG | PMO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0041 | MCAG Approval of Consultation 4 | The Migration Framework Artefacts have been baselined, following consultations 1 - 4. | MI | 2025-04-29 |  | M10 |  |  | SITAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0042 | Schedule Production Complete | Schedule Production has been completed. | MI | 2024-12-20 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0043 | Supplier Schedule Submission #2 complete | Second Supplier Submission is complete | MI | 2025-06-20 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0044 | MCC Dress Rehersal 1 - complete | MCC Dress Rehersal 1 has been completed. | MI | 2025-07-15 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0045 | MCC Dress Rehersal 2 - complete | MCC Dress Rehersal 2 has been completed. | MI | 2025-08-29 |  | M10 |  |  | MCAG | SI Migration | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0046 | M10 Checkpoint 2 Complete | PSG have reviewed M10 acceptance criteria is on track for M10 complete. | MI | 2025-07-02 |  |  |  |  | PSG | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0047 | M10 Acceptance Criteria Ratification | Governance sign off for M10 completion. | MI | 2025-09-24 |  | M10 |  |  | PSG | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T4 |  | T3-MI-0048 | PSG (OFGEM and PSG to Approve That Conditions of M10 and M13 Have Been Met) | OFGEM and PSG to Approve That Conditions of M10 and M13 Have Been Met at PSG. | MI | 2025-09-24 |  | M10 / M13 |  |  | PSG | CPT | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-MI-0500 | M16 Methodology Approved at MCAG | M16 Decision Making and Monitoring Criteria Consultation - M16 Approach Approved at MCAG | MI | 2026-06-23 | No | T1-EL-1000 |  |  | MCAG | SRO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | C | I | C | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C | C
| T3 |  | T3-PC-0010 | Benefit Realisation Report approved | The Benefits Realisation Report will be a concise word document that will summarise the achievement progress of each Success Measure outlined in the Programme Initiation Document (PID) and the Benefits Realisation Plan. It will be produced at milestone 15. The report will capture all the Programme Outcomes and Deliverables that have been identified as contributing to the final achievement of each Success Measure in the Benefits Realisation Plan, as well as the quantifiable delivery progress against each of these Programme Outcomes and Deliverables. | PC | 2027-05-07 | No |  | MHHS-ART124 | Benefit Realisation Report | PSG | PMO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | A | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C | I
| T3 |  | T3-PC-0020 | Operating Model Gap Review with recommendations approved | This product will be provided for Milestone M15 – Full Transition Complete. It will identify where variations to the Target Operating Model, in terms of services and systems, have been incorporated within the process, in agreement with all stakeholders as the development of the design has progressed throughout the programme. The purpose of “Operating Model Variations Review” is to formally document known variations in the solution and to provide insight on the impact or risk associated, and the recommended next steps (if any) to address or tolerate these variations. | PC | 2027-05-07 | No |  | MHHS-ART128 | Operating Model Gap Review with recommendations | IAG | PMO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | I | I
| T3 |  | T3-PC-0030 | Post-Implementation Review approved | The Post Implementation Review (PIR) is conducted at the end of Milestone 15 as detailed in Ofgem’s MHHS Transition Timetable and the detailed programme plan that will supersede it. The purpose of the PIR is to evaluate whether programme’s objectives have been met, identify whether further improvements will deliver any unidentified benefits and ensure lessons learned effectively informs the planning and management of future programmes. | PC | 2027-05-07 | No |  | MHHS-ART129 | Post-Implementation Review | PSG | PMO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | R | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C | C
| T3 |  | T3-PC-0040 | Reinforcement Guide approved | The purpose to provide Programme Participants with an understanding of post implementation and programme closedown and confidence in the processes, procedures and tooling that underpins this. The guide will provide guidance and clarity to Programme Participants, setting expectations for their responsibilities, obligations and outputs post the programme in relation to MHHS. The guide will also include generic useful information to help Programme Participants manage going forward. | PC | 2027-05-07 | No |  | MHHS-ART133 | Reinforcement Guide | PSG | PMO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C | C
| T3 |  | T3-QU-0007 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Programme Test Readiness confirmed | Date when the LDSOs are expected to have completed their preparatory testing and evidence provision & assurance and be able to start for non-SIT LDSO Qualification Testing, as per the plan | QU | 2024-12-20 | No |  |  |  | TMAG / REC PAB / BSC PAB | SI Test / Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | I | A/R | I | A/R | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T3 |  | T3-QU-0008 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Execution Schedule Complete | Date when the BSC & REC PABs are expected to approve the schedule for non-SIT LDSO Qualification Testing | QU | 2024-11-29 | No |  |  |  | TMAG / REC PAB / BSC PAB | SI Test / Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | C | I | A/R | I | A/R | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T3 |  | T3-QU-0009 | Qualification Testing for Non-SIT LDSOs Participants' environments) Ready to start DIP onboarding (incl. certificates and security compliance) | Date when the LDSOs are expected to have their environments ready to start preparatory testing, for non-SIT LDSO Qualification Testing, as per the plan | QU | 2024-08-05 | No |  |  |  | REC PAB / BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | I | A/R | I | A/R | R | R | R | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T3 |  | T3-QU-0010 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | Date when non-SIT LDSO Qualification Testing is expecting to complete | QU | 2025-05-16 | No |  |  |  | REC PAB / BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | C | I | A/R | I | A/R | C | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T3 |  | T3-QU-0011 | Confirmation of Participants for Non-SIT LDSO Qualification Testing | LDSO SIT Participants will be confirmed and therefore this is the date Non-SIT LDSO Qualification Testing Particpants will be confirmed at entry to preparation activities | QU | 2024-03-21 | No | T1-MI-1000 |  |  | TMAG | SI Test / Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | Notified of Non-SIT LDSOs | Notified of Non-SIT LDSOs | Notified of Non-SIT LDSOs | C | A | I | I | R | I | I | C | I | R | I | R | R | R | R | I | I | I | I | I | I | I | I | I | I | I | I | I | C | C
| T3 |  | T3-QU-0012 | Confirmation of participant Qualification Wave allocation | The date by which the Code Bodies confirm to the programme all the participants that will be included in Wave 1 Qualification Testing. | QU | 2024-06-28 | No |  |  |  | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | i | i | i | I
| T3 |  | T3-QU-0016 | Minimum threshold of Qualification Test Plans for Wave 1 Participants required for QT start approved | Minimum threshold of Qualification Test Plans for Wave 1 Participants required for QT start approved, non-milestone activity to track full wave. | QU | 2025-08-15 |  |  |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0017 | Confirmation from Qualification Wave 1 Participants that DIP onboarding has commenced | The final date by which Wave 1 Qualification Test participants are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | QU | 2025-05-26 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | R | I | I | I | C | R | C | R | C | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | [6 empty] | I
| T3 |  | T3-QU-0020 | Minimum threshold of Qualification Test Plans for Wave 2 Participants required for QT start approved | The approval by QAG of the Test Execution Schedule for the Wave 2 Qualification Test stage, non-milestone activity to track full wave. | QU | 2025-09-05 | No |  | Artefact ID not yet defined | Test Execution Schedule - Qualification | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-QU-0021 | Confirmation from Qualification Wave 2 Participants that DIP Onboarding has commenced | The final date by which Wave 2 Qualification Test participants are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | QU | 2025-07-21 | No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | R | I | I | I | C | R | C | R | C | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | [6 empty] | I
| T3 |  | T3-QU-0024 | Minimum threshold of Qualification Test Plans for Wave 3 Participants required for QT start approved | Minimum threshold of Qualification Test Plans for Wave 3 Participants required for QT start approved, non-milestone activity to track full wave. | QU | 2025-11-07 | No |  | 1. MHHS-ART146 2. Artefact ID not yet defined | 1. Qualification Testing Approach & Plan 2. Qualification Test execution schedule | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-QU-0025 | Confirmation from Qualification Wave 3 Participants that DIP Onboarding has commenced | The final date by which Wave 3 Qualification Test participants are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | QU | 2025-09-15 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | R | I | I | I | C | R | C | R | C | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | [6 empty] | I
| T3 |  | T3-QU-0027 | Minimum threshold of Qualification Wave 1 Participant Test Readiness Confirmed | Minimum threshold of Qualification Wave 1 Participant Test Readiness Confirmed, non-milestone activity to track full wave. | QU | 2025-08-22 | No |  |  |  | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T3 |  | T3-QU-0028 | Qualification Wave 1 QT Execution Start | The start of Qualification Wave 1 test execution is approved by PAB (MHHS Programme Informed). | QU | 2025-08-25 | No |  |  |  | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | C | I
| T3 |  | T3-QU-0030 | Qualification Test Plans for Qualification Wave 4 Participants approved | Qualification Test Plans for Qualification Wave 4 Participants approved | QU | 2026-01-09 | No |  | 1. MHHS-ART146 2. Artefact ID not yet defined | 1. Qualification Testing Approach & Plan 2. Qualification Test execution schedule | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-QU-0031 | Confirmation from Qualification 4 Participants that DIP Onboarding has commenced | Confirmation from Qualification 4 Participants that DIP Onboarding has commenced | QU | 2025-11-03 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | C | R | I | I | I | C | R | C | R | C | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | [6 empty] | I
| T3 |  | T3-QU-0033 | Minimum threshold of Qualification Wave 2 Participant Test Readiness Confirmed | Minimum threshold of Qualification Wave 2 Participant Test Readiness Confirmed, non-milestone activity to track full wave. | QU | 2025-10-17 | No |  |  |  | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | C | I
| T3 |  | T3-QU-0034 | Qualification Wave 2 Execution Start | The start of Qualification Wave 2 execution is approved by the PAB (MHHS Programme Informed). | QU | 2025-10-20 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | C | I
| T3 |  | T3-QU-0038 | Minimum threshold of Qualification Wave 3 Participant Test Readiness confirmed | Minimum threshold of Qualification Wave 3 Participant Test Readiness confirmed, non-milestone activity to track full wave. | QU | 2025-12-19 | No |  |  |  | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T3 |  | T3-QU-0039 | Qualification Wave 3 Execution Start | The start of Qualification Wave 3 execution is approved by the PAB (MHHS Programme Informed). | QU | 2026-01-12 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | C | I
| T3 |  | T3-QU-0043 | Qualification Wave 4 Participant Test Readiness Confirmed | QAG approves that all preparation activities required to commence Qualification Testing Wave 4 have been completed and assured. | QU | 2026-03-06 | No |  |  |  | SITAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | C | C | C | C | I
| T3 |  | T3-QU-0044 | Qualification Wave 4 QT Execution Start | The start of Qualification Wave 4 execution is approved by the PAB (MHHS Programme Informed). | QU | 2026-03-09 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | C | I
| T3 |  | T3-QU-0054 | Qualification Wave 1 QT Projected Execution End | The end of Qualification Wave 1 test execution. | QU | 2026-01-09 | No |  |  |  | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | C | R | A/R | R | A/R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-QU-0055 | Qualfication Wave 2 QT Execution End | The end of Qualification Wave 2 test execution. | QU | 2026-02-27 | No |  |  |  | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | C | R | A/R | R | A/R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-QU-0056 | Qualification Wave 3 Projected Execution End | The end of Qualification Wave 3 test execution. | QU | 2026-05-15 | No |  |  |  | BSC PAB & REC Manager | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | C | R | A/R | R | A/R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-QU-0057 | Qualification Wave 4 Projected Execution End | The end of Qualification Wave 4 test execution. | QU | 2026-07-17 | No |  |  |  | BSC PAB & REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | C | R | A/R | R | A/R | R | R | R | R | R | R | R | R | R | R | i | i | i | I | I | I | I
| T3 |  | T3-QU-0063 | Functional Testing elements of Qualification Approach & Plan v2 approvement by REC PAB and BSC PAB | The approval by REC PAB of the SIT Functional Testing Approach & Plan for Qualification. | QU | 2024-03-28 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | I | C
| T3 |  | T3-QU-0064 | Migration Testing elements of Qualification Approach & Plan v2 appoved by REC PAB and BSC PAB | The approval by REC BSC of the SIT Migration Testing Approach & Plan for Qualification. | QU | 2024-03-28 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | I | C
| T3 |  | T3-QU-0065 | Non-Functional Testing elements of Qualification Approach and Plan v3 approved by REC PAB and BSC PAB | The approval by BSC PAB of the SIT Non Functional Testing Approach & Plan for Qualification. | QU | 2024-08-29 | No |  | MHHS-ART073 | Qualification Testing Approach & Plan | REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | C | A/R | C | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | C | C | I | C
| T3 |  | T3-QU-0066 | Qualification Assessment Document v1 approved by REC PAB and BSC PAB | The approval by BSC PAB and REC PAB of the Qualification Assessment Document | QU | 2024-03-28 | No |  |  |  | BSC PAB + REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | I | A/R | I | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-QU-0067 | Qualification Assessment Document v3 approved by REC PAB and BSC PAB | The approval by BSC PAB and REC PAB of the Qualification Assessment Document | QU | 2024-08-29 | No |  |  |  | BSC PAB + REC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | I | I | I | I | A/R | I | A/R | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-QU-0069 | Batch 1-3 Non-SIT LDSO QT Functional Test Scenarios and Test Cases approved | All Functional Non-SIT LDSO Test Scenarios and Test Cases have been developed by the project including review and assurance from LDSOs and Code Bodies. | QU (Non-SIT LDSO) | 2024-04-18 | No | M9+12 | MHHS-DEL 2183 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0070 | Test Scenarios & Cases- Functional - Approved at QAG | Functional Non-SIT LDSO Test Materials approved at QAG | QU (Non-SIT LDSO) | 2024-04-18 | No | M9+12 | MHHS-DEL 2183 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0071 | Test Scenarios & Cases - Non-Functional - Approved at QAG | Non-Functional Non-SIT LDSO Test Scenarios and Test Cases have been developed by the project including review and assurance from LDSOs and Code Bodies. | QU (Non-SIT LDSO) | 2024-08-22 | No | M9+12 | MHHS-DEL 2183 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0072 | Test Scenarios & Cases - Migration - Approved at QAG | Migration Non-SIT LDSO Test Scenarios and Test Cases have been developed by the project including review and assurance from LDSOs and Code Bodies. | QU (Non-SIT LDSO) | 2024-05-23 | No | M9+12 | MHHS-DEL 2183 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0073 | Test Scenarios & Cases - Operational - Approved at QAG | Operational Non-SIT LDSO Test Scenarios and Test Cases have been developed by the project including review and assurance from LDSOs and Code Bodies. | QU (Non-SIT LDSO) | 2024-08-22 | No | M9+12 | MHHS-DEL 2183 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0074 | Non-SIT LDSO QT Test Data Plan Approved by QAG | Test Data Plan supporting Non-SIT LDSO QT is approved at QAG following LDSO and Code Body Consultation | QU (Non-SIT LDSO) | 2024-05-23 | No | M9+12 | MHHS-DEL 813, MHHS-DEL 816 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0075 | PIT Test Approach & Plan Deadline for Submission for Non-SIT LDSO​ QT | Non-LDSOs PIT Approach and Plan documents have been submitted, reviewed by the programme and approved | QU (Non-SIT LDSO) | 2024-07-01 | No | M9+12 | MHHS-DEL 2183, MHHS-DEL 852 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [34 empty] | Critical Path comment is against the project plan, not overall programme plan | bar: C; I to C; A/R to C; I to I
| T3 |  | T3-QU-0076 | Non-SIT LDSO Participants have submitted functional PIT Test Completion Report & evidence for QT Entry​ | Non-'LDSOs have completed PIT, presented their test evidence ahead of QT Entry Readiness | QU (Non-SIT LDSO) | 2024-11-29 | No | M9+12 | MHHS-DEL 2183, MHHS-DEL 852 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [34 empty] | Critical Path comment is against the project plan, not overall programme plan | bar: C; I to C; A/R to C; I to I
| T3 |  | T3-QU-0077 | PP Test Scope Presented at QAG | Non-SIT LDSOs have their final test scopes approved including any placing reliance across Functional, non-Functional, Operational and Migration | QU (Non-SIT LDSO) | 2024-08-22 | No | M9+12 | TBC | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0078 | LDSO Test Environments Connection Confirmed to UIT Environment | LDSOs have connection to DIP and Helix Test Environments as well as ADO confirmed following onboarding and smoke testing | QU (Non-SIT LDSO) | 2024-11-29 | No | M9+12 | TBC | N/A | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [34 empty] | Critical Path comment is against the project plan, not overall programme plan | bar: C; I to C; A/R to C; I to I
| T3 |  | T3-QU-0079 | Non-SIT LDSOs submission deadline for their QT Test Completion Report to MHHS Programme | All LDSOs will have completed their QT scope and submitted their completion report detailing the evidence, errors and concessions for assurance by Code Bodies | QU (Non-SIT LDSO) | 2025-05-16 | No | M10 | TBC | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: R; C: R; I: I; I: I |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0080 | Assessment Criteria (Functional, Non-Functional, Migration, Operational) Approved by REC PAB and BSC PAB | The approval by BSC PAB and REC PAB of the Assessment Criteria (Functional, Non-Functional, Migration, Operational) | QU | 2025-08-14 | No |  |  |  | REC PAB & BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0081 | QAG Approval of Qualification Approach and Plan v3 | The approval by QAG of the Qualification Approach and Plan v3 Document | QU | 2024-08-22 | No |  | MHHS-DEL1118 | Y | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0083 | QAG Endorsement of Qualification Assessment Document v3 | The approval by QAG of the Qualification Approach and Plan v4 Document | QU | 2024-08-22 | No |  | MHHS-DEL2296 | Y | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0084 | Update to Qualification Assessment Document Portal post QAD V3 Complete | QAG have formally endorsd of the Qualification Assessment Document v2 | QU | 2024-09-12 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0085 | M10-Ready Participants are Qualified | The required updates to Qualification Assessment Document Portal post QAD V2 have been completed. | QU | 2025-09-10 | No | M10 | TBC | TBC | REC PAB & BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0086 | SIT Participants are Qualified | BSC PAB and the REC code manager have approved Qualification | QU | 2025-12-17 | No |  | TBC | TBC | REC PAB & BSC PAB | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0087 | Non-SIT LDSO QT Participants have submitted their initial QAD | BSC PAB and the REC code manager have approved Qualification (Non-MVC) | QU | 2025-02-14 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0088 | Non-SIT LDSO QT Participants have submitted their final QAD | The Non-SIT LDSO QT Participants have submitted their initial Qualification Assessment Document for QAG Approval | QU | 2025-05-23 | No | M10 |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0089 | QAG Approval of Non-SIT S&A Test Approach and Plan | QAG approve the Approach and Plan for Non-SIT Supplier and Agent Qualification Testing | QU (Non-SIT S&A) | 2024-05-23 |  | M10 |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0090 | BSC & REC PAB Approval of Non-SIT S&A Test Approach and Plan | BSC & REC PAB approve the Approach and Plan for Non-SIT Supplier and Agent Qualification Testing | QU (Non-SIT S&A) | 2024-05-30 |  | M10 |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0091 | QAG Approval of QT Test Data Approach and Plan | Completion of governance for Non-SIT LDSO data approach. | QU (Non-SIT LDSO) | 2024-07-18 |  | M10 |  |  | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0092 | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 1 and 2 | The approval by QAG of the QT Test Data Approach and Plan | QU | 2024-05-23 | No |  | MHHS-DEL2434 | Y | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0094 | Minimum threshold of Qualification Wave 1 Participantsrequired for QT start have submitted their initial QAD | The completion of Qualification Testing Framework (Test Stubs and Supporting UI), non-milestone activity to track full wave. | QU | 2025-07-14 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0095 | Minimum threshold of Qualification Wave 1 Participants' required for QT start to provide status of PIT completion and submit QT Test Plan | The submission of the initial Qualification Assessment Document by Wave 1 participants, non-milestone activity to track full wave. | QU | 2025-07-14 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0096 | Minimum threshold of Qualification Wave 1 Participants required for QT start have submitted PIT Test Completion Report and evidence for QT Entry | Qualification Wave 1 Participants have provided a status report of PIT completion and submitted a QT Test Plan, non-milestone activity to track full wave. | QU | 2025-07-14 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0097 | 80% of M14 Critical Qualification Wave 1 Participants have submitted their final QAD | The submission of PIT Test Completion Report and evidence for QT Entry by Qualification Wave 1 Participants , non-milestone activity to track full wave. | QU | 2026-01-16 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0098 | Minimum threshold of Qualification Wave 2 Participants required for QT start have submitted their initial QAD | The submission of the final Qualification Assessment Document by Wave 1 participants, non-milestone activity to track full wave. | QU | 2025-09-12 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0099 | Minimum threshold of Qualification Wave 2 Participants' required for QT start to provide status of PIT completion and submit QT Test Plan | The submission of the initial Qualification Assessment Document by Wave 2 participants, non-milestone activity to track full wave. | QU | 2025-08-18 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0100 | Minimum threshold of Qualification Wave 2 Participants required for QT start have submitted PIT Test Completion Report and evidence for QT entry | Qualification Wave 2 Participants have provided a status report of PIT completion and submitted a QT Test Plannon-milestone activity to track full wave. | QU | 2025-09-08 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0101 | 80% of M14 Critical Qualification Wave 2 Participants have submitted their final QAD | The submission of PIT Test Completion Report and evidence for QT Entry by Wave 2 participants, non-milestone activity to track full wave. | QU | 2026-03-06 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0102 | Minimum threshold of Qualification Wave 3 Participants required for QT start have submitted their initial QAD | The submission of the final Qualification Assessment Document by Wave 2 participants, non-milestone activity to track full wave. | QU | 2025-11-07 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0103 | Minimum threshold of Qualification Wave 3 Participants' required for QT start to provide status of PIT completion and submit QT Test Plan | The submission of the initial Qualification Assessment Document by Wave 3 participants, non-milestone activity to track full wave. | QU | 2025-10-20 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0104 | Minimum threshold of Qualification Wave 3 Participants required for QT start have submitted PIT Test Completion Report and evidence for QT Entry | Qualification Wave 3 Participants have provided a status report of PIT completion and submitted a QT Test Plan, non-milestone activity to track full wave. | QU | 2025-11-10 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0105 | 80% of M14 Critical Qualification Wave 3 Participants have submitted their Final QAD | The submission of PIT Test Completion Report and evidence for QT Entry by Wave 3 participants, non-milestone activity to track full wave. | QU | 2026-05-22 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0106 | Qualification Wave 4 Participants have submitted their Initial QAD | The submission of the final Qualification Assessment Document by Wave 4 participants | QU | 2026-01-16 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0107 | Qualification Wave 4 Participants' to provide status of PIT completion and submit QT Test Plan | The submission of the initial Qualification Assessment Document by Wave 4 participants | QU | 2025-12-08 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0108 | Qualification Wave 4 Participants have submitted PIT Test Completion Report and evidence for QT entry | Qualification Wave 4 Participants have provided a status report of PIT completion and submitted a QT Test Plan | QU | 2026-01-09 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0109 | Qualification Wave 4 Participants have submitted their Final QAD | The submission of PIT Test Completion Report and evidence for QT Entry by Wave 4 participants | QU | 2026-07-24 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0110 | QAG Approval for Operational, Non-Functional & Migration Annexes of Approach & Plan | The submission of the final Qualification Assessment Document by Wave 4 participants | QU (Non-SIT LDSO) | 2024-08-22 | No | M9+12 | MHHS-DEL 2183 | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0111 | Agree Test Execution Timetable Format at QAG, Including Anonymisation Requirements | Plan format for LDSOs to complete agreed at QWG | QU (Non-SIT LDSO) | 2024-07-18 | No | M9+12 | TBC | Y | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [34 empty] | Critical Path comment is against the project plan, not overall programme plan | bar: C; I to C; A/R to C; I to I
| T3 |  | T3-QU-0112 | Test Data Cut Complete | All LDSOs have completed their test data cut (between 3 and 17 June) | QU (Non-SIT LDSO) | 2024-06-17 | No | M9+12 | TBC | N/A | NA | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: R; C: R; I: I; I: I |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0113 | Test Data Signed Off | Following review, the test data for all LDSOs has been approved by MHHSP and Code Bodies | QU (Non-SIT LDSO) | 2024-12-06 | No | M9+12 | TBC | Y | NA | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0114 | Test Plan Submission to MHHS Programme For Review | All LDSOs have submitted their QT Test Plans (based on the format in T3-QU-0111) | QU (Non-SIT LDSO) | 2024-07-26 | No | M9+12 | TBC | Y | NA | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [34 empty] | Critical Path comment is against the project plan, not overall programme plan | bar: C; I to C; A/R to C; I to I
| T3 |  | T3-QU-0115 | Non-SIT LDSO QT Test Execution Starts | The Non-SIT LDSO QT test execution window is approved to open | QU (Non-SIT LDSO) | 2025-01-06 | No | M9+12 | N/A | N/A | NA | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C: I; I: I; I: I; C: I; A/R: C; C: I; A: C; C: C; C: C; C: C; I: A; I: A |  |  | Critical Path comment is against the project plan, not overall programme plan
| T3 |  | T3-QU-0116 | Interim Test Readiness Report Submission to MHHS Programme for Review | Prior to final readiness review, LDSOs have completed their interim assessment reports to inform them of gaps and areas to develop ahead of final readiness review | QU (Non-SIT LDSO) | 2024-07-26 | No | M9+12 | TBC | Y | NA | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | [34 empty] | Critical Path comment is against the project plan, not overall programme plan | bar: C; I to C; A/R to C; I to I
| T3 |  | T3-QU-0118 | Pre-Qualification Submission and PIT Test Plan Deadline for Submission​ | The final date by when Pre-Qualification Submission and PIT Test Plans should be submitted by Non-SIT Supplier and Agents. | QU | 2024-04-26 | No |  |  |  | QAG | Code Bodies | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0119 | QAG Approval of QT Migration Test Scenarios and Test Cases Batches 1 | The Migration Test Scenarios and Test Cases (Batch 1) required for QT are approved at QAG | QU | 2024-07-18 | No |  |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0123 | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 3 | Completion of governance for all functional test materias for Non-SIT LDSO Qualification testing. | QU (Non-SIT LDSO) | 2025-02-20 |  | M10 |  |  | QAG | Non-SIT LDSO Qualifcation | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0124 | E2E Sandbox Test Data Approach and Plan | This document should be read alongside the E2E Sandbox Guidance document. This document sets out the approach for how test data will be created and managed in support of participants if they choose to carry out Sandbox Testing. | QU | 2025-04-16 | No |  | TBC | Y | QAG | Sandbox (Qualification Governance) | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C to I; C to A; C to I
| T3 |  | T3-QU-0125 | UIT E2E Sandbox Preparation Complete | UIT E2E Sandbox Preparation has been completed | QU | 2025-05-26 |  | M10 |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0126 | Sandbox Testing Start (UIT) - Supplier and Agent Participants | Sandbox Testing Start (UIT) for Supplier and Agent Participants | QU | 2025-09-01 |  | M14 |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0127 | Sandbox Testing End (UIT) - Supplier and Agent Participants | Sandbox Testing End (UIT) for Supplier and Agent Participants | QU | 2026-08-28 |  | M14 |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0128 | SIT PPs E2E Sandbox Testing Start | SIT PPs E2E Sandbox Testing Start | QU | 2025-08-08 |  | M14 |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0129 | SIT PPs E2E Sandbox Testing End | SIT PPs E2E Sandbox Testing End | QU | 2025-10-24 |  | M14 |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0130 | Sandbox Testing Start (UIT) - LDSO Participants | The Sandbox testing window opens for LDSO Participants. | QU | 2025-06-02 |  |  |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0131 | Sandbox Testing End (UIT) - LDSO Participants | The Sandbox testing window closes for LDSO Participants. | QU | 2026-01-22 |  |  |  |  | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
T3 | T3 |  | T3-QU-0132 | UIT E2E Sandbox Preparation Complete - Supplier and Agent | QAG approves that all preparation activities required to commence UIT E2E Sandbox have been completed and assured. | TE | 2025-09-01 | No |  | 1. MHHS-ART154 2. MHHS-ART147 | 1. E2E Sandbox Test Data Approach and Plan 2. E2E Sandbox Guidance | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
T3 | T3 |  | T3-QU-0133 | Confirmation from Qualification Wave 1 Participants that DIP onboarding has completed | Qualification Wave 1 participants confirm that their DIP onboarding has concluded. | QU (Non-SIT S&A) | 2025-07-11 |  | M10 |  |  | QAG | S and A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
T3 | T3 |  | T3-QU-0134 | 80% of M14 Critical Wave 1 Participants Qualification approved by BSC PAB and REC Manager | 80% of M14 Critical Wave 1 Participants Qualification approved by BSC PAB and REC Manager, non-milestone activity to track full wave approval. | QU | 2026-04-15 |  | M14 |  |  | QAG | S&A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0135 | 80% of M14 Critical Wave 2 Participants Qualification approved by BSC PAB and REC Manager | 80% of M14 Critical Wave 2 Participants Qualification approved by BSC PAB and REC Manager, non-milestone activity to track full wave approval. | QU | 2026-05-28 |  | M14 |  |  | QAG | S&A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-QU-0136 | 80% of M14 Critical Wave 3 Participants Qualification approved by BSC PAB and REC Manager | 80% of M14 Critical Wave 3 Participants Qualification approved by BSC PAB and REC Manager, non-milestone activity to track full wave approval. | QU | 2026-07-30 |  | M14 |  |  | QAG | S&A Qualification | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-RE-0300 | Code drafting for Governance and Qualification topic areas approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2023-11-22 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | R | A/R | C | C | C | A/R | I
| T3 |  | T3-RE-0350 | Code drafting for Interfaces / Data Specification topic areas approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2024-01-23 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | C | C | C | A/R | C
| T3 |  | T3-RE-0400 | Code drafting for Migration topic area approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2023-11-22 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | A/R | A/R | C | A/R | C | I
| T3 |  | T3-RE-0450 | Code drafting for Transition Text topic area approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2024-01-23 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | PP | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | C | C | C | A/R | C
| T3 |  | T3-RE-0500 | Final code drafting (mop-up) approved | Code drafting for the topic area has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2024-05-22 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | SRO Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | A/R | C | A/R | A/R | C
| T3 |  | T3-RE-0550 | CCAG recommend final code to PSG for baselining | Final suite of code drafting documents has been sent out for industry review via consultation and participant comments have been actioned by code drafters.The final CDWG recommended version of the drafting has been approved by CCAG. | RE | 2024-08-21 | No | T1-RE-1000 | MHHS-ART060 | Draft code changes delivered to all impacted code management bodies, following approval by programme governance | CCAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | I | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | A/R | A/R | C | A/R | A/R | C
| T3 |  | T3-RE-0600 | Resources confirmed | M8 Code Change Resources confirmed | RE | 2025-01-31 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0650 | CDWG Endorsement | CDWG Endorsement | RE | 2025-06-10 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0700 | CCAG Endorsement | CCAG Endorsement | RE | 2025-06-25 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0750 | Send to Ofgem for SCR Direction | Send to Ofgem for SCR Direction | RE | 2025-06-25 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0800 | Freeze M8 Change Control Log 1.0 and create V2.0 | Freeze M8 Change Control Log 1.0 and create V2.0 | RE | 2025-07-02 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0850 | Agree Fast Track Code Change Process | Agree Fast Track Code Change Process | RE | 2025-07-02 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0900 | Ofgem direct SCR Code change | Ofgem direct SCR Code change | RE | 2025-07-03 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-0950 | Present to Panel | Present to Panel | RE | 2025-07-10 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-1000 | Code Change Industry Consultation | Code Change Industry Consultation | RE | 2025-07-29 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-1050 | Panel Recommendation | Panel Recommendation | RE | 2025-08-14 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-RE-1100 | Ofgem Decision | Ofgem Decision | RE | 2025-09-05 |  |  |  |  | CCAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework | bar: C
| T3 |  | T3-TE-0010 | Environment Approach & Plan approved | The approval by TMAG of the Environment Approach & Plan | TE | 2022-11-16 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-TE-0012 | SIT Component Integration Testing Test Approach & Plan approved | The approval by TMAG of the Test Approach & Plan for the SIT Component Integration stage. | TE | 2023-07-19 | No |  | MHHS-ART073 | Test Approach & Plan - SIT Component Integration | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | C | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0013 | SIT Functional Test Approach & Plan approved | The approval by TMAG of the Test Approach & Plan for the SIT Functional stage. | TE | 2023-08-16 | No |  | MHHS-ART073 | SIT - Functional Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | C | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0014 | SIT Component Integration Testing Test scenarios approved | The approval by TMAG of Test scenarios for SIT Component Integration | TE | 2023-08-30 | No |  | MHHS-ART148 | SIT - Component Integration Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0015 | SIT Functional Testing Test scenarios (themes 1-5) approved | The approval by TMAG of Test scenarios for the SIT Functional stage. | TE | 2023-12-08 | No |  | MMHS-ART073 | SIT Functional Testing Approach & Plan (formerly E2E Testing Approach and Plan) | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0018 | SIT Migration Testing Test Approach & Plan approved | The approval by TMAG of the Test Approach & Plan for the SIT Migration stage. | TE | 2023-12-20 | No |  | MHHS-ART073 | SIT - Migration Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0019 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 1 | The final date by which all SIT participants are expected to declare that their SIT-A environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2023-09-01 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0020 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 2 | The final date by which all SIT participants are expected to declare that their SIT-A environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2023-09-22 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0021 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 3 | The final date by which all SIT participants are expected to declare that their SIT-A environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2023-10-06 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0022 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 4 | The final date by which all SIT participants are expected to declare that their SIT-A environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2023-10-23 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0023 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 5 | The final date by which all SIT participants are expected to declare that their SIT-A environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2023-11-10 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0024 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 6 | The final date by which all SIT participants are expected to declare that their SIT-A environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2023-11-24 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | C | C | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0026 | SIT Non-Functional Testing Test Approach & Plan approved | 'The approval by TMAG of the Test Approach & Plan for the SIT Non-Functional stage. | TE | 2024-05-15 | No |  | MHHS-ART073 | SIT - Non-Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0029 | SIT Operational Testing Test Approach & Plan approved | The approval by TMAG of the Test Approach & Plan for the SIT Operational stage. | TE | 2024-05-15 | No |  | MHHS-ART073 | SIT - Operational Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | C | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0032 | SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | The end of SIT Component Integration test execution is approved by TMAG | TE | 2024-02-23 | No |  | MHHS-ART074 | SIT - Component Integration Test Completion Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | I | R | R | R | R | R | R | R | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0033 | SIT Participants' SIT B environments ready to start connectivity proving (incl. certificates and security compliance) | The final date by which all SIT participants are expected to declare that their SIT-B environments have been stood up, security certificates applied and they are ready to commence connectivity proving. | TE | 2024-06-05 | No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0034 | SIT Functional Testing Start | The start of SIT Functional Testing is approved by the relevant governance forum. During SIT Functional, together, the systems and their interfaces are tested E2E for compliance with the E2E MHHS Design, using pre-defined E2E business scenarios. | TE | 2024-03-11 | No |  | MHHS-ART073 | SIT Functional Testing Approach & Plan (formerly E2E Testing Approach and Plan) | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0035 | Non-SIT LDSO Test Harness Released | The simulators and emulators team will deliver CSS and SMRS Simulators. The simulators will be fully tested and corresponding business readiness activities completed prior to release. | TE | 2024-11-29 | No |  | MHHS-ART080 | Non-MHHS Simulators - CSS & MPRS | SITAG | SI DevOps | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | C | R | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0040 | Theme 2 & 3 SIT Non-Functional Testing Start | SIT Non-Functional testing for all SIT Participants commences, following conclusion of initial volume testing between DIP and Helix systems. The SIT Non-Functional test stage will test non-functional characteristics (including performance and security requirements) specified in the E2E MHHS Design in an E2E manner. | TE | 2025-03-31 | No |  | MHHS-ART079 | SIT Functional Test Completion Report (formerly Non-Functional Test Completion Report) | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0042 | SIT Operational Testing Start (SIT B) | The start of SIT Operational Testing is approved by the relevant governance forum. During SIT Operational, the systems are tested for compliance with with operational requirements of the E2E MHHS Design. | TE | 2025-03-31 | No |  | 1. MHHS-ART073 2. MHHS-ART143 | SIT - Operational Test Data Approach and Plan 2. Operational Testing Approach & Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0044 | Central Parties' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | The final date by which Central Parties are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | TE | 2024-08-23 | No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | R | R | R | R | R | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0047 | SIT Non-Functional Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | The end of SIT Non-Functional test execution is approved by TMAG | TE | 2025-05-23 | No |  | MHHS-ART079 | SIT Non-Functional Test Completion Report (formerly Non-Functional Test Completion Report) | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0050 | SIT Operational Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Exit Reports to Programme for assurance) | The end of SIT Operational test execution is approved by TMAG | TE | 2025-07-11 | No |  | MHHS-ART081 | Operational Test Completion Report | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | I | I | I | R | R | R | R | R | R | R | R | R | R | R | R | R | R | I | I | I | I | I | I | I
| T3 |  | T3-TE-0060 | Component Integration Testing Interval 1 Start | The start of SIT Component Integration Testing (CIT) is approved by the relevant governance forum. Within the SIT CIT test stage all components of the MHHS E2E solution are integrated and tested for compliance with the interface specifications and codes of connection. This includes step-by-step integration of the DIP (including PKI), central systems, supplier services, Data Services, Metering Services, Registration Services, UMSO services, network operator services, DSP, CSS and DTN. | TE | 2023-10-30 | No |  | MHHS-ART071 | SIT - Component Integration Test Readiness Report | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0061 | Component Integration Testing Interval 2 Start | The start of SIT Component Integration Testing (CIT) Interval 2. Within the SIT CIT test stage all components of the MHHS E2E solution are integrated and tested for compliance with the interface specifications and codes of connection. This includes step-by-step integration of the DIP (including PKI), central systems, supplier services, Data Services, Metering Services, Registration Services, UMSO services, network operator services, DSP, CSS and DTN. | TE | 2023-11-13 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0062 | Component Integration Testing Interval 3 Start | The start of SIT Component Integration Testing (CIT) Interval 3. Within the SIT CIT test stage all components of the MHHS E2E solution are integrated and tested for compliance with the interface specifications and codes of connection. This includes step-by-step integration of the DIP (including PKI), central systems, supplier services, Data Services, Metering Services, Registration Services, UMSO services, network operator services, DSP, CSS and DTN. | TE | 2023-11-27 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0063 | Component Integration Testing Interval 4 Start | The start of SIT Component Integration Testing (CIT) Interval 4. Within the SIT CIT test stage all components of the MHHS E2E solution are integrated and tested for compliance with the interface specifications and codes of connection. This includes step-by-step integration of the DIP (including PKI), central systems, supplier services, Data Services, Metering Services, Registration Services, UMSO services, network operator services, DSP, CSS and DTN. | TE | 2023-12-11 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0064 | Component Integration Testing Interval 5 Start | The start of SIT Component Integration Testing (CIT) Interval 5. Within the SIT CIT test stage all components of the MHHS E2E solution are integrated and tested for compliance with the interface specifications and codes of connection. This includes step-by-step integration of the DIP (including PKI), central systems, supplier services, Data Services, Metering Services, Registration Services, UMSO services, network operator services, DSP, CSS and DTN. | TE | 2024-01-15 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0065 | Component Integration Testing Interval 6 Start | The start of SIT Component Integration Testing (CIT) Interval 6. Within the SIT CIT test stage all components of the MHHS E2E solution are integrated and tested for compliance with the interface specifications and codes of connection. This includes step-by-step integration of the DIP (including PKI), central systems, supplier services, Data Services, Metering Services, Registration Services, UMSO services, network operator services, DSP, CSS and DTN. | TE | 2024-01-29 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | C | R | C | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0067 | E2E Sandbox Guidance approved | The approval by TMAG of the E2E Sandbox Guidance document | TE | 2024-07-18 | No |  | MHHS-ART154 | E2E Sandbox Guidance | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0068 | Environment Approach & Plan - Work Off Approved | The approval by TMAG of the Environment Approach & Plan Work Off Items | TE | 2023-08-16 | No |  | MHHS-ART139 | Environment Approach & Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | C
| T3 |  | T3-TE-0069 | SIT Component Integration Testing Test cases Batch 1 (CIT Intervals 1 and 2) approved at ETMAG | The approval by TMAG of test cases for the SIT Component Integration stage. | TE | 2023-09-29 | No |  | MHHS-ART073 | Test Approach & Plan - SIT Component Integration | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0070 | SIT Functional Testing Test Cases (themes 1-5) approved | The approval by TMAG of test cases for the SIT Functional stage. | TE | 2024-01-17 | No |  | MHHS-ART140 | SIT - Functional Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | C | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0072 | Test Data Overarching Approach & Plan approved by TMAG | The approval by TMAG of the Test Data Overarching Approach and Plan | TE | 2023-07-19 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | C | C | i | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0073 | Test Data (SIT A) Interval 1 Complete | All test data prep activities including cleanse, transform and load are complete for SIT component test data interval 1 | TE | 2023-10-27 | Yes | T1-TE-1000 | MHHS-ART148 MHHS-ART169 | Data Cleanse Plan System Integration Test CIT Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0074 | Test Data (SIT A) Interval 2 Complete | All test data prep activities including cleanse, transform and load are complete for SIT component test data interval 2 | TE | 2023-11-17 | Yes | T1-TE-2000 | MHHS-ART148 MHHS-ART169 | Data Cleanse Plan System Integration Test CIT Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0075 | Test Data (SIT A) Interval 3 Complete | All test data prep activities including cleanse, transform and load are complete for SIT component test data interval 3 | TE | 2023-11-17 | Yes | T1-TE-2000 | MHHS-ART148 MHHS-ART169 | Data Cleanse Plan System Integration Test CIT Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0076 | Test Data (SIT A) Interval 4 Complete | All test data prep activities including cleanse, transform and load are complete for SIT component test data interval 4 | TE | 2023-12-01 | Yes | T1-TE-2000 | MHHS-ART148 MHHS-ART169 | Data Cleanse Plan System Integration Test CIT Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0077 | Test Data (SIT A) Interval 5 Complete | All test data prep activities including cleanse, transform and load are complete for SIT component test data interval 5 | TE | 2023-12-15 | Yes | T1-TE-2000 | MHHS-ART148 MHHS-ART169 | Data Cleanse Plan System Integration Test CIT Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0078 | Test Data (SIT A) Interval 6 Complete | All test data prep activities including cleanse, transform and load are complete for SIT component test data interval 6 | TE | 2023-12-22 | Yes | T1-TE-2000 | MHHS-ART148 MHHS-ART169 | Data Cleanse Plan System Integration Test CIT Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0079 | Cycle 1 - PP's confirmation that test data is ready for SIT Functional | All test data prep activities including cleanse, transform and load are complete for SIT functional for Cycle 1 | TE | 2024-03-01 | Yes | T1-TE-2000 | MHHS-ART140 MHHS-ART169 | Data Cleanse Plan System Integration Test Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0080 | Cycle 2 - PP's confirmation that test data is ready for SIT Functional | All test data prep activities including cleanse, transform and load are complete for SIT functional for Cycle 2 | TE | 2024-06-14 | Yes | T1-TE-2000 | MHHS-ART140 MHHS-ART169 | Data Cleanse Plan System Integration Test Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0081 | All parties to finalise data load | All test data prep activities including cleanse, transform and load are complete for SIT functional for Cycle 3 | TE | 2024-10-21 | Yes | T1-TE-2000 | MHHS-ART140 MHHS-ART169 | Data Cleanse Plan System Integration Test Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0083 | Test Data - ISD Creation Complete | Test ISD data augmented by SI | TE | 2023-09-01 | Yes | T1-TE-2000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0084 | Test Data - SFTP Onboarding Complete | SIT participants can access SSTP | TE | 2023-11-24 | Yes | T1-TE-2000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0085 | Test Data - Provide Sample Files Complete | SI has provided example files to SIT participants | TE | 2023-09-01 | No |  |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0088 | SIT participants have received DCC CSS PKI certificates for UIT-B environment |  | TE | 2023-12-15 |  |  |  |  | TMAG | SIT Participants (Suppliers & Third Parties) | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0089 | SIT participants have received DCC DSP PKI certificates for UIT-B environment |  | TE | 2023-12-15 |  |  |  |  | TMAG | SIT Participants (Suppliers & Third Parties) | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0090 | Environment Approach and Plan - SIT Functional | V2.5 is the current version of the environments approach and plan. This doc will be uplifted to cover the SIT Functional Test env architecture | TE | 2023-11-20 | No |  | MHHS-DEL 618 | Env Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0091 | Environment Approach and Plan - Non SIT LDSO Testing | V2.5 is the current version of the environments approach and plan. This doc will be uplifted to cover the Sit Non Functional env architecture | TE | 2024-04-17 | No |  | MHHS-DEL 619 | Env Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0092 | Environment Approach and Plan - SIT Non Functional | V2.5 is the current version of the environments approach and plan. This doc will be uplifted to cover the qualification and Sandbox env architecture | TE | 2024-06-19 | No |  | MHHS-DEL 620 | Env Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0093 | Environment Approach and Plan - Sandbox | V2.5 is the current version of the environments approach and plan. This doc will be uplifted to cover the non-SIT LDSO env architecture | TE | 2024-08-21 | No |  | MHHS-DEL 621 | Env Approach and Plan | QAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0094 | PPs register PKI Officers and request PKI certificates Complete - Interval 1 | MHHS PPs wil require pki certificates to connect to the DIP. They will also be required to appoint PKI Officer | TE | 2023-10-25 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0095 | Test Data - Detailed SIT Functional Data Load Guidance Complete | Summary of SIT data loading activities required per market participant role in prep for SIT Functional test | TE | 2023-12-06 | No |  | MHHS-DEL 1545 | SIT Functionl Data Load Guidance | TMAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0096 | Test Data - Population of Data Items for Testing Guidance - Draft Complete | Document describing the data items used in the DIP interface and the data items identified as required in the D-flows which will continue to be used in the new arrangements. This is an intermediate version describing how the data will be obtained or manufactured | TE | 2023-12-06 | No |  | MHHS-DEL 816 | Population of Data Items for Testing | TMAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0097 | Test Data - Population of Data Items for Testing Guidance - Final Complete | Document describing the data items used in the DIP interface and the data items identified as required in the D-flows which will continue to be used in the new arrangements. This is a final version describing how the data will be obtained or manufactured | TE | 2023-12-15 | No |  | MHHS-DEL 816 | Population of Data Items for Testing | TMAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | R | C | C | A | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I | I
| T3 |  | T3-TE-0098 | PPs Register PKI Officers and request PKI certificates Complete - Interval 2 | MHHS PPs wil require pki certificates to connect to the DIP. They will also be required to appoint PKI Officer | TE | 2023-11-22 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0099 | PPs Register PKI Officers and Request PKI certificates Complete - Interval 3 | MHHS PPs wil require pki certificates to connect to the DIP. They will also be required to appoint PKI Officer | TE | 2023-12-15 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0100 | PPs register PKI Officers and Request PKI Certificates Complete - Interval 4 | MHHS PPs wil require pki certificates to connect to the DIP. They will also be required to appoint PKI Officer | TE | 2023-11-24 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0101 | PPs register PKI Officers and Request PKI Certificates Complete - Interval 5 | MHHS PPs wil require pki certificates to connect to the DIP. They will also be required to appoint PKI Officer | TE | 2023-12-08 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0102 | PPs register PKI Officers and Request PKI Certificates Complete - Interval 6 | MHHS PPs wil require pki certificates to connect to the DIP. They will also be required to appoint PKI Officer | TE | 2023-12-08 | Yes | T1-TE-1000 |  |  | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0103 | SIT Functional Connectivity Proving Complete | In prep for SIT Functional test execution SIT participants will be required to conduct a connectivity proving phase in order to ensure that their market roles connect to all of the other appropriate market roles and central functions | TE | 2024-03-01 | Yes | T1-TE-1000 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0104 | SIT Component Integration Testing Test cases Batch 2 (CIT Intervals 3 and 4) approved at ETMAG | Test cases for CIT (intervals 3 and 4) are approved at TMAG | TE | 2023-11-03 | No | M9+5 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0105 | SIT Component Integration Testing Test cases Batch 3 (CIT Intervals 5 and 6) approved at ETMAG | Test cases for CIT (intervals5 and 6) are approved at TMAG | TE | 2023-12-08 | No | M9+5 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0106 | SIT Functional Testing Test scenarios (themes 6,7,9) approved | The approval by TMAG of Test scenarios for the SIT Functional stage. | TE | 2024-01-17 | No |  | MMHS-ART073 | SIT Functional Testing Approach & Plan (formerly E2E Testing Approach and Plan) | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0107 | SIT Functional Testing Test scenarios (theme 8) approved | The approval by TMAG of Test scenarios for the SIT Functional stage. | TE | 2024-02-21 | No |  | MMHS-ART073 | SIT Functional Testing Approach & Plan (formerly E2E Testing Approach and Plan) | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0108 | SIT Functional Testing Test cases (themes 6,7,9) approved | The approval by TMAG of test cases for the SIT Functional stage. | TE | 2024-01-17 | No |  | MHHS-ART140 | SIT - Functional Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0109 | SIT Functional Testing Test cases (theme 8) approved | The approval by TMAG of test cases for the SIT Functional stage. | TE | 2024-02-21 | No |  | MHHS-ART140 | SIT - Functional Test Data Approach and Plan | TMAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0110 | SIT Migration Test scenarios & Test Cases Approved - Theme 1 | The approval by SITAG of Test Scenarios and test cases for the SIT Migration stage | TE | 2024-03-20 | No |  | N/A | N/A | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0111 | SIT Migration Test scenarios & Test Cases Approved - Theme 2 | The approval by SITAG of Test Scenarios and test cases for the SIT Migration stage | TE | 2024-04-17 | No |  | N/A | N/A | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0112 | SIT Migration Test scenarios & Test Cases Approved - Theme 3 | The approval by SITAG of Test Scenarios and test cases for the SIT Migration stage | TE | 2024-04-17 | No |  | N/A | N/A | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0113 | SIT Non-Functional Testing Test Data Approach & Plan approved | The approval by SITAG of the Test Data Approach & Plan for the SIT Non-Functional stage. | TE | 2024-05-15 | No |  | MHHS-ART073 | SIT - Non-Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | C | I | R | I | C | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0114 | SIT NFT Scenarios & Test Cases Approved - Theme 1 | The approval by SITAG of test scenarios and cases for the SIT Non-Functional stage | TE | 2024-06-19 | No |  | MHHS-ART144 | SIT - Non-Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0115 | SIT NFT Scenarios & Test Cases Approved - Theme 2 | The approval by SITAG of test scenarios and cases for the SIT Non-Functional stage | TE | 2024-07-17 | No |  | MHHS-ART144 | SIT - Non-Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0116 | SIT NFT Scenarios & Test Cases Approved - Theme 3 | The approval by SITAG of test scenarios and cases for the SIT Non-Functional stage | TE | 2024-09-18 | No |  | MHHS-ART144 | SIT - Non-Functional Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0117 | SIT Operational Scenarios & Test Cases Approved - Theme 1 | The approval by SITAG of test scenarios and cases for the SIT Operational stage | TE | 2024-09-06 | No |  | MHHS-ART143 | SIT - Operational Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0118 | SIT Operational Scenarios & Test Cases Approved - Theme 2 | The approval by SITAG of test scenarios and cases for the SIT Operational stage | TE | 2024-09-06 | No |  | MHHS-ART143 | SIT - Operational Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0119 | SIT Operational Scenarios & Test Cases Approved - Theme 3 (Batch 1 + 2) | The approval by SITAG of test scenarios and cases for the SIT Operational stage | TE | 2024-12-18 | No |  | MHHS-ART143 | SIT - Operational Test Data Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | I | I | I | I | I | I
| T3 |  | T3-TE-0120 | Environment Approach and Plan - S and A Testing | V2.5 is the current version of the environments approach and plan. This doc will be uplifted to cover the Sit Non Functional env architecture | TE | 2024-07-17 | No |  | MHHS-DEL 619 | Env Approach and Plan | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework |  |  |  | C | A | I | I | R | I | I | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | I | C | I | I | I
| T3 |  | T3-TE-0121 | SIT Operational Testing Start (Theme 3 - Batch 1 (Service Management)) |  | TE | 2025-02-03 | No |  |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0122 | SIT Regression Suite Approval at SITAG | The full scope of tests needed for regression testing has been agreed at SITAG | TE | 2025-04-24 | No | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0123 | SIT Regression Testing Approach and Plan Approval | The proposed approach to Regression Testing is approved at SITAG | TE | 2025-02-28 | No | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0124 | Theme 1 (Helix and DIP Volume Testing) Start | Non-Functional Theme 1 Testing scripts are approved and overarching readiness reports are endorsed FTIG and SITAG, therefore Non-Functional Theme 1 test execution can commence. | TE | 2025-03-03 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0125 | Exit point identified and evidence capture flags updated | Exit points and evidence capture flags for each of the Functional Sprints have been identified. | TE | 2025-02-07 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0126 | Non-Functional Theme 1 (Avenade) Data Load | Non-Functional Theme 1 Data Load is complete ahead of Theme 1 Testing | TE | 2025-02-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0127 | Non-Functional Theme 2 & 3 (Helix, Avenade & PPs) Data Load | Non-Functional Theme 2 & 3 Data Load for Helix, Avenade & PPs is complete ahead of Theme 1 Testing | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0128 | Non-Functional Themes 2 & 3 (LDSO's and DCC) Data Load | Non-Functional Theme 2 & 3 Data Load for LDSOs and DCC is complete ahead of Theme 2 & 3 Testing | TE | 2025-03-21 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0129 | Operational Themes 1, 2 & 3 (Batch 2) (LDSO's and DCC) Data Load | Operational Theme 2 & 3 Data Load for LDSOs and DCC is complete ahead of Theme 2 & 3 Testing | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0130 | Operational Themes 1, 2 & 3 (Batch 2) (Helix, Avenade & PPs) Data Load | Non-Functional Theme 2 & 3 Data Load for Helix, Avenade & PPs is complete ahead of Theme 2 & 3 Testing | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0131 | Non-Functional and Operational Test Data Preparation Complete | Data preparation for both Non-Functional and Operational is complete | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test Data | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0132 | Version 2 SIT Operations Manual Completed | Helix complete drafting of Version 2 of the Operations Manual | TE | 2024-11-27 |  | M10 |  |  | SITAG | Helix | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0133 | SIT Operations Manual (Final) Version 3 Completed | Helix complete drafting of the final Operation Manual Version 3 | TE | 2025-01-08 |  | M10 |  |  | SITAG | Helix | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0135 | January MCAG (Final SIT Operations Manual Endorsement) [Advisory Group Sign-off] | MCAG endorse Version 3 of the Operations Manual ahead of SIT Ops start. | TE | 2025-01-28 |  | M10 |  |  | SITAG | Helix | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0136 | ServiceNow SIT Ops Available | ServiceNow is ready for SIT Operations. | TE | 2025-01-14 |  | M10 |  |  | SITAG | Helix | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0137 | Stage 1 - Helix SIT Operational Readiness Completed | Heix SIT Operational Readiness activity is complete for Stage 1 | TE | 2025-01-31 |  | M10 |  |  | SITAG | Helix | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0138 | SITAG approve Theme 3 (Batch 2) | SIT Operational Theme 2 (Batch 2) has been reviewed by SITAG, including industry consultation. | TE | 2024-12-18 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0139 | SITAG approve Theme 3 (Batch 1) | SIT Operational Theme 2 (Batch 1) has been reviewed by SITAG, including industry consultation. | TE | 2024-12-18 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0140 | End of Settlement Testing Cycle 3 | Settlement Testing for Cycle 3 has concluded. | TE | 2025-02-21 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0141 | Test Case Rationalisation complete | Functional and Migration rationalisation is complete. | TE | 2025-02-07 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0187 | Interim Release 8.6 Deployed to SIT by Participants | Interim Release 8.6 SIT by Participants has been successfully published, and deployed by participants. | TE | 2025-01-22 |  | M10 |  |  | SITAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0188 | Interim Release 8.7 Deployed to SIT by Participants | Interim Release 8.7 SIT by Participants has been successfully published, and deployed by participants. | TE | 2025-01-27 |  | M10 |  |  | SITAG | SI Design | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0190 | eSITAG approve Non-Functional Theme 1 Overarching Test Readiness Report | An extraordinary SITAG approves the Non-Functional Themes 2 & 3 Overarching Test Readiness Report, giving their endorsement to NF Theme 2 & 3 testing starting. | TE | 2025-02-28 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0191 | eSITAG approve Non-Functional Overarching Test Readiness Report Theme 2 & 3 | An extraordinary SITAG approves the Non-Functional Theme 1 Overarching Test Readiness Report, giving their endorsement to NF Theme 1 testing starting. | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0192 | SITAG approve Theme 3 (Batch 1) Test Readiness Report | SITAG approves the Operational Theme 3 (Batch 1) Overarching Test Readiness Report, giving their endorsement to Operational Theme 1 (Batch 1) testing starting. | TE | 2025-01-29 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T3 |  | T3-TE-0193 | eSITAG approve Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | SITAG approves the Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report, giving their endorsement to Operational Theme 1, 2 and 3 (Batch 2) testing starting. | TE | 2025-03-28 |  | M10 |  |  | SITAG | SI Test | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-MR-0400 | M16 Checkpoint 1 | Review the monitoring data from Step 2 to understand the volume of actual data at each Settlement Run. | MR | 2026-06-25 |  | M16 |  |  | STEG | SRO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-MR-0500 | MCAG Endorses Assessment | STEG to Assess Monitoring Report and recommend interim position to MCAG on Decision 1 - MCAG Endorses Assessment | MI | 2026-07-17 |  | M16 |  |  | MCAG | SRO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-EL-0200 | MCAG Approve Recommendation to change to RF 7 months calendar | Decision 1 RF Change to 7 months from Settlement Day 01/10 - MCAG Approve Recommendation to change to RF 7 months calendar | MI | 2026-09-18 |  | M16 |  |  | MCAG | SRO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework
| T2 |  | T2-EL-0100 | MCAG Approve Recommendation - Confirm M16 Date | Decision 3 SF Change from 15WD to 7WD from Settlement Date 02/07 - MCAG Approve Recommendation - Confirm M16 Date | MI | 2027-06-18 |  | M16 |  |  | MCAG | SRO | Is informed as a PSG member, and as Sponsor addresses any needed escalation per governance framework

## Sheet3 (hidden)
Milestone Title | Milestone ID
BSC PAB & REC Manager sign-off of qualified SIT participants for Migration (post-M8 & pre-M11) | T2-QU-0100
BSC PAB & REC Manager approval of Qualification Testing Tranche 1 Completion | T2-QU-0150
BSC PAB & REC Manager approval of Qualification Testing Tranche 2 Completion | T2-QU-0200
BSC PAB & REC Manager approval of Qualification Testing Tranche 3 Completion | T2-QU-0250
BSC PAB & REC Manager approval of Qualification Testing Tranche 4 Completion | T2-QU-0300
BSC PAB & REC Manager approval of Qualification Testing Tranche 5 Completion | T2-QU-0350
BSC PAB & REC Manager approval of Qualification Testing Tranche 6 Completion | T2-QU-0400
BSC PAB & REC Manager approval of Qualification Testing Tranche 7 Completion | T2-QU-0450
BSC PAB & REC Manager approval of Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Completion (Start of Migration for Qualification Participants) | T2-QU-0500
Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) environments (TBC) ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0009
Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | T3-QU-0010
Confirm Qualification Testing Tranche 1 Participants | T3-QU-0012
Confirm Qualification Testing Tranche 2 Participants | T3-QU-0013
Confirm Qualification Testing Tranche 3 Participants | T3-QU-0014
Confirm Qualification Testing Tranche 4 Participants | T3-QU-0015
Qualification Testing Tranche 1 Test execution schedule approved | T3-QU-0016
Confirm Qualification Testing Tranche 5 Participants | T3-QU-0019
Qualification Testing Tranche 2 Test execution schedule approved | T3-QU-0020
Confirm Qualification Testing Tranche 6 Participants | T3-QU-0023
Qualification Testing Tranche 3 Test execution schedule approved | T3-QU-0024
Qualification Testing Tranche 1 Test Readiness confirmed | T3-QU-0027
Qualification Testing Tranche 1 Start | T3-QU-0028
Confirm Qualification Testing Tranche 7 Participants | T3-QU-0029
Qualification Testing Tranche 4 Test execution schedule approved | T3-QU-0030
Qualification Testing Tranche 2 Test Readiness confirmed | T3-QU-0033
Qualification Testing Tranche 2 Start | T3-QU-0034
Qualification Testing Tranche 5 Test execution schedule approved | T3-QU-0035
Qualification Testing Tranche 3 Test Readiness confirmed | T3-QU-0038
Qualification Testing Tranche 3 Start | T3-QU-0039
Qualification Testing Tranche 6 Test execution schedule approved | T3-QU-0040
Qualification Testing Tranche 4 Test Readiness confirmed | T3-QU-0043
Qualification Testing Tranche 4 Start | T3-QU-0044
Qualification Testing Tranche 7 Test execution schedule approved | T3-QU-0045
Qualification Testing Tranche 5 Test Readiness confirmed | T3-QU-0048
Qualification Testing Tranche 5 Start | T3-QU-0049
Qualification Testing Tranche 6 Test Readiness confirmed | T3-QU-0050
Qualification Testing Tranche 6 Start | T3-QU-0051
Qualification Testing Tranche 7 Test Readiness confirmed | T3-QU-0052
Qualification Testing Tranche 7 Start | T3-QU-0053
Qualification Testing Tranche 1 End | T3-QU-0054
Qualification Testing Tranche 2 End | T3-QU-0055
Qualification Testing Tranche 3 End | T3-QU-0056
Qualification Testing Tranche 4 End | T3-QU-0057
Qualification Testing Tranche 5 End | T3-QU-0058
Qualification Testing Tranche 6 End | T3-QU-0059
Qualification Testing Tranche 7 End | T3-QU-0060
Final Qualification Approach & Plan approved by REC Manager and BSC PAB | T3-QU-0062
Functional Testing elements of Qualification Approach & Plan approved by REC Manager and BSC PAB | T3-QU-0063
Migration Testing elements of Qualification Approach & Plan approved by REC Manager and BSC PAB | T3-QU-0064
Non-Functional Testing elements of Qualification Approach & Plan approved by REC Manager and BSC PAB | T3-QU-0065
Qualification Assessment Document Initial Draft (Functional) | T3-QU-0066
Qualification Assessment Document Baselined | T3-QU-0067
Operational Testing elements of Qualification Approach & Plan approved by REC Manager and BSC PAB | T3-QU-0068
Plan Rebaselined (subject to Ofgem decision) | T1-PM-1000
System Integration Testing Start (M9) | T1-TE-1000
SIT Minimum Viable Cohort Complete (SIT Minimum Viable Cohort Test Exit Report Approved) | T1-TE-2000
M10, M11, M12 and M13 checkpoint - date approval | T2-MR-0100
M14 milestone checkpoint - date approval | T2-MR-0200
M15 milestone checkpoint - date approval | T2-MR-0300
M16 milestone checkpoint - date approval | T2-MR-0400
DCC Capacity Upgrade Operational | T2-MI-0350
Confirm M16 date | T2-EL-0100
Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | T1-CP-1000
Operating Model Gap Review with recommendations approved | T3-PC-0020
Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | T1-CP-2000
Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | T1-CP-3000
Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | T1-CP-4000
Cut over to new settlement timetable (M16) | T1-EL-1000
Cut over to new settlement timetable (M16*) | T1-EL-2000
Central systems ready for migrating MPANs (M10) | T1-MI-1000
Central systems ready for migrating MPANs (M10*) | T1-MI-1500
Load Shaping Service switched on (M13) | T1-MI-2000
Start of 18-month migration for UMS / Advanced (M11) | T1-MI-3000
Start of 18-month migration for Smart / Non-smart (M12) | T1-MI-4000
All suppliers must be able to access MPANs under the new TOM (M14) | T1-MI-5000
All suppliers must be able to access MPANs under the new TOM (M14*) | T1-MI-5500
Full transition complete (M15) | T1-MI-6000
Full transition complete (M15*) | T1-MI-6500
Code changes baselined (M6) | T1-RE-1000
Start of 18-month migration for UMS / Advanced (M11*) | T2-MI-3500
Load Shaping Service switched on (M13*) | T2-MI-2500
Start of 18-month migration for Smart / Non-smart (M12*) | T2-MI-4500
Migration Design approved | T2-MI-0050
Physical design baselined (M5) | T1-DB-1000
Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | T2-RA-0200
Readiness Assessment 4 - Design & Build Checkpoint 2 - Completed (incl. Readiness Assessment Report approval) | T2-RA-0300
Readiness Assessment 5 - Start of Qualification - Completed (incl. Readiness Assessment Report approval) | T2-RA-0400
Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | T2-RA-0500
Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | T2-RA-0600
Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | T2-RA-0700
Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | T2-RA-0800
M16 methodology approved | T2-MI-0500
Benefit Realisation Report approved | T3-PC-0010
Code drafting for Data Services topic area approved | T2-RE-0100
Code drafting for Metering topic area approved | T2-RE-0150
Code drafting for BSC Central Services topic area approved | T2-RE-0200
Code drafting for Registration topic area approved | T2-RE-0250
Code drafting for Governance and Qualification topic areas approved | T2-RE-0300
Code drafting for Interfaces / Data Specification topic areas approved | T2-RE-0350
Code drafting for Migration topic area approved | T2-RE-0400
Code drafting for Transition Text topic area approved | T2-RE-0450
Service Management Strategy approved | T3-BC-0010
DCC PIT Completion Report submitted to Programme for assurance (dependent on DCC TAB) | T3-DB-0024
DIP Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0026
Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0028
Elexon Central Systems RTTM submitted to Programme for assurance | T3-DB-0030
Elexon Central Systems test scenarios submitted to Programme for assurance | T3-DB-0032
DIP RTTM submitted to Programme for assurance | T3-DB-0034
Metering Services Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0040
Registration Services RTTM submitted to Programme for assurance | T3-DB-0042
SIT Suppliers Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0046
Metering Services RTTM submitted to Programme for assurance | T3-DB-0048
UMSO Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0052
Network Operation Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0054
UMSO RTTM submitted to Programme for assurance | T3-DB-0060
Network Operation RTTM submitted to Programme for assurance | T3-DB-0062
SIT Suppliers RTTM submitted to Programme for assurance | T3-DB-0064
EES Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0066
DCC Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0068
CSS Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0070
EES RTTM submitted to Programme for assurance | T3-DB-0072
DCC RTTM submitted to Programme for assurance | T3-DB-0074
CSS RTTM submitted to Programme for assurance | T3-DB-0076
Registration Services Migration/Reverse Migration PIT Completion Report for Bulk submitted to Programme for assurance | T3-DB-0080
Elexon Central Systems Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | T3-DB-0082
DIP Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | T3-DB-0084
UMSO Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | T3-DB-0086
Network Operation Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | T3-DB-0088
SIT Suppliers Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | T3-DB-0090
SIT Metering Services & Data Services' Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | T3-DB-0092
Registration Services Migration/Reverse Migration PIT Completion Report for Production Interfaces submitted to Programme for assurance | T3-DB-0094
Post-Implementation Review approved | T3-PC-0030
Migration design artefacts issued for consultation | T3-MI-0011
Data Assessment Report approved | T3-MI-0012
Updated Migration Design artefacts issued to PPs for assurance review | T3-MI-0013
Migration, Cutover & Data Strategy approved | T3-MI-0014
Migration Implementation Plan approved | T3-MI-0015
Threshold volumes approved at TMAG | T3-MI-0021
Acceptance criteria for M15 agreed at TMAG | T3-MI-0022
TMAG approval of cut-over plan | T3-MI-0023
Migration Period Plan Review 1 Completed | T3-MI-0016
Migration Processes & Procedures approved | T3-MI-0017
Migration Period Plan Review 2 Completed | T3-MI-0018
Migration Period Plan Review 3 Completed | T3-MI-0019
Central Systems & Registration Services design assurance (excl Migration/Reverse Migration) complete | T2-DB-0100
Tranche 1 Transition Design approved | T2-DB-0150
SIT PPs design assurance (excl Migration/Reverse Migration) complete | T2-DB-0200
Tranche 2 Transition Design approved | T2-DB-0250
CCAG recommend final code to PSG for baselining | T2-RE-0550
Design Authority ToR approved | T3-DB-0010
M5 design Work-Off Plan completion approved | T3-DB-0014
Enduring change management process approved | T3-DB-0016
Interim Design Artefact release 1 go live | T3-DB-0095
Interim Design Artefact release 2 go live | T3-DB-0096
Interim Design Artefact release 3 go live | T3-DB-0097
SCR powers enabled (M7) | T2-RE-0600
Code changes delivered (M8) | T2-RE-0650
DIP Simulator released | T3-DB-0018
Data generator released | T3-DB-0022
Data Service emulators released | T3-TE-0031
CSS & SMRS Simulators Released | T3-TE-0035
Reinforcement Guide approved | T3-PC-0040
Pre-Migration data cleanse complete | T2-MI-0450
SIT Volunteers identified | T2-TE-0100
SIT Participants Agreed | T2-TE-0150
Data cut from relevant participants' production systems completed | T2-TE-0200
Test data ready to start SIT (M9) | T2-TE-0050
SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | T2-TE-0250
SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | T2-TE-0300
SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | T2-TE-0350
SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | T2-TE-0400
SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | T2-TE-0450
SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | T2-TE-0500
SIT Functional Testing Preparation Complete | T2-TE-0550
SIT Component Integration Testing Test Completion Report Approved | T2-TE-0600
SIT Migration Testing Preparation Complete | T2-TE-0650
SIT Non-Functional Testing Preparation Complete | T2-TE-0700
SIT Operational Testing Preparation Complete | T2-TE-0750
SIT Migration Testing Test Completion Report (Minimum Viable Cohort) Approved | T2-TE-0800
SIT Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | T2-TE-0850
SIT Non-Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | T2-TE-0900
SIT Operational Testing Test Completion Report (Minimum Viable Cohort) Approved | T2-TE-0950
Network Operation test scenarios submitted to Programme for assurance | T3-DB-0011
PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 1 | T3-DB-0013
PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 2 | T3-DB-0015
PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | T3-DB-0017
PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | T3-DB-0019
PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | T3-DB-0021
PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | T3-DB-0023
UMSO test scenarios submitted to Programme for assurance | T3-DB-0025
EES test scenarios submitted to Programme for assurance | T3-DB-0031
DIP test scenarios submitted to Programme for assurance | T3-DB-0036
SIT Suppliers test scenarios submitted to Programme for assurance | T3-DB-0037
Data Services Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0038
Registration Services test scenarios submitted to Programme for assurance | T3-DB-0044
Metering Services test scenarios submitted to Programme for assurance | T3-DB-0050
Data Services test scenarios submitted to Programme for assurance | T3-DB-0056
Data Services RTTM submitted to Programme for assurance | T3-DB-0058
CSS test scenarios submitted to Programme for assurance | T3-DB-0067
DCC test scenarios submitted to Programme for assurance | T3-DB-0078
Qualification Testing Tranche 1 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0017
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 1 Participants) | T3-QU-0018
Qualification Testing Tranche 2 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0021
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 2 Participants) | T3-QU-0022
Qualification Testing Tranche 3 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0025
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 3 Participants) | T3-QU-0026
Qualification Testing Tranche 4 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0031
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 4 Participants) | T3-QU-0032
Qualification Testing Tranche 5 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0036
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 5 Participants) | T3-QU-0037
Qualification Testing Tranche 6 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0041
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 6 Participants) | T3-QU-0042
Qualification Testing Tranche 7 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-QU-0046
Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 7 Participants) | T3-QU-0047
Environment Approach & Plan approved | T3-TE-0010
Notification of Production Data Cut issued to relevant participants | T3-TE-0011
SIT Component Integration Testing Test Approach & Plan approved | T3-TE-0012
SIT Functional Testing Test Approach & Plan approved | T3-TE-0013
SIT Component Integration Testing Test scenarios approved | T3-TE-0014
SIT Functional Testing Test scenarios approved | T3-TE-0015
Production data cut GONG decision | T3-TE-0017
SIT Migration Testing Test Approach & Plan approved | T3-TE-0018
SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 1 | T3-TE-0019
SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 2 | T3-TE-0020
SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 3 | T3-TE-0021
SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 4 | T3-TE-0022
SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 5 | T3-TE-0023
SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 6 | T3-TE-0024
SIT Migration Testing Test scripts approved | T3-TE-0025
SIT Non-Functional Testing Test Approach & Plan approved | T3-TE-0026
SIT Participants' SIT-Staging environments ready to start connectivity proving (incl certificates and security compliance) | T3-TE-0027
SIT Non-Functional Testing Test scenarios approved | T3-TE-0028
SIT Operational Testing Test Approach & Plan approved | T3-TE-0029
SIT Operational Testing Test scenarios approved | T3-TE-0030
SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0032
SIT Participants' SIT B environments ready to start connectivity proving (incl certificates and security compliance) | T3-TE-0033
SIT Functional Testing Start | T3-TE-0034
SIT Non-Functional Testing Test Cases approved | T3-TE-0036
SIT Operational Testing Test Cases approved | T3-TE-0037
SIT Migration Testing Start | T3-TE-0038
TMAG decision on early Qualification Testing Execution start | T3-TE-0039
SIT Non-Functional Testing Start | T3-TE-0040
Back-up TMAG decision on early Qualification Testing Execution start | T3-TE-0041
SIT Operational Testing Start | T3-TE-0042
SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0043
Central Parties' UIT environments ready to start connectivity proving (incl certificates and security compliance) | T3-TE-0044
Core Systems Code Freeze | T3-TE-0045
SIT Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0046
SIT Non-Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0047
UIT E2E Sandbox Preparation Complete | T3-TE-0048
SIT PPs E2E Sandbox Testing Start | T3-TE-0049
SIT Operational Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0050
SIT Migration Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0051
SIT Functional Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0052
SIT Non-Functional Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0053
SIT Operational Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | T3-TE-0054
SIT Functional Testing Test Completion Report (Other Participants) Approved | T3-TE-0055
SIT Migration Testing Test Completion Report (Other Participants) Approved | T3-TE-0056
SIT Non-Functional Testing Test Completion Report (Other Participants) Approved | T3-TE-0057
SIT Operational Testing Test Completion Report (Other Participants) Approved | T3-TE-0058
SIT - Other Participants Complete | T3-TE-0059
Component Integration Testing Interval 1 Start | T3-TE-0060
Component Integration Testing Interval 2 Start | T3-TE-0061
Component Integration Testing Interval 3 Start | T3-TE-0062
Component Integration Testing Interval 4 Start | T3-TE-0063
Component Integration Testing Interval 5 Start | T3-TE-0064
Component Integration Testing Interval 6 Start | T3-TE-0065
E2E Sandbox Guidance approved | T3-TE-0067
Environment Approach & Plan - Work Off Approved | T3-TE-0068
SIT Component Integration Testing Test Cases approved | T3-TE-0069
SIT Functional Testing Test Cases approved | T3-TE-0070
SIT Migration Testing Test scenarios approved | T3-TE-0071
Test Data Overarching Approach & Plan approved by TMAG | T3-TE-0072
Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness confirmed | T3-QU-0007
Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test execution schedule approved | T3-QU-0008
Confirm Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Participants | T3-QU-0011
Migration Approach approved | T3-MI-0010
Final code drafting (mop-up) approved | T2-RE-0500
All SIT LDSOs have procured their adapter providers | T3-DB-0020
Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | T3-DB-0029
Data Cleanse Plan approved | T3-MI-0020

## Sheet4 (hidden)
| ID | Outline_Level | WBS | Milestone Tier | Task Name | Start_Date | Finish_Date | Split out | Predecessors
| 2 | 2 | 1.1 |  | PROGRAMME MANAGEMENT | 31 October 2022 08:00 | 31 December 2026 17:00
| 3 | 3 | 1.1.1 |  | Sprint-based prioritisation planning and execution | 31 October 2022 08:00 | 31 December 2026 17:00
| 4 | 3 | 1.1.2 |  | Programme governance secretariat | 31 October 2022 08:00 | 31 December 2026 17:00
| 5 | 3 | 1.1.3 |  | RAID management and reporting | 31 October 2022 08:00 | 31 December 2026 17:00
| 6 | 3 | 1.1.4 |  | Tracking against Programme outcomes and KPIs | 31 October 2022 08:00 | 31 December 2026 17:00
| 7 | 3 | 1.1.5 |  | Change control and reporting | 31 October 2022 08:00 | 31 December 2026 17:00
| 8 | 3 | 1.1.6 |  | Ongoing identification of lessons learned relating to the PMO and implementation of improvements | 31 October 2022 08:00 | 31 December 2026 17:00
| 9 | 2 | 1.2 |  | Programme Internal Assurance Reviews | 31 October 2022 08:00 | 31 December 2026 17:00
| 10 | 3 | 1.2.1 |  | Programme Internal Assurance Reviews | 31 October 2022 08:00 | 31 December 2026 17:00
| 11 | 2 | 1.3 |  | Engagement with PPs | 31 October 2022 08:00 | 31 December 2026 17:00
| 12 | 3 | 1.3.1 |  | Ongoing PP liaison activities | 31 October 2022 08:00 | 31 December 2026 17:00
| 13 | 3 | 1.3.2 |  | Milestone and Control Point objective setting | 31 October 2022 08:00 | 31 December 2026 17:00
| 14 | 3 | 1.3.3 |  | Reporting | 31 October 2022 08:00 | 31 December 2026 17:00
| 15 | 3 | 1.3.4 |  | PP Engagement Events | 31 October 2022 08:00 | 31 December 2026 17:00
| 16 | 4 | 1.3.4.1 |  | Bilateral meetings | 31 October 2022 08:00 | 31 December 2026 17:00
| 17 | 4 | 1.3.4.2 |  | Monthly webinars | 31 October 2022 08:00 | 31 December 2026 17:00
| 18 | 4 | 1.3.4.3 |  | Open days | 31 October 2022 08:00 | 31 December 2026 17:00
| 19 | 3 | 1.3.5 |  | PP Communications | 31 October 2022 08:00 | 30 December 2026 17:00
| 20 | 4 | 1.3.5.1 |  | The Clock updates (weekly) | 31 October 2022 08:00 | 30 December 2026 17:00
| 21 | 4 | 1.3.5.2 |  | Maintain and update content on public-facing Portal (and ongoing feedback reviews to identify and implement Portal improvements) | 31 October 2022 08:00 | 30 December 2026 17:00
| 22 | 2 | 1.4 |  | Code Change Support / Other Programme Alignment | 31 October 2022 08:00 | 31 December 2026 17:00
| 23 | 3 | 1.4.1 |  | Support DCC/BEIS on SEC change | 31 October 2022 08:00 | 31 December 2026 17:00
| 24 | 3 | 1.4.2 |  | Support on Smart Meters Act changes | 31 October 2022 08:00 | 31 December 2026 17:00
| 25 | 3 | 1.4.3 |  | Support DCC/RECCo on CSS change | 31 October 2022 08:00 | 31 December 2026 17:00
| 26 | 3 | 1.4.4 |  | Support Elexon on BSC change | 31 October 2022 08:00 | 31 December 2026 17:00
| 27 | 3 | 1.4.5 |  | Support code change inside & outside CCIAG | 31 October 2022 08:00 | 31 December 2026 17:00
| 28 | 3 | 1.4.6 |  | Support code change inside & outside CCAG | 31 October 2022 08:00 | 31 December 2026 17:00
| 29 | 2 | 1.5 |  | Programme Replan Baseline | 31 October 2022 08:00 | 14 June 2023 17:00
| 30 | 3 | 1.5.1 |  | Round 3 consultation preparation | 31 October 2022 08:00 | 13 December 2022 17:00
| 31 | 3 | 1.5.2 |  | PSG decision to launch Round 3 consultation | 07 December 2022 08:00 | 07 December 2022 08:00 |  | 30FS
| 32 | 3 | 1.5.3 |  | Round 3 consultation (incl. walkthroughs and Q&A) | 14 December 2022 08:00 | 31 January 2023 17:00 |  | 31FS
| 33 | 3 | 1.5.4 |  | Review and uplift of foundational testing documents to align with replan approach | 14 December 2022 08:00 | 20 April 2023 17:00 |  | 32SS
| 34 | 3 | 1.5.5 |  | Round 3 consultation responses analysis (incl. identification of SIT volunteers) | 01 February 2023 08:00 | 14 February 2023 17:00 |  | 32
| 35 | 3 | 1.5.6 |  | Replan re-drafting and supporting artefact updates (incl. engagement with Ofgem) | 15 February 2023 08:00 | 22 March 2023 17:00 |  | 34
| 36 | 3 | 1.5.7 |  | Draft Replan Change Request | 15 February 2023 08:00 | 29 March 2023 17:00 |  | 34
| 37 | 3 | 1.5.8 |  | PSG decision to issue CR for industry impact assessment | 05 April 2023 17:00 | 05 April 2023 17:00 |  | 36FS
| 38 | 3 | 1.5.9 |  | Industry impact assessment | 06 April 2023 08:00 | 19 April 2023 17:00 |  | 37
| 39 | 3 | 1.5.10 |  | Replan playbacks (to assist PPs in impact assessment) | 11 April 2023 08:00 | 17 April 2023 17:00 |  | 38SS
| 40 | 3 | 1.5.11 |  | Industry impact assessment responses analysis | 20 April 2023 08:00 | 26 April 2023 17:00 |  | 38
| 41 | 3 | 1.5.12 |  | Extraordinary PSG decision to agree baseline recommendation | 03 May 2023 17:00 | 03 May 2023 17:00 |  | 40FS+5d
41 | 42 | 3 | 1.5.13 | Tier 1 | Plan Rebaselined (subject to Ofgem decision) | 07 June 2023 17:00 | 07 June 2023 17:00 | 41 | 41FS
| 43 | 3 | 1.5.14 |  | Programme Replan playbacks and drop-in sessions | 08 June 2023 08:00 | 14 June 2023 17:00 |  | 42
| 44 | 2 | 1.6 |  | Business Case Update | 11 September 2023 08:00 | 20 October 2023 17:00
| 45 | 3 | 1.6.1 |  | Update Business Case | 11 September 2023 08:00 | 22 September 2023 17:00 |  | 1198FS-35d
| 46 | 3 | 1.6.2 |  | Document review and update | 25 September 2023 08:00 | 20 October 2023 17:00 |  | 45
| 47 | 3 | 1.6.3 |  | Updated Business Case approved by SRO | 20 October 2023 17:00 | 20 October 2023 17:00 |  | 46
| 48 | 2 | 1.7 |  | Programme Management - Tier 1 Milestones | 07 June 2023 17:00 | 07 June 2023 17:00
| 50 | 1 | 2 |  | DESIGN, BUILD & TEST (PIT) | 31 October 2022 08:00 | 18 January 2027 17:00
| 51 | 2 | 2.1 |  | Design Baseline & Enduring PP Support | 31 October 2022 08:00 | 18 January 2027 17:00
| 52 | 3 | 2.1.1 | Tier 1 | Physical design baselined (M5) | 31 October 2022 08:00 | 31 October 2022 08:00
| 53 | 3 | 2.1.2 |  | M5 Design Work-Off Plan Implementation & Approval | 31 October 2022 08:00 | 16 February 2023 17:00
| 54 | 4 | 2.1.2.1 |  | Implementation of M5 design Work-Off Plan | 31 October 2022 08:00 | 09 February 2023 17:00 |  | 52
54 | 55 | 4 | 2.1.2.2 | Tier 3 | M5 design Work-Off Plan completion approved | 16 February 2023 17:00 | 16 February 2023 17:00 | 54 | 54FS
| 56 | 3 | 2.1.3 |  | Enduring PP Design Support | 31 October 2022 08:00 | 31 December 2026 17:00
| 57 | 4 | 2.1.3.1 |  | Design playbacks and drop-in sessions | 31 October 2022 08:00 | 30 December 2022 17:00 |  | 52
| 58 | 4 | 2.1.3.2 |  | Support participants on E2E MHHS Design | 31 October 2022 08:00 | 31 December 2026 17:00 |  | 52
| 59 | 4 | 2.1.3.3 |  | DIP Onboarding Support | 14 November 2022 08:00 | 17 February 2023 17:00
| 60 | 4 | 2.1.3.4 |  | iServer Launch | 16 February 2023 17:00 | 16 February 2023 17:00 |  | 55
| 61 | 3 | 2.1.4 |  | Establish Design Change Management Processes | 31 October 2022 08:00 | 18 January 2027 17:00
| 62 | 4 | 2.1.4.1 |  | Internal review of internal change management processes | 31 October 2022 08:00 | 16 December 2022 17:00
| 63 | 4 | 2.1.4.2 |  | SRO approval of internal change management processes | 16 December 2022 17:00 | 16 December 2022 17:00 |  | 62FF
| 64 | 4 | 2.1.4.3 |  | Change Process Webinar | 16 January 2023 08:00 | 16 January 2023 08:00
| 65 | 4 | 2.1.4.4 |  | Enduring change management process approved | 16 February 2023 17:00 | 16 February 2023 17:00 |  | 55FF
65 | 66 | 4 | 2.1.4.5 | Tier 3 | Maintain E2E MHHS Design (post-M5 design change management processes operational) | 17 February 2023 08:00 | 18 January 2027 17:00 | 65 | 65
| 67 | 3 | 2.1.5 |  | Design Authority Mobilisation | 14 December 2022 08:00 | 23 January 2023 17:00
| 68 | 4 | 2.1.5.1 |  | Design Authority ToR approved | 14 December 2022 08:00 | 14 December 2022 08:00
68 | 69 | 4 | 2.1.5.2 | Tier 3 | Inaugural Design Authority | 23 January 2023 17:00 | 23 January 2023 17:00 | 68 | 68FS
| 70 | 2 | 2.2 |  | PP Mobilisation | 31 October 2022 08:00 | 31 January 2023 17:00
| 71 | 3 | 2.2.1 |  | Set up governance | 31 October 2022 08:00 | 31 January 2023 17:00
| 72 | 3 | 2.2.2 |  | Set up reporting | 31 October 2022 08:00 | 31 January 2023 17:00
| 73 | 3 | 2.2.3 |  | Obtain funding | 31 October 2022 08:00 | 31 January 2023 17:00
| 74 | 3 | 2.2.4 |  | Earmark resources | 31 October 2022 08:00 | 31 January 2023 17:00
| 75 | 3 | 2.2.5 |  | Mobilise initial team | 31 October 2022 08:00 | 31 January 2023 17:00
| 76 | 2 | 2.3 |  | PIT Stub Specification and Delivery | 31 October 2022 08:00 | 31 May 2023 17:00
| 77 | 3 | 2.3.1 |  | DIP Simulator | 31 October 2022 08:00 | 29 March 2023 17:00
| 78 | 4 | 2.3.1.1 |  | Build & Test | 31 October 2022 08:00 | 10 March 2023 17:00 |  | 52
| 79 | 4 | 2.3.1.2 |  | UAT | 14 November 2022 08:00 | 10 March 2023 17:00 |  | 78SS+10d
| 80 | 4 | 2.3.1.3 |  | Beta test | 31 October 2022 08:00 | 10 March 2023 17:00 |  | 78SS
| 81 | 4 | 2.3.1.4 |  | Prepare for release | 06 March 2023 08:00 | 29 March 2023 17:00 |  | 80FS-5d
81 | 82 | 4 | 2.3.1.5 | Tier 3 | DIP Simulator released | 29 March 2023 17:00 | 29 March 2023 17:00 | 81 | 81FF
| 83 | 3 | 2.3.2 |  | Data Generator | 01 December 2022 08:00 | 31 May 2023 17:00
| 84 | 4 | 2.3.2.1 |  | Design | 01 December 2022 08:00 | 21 December 2022 17:00
| 85 | 4 | 2.3.2.2 |  | Build & Test | 16 February 2023 08:00 | 26 April 2023 17:00 |  | 84FS+40d
| 86 | 4 | 2.3.2.3 |  | UAT | 27 April 2023 08:00 | 10 May 2023 17:00 |  | 85
| 87 | 4 | 2.3.2.4 |  | Beta test | 30 March 2023 08:00 | 31 May 2023 17:00 |  | 85FS-20d,89FF
| 88 | 4 | 2.3.2.5 |  | Prepare for release | 27 April 2023 08:00 | 30 May 2023 17:00 |  | 86SS
88 | 89 | 4 | 2.3.2.6 | Tier 3 | Data Generator released | 31 May 2023 17:00 | 31 May 2023 17:00 | 88 | 88FS
| 90 | 2 | 2.4 |  | PP Design, Build & Test (DBT) | 31 October 2022 08:00 | 16 February 2026 17:00
| 91 | 3 | 2.4.1 |  | PP Impact Assessment, Planning & Procurement | 31 October 2022 08:00 | 31 March 2023 17:00
| 92 | 4 | 2.4.1.1 |  | PP Impact Assessment | 31 October 2022 08:00 | 31 January 2023 17:00
| 93 | 5 | 2.4.1.1.1 |  | Develop heatmap for impact of MHHS | 31 October 2022 08:00 | 31 January 2023 17:00 |  | 52
| 94 | 5 | 2.4.1.1.2 |  | Develop detailed impact assessment | 31 October 2022 08:00 | 31 January 2023 17:00 |  | 52
| 95 | 4 | 2.4.1.2 |  | PP Planning | 31 October 2022 08:00 | 31 January 2023 17:00
| 96 | 5 | 2.4.1.2.1 |  | Develop detailed short-term plan | 31 October 2022 08:00 | 30 November 2022 17:00 |  | 52
| 97 | 5 | 2.4.1.2.2 |  | Develop overall project plan for implementation | 31 October 2022 08:00 | 31 January 2023 17:00 |  | 52
| 98 | 5 | 2.4.1.2.3 |  | Develop procurement plan | 31 October 2022 08:00 | 31 January 2023 17:00 |  | 52
| 99 | 4 | 2.4.1.3 |  | PP Software/Service Procurement | 31 October 2022 08:00 | 31 March 2023 17:00
| 100 | 5 | 2.4.1.3.1 |  | Run tender process | 31 October 2022 08:00 | 31 January 2023 17:00 |  | 52
| 101 | 5 | 2.4.1.3.2 |  | Select provider & sign commercials | 01 February 2023 08:00 | 31 March 2023 17:00 |  | 100
| 102 | 3 | 2.4.2 |  | Central Systems DBT | 31 October 2022 08:00 | 13 May 2024 17:00
| 103 | 4 | 2.4.2.1 |  | Elexon Central Systems DBT | 31 October 2022 08:00 | 13 May 2024 17:00
| 104 | 5 | 2.4.2.1.1 |  | Elexon Central Systems DBT (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 29 September 2023 17:00
| 105 | 6 | 2.4.2.1.1.1 |  | Design | 31 October 2022 08:00 | 29 September 2023 17:00
| 106 | 6 | 2.4.2.1.1.2 |  | Build | 31 October 2022 08:00 | 29 September 2023 17:00 |  | 105SS
| 107 | 6 | 2.4.2.1.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 21 July 2023 17:00
| 108 | 7 | 2.4.2.1.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 07 July 2023 17:00
108 | 109 | 7 | 2.4.2.1.1.3.2 | Tier 3 | Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | 07 July 2023 17:00 | 07 July 2023 17:00 | 108 | 108FF
| 110 | 7 | 2.4.2.1.1.3.3 |  | Test approach and plan assured by SI | 10 July 2023 08:00 | 21 July 2023 17:00 |  | 109
| 111 | 6 | 2.4.2.1.1.4 |  | Test Readiness Report | 21 July 2023 08:00 | 29 September 2023 17:00
| 112 | 7 | 2.4.2.1.1.4.1 |  | Develop test readiness report | 21 July 2023 08:00 | 29 September 2023 17:00 |  | 109FS+9d
| 113 | 6 | 2.4.2.1.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 18 August 2023 17:00
| 114 | 7 | 2.4.2.1.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 04 August 2023 17:00
114 | 115 | 7 | 2.4.2.1.1.5.2 | Tier 3 | Elexon Central Systems RTTM submitted to Programme for assurance | 04 August 2023 17:00 | 04 August 2023 17:00 | 114 | 114FF
| 116 | 7 | 2.4.2.1.1.5.3 |  | RTTM assured by SI | 07 August 2023 08:00 | 18 August 2023 17:00 |  | 115
| 117 | 6 | 2.4.2.1.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 18 August 2023 17:00
| 118 | 7 | 2.4.2.1.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 04 August 2023 17:00
118 | 119 | 7 | 2.4.2.1.1.6.2 | Tier 3 | Elexon Central Systems test scenarios submitted to Programme for assurance | 04 August 2023 17:00 | 04 August 2023 17:00 | 118 | 118FF
| 120 | 7 | 2.4.2.1.1.6.3 |  | Test scenarios assured by SI | 07 August 2023 08:00 | 18 August 2023 17:00 |  | 119
| 121 | 6 | 2.4.2.1.1.7 |  | PIT execution | 31 October 2022 08:00 | 29 September 2023 17:00 |  | 106SS
| 122 | 7 | 2.4.2.1.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 22 September 2023 17:00 |  | 123FF-5d
| 123 | 7 | 2.4.2.1.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 29 September 2023 17:00 |  | 534FF
| 124 | 5 | 2.4.2.1.2 |  | Elexon Central Systems Migration/Reverse Migration DBT (if applicable) | 01 May 2023 08:00 | 13 May 2024 17:00
| 125 | 6 | 2.4.2.1.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 126 | 6 | 2.4.2.1.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 125SS
| 127 | 6 | 2.4.2.1.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 126SS
| 128 | 6 | 2.4.2.1.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 129 | 7 | 2.4.2.1.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 127FF-20d
| 130 | 7 | 2.4.2.1.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 127FF
130 | 131 | 7 | 2.4.2.1.2.4.3 | Tier 3 | Elexon Central Systems Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 130 | 130FF
| 132 | 4 | 2.4.2.2 |  | DIP DBT | 31 October 2022 08:00 | 13 May 2024 17:00
| 133 | 5 | 2.4.2.2.1 |  | DIP DBT (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 29 September 2023 17:00
| 134 | 6 | 2.4.2.2.1.1 |  | Design | 02 January 2023 08:00 | 21 April 2023 17:00
| 135 | 6 | 2.4.2.2.1.2 |  | Build | 09 January 2023 08:00 | 11 August 2023 17:00 |  | 134SS+5d
| 136 | 6 | 2.4.2.2.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 21 July 2023 17:00
| 137 | 7 | 2.4.2.2.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 07 July 2023 17:00
137 | 138 | 7 | 2.4.2.2.1.3.2 | Tier 3 | DIP Test Approach & Plan (PIT) submitted to Programme for assurance | 07 July 2023 17:00 | 07 July 2023 17:00 | 137 | 137FF
| 139 | 7 | 2.4.2.2.1.3.3 |  | Test approach and plan assured by SI | 10 July 2023 08:00 | 21 July 2023 17:00 |  | 138
| 140 | 6 | 2.4.2.2.1.4 |  | Test Readiness Report | 21 July 2023 08:00 | 29 September 2023 17:00
| 141 | 7 | 2.4.2.2.1.4.1 |  | Develop test readiness report | 21 July 2023 08:00 | 29 September 2023 17:00 |  | 138FS+9d
| 142 | 6 | 2.4.2.2.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 18 August 2023 17:00
| 143 | 7 | 2.4.2.2.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 04 August 2023 17:00
143 | 144 | 7 | 2.4.2.2.1.5.2 | Tier 3 | DIP RTTM submitted to Programme for assurance | 04 August 2023 17:00 | 04 August 2023 17:00 | 143 | 143FF
| 145 | 7 | 2.4.2.2.1.5.3 |  | RTTM assured by SI | 07 August 2023 08:00 | 18 August 2023 17:00 |  | 144
| 146 | 6 | 2.4.2.2.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 18 August 2023 17:00
| 147 | 7 | 2.4.2.2.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 04 August 2023 17:00
147 | 148 | 7 | 2.4.2.2.1.6.2 | Tier 3 | DIP test scenarios submitted to Programme for assurance | 04 August 2023 17:00 | 04 August 2023 17:00 | 147 | 147FF
| 149 | 7 | 2.4.2.2.1.6.3 |  | Test scenarios assured by SI | 07 August 2023 08:00 | 18 August 2023 17:00 |  | 148
| 150 | 6 | 2.4.2.2.1.7 |  | PIT execution | 31 October 2022 08:00 | 29 September 2023 17:00 |  | 106SS
| 151 | 7 | 2.4.2.2.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 22 September 2023 17:00 |  | 152FF-5d
| 152 | 7 | 2.4.2.2.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 29 September 2023 17:00 |  | 534FF
| 153 | 5 | 2.4.2.2.2 |  | DIP Migration/Reverse Migration DBT (if applicable) | 01 May 2023 08:00 | 13 May 2024 17:00
| 154 | 6 | 2.4.2.2.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 155 | 6 | 2.4.2.2.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 154SS
| 156 | 6 | 2.4.2.2.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 155SS
| 157 | 6 | 2.4.2.2.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 158 | 7 | 2.4.2.2.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 156FF-20d
| 159 | 7 | 2.4.2.2.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 156FF
159 | 160 | 7 | 2.4.2.2.2.4.3 | Tier 3 | DIP Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 159 | 159FF
| 161 | 4 | 2.4.2.3 |  | DCC (DSP) DBT | 31 October 2022 08:00 | 05 January 2024 17:00
| 162 | 5 | 2.4.2.3.1 |  | DCC (DSP) DBT | 31 October 2022 08:00 | 05 January 2024 17:00
| 163 | 6 | 2.4.2.3.1.1 |  | Design | 31 October 2022 08:00 | 31 January 2023 17:00
| 164 | 6 | 2.4.2.3.1.2 |  | Build & DCC PIT | 31 October 2022 08:00 | 05 January 2024 17:00
| 165 | 7 | 2.4.2.3.1.2.1 |  | Build & DCC PIT | 16 January 2023 08:00 | 15 May 2023 17:00 |  | 163FS-12d
165 | 166 | 7 | 2.4.2.3.1.2.2 | Tier 3 | DCC PIT Completion Report submitted to Programme for assurance (dependent on DCC TAB) | 08 June 2023 17:00 | 08 June 2023 17:00 | 165 | 165FS
| 167 | 7 | 2.4.2.3.1.2.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 27 October 2023 17:00
| 168 | 8 | 2.4.2.3.1.2.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 13 October 2023 17:00
168 | 169 | 8 | 2.4.2.3.1.2.3.2 | Tier 3 | DCC Test Approach & Plan (PIT) submitted to Programme for assurance | 13 October 2023 17:00 | 13 October 2023 17:00 | 168 | 168FF
| 170 | 8 | 2.4.2.3.1.2.3.3 |  | Test approach and plan assured by SI | 16 October 2023 08:00 | 27 October 2023 17:00 |  | 169
| 171 | 7 | 2.4.2.3.1.2.4 |  | Test Readiness Report | 27 October 2023 08:00 | 05 January 2024 17:00
| 172 | 8 | 2.4.2.3.1.2.4.1 |  | Develop test readiness report | 27 October 2023 08:00 | 05 January 2024 17:00 |  | 169FS+9d
| 173 | 7 | 2.4.2.3.1.2.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 24 November 2023 17:00
| 174 | 8 | 2.4.2.3.1.2.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 10 November 2023 17:00
174 | 175 | 8 | 2.4.2.3.1.2.5.2 | Tier 3 | DCC RTTM submitted to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 | 174 | 174FF
| 176 | 8 | 2.4.2.3.1.2.5.3 |  | RTTM assured by SI | 13 November 2023 08:00 | 24 November 2023 17:00 |  | 175
| 177 | 7 | 2.4.2.3.1.2.6 |  | Test Scenarios | 31 October 2022 08:00 | 24 November 2023 17:00
| 178 | 8 | 2.4.2.3.1.2.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 10 November 2023 17:00
178 | 179 | 8 | 2.4.2.3.1.2.6.2 | Tier 3 | DCC test scenarios submitted to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 | 178 | 178FF
| 180 | 8 | 2.4.2.3.1.2.6.3 |  | Test scenarios assured by SI | 13 November 2023 08:00 | 24 November 2023 17:00 |  | 179
| 181 | 7 | 2.4.2.3.1.2.7 |  | PIT execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 106SS
| 182 | 8 | 2.4.2.3.1.2.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 29 December 2023 17:00 |  | 183FF-5d
| 183 | 8 | 2.4.2.3.1.2.7.2 |  | PIT Execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 713FF
| 184 | 4 | 2.4.2.4 |  | RECCo (CSS/EES) DBT | 31 October 2022 08:00 | 05 January 2024 17:00
| 185 | 5 | 2.4.2.4.1 |  | RECCo (CSS/EES) DBT | 31 October 2022 08:00 | 05 January 2024 17:00
| 186 | 6 | 2.4.2.4.1.1 |  | EES | 31 October 2022 08:00 | 05 January 2024 17:00
| 187 | 7 | 2.4.2.4.1.1.1 |  | Design | 01 March 2023 08:00 | 02 January 2024 17:00
| 188 | 7 | 2.4.2.4.1.1.2 |  | Build | 01 March 2023 08:00 | 02 January 2024 17:00 |  | 187SS
| 189 | 7 | 2.4.2.4.1.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 27 October 2023 17:00
| 190 | 8 | 2.4.2.4.1.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 13 October 2023 17:00
190 | 191 | 8 | 2.4.2.4.1.1.3.2 | Tier 3 | EES Test Approach & Plan (PIT) submitted to Programme for assurance | 13 October 2023 17:00 | 13 October 2023 17:00 | 190 | 190FF
| 192 | 8 | 2.4.2.4.1.1.3.3 |  | Test approach and plan assured by SI | 16 October 2023 08:00 | 27 October 2023 17:00 |  | 191
| 193 | 7 | 2.4.2.4.1.1.4 |  | Test Readiness Report | 27 October 2023 08:00 | 05 January 2024 17:00
| 194 | 8 | 2.4.2.4.1.1.4.1 |  | Develop test readiness report | 27 October 2023 08:00 | 05 January 2024 17:00 |  | 191FS+9d
| 195 | 7 | 2.4.2.4.1.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 24 November 2023 17:00
| 196 | 8 | 2.4.2.4.1.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 10 November 2023 17:00
196 | 197 | 8 | 2.4.2.4.1.1.5.2 | Tier 3 | EES RTTM submitted to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 | 196 | 196FF
| 198 | 8 | 2.4.2.4.1.1.5.3 |  | RTTM assured by SI | 13 November 2023 08:00 | 24 November 2023 17:00 |  | 197
| 199 | 7 | 2.4.2.4.1.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 24 November 2023 17:00
| 200 | 8 | 2.4.2.4.1.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 10 November 2023 17:00
200 | 201 | 8 | 2.4.2.4.1.1.6.2 | Tier 3 | EES test scenarios submitted to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 | 200 | 200FF
| 202 | 8 | 2.4.2.4.1.1.6.3 |  | Test scenarios assured by SI | 13 November 2023 08:00 | 24 November 2023 17:00 |  | 201
| 203 | 7 | 2.4.2.4.1.1.7 |  | PIT execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 106SS
| 204 | 8 | 2.4.2.4.1.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 29 December 2023 17:00 |  | 205FF-5d
| 205 | 8 | 2.4.2.4.1.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 713FF
| 206 | 6 | 2.4.2.4.1.2 |  | CSS | 31 October 2022 08:00 | 05 January 2024 17:00
| 207 | 7 | 2.4.2.4.1.2.1 |  | Design | 07 November 2022 08:00 | 08 September 2023 17:00
| 208 | 7 | 2.4.2.4.1.2.2 |  | Build | 07 November 2022 08:00 | 08 September 2023 17:00 |  | 207SS
| 209 | 7 | 2.4.2.4.1.2.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 27 October 2023 17:00
| 210 | 8 | 2.4.2.4.1.2.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 13 October 2023 17:00
210 | 211 | 8 | 2.4.2.4.1.2.3.2 | Tier 3 | CSS Test Approach & Plan (PIT) submitted to Programme for assurance | 13 October 2023 17:00 | 13 October 2023 17:00 | 210 | 210FF
| 212 | 8 | 2.4.2.4.1.2.3.3 |  | Test approach and plan assured by SI | 16 October 2023 08:00 | 27 October 2023 17:00 |  | 211
| 213 | 7 | 2.4.2.4.1.2.4 |  | Test Readiness Report | 27 October 2023 08:00 | 05 January 2024 17:00
| 214 | 8 | 2.4.2.4.1.2.4.1 |  | Develop test readiness report | 27 October 2023 08:00 | 05 January 2024 17:00 |  | 211FS+9d
| 215 | 7 | 2.4.2.4.1.2.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 24 November 2023 17:00
| 216 | 8 | 2.4.2.4.1.2.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 10 November 2023 17:00
216 | 217 | 8 | 2.4.2.4.1.2.5.2 | Tier 3 | CSS RTTM submitted to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 | 216 | 216FF
| 218 | 8 | 2.4.2.4.1.2.5.3 |  | RTTM assured by SI | 13 November 2023 08:00 | 24 November 2023 17:00 |  | 217
| 219 | 7 | 2.4.2.4.1.2.6 |  | Test Scenarios | 31 October 2022 08:00 | 24 November 2023 17:00
| 220 | 8 | 2.4.2.4.1.2.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 10 November 2023 17:00
220 | 221 | 8 | 2.4.2.4.1.2.6.2 | Tier 3 | CSS test scenarios submitted to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 | 220 | 220FF
| 222 | 8 | 2.4.2.4.1.2.6.3 |  | Test scenarios assured by SI | 13 November 2023 08:00 | 24 November 2023 17:00 |  | 221
| 223 | 7 | 2.4.2.4.1.2.7 |  | PIT execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 106SS
| 224 | 8 | 2.4.2.4.1.2.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 29 December 2023 17:00 |  | 225FF-5d
| 225 | 8 | 2.4.2.4.1.2.7.2 |  | PIT Execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 713FF
| 226 | 3 | 2.4.3 |  | SIT Participants DBT | 31 October 2022 08:00 | 14 March 2025 17:00
| 227 | 4 | 2.4.3.1 |  | SIT LDSOs DBT | 31 October 2022 08:00 | 14 March 2025 17:00
| 228 | 5 | 2.4.3.1.1 |  | Registration Services DBT | 31 October 2022 08:00 | 30 September 2024 17:00
| 229 | 6 | 2.4.3.1.1.1 |  | Registration Services DBT (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 28 February 2024 17:00
| 230 | 7 | 2.4.3.1.1.1.1 |  | Design | 31 October 2022 08:00 | 28 February 2023 17:00 |  | 52
| 231 | 7 | 2.4.3.1.1.1.2 |  | Build | 06 February 2023 08:00 | 28 February 2024 17:00 |  | 230FS-20d
| 232 | 8 | 2.4.3.1.1.1.2.1 |  | Sprint 1 | 06 February 2023 08:00 | 30 June 2023 17:00
| 233 | 8 | 2.4.3.1.1.1.2.2 |  | Sprint 2 | 17 March 2023 08:00 | 30 August 2023 17:00 |  | 232SS+29d
| 234 | 8 | 2.4.3.1.1.1.2.3 |  | Sprint 3 | 07 June 2023 08:00 | 31 October 2023 17:00 |  | 233SS+58d
| 235 | 8 | 2.4.3.1.1.1.2.4 |  | Sprint 4 | 18 July 2023 08:00 | 31 January 2024 17:00 |  | 234SS+29d
| 236 | 8 | 2.4.3.1.1.1.2.5 |  | Sprint 5 | 28 September 2023 08:00 | 28 February 2024 17:00 |  | 235SS+52d
| 237 | 7 | 2.4.3.1.1.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 11 August 2023 17:00
| 238 | 8 | 2.4.3.1.1.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 28 July 2023 17:00
238 | 239 | 8 | 2.4.3.1.1.1.3.2 | Tier 3 | Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | 28 July 2023 17:00 | 28 July 2023 17:00 | 238 | 238FF
| 240 | 8 | 2.4.3.1.1.1.3.3 |  | Test approach and plan assured by SI | 31 July 2023 08:00 | 11 August 2023 17:00 |  | 239
| 241 | 7 | 2.4.3.1.1.1.4 |  | Test Readiness Report | 11 August 2023 08:00 | 20 October 2023 17:00
| 242 | 8 | 2.4.3.1.1.1.4.1 |  | Develop test readiness report | 11 August 2023 08:00 | 20 October 2023 17:00 |  | 239FS+9d
| 243 | 7 | 2.4.3.1.1.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 15 September 2023 17:00
| 244 | 8 | 2.4.3.1.1.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 01 September 2023 17:00
244 | 245 | 8 | 2.4.3.1.1.1.5.2 | Tier 3 | Registration Services RTTM submitted to Programme for assurance | 01 September 2023 17:00 | 01 September 2023 17:00 | 244 | 244FF
| 246 | 8 | 2.4.3.1.1.1.5.3 |  | RTTM assured by SI | 04 September 2023 08:00 | 15 September 2023 17:00 |  | 245
| 247 | 7 | 2.4.3.1.1.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 15 September 2023 17:00
| 248 | 8 | 2.4.3.1.1.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 01 September 2023 17:00
248 | 249 | 8 | 2.4.3.1.1.1.6.2 | Tier 3 | Registration Services test scenarios submitted to Programme for assurance | 01 September 2023 17:00 | 01 September 2023 17:00 | 248 | 248FF
| 250 | 8 | 2.4.3.1.1.1.6.3 |  | Test scenarios assured by SI | 04 September 2023 08:00 | 15 September 2023 17:00 |  | 249
| 251 | 7 | 2.4.3.1.1.1.7 |  | PIT execution (CIT interval 2) | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 106SS
| 252 | 8 | 2.4.3.1.1.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 29 December 2023 17:00 |  | 253FF-5d
| 253 | 8 | 2.4.3.1.1.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 569FF
| 254 | 7 | 2.4.3.1.1.1.8 |  | PIT execution (CIT interval 6) | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 106SS
| 255 | 8 | 2.4.3.1.1.1.8.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 29 December 2023 17:00 |  | 256FF-5d
| 256 | 8 | 2.4.3.1.1.1.8.2 |  | PIT Execution | 31 October 2022 08:00 | 05 January 2024 17:00 |  | 713FF
| 257 | 6 | 2.4.3.1.1.2 |  | Registration Services Migration/Reverse Migration DBT (Bulk) | 01 March 2023 08:00 | 29 March 2024 17:00
| 258 | 7 | 2.4.3.1.1.2.1 |  | Design | 01 March 2023 08:00 | 31 July 2023 17:00
| 259 | 7 | 2.4.3.1.1.2.2 |  | Build | 01 August 2023 08:00 | 30 November 2023 17:00 |  | 258
| 260 | 7 | 2.4.3.1.1.2.3 |  | PIT execution | 01 December 2023 08:00 | 29 March 2024 17:00 |  | 259
| 261 | 7 | 2.4.3.1.1.2.4 |  | PIT Test Completion Report (incl. evidence) | 05 February 2024 08:00 | 29 March 2024 17:00
| 262 | 8 | 2.4.3.1.1.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 05 February 2024 08:00 | 01 March 2024 17:00 |  | 260FF-20d
| 263 | 8 | 2.4.3.1.1.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 06 March 2024 08:00 | 29 March 2024 17:00 |  | 260FF
263 | 264 | 8 | 2.4.3.1.1.2.4.3 | Tier 3 | Registration Services Migration/Reverse Migration PIT Completion Report for Bulk submitted to Programme for assurance | 29 March 2024 17:00 | 29 March 2024 17:00 | 263 | 263FF
| 265 | 6 | 2.4.3.1.1.3 |  | Registration Services Migration/Reverse Migration DBT (Production Interfaces) | 01 May 2023 08:00 | 30 September 2024 17:00
| 266 | 7 | 2.4.3.1.1.3.1 |  | Design | 01 May 2023 08:00 | 31 August 2023 17:00 |  | 1685
| 267 | 7 | 2.4.3.1.1.3.2 |  | Build | 01 September 2023 08:00 | 29 February 2024 17:00 |  | 266
| 268 | 7 | 2.4.3.1.1.3.3 |  | PIT execution | 01 March 2024 08:00 | 30 September 2024 17:00 |  | 267
| 269 | 7 | 2.4.3.1.1.3.4 |  | PIT Test Completion Report (incl. evidence) | 06 August 2024 08:00 | 30 September 2024 17:00
| 270 | 8 | 2.4.3.1.1.3.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 06 August 2024 08:00 | 02 September 2024 17:00 |  | 268FF-20d
| 271 | 8 | 2.4.3.1.1.3.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 05 September 2024 08:00 | 30 September 2024 17:00 |  | 268FF
271 | 272 | 8 | 2.4.3.1.1.3.4.3 | Tier 3 | Registration Services Migration/Reverse Migration PIT Completion Report for Production Interfaces submitted to Programme for assurance | 30 September 2024 17:00 | 30 September 2024 17:00 | 271 | 271FF
| 273 | 5 | 2.4.3.1.2 |  | UMSO DBT | 31 October 2022 08:00 | 13 May 2024 17:00
| 274 | 6 | 2.4.3.1.2.1 |  | UMSO DBT (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 08 December 2023 17:00
| 275 | 7 | 2.4.3.1.2.1.1 |  | Design | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 276 | 7 | 2.4.3.1.2.1.2 |  | Build | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 277 | 7 | 2.4.3.1.2.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 29 September 2023 17:00
| 278 | 8 | 2.4.3.1.2.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 15 September 2023 17:00
278 | 279 | 8 | 2.4.3.1.2.1.3.2 | Tier 3 | UMSO Test Approach & Plan (PIT) submitted to Programme for assurance | 15 September 2023 17:00 | 15 September 2023 17:00 | 278 | 278FF
| 280 | 8 | 2.4.3.1.2.1.3.3 |  | Test approach and plan assured by SI | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 279
| 281 | 7 | 2.4.3.1.2.1.4 |  | Test Readiness Report | 29 September 2023 08:00 | 08 December 2023 17:00
| 282 | 8 | 2.4.3.1.2.1.4.1 |  | Develop test readiness report | 29 September 2023 08:00 | 08 December 2023 17:00 |  | 279FS+9d
| 283 | 7 | 2.4.3.1.2.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 20 October 2023 17:00
| 284 | 8 | 2.4.3.1.2.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 06 October 2023 17:00
284 | 285 | 8 | 2.4.3.1.2.1.5.2 | Tier 3 | UMSO RTTM submitted to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 | 284 | 284FF
| 286 | 8 | 2.4.3.1.2.1.5.3 |  | RTTM assured by SI | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 285
| 287 | 7 | 2.4.3.1.2.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 20 October 2023 17:00
| 288 | 8 | 2.4.3.1.2.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 06 October 2023 17:00
288 | 289 | 8 | 2.4.3.1.2.1.6.2 | Tier 3 | UMSO test scenarios submitted to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 | 288 | 288FF
| 290 | 8 | 2.4.3.1.2.1.6.3 |  | Test scenarios assured by SI | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 289
| 291 | 7 | 2.4.3.1.2.1.7 |  | PIT execution | 31 October 2022 08:00 | 08 December 2023 17:00 |  | 106SS
| 292 | 8 | 2.4.3.1.2.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 01 December 2023 17:00 |  | 293FF-5d
| 293 | 8 | 2.4.3.1.2.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 08 December 2023 17:00 |  | 677FF
| 294 | 6 | 2.4.3.1.2.2 |  | UMSO Migration/Reverse Migration DBT | 01 May 2023 08:00 | 13 May 2024 17:00
| 295 | 7 | 2.4.3.1.2.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 296 | 7 | 2.4.3.1.2.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 295SS
| 297 | 7 | 2.4.3.1.2.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 296SS
| 298 | 7 | 2.4.3.1.2.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 299 | 8 | 2.4.3.1.2.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 297FF-20d
| 300 | 8 | 2.4.3.1.2.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 297FF
300 | 301 | 8 | 2.4.3.1.2.2.4.3 | Tier 3 | UMSO Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 300 | 300FF
| 302 | 5 | 2.4.3.1.3 |  | Network Operation Services DBT | 31 October 2022 08:00 | 14 March 2025 17:00
| 303 | 6 | 2.4.3.1.3.1 |  | Network Operation Services DBT1 (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 08 December 2023 17:00
| 304 | 7 | 2.4.3.1.3.1.1 |  | Design | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 305 | 7 | 2.4.3.1.3.1.2 |  | Build | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 306 | 7 | 2.4.3.1.3.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 29 September 2023 17:00
| 307 | 8 | 2.4.3.1.3.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 15 September 2023 17:00
307 | 308 | 8 | 2.4.3.1.3.1.3.2 | Tier 3 | Network Operation Test Approach & Plan (PIT) submitted to Programme for assurance | 15 September 2023 17:00 | 15 September 2023 17:00 | 307 | 307FF
| 309 | 8 | 2.4.3.1.3.1.3.3 |  | Test approach and plan assured by SI | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 308
| 310 | 7 | 2.4.3.1.3.1.4 |  | Test Readiness Report | 29 September 2023 08:00 | 08 December 2023 17:00
| 311 | 8 | 2.4.3.1.3.1.4.1 |  | Develop test readiness report | 29 September 2023 08:00 | 08 December 2023 17:00 |  | 308FS+9d
| 312 | 7 | 2.4.3.1.3.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 20 October 2023 17:00
| 313 | 8 | 2.4.3.1.3.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 06 October 2023 17:00
313 | 314 | 8 | 2.4.3.1.3.1.5.2 | Tier 3 | Network Operation RTTM submitted to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 | 313 | 313FF
| 315 | 8 | 2.4.3.1.3.1.5.3 |  | RTTM assured by SI | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 314
| 316 | 7 | 2.4.3.1.3.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 20 October 2023 17:00
| 317 | 8 | 2.4.3.1.3.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 06 October 2023 17:00
317 | 318 | 8 | 2.4.3.1.3.1.6.2 | Tier 3 | Network Operation test scenarios submitted to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 | 317 | 317FF
| 319 | 8 | 2.4.3.1.3.1.6.3 |  | Test scenarios assured by SI | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 318
| 320 | 7 | 2.4.3.1.3.1.7 |  | PIT execution | 31 October 2022 08:00 | 08 December 2023 17:00 |  | 106SS
| 321 | 8 | 2.4.3.1.3.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 01 December 2023 17:00 |  | 322FF-5d
| 322 | 8 | 2.4.3.1.3.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 08 December 2023 17:00 |  | 677FF
| 323 | 6 | 2.4.3.1.3.2 |  | Network Operations DBT1 Migration/Reverse Migration DBT | 01 May 2023 08:00 | 13 May 2024 17:00
| 324 | 7 | 2.4.3.1.3.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 325 | 7 | 2.4.3.1.3.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 324SS
| 326 | 7 | 2.4.3.1.3.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 325SS
| 327 | 7 | 2.4.3.1.3.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 328 | 8 | 2.4.3.1.3.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 326FF-20d
| 329 | 8 | 2.4.3.1.3.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 326FF
329 | 330 | 8 | 2.4.3.1.3.2.4.3 | Tier 3 | Network Operation Services Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 329 | 329FF
| 331 | 6 | 2.4.3.1.3.3 |  | Network Operation Services DBT2 (consequentially-changed systems) | 01 February 2023 08:00 | 14 March 2025 17:00
| 332 | 7 | 2.4.3.1.3.3.1 |  | Network Operation Services DBT2 (consequentially-changed systems) | 01 February 2023 08:00 | 14 March 2025 17:00 |  | 94,1651FF
933 | 333 | 5 | 2.4.3.1.4 | Tier 3 | All SIT LDSOs have procured their adapter providers | 23 May 2023 08:00 | 23 May 2023 08:00 | 933 | 933SS
| 334 | 4 | 2.4.3.2 |  | SIT Suppliers, Metering Services & Data Services DBT | 31 October 2022 08:00 | 14 March 2025 17:00
| 335 | 5 | 2.4.3.2.1 |  | Suppliers DBT | 31 October 2022 08:00 | 14 March 2025 17:00
| 336 | 6 | 2.4.3.2.1.1 |  | Suppliers DBT1 (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 08 December 2023 17:00
| 337 | 7 | 2.4.3.2.1.1.1 |  | Design | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 338 | 7 | 2.4.3.2.1.1.2 |  | Build | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 339 | 7 | 2.4.3.2.1.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 29 September 2023 17:00
| 340 | 8 | 2.4.3.2.1.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 15 September 2023 17:00
340 | 341 | 8 | 2.4.3.2.1.1.3.2 | Tier 3 | SIT Suppliers Test Approach & Plan (PIT) submitted to Programme for assurance | 15 September 2023 17:00 | 15 September 2023 17:00 | 340 | 340FF
| 342 | 8 | 2.4.3.2.1.1.3.3 |  | Test approach and plan assured by SI | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 341
| 343 | 7 | 2.4.3.2.1.1.4 |  | Test Readiness Report | 29 September 2023 08:00 | 08 December 2023 17:00
| 344 | 8 | 2.4.3.2.1.1.4.1 |  | Develop test readiness report | 29 September 2023 08:00 | 08 December 2023 17:00 |  | 341FS+9d
| 345 | 7 | 2.4.3.2.1.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 20 October 2023 17:00
| 346 | 8 | 2.4.3.2.1.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 06 October 2023 17:00
346 | 347 | 8 | 2.4.3.2.1.1.5.2 | Tier 3 | SIT Suppliers RTTM submitted to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 | 346 | 346FF
| 348 | 8 | 2.4.3.2.1.1.5.3 |  | RTTM assured by SI | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 347
| 349 | 7 | 2.4.3.2.1.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 20 October 2023 17:00
| 350 | 8 | 2.4.3.2.1.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 06 October 2023 17:00
350 | 351 | 8 | 2.4.3.2.1.1.6.2 | Tier 3 | SIT Suppliers test scenarios submitted to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 | 350 | 350FF
| 352 | 8 | 2.4.3.2.1.1.6.3 |  | Test scenarios assured by SI | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 351
| 353 | 7 | 2.4.3.2.1.1.7 |  | PIT execution | 31 October 2022 08:00 | 08 December 2023 17:00 |  | 106SS
| 354 | 8 | 2.4.3.2.1.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 01 December 2023 17:00 |  | 355FF-5d
| 355 | 8 | 2.4.3.2.1.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 08 December 2023 17:00 |  | 677FF
| 356 | 6 | 2.4.3.2.1.2 |  | Suppliers DBT1 Migration/Reverse Migration DBT | 01 May 2023 08:00 | 13 May 2024 17:00
| 357 | 7 | 2.4.3.2.1.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 358 | 7 | 2.4.3.2.1.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 357SS
| 359 | 7 | 2.4.3.2.1.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 358SS
| 360 | 7 | 2.4.3.2.1.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 361 | 8 | 2.4.3.2.1.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 359FF-20d
| 362 | 8 | 2.4.3.2.1.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 359FF
362 | 363 | 8 | 2.4.3.2.1.2.4.3 | Tier 3 | SIT Suppliers' Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 362 | 362FF
| 364 | 6 | 2.4.3.2.1.3 |  | Suppliers DBT2 (consequentially-changed systems) | 01 February 2023 08:00 | 14 March 2025 17:00
| 365 | 7 | 2.4.3.2.1.3.1 |  | SIT Suppliers Core Systems DBT2 (consequentially-changed systems) | 01 February 2023 08:00 | 14 March 2025 17:00 |  | 94,1651FF
| 366 | 5 | 2.4.3.2.2 |  | Data Services DBT | 31 October 2022 08:00 | 13 May 2024 17:00
| 367 | 6 | 2.4.3.2.2.1 |  | Data Services DBT (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 03 November 2023 17:00
| 368 | 7 | 2.4.3.2.2.1.1 |  | Design | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 369 | 7 | 2.4.3.2.2.1.2 |  | Build | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 370 | 7 | 2.4.3.2.2.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 25 August 2023 17:00
| 371 | 8 | 2.4.3.2.2.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 11 August 2023 17:00
371 | 372 | 8 | 2.4.3.2.2.1.3.2 | Tier 3 | Data Services Test Approach & Plan (PIT) submitted to Programme for assurance | 11 August 2023 17:00 | 11 August 2023 17:00 | 371 | 371FF
| 373 | 8 | 2.4.3.2.2.1.3.3 |  | Test approach and plan assured by SI | 14 August 2023 08:00 | 25 August 2023 17:00 |  | 372
| 374 | 7 | 2.4.3.2.2.1.4 |  | Test Readiness Report | 25 August 2023 08:00 | 03 November 2023 17:00
| 375 | 8 | 2.4.3.2.2.1.4.1 |  | Develop test readiness report | 25 August 2023 08:00 | 03 November 2023 17:00 |  | 372FS+9d
| 376 | 7 | 2.4.3.2.2.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 06 October 2023 17:00
| 377 | 8 | 2.4.3.2.2.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 22 September 2023 17:00
377 | 378 | 8 | 2.4.3.2.2.1.5.2 | Tier 3 | Data Services RTTM submitted to Programme for assurance | 22 September 2023 17:00 | 22 September 2023 17:00 | 377 | 377FF
| 379 | 8 | 2.4.3.2.2.1.5.3 |  | RTTM assured by SI | 25 September 2023 08:00 | 06 October 2023 17:00 |  | 378
| 380 | 7 | 2.4.3.2.2.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 06 October 2023 17:00
| 381 | 8 | 2.4.3.2.2.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 22 September 2023 17:00
381 | 382 | 8 | 2.4.3.2.2.1.6.2 | Tier 3 | Data Services test scenarios submitted to Programme for assurance | 22 September 2023 17:00 | 22 September 2023 17:00 | 381 | 381FF
| 383 | 8 | 2.4.3.2.2.1.6.3 |  | Test scenarios assured by SI | 25 September 2023 08:00 | 06 October 2023 17:00 |  | 382
| 384 | 7 | 2.4.3.2.2.1.7 |  | PIT execution | 31 October 2022 08:00 | 03 November 2023 17:00 |  | 106SS
| 385 | 8 | 2.4.3.2.2.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 27 October 2023 17:00 |  | 386FF-5d
| 386 | 8 | 2.4.3.2.2.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 03 November 2023 17:00 |  | 605FF
| 387 | 6 | 2.4.3.2.2.2 |  | Data Services Migration/Reverse Migration DBT | 01 May 2023 08:00 | 13 May 2024 17:00
| 388 | 7 | 2.4.3.2.2.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 389 | 7 | 2.4.3.2.2.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 388SS
| 390 | 7 | 2.4.3.2.2.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 389SS
| 391 | 7 | 2.4.3.2.2.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 392 | 8 | 2.4.3.2.2.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 419FF-20d
| 393 | 8 | 2.4.3.2.2.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 419FF
393 | 394 | 8 | 2.4.3.2.2.2.4.3 | Tier 3 | SIT Metering Services' & Data Services' Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 393 | 393FF
| 395 | 5 | 2.4.3.2.3 |  | Metering Services DBT | 31 October 2022 08:00 | 13 May 2024 17:00
| 396 | 6 | 2.4.3.2.3.1 |  | Metering Services DBT (excl Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 17 November 2023 17:00
| 397 | 7 | 2.4.3.2.3.1.1 |  | Design | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 398 | 7 | 2.4.3.2.3.1.2 |  | Build | 01 February 2023 08:00 | 29 September 2023 17:00 |  | 94
| 399 | 7 | 2.4.3.2.3.1.3 |  | Test Approach & Plan | 31 October 2022 08:00 | 08 September 2023 17:00
| 400 | 8 | 2.4.3.2.3.1.3.1 |  | Develop Test Approach & Plan | 31 October 2022 08:00 | 25 August 2023 17:00
400 | 401 | 8 | 2.4.3.2.3.1.3.2 | Tier 3 | Metering Services Test Approach & Plan (PIT) submitted to Programme for assurance | 25 August 2023 17:00 | 25 August 2023 17:00 | 400 | 400FF
| 402 | 8 | 2.4.3.2.3.1.3.3 |  | Test approach and plan assured by SI | 28 August 2023 08:00 | 08 September 2023 17:00 |  | 401
| 403 | 7 | 2.4.3.2.3.1.4 |  | Test Readiness Report | 08 September 2023 08:00 | 17 November 2023 17:00
| 404 | 8 | 2.4.3.2.3.1.4.1 |  | Develop test readiness report | 08 September 2023 08:00 | 17 November 2023 17:00 |  | 401FS+9d
| 405 | 7 | 2.4.3.2.3.1.5 |  | Requirements to test Traceability Matrix (RTTM) | 31 October 2022 08:00 | 29 September 2023 17:00
| 406 | 8 | 2.4.3.2.3.1.5.1 |  | Develop RTTM | 31 October 2022 08:00 | 15 September 2023 17:00
406 | 407 | 8 | 2.4.3.2.3.1.5.2 | Tier 3 | Metering Services RTTM submitted to Programme for assurance | 15 September 2023 17:00 | 15 September 2023 17:00 | 406 | 406FF
| 408 | 8 | 2.4.3.2.3.1.5.3 |  | RTTM assured by SI | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 407
| 409 | 7 | 2.4.3.2.3.1.6 |  | Test Scenarios | 31 October 2022 08:00 | 29 September 2023 17:00
| 410 | 8 | 2.4.3.2.3.1.6.1 |  | Develop test scenarios | 31 October 2022 08:00 | 15 September 2023 17:00
410 | 411 | 8 | 2.4.3.2.3.1.6.2 | Tier 3 | Metering Services test scenarios submitted to Programme for assurance | 15 September 2023 17:00 | 15 September 2023 17:00 | 410 | 410FF
| 412 | 8 | 2.4.3.2.3.1.6.3 |  | Test scenarios assured by SI | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 411
| 413 | 7 | 2.4.3.2.3.1.7 |  | PIT execution | 31 October 2022 08:00 | 17 November 2023 17:00 |  | 106SS
| 414 | 8 | 2.4.3.2.3.1.7.1 |  | PIT Test Execution Progress Report | 31 October 2022 08:00 | 10 November 2023 17:00 |  | 415FF-5d
| 415 | 8 | 2.4.3.2.3.1.7.2 |  | PIT Execution | 31 October 2022 08:00 | 17 November 2023 17:00 |  | 641FF
| 416 | 6 | 2.4.3.2.3.2 |  | Metering Services Migration/Reverse Migration DBT | 01 May 2023 08:00 | 13 May 2024 17:00
| 417 | 7 | 2.4.3.2.3.2.1 |  | Design | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 1685
| 418 | 7 | 2.4.3.2.3.2.2 |  | Build | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 417SS
| 419 | 7 | 2.4.3.2.3.2.3 |  | PIT execution | 01 May 2023 08:00 | 13 May 2024 17:00 |  | 418SS
| 420 | 7 | 2.4.3.2.3.2.4 |  | PIT Test Completion Report (incl. evidence) | 19 March 2024 08:00 | 13 May 2024 17:00
| 421 | 8 | 2.4.3.2.3.2.4.1 |  | Develop PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 19 March 2024 08:00 | 15 April 2024 17:00 |  | 419FF-20d
| 422 | 8 | 2.4.3.2.3.2.4.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 18 April 2024 08:00 | 13 May 2024 17:00 |  | 419FF
422 | 423 | 8 | 2.4.3.2.3.2.4.3 | Tier 3 | SIT Metering Services' & Data Services' Migration/Reverse Migration PIT Completion Report submitted to Programme for assurance | 13 May 2024 17:00 | 13 May 2024 17:00 | 422 | 422FF
| 424 | 3 | 2.4.4 |  | Non-SIT Participants DBT | 01 February 2023 08:00 | 16 February 2026 17:00
| 425 | 4 | 2.4.4.1 |  | Non-SIT Participants DBT1 | 01 February 2023 08:00 | 30 June 2025 17:00 |  | 94,1593FF
| 426 | 4 | 2.4.4.2 |  | Non-SIT Participants DBT2 (consequentially-changed systems) | 01 February 2023 08:00 | 16 February 2026 17:00 |  | 94,1647FF
| 427 | 3 | 2.4.5 |  | DBT Monitoring and Assurance | 31 October 2022 08:00 | 19 January 2026 17:00
| 428 | 4 | 2.4.5.1 |  | Planning and DBT Progress Monitoring | 31 October 2022 08:00 | 19 January 2026 17:00
| 429 | 5 | 2.4.5.1.1 |  | DBT Progress Monitoring of Central Systems (incl. Migration/Reverse Migration DBT where applicable) | 31 October 2022 08:00 | 13 May 2024 17:00 |  | 102SS
| 430 | 5 | 2.4.5.1.2 |  | Planning and DBT Progress Monitoring of PPs | 31 October 2022 08:00 | 30 June 2025 17:00
| 431 | 6 | 2.4.5.1.2.1 |  | Monitor SIT Participants' Planning and DBT1 progress (incl. Migration/Reverse Migration DBT) | 31 October 2022 08:00 | 13 May 2024 17:00 |  | 96SS
| 432 | 6 | 2.4.5.1.2.2 |  | Monitor Non-SIT PPs Planning and DBT1 progress (to inform confirmation of Qualification Testing Tranche participants milestones) | 31 October 2022 08:00 | 30 June 2025 17:00 |  | 96SS
| 433 | 5 | 2.4.5.1.3 |  | DBT Progress Monitoring of Consequential Change | 01 February 2023 08:00 | 19 January 2026 17:00
| 434 | 6 | 2.4.5.1.3.1 |  | Monitor SMRS DBT progress | 01 February 2023 08:00 | 19 January 2026 17:00 |  | 332SS,365SS
| 435 | 6 | 2.4.5.1.3.2 |  | Monitor ECOES DBT progress | 01 February 2023 08:00 | 19 January 2026 17:00 |  | 332SS,365SS
| 436 | 6 | 2.4.5.1.3.3 |  | Monitor DTN DBT progress | 01 February 2023 08:00 | 19 January 2026 17:00 |  | 332SS,365SS
| 437 | 6 | 2.4.5.1.3.4 |  | Monitor & report data cleanse progress | 01 February 2023 08:00 | 19 January 2026 17:00 |  | 332SS,365SS
| 438 | 4 | 2.4.5.2 |  | Design Assurance | 14 November 2022 08:00 | 20 January 2025 17:00
| 439 | 5 | 2.4.5.2.1 |  | Participant Design Assurance Approach | 14 November 2022 08:00 | 11 January 2023 17:00
| 440 | 6 | 2.4.5.2.1.1 |  | Develop document | 14 November 2022 08:00 | 09 December 2022 17:00 |  | 52FS+10d
| 441 | 6 | 2.4.5.2.1.2 |  | Review document | 12 December 2022 08:00 | 04 January 2023 17:00 |  | 440
441 | 442 | 6 | 2.4.5.2.1.3 | Tier 3 | Participant Design Assurance Approach approved | 11 January 2023 17:00 | 11 January 2023 17:00 | 441 | 441FF+5d
| 443 | 5 | 2.4.5.2.2 |  | Central Systems & Registraion Services design assurance | 11 April 2023 08:00 | 27 October 2023 17:00
| 444 | 6 | 2.4.5.2.2.1 |  | Central Systems & Registration Services design assurance (excl Migration/Reverse Migration) | 11 April 2023 08:00 | 20 October 2023 17:00
444 | 445 | 6 | 2.4.5.2.2.2 | Tier 2 | Central Systems & Registration Services design assurance (excl Migration/Reverse Migration) complete | 27 October 2023 17:00 | 27 October 2023 17:00 | 444 | 444FF+5d
| 446 | 5 | 2.4.5.2.3 |  | SIT Participants design assurance | 09 May 2023 08:00 | 07 November 2023 17:00
| 447 | 6 | 2.4.5.2.3.1 |  | SIT PPs design assurance | 09 May 2023 08:00 | 31 October 2023 17:00
447 | 448 | 6 | 2.4.5.2.3.2 | Tier 2 | SIT PPs design assurance (excl Migration/Reverse Migration) complete | 07 November 2023 08:00 | 07 November 2023 17:00 | 447 | 447FF+5d
| 449 | 5 | 2.4.5.2.4 |  | Non-SIT PPs design assurance | 09 May 2023 08:00 | 20 January 2025 17:00
| 450 | 6 | 2.4.5.2.4.1 |  | Non-SIT PPs design assurance (risk-based sample) | 09 May 2023 08:00 | 20 January 2025 17:00 |  | 447SS,1615FF
| 451 | 4 | 2.4.5.3 |  | Test Assurance | 31 October 2022 08:00 | 30 June 2025 17:00
| 452 | 5 | 2.4.5.3.1 |  | Central Systems test assurance | 31 October 2022 08:00 | 09 October 2023 17:00 |  | 102SS
| 453 | 5 | 2.4.5.3.2 |  | SIT PPs test assurance | 31 October 2022 08:00 | 09 October 2023 17:00 |  | 226SS
| 454 | 5 | 2.4.5.3.3 |  | Non-SIT PPs test assurance | 01 February 2023 08:00 | 30 June 2025 17:00 |  | 424SS
| 455 | 2 | 2.5 |  | Pre-Qualification Guidance (PIT Guidance) | 31 October 2022 08:00 | 31 January 2023 17:00
| 456 | 3 | 2.5.1 |  | Develop document (incl collaboration with code bodies, as required) | 31 October 2022 08:00 | 16 January 2023 17:00
| 457 | 3 | 2.5.2 |  | Review, update and agree Pre-Qualification Guidance internally | 17 January 2023 08:00 | 31 January 2023 17:00 |  | 456
| 458 | 2 | 2.6 |  | External Programme Dependency Management | 03 November 2022 08:00 | 03 November 2022 08:00
| 459 | 3 | 2.6.1 |  | SLC47 | 03 November 2022 08:00 | 03 November 2022 08:00
| 460 | 4 | 2.6.1.1 |  | SLC47 implementation date | 03 November 2022 08:00 | 03 November 2022 08:00
| 461 | 2 | 2.7 | Tier 1 | System Design & Build - Tier 1 Milestones | 31 October 2022 08:00 | 31 October 2022 08:00
| 462 | 3 | 2.7.1 |  | Physical design baselined (M5) | 31 October 2022 08:00 | 31 October 2022 08:00
| 463 | 1 | 3 |  | SYSTEMS INTEGRATION TESTING (SIT) | 31 October 2022 08:00 | 19 January 2026 17:00
| 464 | 2 | 3.1 |  | SIT Preparation | 31 October 2022 08:00 | 09 September 2024 17:00
| 465 | 3 | 3.1.1 |  | Test Artefact Development | 31 October 2022 08:00 | 30 June 2023 17:00
| 466 | 4 | 3.1.1.1 |  | Environment Approach & Plan | 16 November 2022 08:00 | 30 June 2023 17:00
| 467 | 5 | 3.1.1.1.1 | Tier 3 | Environment Approach & Plan approved | 16 November 2022 08:00 | 16 November 2022 08:00
| 468 | 5 | 3.1.1.1.2 |  | Environment Approach & Plan - Work Off | 17 November 2022 08:00 | 23 June 2023 17:00 |  | 467FS+1d
468 | 469 | 5 | 3.1.1.1.3 | Tier 3 | Environment Approach & Plan - Work Off Approved | 30 June 2023 17:00 | 30 June 2023 17:00 | 468 | 468FS+5d
| 470 | 4 | 3.1.1.2 |  | Overarching Test Scope (for all stages) | 31 October 2022 08:00 | 30 June 2023 17:00
| 471 | 5 | 3.1.1.2.1 |  | Overarching Test Scope (excl. Migration/Reverse Migration, NFT and Ops components) | 31 October 2022 08:00 | 27 January 2023 17:00
| 472 | 6 | 3.1.1.2.1.1 |  | Develop document (excl Migration/Reverse Migration, NFT and Ops components) | 31 October 2022 08:00 | 13 January 2023 17:00 |  | 52
| 473 | 6 | 3.1.1.2.1.2 |  | Review, update & agree document (excl Migration/Reverse Migration, NFT and Ops components) | 16 January 2023 08:00 | 27 January 2023 17:00 |  | 472
| 474 | 5 | 3.1.1.2.2 |  | Updated Overarching Test Scope (incl. Migration/Reverse Migration, NFT and Ops components) | 01 May 2023 08:00 | 30 June 2023 17:00
| 475 | 6 | 3.1.1.2.2.1 |  | Develop Migration/Reverse Migration, NFT and Ops components of document | 01 May 2023 08:00 | 23 June 2023 17:00 |  | 1685
| 476 | 6 | 3.1.1.2.2.2 |  | Review, update & agree Migration/Reverse Migration, NFT and Ops components of document | 26 June 2023 08:00 | 30 June 2023 17:00 |  | 475
| 477 | 4 | 3.1.1.3 |  | Configuration and Release Management Approach & Plan | 01 November 2022 08:00 | 28 April 2023 17:00
| 478 | 5 | 3.1.1.3.1 |  | Develop document | 01 November 2022 08:00 | 31 January 2023 17:00
| 479 | 5 | 3.1.1.3.2 |  | Review, update and agree Configuration and Release Management Approach & Plan internally | 01 February 2023 08:00 | 28 April 2023 17:00 |  | 478
| 480 | 4 | 3.1.1.4 |  | Test Data Overarching Approach & Plan | 14 November 2022 08:00 | 26 May 2023 17:00
| 481 | 5 | 3.1.1.4.1 |  | Develop document | 14 November 2022 08:00 | 09 December 2022 17:00
| 482 | 5 | 3.1.1.4.2 |  | Document review and update | 12 December 2022 08:00 | 17 May 2023 17:00 |  | 481
482 | 483 | 5 | 3.1.1.4.3 | Tier 3 | Test Data Overarching Approach & Plan approved by TMAG | 17 May 2023 17:00 | 17 May 2023 17:00 | 482 | 482
| 484 | 5 | 3.1.1.4.4 |  | Document publication final version | 26 May 2023 08:00 | 26 May 2023 17:00 |  | 483FS+6d
| 485 | 4 | 3.1.1.5 |  | Interface Code of Connection (dates subject to DIP Service Provider's plan) | 01 March 2023 08:00 | 05 May 2023 17:00
| 486 | 5 | 3.1.1.5.1 |  | Develop Interface Code of Connection with DIP Service Provider | 01 March 2023 08:00 | 28 April 2023 17:00
| 487 | 5 | 3.1.1.5.2 |  | Interface Code of Connection approved at SDWG | 05 May 2023 17:00 | 05 May 2023 17:00 |  | 486FS+5d
| 488 | 3 | 3.1.2 |  | Test Tool Development | 31 October 2022 08:00 | 19 May 2023 17:00
| 489 | 4 | 3.1.2.1 |  | Test Management Tool | 31 October 2022 08:00 | 19 May 2023 17:00
| 490 | 5 | 3.1.2.1.1 |  | Test Management Tool Implementation | 31 October 2022 08:00 | 01 May 2023 17:00
| 491 | 6 | 3.1.2.1.1.1 |  | Requirements identification | 31 October 2022 08:00 | 23 December 2022 17:00
| 492 | 6 | 3.1.2.1.1.2 |  | Development | 02 January 2023 08:00 | 28 April 2023 17:00 |  | 491FS+5d
| 493 | 6 | 3.1.2.1.1.3 |  | Testing | 02 January 2023 08:00 | 28 April 2023 17:00 |  | 492FF
| 494 | 6 | 3.1.2.1.1.4 |  | Accept tool | 28 April 2023 17:00 | 28 April 2023 17:00 |  | 493FF
| 495 | 6 | 3.1.2.1.1.5 |  | Implementation | 01 May 2023 08:00 | 01 May 2023 17:00 |  | 494
| 496 | 5 | 3.1.2.1.2 |  | Test Management Tool User Guide | 27 February 2023 08:00 | 19 May 2023 17:00
| 497 | 6 | 3.1.2.1.2.1 |  | Develop document | 27 February 2023 08:00 | 28 April 2023 17:00 |  | 492FF,493FF
| 498 | 6 | 3.1.2.1.2.2 |  | Review, update and agree Test Management Tool User Guide internally | 01 May 2023 08:00 | 19 May 2023 17:00 |  | 497
| 499 | 5 | 3.1.2.1.3 |  | Test Management Tool Configuration Guide | 27 February 2023 08:00 | 19 May 2023 17:00
| 500 | 6 | 3.1.2.1.3.1 |  | Develop document | 27 February 2023 08:00 | 28 April 2023 17:00 |  | 492FF,493FF
| 501 | 6 | 3.1.2.1.3.2 |  | Review, update and agree Test Management Tool Configuration Guide internally | 01 May 2023 08:00 | 19 May 2023 17:00 |  | 500
| 502 | 4 | 3.1.2.2 |  | Test Query Tool | 31 October 2022 08:00 | 28 April 2023 17:00
| 503 | 5 | 3.1.2.2.1 |  | Test Query Tool Implementation | 31 October 2022 08:00 | 28 April 2023 17:00
| 504 | 6 | 3.1.2.2.1.1 |  | Requirements identification | 31 October 2022 08:00 | 25 November 2022 17:00
| 505 | 6 | 3.1.2.2.1.2 |  | Development | 11 April 2023 08:00 | 24 April 2023 17:00 |  | 504
| 506 | 6 | 3.1.2.2.1.3 |  | Testing | 18 April 2023 08:00 | 24 April 2023 17:00 |  | 505FF
| 507 | 6 | 3.1.2.2.1.4 |  | Accept tool | 24 April 2023 17:00 | 24 April 2023 17:00 |  | 506FF
| 508 | 6 | 3.1.2.2.1.5 |  | Implementation | 28 April 2023 08:00 | 28 April 2023 17:00 |  | 507FS+3d
| 509 | 5 | 3.1.2.2.2 |  | Test Query Tool User Guide | 11 April 2023 08:00 | 28 April 2023 17:00
| 510 | 6 | 3.1.2.2.2.1 |  | Develop document | 11 April 2023 08:00 | 24 April 2023 17:00 |  | 505SS
| 511 | 6 | 3.1.2.2.2.2 |  | Review, update and agree Test Query Tool User Guide internally | 25 April 2023 08:00 | 28 April 2023 17:00 |  | 510
| 512 | 3 | 3.1.3 |  | SIT Stage-Specific Preparation | 31 October 2022 08:00 | 09 September 2024 17:00
| 513 | 4 | 3.1.3.1 |  | SIT Component Integration Preparation | 31 October 2022 08:00 | 22 January 2024 17:00
| 514 | 5 | 3.1.3.1.1 |  | Test Approach & Plan | 31 October 2022 08:00 | 30 June 2023 17:00
| 515 | 6 | 3.1.3.1.1.1 |  | Develop document with SITWG | 31 October 2022 08:00 | 12 May 2023 17:00
| 516 | 6 | 3.1.3.1.1.2 |  | Artefact review (via TMAG) and updates | 15 May 2023 08:00 | 23 June 2023 17:00 |  | 515
516 | 517 | 6 | 3.1.3.1.1.3 | Tier 3 | SIT Component Integration Testing Test Approach & Plan approved | 30 June 2023 17:00 | 30 June 2023 17:00 | 516 | 516FS+5d
| 518 | 5 | 3.1.3.1.2 |  | Test Data Approach & Plan | 31 October 2022 08:00 | 30 June 2023 17:00
| 519 | 6 | 3.1.3.1.2.1 |  | Develop document | 31 October 2022 08:00 | 12 May 2023 17:00 |  | 515SS
| 520 | 6 | 3.1.3.1.2.2 |  | Review, update & agree document internally | 22 May 2023 08:00 | 30 June 2023 17:00 |  | 519,517FF
| 521 | 5 | 3.1.3.1.3 |  | Test scenarios | 02 January 2023 08:00 | 02 June 2023 17:00
| 522 | 6 | 3.1.3.1.3.1 |  | Development of test scenarios | 02 January 2023 08:00 | 28 April 2023 17:00 |  | 515SS+45d
| 523 | 6 | 3.1.3.1.3.2 |  | Review test scenarios with SIT Working Group | 01 February 2023 08:00 | 26 May 2023 17:00 |  | 522SS+22d
523 | 524 | 6 | 3.1.3.1.3.3 | Tier 3 | SIT Component Integration Testing Test scenarios approved | 02 June 2023 17:00 | 02 June 2023 17:00 | 523 | 523FS+5d
| 525 | 5 | 3.1.3.1.4 |  | Test cases | 01 May 2023 08:00 | 01 September 2023 17:00
| 526 | 6 | 3.1.3.1.4.1 |  | SI Test cases | 01 May 2023 08:00 | 01 September 2023 17:00
| 527 | 7 | 3.1.3.1.4.1.1 |  | Development of Test cases | 01 May 2023 08:00 | 28 July 2023 17:00 |  | 522
| 528 | 7 | 3.1.3.1.4.1.2 |  | Review Test cases with SIT Working Group | 26 May 2023 08:00 | 25 August 2023 17:00 |  | 527SS+19d
528 | 529 | 7 | 3.1.3.1.4.1.3 | Tier 3 | SIT Component Integration Testing Test cases approved | 01 September 2023 17:00 | 01 September 2023 17:00 | 528 | 528FS+5d
| 530 | 5 | 3.1.3.1.5 |  | CIT Interval 1 Preparation | 16 November 2022 08:00 | 24 November 2023 17:00
| 531 | 6 | 3.1.3.1.5.1 |  | PIT Test Completion Report (incl. evidence) | 08 September 2023 08:00 | 06 October 2023 17:00
| 532 | 7 | 3.1.3.1.5.1.1 |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 08 September 2023 08:00 | 08 September 2023 17:00
| 533 | 7 | 3.1.3.1.5.1.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 11 September 2023 08:00 | 29 September 2023 17:00 |  | 532
533 | 534 | 7 | 3.1.3.1.5.1.3 | Tier 3 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 1 | 29 September 2023 17:00 | 29 September 2023 17:00 | 533 | 533
| 535 | 7 | 3.1.3.1.5.1.4 |  | PP Final PIT Completion Reports assured by SI | 02 October 2023 08:00 | 06 October 2023 17:00 |  | 534
| 536 | 6 | 3.1.3.1.5.2 |  | Environments (SIT A) | 16 November 2022 08:00 | 06 October 2023 17:00
| 537 | 7 | 3.1.3.1.5.2.1 |  | PPs register PKI Officers and request PKI certificates | 28 August 2023 08:00 | 01 September 2023 17:00 |  | 538FF
| 538 | 7 | 3.1.3.1.5.2.2 |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 01 September 2023 17:00 |  | 467
| 539 | 7 | 3.1.3.1.5.2.3 |  | SI coordinate SIT Participants' SIT A environment preparation | 16 November 2022 08:00 | 01 September 2023 17:00 |  | 538SS
| 540 | 7 | 3.1.3.1.5.2.4 |  | PP submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 01 September 2023 17:00 | 01 September 2023 17:00 |  | 538FF
| 541 | 7 | 3.1.3.1.5.2.5 |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 04 September 2023 08:00 | 08 September 2023 17:00 |  | 540FF+5d
540 | 542 | 7 | 3.1.3.1.5.2.6 | Tier 3 | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 1 | 01 September 2023 17:00 | 01 September 2023 17:00 | 540 | 540SS
| 543 | 7 | 3.1.3.1.5.2.7 |  | PP SIT A environment connectivity proving | 04 September 2023 08:00 | 29 September 2023 17:00 |  | 534FF,542
| 544 | 7 | 3.1.3.1.5.2.8 |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 04 September 2023 08:00 | 29 September 2023 17:00 |  | 543SS
| 545 | 7 | 3.1.3.1.5.2.9 |  | PP deployment of MHHS solution code to SIT A environments | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 560FF
| 546 | 7 | 3.1.3.1.5.2.10 |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 560FF
| 547 | 7 | 3.1.3.1.5.2.11 |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 04 September 2023 08:00 | 29 September 2023 17:00 |  | 543SS
| 548 | 7 | 3.1.3.1.5.2.12 |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 04 September 2023 08:00 | 06 October 2023 17:00 |  | 547FF+5d
| 549 | 6 | 3.1.3.1.5.3 |  | Test Data (SIT A) | 17 July 2023 08:00 | 06 October 2023 17:00
| 550 | 7 | 3.1.3.1.5.3.1 |  | SI allocate test data to SIT Participants | 17 July 2023 08:00 | 01 September 2023 17:00 |  | 542FF
| 551 | 7 | 3.1.3.1.5.3.2 |  | PP SIT A environment test data loading & verification (& data cleansing, if required) | 04 September 2023 08:00 | 29 September 2023 17:00 |  | 543SS,552SS,560FF
| 552 | 7 | 3.1.3.1.5.3.3 |  | SI coordinate SIT A environment test data loading and verification (and data cleansing, if required) | 04 September 2023 08:00 | 29 September 2023 17:00 |  | 534FF,560FF
| 553 | 7 | 3.1.3.1.5.3.4 |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 29 September 2023 17:00 | 29 September 2023 17:00 |  | 551FF
| 554 | 7 | 3.1.3.1.5.3.5 |  | SI assure evidence of SIT Participants' SIT A environment test data load and verification | 04 September 2023 08:00 | 06 October 2023 17:00 |  | 551FF+5d
| 555 | 6 | 3.1.3.1.5.4 |  | Other Preparation | 12 June 2023 08:00 | 24 November 2023 17:00
| 556 | 7 | 3.1.3.1.5.4.1 |  | Onboarding of Test Participants to Test Management Tool | 12 June 2023 08:00 | 01 September 2023 17:00 |  | 542SF
| 557 | 7 | 3.1.3.1.5.4.2 |  | Test Management Tool onboarding | 12 June 2023 08:00 | 01 September 2023 17:00 |  | 542SF
| 558 | 7 | 3.1.3.1.5.4.3 |  | Other Preparation (activities TBC) | 03 July 2023 08:00 | 24 November 2023 17:00 |  | 517
| 559 | 6 | 3.1.3.1.5.5 |  | SIT Component Integration Test Readiness Report | 11 September 2023 08:00 | 13 October 2023 17:00
| 560 | 7 | 3.1.3.1.5.5.1 |  | PP submit Test Readiness Report to Programme for assurance | 29 September 2023 17:00 | 29 September 2023 17:00 |  | 543FF
| 561 | 7 | 3.1.3.1.5.5.2 |  | SI assure Test Participants' Test Readiness Reports | 02 October 2023 08:00 | 06 October 2023 17:00 |  | 560FF+5d
| 562 | 7 | 3.1.3.1.5.5.3 |  | SI develop Overarching SIT Component Integration Test Readiness Report | 11 September 2023 08:00 | 06 October 2023 17:00 |  | 561FF
| 563 | 7 | 3.1.3.1.5.5.4 |  | Artefact review (via TMAG) and updates | 09 October 2023 08:00 | 13 October 2023 17:00 |  | 562
563 | 564 | 6 | 3.1.3.1.5.6 | Tier 2 | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 23 October 2023 17:00 | 23 October 2023 17:00 | 563 | 563SS+11d
| 565 | 5 | 3.1.3.1.6 |  | CIT Interval 2 Preparation | 16 November 2022 08:00 | 24 November 2023 17:00
| 566 | 6 | 3.1.3.1.6.1 |  | PIT Test Completion Report (incl. evidence) | 29 September 2023 08:00 | 27 October 2023 17:00
| 567 | 7 | 3.1.3.1.6.1.1 |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 29 September 2023 08:00 | 29 September 2023 17:00 |  | 232,233
| 568 | 7 | 3.1.3.1.6.1.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 02 October 2023 08:00 | 20 October 2023 17:00 |  | 567
568 | 569 | 7 | 3.1.3.1.6.1.3 | Tier 3 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 2 | 20 October 2023 17:00 | 20 October 2023 17:00 | 568 | 568
| 570 | 7 | 3.1.3.1.6.1.4 |  | PP Final PIT Completion Reports assured by SI | 23 October 2023 08:00 | 27 October 2023 17:00 |  | 569
| 571 | 6 | 3.1.3.1.6.2 |  | Environments (SIT A) | 16 November 2022 08:00 | 27 October 2023 17:00
| 572 | 7 | 3.1.3.1.6.2.1 |  | PPs register PKI Officers | 11 September 2023 08:00 | 15 September 2023 17:00 |  | 573FF-5d
| 573 | 7 | 3.1.3.1.6.2.2 |  | PPs request PKI certificates | 18 September 2023 08:00 | 22 September 2023 17:00 |  | 574FF
| 574 | 7 | 3.1.3.1.6.2.3 |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 22 September 2023 17:00 |  | 467
| 575 | 7 | 3.1.3.1.6.2.4 |  | SI coordinate SIT Participants' SIT A environment preparation | 16 November 2022 08:00 | 22 September 2023 17:00 |  | 574SS
| 576 | 7 | 3.1.3.1.6.2.5 |  | PP submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 22 September 2023 17:00 | 22 September 2023 17:00 |  | 574FF
| 577 | 7 | 3.1.3.1.6.2.6 |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 25 September 2023 08:00 | 29 September 2023 17:00 |  | 576FF+5d
576 | 578 | 7 | 3.1.3.1.6.2.7 | Tier 3 | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 2 | 22 September 2023 17:00 | 22 September 2023 17:00 | 576 | 576SS
| 579 | 7 | 3.1.3.1.6.2.8 |  | PP SIT A environment connectivity proving | 25 September 2023 08:00 | 20 October 2023 17:00 |  | 569FF,578
| 580 | 7 | 3.1.3.1.6.2.9 |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 25 September 2023 08:00 | 20 October 2023 17:00 |  | 579SS
| 581 | 7 | 3.1.3.1.6.2.10 |  | PP deployment of MHHS solution code to SIT A environments | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 596FF
| 582 | 7 | 3.1.3.1.6.2.11 |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 09 October 2023 08:00 | 20 October 2023 17:00 |  | 596FF
| 583 | 7 | 3.1.3.1.6.2.12 |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 25 September 2023 08:00 | 20 October 2023 17:00 |  | 579SS
| 584 | 7 | 3.1.3.1.6.2.13 |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 25 September 2023 08:00 | 27 October 2023 17:00 |  | 583FF+5d
| 585 | 6 | 3.1.3.1.6.3 |  | Test Data (SIT A) | 07 August 2023 08:00 | 27 October 2023 17:00
| 586 | 7 | 3.1.3.1.6.3.1 |  | SI allocate test data to SIT Participants | 07 August 2023 08:00 | 22 September 2023 17:00 |  | 578FF
| 587 | 7 | 3.1.3.1.6.3.2 |  | PP SIT A environment test data loading & verification (& data cleansing, if required) | 25 September 2023 08:00 | 20 October 2023 17:00 |  | 588SS,579SS,596FF
| 588 | 7 | 3.1.3.1.6.3.3 |  | SI coordinate SIT A environment test data loading and verification (and data cleansing, if required) | 25 September 2023 08:00 | 20 October 2023 17:00 |  | 569FF,596FF
| 589 | 7 | 3.1.3.1.6.3.4 |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 20 October 2023 17:00 | 20 October 2023 17:00 |  | 587FF
| 590 | 7 | 3.1.3.1.6.3.5 |  | SI assure evidence of SIT Participants' SIT A environment test data load and verification | 25 September 2023 08:00 | 27 October 2023 17:00 |  | 587FF+5d
| 591 | 6 | 3.1.3.1.6.4 |  | Other Preparation | 03 July 2023 08:00 | 24 November 2023 17:00
| 592 | 7 | 3.1.3.1.6.4.1 |  | Onboarding of Test Participants to Test Management Tool | 03 July 2023 08:00 | 22 September 2023 17:00 |  | 578SF
| 593 | 7 | 3.1.3.1.6.4.2 |  | Test Management Tool onboarding | 03 July 2023 08:00 | 22 September 2023 17:00 |  | 578SF
| 594 | 7 | 3.1.3.1.6.4.3 |  | Other Preparation (activities TBC) | 03 July 2023 08:00 | 24 November 2023 17:00 |  | 517,569FF
| 595 | 6 | 3.1.3.1.6.5 |  | SIT Component Integration Test Readiness Report | 02 October 2023 08:00 | 03 November 2023 17:00
| 596 | 7 | 3.1.3.1.6.5.1 |  | PP submit Test Readiness Report to Programme for assurance | 20 October 2023 17:00 | 20 October 2023 17:00 |  | 579FF
| 597 | 7 | 3.1.3.1.6.5.2 |  | SI assure Test Participants' Test Readiness Reports | 23 October 2023 08:00 | 27 October 2023 17:00 |  | 596FF+5d
| 598 | 7 | 3.1.3.1.6.5.3 |  | SI develop Overarching SIT Component Integration Test Readiness Report | 02 October 2023 08:00 | 27 October 2023 17:00 |  | 597FF
| 599 | 7 | 3.1.3.1.6.5.4 |  | Artefact review (via TMAG) and updates | 30 October 2023 08:00 | 03 November 2023 17:00 |  | 598
599 | 600 | 6 | 3.1.3.1.6.6 | Tier 2 | SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 06 November 2023 17:00 | 06 November 2023 17:00 | 599 | 599SS+6d
| 601 | 5 | 3.1.3.1.7 |  | CIT Interval 3 Preparation | 16 November 2022 08:00 | 24 November 2023 17:00
| 602 | 6 | 3.1.3.1.7.1 |  | PIT Test Completion Report (incl. evidence) | 13 October 2023 08:00 | 10 November 2023 17:00
| 603 | 7 | 3.1.3.1.7.1.1 |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 13 October 2023 08:00 | 13 October 2023 17:00
| 604 | 7 | 3.1.3.1.7.1.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 16 October 2023 08:00 | 03 November 2023 17:00 |  | 603
604 | 605 | 7 | 3.1.3.1.7.1.3 | Tier 3 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | 03 November 2023 17:00 | 03 November 2023 17:00 | 604 | 604
| 606 | 7 | 3.1.3.1.7.1.4 |  | PP Final PIT Completion Reports assured by SI | 06 November 2023 08:00 | 10 November 2023 17:00 |  | 605
| 607 | 6 | 3.1.3.1.7.2 |  | Environments (SIT A) | 16 November 2022 08:00 | 10 November 2023 17:00
| 608 | 7 | 3.1.3.1.7.2.1 |  | PPs register PKI Officers | 25 September 2023 08:00 | 29 September 2023 17:00 |  | 609FF-5d
| 609 | 7 | 3.1.3.1.7.2.2 |  | PPs request PKI certificates | 02 October 2023 08:00 | 06 October 2023 17:00 |  | 610FF
| 610 | 7 | 3.1.3.1.7.2.3 |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 06 October 2023 17:00 |  | 467
| 611 | 7 | 3.1.3.1.7.2.4 |  | SI coordinate SIT Participants' SIT A environment preparation | 16 November 2022 08:00 | 06 October 2023 17:00 |  | 610SS
| 612 | 7 | 3.1.3.1.7.2.5 |  | PP submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 06 October 2023 17:00 | 06 October 2023 17:00 |  | 610FF
| 613 | 7 | 3.1.3.1.7.2.6 |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 09 October 2023 08:00 | 13 October 2023 17:00 |  | 612FF+5d
612 | 614 | 7 | 3.1.3.1.7.2.7 | Tier 3 | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 3 | 06 October 2023 17:00 | 06 October 2023 17:00 | 612 | 612SS
| 615 | 7 | 3.1.3.1.7.2.8 |  | PP SIT A environment connectivity proving | 09 October 2023 08:00 | 03 November 2023 17:00 |  | 605FF,614
| 616 | 7 | 3.1.3.1.7.2.9 |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 09 October 2023 08:00 | 03 November 2023 17:00 |  | 615SS
| 617 | 7 | 3.1.3.1.7.2.10 |  | PP deployment of MHHS solution code to SIT A environments | 23 October 2023 08:00 | 03 November 2023 17:00 |  | 632FF
| 618 | 7 | 3.1.3.1.7.2.11 |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 23 October 2023 08:00 | 03 November 2023 17:00 |  | 632FF
| 619 | 7 | 3.1.3.1.7.2.12 |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 09 October 2023 08:00 | 03 November 2023 17:00 |  | 615SS
| 620 | 7 | 3.1.3.1.7.2.13 |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 09 October 2023 08:00 | 10 November 2023 17:00 |  | 619FF+5d
| 621 | 6 | 3.1.3.1.7.3 |  | Test Data (SIT A) | 21 August 2023 08:00 | 10 November 2023 17:00
| 622 | 7 | 3.1.3.1.7.3.1 |  | SI allocate test data to SIT Participants | 21 August 2023 08:00 | 06 October 2023 17:00 |  | 614FF
| 623 | 7 | 3.1.3.1.7.3.2 |  | PP SIT A environment test data loading & verification (& data cleansing, if required) | 09 October 2023 08:00 | 03 November 2023 17:00 |  | 615SS,624SS,632FF
| 624 | 7 | 3.1.3.1.7.3.3 |  | SI coordinate SIT A environment test data loading and verification (and data cleansing, if required) | 09 October 2023 08:00 | 03 November 2023 17:00 |  | 605FF,632FF
| 625 | 7 | 3.1.3.1.7.3.4 |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 03 November 2023 17:00 | 03 November 2023 17:00 |  | 623FF
| 626 | 7 | 3.1.3.1.7.3.5 |  | SI assure evidence of SIT Participants' SIT A environment test data load and verification | 09 October 2023 08:00 | 10 November 2023 17:00 |  | 623FF+5d
| 627 | 6 | 3.1.3.1.7.4 |  | Other Preparation | 03 July 2023 08:00 | 24 November 2023 17:00
| 628 | 7 | 3.1.3.1.7.4.1 |  | Onboarding of Test Participants to Test Management Tool | 17 July 2023 08:00 | 06 October 2023 17:00 |  | 614SF
| 629 | 7 | 3.1.3.1.7.4.2 |  | Test Management Tool onboarding | 17 July 2023 08:00 | 06 October 2023 17:00 |  | 614SF
| 630 | 7 | 3.1.3.1.7.4.3 |  | Other Preparation (activities TBC) | 03 July 2023 08:00 | 24 November 2023 17:00 |  | 517,605FF
| 631 | 6 | 3.1.3.1.7.5 |  | SIT Component Integration Test Readiness Report | 16 October 2023 08:00 | 17 November 2023 17:00
| 632 | 7 | 3.1.3.1.7.5.1 |  | PP submit Test Readiness Report to Programme for assurance | 03 November 2023 17:00 | 03 November 2023 17:00 |  | 615FF
| 633 | 7 | 3.1.3.1.7.5.2 |  | SI assure Test Participants' Test Readiness Reports | 06 November 2023 08:00 | 10 November 2023 17:00 |  | 632FF+5d
| 634 | 7 | 3.1.3.1.7.5.3 |  | SI develop Overarching SIT Component Integration Test Readiness Report | 16 October 2023 08:00 | 10 November 2023 17:00 |  | 633FF
| 635 | 7 | 3.1.3.1.7.5.4 |  | Artefact review (via TMAG) and updates | 13 November 2023 08:00 | 17 November 2023 17:00 |  | 634
635 | 636 | 6 | 3.1.3.1.7.6 | Tier 2 | SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 20 November 2023 17:00 | 20 November 2023 17:00 | 635 | 635SS+6d
| 637 | 5 | 3.1.3.1.8 |  | CIT Interval 4 Preparation | 16 November 2022 08:00 | 04 December 2023 17:00
| 638 | 6 | 3.1.3.1.8.1 |  | PIT Test Completion Report (incl. evidence) | 27 October 2023 08:00 | 24 November 2023 17:00
| 639 | 7 | 3.1.3.1.8.1.1 |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 27 October 2023 08:00 | 27 October 2023 17:00
| 640 | 7 | 3.1.3.1.8.1.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 30 October 2023 08:00 | 17 November 2023 17:00 |  | 639
640 | 641 | 7 | 3.1.3.1.8.1.3 | Tier 3 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | 17 November 2023 17:00 | 17 November 2023 17:00 | 640 | 640
| 642 | 7 | 3.1.3.1.8.1.4 |  | PP Final PIT Completion Reports assured by SI | 20 November 2023 08:00 | 24 November 2023 17:00 |  | 641
| 643 | 6 | 3.1.3.1.8.2 |  | Environments (SIT A) | 16 November 2022 08:00 | 24 November 2023 17:00
| 644 | 7 | 3.1.3.1.8.2.1 |  | PPs register PKI Officers | 09 October 2023 08:00 | 13 October 2023 17:00 |  | 645FF-5d
| 645 | 7 | 3.1.3.1.8.2.2 |  | PPs request PKI certificates | 16 October 2023 08:00 | 20 October 2023 17:00 |  | 646FF
| 646 | 7 | 3.1.3.1.8.2.3 |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 20 October 2023 17:00 |  | 467
| 647 | 7 | 3.1.3.1.8.2.4 |  | SI coordinate SIT Participants' SIT A environment preparation | 16 November 2022 08:00 | 20 October 2023 17:00 |  | 646SS
| 648 | 7 | 3.1.3.1.8.2.5 |  | PP submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 20 October 2023 17:00 | 20 October 2023 17:00 |  | 646FF
| 649 | 7 | 3.1.3.1.8.2.6 |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 23 October 2023 08:00 | 27 October 2023 17:00 |  | 648FF+5d
648 | 650 | 7 | 3.1.3.1.8.2.7 | Tier 3 | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 4 | 20 October 2023 17:00 | 20 October 2023 17:00 | 648 | 648SS
| 651 | 7 | 3.1.3.1.8.2.8 |  | PP SIT A environment connectivity proving | 23 October 2023 08:00 | 17 November 2023 17:00 |  | 641FF,650
| 652 | 7 | 3.1.3.1.8.2.9 |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 23 October 2023 08:00 | 17 November 2023 17:00 |  | 651SS
| 653 | 7 | 3.1.3.1.8.2.10 |  | PP deployment of MHHS solution code to SIT A environments | 06 November 2023 08:00 | 17 November 2023 17:00 |  | 668FF
| 654 | 7 | 3.1.3.1.8.2.11 |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 06 November 2023 08:00 | 17 November 2023 17:00 |  | 668FF
| 655 | 7 | 3.1.3.1.8.2.12 |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 23 October 2023 08:00 | 17 November 2023 17:00 |  | 651SS
| 656 | 7 | 3.1.3.1.8.2.13 |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 23 October 2023 08:00 | 24 November 2023 17:00 |  | 655FF+5d
| 657 | 6 | 3.1.3.1.8.3 |  | Test Data (SIT A) | 04 September 2023 08:00 | 24 November 2023 17:00
| 658 | 7 | 3.1.3.1.8.3.1 |  | SI allocate test data to SIT Participants | 04 September 2023 08:00 | 20 October 2023 17:00 |  | 650FF
| 659 | 7 | 3.1.3.1.8.3.2 |  | PP SIT A environment test data loading & verification (& data cleansing, if required) | 23 October 2023 08:00 | 17 November 2023 17:00 |  | 651SS,660SS,668FF
| 660 | 7 | 3.1.3.1.8.3.3 |  | SI coordinate SIT A environment test data loading and verification (and data cleansing, if required) | 23 October 2023 08:00 | 17 November 2023 17:00 |  | 641FF,668FF
| 661 | 7 | 3.1.3.1.8.3.4 |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 17 November 2023 17:00 | 17 November 2023 17:00 |  | 659FF
| 662 | 7 | 3.1.3.1.8.3.5 |  | SI assure evidence of SIT Participants' SIT A environment test data load and verification | 23 October 2023 08:00 | 24 November 2023 17:00 |  | 659FF+5d
| 663 | 6 | 3.1.3.1.8.4 |  | Other Preparation | 03 July 2023 08:00 | 24 November 2023 17:00
| 664 | 7 | 3.1.3.1.8.4.1 |  | Onboarding of Test Participants to Test Management Tool | 31 July 2023 08:00 | 20 October 2023 17:00 |  | 650SF
| 665 | 7 | 3.1.3.1.8.4.2 |  | Test Management Tool onboarding | 31 July 2023 08:00 | 20 October 2023 17:00 |  | 650SF
| 666 | 7 | 3.1.3.1.8.4.3 |  | Other Preparation (activities TBC) | 03 July 2023 08:00 | 24 November 2023 17:00 |  | 641FF,517
| 667 | 6 | 3.1.3.1.8.5 |  | SIT Component Integration Test Readiness Report | 30 October 2023 08:00 | 01 December 2023 17:00
| 668 | 7 | 3.1.3.1.8.5.1 |  | PP submit Test Readiness Report to Programme for assurance | 17 November 2023 17:00 | 17 November 2023 17:00 |  | 651FF
| 669 | 7 | 3.1.3.1.8.5.2 |  | SI assure Test Participants' Test Readiness Reports | 20 November 2023 08:00 | 24 November 2023 17:00 |  | 668FF+5d
| 670 | 7 | 3.1.3.1.8.5.3 |  | SI develop Overarching SIT Component Integration Test Readiness Report | 30 October 2023 08:00 | 24 November 2023 17:00 |  | 669FF
| 671 | 7 | 3.1.3.1.8.5.4 |  | Artefact review (via TMAG) and updates | 27 November 2023 08:00 | 01 December 2023 17:00 |  | 670
671 | 672 | 6 | 3.1.3.1.8.6 | Tier 2 | SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 04 December 2023 17:00 | 04 December 2023 17:00 | 671 | 671SS+6d
| 673 | 5 | 3.1.3.1.9 |  | CIT Interval 5 Preparation | 16 November 2022 08:00 | 08 January 2024 17:00
| 674 | 6 | 3.1.3.1.9.1 |  | PIT Test Completion Report (incl. evidence) | 17 November 2023 08:00 | 15 December 2023 17:00
| 675 | 7 | 3.1.3.1.9.1.1 |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 17 November 2023 08:00 | 17 November 2023 17:00
| 676 | 7 | 3.1.3.1.9.1.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 20 November 2023 08:00 | 08 December 2023 17:00 |  | 675
676 | 677 | 7 | 3.1.3.1.9.1.3 | Tier 3 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | 08 December 2023 17:00 | 08 December 2023 17:00 | 676 | 676
| 678 | 7 | 3.1.3.1.9.1.4 |  | PP Final PIT Completion Reports assured by SI | 11 December 2023 08:00 | 15 December 2023 17:00 |  | 677
| 679 | 6 | 3.1.3.1.9.2 |  | Environments (SIT A) | 16 November 2022 08:00 | 15 December 2023 17:00
| 680 | 7 | 3.1.3.1.9.2.1 |  | PPs register PKI Officers | 30 October 2023 08:00 | 03 November 2023 17:00 |  | 681FF-5d
| 681 | 7 | 3.1.3.1.9.2.2 |  | PPs request PKI certificates | 06 November 2023 08:00 | 10 November 2023 17:00 |  | 682FF
| 682 | 7 | 3.1.3.1.9.2.3 |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 10 November 2023 17:00 |  | 467
| 683 | 7 | 3.1.3.1.9.2.4 |  | SI coordinate SIT Participants' SIT A environment preparation | 16 November 2022 08:00 | 10 November 2023 17:00 |  | 682SS
| 684 | 7 | 3.1.3.1.9.2.5 |  | PP submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 10 November 2023 17:00 | 10 November 2023 17:00 |  | 682FF
| 685 | 7 | 3.1.3.1.9.2.6 |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 13 November 2023 08:00 | 17 November 2023 17:00 |  | 684FF+5d
684 | 686 | 7 | 3.1.3.1.9.2.7 | Tier 3 | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 5 | 10 November 2023 17:00 | 10 November 2023 17:00 | 684 | 684SS
| 687 | 7 | 3.1.3.1.9.2.8 |  | PP SIT A environment connectivity proving | 13 November 2023 08:00 | 08 December 2023 17:00 |  | 677FF,686
| 688 | 7 | 3.1.3.1.9.2.9 |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 13 November 2023 08:00 | 08 December 2023 17:00 |  | 687SS
| 689 | 7 | 3.1.3.1.9.2.10 |  | PP deployment of MHHS solution code to SIT A environments | 27 November 2023 08:00 | 08 December 2023 17:00 |  | 704FF
| 690 | 7 | 3.1.3.1.9.2.11 |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 27 November 2023 08:00 | 08 December 2023 17:00 |  | 704FF
| 691 | 7 | 3.1.3.1.9.2.12 |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 13 November 2023 08:00 | 08 December 2023 17:00 |  | 687SS
| 692 | 7 | 3.1.3.1.9.2.13 |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 13 November 2023 08:00 | 15 December 2023 17:00 |  | 691FF+5d
| 693 | 6 | 3.1.3.1.9.3 |  | Test Data (SIT A) | 25 September 2023 08:00 | 15 December 2023 17:00
| 694 | 7 | 3.1.3.1.9.3.1 |  | SI allocate test data to SIT Participants | 25 September 2023 08:00 | 10 November 2023 17:00 |  | 686FF
| 695 | 7 | 3.1.3.1.9.3.2 |  | PP SIT A environment test data loading & verification (& data cleansing, if required) | 13 November 2023 08:00 | 08 December 2023 17:00 |  | 687SS,696SS,704FF
| 696 | 7 | 3.1.3.1.9.3.3 |  | SI coordinate SIT A environment test data loading and verification (and data cleansing, if required) | 13 November 2023 08:00 | 08 December 2023 17:00 |  | 677FF,704FF
| 697 | 7 | 3.1.3.1.9.3.4 |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 08 December 2023 17:00 | 08 December 2023 17:00 |  | 695FF
| 698 | 7 | 3.1.3.1.9.3.5 |  | SI assure evidence of SIT Participants' SIT A environment test data load and verification | 13 November 2023 08:00 | 15 December 2023 17:00 |  | 695FF+5d
| 699 | 6 | 3.1.3.1.9.4 |  | Other Preparation | 17 July 2023 08:00 | 08 December 2023 17:00
| 700 | 7 | 3.1.3.1.9.4.1 |  | Onboarding of Test Participants to Test Management Tool | 21 August 2023 08:00 | 10 November 2023 17:00 |  | 686SF
| 701 | 7 | 3.1.3.1.9.4.2 |  | Test Management Tool onboarding | 21 August 2023 08:00 | 10 November 2023 17:00 |  | 686SF
| 702 | 7 | 3.1.3.1.9.4.3 |  | Other Preparation (activities TBC) | 17 July 2023 08:00 | 08 December 2023 17:00 |  | 677FF,517
| 703 | 6 | 3.1.3.1.9.5 |  | SIT Component Integration Test Readiness Report | 20 November 2023 08:00 | 05 January 2024 17:00
| 704 | 7 | 3.1.3.1.9.5.1 |  | PP submit Test Readiness Report to Programme for assurance | 08 December 2023 17:00 | 08 December 2023 17:00 |  | 687FF
| 705 | 7 | 3.1.3.1.9.5.2 |  | SI assure Test Participants' Test Readiness Reports | 11 December 2023 08:00 | 15 December 2023 17:00 |  | 704FF+5d
| 706 | 7 | 3.1.3.1.9.5.3 |  | SI develop Overarching SIT Component Integration Test Readiness Report | 20 November 2023 08:00 | 15 December 2023 17:00 |  | 705FF
| 707 | 7 | 3.1.3.1.9.5.4 |  | Artefact review (via TMAG) and updates | 18 December 2023 08:00 | 05 January 2024 17:00 |  | 706
707 | 708 | 6 | 3.1.3.1.9.6 | Tier 2 | SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 08 January 2024 17:00 | 08 January 2024 17:00 | 707 | 707SS+16d
| 709 | 5 | 3.1.3.1.10 |  | CIT Interval 6 Preparation | 16 November 2022 08:00 | 22 January 2024 17:00
| 710 | 6 | 3.1.3.1.10.1 |  | PIT Test Completion Report (incl. evidence) | 01 December 2023 08:00 | 12 January 2024 17:00
| 711 | 7 | 3.1.3.1.10.1.1 |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 01 December 2023 08:00 | 01 December 2023 17:00 |  | 234,235,236
| 712 | 7 | 3.1.3.1.10.1.2 |  | Finalise PIT Test Completion Report (incl. evidence) | 04 December 2023 08:00 | 05 January 2024 17:00 |  | 711
712 | 713 | 7 | 3.1.3.1.10.1.3 | Tier 3 | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | 05 January 2024 17:00 | 05 January 2024 17:00 | 712 | 712
| 714 | 7 | 3.1.3.1.10.1.4 |  | PP Final PIT Completion Reports assured by SI | 08 January 2024 08:00 | 12 January 2024 17:00 |  | 713
| 715 | 6 | 3.1.3.1.10.2 |  | Environments (SIT A) | 16 November 2022 08:00 | 05 January 2024 17:00
| 716 | 7 | 3.1.3.1.10.2.1 |  | PPs register PKI Officers | 13 November 2023 08:00 | 17 November 2023 17:00 |  | 717FF-5d
| 717 | 7 | 3.1.3.1.10.2.2 |  | PPs request PKI certificates | 20 November 2023 08:00 | 24 November 2023 17:00 |  | 718FF
| 718 | 7 | 3.1.3.1.10.2.3 |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 24 November 2023 17:00 |  | 467
| 719 | 7 | 3.1.3.1.10.2.4 |  | SI coordinate SIT Participants' SIT A environment preparation | 16 November 2022 08:00 | 24 November 2023 17:00 |  | 718SS
| 720 | 7 | 3.1.3.1.10.2.5 |  | PP submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 24 November 2023 17:00 | 24 November 2023 17:00 |  | 718FF
| 721 | 7 | 3.1.3.1.10.2.6 |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 27 November 2023 08:00 | 01 December 2023 17:00 |  | 720FF+5d
720 | 722 | 7 | 3.1.3.1.10.2.7 | Tier 3 | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 6 | 24 November 2023 17:00 | 24 November 2023 17:00 | 720 | 720SS
| 723 | 7 | 3.1.3.1.10.2.8 |  | PP SIT A environment connectivity proving | 27 November 2023 08:00 | 05 January 2024 17:00 |  | 713FF,722
| 724 | 7 | 3.1.3.1.10.2.9 |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 27 November 2023 08:00 | 22 December 2023 17:00 |  | 723SS
| 725 | 7 | 3.1.3.1.10.2.10 |  | PP deployment of MHHS solution code to SIT A environments | 25 December 2023 08:00 | 05 January 2024 17:00 |  | 740FF
| 726 | 7 | 3.1.3.1.10.2.11 |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 25 December 2023 08:00 | 05 January 2024 17:00 |  | 740FF
| 727 | 7 | 3.1.3.1.10.2.12 |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 27 November 2023 08:00 | 22 December 2023 17:00 |  | 723SS
| 728 | 7 | 3.1.3.1.10.2.13 |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 27 November 2023 08:00 | 29 December 2023 17:00 |  | 727FF+5d
| 729 | 6 | 3.1.3.1.10.3 |  | Test Data (SIT A) | 09 October 2023 08:00 | 12 January 2024 17:00
| 730 | 7 | 3.1.3.1.10.3.1 |  | SI allocate test data to SIT Participants | 09 October 2023 08:00 | 24 November 2023 17:00 |  | 722FF
| 731 | 7 | 3.1.3.1.10.3.2 |  | PP SIT A environment test data loading & verification (& data cleansing, if required) | 11 December 2023 08:00 | 05 January 2024 17:00 |  | 723SS,732SS,740FF
| 732 | 7 | 3.1.3.1.10.3.3 |  | SI coordinate SIT A environment test data loading and verification (and data cleansing, if required) | 11 December 2023 08:00 | 05 January 2024 17:00 |  | 713FF,740FF
| 733 | 7 | 3.1.3.1.10.3.4 |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 05 January 2024 17:00 | 05 January 2024 17:00 |  | 731FF
| 734 | 7 | 3.1.3.1.10.3.5 |  | SI assure evidence of SIT Participants' SIT A environment test data load and verification | 11 December 2023 08:00 | 12 January 2024 17:00 |  | 731FF+5d
| 735 | 6 | 3.1.3.1.10.4 |  | Other Preparation | 14 August 2023 08:00 | 05 January 2024 17:00
| 736 | 7 | 3.1.3.1.10.4.1 |  | Onboarding of Test Participants to Test Management Tool | 04 September 2023 08:00 | 24 November 2023 17:00 |  | 722SF
| 737 | 7 | 3.1.3.1.10.4.2 |  | Test Management Tool onboarding | 04 September 2023 08:00 | 24 November 2023 17:00 |  | 722SF
| 738 | 7 | 3.1.3.1.10.4.3 |  | Other Preparation (activities TBC) | 14 August 2023 08:00 | 05 January 2024 17:00 |  | 713FF,517
| 739 | 6 | 3.1.3.1.10.5 |  | SIT Component Integration Test Readiness Report | 18 December 2023 08:00 | 19 January 2024 17:00
| 740 | 7 | 3.1.3.1.10.5.1 |  | PP submit Test Readiness Report to Programme for assurance | 05 January 2024 17:00 | 05 January 2024 17:00 |  | 723FF
| 741 | 7 | 3.1.3.1.10.5.2 |  | SI assure Test Participants' Test Readiness Reports | 08 January 2024 08:00 | 12 January 2024 17:00 |  | 740FF+5d
| 742 | 7 | 3.1.3.1.10.5.3 |  | SI develop Overarching SIT Component Integration Test Readiness Report | 18 December 2023 08:00 | 12 January 2024 17:00 |  | 741FF
| 743 | 7 | 3.1.3.1.10.5.4 |  | Artefact review (via TMAG) and updates | 15 January 2024 08:00 | 19 January 2024 17:00 |  | 742
743 | 744 | 6 | 3.1.3.1.10.6 | Tier 2 | SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 22 January 2024 17:00 | 22 January 2024 17:00 | 743 | 743SS+6d
| 745 | 4 | 3.1.3.2 |  | SIT Functional Preparation | 31 October 2022 08:00 | 01 March 2024 17:00
| 746 | 5 | 3.1.3.2.1 |  | Test Approach & Plan | 31 October 2022 08:00 | 21 July 2023 17:00
| 747 | 6 | 3.1.3.2.1.1 |  | Develop document with SITWG | 31 October 2022 08:00 | 26 May 2023 17:00
| 748 | 6 | 3.1.3.2.1.2 |  | Draft document review with Code Bodies | 15 May 2023 08:00 | 26 May 2023 17:00 |  | 747FF
| 749 | 6 | 3.1.3.2.1.3 |  | Artefact review (via TMAG) and updates | 29 May 2023 08:00 | 14 July 2023 17:00 |  | 747
749 | 750 | 6 | 3.1.3.2.1.4 | Tier 3 | SIT Functional Testing Test Approach & Plan approved | 21 July 2023 17:00 | 21 July 2023 17:00 | 749 | 749FF+5d
| 751 | 5 | 3.1.3.2.2 |  | Test Data Approach & Plan | 31 October 2022 08:00 | 21 July 2023 17:00
| 752 | 6 | 3.1.3.2.2.1 |  | Develop document | 31 October 2022 08:00 | 26 May 2023 17:00 |  | 747SS
| 753 | 6 | 3.1.3.2.2.2 |  | Review, update & agree document internally | 05 June 2023 08:00 | 21 July 2023 17:00 |  | 752,750FF
| 754 | 5 | 3.1.3.2.3 |  | Test scenarios | 02 January 2023 08:00 | 02 June 2023 17:00
| 755 | 6 | 3.1.3.2.3.1 |  | Development of test scenarios | 02 January 2023 08:00 | 28 April 2023 17:00 |  | 747SS+45d
| 756 | 6 | 3.1.3.2.3.2 |  | Review test scenarios with SIT Working Group | 01 February 2023 08:00 | 26 May 2023 17:00 |  | 755SS+22d
756 | 757 | 6 | 3.1.3.2.3.3 | Tier 3 | SIT Functional Testing Test scenarios approved | 02 June 2023 17:00 | 02 June 2023 17:00 | 756 | 756FS+5d
| 758 | 5 | 3.1.3.2.4 |  | Test cases | 01 May 2023 08:00 | 01 September 2023 17:00
| 759 | 6 | 3.1.3.2.4.1 |  | SI Test cases | 01 May 2023 08:00 | 01 September 2023 17:00
| 760 | 7 | 3.1.3.2.4.1.1 |  | Development of Test cases | 01 May 2023 08:00 | 28 July 2023 17:00 |  | 755
| 761 | 7 | 3.1.3.2.4.1.2 |  | Review Test cases with SIT Working Group | 26 May 2023 08:00 | 25 August 2023 17:00 |  | 760SS+19d
761 | 762 | 7 | 3.1.3.2.4.1.3 | Tier 3 | SIT Functional Testing Test cases approved | 01 September 2023 17:00 | 01 September 2023 17:00 | 761 | 761FS+5d
| 763 | 5 | 3.1.3.2.5 |  | Environments (SIT-Staging) | 16 November 2022 08:00 | 09 February 2024 17:00
| 764 | 6 | 3.1.3.2.5.1 |  | PP Environments (SIT-Staging) | 16 November 2022 08:00 | 09 February 2024 17:00
| 765 | 7 | 3.1.3.2.5.1.1 |  | SIT-Staging environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 01 January 2024 17:00 |  | 467
| 766 | 7 | 3.1.3.2.5.1.2 |  | Submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 16 November 2022 08:00 | 01 January 2024 17:00 |  | 765SS
| 767 | 7 | 3.1.3.2.5.1.3 |  | SIT-Staging environment connectivity proving | 02 January 2024 08:00 | 26 January 2024 17:00 |  | 773FS-1d
| 768 | 7 | 3.1.3.2.5.1.4 |  | Deployment of MHHS solution code to SIT-Staging environments | 15 January 2024 08:00 | 26 January 2024 17:00 |  | 767FF
| 769 | 7 | 3.1.3.2.5.1.5 |  | SIT-Staging environment CIT Regression Testing | 29 January 2024 08:00 | 09 February 2024 17:00 |  | 767
| 770 | 6 | 3.1.3.2.5.2 |  | SI Environments (SIT-Staging) | 16 November 2022 08:00 | 09 February 2024 17:00
| 771 | 7 | 3.1.3.2.5.2.1 |  | Coordinate SIT Participants' SIT-Staging environment preparation | 16 November 2022 08:00 | 01 January 2024 17:00 |  | 765SS
| 772 | 7 | 3.1.3.2.5.2.2 |  | Assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 16 November 2022 08:00 | 01 January 2024 17:00 |  | 766SS
772 | 773 | 7 | 3.1.3.2.5.2.3 | Tier 3 | SIT Participants' SIT-Staging environments ready to start connectivity proving (incl certificates and security compliance) | 02 January 2024 17:00 | 02 January 2024 17:00 | 772 | 772FS+1d
| 774 | 7 | 3.1.3.2.5.2.4 |  | Coordinate SIT Participants' SIT-Staging environment connectivity proving | 02 January 2024 08:00 | 26 January 2024 17:00 |  | 767SS
| 775 | 7 | 3.1.3.2.5.2.5 |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT-Staging environments | 15 January 2024 08:00 | 26 January 2024 17:00 |  | 768SS
| 776 | 7 | 3.1.3.2.5.2.6 |  | Coordinate SIT-Staging environment Functional Regression Testing | 29 January 2024 08:00 | 09 February 2024 17:00 |  | 769SS
| 777 | 5 | 3.1.3.2.6 |  | Environments (SIT A) | 05 February 2024 08:00 | 09 February 2024 17:00
| 778 | 6 | 3.1.3.2.6.1 |  | PP Environments (SIT A) | 05 February 2024 08:00 | 09 February 2024 17:00
| 779 | 7 | 3.1.3.2.6.1.1 |  | Deployment of MHHS solution code to SIT A environments | 05 February 2024 08:00 | 09 February 2024 17:00 |  | 769FF
| 780 | 6 | 3.1.3.2.6.2 |  | SI Environments (SIT A) | 05 February 2024 08:00 | 09 February 2024 17:00
| 781 | 7 | 3.1.3.2.6.2.1 |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 05 February 2024 08:00 | 09 February 2024 17:00 |  | 779SS
| 782 | 5 | 3.1.3.2.7 |  | Other Preparation | 24 July 2023 08:00 | 09 February 2024 17:00
| 783 | 6 | 3.1.3.2.7.1 |  | SI Other Preparation | 24 July 2023 08:00 | 09 February 2024 17:00
| 784 | 7 | 3.1.3.2.7.1.1 |  | Other Preparation (activities TBC) | 24 July 2023 08:00 | 09 February 2024 17:00 |  | 750
| 785 | 6 | 3.1.3.2.7.2 |  | PP Other Preparation | 24 July 2023 08:00 | 09 February 2024 17:00
| 786 | 7 | 3.1.3.2.7.2.1 |  | Other Prearation (incl. test execution planning) | 24 July 2023 08:00 | 09 February 2024 17:00 |  | 784SS
| 787 | 5 | 3.1.3.2.8 |  | SIT Functional Test Readiness Report | 01 January 2024 08:00 | 23 February 2024 17:00
| 788 | 6 | 3.1.3.2.8.1 |  | PP SIT Functional Test Readiness Report | 01 January 2024 08:00 | 09 February 2024 17:00
| 789 | 7 | 3.1.3.2.8.1.1 |  | Develop draft Test Readiness Report and submit to Programme for assurance | 01 January 2024 08:00 | 29 January 2024 08:00 |  | 790SF
| 790 | 7 | 3.1.3.2.8.1.2 |  | Finalise Test Readiness Report and submit to Programme for assurance | 29 January 2024 08:00 | 09 February 2024 17:00 |  | 769FF
| 791 | 6 | 3.1.3.2.8.2 |  | SI SIT Functional Test Readiness Report | 01 January 2024 08:00 | 23 February 2024 17:00
| 792 | 7 | 3.1.3.2.8.2.1 |  | Assure Test Participants' Test Readiness Reports | 01 January 2024 08:00 | 16 February 2024 17:00 |  | 789SS,790FF+5d
| 793 | 7 | 3.1.3.2.8.2.2 |  | Develop Overarching SIT Functional Test Readiness Report | 22 January 2024 08:00 | 16 February 2024 17:00 |  | 792FF
| 794 | 7 | 3.1.3.2.8.2.3 |  | Artefact review (via TMAG) and updates | 19 February 2024 08:00 | 23 February 2024 17:00 |  | 793
794 | 795 | 5 | 3.1.3.2.9 | Tier 2 | SIT Functional Testing Preparation Complete | 01 March 2024 17:00 | 01 March 2024 17:00 | 794 | 794FF+5d
| 796 | 4 | 3.1.3.3 |  | SIT Migration Preparation | 16 November 2022 08:00 | 31 May 2024 17:00
| 797 | 5 | 3.1.3.3.1 |  | Test Approach & Plan | 03 April 2023 08:00 | 20 September 2023 17:00
| 798 | 6 | 3.1.3.3.1.1 |  | Develop document with SITWG | 03 April 2023 08:00 | 21 July 2023 17:00 |  | 1668
| 799 | 6 | 3.1.3.3.1.2 |  | Draft document review with Code Bodies | 10 July 2023 08:00 | 21 July 2023 17:00 |  | 798FF
| 800 | 6 | 3.1.3.3.1.3 |  | Artefact review (via TMAG) and updates | 24 July 2023 08:00 | 13 September 2023 17:00 |  | 798
800 | 801 | 6 | 3.1.3.3.1.4 | Tier 3 | SIT Migration Testing Test Approach & Plan approved | 20 September 2023 17:00 | 20 September 2023 17:00 | 800 | 800FF+5d
| 802 | 5 | 3.1.3.3.2 |  | Test Data Approach & Plan | 03 April 2023 08:00 | 13 September 2023 17:00
| 803 | 6 | 3.1.3.3.2.1 |  | Develop document | 03 April 2023 08:00 | 21 July 2023 17:00 |  | 1668
| 804 | 6 | 3.1.3.3.2.2 |  | Review, update & agree document internally | 24 July 2023 08:00 | 13 September 2023 17:00 |  | 803
| 805 | 5 | 3.1.3.3.3 |  | Test scenarios | 24 July 2023 08:00 | 17 January 2024 17:00
| 806 | 6 | 3.1.3.3.3.1 |  | Development of test scenarios | 24 July 2023 08:00 | 10 November 2023 17:00 |  | 798
| 807 | 6 | 3.1.3.3.3.2 |  | Review test scenarios with SIT Working Group | 13 November 2023 08:00 | 10 January 2024 17:00 |  | 806
807 | 808 | 6 | 3.1.3.3.3.3 | Tier 3 | SIT Migration Testing Test scenarios approved | 17 January 2024 17:00 | 17 January 2024 17:00 | 807 | 807FS+5d
| 809 | 5 | 3.1.3.3.4 |  | Test cases | 30 November 2023 08:00 | 17 April 2024 17:00
| 810 | 6 | 3.1.3.3.4.1 |  | SI Test Scripts | 30 November 2023 08:00 | 17 April 2024 17:00
| 811 | 7 | 3.1.3.3.4.1.1 |  | Development of test scripts | 30 November 2023 08:00 | 08 February 2024 17:00 |  | 806FS+13d
| 812 | 7 | 3.1.3.3.4.1.2 |  | Review test scripts with SIT Working Group | 09 February 2024 08:00 | 10 April 2024 17:00 |  | 811
812 | 813 | 7 | 3.1.3.3.4.1.3 | Tier 3 | SIT Migration Testing Test scripts approved | 17 April 2024 17:00 | 17 April 2024 17:00 | 812 | 812FS+5d
| 814 | 5 | 3.1.3.3.5 |  | Environments (SIT B) | 16 November 2022 08:00 | 10 May 2024 17:00
| 815 | 6 | 3.1.3.3.5.1 |  | PP Environments (SIT B) | 16 November 2022 08:00 | 10 May 2024 17:00
| 816 | 7 | 3.1.3.3.5.1.1 |  | SIT B environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 29 March 2024 17:00 |  | 467
| 817 | 7 | 3.1.3.3.5.1.2 |  | Submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 16 November 2022 08:00 | 29 March 2024 17:00 |  | 816SS
| 818 | 7 | 3.1.3.3.5.1.3 |  | SIT B environment connectivity proving | 01 April 2024 08:00 | 26 April 2024 17:00 |  | 824SS-1d
| 819 | 7 | 3.1.3.3.5.1.4 |  | Deployment of MHHS solution code to SIT B environments | 15 April 2024 08:00 | 26 April 2024 17:00 |  | 818FF
| 820 | 7 | 3.1.3.3.5.1.5 |  | SIT B environment Functional Regression Testing | 29 April 2024 08:00 | 10 May 2024 17:00 |  | 819
| 821 | 6 | 3.1.3.3.5.2 |  | SI Environments (SIT B) | 16 November 2022 08:00 | 10 May 2024 17:00
| 822 | 7 | 3.1.3.3.5.2.1 |  | Coordinate SIT Participants' SIT B environment preparation | 16 November 2022 08:00 | 29 March 2024 17:00 |  | 816SS
| 823 | 7 | 3.1.3.3.5.2.2 |  | Assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 16 November 2022 08:00 | 29 March 2024 17:00 |  | 817SS
823 | 824 | 7 | 3.1.3.3.5.2.3 | Tier 3 | SIT Participants' SIT B environments ready to start connectivity proving (incl certificates and security compliance) | 01 April 2024 17:00 | 01 April 2024 17:00 | 823 | 823FS+1d
| 825 | 7 | 3.1.3.3.5.2.4 |  | Coordinate SIT Participants' SIT B environment connectivity proving | 01 April 2024 08:00 | 26 April 2024 17:00 |  | 818SS
| 826 | 7 | 3.1.3.3.5.2.5 |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 15 April 2024 08:00 | 26 April 2024 17:00 |  | 819SS
| 827 | 7 | 3.1.3.3.5.2.6 |  | Coordinate SIT B environment Functional Regression Testing | 29 April 2024 08:00 | 10 May 2024 17:00 |  | 820SS
| 828 | 5 | 3.1.3.3.6 |  | Other Preparation | 21 September 2023 08:00 | 10 May 2024 17:00
| 829 | 6 | 3.1.3.3.6.1 |  | SI Other Preparation | 21 September 2023 08:00 | 10 May 2024 17:00
| 830 | 7 | 3.1.3.3.6.1.1 |  | Other Preparation (activities TBC) | 21 September 2023 08:00 | 10 May 2024 17:00 |  | 801
| 831 | 6 | 3.1.3.3.6.2 |  | PP Other Preparation | 21 September 2023 08:00 | 10 May 2024 17:00
| 832 | 7 | 3.1.3.3.6.2.1 |  | Other Preparation (incl. test execution planning) | 21 September 2023 08:00 | 10 May 2024 17:00 |  | 830SS
| 833 | 5 | 3.1.3.3.7 |  | SIT Migration Test Readiness Report | 01 April 2024 08:00 | 24 May 2024 17:00
| 834 | 6 | 3.1.3.3.7.1 |  | PP SIT Migration Test Readiness Report | 01 April 2024 08:00 | 10 May 2024 17:00
| 835 | 7 | 3.1.3.3.7.1.1 |  | Develop draft Test Readiness Report and submit to Programme for assurance | 01 April 2024 08:00 | 29 April 2024 08:00 |  | 836SF
| 836 | 7 | 3.1.3.3.7.1.2 |  | Finalise Test Readiness Report and submit to Programme for assurance | 29 April 2024 08:00 | 10 May 2024 17:00 |  | 820FF
| 837 | 6 | 3.1.3.3.7.2 |  | SI SIT Migration Test Readiness Report | 01 April 2024 08:00 | 24 May 2024 17:00
| 838 | 7 | 3.1.3.3.7.2.1 |  | Assure Test Participants' Test Readiness Reports | 01 April 2024 08:00 | 17 May 2024 17:00 |  | 835SS,836FF+5d
| 839 | 7 | 3.1.3.3.7.2.2 |  | Develop Overarching SIT Migration Test Readiness Report | 22 April 2024 08:00 | 17 May 2024 17:00 |  | 838FF
| 840 | 7 | 3.1.3.3.7.2.3 |  | Artefact review (via TMAG) and updates | 20 May 2024 08:00 | 24 May 2024 17:00 |  | 839
840 | 841 | 5 | 3.1.3.3.8 | Tier 2 | SIT Migration Testing Preparation Complete | 31 May 2024 17:00 | 31 May 2024 17:00 | 840 | 840FF+5d
| 842 | 4 | 3.1.3.4 |  | SIT Non-Functional Preparation | 31 October 2022 08:00 | 05 August 2024 17:00
| 843 | 5 | 3.1.3.4.1 |  | Test Approach & Plan | 01 May 2023 08:00 | 03 November 2023 17:00
| 844 | 6 | 3.1.3.4.1.1 |  | Develop document with SITWG | 01 May 2023 08:00 | 29 August 2023 17:00
| 845 | 6 | 3.1.3.4.1.2 |  | Draft document review with Code Bodies | 16 August 2023 08:00 | 29 August 2023 17:00 |  | 844FF
| 846 | 6 | 3.1.3.4.1.3 |  | Artefact review (via TMAG) and updates | 30 August 2023 08:00 | 27 October 2023 17:00 |  | 844
846 | 847 | 6 | 3.1.3.4.1.4 | Tier 3 | SIT Non-Functional Testing Test Approach & Plan approved | 03 November 2023 17:00 | 03 November 2023 17:00 | 846 | 846FF+5d
| 848 | 5 | 3.1.3.4.2 |  | Test Data Approach & Plan | 29 May 2023 08:00 | 03 November 2023 17:00
| 849 | 6 | 3.1.3.4.2.1 |  | Develop document | 29 May 2023 08:00 | 29 August 2023 17:00 |  | 844SS+20d
| 850 | 6 | 3.1.3.4.2.2 |  | Review, update & agree document internally | 30 August 2023 08:00 | 03 November 2023 17:00 |  | 847FF,849
| 851 | 5 | 3.1.3.4.3 |  | Test scenarios | 03 July 2023 08:00 | 01 December 2023 17:00
| 852 | 6 | 3.1.3.4.3.1 |  | Development of test scenarios | 03 July 2023 08:00 | 27 October 2023 17:00 |  | 844SS+45d
| 853 | 6 | 3.1.3.4.3.2 |  | Review test scenarios with SIT Working Group | 02 August 2023 08:00 | 24 November 2023 17:00 |  | 852SS+22d
853 | 854 | 6 | 3.1.3.4.3.3 | Tier 3 | SIT Non-Functional Testing Test scenarios approved | 01 December 2023 17:00 | 01 December 2023 17:00 | 853 | 853FS+5d
| 855 | 5 | 3.1.3.4.4 |  | Test cases | 30 October 2023 08:00 | 01 March 2024 17:00
| 856 | 6 | 3.1.3.4.4.1 |  | SI Test cases | 30 October 2023 08:00 | 01 March 2024 17:00
| 857 | 7 | 3.1.3.4.4.1.1 |  | Development of Test cases | 30 October 2023 08:00 | 26 January 2024 17:00 |  | 852
| 858 | 7 | 3.1.3.4.4.1.2 |  | Review Test cases with SIT Working Group | 24 November 2023 08:00 | 23 February 2024 17:00 |  | 857SS+19d
858 | 859 | 7 | 3.1.3.4.4.1.3 | Tier 3 | SIT Non-Functional Testing Test cases approved | 01 March 2024 17:00 | 01 March 2024 17:00 | 858 | 858FS+5d
| 860 | 5 | 3.1.3.4.5 |  | Environments (SIT B) | 30 July 2024 08:00 | 05 August 2024 17:00
| 861 | 6 | 3.1.3.4.5.1 |  | PP Environments (SIT B) | 30 July 2024 08:00 | 05 August 2024 17:00
| 862 | 7 | 3.1.3.4.5.1.1 |  | Deployment of MHHS solution code to SIT B environments | 30 July 2024 08:00 | 05 August 2024 17:00
| 863 | 6 | 3.1.3.4.5.2 |  | SI Environments (SIT B) | 30 July 2024 08:00 | 05 August 2024 17:00
| 864 | 7 | 3.1.3.4.5.2.1 |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 30 July 2024 08:00 | 05 August 2024 17:00 |  | 862SS
| 865 | 5 | 3.1.3.4.6 |  | Other Preparation | 31 October 2022 08:00 | 05 August 2024 17:00
| 866 | 6 | 3.1.3.4.6.1 |  | SI Other Preparation | 06 November 2023 08:00 | 05 August 2024 17:00
| 867 | 7 | 3.1.3.4.6.1.1 |  | Other Preparation (activities TBC) | 06 November 2023 08:00 | 05 August 2024 17:00 |  | 847
| 868 | 6 | 3.1.3.4.6.2 |  | PP Other Preparation | 31 October 2022 08:00 | 06 June 2023 17:00
| 869 | 7 | 3.1.3.4.6.2.1 |  | Other Prearation (incl. test execution planning) | 31 October 2022 08:00 | 06 June 2023 17:00
| 870 | 5 | 3.1.3.4.7 |  | SIT Non-Functional Test Readiness Report | 26 April 2023 08:00 | 20 June 2023 17:00
| 871 | 6 | 3.1.3.4.7.1 |  | PP SIT Non-Functional Test Readiness Report | 26 April 2023 08:00 | 06 June 2023 17:00
| 872 | 7 | 3.1.3.4.7.1.1 |  | Develop draft Test Readiness Report and submit to Programme for assurance | 26 April 2023 08:00 | 23 May 2023 17:00 |  | 869FF-10d
| 873 | 7 | 3.1.3.4.7.1.2 |  | Finalise Test Readiness Report and submit to Programme for assurance | 24 May 2023 08:00 | 06 June 2023 17:00 |  | 869FF,872
| 874 | 6 | 3.1.3.4.7.2 |  | SI SIT Non-Functional Test Readiness Report | 26 April 2023 08:00 | 20 June 2023 17:00
| 875 | 7 | 3.1.3.4.7.2.1 |  | Assure Test Participants' Test Readiness Reports | 26 April 2023 08:00 | 13 June 2023 17:00 |  | 872SS,873FF+5d
| 876 | 7 | 3.1.3.4.7.2.2 |  | Develop Overarching SIT Non-Functional Test Readiness Report | 17 May 2023 08:00 | 13 June 2023 17:00 |  | 875FF
| 877 | 7 | 3.1.3.4.7.2.3 |  | Artefact review (via TMAG) and updates | 14 June 2023 08:00 | 20 June 2023 17:00 |  | 876
877 | 878 | 5 | 3.1.3.4.8 | Tier 2 | SIT Non-Functional Testing Preparation Complete | 27 June 2023 17:00 | 27 June 2023 17:00 | 877 | 877FF+5d
| 879 | 4 | 3.1.3.5 |  | SIT Operational Preparation | 31 October 2022 08:00 | 09 September 2024 17:00
| 880 | 5 | 3.1.3.5.1 |  | Test Approach & Plan | 01 June 2023 08:00 | 06 December 2023 17:00
| 881 | 6 | 3.1.3.5.1.1 |  | Develop document with SITWG | 01 June 2023 08:00 | 29 September 2023 17:00
| 882 | 6 | 3.1.3.5.1.2 |  | Draft document review with Code Bodies | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 881FF
| 883 | 6 | 3.1.3.5.1.3 |  | Artefact review (via TMAG) and updates | 02 October 2023 08:00 | 29 November 2023 17:00 |  | 881
883 | 884 | 6 | 3.1.3.5.1.4 | Tier 3 | SIT Operational Testing Test Approach & Plan approved | 06 December 2023 17:00 | 06 December 2023 17:00 | 883 | 883FF+5d
| 885 | 5 | 3.1.3.5.2 |  | Test Data Approach & Plan | 29 June 2023 08:00 | 06 December 2023 17:00
| 886 | 6 | 3.1.3.5.2.1 |  | Develop document | 29 June 2023 08:00 | 29 September 2023 17:00 |  | 881SS+20d
| 887 | 6 | 3.1.3.5.2.2 |  | Review, update & agree document internally | 02 October 2023 08:00 | 06 December 2023 17:00 |  | 884FF,886
| 888 | 5 | 3.1.3.5.3 |  | Test scenarios | 03 August 2023 08:00 | 03 January 2024 17:00
| 889 | 6 | 3.1.3.5.3.1 |  | Development of test scenarios | 03 August 2023 08:00 | 29 November 2023 17:00 |  | 881SS+45d
| 890 | 6 | 3.1.3.5.3.2 |  | Review test scenarios with SIT Working Group | 04 September 2023 08:00 | 27 December 2023 17:00 |  | 889SS+22d
890 | 891 | 6 | 3.1.3.5.3.3 | Tier 3 | SIT Operational Testing Test scenarios approved | 03 January 2024 17:00 | 03 January 2024 17:00 | 890 | 890FS+5d
| 892 | 5 | 3.1.3.5.4 |  | Test cases | 30 November 2023 08:00 | 03 April 2024 17:00
| 893 | 6 | 3.1.3.5.4.1 |  | SI Test cases | 30 November 2023 08:00 | 03 April 2024 17:00
| 894 | 7 | 3.1.3.5.4.1.1 |  | Development of Test cases | 30 November 2023 08:00 | 28 February 2024 17:00 |  | 889
| 895 | 7 | 3.1.3.5.4.1.2 |  | Review Test cases with SIT Working Group | 27 December 2023 08:00 | 27 March 2024 17:00 |  | 894SS+19d
895 | 896 | 7 | 3.1.3.5.4.1.3 | Tier 3 | SIT Operational Testing Test cases approved | 03 April 2024 17:00 | 03 April 2024 17:00 | 895 | 895FS+5d
| 897 | 5 | 3.1.3.5.5 |  | Environments (SIT B) | 03 September 2024 08:00 | 09 September 2024 17:00
| 898 | 6 | 3.1.3.5.5.1 |  | PP Environments (SIT B) | 03 September 2024 08:00 | 09 September 2024 17:00
| 899 | 7 | 3.1.3.5.5.1.1 |  | Deployment of MHHS solution code to SIT B environments | 03 September 2024 08:00 | 09 September 2024 17:00
| 900 | 6 | 3.1.3.5.5.2 |  | SI Environments (SIT B) | 03 September 2024 08:00 | 09 September 2024 17:00
| 901 | 7 | 3.1.3.5.5.2.1 |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 03 September 2024 08:00 | 09 September 2024 17:00 |  | 899SS
| 902 | 5 | 3.1.3.5.6 |  | Other Preparation | 31 October 2022 08:00 | 09 September 2024 17:00
| 903 | 6 | 3.1.3.5.6.1 |  | SI Other Preparation | 07 December 2023 08:00 | 09 September 2024 17:00
| 904 | 7 | 3.1.3.5.6.1.1 |  | Other Preparation (activities TBC) | 07 December 2023 08:00 | 09 September 2024 17:00 |  | 884
| 905 | 6 | 3.1.3.5.6.2 |  | PP Other Preparation | 31 October 2022 08:00 | 08 June 2023 17:00
| 906 | 7 | 3.1.3.5.6.2.1 |  | Other Prearation (incl. test execution planning) | 31 October 2022 08:00 | 08 June 2023 17:00
| 907 | 5 | 3.1.3.5.7 |  | SIT Operational Test Readiness Report | 28 April 2023 08:00 | 22 June 2023 17:00
| 908 | 6 | 3.1.3.5.7.1 |  | PP SIT Operational Test Readiness Report | 28 April 2023 08:00 | 08 June 2023 17:00
| 909 | 7 | 3.1.3.5.7.1.1 |  | Develop draft Test Readiness Report and submit to Programme for assurance | 28 April 2023 08:00 | 25 May 2023 17:00 |  | 906FF-10d
| 910 | 7 | 3.1.3.5.7.1.2 |  | Finalise Test Readiness Report and submit to Programme for assurance | 26 May 2023 08:00 | 08 June 2023 17:00 |  | 906FF,909
| 911 | 6 | 3.1.3.5.7.2 |  | SI SIT Operational Test Readiness Report | 28 April 2023 08:00 | 22 June 2023 17:00
| 912 | 7 | 3.1.3.5.7.2.1 |  | Assure Test Participants' Test Readiness Reports | 28 April 2023 08:00 | 15 June 2023 17:00 |  | 909SS,910FF+5d
| 913 | 7 | 3.1.3.5.7.2.2 |  | Develop Overarching SIT Non-Functional Test Readiness Report | 19 May 2023 08:00 | 15 June 2023 17:00 |  | 912FF
| 914 | 7 | 3.1.3.5.7.2.3 |  | Artefact review (via TMAG) and updates | 16 June 2023 08:00 | 22 June 2023 17:00 |  | 913
914 | 915 | 5 | 3.1.3.5.8 | Tier 2 | SIT Operational Testing Preparation Complete | 29 June 2023 17:00 | 29 June 2023 17:00 | 914 | 914FF+5d
| 916 | 3 | 3.1.4 |  | Data Protection Impact Assessment (DPIA) | 01 June 2023 08:00 | 14 July 2023 17:00
| 917 | 4 | 3.1.4.1 |  | Conduct DPIA on Overall Test Data Approach | 01 June 2023 08:00 | 30 June 2023 17:00 |  | 481SS+15d
| 918 | 4 | 3.1.4.2 |  | Revise Overarching Test Data Approach & plan for DPIA (if required), including engagement with DWG | 03 July 2023 08:00 | 13 July 2023 17:00 |  | 917
| 919 | 4 | 3.1.4.3 |  | Review (internal), update and approve revised Overarching Test Data Approach & Plan (if required) | 14 July 2023 08:00 | 14 July 2023 17:00 |  | 918
| 920 | 3 | 3.1.5 |  | SIT Stub Specification and Delivery | 03 April 2023 08:00 | 31 January 2024 17:00
| 921 | 4 | 3.1.5.1 |  | Data Service Emulators | 03 April 2023 08:00 | 31 January 2024 17:00
| 922 | 5 | 3.1.5.1.1 |  | Specify | 03 April 2023 08:00 | 26 May 2023 17:00
| 923 | 5 | 3.1.5.1.2 |  | Build & Test | 29 May 2023 08:00 | 27 October 2023 17:00 |  | 922
| 924 | 5 | 3.1.5.1.3 |  | UAT | 30 October 2023 08:00 | 01 December 2023 17:00 |  | 923
| 925 | 5 | 3.1.5.1.4 |  | Beta test | 04 December 2023 08:00 | 29 December 2023 17:00 |  | 924
| 926 | 5 | 3.1.5.1.5 |  | Prepare for release | 01 January 2024 08:00 | 26 January 2024 17:00 |  | 925
926 | 927 | 5 | 3.1.5.1.6 | Tier 3 | Data Service emulators released | 31 January 2024 17:00 | 31 January 2024 17:00 | 926 | 926FS+3d
| 928 | 3 | 3.1.6 |  | SIT Participation | 31 October 2022 08:00 | 23 May 2023 08:00
| 929 | 4 | 3.1.6.1 |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 31 October 2022 08:00 | 31 January 2023 17:00 |  | 32FF
| 930 | 4 | 3.1.6.2 |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 01 February 2023 08:00 | 14 February 2023 17:00 |  | 929,32
930 | 931 | 4 | 3.1.6.3 | Tier 2 | SIT Participant Volunteers Identified | 14 February 2023 17:00 | 14 February 2023 17:00 | 930 | 930FF
| 932 | 4 | 3.1.6.4 |  | Engagement with SIT volunteers | 31 October 2022 08:00 | 27 December 2022 17:00
| 933 | 4 | 3.1.6.5 | Tier 2 | SIT Participants Agreed | 23 May 2023 08:00 | 23 May 2023 08:00 | 0 | 932,538FS-74d
| 934 | 3 | 3.1.7 |  | Production Data Cut & Data Obfuscation | 04 April 2023 08:00 | 20 October 2023 17:00
| 935 | 4 | 3.1.7.1 |  | SI Data Cut Preparation | 04 April 2023 08:00 | 31 July 2023 17:00
| 936 | 5 | 3.1.7.1.1 |  | SI Data Cut Planning activities (incl pre-cut and post-cut cleansing and population approach) | 04 April 2023 08:00 | 19 June 2023 17:00
| 937 | 5 | 3.1.7.1.2 |  | Set up SI database and transmission structure | 19 June 2023 08:00 | 31 July 2023 17:00
| 938 | 5 | 3.1.7.1.3 |  | Develop software to load data onto SI database | 19 June 2023 08:00 | 31 July 2023 17:00 |  | 937SS
| 939 | 5 | 3.1.7.1.4 |  | Provisions available for data storage in place | 31 July 2023 08:00 | 31 July 2023 17:00 |  | 937FF
| 940 | 5 | 3.1.7.1.5 |  | Mechanism for transfer of data in place | 31 July 2023 08:00 | 31 July 2023 17:00 |  | 937FF
| 941 | 4 | 3.1.7.2 |  | PP Data Cut Preparation | 04 April 2023 08:00 | 31 July 2023 17:00
| 942 | 5 | 3.1.7.2.1 |  | Implement system changes for new/changed data items | 04 April 2023 08:00 | 03 July 2023 17:00 |  | 936SS
| 943 | 5 | 3.1.7.2.2 |  | Develop software to load data onto PP database | 19 June 2023 08:00 | 31 July 2023 17:00 |  | 937SS
| 944 | 4 | 3.1.7.3 |  | Production Data Cut | 23 June 2023 08:00 | 13 October 2023 17:00
948 | 945 | 5 | 3.1.7.3.1 | Tier 3 | Notification of Production Data Cut issued to relevant participants | 23 June 2023 08:00 | 23 June 2023 08:00 | 948 | 948FS-45d
| 946 | 5 | 3.1.7.3.2 |  | Coordinate relevant participants taking data cut from production systems | 23 June 2023 08:00 | 17 August 2023 17:00 |  | 945
948 | 947 | 5 | 3.1.7.3.3 | Tier 3 | Production data cut GONG decision | 18 August 2023 08:00 | 18 August 2023 08:00 | 948 | 948FS-5d
| 948 | 5 | 3.1.7.3.4 |  | Relevant participants take data cut from production systems | 24 August 2023 08:00 | 24 August 2023 17:00
| 949 | 5 | 3.1.7.3.5 |  | Cleanse data post cut, review test data quality and develop plan to address quality issues (if required) | 25 August 2023 08:00 | 22 September 2023 17:00 |  | 948
| 950 | 5 | 3.1.7.3.6 |  | Load data sets and check data integrity | 25 September 2023 08:00 | 13 October 2023 17:00 |  | 949
948 | 951 | 5 | 3.1.7.3.7 | Tier 2 | Data cut from relevant participants' production systems completed | 24 August 2023 17:00 | 24 August 2023 17:00 | 948 | 948FF
| 952 | 4 | 3.1.7.4 |  | Data Obfuscation | 21 July 2023 08:00 | 20 October 2023 17:00
| 953 | 5 | 3.1.7.4.1 |  | Develop software for data obfuscation and quality checks (if required) | 21 July 2023 08:00 | 18 August 2023 08:00 |  | 918,947FF
| 954 | 5 | 3.1.7.4.2 |  | Apply data obfuscation policy | 18 August 2023 08:00 | 20 October 2023 17:00 |  | 953
| 955 | 2 | 3.2 |  | SIT Execution | 30 October 2023 08:00 | 25 April 2025 17:00
| 956 | 3 | 3.2.1 | Tier 1 | System Integration Testing Start (M9) | 30 October 2023 08:00 | 30 October 2023 08:00 | 0 | 600FS+5d,636FS+5d,564FS+5d,672FS+5d,708FS+5d,744FS+5d
| 957 | 3 | 3.2.2 |  | SIT Component Integration Testing | 30 October 2023 08:00 | 08 March 2024 17:00
| 958 | 4 | 3.2.2.1 |  | SIT Component Integration Testing Start | 30 October 2023 08:00 | 30 October 2023 08:00 |  | 956
564 | 959 | 4 | 3.2.2.2 | Tier 3 | Component Integration Testing Interval 1 Start | 30 October 2023 17:00 | 30 October 2023 17:00 | 564 | 564SS+5d
| 960 | 4 | 3.2.2.3 | Tier 3 | Component Integration Testing Interval 2 Start | 13th November 2023 | 13th November 2023 | 600 | 600SS+5d,636SS+5d,564SS+5d,672SS+5d,708SS+5d,744SS+5d
| 961 | 4 | 3.2.2.4 | Tier 3 | Component Integration Testing Interval 3 Start | 27th November 2023 | 27th November 2023 | 636 | 636SS+5d,672SS+5d,708SS+5d,744SS+5d
| 962 | 4 | 3.2.2.5 | Tier 3 | Component Integration Testing Interval 4 Start | 11th December 2023 | 11th December 2023 | 672 | 672SS+5d,708SS+5d,744SS+5d
| 963 | 4 | 3.2.2.6 | Tier 3 | Component Integration Testing Interval 5 Start | 15th January 2023 | 15th January 2023 | 708 | 708SS+5d,744SS+5d
| 964 | 4 | 3.2.2.7 | Tier 3 | Component Integration Testing Interval 6 Start | 29 January 2024 08:00 | 29 January 2024 08:00 | 744
| 965 | 4 | 3.2.2.8 |  | SIT Component Integration Testing Execution | 30 October 2023 08:00 | 23 February 2024 17:00 |  | 959SS
965 | 966 | 4 | 3.2.2.9 | Tier 3 | SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 23 February 2024 17:00 | 23 February 2024 17:00 | 965 | 965FF
| 967 | 4 | 3.2.2.10 |  | Assurance of PPs Test Completion Reports | 22 January 2024 08:00 | 01 March 2024 17:00 |  | 966FF+5d
| 968 | 4 | 3.2.2.11 |  | SIT CI Test Completion Report | 07 February 2024 08:00 | 01 March 2024 17:00
| 969 | 5 | 3.2.2.11.1 |  | Develop document | 07 February 2024 08:00 | 23 February 2024 17:00 |  | 966FF
| 970 | 5 | 3.2.2.11.2 |  | Review & agree document | 26 February 2024 08:00 | 01 March 2024 17:00 |  | 969,967FF
970 | 971 | 4 | 3.2.2.12 | Tier 2 | SIT Component Integration Testing Test Completion Report Approved | 08 March 2024 17:00 | 08 March 2024 17:00 | 970 | 970FS+5d
| 972 | 3 | 3.2.3 |  | SIT - Minimum Viable Cohort (MVC) | 11 March 2024 08:00 | 07 February 2025 17:00
| 973 | 4 | 3.2.3.1 |  | SIT Functional Testing (MVC) | 11 March 2024 08:00 | 17 January 2025 17:00
| 974 | 5 | 3.2.3.1.1 | Tier 3 | SIT Functional Testing Start | 11 March 2024 17:00 | 11 March 2024 17:00 | 0 | 971FS+1d,795FS+5d
| 975 | 5 | 3.2.3.1.2 |  | SIT Functional Testing Execution (Minimum Viable Cohort) | 11 March 2024 08:00 | 17 January 2025 17:00
| 976 | 6 | 3.2.3.1.2.1 |  | Cycle 1 (Full Cycle) | 11 March 2024 08:00 | 12 July 2024 17:00
| 977 | 7 | 3.2.3.1.2.1.1 |  | Test Execution | 11 March 2024 08:00 | 28 June 2024 17:00 |  | 974SS-1d
| 978 | 7 | 3.2.3.1.2.1.2 |  | Defect resolution, assurance, review, data & environments maintenance | 01 July 2024 08:00 | 12 July 2024 17:00 |  | 977
| 979 | 6 | 3.2.3.1.2.2 |  | SIT Functional Testing progress risk-assessment | 15 July 2024 08:00 | 09 August 2024 17:00
| 980 | 7 | 3.2.3.1.2.2.1 |  | Risk-assessment of SIT Functional progress to assess whether Qualification Testing Execution can start early | 15 July 2024 08:00 | 02 August 2024 17:00 |  | 978
980 | 981 | 7 | 3.2.3.1.2.2.2 | Tier 3 | TMAG decision on early Qualification Testing Execution start | 09 August 2024 17:00 | 09 August 2024 17:00 | 980 | 980FS+5d
| 982 | 6 | 3.2.3.1.2.3 |  | Cycle 2 (Defect retests and targeted regression testing) | 15 July 2024 08:00 | 20 September 2024 17:00
| 983 | 7 | 3.2.3.1.2.3.1 |  | Test Execution | 15 July 2024 08:00 | 06 September 2024 17:00 |  | 978
| 984 | 7 | 3.2.3.1.2.3.2 |  | Defect resolution, assurance, review, data & environments maintenance | 09 September 2024 08:00 | 20 September 2024 17:00 |  | 983
| 985 | 6 | 3.2.3.1.2.4 |  | SIT Functional Testing back-up progress risk-assessment | 23 September 2024 08:00 | 18 October 2024 17:00
| 986 | 7 | 3.2.3.1.2.4.1 |  | Back-up risk-assessment of SIT Functional progress to assess whether Qualification Execution can start early | 23 September 2024 08:00 | 11 October 2024 17:00 |  | 984
986 | 987 | 7 | 3.2.3.1.2.4.2 | Tier 3 | Back-up TMAG decision on early Qualification Testing Execution start | 18 October 2024 17:00 | 18 October 2024 17:00 | 986 | 986FS+5d
| 988 | 6 | 3.2.3.1.2.5 |  | Cycle 3 (Defect retests and targeted regression testing) | 23 September 2024 08:00 | 01 November 2024 17:00
| 989 | 7 | 3.2.3.1.2.5.1 |  | Test Execution | 23 September 2024 08:00 | 18 October 2024 17:00 |  | 984
| 990 | 7 | 3.2.3.1.2.5.2 |  | Defect resolution, assurance, review, data & environments maintenance | 21 October 2024 08:00 | 01 November 2024 17:00 |  | 989
990 | 991 | 6 | 3.2.3.1.2.6 | Tier 3 | Core Systems Code Freeze | 01 November 2024 17:00 | 01 November 2024 17:00 | 990 | 990FF
| 992 | 6 | 3.2.3.1.2.7 |  | Regression Testing (code freeze) | 04 November 2024 08:00 | 03 January 2025 17:00 |  | 990
992 | 993 | 6 | 3.2.3.1.2.8 | Tier 3 | SIT Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 03 January 2025 17:00 | 03 January 2025 17:00 | 992 | 992FF
| 994 | 6 | 3.2.3.1.2.9 |  | Assurance of PPs Test Completion Reports | 02 December 2024 08:00 | 10 January 2025 17:00 |  | 993FF+5d
| 995 | 6 | 3.2.3.1.2.10 |  | SIT Functional Test Completion Report (Minimum Viable Cohort) | 16 December 2024 08:00 | 10 January 2025 17:00
| 996 | 7 | 3.2.3.1.2.10.1 |  | Develop document | 16 December 2024 08:00 | 03 January 2025 17:00 |  | 993FF
| 997 | 7 | 3.2.3.1.2.10.2 |  | Review & agree document | 06 January 2025 08:00 | 10 January 2025 17:00 |  | 996,994FF
997 | 998 | 6 | 3.2.3.1.2.11 | Tier 2 | SIT Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | 17 January 2025 17:00 | 17 January 2025 17:00 | 997 | 997FF+5d
| 999 | 4 | 3.2.3.2 |  | SIT Migration Testing (MVC) | 10 June 2024 08:00 | 18 October 2024 17:00
841 | 1000 | 5 | 3.2.3.2.1 | Tier 3 | SIT Migration Testing Start | 10 June 2024 08:00 | 10 June 2024 08:00 | 841 | 841FS+5d
| 1001 | 5 | 3.2.3.2.2 |  | SIT Migration Testing Execution (Minimum Viable Cohort) | 10 June 2024 08:00 | 04 October 2024 17:00 |  | 1000SS
100 | 1002 | 5 | 3.2.3.2.3 | Tier 3 | SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 04 October 2024 17:00 | 04 October 2024 17:00 | 100 | 1001FF
| 1003 | 5 | 3.2.3.2.4 |  | Assurance of PPs Test Completion Reports | 02 September 2024 08:00 | 11 October 2024 17:00 |  | 1002FF+5d
| 1004 | 5 | 3.2.3.2.5 |  | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) | 16 September 2024 08:00 | 11 October 2024 17:00
| 1005 | 6 | 3.2.3.2.5.1 |  | Develop document | 16 September 2024 08:00 | 04 October 2024 17:00 |  | 1002FF
| 1006 | 6 | 3.2.3.2.5.2 |  | Review & agree document | 07 October 2024 08:00 | 11 October 2024 17:00 |  | 1005,1003FF
100 | 1007 | 5 | 3.2.3.2.6 | Tier 2 | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) Approved | 18 October 2024 17:00 | 18 October 2024 17:00 | 100 | 1006FF+5d
| 1008 | 4 | 3.2.3.3 |  | SIT Non-Functional Testing (MVC) | 02 September 2024 08:00 | 17 January 2025 17:00
| 1009 | 5 | 3.2.3.3.1 | Tier 3 | SIT Non-Functional Testing Start | 02 September 2024 08:00 | 02 September 2024 08:00 | 0 | 878FS+5d,983FS+5d
| 1010 | 5 | 3.2.3.3.2 |  | SIT Non-Functional Testing Execution (Minimum Viable Cohort) | 02 September 2024 08:00 | 03 January 2025 17:00 |  | 1009SS
1010 | 1011 | 5 | 3.2.3.3.3 | Tier 3 | SIT Non-Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 03 January 2025 17:00 | 03 January 2025 17:00 | 1010 | 1010FF
| 1012 | 5 | 3.2.3.3.4 |  | Assurance of PPs Test Completion Reports | 02 December 2024 08:00 | 10 January 2025 17:00 |  | 1011FF+5d
| 1013 | 5 | 3.2.3.3.5 |  | SIT Non-Functional Testing Test Completion Report (Minimum Viable Cohort) | 16 December 2024 08:00 | 10 January 2025 17:00
| 1014 | 6 | 3.2.3.3.5.1 |  | Develop document | 16 December 2024 08:00 | 03 January 2025 17:00 |  | 1011FF
| 1015 | 6 | 3.2.3.3.5.2 |  | Review & agree document | 06 January 2025 08:00 | 10 January 2025 17:00 |  | 1014,1012FF
| 1016 | 5 | 3.2.3.3.6 | Tier 2 | SIT Non-Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | 17 January 2025 17:00 | 17 January 2025 17:00 | 1015 | 1015FF+5d
| 1017 | 4 | 3.2.3.4 |  | SIT Operational Testing (MVC) | 07 October 2024 08:00 | 07 February 2025 17:00
| 1018 | 5 | 3.2.3.4.1 | Tier 3 | SIT Operational Testing Start | 07 October 2024 08:00 | 07 October 2024 08:00 | 0 | 915FS+5d,989
| 1019 | 5 | 3.2.3.4.2 |  | SIT Operational Testing Execution (Minimum Viable Cohort) | 07 October 2024 08:00 | 24 January 2025 17:00 |  | 1018SS
1019 | 1020 | 5 | 3.2.3.4.3 | Tier 3 | SIT Operational Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 24 January 2025 17:00 | 24 January 2025 17:00 | 1019 | 1019FF
| 1021 | 5 | 3.2.3.4.4 |  | Assurance of PPs Test Completion Reports | 23 December 2024 08:00 | 31 January 2025 17:00 |  | 1020FF+5d
| 1022 | 5 | 3.2.3.4.5 |  | SIT Operational Testing Test Completion Report (Minimum Viable Cohort) | 06 January 2025 08:00 | 31 January 2025 17:00
| 1023 | 6 | 3.2.3.4.5.1 |  | Develop document | 06 January 2025 08:00 | 24 January 2025 17:00 |  | 1020FF
| 1024 | 6 | 3.2.3.4.5.2 |  | Review & agree document | 27 January 2025 08:00 | 31 January 2025 17:00 |  | 1023,1021FF
1024 | 1025 | 5 | 3.2.3.4.6 | Tier 2 | SIT Operational Testing Test Completion Report (Minimum Viable Cohort) Approved | 07 February 2025 17:00 | 07 February 2025 17:00 | 1024 | 1024FF+5d
| 1026 | 4 | 3.2.3.5 |  | SIT MVC Test Exit Report | 06 January 2025 08:00 | 31 January 2025 17:00
| 1027 | 5 | 3.2.3.5.1 |  | Develop document | 06 January 2025 08:00 | 24 January 2025 17:00 |  | 1023FF
| 1028 | 5 | 3.2.3.5.2 |  | Review & agree document | 27 January 2025 08:00 | 31 January 2025 17:00 |  | 1027
| 1029 | 4 | 3.2.3.6 | Tier 1 | SIT Minimum Viable Cohort Complete (SIT Minimum Viable Cohort Test Exit Report Approved) | 07 February 2025 08:00 | 07 February 2025 08:00 | 0 | 1028FS+5d,971,998,1007,1016,1025
| 1030 | 3 | 3.2.4 |  | SIT - Other Participants | 11 March 2024 08:00 | 25 April 2025 17:00
| 1031 | 4 | 3.2.4.1 |  | SIT Functional Testing (Other Participants) | 11 March 2024 08:00 | 25 April 2025 17:00
| 1032 | 5 | 3.2.4.1.1 |  | SIT Functional Testing Execution (Other Participants) | 11 March 2024 08:00 | 04 April 2025 17:00
| 1033 | 6 | 3.2.4.1.1.1 |  | Cycle 1 (Full Cycle) | 11 March 2024 08:00 | 12 July 2024 17:00
| 1034 | 7 | 3.2.4.1.1.1.1 |  | Test Execution | 11 March 2024 08:00 | 28 June 2024 17:00 |  | 977SS
| 1035 | 7 | 3.2.4.1.1.1.2 |  | Defect resolution, assurance, review, data & environments maintenance | 01 July 2024 08:00 | 12 July 2024 17:00 |  | 1034
| 1036 | 6 | 3.2.4.1.1.2 |  | Cycle 2 (Defect retests and targeted regression testing) | 15 July 2024 08:00 | 20 September 2024 17:00
| 1037 | 7 | 3.2.4.1.1.2.1 |  | Test Execution | 15 July 2024 08:00 | 06 September 2024 17:00 |  | 1035
| 1038 | 7 | 3.2.4.1.1.2.2 |  | Defect resolution, assurance, review, data & environments maintenance | 09 September 2024 08:00 | 20 September 2024 17:00 |  | 1037
| 1039 | 6 | 3.2.4.1.1.3 |  | Cycle 3 (Defect retests and targeted regression testing) | 23 September 2024 08:00 | 01 November 2024 17:00
| 1040 | 7 | 3.2.4.1.1.3.1 |  | Test Execution | 23 September 2024 08:00 | 18 October 2024 17:00 |  | 1038
| 1041 | 7 | 3.2.4.1.1.3.2 |  | Defect resolution, assurance, review, data & environments maintenance | 21 October 2024 08:00 | 01 November 2024 17:00 |  | 1040
| 1042 | 6 | 3.2.4.1.1.4 |  | Regression Testing (code freeze) | 04 November 2024 08:00 | 03 January 2025 17:00 |  | 1041
| 1043 | 6 | 3.2.4.1.1.5 |  | SIT Other PPs continued support | 06 January 2025 08:00 | 04 April 2025 17:00 |  | 1042
1043 | 1044 | 5 | 3.2.4.1.2 | Tier 3 | SIT Functional Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1043 | 1043FF
| 1045 | 5 | 3.2.4.1.3 |  | Assurance of PPs Test Completion Reports | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1044FS+5d
| 1046 | 5 | 3.2.4.1.4 |  | SIT Functional Testing Test Completion Report (Other Participants) | 17 March 2025 08:00 | 18 April 2025 17:00
| 1047 | 6 | 3.2.4.1.4.1 |  | Develop document | 17 March 2025 08:00 | 04 April 2025 17:00 |  | 1044FF
| 1048 | 6 | 3.2.4.1.4.2 |  | Review & agree document | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1047,1045FF
1048 | 1049 | 5 | 3.2.4.1.5 | Tier 3 | SIT Functional Testing Test Completion Report (Other Participants) Approved | 25 April 2025 17:00 | 25 April 2025 17:00 | 1048 | 1048FF+5d
| 1050 | 4 | 3.2.4.2 |  | SIT Migration Testing (Other Participants) | 10 June 2024 08:00 | 25 April 2025 17:00
| 1051 | 5 | 3.2.4.2.1 |  | SIT Migration Testing Execution (Other Participants) | 10 June 2024 08:00 | 04 April 2025 17:00 |  | 1000SS
1051 | 1052 | 5 | 3.2.4.2.2 | Tier 3 | SIT Migration Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1051 | 1051FF
| 1053 | 5 | 3.2.4.2.3 |  | Assurance of PPs Test Completion Reports | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1052FS+5d
| 1054 | 5 | 3.2.4.2.4 |  | SIT Migration Testing Test Completion Report (Other Participants) | 17 March 2025 08:00 | 18 April 2025 17:00
| 1055 | 6 | 3.2.4.2.4.1 |  | Develop document | 17 March 2025 08:00 | 04 April 2025 17:00 |  | 1052FF
| 1056 | 6 | 3.2.4.2.4.2 |  | Review & agree document | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1055,1053FF
1056 | 1057 | 5 | 3.2.4.2.5 | Tier 3 | SIT Migration Testing Test Completion Report (Other Participants) Approved | 25 April 2025 17:00 | 25 April 2025 17:00 | 1056 | 1056FF+5d
| 1058 | 4 | 3.2.4.3 |  | SIT Non-Functional Testing (Other Participants) | 02 September 2024 08:00 | 25 April 2025 17:00
| 1059 | 5 | 3.2.4.3.1 |  | SIT Non-Functional Testing Execution (Other Participants) | 02 September 2024 08:00 | 04 April 2025 17:00 |  | 1009SS
1059 | 1060 | 5 | 3.2.4.3.2 | Tier 3 | SIT Non-Functional Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1059 | 1059FF
| 1061 | 5 | 3.2.4.3.3 |  | Assurance of PPs Test Completion Reports | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1060FS+5d
| 1062 | 5 | 3.2.4.3.4 |  | SIT Non-Functional Testing Test Completion Report (Other Participants) | 17 March 2025 08:00 | 18 April 2025 17:00
| 1063 | 6 | 3.2.4.3.4.1 |  | Develop document | 17 March 2025 08:00 | 04 April 2025 17:00 |  | 1060FF
| 1064 | 6 | 3.2.4.3.4.2 |  | Review & agree document | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1063,1061FF
1064 | 1065 | 5 | 3.2.4.3.5 | Tier 3 | SIT Non-Functional Testing Test Completion Report (Other Participants) Approved | 25 April 2025 17:00 | 25 April 2025 17:00 | 1064 | 1064FF+5d
| 1066 | 4 | 3.2.4.4 |  | SIT Operational Testing (Other Participants) | 07 October 2024 08:00 | 25 April 2025 17:00
| 1067 | 5 | 3.2.4.4.1 |  | SIT Operational Testing Execution (Other Participants) | 07 October 2024 08:00 | 04 April 2025 17:00 |  | 1018SS
1067 | 1068 | 5 | 3.2.4.4.2 | Tier 3 | SIT Operational Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1067 | 1067FF
| 1069 | 5 | 3.2.4.4.3 |  | Assurance of PPs Test Completion Reports | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1068FS+5d
| 1070 | 5 | 3.2.4.4.4 |  | SIT Operational Testing Test Completion Report (Other Participants) | 17 March 2025 08:00 | 18 April 2025 17:00
| 1071 | 6 | 3.2.4.4.4.1 |  | Develop document | 17 March 2025 08:00 | 04 April 2025 17:00 |  | 1068FF
| 1072 | 6 | 3.2.4.4.4.2 |  | Review & agree document | 14 April 2025 08:00 | 18 April 2025 17:00 |  | 1071,1069FF
1072 | 1073 | 5 | 3.2.4.4.5 | Tier 3 | SIT Operational Testing Test Completion Report (Other Participants) Approved | 25 April 2025 17:00 | 25 April 2025 17:00 | 1072 | 1072FF+5d
| 1074 | 4 | 3.2.4.5 |  | SIT Other Participants Test Exit Report | 17 March 2025 08:00 | 11 April 2025 17:00
| 1075 | 5 | 3.2.4.5.1 |  | Develop document | 17 March 2025 08:00 | 04 April 2025 17:00 |  | 1071FF
| 1076 | 5 | 3.2.4.5.2 |  | Review & agree document | 07 April 2025 08:00 | 11 April 2025 17:00 |  | 1075
| 1077 | 4 | 3.2.4.6 | Tier 3 | SIT - Other Participants Complete | 21 April 2025 08:00 | 21 April 2025 08:00 | 0 | 1076FS+5d,1049,1057,1065,1073
| 1078 | 2 | 3.3 |  | MHHS Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) | 29 January 2024 08:00 | 21 March 2025 17:00
| 1079 | 3 | 3.3.1 |  | MHHS Qualification Testing for Non-SIT LDSOs Preparation | 29 January 2024 08:00 | 05 July 2024 17:00
| 1080 | 4 | 3.3.1.1 |  | SI Tranche for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Preparation | 29 January 2024 08:00 | 05 July 2024 17:00
1110 | 1081 | 5 | 3.3.1.1.1 | Tier 3 | Confirm Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Participants | 29 January 2024 08:00 | 29 January 2024 08:00 | 1110 | 1110FS-6mo
| 1082 | 5 | 3.3.1.1.2 |  | Test execution schedule | 29 January 2024 08:00 | 26 April 2024 17:00
| 1083 | 6 | 3.3.1.1.2.1 |  | Develop document | 29 January 2024 08:00 | 22 March 2024 17:00 |  | 1081
| 1084 | 6 | 3.3.1.1.2.2 |  | Review & agree document | 25 March 2024 08:00 | 19 April 2024 17:00 |  | 1083
1084 | 1085 | 6 | 3.3.1.1.2.3 | Tier 3 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test execution schedule approved | 26 April 2024 17:00 | 26 April 2024 17:00 | 1084 | 1084FS+5d
| 1086 | 5 | 3.3.1.1.3 |  | Environments (environments TBC) | 29 January 2024 08:00 | 05 July 2024 17:00
| 1087 | 6 | 3.3.1.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 29 January 2024 08:00 | 19 April 2024 17:00 |  | 1081
| 1088 | 6 | 3.3.1.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' environments (TBC) | 08 April 2024 08:00 | 19 April 2024 17:00 |  | 1087FF
1088 | 1089 | 6 | 3.3.1.1.3.3 | Tier 3 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) environments (TBC) ready to start connectivity proving (incl certificates and security compliance) | 26 April 2024 17:00 | 26 April 2024 17:00 | 1088 | 1088FS+5d
| 1090 | 6 | 3.3.1.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 29 April 2024 08:00 | 05 July 2024 17:00 |  | 1089
| 1091 | 6 | 3.3.1.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 29 April 2024 08:00 | 05 July 2024 17:00 |  | 1090SS
| 1092 | 5 | 3.3.1.1.4 |  | Test Data | 26 April 2024 17:00 | 26 April 2024 17:00
1089 | 1093 | 6 | 3.3.1.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 1 Participants) | 26 April 2024 17:00 | 26 April 2024 17:00 | 1089 | 1089
| 1094 | 5 | 3.3.1.1.5 |  | Other Preparation | 29 January 2024 08:00 | 05 July 2024 17:00
| 1095 | 6 | 3.3.1.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 29 January 2024 08:00 | 05 July 2024 17:00 |  | 1081
| 1096 | 6 | 3.3.1.1.5.2 |  | Other Preparation (activities TBC) | 29 January 2024 08:00 | 05 July 2024 17:00 |  | 1081
1090 | 1097 | 5 | 3.3.1.1.6 | Tier 3 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness confirmed | 05 July 2024 17:00 | 05 July 2024 17:00 | 1090 | 1090,1095,1096
| 1098 | 4 | 3.3.1.2 |  | PP for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Preparation | 29 January 2024 08:00 | 05 July 2024 17:00
1110 | 1099 | 5 | 3.3.1.2.1 | Tier 3 | Confirm Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Participants | 29 January 2024 08:00 | 29 January 2024 08:00 | 1110 | 1110FS-6mo
| 1100 | 5 | 3.3.1.2.2 |  | Environments | 29 January 2024 08:00 | 05 July 2024 17:00
| 1101 | 6 | 3.3.1.2.2.1 |  | Environment preparation (environment TBC) | 29 January 2024 08:00 | 19 April 2024 17:00 |  | 1099
| 1102 | 6 | 3.3.1.2.2.2 |  | Deployment of MHHS solution code to environments (TBC) | 08 April 2024 08:00 | 19 April 2024 17:00 |  | 1101FF
1102 | 1103 | 6 | 3.3.1.2.2.3 | Tier 3 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) environments (TBC) ready to start connectivity proving (incl certificates and security compliance) | 26 April 2024 17:00 | 26 April 2024 17:00 | 1102 | 1102FS+5d
| 1104 | 6 | 3.3.1.2.2.4 |  | Environment (TBC) connectivity proving | 29 April 2024 08:00 | 05 July 2024 17:00 |  | 1103
| 1105 | 6 | 3.3.1.2.2.5 |  | Submit evidence of environment (TBC) connectivity proving to Programme for assurance | 29 April 2024 08:00 | 05 July 2024 17:00 |  | 1104SS
| 1106 | 5 | 3.3.1.2.3 |  | Other Preparation | 29 January 2024 08:00 | 05 July 2024 17:00
| 1107 | 6 | 3.3.1.2.3.1 |  | Other Preparation (incl. test execution planning) | 29 January 2024 08:00 | 05 July 2024 17:00 |  | 1099
| 1108 | 5 | 3.3.1.2.4 |  | Monitoring of provisional Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Participants' PIT progress and test readiness | 29 January 2024 08:00 | 05 July 2024 17:00 |  | 1081
1104 | 1109 | 5 | 3.3.1.2.5 | Tier 3 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness confirmed | 05 July 2024 17:00 | 05 July 2024 17:00 | 1104 | 1104FF
| 1110 | 3 | 3.3.2 |  | MHHS Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) start | 15 July 2024 08:00 | 15 July 2024 08:00 |  | 983SS
| 1111 | 3 | 3.3.3 |  | MHHS Qualification Testing for Non-SIT LDSOs Execution | 15 July 2024 08:00 | 24 January 2025 17:00
| 1112 | 4 | 3.3.3.1 |  | Functional Testing | 15 July 2024 08:00 | 01 November 2024 17:00
| 1113 | 5 | 3.3.3.1.1 |  | Cycle 1 (including defect fix period) | 15 July 2024 08:00 | 04 October 2024 17:00 |  | 983SS
| 1114 | 5 | 3.3.3.1.2 |  | Cycle 2 (including defect fix period) | 07 October 2024 08:00 | 01 November 2024 17:00 |  | 1113
| 1115 | 4 | 3.3.3.2 |  | Migration Testing | 09 September 2024 08:00 | 01 November 2024 17:00 |  | 1113SS+40d
| 1116 | 4 | 3.3.3.3 |  | Non-Functional Testing | 07 October 2024 08:00 | 29 November 2024 17:00 |  | 1113
| 1117 | 4 | 3.3.3.4 |  | Operational Testing | 02 December 2024 08:00 | 24 January 2025 17:00 |  | 1116
1020 | 1118 | 3 | 3.3.4 | Tier 3 | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | 24 January 2025 17:00 | 24 January 2025 17:00 | 1020 | 1020FF
1118 | 1119 | 3 | 3.3.5 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Completion (Start of Migration for Qualification Participants) | 21 February 2025 17:00 | 21 February 2025 17:00 | 1118 | 1118FS+20d
| 1120 | 3 | 3.3.6 |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Participants mobilise production environments | 27 January 2025 08:00 | 21 March 2025 17:00 |  | 1118
| 1121 | 2 | 3.4 |  | E2E Sandbox Testing Preparation | 31 October 2022 08:00 | 06 June 2025 17:00
| 1122 | 3 | 3.4.1 |  | Test Artefact Development | 01 March 2023 08:00 | 04 August 2023 17:00
| 1123 | 4 | 3.4.1.1 |  | E2E Sandbox Guidance | 01 March 2023 08:00 | 04 August 2023 17:00
| 1124 | 5 | 3.4.1.1.1 |  | Develop document | 01 March 2023 08:00 | 23 June 2023 17:00
| 1125 | 5 | 3.4.1.1.2 |  | Artefact review (via TMAG) and updates | 26 June 2023 08:00 | 28 July 2023 17:00 |  | 1124
1125 | 1126 | 5 | 3.4.1.1.3 | Tier 3 | E2E Sandbox Guidance approved | 04 August 2023 17:00 | 04 August 2023 17:00 | 1125 | 1125FF+5d
| 1127 | 4 | 3.4.1.2 |  | E2E Sandbox Test Data Approach & Plan | 29 March 2023 08:00 | 04 August 2023 17:00
| 1128 | 5 | 3.4.1.2.1 |  | Develop document | 29 March 2023 08:00 | 30 June 2023 17:00 |  | 1124SS+20d
| 1129 | 5 | 3.4.1.2.2 |  | Review, update & agree document internally | 03 July 2023 08:00 | 04 August 2023 17:00 |  | 1128
| 1130 | 3 | 3.4.2 |  | UIT Stub Specification and Delivery | 27 October 2023 08:00 | 23 August 2024 17:00
| 1131 | 4 | 3.4.2.1 |  | CSS & SMRS Simulators | 27 October 2023 08:00 | 23 August 2024 17:00
| 1132 | 5 | 3.4.2.1.1 |  | Specify | 27 October 2023 08:00 | 29 December 2023 08:00 |  | 1133SF
| 1133 | 5 | 3.4.2.1.2 |  | Build & Test | 29 December 2023 08:00 | 24 May 2024 08:00 |  | 1134SF
| 1134 | 5 | 3.4.2.1.3 |  | UAT | 24 May 2024 08:00 | 10 June 2024 08:00 |  | 1135SF
| 1135 | 5 | 3.4.2.1.4 |  | Beta test | 10 June 2024 08:00 | 29 July 2024 08:00 |  | 1136SF
| 1136 | 5 | 3.4.2.1.5 |  | Prepare for release | 29 July 2024 08:00 | 23 August 2024 17:00 |  | 1137FF
1154 | 1137 | 5 | 3.4.2.1.6 | Tier 3 | CSS & SMRS Simulators Released | 23 August 2024 17:00 | 23 August 2024 17:00 | 1154 | 1154FF
| 1138 | 3 | 3.4.3 |  | Environments (UIT) | 31 October 2022 08:00 | 06 June 2025 17:00
| 1139 | 4 | 3.4.3.1 |  | Central Party Environments (UIT) | 16 November 2022 08:00 | 04 October 2024 17:00
| 1140 | 5 | 3.4.3.1.1 |  | Central Parties' environment preparation (incl. security certificates and security compliance) | 16 November 2022 08:00 | 23 August 2024 17:00 |  | 467
| 1141 | 5 | 3.4.3.1.2 |  | Submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 16 November 2022 08:00 | 23 August 2024 17:00 |  | 1140SS
| 1142 | 5 | 3.4.3.1.3 |  | Central Parties' UIT environment connectivity proving | 27 August 2024 08:00 | 20 September 2024 17:00 |  | 1154FS+1d
| 1143 | 5 | 3.4.3.1.4 |  | Deployment of MHHS solution code to UIT environments | 09 September 2024 08:00 | 20 September 2024 17:00 |  | 1142FF
| 1144 | 5 | 3.4.3.1.5 |  | Central Parties' UIT environment Regression Testing | 23 September 2024 08:00 | 04 October 2024 17:00 |  | 1143
| 1145 | 4 | 3.4.3.2 |  | E2E Sandbox Participants (UIT) | 31 October 2022 08:00 | 06 June 2025 17:00
| 1146 | 5 | 3.4.3.2.1 |  | E2E Sandbox Participants environment preparation (incl. security certificates and security compliance) | 31 October 2022 08:00 | 09 May 2025 17:00 |  | 1645FF-2mo
| 1147 | 5 | 3.4.3.2.2 |  | Submit self-declaration of envionment preparation complete (incl. security cerificates and security compliance) to Programme for assurance | 31 October 2022 08:00 | 09 May 2025 17:00
| 1148 | 5 | 3.4.3.2.3 |  | E2E Sandbox Participants UIT environment connectivity proving | 12 May 2025 08:00 | 06 June 2025 17:00 |  | 1147
| 1149 | 5 | 3.4.3.2.4 |  | Deployment of MHHS solution code to UIT environments | 26 May 2025 08:00 | 06 June 2025 17:00 |  | 1148FF
| 1150 | 4 | 3.4.3.3 |  | SI Environments (UIT) | 31 October 2022 08:00 | 06 June 2025 17:00
| 1151 | 5 | 3.4.3.3.1 |  | Coordinate Central Parties' UIT environment preparation | 16 November 2022 08:00 | 23 August 2024 17:00 |  | 1140SS
| 1152 | 5 | 3.4.3.3.2 |  | Coordinate E2E Sandbox Participants' UIT environment preparation (for E2E Sandbox Testing Start) | 31 October 2022 08:00 | 07 August 2024 17:00 |  | 1146SS
| 1153 | 5 | 3.4.3.3.3 |  | Assure Central Parties' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 16 November 2022 08:00 | 23 August 2024 17:00 |  | 1141SS,1147SS
1153 | 1154 | 5 | 3.4.3.3.4 | Tier 3 | Central Parties' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 23 August 2024 17:00 | 23 August 2024 17:00 | 1153 | 1153
| 1155 | 5 | 3.4.3.3.5 |  | Coordinate Central Parties' UIT environment connectivity proving | 12 May 2025 08:00 | 05 June 2025 17:00 |  | 1142SS,1148SS
| 1156 | 5 | 3.4.3.3.6 |  | Coordinate deployment of MHHS solution code to Central Parties' UIT environments | 26 May 2025 08:00 | 06 June 2025 17:00 |  | 1143SS,1149SS
| 1157 | 5 | 3.4.3.3.7 |  | Coordinate Central Parties' UIT environment Regression Testing | 23 September 2024 08:00 | 04 October 2024 17:00 |  | 1144SS
| 1158 | 3 | 3.4.4 |  | Test Data | 26 August 2024 08:00 | 04 October 2024 17:00
| 1159 | 4 | 3.4.4.1 |  | Central Parties (for E2E Sandbox & Qualification) | 26 August 2024 08:00 | 04 October 2024 17:00
| 1160 | 5 | 3.4.4.1.1 |  | Central Parties' UIT environment test data loading & verification (& data cleansing, if required) | 26 August 2024 08:00 | 04 October 2024 17:00 |  | 1144FF
| 1161 | 5 | 3.4.4.1.2 |  | Submit self-declaration to Programme to confirm loading & verification of test data | 26 August 2024 08:00 | 04 October 2024 17:00 |  | 1160SS
| 1162 | 4 | 3.4.4.2 |  | E2E Sandbox Participants | 26 August 2024 08:00 | 04 October 2024 17:00
| 1163 | 5 | 3.4.4.2.1 |  | UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 26 August 2024 08:00 | 04 October 2024 17:00 |  | 1160FF
| 1164 | 4 | 3.4.4.3 |  | SI Test Data | 26 August 2024 08:00 | 04 October 2024 17:00
| 1165 | 5 | 3.4.4.3.1 |  | Coordinate Central Parties' UIT environment test data loading and verification (and data cleansing, if required) | 26 August 2024 08:00 | 04 October 2024 17:00 |  | 1160SS
| 1166 | 5 | 3.4.4.3.2 |  | Assure evidence of Central Parties' UIT environment test data load and verification | 26 August 2024 08:00 | 04 October 2024 17:00 |  | 1161SS
| 1167 | 5 | 3.4.4.3.3 |  | Coordinate E2E Sandbox Participants' UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 26 August 2024 08:00 | 04 October 2024 17:00 |  | 1163SS
| 1168 | 3 | 3.4.5 |  | Other Preparation | 16 November 2022 08:00 | 24 September 2024 17:00
| 1169 | 4 | 3.4.5.1 |  | SI Other Preparation | 01 March 2023 08:00 | 24 September 2024 17:00
| 1170 | 5 | 3.4.5.1.1 |  | Onboarding of UIT E2E Sandbox Participants to Test Management Tool for E2E Sandbox Testing Start (onboarding of participants will be ongoing hereafter) | 02 May 2024 08:00 | 01 August 2024 17:00 |  | 1186SS-132d
| 1171 | 5 | 3.4.5.1.2 |  | Other Preparation (activities TBC) | 01 March 2023 08:00 | 24 September 2024 17:00 |  | 1124SS
| 1172 | 4 | 3.4.5.2 |  | Other Preparation (for Central Parties & E2E Sandbox Participants) | 16 November 2022 08:00 | 23 September 2024 17:00
| 1173 | 5 | 3.4.5.2.1 |  | Test Management Tool onboarding for E2E Sandbox Testing Start (onboarding will be ongoing hereafter) | 02 May 2024 08:00 | 01 August 2024 17:00 |  | 1170SS
| 1174 | 5 | 3.4.5.2.2 |  | Other Preparation (incl. test execution planning) | 16 November 2022 08:00 | 23 September 2024 17:00 |  | 1140SS,1146SS
| 1175 | 3 | 3.4.6 |  | UIT E2E Sandbox Test Readiness Report | 26 August 2024 08:00 | 25 October 2024 17:00
| 1176 | 4 | 3.4.6.1 |  | Central Parties E2E Sandbox Test Readiness Report | 26 August 2024 08:00 | 04 October 2024 17:00
| 1177 | 5 | 3.4.6.1.1 |  | Develop draft Test Readiness Report and submit to Programme for assurance | 26 August 2024 08:00 | 20 September 2024 17:00 |  | 1161FF-10d
| 1178 | 5 | 3.4.6.1.2 |  | Finalise Test Readiness Report and submit to Programme for assurance | 23 September 2024 08:00 | 04 October 2024 17:00 |  | 1161FF
| 1179 | 4 | 3.4.6.2 |  | SI E2E Sandbox Test Readiness Report | 26 August 2024 08:00 | 18 October 2024 17:00
| 1180 | 5 | 3.4.6.2.1 |  | Assure Central Parties' E2E Sandbox Test Readiness Reports | 26 August 2024 08:00 | 11 October 2024 17:00 |  | 1177SS,1178FF+5d
| 1181 | 5 | 3.4.6.2.2 |  | Develop Overarching E2E Sandbox Test Readiness Report | 16 September 2024 08:00 | 11 October 2024 17:00 |  | 1180FF
| 1182 | 5 | 3.4.6.2.3 |  | Artefact review (via TMAG) and updates | 14 October 2024 08:00 | 18 October 2024 17:00 |  | 1181
1182 | 1183 | 4 | 3.4.6.3 | Tier 3 | UIT E2E Sandbox Preparation Complete | 25 October 2024 17:00 | 25 October 2024 17:00 | 1182 | 1182FS+5d
| 1184 | 2 | 3.5 |  | SIT PPs E2E Sandbox Testing Execution | 04 November 2024 08:00 | 19 January 2026 17:00
| 1185 | 3 | 3.5.1 | Tier 3 | SIT PPs E2E Sandbox Testing Start | 04 November 2024 17:00 | 04 November 2024 17:00 | 0 | 991FS+1d,1183FS+5d
| 1186 | 3 | 3.5.2 |  | SIT PPs E2E Sandbox Testing Execution | 04 November 2024 08:00 | 19 January 2026 17:00 |  | 1185SS-1d,1646FF
| 1187 | 2 | 3.6 |  | External Programme Dependency Management | 31 October 2022 08:00 | 30 June 2023 08:00
| 1188 | 3 | 3.6.1 |  | BSC CP1558 | 31 October 2022 08:00 | 29 June 2023 08:00
| 1189 | 4 | 3.6.1.1 |  | Monitor progress to implementation date | 31 October 2022 08:00 | 28 June 2023 17:00
| 1190 | 4 | 3.6.1.2 |  | BSC CP1558 Implementation Date | 29 June 2023 08:00 | 29 June 2023 08:00 |  | 1189
| 1191 | 3 | 3.6.2 |  | REC CP R0032 | 31 October 2022 08:00 | 30 June 2023 08:00
| 1192 | 4 | 3.6.2.1 |  | Monitor progress to implementation date | 31 October 2022 08:00 | 29 June 2023 17:00
| 1193 | 4 | 3.6.2.2 |  | REC CP R0032 Implementation Date | 30 June 2023 08:00 | 30 June 2023 08:00 |  | 1192
| 1194 | 3 | 3.6.3 |  | REC CP R0044 | 31 October 2022 08:00 | 29 June 2023 08:00
| 1195 | 4 | 3.6.3.1 |  | Monitor progress to implementation date | 31 October 2022 08:00 | 28 June 2023 17:00
| 1196 | 4 | 3.6.3.2 |  | REC CP R0044 Implementation Date | 29 June 2023 08:00 | 29 June 2023 08:00 |  | 1195
| 1197 | 2 | 3.7 |  | Systems Integration Testing - Tier 1 Milestones | 30 October 2023 08:00 | 07 February 2025 08:00
| 1198 | 3 | 3.7.1 | Tier 1 | System Integration Testing Start (M9) | 30 October 2023 08:00 | 30 October 2023 08:00 | 0 | 1193,1190,1196
| 1199 | 3 | 3.7.2 | Tier 1 | SIT Minimum Viable Cohort Complete (SIT Minimum Viable Cohort Test Exit Report Approved) | 07 February 2025 08:00 | 07 February 2025 08:00
| 1200 | 1 | 4 |  | REGULATORY | 31 October 2022 08:00 | 07 March 2025 17:00
| 1201 | 2 | 4.1 |  | Baseline MHHS Code Changes | 31 October 2022 08:00 | 23 August 2024 17:00 |  | 51SS
| 1202 | 3 | 4.1.1 |  | Preparation and planning | 31 October 2022 08:00 | 16 December 2022 17:00
| 1203 | 4 | 4.1.1.1 |  | Impact assessment of Programme design on codes to determine required changes | 31 October 2022 08:00 | 25 November 2022 17:00 |  | 52
| 1204 | 4 | 4.1.1.2 |  | Become 'code draft ready' | 31 October 2022 08:00 | 16 December 2022 17:00
| 1205 | 4 | 4.1.1.3 |  | Soft start drafting where possible | 31 October 2022 08:00 | 16 December 2022 17:00
| 1206 | 3 | 4.1.2 |  | Code drafting | 12 December 2022 08:00 | 23 August 2024 17:00
| 1207 | 4 | 4.1.2.1 |  | Data Services (BSC driven) | 12 December 2022 08:00 | 13 November 2023 17:00
| 1208 | 5 | 4.1.2.1.1 |  | Pre Code Drafting activities | 12 December 2022 08:00 | 16 December 2022 17:00
| 1209 | 5 | 4.1.2.1.2 |  | Code and subsidiary document drafting takes place offline | 03 January 2023 08:00 | 27 January 2023 17:00 |  | 1208FS+11d
| 1210 | 5 | 4.1.2.1.3 |  | Internal review and cross-checking of drafting across code drafters | 30 January 2023 08:00 | 13 February 2023 17:00 |  | 1209
| 1211 | 5 | 4.1.2.1.4 |  | External industry review via consultation | 14 February 2023 08:00 | 13 March 2023 17:00 |  | 1210
| 1212 | 5 | 4.1.2.1.5 |  | Triage and action comments | 10 March 2023 08:00 | 05 April 2023 17:00 |  | 1211FS-2d
| 1213 | 5 | 4.1.2.1.6 |  | CDWG review | 06 April 2023 08:00 | 17 May 2023 17:00 |  | 1212
| 1214 | 5 | 4.1.2.1.7 |  | CCAG review | 18 May 2023 08:00 | 24 May 2023 17:00 |  | 1213
| 1215 | 5 | 4.1.2.1.8 | Tier 2 | Code drafting for Data Services topic area approved | 13 November 2023 17:00 | 13 November 2023 17:00 | 0 | 1214,1223,1232,1241,1250,1259,1268
| 1216 | 4 | 4.1.2.2 |  | Metering (REC driven) | 12 December 2022 08:00 | 24 May 2023 17:00
| 1217 | 5 | 4.1.2.2.1 |  | Pre Code Drafting activities | 12 December 2022 08:00 | 16 December 2022 17:00 |  | 1208SS
| 1218 | 5 | 4.1.2.2.2 |  | Code and subsidiary document drafting takes place offline | 03 January 2023 08:00 | 27 January 2023 17:00 |  | 1217FS+11d
| 1219 | 5 | 4.1.2.2.3 |  | Internal review and cross-checking of drafting across code drafters | 30 January 2023 08:00 | 13 February 2023 17:00 |  | 1218
| 1220 | 5 | 4.1.2.2.4 |  | External industry review via consultation | 14 February 2023 08:00 | 13 March 2023 17:00 |  | 1219
| 1221 | 5 | 4.1.2.2.5 |  | Triage and action comments | 10 March 2023 08:00 | 05 April 2023 17:00 |  | 1220FS-2d
| 1222 | 5 | 4.1.2.2.6 |  | CDWG review | 06 April 2023 08:00 | 17 May 2023 17:00 |  | 1221
| 1223 | 5 | 4.1.2.2.7 |  | CCAG review | 18 May 2023 08:00 | 24 May 2023 17:00 |  | 1222
1223 | 1224 | 5 | 4.1.2.2.8 | Tier 2 | Code drafting for Metering topic area approved | 24 May 2023 17:00 | 24 May 2023 17:00 | 1223 | 1223
| 1225 | 4 | 4.1.2.3 |  | BSC Central Services (BSC driven) | 22 February 2023 08:00 | 14 September 2023 17:00
| 1226 | 5 | 4.1.2.3.1 |  | Pre Code Drafting activities | 22 February 2023 08:00 | 28 February 2023 17:00 |  | 1227SS-5d
| 1227 | 5 | 4.1.2.3.2 |  | Code Drafting (offline) | 01 March 2023 08:00 | 20 June 2023 17:00 |  | 1211SS
| 1228 | 5 | 4.1.2.3.3 |  | Internal review and cross-checking of drafting across code drafters | 15 March 2023 08:00 | 20 June 2023 17:00 |  | 1227SS+10d
| 1229 | 5 | 4.1.2.3.4 |  | External industry review via consultation | 21 June 2023 08:00 | 11 July 2023 17:00 |  | 1228
| 1230 | 5 | 4.1.2.3.5 |  | Triage and action comments | 10 July 2023 08:00 | 03 August 2023 17:00 |  | 1229FS-2d
| 1231 | 5 | 4.1.2.3.6 |  | CDWG review | 04 August 2023 08:00 | 07 September 2023 17:00 |  | 1230
| 1232 | 5 | 4.1.2.3.7 |  | CCAG review | 08 September 2023 08:00 | 14 September 2023 17:00 |  | 1231
1232 | 1233 | 5 | 4.1.2.3.8 | Tier 2 | Code drafting for BSC Central Services topic area approved | 14 September 2023 17:00 | 14 September 2023 17:00 | 1232 | 1232
| 1234 | 4 | 4.1.2.4 |  | Registration (BSC & REC driven) | 22 February 2023 08:00 | 23 August 2023 17:00
| 1235 | 5 | 4.1.2.4.1 |  | Pre Code Drafting activities | 22 February 2023 08:00 | 28 February 2023 17:00 |  | 1236SS-5d
| 1236 | 5 | 4.1.2.4.2 |  | Code Drafting (offline) | 01 March 2023 08:00 | 30 May 2023 17:00 |  | 1210,1219
| 1237 | 5 | 4.1.2.4.3 |  | Internal review and cross-checking of drafting across code drafters | 15 March 2023 08:00 | 30 May 2023 17:00 |  | 1236SS+10d
| 1238 | 5 | 4.1.2.4.4 |  | External industry review via consultation | 31 May 2023 08:00 | 20 June 2023 17:00 |  | 1237
| 1239 | 5 | 4.1.2.4.5 |  | Triage and action comments | 19 June 2023 08:00 | 13 July 2023 17:00 |  | 1238FS-2d
| 1240 | 5 | 4.1.2.4.6 |  | CDWG review | 14 July 2023 08:00 | 16 August 2023 17:00 |  | 1239
| 1241 | 5 | 4.1.2.4.7 |  | CCAG review | 17 August 2023 08:00 | 23 August 2023 17:00 |  | 1240
1241 | 1242 | 5 | 4.1.2.4.8 | Tier 2 | Code drafting for Registration topic area approved | 23 August 2023 17:00 | 23 August 2023 17:00 | 1241 | 1241
| 1243 | 4 | 4.1.2.5 |  | Governance and Qualification (BSC & REC driven) | 25 May 2023 08:00 | 13 November 2023 17:00
| 1244 | 5 | 4.1.2.5.1 |  | Pre Code Drafting activities | 25 May 2023 08:00 | 31 May 2023 17:00 |  | 1245SS-5d
| 1245 | 5 | 4.1.2.5.2 |  | Code Drafting (offline) | 01 June 2023 08:00 | 16 August 2023 17:00 |  | 1238SS+1d
| 1246 | 5 | 4.1.2.5.3 |  | Internal review and cross-checking of drafting across code drafters | 15 June 2023 08:00 | 16 August 2023 17:00 |  | 1245SS+10d
| 1247 | 5 | 4.1.2.5.4 |  | External industry review via consultation | 18 August 2023 08:00 | 07 September 2023 17:00 |  | 1246FS+1d
| 1248 | 5 | 4.1.2.5.5 |  | Triage and action comments | 06 September 2023 08:00 | 02 October 2023 17:00 |  | 1247FS-2d
| 1249 | 5 | 4.1.2.5.6 |  | CDWG review | 03 October 2023 08:00 | 06 November 2023 17:00 |  | 1248
| 1250 | 5 | 4.1.2.5.7 |  | CCAG review | 07 November 2023 08:00 | 13 November 2023 17:00 |  | 1249
1250 | 1251 | 5 | 4.1.2.5.8 | Tier 2 | Code drafting for Governance and Qualification topic areas approved | 13 November 2023 17:00 | 13 November 2023 17:00 | 1250 | 1250
| 1252 | 4 | 4.1.2.6 |  | Interfaces / Data Specification (REC driven) | 25 May 2023 08:00 | 13 November 2023 17:00
| 1253 | 5 | 4.1.2.6.1 |  | Pre Code Drafting activities | 25 May 2023 08:00 | 31 May 2023 17:00 |  | 1254SS-5d
| 1254 | 5 | 4.1.2.6.2 |  | Code Drafting (offline) | 01 June 2023 08:00 | 16 August 2023 17:00 |  | 1238SS+1d
| 1255 | 5 | 4.1.2.6.3 |  | Internal review and cross-checking of drafting across code drafters | 15 June 2023 08:00 | 16 August 2023 17:00 |  | 1254SS+10d
| 1256 | 5 | 4.1.2.6.4 |  | External industry review via consultation | 18 August 2023 08:00 | 07 September 2023 17:00 |  | 1255FS+1d
| 1257 | 5 | 4.1.2.6.5 |  | Triage and action comments | 06 September 2023 08:00 | 02 October 2023 17:00 |  | 1256FS-2d
| 1258 | 5 | 4.1.2.6.6 |  | CDWG review | 03 October 2023 08:00 | 06 November 2023 17:00 |  | 1257
| 1259 | 5 | 4.1.2.6.7 |  | CCAG review | 07 November 2023 08:00 | 13 November 2023 17:00 |  | 1258
1259 | 1260 | 5 | 4.1.2.6.8 | Tier 2 | Code drafting for Interfaces / Data Specification topic areas approved | 13 November 2023 17:00 | 13 November 2023 17:00 | 1259 | 1259
| 1261 | 5 | 4.1.2.6.9 |  | Migration (BSC & REC driven) | 25 May 2023 08:00 | 13 November 2023 17:00
| 1262 | 6 | 4.1.2.6.9.1 |  | Pre Code Drafting activities | 25 May 2023 08:00 | 31 May 2023 17:00 |  | 1263SS-5d
| 1263 | 6 | 4.1.2.6.9.2 |  | Code Drafting (offline) | 01 June 2023 08:00 | 16 August 2023 17:00 |  | 1238SS+1d
| 1264 | 6 | 4.1.2.6.9.3 |  | Internal review and cross-checking of drafting across code drafters | 15 June 2023 08:00 | 16 August 2023 17:00 |  | 1263SS+10d
| 1265 | 6 | 4.1.2.6.9.4 |  | External industry review via consultation | 18 August 2023 08:00 | 07 September 2023 17:00 |  | 1264FS+1d
| 1266 | 6 | 4.1.2.6.9.5 |  | Triage and action comments | 06 September 2023 08:00 | 02 October 2023 17:00 |  | 1265FS-2d
| 1267 | 6 | 4.1.2.6.9.6 |  | CDWG review | 03 October 2023 08:00 | 06 November 2023 17:00 |  | 1266
| 1268 | 6 | 4.1.2.6.9.7 |  | CCAG review | 07 November 2023 08:00 | 13 November 2023 17:00 |  | 1267
1268 | 1269 | 6 | 4.1.2.6.9.8 | Tier 2 | Code drafting for Migration topic area approved | 13 November 2023 17:00 | 13 November 2023 17:00 | 1268 | 1268
| 1270 | 4 | 4.1.2.7 |  | Transition Text (all codes) | 11 August 2023 08:00 | 23 August 2024 17:00
| 1271 | 5 | 4.1.2.7.1 |  | Pre Code Drafting activities | 11 August 2023 08:00 | 17 August 2023 17:00 |  | 1272SS-5d
| 1272 | 5 | 4.1.2.7.2 |  | Code Drafting (offline) | 18 August 2023 08:00 | 12 October 2023 17:00 |  | 1265SS
| 1273 | 5 | 4.1.2.7.3 |  | Internal review and cross-checking of drafting across code drafters | 01 September 2023 08:00 | 12 October 2023 17:00 |  | 1272SS+10d
| 1274 | 5 | 4.1.2.7.4 |  | External industry review via consultation | 16 October 2023 08:00 | 03 November 2023 17:00 |  | 1273FS+1d
| 1275 | 5 | 4.1.2.7.5 |  | Triage and action comments | 02 November 2023 08:00 | 21 November 2023 17:00 |  | 1274FS-2d
| 1276 | 5 | 4.1.2.7.6 |  | CDWG review | 22 November 2023 08:00 | 17 January 2024 17:00 |  | 1275
| 1277 | 5 | 4.1.2.7.7 |  | CCAG review | 18 January 2024 08:00 | 25 January 2024 17:00 |  | 1276
| 1278 | 5 | 4.1.2.7.8 | Tier 2 | Code drafting for Transition Text topic area approved | 23 August 2024 17:00 | 23 August 2024 17:00 | 0 | 1277,1287,1296
| 1279 | 4 | 4.1.2.8 |  | Final Code Drafting (mop-up) (all codes) | 18 August 2023 08:00 | 23 August 2024 17:00
| 1280 | 5 | 4.1.2.8.1 |  | Forward look and confirm remaining plan | 18 August 2023 08:00 | 07 September 2023 17:00 |  | 1272SS
| 1281 | 5 | 4.1.2.8.2 |  | Identify remaining or additional areas of code (e.g. consequential change requirements) to be completed | 18 August 2023 08:00 | 07 September 2023 17:00 |  | 1280SS
| 1282 | 5 | 4.1.2.8.3 |  | Code Drafting (offline) | 08 September 2023 08:00 | 15 February 2024 17:00 |  | 1281
| 1283 | 5 | 4.1.2.8.4 |  | Internal review and cross-checking of drafting across code drafters | 22 September 2023 08:00 | 15 February 2024 17:00 |  | 1282SS+10d
| 1284 | 5 | 4.1.2.8.5 |  | External industry review via consultation | 19 February 2024 08:00 | 08 March 2024 17:00 |  | 1283FS+1d
| 1285 | 5 | 4.1.2.8.6 |  | Triage and action comments | 07 March 2024 08:00 | 03 April 2024 17:00 |  | 1284FS-2d
| 1286 | 5 | 4.1.2.8.7 |  | CDWG review | 04 April 2024 08:00 | 03 May 2024 17:00 |  | 1285
| 1287 | 5 | 4.1.2.8.8 |  | CCAG review | 06 May 2024 08:00 | 13 May 2024 17:00 |  | 1286
| 1288 | 5 | 4.1.2.8.9 | Tier 2 | Final code drafting (mop-up) approved | 23 August 2024 17:00 | 23 August 2024 17:00 |  | 1287,1296
| 1289 | 4 | 4.1.2.9 |  | Final code review, consistency check and approval | 06 May 2024 08:00 | 23 August 2024 17:00
| 1290 | 5 | 4.1.2.9.1 |  | Gap analysis of final code against design artefacts (reverse process to code drafting) | 06 May 2024 08:00 | 17 May 2024 17:00 |  | 1286
| 1291 | 5 | 4.1.2.9.2 |  | Outputs of gap analysis actioned offline | 20 May 2024 08:00 | 07 June 2024 17:00 |  | 1290
| 1292 | 5 | 4.1.2.9.3 |  | Final documentation collated for final consultation | 10 June 2024 08:00 | 13 June 2024 17:00 |  | 1291
| 1293 | 5 | 4.1.2.9.4 |  | External industry review via consultation | 14 June 2024 08:00 | 04 July 2024 17:00 |  | 1292
| 1294 | 5 | 4.1.2.9.5 |  | Triage and action comments | 03 July 2024 08:00 | 19 July 2024 17:00 |  | 1293FS-2d
| 1295 | 5 | 4.1.2.9.6 |  | Final CDWG review | 22 July 2024 08:00 | 16 August 2024 17:00 |  | 1294
| 1296 | 5 | 4.1.2.9.7 |  | Final CCAG review | 19 August 2024 08:00 | 23 August 2024 17:00 |  | 1295
1295 | 1297 | 5 | 4.1.2.9.8 | Tier 2 | CCAG recommend final code to PSG for baselining | 23 August 2024 17:00 | 23 August 2024 17:00 | 1295 | 1295FS+5d
1296 | 1298 | 3 | 4.1.3 | Tier 1 | Code changes baselined (M6) | 23 August 2024 17:00 | 23 August 2024 17:00 | 1296 | 1296
| 1299 | 2 | 4.2 |  | Ofgem preparation and enactment of SCR powers | 26 January 2024 08:00 | 12 November 2024 08:00
| 1300 | 3 | 4.2.1 |  | Preparation and enactment of SCR Powers | 26 January 2024 08:00 | 11 November 2024 17:00
| 1301 | 4 | 4.2.1.1 |  | Ofgem to keep Ofgem legal informed of process followed and nature of Code drafting to ensure that prepared for SCR go/no go decision | 26 January 2024 08:00 | 14 June 2024 08:00 |  | 1302SF
| 1302 | 4 | 4.2.1.2 |  | OFGEM Legal to review Code Artefacts deliver policy intent and process followed and confirm that SCR powers are appropriate to use rather than SMAP - SCR go/no go | 14 June 2024 08:00 | 04 July 2024 17:00 |  | 1293SS
| 1303 | 4 | 4.2.1.3 |  | Code Bodies to draft MOD proposal forms | 05 July 2024 08:00 | 01 August 2024 17:00 |  | 1302
| 1304 | 4 | 4.2.1.4 |  | Ofgem discuss and agree code mod timetable with code bodies (and MHHSP in relation to the dates for expected decisions) | 05 July 2024 08:00 | 01 August 2024 17:00 |  | 1302
| 1305 | 4 | 4.2.1.5 |  | Ofgem to draft open letter and direction to each code body specifying the timetable for each modification | 02 August 2024 08:00 | 08 August 2024 17:00 |  | 1304
| 1306 | 4 | 4.2.1.6 |  | Ofgem to publish open letter | 26 August 2024 08:00 | 26 August 2024 17:00 |  | 1298
| 1307 | 4 | 4.2.1.7 |  | Ofgem to publish each Direction to each code body specifying the timetable for each modification | 28 August 2024 08:00 | 28 August 2024 17:00 |  | 1306FS+1d
| 1308 | 4 | 4.2.1.8 |  | Formally submit (by separate email) Modification Proposal Forms and legal texts to each code body | 28 August 2024 08:00 | 28 August 2024 17:00 |  | 1306FS+1d
| 1309 | 4 | 4.2.1.9 |  | Each Code Body publishes and issues Modification Proposal Forms | 29 August 2024 08:00 | 02 September 2024 17:00 |  | 1308
| 1310 | 4 | 4.2.1.10 |  | Each Code Body sends Modification Proposal Forms to Panel to approve Mod to go to consultation | 03 September 2024 08:00 | 16 September 2024 17:00 |  | 1309
| 1311 | 4 | 4.2.1.11 |  | Modification Proposal approved by Panel for Consultation | 17 September 2024 08:00 | 17 September 2024 17:00 |  | 1310
| 1312 | 4 | 4.2.1.12 |  | Draft Modification Report issued for consultation | 18 September 2024 08:00 | 18 September 2024 17:00 |  | 1311
| 1313 | 4 | 4.2.1.13 |  | Consultation Close-out for representations | 19 September 2024 08:00 | 09 October 2024 17:00 |  | 1312
| 1314 | 4 | 4.2.1.14 |  | Each Code Body reviews consultation response and drafts Modification Report | 10 October 2024 08:00 | 23 October 2024 17:00 |  | 1313
| 1315 | 4 | 4.2.1.15 |  | Final Modification Report sent to Panel for decision with recommendation to approve | 24 October 2024 08:00 | 24 October 2024 17:00 |  | 1314
| 1316 | 4 | 4.2.1.16 |  | Modification Panel decision | 07 November 2024 08:00 | 07 November 2024 17:00 |  | 1315FS+9d
| 1317 | 4 | 4.2.1.17 |  | Panel make recommendation to OFGEM | 08 November 2024 08:00 | 11 November 2024 17:00 |  | 1316
1316 | 1318 | 4 | 4.2.1.18 | Tier 2 | Ofgem publish decision to implement Mods in line with MHHSP timetable (M7) | 08 November 2024 08:00 | 11 November 2024 17:00 | 1316 | 1316
| 1319 | 3 | 4.2.2 |  | SCR powers enabled (M7) | 11 November 2024 17:00 | 11 November 2024 17:00 |  | 1318FF
| 1320 | 3 | 4.2.3 |  | Ofgem preparation to enact Smart Meter Act powers [CONTINGENCY ONLY] | 14 June 2024 08:00 | 12 November 2024 08:00
| 1321 | 4 | 4.2.3.1 |  | SRO recommends Ofgem begin preparation to enact Smart Meter Act powers [CONTINGENCY ONLY] | 14 June 2024 08:00 | 14 June 2024 17:00 |  | 1302SS
| 1322 | 4 | 4.2.3.2 |  | Ofgem drafts letter to DESNZ to request trigger of Smart Meter Act powers [CONTINGENCY ONLY] | 17 June 2024 08:00 | 05 July 2024 17:00 |  | 1321
| 1323 | 4 | 4.2.3.3 |  | DESNZ SoS letter response to trigger SMAP Powers [CONTINGENCY ONLY] | 08 July 2024 08:00 | 02 August 2024 17:00 |  | 1322
| 1324 | 4 | 4.2.3.4 |  | Ofgem enables Smart Meters Act powers (support from the Programme, where required) [CONTINGENCY ONLY] | 05 August 2024 08:00 | 06 August 2024 08:00 |  | 1328SF
| 1325 | 4 | 4.2.3.5 |  | Smart Meters Act powers enabled (M7) [CONTINGENCY ONLY] | 06 August 2024 08:00 | 06 August 2024 08:00 |  | 1324
| 1326 | 4 | 4.2.3.6 |  | Deliver MHHS Code Changes [CONTINGENCY UNDER SMAP] | 06 August 2024 08:00 | 12 November 2024 08:00
| 1327 | 5 | 4.2.3.6.1 |  | Ofgem consultation and decision | 06 August 2024 08:00 | 12 November 2024 08:00
| 1328 | 6 | 4.2.3.6.1.1 |  | Ofgem issue completed code to industry for consultation under SMAP (consultaiton confirms robustness of the process undertaken via CCAG and does not re-open the detail of drafted code) | 06 August 2024 08:00 | 20 August 2024 08:00 |  | 1329SF
| 1329 | 6 | 4.2.3.6.1.2 |  | Industry respond to consultation on new Code (28-day consultation) | 20 August 2024 08:00 | 17 September 2024 08:00 |  | 1330SF
| 1330 | 6 | 4.2.3.6.1.3 |  | Ofgem considers consultation responses and publishes decision confirming Code Releases dates (release dates may be <56 days following publication of Ofgem decision) | 17 September 2024 08:00 | 12 November 2024 08:00 |  | 1333SF
| 1331 | 2 | 4.3 |  | Deliver MHHS Code Changes | 12 November 2024 08:00 | 07 March 2025 17:00
| 1332 | 3 | 4.3.1 |  | Releases | 12 November 2024 08:00 | 07 March 2025 17:00
| 1333 | 4 | 4.3.1.1 |  | Impacted codes make resourcing provisions and prepare to implement new Code via internal code body change processes | 12 November 2024 08:00 | 27 February 2025 17:00 |  | 1319
| 1334 | 4 | 4.3.1.2 |  | Main Code Release | 28 February 2025 08:00 | 07 March 2025 17:00
| 1335 | 5 | 4.3.1.2.1 |  | Release preparation (e.g. preparing release documentation) | 28 February 2025 08:00 | 07 March 2025 08:00 |  | 1336SF
1337 | 1336 | 5 | 4.3.1.2.2 | Tier 2 | Implement new code on day of code release | 07 March 2025 08:00 | 07 March 2025 17:00 | 1337 | 1337SF
| 1337 | 5 | 4.3.1.2.3 |  | Code changes delivered (M8) | 07 March 2025 17:00 | 07 March 2025 17:00 |  | 1756SS
| 1338 | 2 | 4.4 |  | External Programme Dependency Management | 08 September 2023 08:00 | 24 January 2024 08:00
| 1339 | 3 | 4.4.1 |  | DCP397 | 08 September 2023 08:00 | 24 January 2024 08:00
| 1340 | 4 | 4.4.1.1 |  | Ensure DCP397 drafting included in mop-up code drafting activitiy (link to mop-up) | 08 September 2023 08:00 | 05 October 2023 17:00 |  | 1282SS
| 1341 | 4 | 4.4.1.2 |  | Implementation of DCP397 | 24 January 2024 08:00 | 24 January 2024 08:00
| 1342 | 2 | 4.5 |  | Regulatory - Tier 1 Milestones | 23 August 2024 17:00 | 23 August 2024 17:00
1298 | 1343 | 3 | 4.5.1 | Tier 2 | Code changes baselined (M6) | 23 August 2024 17:00 | 23 August 2024 17:00 | 1298 | 1298
| 1344 | 1 | 5 |  | QUALIFICATION | 31 October 2022 08:00 | 31 December 2026 17:00
| 1345 | 2 | 5.1 |  | Qualification Preparation | 31 October 2022 08:00 | 30 June 2025 17:00
| 1346 | 3 | 5.1.1 |  | Artefact Development | 31 October 2022 08:00 | 19 December 2023 08:00
| 1347 | 4 | 5.1.1.1 |  | Collaborative ways of working | 27 February 2023 08:00 | 14 April 2023 17:00
| 1348 | 5 | 5.1.1.1.1 |  | Develop collaboration ways of working with Code Bodies | 27 February 2023 08:00 | 31 March 2023 17:00
| 1349 | 5 | 5.1.1.1.2 |  | Internal review and updates | 03 April 2023 08:00 | 14 April 2023 17:00 |  | 1348
| 1350 | 5 | 5.1.1.1.3 |  | Collaborative ways of working agreed | 14 April 2023 17:00 | 14 April 2023 17:00 |  | 1349
| 1351 | 4 | 5.1.1.2 |  | Qualification Approach & Plan (iterative development) | 31 October 2022 08:00 | 19 December 2023 08:00
| 1352 | 5 | 5.1.1.2.1 |  | Qualification Functional Testing | 31 October 2022 08:00 | 26 July 2023 17:00
| 1353 | 6 | 5.1.1.2.1.1 |  | Develop Functional Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 31 October 2022 08:00 | 28 February 2023 17:00 |  | 747SS
| 1354 | 6 | 5.1.1.2.1.2 |  | Review draft artefact with Programme to ensure alignment with SIT | 15 May 2023 08:00 | 26 May 2023 17:00 |  | 748SS
| 1355 | 6 | 5.1.1.2.1.3 |  | Artefact review (via TMAG) and updates | 29 May 2023 08:00 | 26 July 2023 17:00 |  | 749SS
750 | 1356 | 6 | 5.1.1.2.1.4 | Tier 3 | Functional Testing elements of Qualification Approach & Plan approved by TMAG | 21 July 2023 17:00 | 21 July 2023 17:00 | 750 | 750FF
| 1357 | 6 | 5.1.1.2.1.5 | Tier 3 | Functional Testing elements of Qualification Approach & Plan approved by REC PAB | 30 May 2023 08:00 | 30 May 2023 08:00
| 1358 | 6 | 5.1.1.2.1.6 | Tier 3 | Functional Testing elements of Qualification Approach & Plan approved by BSC PAB | 25 May 2023 08:00 | 25 May 2023 08:00
| 1359 | 5 | 5.1.1.2.2 |  | Qualification Migration Testing | 03 April 2023 08:00 | 20 September 2023 17:00
| 1360 | 6 | 5.1.1.2.2.1 |  | Develop Migration Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 03 April 2023 08:00 | 01 August 2023 17:00 |  | 798SS
| 1361 | 6 | 5.1.1.2.2.2 |  | Review draft artefact with Programme to ensure alignment with SIT | 10 July 2023 08:00 | 21 July 2023 17:00 |  | 799SS
| 1362 | 6 | 5.1.1.2.2.3 |  | Artefact review (via TMAG) and updates | 24 July 2023 08:00 | 13 September 2023 17:00 |  | 800SS
801 | 1363 | 6 | 5.1.1.2.2.4 | Tier 3 | Migration Testing elements of Qualification Approach & Plan approved by TMAG | 20 September 2023 17:00 | 20 September 2023 17:00 | 801 | 801SS
| 1364 | 6 | 5.1.1.2.2.5 | Tier 3 | Migration Testing elements of Qualification Approach & Plan approved by REC PAB | 25 July 2023 08:00 | 25 July 2023 08:00
| 1365 | 6 | 5.1.1.2.2.6 | Tier 3 | Migration Testing elements of Qualification Approach & Plan approved by BSC PAB | 27 July 2023 08:00 | 27 July 2023 08:00
| 1366 | 5 | 5.1.1.2.3 |  | Qualification Non-Functional Testing | 01 May 2023 08:00 | 30 November 2023 08:00
| 1367 | 6 | 5.1.1.2.3.1 |  | Develop Non-Functional Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 01 May 2023 08:00 | 29 August 2023 17:00 |  | 844SS
| 1368 | 6 | 5.1.1.2.3.2 |  | Review draft artefact with Programme to ensure alignment with SIT | 16 August 2023 08:00 | 29 August 2023 17:00 |  | 845SS
| 1369 | 6 | 5.1.1.2.3.3 |  | Artefact review (via TMAG) and updates | 30 August 2023 08:00 | 27 October 2023 17:00 |  | 846SS
847 | 1370 | 6 | 5.1.1.2.3.4 | Tier 3 | Non-Functional Testing elements of Qualification Approach & Plan approved by TMAG | 03 November 2023 17:00 | 03 November 2023 17:00 | 847 | 847SS
| 1371 | 6 | 5.1.1.2.3.5 | Tier 3 | Non-Functional Testing elements of Qualification Approach & Plan approved by REC PAB | 28 November 2023 08:00 | 28 November 2023 08:00
| 1372 | 6 | 5.1.1.2.3.6 | Tier 3 | Non-Functional Testing elements of Qualification Approach & Plan approved by BSC PAB | 30 November 2023 08:00 | 30 November 2023 08:00
| 1373 | 5 | 5.1.1.2.4 |  | Qualification Operational Testing | 01 June 2023 08:00 | 19 December 2023 08:00
| 1374 | 6 | 5.1.1.2.4.1 |  | Develop Operational Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 01 June 2023 08:00 | 29 September 2023 17:00 |  | 881SS
| 1375 | 6 | 5.1.1.2.4.2 |  | Review draft artefact with Programme to ensure alignment with SIT | 18 September 2023 08:00 | 29 September 2023 17:00 |  | 882SS
| 1376 | 6 | 5.1.1.2.4.3 |  | Artefact review (via TMAG) and updates | 02 October 2023 08:00 | 29 November 2023 17:00 |  | 883SS
884 | 1377 | 6 | 5.1.1.2.4.4 | Tier 3 | Final Qualification Approach & Plan approved by TMAG | 06 December 2023 17:00 | 06 December 2023 17:00 | 884 | 884SS
| 1378 | 6 | 5.1.1.2.4.5 | Tier 3 | Final Qualification Approach & Plan approved by REC PAB | 19 December 2023 08:00 | 19 December 2023 08:00
| 1379 | 6 | 5.1.1.2.4.6 | Tier 3 | Final Qualification Approach & Plan approved by BSC PAB | 14 December 2023 08:00 | 14 December 2023 08:00
| 1380 | 4 | 5.1.1.3 |  | Qualification Test Traceability Matrix | 03 January 2023 08:00 | 02 June 2023 17:00
| 1381 | 5 | 5.1.1.3.1 |  | Qualification Test Traceability Matrix (excl. Migration/Reverse Migration components) | 03 January 2023 08:00 | 03 April 2023 17:00
| 1382 | 6 | 5.1.1.3.1.1 |  | Develop document with QWG (excl Migration/Reverse Migration components) | 03 January 2023 08:00 | 20 March 2023 17:00
| 1383 | 6 | 5.1.1.3.1.2 |  | Review draft artefact with Programme to ensure alignment with SIT Overarching Test Traceability & Coverage, update and agree | 21 March 2023 08:00 | 03 April 2023 17:00 |  | 1382
| 1384 | 5 | 5.1.1.3.2 |  | Updated Qualification Test Traceability Matrix (incl. Migration/Reverse Migration components) | 01 May 2023 08:00 | 02 June 2023 17:00
| 1385 | 6 | 5.1.1.3.2.1 |  | Develop document with QWG (excl Migration/Reverse Migration components) | 01 May 2023 08:00 | 26 May 2023 17:00
| 1386 | 6 | 5.1.1.3.2.2 |  | Review draft artefact with Programme to ensure alignment with SIT Overarching Test Traceability & Coverage, update and agree | 29 May 2023 08:00 | 02 June 2023 17:00 |  | 1385
| 1387 | 3 | 5.1.2 |  | Qualification Test Tranche-Specific Preparation | 06 August 2024 08:00 | 30 June 2025 17:00
| 1388 | 4 | 5.1.2.1 |  | Tranche 1 Preparation | 06 August 2024 08:00 | 13 January 2025 17:00
| 1389 | 5 | 5.1.2.1.1 |  | SI Tranche 1 Preparation | 06 August 2024 08:00 | 13 January 2025 17:00
1615 | 1390 | 6 | 5.1.2.1.1.1 | Tier 3 | Confirm Qualification Testing Tranche 1 Participants | 06 August 2024 08:00 | 06 August 2024 08:00 | 1615 | 1615FS-6mo
| 1391 | 6 | 5.1.2.1.1.2 |  | Test execution schedule | 06 August 2024 08:00 | 04 November 2024 17:00
| 1392 | 7 | 5.1.2.1.1.2.1 |  | Develop document | 06 August 2024 08:00 | 30 September 2024 17:00 |  | 1390
| 1393 | 7 | 5.1.2.1.1.2.2 |  | Review & agree document | 01 October 2024 08:00 | 28 October 2024 17:00 |  | 1392
1393 | 1394 | 7 | 5.1.2.1.1.2.3 | Tier 3 | Qualification Testing Tranche 1 Test execution schedule approved | 04 November 2024 17:00 | 04 November 2024 17:00 | 1393 | 1393FS+5d
| 1395 | 6 | 5.1.2.1.1.3 |  | Environments | 06 August 2024 08:00 | 13 January 2025 17:00
| 1396 | 7 | 5.1.2.1.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 06 August 2024 08:00 | 28 October 2024 17:00 |  | 1390
| 1397 | 7 | 5.1.2.1.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 15 October 2024 08:00 | 28 October 2024 17:00 |  | 1396FF
1397 | 1398 | 7 | 5.1.2.1.1.3.3 | Tier 3 | Qualification Testing Tranche 1 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 04 November 2024 17:00 | 04 November 2024 17:00 | 1397 | 1397FS+5d
| 1399 | 7 | 5.1.2.1.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 05 November 2024 08:00 | 13 January 2025 17:00 |  | 1398
| 1400 | 7 | 5.1.2.1.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 05 November 2024 08:00 | 13 January 2025 17:00 |  | 1399SS
| 1401 | 6 | 5.1.2.1.1.4 |  | Test Data | 04 November 2024 17:00 | 04 November 2024 17:00
1398 | 1402 | 7 | 5.1.2.1.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 1 Participants) | 04 November 2024 17:00 | 04 November 2024 17:00 | 1398 | 1398
| 1403 | 6 | 5.1.2.1.1.5 |  | Other Preparation | 06 August 2024 08:00 | 13 January 2025 17:00
| 1404 | 7 | 5.1.2.1.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 06 August 2024 08:00 | 13 January 2025 17:00 |  | 1390
| 1405 | 7 | 5.1.2.1.1.5.2 |  | Other Preparation (activities TBC) | 06 August 2024 08:00 | 13 January 2025 17:00 |  | 1390
| 1406 | 6 | 5.1.2.1.1.6 | Tier 3 | Qualification Testing Tranche 1 Test Readiness confirmed | 13 January 2025 17:00 | 13 January 2025 17:00 | 0 | 1399,1404,1405
| 1407 | 5 | 5.1.2.1.2 |  | PP Tranche 1 Preparation | 06 August 2024 08:00 | 13 January 2025 17:00
1615 | 1408 | 6 | 5.1.2.1.2.1 | Tier 3 | Confirm Qualification Testing Tranche 1 Participants | 06 August 2024 08:00 | 06 August 2024 08:00 | 1615 | 1615FS-6mo
| 1409 | 6 | 5.1.2.1.2.2 |  | Environments | 06 August 2024 08:00 | 13 January 2025 17:00
| 1410 | 7 | 5.1.2.1.2.2.1 |  | UIT environment preparation | 06 August 2024 08:00 | 28 October 2024 17:00 |  | 1408
| 1411 | 7 | 5.1.2.1.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 15 October 2024 08:00 | 28 October 2024 17:00 |  | 1410FF
1411 | 1412 | 7 | 5.1.2.1.2.2.3 | Tier 3 | Qualification Testing Tranche 1 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 04 November 2024 17:00 | 04 November 2024 17:00 | 1411 | 1411FS+5d
| 1413 | 7 | 5.1.2.1.2.2.4 |  | UIT environment connectivity proving | 05 November 2024 08:00 | 13 January 2025 17:00 |  | 1412
| 1414 | 7 | 5.1.2.1.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 05 November 2024 08:00 | 13 January 2025 17:00 |  | 1413SS
| 1415 | 6 | 5.1.2.1.2.3 |  | Other Preparation | 06 August 2024 08:00 | 13 January 2025 17:00
| 1416 | 7 | 5.1.2.1.2.3.1 |  | Other Preparation (incl. test execution planning) | 06 August 2024 08:00 | 13 January 2025 17:00 |  | 1408
| 1417 | 6 | 5.1.2.1.2.4 |  | Monitoring of provisional Qualification Testing Tranche 1 Participants' PIT progress and test readiness | 06 August 2024 08:00 | 13 January 2025 17:00 |  | 1390
1413 | 1418 | 6 | 5.1.2.1.2.5 | Tier 3 | Qualification Testing Tranche 1 Test Readiness confirmed | 13 January 2025 17:00 | 13 January 2025 17:00 | 1413 | 1413FF
| 1419 | 4 | 5.1.2.2 |  | Tranche 2 Preparation | 03 September 2024 08:00 | 10 February 2025 17:00
| 1420 | 5 | 5.1.2.2.1 |  | SI Tranche 2 Preparation | 03 September 2024 08:00 | 10 February 2025 17:00
1620 | 1421 | 6 | 5.1.2.2.1.1 | Tier 3 | Confirm Qualification Testing Tranche 2 Participants | 03 September 2024 08:00 | 03 September 2024 08:00 | 1620 | 1620FS-6mo
| 1422 | 6 | 5.1.2.2.1.2 |  | Test execution schedule | 03 September 2024 08:00 | 02 December 2024 17:00
| 1423 | 7 | 5.1.2.2.1.2.1 |  | Develop document | 03 September 2024 08:00 | 28 October 2024 17:00 |  | 1421
| 1424 | 7 | 5.1.2.2.1.2.2 |  | Review & agree document | 29 October 2024 08:00 | 25 November 2024 17:00 |  | 1423
1424 | 1425 | 7 | 5.1.2.2.1.2.3 | Tier 3 | Qualification Testing Tranche 2 Test execution schedule approved | 02 December 2024 17:00 | 02 December 2024 17:00 | 1424 | 1424FS+5d
| 1426 | 6 | 5.1.2.2.1.3 |  | Environments | 03 September 2024 08:00 | 10 February 2025 17:00
| 1427 | 7 | 5.1.2.2.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 03 September 2024 08:00 | 25 November 2024 17:00 |  | 1421
| 1428 | 7 | 5.1.2.2.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 12 November 2024 08:00 | 25 November 2024 17:00 |  | 1427FF
1428 | 1429 | 7 | 5.1.2.2.1.3.3 | Tier 3 | Qualification Testing Tranche 2 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 02 December 2024 17:00 | 02 December 2024 17:00 | 1428 | 1428FS+5d
| 1430 | 7 | 5.1.2.2.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 03 December 2024 08:00 | 10 February 2025 17:00 |  | 1429
| 1431 | 7 | 5.1.2.2.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 03 December 2024 08:00 | 10 February 2025 17:00 |  | 1430SS
| 1432 | 6 | 5.1.2.2.1.4 |  | Test Data | 02 December 2024 17:00 | 02 December 2024 17:00
1429 | 1433 | 7 | 5.1.2.2.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 2 Participants) | 02 December 2024 17:00 | 02 December 2024 17:00 | 1429 | 1429
| 1434 | 6 | 5.1.2.2.1.5 |  | Other Preparation | 03 September 2024 08:00 | 10 February 2025 17:00
| 1435 | 7 | 5.1.2.2.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 03 September 2024 08:00 | 10 February 2025 17:00 |  | 1421
| 1436 | 7 | 5.1.2.2.1.5.2 |  | Other Preparation (activities TBC) | 03 September 2024 08:00 | 10 February 2025 17:00 |  | 1421
| 1437 | 6 | 5.1.2.2.1.6 |  | Monitoring of provisional Qualification Testing Tranche 2 Participants' PIT progress and test readiness
| 1438 | 6 | 5.1.2.2.1.7 | Tier 3 | Qualification Testing Tranche 2 Test Readiness confirmed | 10 February 2025 17:00 | 10 February 2025 17:00 | 0 | 1430,1435,1436
| 1439 | 5 | 5.1.2.2.2 |  | PP Tranche 2 Preparation | 03 September 2024 08:00 | 10 February 2025 17:00
1620 | 1440 | 6 | 5.1.2.2.2.1 | Tier 3 | Confirm Qualification Testing Tranche 2 Participants | 03 September 2024 08:00 | 03 September 2024 08:00 | 1620 | 1620FS-6mo
| 1441 | 6 | 5.1.2.2.2.2 |  | Environments | 03 September 2024 08:00 | 10 February 2025 17:00
| 1442 | 7 | 5.1.2.2.2.2.1 |  | UIT environment preparation | 03 September 2024 08:00 | 25 November 2024 17:00 |  | 1440
| 1443 | 7 | 5.1.2.2.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 12 November 2024 08:00 | 25 November 2024 17:00 |  | 1442FF
1443 | 1444 | 7 | 5.1.2.2.2.2.3 | Tier 3 | Qualification Testing Tranche 2 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 02 December 2024 17:00 | 02 December 2024 17:00 | 1443 | 1443FS+5d
| 1445 | 7 | 5.1.2.2.2.2.4 |  | UIT environment connectivity proving | 03 December 2024 08:00 | 10 February 2025 17:00 |  | 1444
| 1446 | 7 | 5.1.2.2.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 03 December 2024 08:00 | 10 February 2025 17:00 |  | 1445SS
| 1447 | 6 | 5.1.2.2.2.3 |  | Other Preparation | 03 September 2024 08:00 | 10 February 2025 17:00
| 1448 | 7 | 5.1.2.2.2.3.1 |  | Other Preparation (incl. test execution planning) | 03 September 2024 08:00 | 10 February 2025 17:00 |  | 1440
1445 | 1449 | 6 | 5.1.2.2.2.4 | Tier 3 | Qualification Testing Tranche 2 Test Readiness confirmed | 10 February 2025 17:00 | 10 February 2025 17:00 | 1445 | 1445FF
| 1450 | 4 | 5.1.2.3 |  | Tranche 3 Preparation | 01 October 2024 08:00 | 10 March 2025 17:00
| 1451 | 5 | 5.1.2.3.1 |  | SI Tranche 3 Preparation | 01 October 2024 08:00 | 10 March 2025 17:00
1625 | 1452 | 6 | 5.1.2.3.1.1 | Tier 3 | Confirm Qualification Testing Tranche 3 Participants | 01 October 2024 08:00 | 01 October 2024 08:00 | 1625 | 1625FS-6mo
| 1453 | 6 | 5.1.2.3.1.2 |  | Test execution schedule | 01 October 2024 08:00 | 30 December 2024 17:00
| 1454 | 7 | 5.1.2.3.1.2.1 |  | Develop document | 01 October 2024 08:00 | 25 November 2024 17:00 |  | 1452
| 1455 | 7 | 5.1.2.3.1.2.2 |  | Review & agree document | 26 November 2024 08:00 | 23 December 2024 17:00 |  | 1454
1455 | 1456 | 7 | 5.1.2.3.1.2.3 | Tier 3 | Qualification Testing Tranche 3 Test execution schedule approved | 30 December 2024 17:00 | 30 December 2024 17:00 | 1455 | 1455FS+5d
| 1457 | 6 | 5.1.2.3.1.3 |  | Environments | 01 October 2024 08:00 | 10 March 2025 17:00
| 1458 | 7 | 5.1.2.3.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 01 October 2024 08:00 | 23 December 2024 17:00 |  | 1452
| 1459 | 7 | 5.1.2.3.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 10 December 2024 08:00 | 23 December 2024 17:00 |  | 1458FF
1459 | 1460 | 7 | 5.1.2.3.1.3.3 | Tier 3 | Qualification Testing Tranche 3 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 30 December 2024 17:00 | 30 December 2024 17:00 | 1459 | 1459FS+5d
| 1461 | 7 | 5.1.2.3.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 31 December 2024 08:00 | 10 March 2025 17:00 |  | 1460
| 1462 | 7 | 5.1.2.3.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 31 December 2024 08:00 | 10 March 2025 17:00 |  | 1461SS
| 1463 | 6 | 5.1.2.3.1.4 |  | Test Data | 30 December 2024 17:00 | 30 December 2024 17:00
1460 | 1464 | 7 | 5.1.2.3.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 3 Participants) | 30 December 2024 17:00 | 30 December 2024 17:00 | 1460 | 1460
| 1465 | 6 | 5.1.2.3.1.5 |  | Other Preparation | 01 October 2024 08:00 | 10 March 2025 17:00
| 1466 | 7 | 5.1.2.3.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 01 October 2024 08:00 | 10 March 2025 17:00 |  | 1452
| 1467 | 7 | 5.1.2.3.1.5.2 |  | Other Preparation (activities TBC) | 01 October 2024 08:00 | 10 March 2025 17:00 |  | 1452
| 1468 | 6 | 5.1.2.3.1.6 |  | Monitoring of provisional Qualification Testing Tranche 3 Participants' PIT progress and test readiness
| 1469 | 6 | 5.1.2.3.1.7 | Tier 3 | Qualification Testing Tranche 3 Test Readiness confirmed | 10 March 2025 17:00 | 10 March 2025 17:00 | 0 | 1461,1466,1467
| 1470 | 5 | 5.1.2.3.2 |  | PP Tranche 3 Preparation | 01 October 2024 08:00 | 10 March 2025 17:00
1625 | 1471 | 6 | 5.1.2.3.2.1 | Tier 3 | Confirm Qualification Testing Tranche 3 Participants | 01 October 2024 08:00 | 01 October 2024 08:00 | 1625 | 1625FS-6mo
| 1472 | 6 | 5.1.2.3.2.2 |  | Environments | 01 October 2024 08:00 | 10 March 2025 17:00
| 1473 | 7 | 5.1.2.3.2.2.1 |  | UIT environment preparation | 01 October 2024 08:00 | 23 December 2024 17:00 |  | 1471
| 1474 | 7 | 5.1.2.3.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 10 December 2024 08:00 | 23 December 2024 17:00 |  | 1473FF
1474 | 1475 | 7 | 5.1.2.3.2.2.3 | Tier 3 | Qualification Testing Tranche 3 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 30 December 2024 17:00 | 30 December 2024 17:00 | 1474 | 1474FS+5d
| 1476 | 7 | 5.1.2.3.2.2.4 |  | UIT environment connectivity proving | 31 December 2024 08:00 | 10 March 2025 17:00 |  | 1475
| 1477 | 7 | 5.1.2.3.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 31 December 2024 08:00 | 10 March 2025 17:00 |  | 1476SS
| 1478 | 6 | 5.1.2.3.2.3 |  | Other Preparation | 01 October 2024 08:00 | 10 March 2025 17:00
| 1479 | 7 | 5.1.2.3.2.3.1 |  | Other Preparation (incl. test execution planning) | 01 October 2024 08:00 | 10 March 2025 17:00 |  | 1471
1476 | 1480 | 6 | 5.1.2.3.2.4 | Tier 3 | Qualification Testing Tranche 3 Test Readiness confirmed | 10 March 2025 17:00 | 10 March 2025 17:00 | 1476 | 1476FF
| 1481 | 4 | 5.1.2.4 |  | Tranche 4 Preparation | 29 October 2024 08:00 | 07 April 2025 17:00
| 1482 | 5 | 5.1.2.4.1 |  | SI Tranche 4 Preparation | 29 October 2024 08:00 | 07 April 2025 17:00
1630 | 1483 | 6 | 5.1.2.4.1.1 | Tier 3 | Confirm Qualification Testing Tranche 4 Participants | 29 October 2024 08:00 | 29 October 2024 08:00 | 1630 | 1630FS-6mo
| 1484 | 6 | 5.1.2.4.1.2 |  | Test execution schedule | 29 October 2024 08:00 | 27 January 2025 17:00
| 1485 | 7 | 5.1.2.4.1.2.1 |  | Develop document | 29 October 2024 08:00 | 23 December 2024 17:00 |  | 1483
| 1486 | 7 | 5.1.2.4.1.2.2 |  | Review & agree document | 24 December 2024 08:00 | 20 January 2025 17:00 |  | 1485
1486 | 1487 | 7 | 5.1.2.4.1.2.3 | Tier 3 | Qualification Testing Tranche 4 Test execution schedule approved | 27 January 2025 17:00 | 27 January 2025 17:00 | 1486 | 1486FS+5d
| 1488 | 6 | 5.1.2.4.1.3 |  | Environments | 29 October 2024 08:00 | 07 April 2025 17:00
| 1489 | 7 | 5.1.2.4.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 29 October 2024 08:00 | 20 January 2025 17:00 |  | 1483
| 1490 | 7 | 5.1.2.4.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 07 January 2025 08:00 | 20 January 2025 17:00 |  | 1489FF
1490 | 1491 | 7 | 5.1.2.4.1.3.3 | Tier 3 | Qualification Testing Tranche 4 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 27 January 2025 17:00 | 27 January 2025 17:00 | 1490 | 1490FS+5d
| 1492 | 7 | 5.1.2.4.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 28 January 2025 08:00 | 07 April 2025 17:00 |  | 1491
| 1493 | 7 | 5.1.2.4.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 28 January 2025 08:00 | 07 April 2025 17:00 |  | 1492SS
| 1494 | 6 | 5.1.2.4.1.4 |  | Test Data | 27 January 2025 17:00 | 27 January 2025 17:00
1491 | 1495 | 7 | 5.1.2.4.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 4 Participants) | 27 January 2025 17:00 | 27 January 2025 17:00 | 1491 | 1491
| 1496 | 6 | 5.1.2.4.1.5 |  | Other Preparation | 29 October 2024 08:00 | 07 April 2025 17:00
| 1497 | 7 | 5.1.2.4.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 29 October 2024 08:00 | 07 April 2025 17:00 |  | 1483
| 1498 | 7 | 5.1.2.4.1.5.2 |  | Other Preparation (activities TBC) | 29 October 2024 08:00 | 07 April 2025 17:00 |  | 1483
| 1499 | 6 | 5.1.2.4.1.6 |  | Monitoring of provisional Qualification Testing Tranche 4 Participants' PIT progress and test readiness
| 1500 | 6 | 5.1.2.4.1.7 | Tier 3 | Qualification Testing Tranche 4 Test Readiness confirmed | 07 April 2025 17:00 | 07 April 2025 17:00 | 0 | 1492,1497,1498
| 1501 | 5 | 5.1.2.4.2 |  | PP Tranche 4 Preparation | 29 October 2024 08:00 | 07 April 2025 17:00
1630 | 1502 | 6 | 5.1.2.4.2.1 | Tier 3 | Confirm Qualification Testing Tranche 4 Participants | 29 October 2024 08:00 | 29 October 2024 08:00 | 1630 | 1630FS-6mo
| 1503 | 6 | 5.1.2.4.2.2 |  | Environments | 29 October 2024 08:00 | 07 April 2025 17:00
| 1504 | 7 | 5.1.2.4.2.2.1 |  | UIT environment preparation | 29 October 2024 08:00 | 20 January 2025 17:00 |  | 1502
| 1505 | 7 | 5.1.2.4.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 07 January 2025 08:00 | 20 January 2025 17:00 |  | 1504FF
1505 | 1506 | 7 | 5.1.2.4.2.2.3 | Tier 3 | Qualification Testing Tranche 4 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 27 January 2025 17:00 | 27 January 2025 17:00 | 1505 | 1505FS+5d
| 1507 | 7 | 5.1.2.4.2.2.4 |  | UIT environment connectivity proving | 28 January 2025 08:00 | 07 April 2025 17:00 |  | 1506
| 1508 | 7 | 5.1.2.4.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 28 January 2025 08:00 | 07 April 2025 17:00 |  | 1507SS
| 1509 | 6 | 5.1.2.4.2.3 |  | Other Preparation | 29 October 2024 08:00 | 07 April 2025 17:00
| 1510 | 7 | 5.1.2.4.2.3.1 |  | Other Preparation (incl. test execution planning) | 29 October 2024 08:00 | 07 April 2025 17:00 |  | 1502
1507 | 1511 | 6 | 5.1.2.4.2.4 | Tier 3 | Qualification Testing Tranche 4 Test Readiness confirmed | 07 April 2025 17:00 | 07 April 2025 17:00 | 1507 | 1507FF
| 1512 | 4 | 5.1.2.5 |  | Tranche 5 Preparation | 26 November 2024 08:00 | 05 May 2025 17:00
| 1513 | 5 | 5.1.2.5.1 |  | SI Tranche 5 Preparation | 26 November 2024 08:00 | 05 May 2025 17:00
1635 | 1514 | 6 | 5.1.2.5.1.1 | Tier 3 | Confirm Qualification Testing Tranche 5 Participants | 26 November 2024 08:00 | 26 November 2024 08:00 | 1635 | 1635FS-6mo
| 1515 | 6 | 5.1.2.5.1.2 |  | Test execution schedule | 26 November 2024 08:00 | 24 February 2025 17:00
| 1516 | 7 | 5.1.2.5.1.2.1 |  | Develop document | 26 November 2024 08:00 | 20 January 2025 17:00 |  | 1514
| 1517 | 7 | 5.1.2.5.1.2.2 |  | Review & agree document | 21 January 2025 08:00 | 17 February 2025 17:00 |  | 1516
1517 | 1518 | 7 | 5.1.2.5.1.2.3 | Tier 3 | Qualification Testing Tranche 5 Test execution schedule approved | 24 February 2025 17:00 | 24 February 2025 17:00 | 1517 | 1517FS+5d
| 1519 | 6 | 5.1.2.5.1.3 |  | Environments | 26 November 2024 08:00 | 05 May 2025 17:00
| 1520 | 7 | 5.1.2.5.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 26 November 2024 08:00 | 17 February 2025 17:00 |  | 1514
| 1521 | 7 | 5.1.2.5.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 04 February 2025 08:00 | 17 February 2025 17:00 |  | 1520FF
1521 | 1522 | 7 | 5.1.2.5.1.3.3 | Tier 3 | Qualification Testing Tranche 5 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 24 February 2025 17:00 | 24 February 2025 17:00 | 1521 | 1521FS+5d
| 1523 | 7 | 5.1.2.5.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 25 February 2025 08:00 | 05 May 2025 17:00 |  | 1522
| 1524 | 7 | 5.1.2.5.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 25 February 2025 08:00 | 05 May 2025 17:00 |  | 1523SS
| 1525 | 6 | 5.1.2.5.1.4 |  | Test Data | 24 February 2025 17:00 | 24 February 2025 17:00
1522 | 1526 | 7 | 5.1.2.5.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 5 Participants) | 24 February 2025 17:00 | 24 February 2025 17:00 | 1522 | 1522
| 1527 | 6 | 5.1.2.5.1.5 |  | Other Preparation | 26 November 2024 08:00 | 05 May 2025 17:00
| 1528 | 7 | 5.1.2.5.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 26 November 2024 08:00 | 05 May 2025 17:00 |  | 1514
| 1529 | 7 | 5.1.2.5.1.5.2 |  | Other Preparation (activities TBC) | 26 November 2024 08:00 | 05 May 2025 17:00 |  | 1514
| 1530 | 6 | 5.1.2.5.1.6 |  | Monitoring of provisional Qualification Testing Tranche 5 Participants' PIT progress and test readiness
| 1531 | 6 | 5.1.2.5.1.7 | Tier 3 | Qualification Testing Tranche 5 Test Readiness confirmed | 05 May 2025 17:00 | 05 May 2025 17:00 | 0 | 1523,1528,1529
| 1532 | 5 | 5.1.2.5.2 |  | PP Tranche 5 Preparation | 26 November 2024 08:00 | 05 May 2025 17:00
1635 | 1533 | 6 | 5.1.2.5.2.1 | Tier 3 | Confirm Qualification Testing Tranche 5 Participants | 26 November 2024 08:00 | 26 November 2024 08:00 | 1635 | 1635FS-6mo
| 1534 | 6 | 5.1.2.5.2.2 |  | Environments | 26 November 2024 08:00 | 05 May 2025 17:00
| 1535 | 7 | 5.1.2.5.2.2.1 |  | UIT environment preparation | 26 November 2024 08:00 | 17 February 2025 17:00 |  | 1533
| 1536 | 7 | 5.1.2.5.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 04 February 2025 08:00 | 17 February 2025 17:00 |  | 1535FF
1536 | 1537 | 7 | 5.1.2.5.2.2.3 | Tier 3 | Qualification Testing Tranche 5 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 24 February 2025 17:00 | 24 February 2025 17:00 | 1536 | 1536FS+5d
| 1538 | 7 | 5.1.2.5.2.2.4 |  | UIT environment connectivity proving | 25 February 2025 08:00 | 05 May 2025 17:00 |  | 1537
| 1539 | 7 | 5.1.2.5.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 25 February 2025 08:00 | 05 May 2025 17:00 |  | 1538SS
| 1540 | 6 | 5.1.2.5.2.3 |  | Other Preparation | 26 November 2024 08:00 | 05 May 2025 17:00
| 1541 | 7 | 5.1.2.5.2.3.1 |  | Other Preparation (incl. test execution planning) | 26 November 2024 08:00 | 05 May 2025 17:00 |  | 1533
1538 | 1542 | 6 | 5.1.2.5.2.4 | Tier 3 | Qualification Testing Tranche 5 Test Readiness confirmed | 05 May 2025 17:00 | 05 May 2025 17:00 | 1538 | 1538FF
| 1543 | 4 | 5.1.2.6 |  | Tranche 6 Preparation | 24 December 2024 08:00 | 02 June 2025 17:00
| 1544 | 5 | 5.1.2.6.1 |  | SI Tranche 6 Preparation | 24 December 2024 08:00 | 02 June 2025 17:00
1640 | 1545 | 6 | 5.1.2.6.1.1 | Tier 3 | Confirm Qualification Testing Tranche 6 Participants | 24 December 2024 08:00 | 24 December 2024 08:00 | 1640 | 1640FS-6mo
| 1546 | 6 | 5.1.2.6.1.2 |  | Test execution schedule | 24 December 2024 08:00 | 24 March 2025 17:00
| 1547 | 7 | 5.1.2.6.1.2.1 |  | Develop document | 24 December 2024 08:00 | 17 February 2025 17:00 |  | 1545
| 1548 | 7 | 5.1.2.6.1.2.2 |  | Review & agree document | 18 February 2025 08:00 | 17 March 2025 17:00 |  | 1547
1548 | 1549 | 7 | 5.1.2.6.1.2.3 | Tier 3 | Qualification Testing Tranche 6 Test execution schedule approved | 24 March 2025 17:00 | 24 March 2025 17:00 | 1548 | 1548FS+5d
| 1550 | 6 | 5.1.2.6.1.3 |  | Environments | 24 December 2024 08:00 | 02 June 2025 17:00
| 1551 | 7 | 5.1.2.6.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 24 December 2024 08:00 | 17 March 2025 17:00 |  | 1545
| 1552 | 7 | 5.1.2.6.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 04 March 2025 08:00 | 17 March 2025 17:00 |  | 1551FF
1552 | 1553 | 7 | 5.1.2.6.1.3.3 | Tier 3 | Qualification Testing Tranche 6 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 24 March 2025 17:00 | 24 March 2025 17:00 | 1552 | 1552FS+5d
| 1554 | 7 | 5.1.2.6.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 25 March 2025 08:00 | 02 June 2025 17:00 |  | 1553
| 1555 | 7 | 5.1.2.6.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 25 March 2025 08:00 | 02 June 2025 17:00 |  | 1554SS
| 1556 | 6 | 5.1.2.6.1.4 |  | Test Data | 24 March 2025 17:00 | 24 March 2025 17:00
1553 | 1557 | 7 | 5.1.2.6.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 6 Participants) | 24 March 2025 17:00 | 24 March 2025 17:00 | 1553 | 1553
| 1558 | 6 | 5.1.2.6.1.5 |  | Other Preparation | 24 December 2024 08:00 | 02 June 2025 17:00
| 1559 | 7 | 5.1.2.6.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 24 December 2024 08:00 | 02 June 2025 17:00 |  | 1545
| 1560 | 7 | 5.1.2.6.1.5.2 |  | Other Preparation (activities TBC) | 24 December 2024 08:00 | 02 June 2025 17:00 |  | 1545
| 1561 | 6 | 5.1.2.6.1.6 |  | Monitoring of provisional Qualification Testing Tranche 6 Participants' PIT progress and test readiness
| 1562 | 6 | 5.1.2.6.1.7 | Tier 3 | Qualification Testing Tranche 6 Test Readiness confirmed | 02 June 2025 17:00 | 02 June 2025 17:00 | 0 | 1554,1559,1560
| 1563 | 5 | 5.1.2.6.2 |  | PP Tranche 6 Preparation | 24 December 2024 08:00 | 02 June 2025 17:00
1640 | 1564 | 6 | 5.1.2.6.2.1 | Tier 3 | Confirm Qualification Testing Tranche 6 Participants | 24 December 2024 08:00 | 24 December 2024 08:00 | 1640 | 1640FS-6mo
| 1565 | 6 | 5.1.2.6.2.2 |  | Environments | 24 December 2024 08:00 | 02 June 2025 17:00
| 1566 | 7 | 5.1.2.6.2.2.1 |  | UIT environment preparation | 24 December 2024 08:00 | 17 March 2025 17:00 |  | 1564
| 1567 | 7 | 5.1.2.6.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 04 March 2025 08:00 | 17 March 2025 17:00 |  | 1566FF
1567 | 1568 | 7 | 5.1.2.6.2.2.3 | Tier 3 | Qualification Testing Tranche 6 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 24 March 2025 17:00 | 24 March 2025 17:00 | 1567 | 1567FS+5d
| 1569 | 7 | 5.1.2.6.2.2.4 |  | UIT environment connectivity proving | 25 March 2025 08:00 | 02 June 2025 17:00 |  | 1568
| 1570 | 7 | 5.1.2.6.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 25 March 2025 08:00 | 02 June 2025 17:00 |  | 1569SS
| 1571 | 6 | 5.1.2.6.2.3 |  | Other Preparation | 24 December 2024 08:00 | 02 June 2025 17:00
| 1572 | 7 | 5.1.2.6.2.3.1 |  | Other Preparation (incl. test execution planning) | 24 December 2024 08:00 | 02 June 2025 17:00 |  | 1564
1569 | 1573 | 6 | 5.1.2.6.2.4 | Tier 3 | Qualification Testing Tranche 6 Test Readiness confirmed | 02 June 2025 17:00 | 02 June 2025 17:00 | 1569 | 1569FF
| 1574 | 4 | 5.1.2.7 |  | Tranche 7 Preparation | 21 January 2025 08:00 | 30 June 2025 17:00
| 1575 | 5 | 5.1.2.7.1 |  | SI Tranche 7 Preparation | 21 January 2025 08:00 | 30 June 2025 17:00
1645 | 1576 | 6 | 5.1.2.7.1.1 | Tier 3 | Confirm Qualification Testing Tranche 7 Participants | 21 January 2025 08:00 | 21 January 2025 08:00 | 1645 | 1645FS-6mo
| 1577 | 6 | 5.1.2.7.1.2 |  | Test execution schedule | 21 January 2025 08:00 | 21 April 2025 17:00
| 1578 | 7 | 5.1.2.7.1.2.1 |  | Develop document | 21 January 2025 08:00 | 17 March 2025 17:00 |  | 1576
| 1579 | 7 | 5.1.2.7.1.2.2 |  | Review & agree document | 18 March 2025 08:00 | 14 April 2025 17:00 |  | 1578
1579 | 1580 | 7 | 5.1.2.7.1.2.3 | Tier 3 | Qualification Testing Tranche 7 Test execution schedule approved | 21 April 2025 17:00 | 21 April 2025 17:00 | 1579 | 1579FS+5d
| 1581 | 6 | 5.1.2.7.1.3 |  | Environments | 21 January 2025 08:00 | 30 June 2025 17:00
| 1582 | 7 | 5.1.2.7.1.3.1 |  | Coordinate Qualification Participants' environment preparation | 21 January 2025 08:00 | 14 April 2025 17:00 |  | 1576
| 1583 | 7 | 5.1.2.7.1.3.2 |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 01 April 2025 08:00 | 14 April 2025 17:00 |  | 1582FF
1583 | 1584 | 7 | 5.1.2.7.1.3.3 | Tier 3 | Qualification Testing Tranche 7 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 21 April 2025 17:00 | 21 April 2025 17:00 | 1583 | 1583FS+5d
| 1585 | 7 | 5.1.2.7.1.3.4 |  | Coordinate Qualification Participants' connectivity proving | 22 April 2025 08:00 | 30 June 2025 17:00 |  | 1584
| 1586 | 7 | 5.1.2.7.1.3.5 |  | Assurance of Qualification Participants' connectivity proving | 22 April 2025 08:00 | 30 June 2025 17:00 |  | 1585SS
| 1587 | 6 | 5.1.2.7.1.4 |  | Test Data | 21 April 2025 17:00 | 21 April 2025 17:00
1584 | 1588 | 7 | 5.1.2.7.1.4.1 | Tier 3 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 7 Participants) | 21 April 2025 17:00 | 21 April 2025 17:00 | 1584 | 1584
| 1589 | 6 | 5.1.2.7.1.5 |  | Other Preparation | 21 January 2025 08:00 | 30 June 2025 17:00
| 1590 | 7 | 5.1.2.7.1.5.1 |  | Onboarding of Test Participants to Test Management Tool | 21 January 2025 08:00 | 30 June 2025 17:00 |  | 1576
| 1591 | 7 | 5.1.2.7.1.5.2 |  | Other Preparation (activities TBC) | 21 January 2025 08:00 | 30 June 2025 17:00 |  | 1576
| 1592 | 6 | 5.1.2.7.1.6 |  | Monitoring of provisional Qualification Testing Tranche 7 Participants' PIT progress and test readiness
| 1593 | 6 | 5.1.2.7.1.7 | Tier 3 | Qualification Testing Tranche 7 Test Readiness confirmed | 30 June 2025 17:00 | 30 June 2025 17:00 | 0 | 1585,1590,1591
| 1594 | 5 | 5.1.2.7.2 |  | PP Tranche 7 Preparation | 21 January 2025 08:00 | 30 June 2025 17:00
1645 | 1595 | 6 | 5.1.2.7.2.1 | Tier 3 | Confirm Qualification Testing Tranche 7 Participants | 21 January 2025 08:00 | 21 January 2025 08:00 | 1645 | 1645FS-6mo
| 1596 | 6 | 5.1.2.7.2.2 |  | Environments | 21 January 2025 08:00 | 30 June 2025 17:00
| 1597 | 7 | 5.1.2.7.2.2.1 |  | UIT environment preparation | 21 January 2025 08:00 | 14 April 2025 17:00 |  | 1595
| 1598 | 7 | 5.1.2.7.2.2.2 |  | Deployment of MHHS solution code to UIT environments | 01 April 2025 08:00 | 14 April 2025 17:00 |  | 1597FF
1598 | 1599 | 7 | 5.1.2.7.2.2.3 | Tier 3 | Qualification Testing Tranche 7 Participants' UIT environments ready to start connectivity proving (incl certificates and security compliance) | 21 April 2025 17:00 | 21 April 2025 17:00 | 1598 | 1598FS+5d
| 1600 | 7 | 5.1.2.7.2.2.4 |  | UIT environment connectivity proving | 22 April 2025 08:00 | 30 June 2025 17:00 |  | 1599
| 1601 | 7 | 5.1.2.7.2.2.5 |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 22 April 2025 08:00 | 30 June 2025 17:00 |  | 1600SS
| 1602 | 6 | 5.1.2.7.2.3 |  | Other Preparation | 21 January 2025 08:00 | 30 June 2025 17:00
| 1603 | 7 | 5.1.2.7.2.3.1 |  | Other Preparation (incl. test execution planning) | 21 January 2025 08:00 | 30 June 2025 17:00 |  | 1595
1600 | 1604 | 6 | 5.1.2.7.2.4 | Tier 3 | Qualification Testing Tranche 7 Test Readiness confirmed | 30 June 2025 17:00 | 30 June 2025 17:00 | 1600 | 1600FF
| 1605 | 2 | 5.2 |  | Qualification Assessment Document (QAD) Process | 19 February 2024 08:00 | 19 January 2026 17:00
| 1606 | 3 | 5.2.1 |  | Qualification Assessment Document final review and approval by BSC PAB and REC PAB | 19 February 2024 08:00 | 29 March 2024 17:00
1606 | 1607 | 3 | 5.2.2 | Tier 3 | Qualification Assessment Document Baselined | 29 March 2024 17:00 | 29 March 2024 17:00 | 1606 | 1606
| 1608 | 3 | 5.2.3 |  | PPs complete Qualification Assessment Document process | 04 April 2024 08:00 | 19 January 2026 17:00 |  | 1764FF-2mo,1607FS+3d
| 1609 | 3 | 5.2.4 |  | Qualification Assessment Document process monitoring | 04 April 2024 08:00 | 19 January 2026 17:00 |  | 1764FF-2mo,1607FS+3d
| 1610 | 2 | 5.3 |  | PAB Support | 26 November 2024 08:00 | 16 March 2026 17:00
| 1611 | 3 | 5.3.1 |  | Support PAB in Qualification setup, monitroing & reporting | 26 November 2024 08:00 | 20 January 2025 17:00 |  | 1615FS-40d
| 1612 | 3 | 5.3.2 |  | Support PAB throughout Qualification | 21 January 2025 08:00 | 16 March 2026 17:00 |  | 1615SS
| 1613 | 2 | 5.4 |  | Qualification Testing Execution & PAB Approval (test execution schedule subject to Qualification Approach & Plan) | 20 January 2025 17:00 | 16 March 2026 17:00
| 1614 | 3 | 5.4.1 |  | Qualification Testing Tranche 1 | 20 January 2025 17:00 | 29 September 2025 17:00
998F | 1615 | 4 | 5.4.1.1 | Tier 3 | Qualification Testing Tranche 1 Start | 20 January 2025 17:00 | 20 January 2025 17:00 | 998F | 998FS+1d
1615 | 1616 | 4 | 5.4.1.2 | Tier 3 | Qualification Testing Tranche 1 End | 04 August 2025 17:00 | 04 August 2025 17:00 | 1615 | 1615FS+140d
1616 | 1617 | 4 | 5.4.1.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 1 Completion | 01 September 2025 17:00 | 01 September 2025 17:00 | 1616 | 1616FS+20d
| 1618 | 4 | 5.4.1.4 |  | Qualification Testing Tranche 1 Participants mobilise production environments | 05 August 2025 08:00 | 29 September 2025 17:00 |  | 1616
| 1619 | 3 | 5.4.2 |  | Qualification Testing Tranche 2 | 17 February 2025 17:00 | 27 October 2025 17:00
1615 | 1620 | 4 | 5.4.2.1 | Tier 3 | Qualification Testing Tranche 2 Start | 17 February 2025 17:00 | 17 February 2025 17:00 | 1615 | 1615SS+20d
1620 | 1621 | 4 | 5.4.2.2 | Tier 3 | Qualification Testing Tranche 2 End | 01 September 2025 17:00 | 01 September 2025 17:00 | 1620 | 1620FS+140d
1621 | 1622 | 4 | 5.4.2.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 2 Completion | 29 September 2025 17:00 | 29 September 2025 17:00 | 1621 | 1621FS+20d
| 1623 | 4 | 5.4.2.4 |  | Qualification Testing Tranche 2 Participants mobilise production environments | 02 September 2025 08:00 | 27 October 2025 17:00 |  | 1621
| 1624 | 3 | 5.4.3 |  | Qualification Testing Tranche 3 | 17 March 2025 17:00 | 24 November 2025 17:00
1620 | 1625 | 4 | 5.4.3.1 | Tier 3 | Qualification Testing Tranche 3 Start | 17 March 2025 17:00 | 17 March 2025 17:00 | 1620 | 1620SS+20d
1625 | 1626 | 4 | 5.4.3.2 | Tier 3 | Qualification Testing Tranche 3 End | 29 September 2025 17:00 | 29 September 2025 17:00 | 1625 | 1625FS+140d
1626 | 1627 | 4 | 5.4.3.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 3 Completion | 27 October 2025 17:00 | 27 October 2025 17:00 | 1626 | 1626FS+20d
| 1628 | 4 | 5.4.3.4 |  | Qualification Testing Tranche 3 Participants mobilise production environments | 30 September 2025 08:00 | 24 November 2025 17:00 |  | 1626
| 1629 | 3 | 5.4.4 |  | Qualification Testing Tranche 4 | 14 April 2025 17:00 | 22 December 2025 17:00
1625 | 1630 | 4 | 5.4.4.1 | Tier 3 | Qualification Testing Tranche 4 Start | 14 April 2025 17:00 | 14 April 2025 17:00 | 1625 | 1625SS+20d
1630 | 1631 | 4 | 5.4.4.2 | Tier 3 | Qualification Testing Tranche 4 End | 27 October 2025 17:00 | 27 October 2025 17:00 | 1630 | 1630FS+140d
1631 | 1632 | 4 | 5.4.4.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 4 Completion | 24 November 2025 17:00 | 24 November 2025 17:00 | 1631 | 1631FS+20d
| 1633 | 4 | 5.4.4.4 |  | Qualification Testing Tranche 4 Participants mobilise production environments | 28 October 2025 08:00 | 22 December 2025 17:00 |  | 1631
| 1634 | 3 | 5.4.5 |  | Qualification Testing Tranche 5 | 12 May 2025 17:00 | 19 January 2026 17:00
1630 | 1635 | 4 | 5.4.5.1 | Tier 3 | Qualification Testing Tranche 5 Start | 12 May 2025 17:00 | 12 May 2025 17:00 | 1630 | 1630SS+20d
1635 | 1636 | 4 | 5.4.5.2 | Tier 3 | Qualification Testing Tranche 5 End | 24 November 2025 17:00 | 24 November 2025 17:00 | 1635 | 1635FS+140d
1636 | 1637 | 4 | 5.4.5.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 5 Completion | 22 December 2025 17:00 | 22 December 2025 17:00 | 1636 | 1636FS+20d
| 1638 | 4 | 5.4.5.4 |  | Qualification Testing Tranche 5 Participants mobilise production environments | 25 November 2025 08:00 | 19 January 2026 17:00 |  | 1636
| 1639 | 3 | 5.4.6 |  | Qualification Testing Tranche 6 | 09 June 2025 17:00 | 16 February 2026 17:00
1635 | 1640 | 4 | 5.4.6.1 | Tier 3 | Qualification Testing Tranche 6 Start | 09 June 2025 17:00 | 09 June 2025 17:00 | 1635 | 1635SS+20d
1640 | 1641 | 4 | 5.4.6.2 | Tier 3 | Qualification Testing Tranche 6 End | 22 December 2025 17:00 | 22 December 2025 17:00 | 1640 | 1640FS+140d
1641 | 1642 | 4 | 5.4.6.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 6 Completion | 19 January 2026 17:00 | 19 January 2026 17:00 | 1641 | 1641FS+20d
| 1643 | 4 | 5.4.6.4 |  | Qualification Testing Tranche 6 Participants mobilise production environments | 23 December 2025 08:00 | 16 February 2026 17:00 |  | 1641
| 1644 | 3 | 5.4.7 |  | Qualification Testing Tranche 7 | 07 July 2025 17:00 | 16 March 2026 17:00
1640 | 1645 | 4 | 5.4.7.1 | Tier 3 | Qualification Testing Tranche 7 Start | 07 July 2025 17:00 | 07 July 2025 17:00 | 1640 | 1640SS+20d
1645 | 1646 | 4 | 5.4.7.2 | Tier 3 | Qualification Testing Tranche 7 End | 19 January 2026 17:00 | 19 January 2026 17:00 | 1645 | 1645FS+140d
1646 | 1647 | 4 | 5.4.7.3 | Tier 2 | BSC PAB & REC Manager approval of Qualification Testing Tranche 7 Completion | 16 February 2026 17:00 | 16 February 2026 17:00 | 1646 | 1646FS+20d
| 1648 | 4 | 5.4.7.4 |  | Qualification Testing Tranche 7 Participants mobilise production environments | 20 January 2026 08:00 | 16 March 2026 17:00 |  | 1646
| 1649 | 3 | 5.4.8 |  | Qualification Testing Monitoring | 21 January 2025 08:00 | 19 January 2026 17:00
| 1650 | 2 | 5.5 |  | BSC PAB & REC Manager sign-off of qualified SIT participants for Migration | 14 March 2025 17:00 | 14 March 2025 17:00
1337 | 1651 | 3 | 5.5.1 | Tier 2 | BSC PAB & REC Manager sign-off of qualified SIT participants for Migration (post-M8 & pre-M11) | 14 March 2025 17:00 | 14 March 2025 17:00 | 1337 | 1337FS+5d
| 1652 | 2 | 5.6 |  | Qualification PPs E2E Sandbox Execution | 05 August 2025 08:00 | 31 December 2026 17:00
| 1653 | 3 | 5.6.1 |  | Qualification PPs E2E Sandbox Testing Execution | 05 August 2025 08:00 | 31 December 2026 17:00 |  | 1118,1616
| 1654 | 1 | 6 |  | MIGRATION | 31 October 2022 08:00 | 28 December 2026 17:00
| 1655 | 2 | 6.1 |  | Migration Artefact Development and Publication | 31 October 2022 08:00 | 04 April 2025 17:00
| 1656 | 3 | 6.1.1 |  | Migration Approach | 31 October 2022 08:00 | 07 December 2022 17:00
| 1657 | 4 | 6.1.1.1 |  | Option analysis (via MWG and PPIR) and recommendation | 31 October 2022 08:00 | 30 November 2022 17:00
1657 | 1658 | 4 | 6.1.1.2 | Tier 3 | Migration Approach approved | 07 December 2022 17:00 | 07 December 2022 17:00 | 1657 | 1657FS+5d
| 1659 | 3 | 6.1.2 |  | Migration Design | 14 November 2022 08:00 | 31 March 2023 17:00
| 1660 | 4 | 6.1.2.1 |  | Review and update existing design artefacts and socialise with participants ahead of MDSG | 14 November 2022 08:00 | 25 November 2022 17:00
| 1661 | 4 | 6.1.2.2 |  | Develop design artefacts and supporting technical documents in line with MDSG | 30 November 2022 08:00 | 10 February 2023 17:00 |  | 1660FS+2d
1661 | 1662 | 4 | 6.1.2.3 | Tier 3 | Migration design artefacts issued for consultation | 13 February 2023 17:00 | 13 February 2023 17:00 | 1661 | 1661FS+1d
| 1663 | 4 | 6.1.2.4 |  | Industry consultation | 14 February 2023 08:00 | 20 February 2023 17:00 |  | 1662SS
| 1664 | 4 | 6.1.2.5 |  | Review consultation feedback, address comments and update artefacts | 21 February 2023 08:00 | 27 February 2023 17:00 |  | 1663
| 1665 | 4 | 6.1.2.6 |  | Internal artefact review and comms preparation | 28 February 2023 08:00 | 02 March 2023 17:00 |  | 1664
1665 | 1666 | 4 | 6.1.2.7 | Tier 3 | Updated Migration Design artefacts issued to PPs for assurance review | 03 March 2023 17:00 | 03 March 2023 17:00 | 1665 | 1665FS+1d
| 1667 | 4 | 6.1.2.8 |  | Final Migration Design artefacts walkthrough with PPs | 22 March 2023 17:00 | 22 March 2023 17:00 |  | 1666FS+13d
1667 | 1668 | 4 | 6.1.2.9 | Tier 2 | Migration Design approved | 31 March 2023 17:00 | 31 March 2023 17:00 | 1667 | 1667FS+7d
| 1669 | 3 | 6.1.3 |  | Transition Design | 01 March 2023 08:00 | 03 August 2023 17:00
| 1670 | 4 | 6.1.3.1 |  | Tranche 1 | 01 March 2023 08:00 | 17 May 2023 17:00
| 1671 | 5 | 6.1.3.1.1 |  | Develop design artefacts and supporting technical details with participants | 01 March 2023 08:00 | 09 May 2023 17:00
| 1672 | 5 | 6.1.3.1.2 |  | Issue Material for DAG approval | 10 May 2023 08:00 | 10 May 2023 17:00 |  | 1671
1672 | 1673 | 5 | 6.1.3.1.3 | Tier 2 | Tranche 1 Transition Design approved | 17 May 2023 17:00 | 17 May 2023 17:00 | 1672 | 1672FS+5d
| 1674 | 4 | 6.1.3.2 |  | Tranche 2 | 18 May 2023 08:00 | 03 August 2023 17:00
| 1675 | 5 | 6.1.3.2.1 |  | Develop design artefacts and supporting technical details with participants | 18 May 2023 08:00 | 26 July 2023 17:00 |  | 1673
| 1676 | 5 | 6.1.3.2.2 |  | Issue Material for DAG approval | 27 July 2023 08:00 | 27 July 2023 17:00 |  | 1675
1676 | 1677 | 5 | 6.1.3.2.3 | Tier 2 | Tranche 2 Transition Design approved | 03 August 2023 17:00 | 03 August 2023 17:00 | 1676 | 1676FS+5d
| 1678 | 3 | 6.1.4 |  | Data Assessment Report | 06 December 2022 08:00 | 28 February 2023 17:00
| 1679 | 4 | 6.1.4.1 |  | Develop document with MWG | 06 December 2022 08:00 | 10 February 2023 17:00
| 1680 | 4 | 6.1.4.2 |  | Artefact review (via TMAG) and updates | 18 January 2023 08:00 | 21 February 2023 17:00 |  | 1679FS-18d
1680 | 1681 | 4 | 6.1.4.3 | Tier 3 | Data Assessment Report approved | 28 February 2023 17:00 | 28 February 2023 17:00 | 1680 | 1680FS+5d
| 1682 | 3 | 6.1.5 |  | Migration, Cutover & Data Strategy (incl. Migration Entry Criteria) | 08 December 2022 08:00 | 28 April 2023 17:00 |  | 1656
| 1683 | 4 | 6.1.5.1 |  | Develop document with MWG | 08 December 2022 08:00 | 10 March 2023 17:00 |  | 1658
| 1684 | 4 | 6.1.5.2 |  | Artefact review (via TMAG) and updates | 15 March 2023 08:00 | 21 April 2023 17:00 |  | 1683FS+2d
1684 | 1685 | 4 | 6.1.5.3 | Tier 3 | Migration, Cutover & Data Strategy approved | 28 April 2023 17:00 | 28 April 2023 17:00 | 1684 | 1684FF+5d
| 1686 | 3 | 6.1.6 |  | Data Cleanse Plan | 02 March 2023 08:00 | 04 April 2025 17:00
| 1687 | 4 | 6.1.6.1 |  | Develop document with MWG | 02 March 2023 08:00 | 10 May 2023 17:00
| 1688 | 4 | 6.1.6.2 |  | Artefact review (via TMAG) and updates | 11 May 2023 08:00 | 07 June 2023 17:00 |  | 1687
1688 | 1689 | 4 | 6.1.6.3 | Tier 3 | Data Cleanse Plan approved | 14 June 2023 17:00 | 14 June 2023 17:00 | 1688 | 1688FS+5d
| 1690 | 4 | 6.1.6.4 |  | Monitor Programme Participant adherence to Data Cleanse Plan | 15 June 2023 08:00 | 28 March 2025 17:00 |  | 1689
| 1691 | 4 | 6.1.6.5 | Tier 2 | Pre-migration data cleanse complete | 04 April 2025 17:00 | 04 April 2025 17:00 | 0 | 1760FS-20d,1762FS-20d,1690FS+5d
| 1692 | 2 | 6.2 |  | Migration Period Planning | 01 May 2023 08:00 | 31 October 2025 17:00
| 1693 | 3 | 6.2.1 |  | Migration Implementation Plan (incl. Migration Exit Criteria) | 01 May 2023 08:00 | 26 April 2024 17:00
| 1694 | 4 | 6.2.1.1 |  | Develop document | 01 May 2023 08:00 | 02 February 2024 17:00 |  | 1685
| 1695 | 4 | 6.2.1.2 |  | Review & agree document | 05 February 2024 08:00 | 19 April 2024 17:00 |  | 1694
1695 | 1696 | 4 | 6.2.1.3 | Tier 3 | Migration Implementation Plan approved | 26 April 2024 17:00 | 26 April 2024 17:00 | 1695 | 1695FS+5d
| 1697 | 3 | 6.2.2 |  | Migration Processes & Procedures | 29 April 2024 08:00 | 20 December 2024 17:00
| 1698 | 4 | 6.2.2.1 |  | Develop document | 29 April 2024 08:00 | 30 August 2024 17:00 |  | 1696
| 1699 | 4 | 6.2.2.2 |  | Review & agree document | 02 September 2024 08:00 | 13 December 2024 17:00 |  | 1698
1699 | 1700 | 4 | 6.2.2.3 | Tier 3 | Migration Processes & Procedures approved | 20 December 2024 17:00 | 20 December 2024 17:00 | 1699 | 1699FF+5d
| 1701 | 3 | 6.2.3 |  | Migration Period Plan Review | 04 October 2024 08:00 | 31 October 2025 17:00
| 1702 | 4 | 6.2.3.1 |  | Review 1 | 04 October 2024 08:00 | 31 October 2024 17:00
| 1703 | 5 | 6.2.3.1.1 |  | Consult PPs to validate migration timelines (incl. revisions where necessary) | 04 October 2024 08:00 | 24 October 2024 17:00 |  | 1760FS-131d,1762FS-131d
1703 | 1704 | 5 | 6.2.3.1.2 | Tier 3 | Migration Period Plan Review 1 Completed | 31 October 2024 17:00 | 31 October 2024 17:00 | 1703 | 1703FS+5d
| 1705 | 4 | 6.2.3.2 |  | Review 2 | 04 July 2025 08:00 | 31 July 2025 17:00
| 1706 | 5 | 6.2.3.2.1 |  | Consult PPs to validate migration timelines (incl. revisions where necessary) | 04 July 2025 08:00 | 24 July 2025 17:00 |  | 1760FS+64d,1762FS+64d
1706 | 1707 | 5 | 6.2.3.2.2 | Tier 3 | Migration Period Plan Review 2 Completed | 31 July 2025 17:00 | 31 July 2025 17:00 | 1706 | 1706FS+5d
| 1708 | 4 | 6.2.3.3 |  | Review 3 | 06 October 2025 08:00 | 31 October 2025 17:00
| 1709 | 5 | 6.2.3.3.1 |  | Consult PPs to validate migration timelines (incl. revisions where necessary) | 06 October 2025 08:00 | 24 October 2025 17:00 |  | 1760FS+130d,1762FS+130d
1709 | 1710 | 5 | 6.2.3.3.2 | Tier 3 | Migration Period Plan Review 3 Completed | 31 October 2025 17:00 | 31 October 2025 17:00 | 1709 | 1709FS+5d
| 1711 | 3 | 6.2.4 |  | Other Migration preparation and document refinement (where required) | 23 December 2024 08:00 | 22 May 2025 17:00 |  | 1697
| 1712 | 2 | 6.3 |  | Go-Live Dress Rehearsals | 04 October 2024 08:00 | 06 March 2025 17:00
| 1713 | 3 | 6.3.1 |  | Define dress rehearsal scenarios (incl. engagement with MWG) | 04 October 2024 08:00 | 31 October 2024 17:00 |  | 1760FS-131d,1762FS-131d
| 1714 | 3 | 6.3.2 |  | Set up, coordinate and conduct dress rehearsals | 07 February 2025 08:00 | 20 February 2025 17:00 |  | 1029
| 1715 | 3 | 6.3.3 |  | Evaludate dress rehearsals and identify lessons learned | 21 February 2025 08:00 | 06 March 2025 17:00 |  | 1714
| 1716 | 2 | 6.4 |  | Preparation for Cutover to Live | 07 February 2025 08:00 | 04 April 2025 17:00
| 1717 | 3 | 6.4.1 |  | Central Systems Prepare for Cutover to Live | 07 February 2025 08:00 | 07 March 2025 17:00
| 1718 | 4 | 6.4.1.1 |  | Central Systems Prepare for Cutover to Live | 07 February 2025 08:00 | 07 March 2025 17:00 |  | 1756FF,1199
| 1719 | 3 | 6.4.2 |  | Advanced & UMS Prepare for Cutover to Live | 07 February 2025 08:00 | 04 April 2025 17:00
| 1720 | 4 | 6.4.2.1 |  | Advanced & UMS Prepare for Cutover to Live | 07 February 2025 08:00 | 04 April 2025 17:00 |  | 1199,1760FF
| 1721 | 3 | 6.4.3 |  | Smart/Non-Smart Prepare for Cutover to Live | 07 February 2025 08:00 | 04 April 2025 17:00
| 1722 | 4 | 6.4.3.1 |  | Smart/Non-Smart Prepare for Cutover to Live | 07 February 2025 08:00 | 04 April 2025 17:00 |  | 1199,1762FF
| 1723 | 2 | 6.5 |  | Migration of Advanced Segment | 07 April 2025 08:00 | 05 October 2026 17:00
| 1724 | 3 | 6.5.1 |  | Migration of Advanced Segment (SIT MVC) | 07 April 2025 08:00 | 05 October 2026 17:00 |  | 1760
| 1725 | 3 | 6.5.2 |  | Migration of Advanced Segment (non-SIT PPs) | 30 September 2025 08:00 | 05 October 2026 17:00 |  | 1120,1618
| 1726 | 2 | 6.6 |  | Migration of Unmetered Segment | 07 April 2025 08:00 | 05 October 2026 17:00
| 1727 | 3 | 6.6.1 |  | Migration of Unmetered Segment (SIT MVC) | 07 April 2025 08:00 | 05 October 2026 17:00 |  | 1760
| 1728 | 3 | 6.6.2 |  | Migration of Unmetered Segment (non-SIT PPs) | 30 September 2025 08:00 | 05 October 2026 17:00 |  | 1120,1618
| 1729 | 2 | 6.7 |  | Migration of Smart / Non-Smart Segments | 07 April 2025 08:00 | 05 October 2026 17:00
| 1730 | 3 | 6.7.1 |  | Migration of Smart / Non-Smart Segments (SIT MVC) | 07 April 2025 08:00 | 05 October 2026 17:00 |  | 1760
| 1731 | 3 | 6.7.2 |  | Migration of Smart / Non-Smart Segments (non-SIT PPs) | 30 September 2025 08:00 | 05 October 2026 17:00 |  | 1120,1618
| 1732 | 2 | 6.8 |  | Migration Management | 07 April 2025 08:00 | 05 October 2026 17:00
| 1733 | 3 | 6.8.1 |  | Migration Management | 07 April 2025 08:00 | 05 October 2026 17:00 |  | 1724SS,1727SS,1730SS
| 1734 | 2 | 6.9 |  | External Programme Dependency Management | 31 October 2022 08:00 | 01 July 2025 17:00
| 1735 | 3 | 6.9.1 |  | BSC CP1558 | 31 October 2022 08:00 | 24 June 2025 17:00
| 1736 | 4 | 6.9.1.1 |  | Preparation for data population and data cleansing | 31 October 2022 08:00 | 29 June 2023 17:00 |  | 1190FF
| 1737 | 4 | 6.9.1.2 |  | Data population and data cleansing | 30 June 2023 08:00 | 24 June 2025 17:00 |  | 1190,1736
| 1738 | 3 | 6.9.2 |  | REC CP R0032 | 31 October 2022 08:00 | 30 May 2025 17:00
| 1739 | 4 | 6.9.2.1 |  | Preparation for data population and data cleansing | 31 October 2022 08:00 | 30 June 2023 17:00 |  | 1193FF
| 1740 | 4 | 6.9.2.2 |  | Data population and data cleansing | 03 July 2023 08:00 | 30 May 2025 17:00 |  | 1193,1739
| 1741 | 3 | 6.9.3 |  | BSC Mod P432 & REC CP R0015 | 31 October 2022 08:00 | 01 July 2025 17:00
| 1742 | 4 | 6.9.3.1 |  | MHHSP engagement with BSCCo until Ofgem decision | 31 October 2022 08:00 | 30 December 2022 17:00
| 1743 | 4 | 6.9.3.2 |  | Monitor progress and await implementation date | 02 January 2023 08:00 | 01 July 2025 17:00 |  | 1742
| 1744 | 3 | 6.9.4 |  | BSC Mod P434 | 31 October 2022 08:00 | 01 July 2025 17:00
| 1745 | 4 | 6.9.4.1 |  | MHHSP engagement with BSCCo until Ofgem decision | 31 October 2022 08:00 | 30 December 2022 17:00
| 1746 | 4 | 6.9.4.2 |  | Monitor progress and await implementation date | 02 January 2023 08:00 | 01 July 2025 17:00 |  | 1745
| 1747 | 3 | 6.9.5 |  | Elexon System Capacity Upgrade | 31 October 2022 08:00 | 01 July 2025 17:00
| 1748 | 4 | 6.9.5.1 |  | Monitor progress to implementation | 31 October 2022 08:00 | 01 July 2025 17:00
| 1749 | 4 | 6.9.5.2 |  | Implementation date | 01 July 2025 17:00 | 01 July 2025 17:00 |  | 1748
| 1750 | 3 | 6.9.6 |  | DCC System Capacity Upgrade | 13 January 2025 08:00 | 14 February 2025 17:00
| 1751 | 4 | 6.9.6.1 |  | Assurance of DCC capacity upgrade to ensure suitability to support migration | 13 January 2025 08:00 | 07 February 2025 17:00 |  | 1756FF-20d
1751 | 1752 | 4 | 6.9.6.2 | Tier 2 | DCC Capacity Upgrade Operational | 14 February 2025 17:00 | 14 February 2025 17:00 | 1751 | 1751FS+5d
| 1753 | 3 | 6.9.7 |  | Performance Assurance Arrangements | 01 July 2025 08:00 | 01 July 2025 08:00
| 1754 | 4 | 6.9.7.1 |  | Performance assurance regime for migration success delivered | 01 July 2025 08:00 | 01 July 2025 08:00
| 1755 | 2 | 6.10 |  | Migration - Tier 1 Milestones | 07 March 2025 17:00 | 28 December 2026 17:00
1029 | 1756 | 3 | 6.10.1 | Tier 1 | Central systems ready for migrating MPANs (M10) | 07 March 2025 17:00 | 07 March 2025 17:00 | 1029 | 1029FS+21d
1756 | 1757 | 3 | 6.10.2 | Tier 2 | Central systems ready for migrating MPANs (M10*) | 30 May 2025 17:00 | 30 May 2025 17:00 | 1756 | 1756FS+3mo
1756 | 1758 | 3 | 6.10.3 | Tier 1 | Load Shaping Service switched on (M13) | 07 March 2025 17:00 | 07 March 2025 17:00 | 1756 | 1756
1758 | 1759 | 3 | 6.10.4 | Tier 2 | Load Shaping Service switched on (M13*) | 30 May 2025 17:00 | 30 May 2025 17:00 | 1758 | 1758FS+3mo
1756 | 1760 | 3 | 6.10.5 | Tier 1 | Start of 18-month migration for UMS / Advanced (M11) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1756 | 1756FS+20d
1760 | 1761 | 3 | 6.10.6 | Tier 2 | Start of 18-month migration for UMS / Advanced (M11*) | 27 June 2025 17:00 | 27 June 2025 17:00 | 1760 | 1760FS+3mo
1756 | 1762 | 3 | 6.10.7 | Tier 1 | Start of 18-month migration for Smart / Non-smart (M12) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1756 | 1756FS+20d
1762 | 1763 | 3 | 6.10.8 | Tier 2 | Start of 18-month migration for Smart / Non-smart (M12*) | 27 June 2025 17:00 | 27 June 2025 17:00 | 1762 | 1762FS+3mo
1648 | 1764 | 3 | 6.10.9 | Tier 1 | All suppliers must be able to access MPANs under the new TOM (M14) | 16 March 2026 17:00 | 16 March 2026 17:00 | 1648 | 1648
1764 | 1765 | 3 | 6.10.10 | Tier 2 | All suppliers must be able to access MPANs under the new TOM (M14*) | 08 June 2026 17:00 | 08 June 2026 17:00 | 1764 | 1764FS+3mo
| 1766 | 3 | 6.10.11 | Tier 1 | Full transition complete (M15) | 05 October 2026 17:00 | 05 October 2026 17:00 | 0 | 1724FF,1727FF,1730FF,1725FF,1728FF,1731FF
1766 | 1767 | 3 | 6.10.12 | Tier 2 | Full transition complete (M15*) | 28 December 2026 17:00 | 28 December 2026 17:00 | 1766 | 1766FS+3mo
| 1768 | 1 | 7 |  | BUSINESS AND OPERATIONAL READINESS | 01 March 2023 08:00 | 07 December 2026 17:00
| 1769 | 2 | 7.1 |  | Service Management | 01 March 2023 08:00 | 07 December 2026 17:00
| 1770 | 3 | 7.1.1 |  | Service Management Strategy | 01 March 2023 08:00 | 31 May 2023 17:00
| 1771 | 4 | 7.1.1.1 |  | Develop document with relevant participants (incl. review of the design baseline to ensure service management arrangements are in place across the solution architecture) | 01 March 2023 08:00 | 28 April 2023 17:00
| 1772 | 4 | 7.1.1.2 |  | Artefact review (via relevant Advisory Group) and updates | 01 May 2023 08:00 | 24 May 2023 17:00 |  | 1771
1772 | 1773 | 4 | 7.1.1.3 | Tier 3 | Service Management Strategy approved | 31 May 2023 17:00 | 31 May 2023 17:00 | 1772 | 1772FS+5d
| 1774 | 3 | 7.1.2 |  | Service Management Arrangements Implementation | 10 March 2025 08:00 | 07 December 2026 17:00
| 1775 | 4 | 7.1.2.1 |  | Hypercare post M10 | 10 March 2025 08:00 | 27 June 2025 17:00 |  | 1756
| 1776 | 4 | 7.1.2.2 |  | Implementation of Service Management arrangements | 07 April 2025 08:00 | 07 December 2026 17:00 |  | 1724SS
| 1777 | 2 | 7.2 |  | Post-Implementation Support Plan | 06 January 2025 08:00 | 28 February 2025 17:00
| 1778 | 3 | 7.2.1 |  | Develop document | 06 January 2025 08:00 | 31 January 2025 17:00 |  | 1756FS-45d
| 1779 | 3 | 7.2.2 |  | Document review and update | 03 February 2025 08:00 | 28 February 2025 17:00 |  | 1778
| 1780 | 3 | 7.2.3 |  | Post-Implementation Support Plan approved | 28 February 2025 17:00 | 28 February 2025 17:00 |  | 1779
| 1781 | 2 | 7.3 |  | Business Continuity and Disaster Recovery Plan | 13 January 2025 08:00 | 07 March 2025 17:00
| 1782 | 3 | 7.3.1 |  | Develop document | 13 January 2025 08:00 | 07 February 2025 17:00 |  | 1337FS-40d
| 1783 | 3 | 7.3.2 |  | Document review and update | 10 February 2025 08:00 | 07 March 2025 17:00 |  | 1782
| 1784 | 3 | 7.3.3 |  | Business Continuity and Disaster Recovery Plan approved by SRO | 07 March 2025 17:00 | 07 March 2025 17:00 |  | 1783
| 1785 | 2 | 7.4 |  | Operations Support Guide | 03 February 2025 08:00 | 28 March 2025 17:00
| 1786 | 3 | 7.4.1 |  | Develop document | 03 February 2025 08:00 | 28 February 2025 17:00 |  | 1762FS-45d
| 1787 | 3 | 7.4.2 |  | Document review and update | 03 March 2025 08:00 | 28 March 2025 17:00 |  | 1786
| 1788 | 3 | 7.4.3 |  | Operations Support Guide approved | 28 March 2025 17:00 | 28 March 2025 17:00 |  | 1787
| 1789 | 2 | 7.5 |  | Training and Support Materials | 03 February 2025 08:00 | 28 March 2025 17:00
| 1790 | 3 | 7.5.1 |  | Develop document | 03 February 2025 08:00 | 28 February 2025 17:00 |  | 1762FS-45d
| 1791 | 3 | 7.5.2 |  | Document review and update | 03 March 2025 08:00 | 28 March 2025 17:00 |  | 1790
| 1792 | 3 | 7.5.3 |  | Training and Support Materials approved | 28 March 2025 17:00 | 28 March 2025 17:00 |  | 1791
| 1793 | 2 | 7.6 |  | PP Business Change | 03 February 2025 08:00 | 31 July 2025 17:00
| 1794 | 3 | 7.6.1 |  | Plan stakeholder management | 03 February 2025 08:00 | 31 July 2025 17:00
| 1795 | 3 | 7.6.2 |  | Manage stakeholders | 03 February 2025 08:00 | 31 July 2025 17:00
| 1796 | 3 | 7.6.3 |  | Develop & implement changes to KPIs, organisation & people management | 03 February 2025 08:00 | 31 July 2025 17:00
| 1797 | 3 | 7.6.4 |  | Develop & test changes to business processes | 03 February 2025 08:00 | 31 July 2025 17:00
| 1798 | 3 | 7.6.5 |  | Develop and deliver training | 03 February 2025 08:00 | 31 July 2025 17:00
| 1799 | 3 | 7.6.6 |  | Programme support for PP Business Change activities | 03 February 2025 08:00 | 31 July 2025 17:00
| 1800 | 2 | 7.7 |  | Supplier Business Readiness for Cutover | 01 October 2025 08:00 | 30 October 2026 17:00
| 1801 | 3 | 7.7.1 |  | Programme support for Supplier Business Readiness for Cutover activities (incl. setup, management and evaluation of dress rehearsals) | 01 October 2025 08:00 | 30 October 2026 17:00
| 1802 | 1 | 8 |  | EARLY LIVE RUNNING | 02 January 2024 08:00 | 24 May 2027 17:00
| 1803 | 2 | 8.1 |  | Cut over to new settlement timetable (M16) Success Criteria | 02 January 2024 08:00 | 03 April 2024 17:00
| 1804 | 3 | 8.1.1 |  | Define the criteria measure and governance for M16 | 02 January 2024 08:00 | 13 March 2024 17:00
1804 | 1805 | 3 | 8.1.2 | Tier 3 | M16 Criteria measure and governance approved | 21 March 2024 08:00 | 21 March 2024 08:00 | 1804 | 1804FS+5d
| 1806 | 3 | 8.1.3 |  | Criteria measure and governance approved by BSC PAB | 21 March 2024 08:00 | 03 April 2024 17:00 |  | 1805
| 1807 | 2 | 8.2 |  | Early Live Running Stablisation Period | 06 October 2026 08:00 | 07 December 2026 17:00
| 1808 | 3 | 8.2.1 |  | Manage Early Live Running stablisation period | 06 October 2026 08:00 | 07 December 2026 17:00 |  | 1819FF,1766
| 1809 | 3 | 8.2.2 |  | Monitor Early Live Running stablisation period | 06 October 2026 08:00 | 07 December 2026 17:00 |  | 1808SS
| 1810 | 2 | 8.3 |  | Monitor and Report Against M16 Criteria | 06 October 2026 08:00 | 07 December 2026 17:00
| 1811 | 3 | 8.3.1 |  | Monitor and report against M16 criteria | 06 October 2026 08:00 | 07 December 2026 17:00 |  | 1808SS
| 1812 | 2 | 8.4 |  | M16 Approval Window | 13 October 2026 08:00 | 24 May 2027 17:00
| 1813 | 3 | 8.4.1 |  | Panel approval that M16 criteria met | 07 December 2026 17:00 | 07 December 2026 17:00 |  | 1811FF
1815 | 1814 | 3 | 8.4.2 | Tier 2 | Confirm M16 date | 13 October 2026 08:00 | 13 October 2026 17:00 | 1815 | 1815SS-40d
1813 | 1815 | 3 | 8.4.3 | Tier 3 | Start of 6-month window for approval of M16 | 07 December 2026 17:00 | 07 December 2026 17:00 | 1813 | 1813
| 1816 | 3 | 8.4.4 |  | Maximum 6-month window for approval of M16 | 08 December 2026 08:00 | 24 May 2027 17:00 |  | 1815
1816 | 1817 | 3 | 8.4.5 | Tier 3 | End of 6-month window for approval of M16 | 24 May 2027 17:00 | 24 May 2027 17:00 | 1816 | 1816
| 1818 | 2 | 8.5 |  | Early Live Running - Tier 1 Milestones | 07 December 2026 17:00 | 01 March 2027 17:00
1766 | 1819 | 3 | 8.5.1 | Tier 1 | Cut over to new settlement timetable (M16) | 07 December 2026 17:00 | 07 December 2026 17:00 | 1766 | 1766FS+45d
1819 | 1820 | 3 | 8.5.2 | Tier 2 | Cut over to new settlement timetable (M16*) | 01 March 2027 17:00 | 01 March 2027 17:00 | 1819 | 1819FS+3mo
| 1821 | 1 | 9 |  | PROGRAMME CLOSURE | 04 August 2026 08:00 | 30 November 2026 17:00
| 1822 | 2 | 9.1 |  | Handover Pack | 04 August 2026 08:00 | 30 November 2026 17:00
| 1823 | 3 | 9.1.1 |  | Draft Handover Pack (for M15) | 04 August 2026 08:00 | 28 September 2026 17:00
| 1824 | 4 | 9.1.1.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1825 | 4 | 9.1.1.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1824
| 1826 | 4 | 9.1.1.3 |  | Draft Handover Pack approved | 28 September 2026 17:00 | 28 September 2026 17:00 |  | 1825
| 1827 | 3 | 9.1.2 |  | Master Handover Pack (for M16) | 06 October 2026 08:00 | 30 November 2026 17:00
| 1828 | 4 | 9.1.2.1 |  | Update document | 06 October 2026 08:00 | 02 November 2026 17:00 |  | 1819FS-45d
| 1829 | 4 | 9.1.2.2 |  | Document review and update | 03 November 2026 08:00 | 30 November 2026 17:00 |  | 1828
| 1830 | 4 | 9.1.2.3 |  | Master Handover Pack approved | 30 November 2026 17:00 | 30 November 2026 17:00 |  | 1829
| 1831 | 2 | 9.2 |  | Programme Lessons Learned | 04 August 2026 08:00 | 28 September 2026 17:00
| 1832 | 3 | 9.2.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1833 | 3 | 9.2.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1832
| 1834 | 3 | 9.2.3 |  | Programme Lessons Learned document approved | 28 September 2026 17:00 | 28 September 2026 17:00 |  | 1833
| 1835 | 2 | 9.3 |  | Programme Closure Report | 04 August 2026 08:00 | 28 September 2026 17:00
| 1836 | 3 | 9.3.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1837 | 3 | 9.3.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1836
| 1838 | 3 | 9.3.3 |  | Programme Closure Report approved | 28 September 2026 17:00 | 28 September 2026 17:00 |  | 1837
| 1839 | 2 | 9.4 |  | Benefit Realisation Report | 04 August 2026 08:00 | 05 October 2026 17:00
| 1840 | 3 | 9.4.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1841 | 3 | 9.4.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1840
1841 | 1842 | 3 | 9.4.3 | Tier 3 | Benefit Realisation Report approved | 05 October 2026 17:00 | 05 October 2026 17:00 | 1841 | 1841FS+5d
| 1843 | 2 | 9.5 |  | Operarting Model Gap Review with recommendations | 04 August 2026 08:00 | 05 October 2026 17:00
| 1844 | 3 | 9.5.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1845 | 3 | 9.5.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1844
1845 | 1846 | 3 | 9.5.3 | Tier 3 | Operating Model Gap Review with recommendations approved | 05 October 2026 17:00 | 05 October 2026 17:00 | 1845 | 1845FS+5d
| 1847 | 2 | 9.6 |  | Post-Implementation Review | 04 August 2026 08:00 | 05 October 2026 17:00
| 1848 | 3 | 9.6.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1849 | 3 | 9.6.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1848
1849 | 1850 | 3 | 9.6.3 | Tier 3 | Post-Implementation Review approved | 05 October 2026 17:00 | 05 October 2026 17:00 | 1849 | 1849FS+5d
| 1851 | 2 | 9.7 |  | Reinforcement Guide | 04 August 2026 08:00 | 05 October 2026 17:00
| 1852 | 3 | 9.7.1 |  | Develop document | 04 August 2026 08:00 | 31 August 2026 17:00 |  | 1766FS-45d
| 1853 | 3 | 9.7.2 |  | Document review and update | 01 September 2026 08:00 | 28 September 2026 17:00 |  | 1852
1853 | 1854 | 3 | 9.7.3 | Tier 3 | Reinforcement Guide approved | 05 October 2026 17:00 | 05 October 2026 17:00 | 1853 | 1853FS+5d
| 1855 | 2 | 9.8 |  | Material and Licenses Transfer | 08 September 2026 08:00 | 30 November 2026 17:00
| 1856 | 3 | 9.8.1 |  | Transfer of Programme material to Elexon and perpetual licenses as appropriate | 08 September 2026 08:00 | 30 November 2026 17:00 |  | 1819FF-5d
| 1857 | 1 | 10 |  | READINESS ASSESSMENTS | 11 September 2023 08:00 | 04 December 2026 17:00
| 1858 | 2 | 10.1 |  | Readiness Assessment 3 - Design and Build Progress Check and CP2 Check | 11 September 2023 08:00 | 17 November 2023 17:00
| 1859 | 3 | 10.1.1 |  | Launch Readiness Assessment survey | 11 September 2023 08:00 | 11 September 2023 08:00 |  | 1198FS-35d
| 1860 | 3 | 10.1.2 |  | PPs submit survey responses | 11 September 2023 08:00 | 29 September 2023 17:00 |  | 1859
| 1861 | 3 | 10.1.3 |  | Analyse survey responses | 02 October 2023 08:00 | 20 October 2023 17:00 |  | 1860
| 1862 | 3 | 10.1.4 |  | Conduct deep-dive interviews (sample of PPs) | 02 October 2023 08:00 | 20 October 2023 17:00 |  | 1860
| 1863 | 3 | 10.1.5 |  | Produce Readiness Assessment Report | 23 October 2023 08:00 | 10 November 2023 17:00 |  | 1861,1862
1863 | 1864 | 3 | 10.1.6 | Tier 2 | Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | 17 November 2023 17:00 | 17 November 2023 17:00 | 1863 | 1863FS+5d
| 1865 | 2 | 10.2 |  | Readiness Assessment 4 - Design & Build Progress Check | 08 April 2024 08:00 | 13 June 2024 17:00
| 1866 | 3 | 10.2.1 |  | Launch Readiness Assessment survey | 08 April 2024 08:00 | 08 April 2024 08:00
| 1867 | 3 | 10.2.2 |  | PPs submit survey responses | 08 April 2024 08:00 | 26 April 2024 17:00 |  | 1866
| 1868 | 3 | 10.2.3 |  | Analyse survey responses | 29 April 2024 08:00 | 17 May 2024 17:00 |  | 1867
| 1869 | 3 | 10.2.4 |  | Conduct deep-dive interviews (sample of PPs) | 29 April 2024 08:00 | 17 May 2024 17:00 |  | 1867
| 1870 | 3 | 10.2.5 |  | Produce Readiness Assessment Report | 20 May 2024 08:00 | 07 June 2024 17:00 |  | 1868,1869
1870 | 1871 | 3 | 10.2.6 | Tier 2 | Readiness Assessment 4 - Design & Build Checkpoint 2 - Completed (incl. Readiness Assessment Report approval) | 13 June 2024 17:00 | 13 June 2024 17:00 | 1870 | 1870FS+4d
| 1872 | 2 | 10.3 |  | Readiness Assessment 5 - Start of Qualification | 12 November 2024 08:00 | 17 January 2025 17:00
| 1873 | 3 | 10.3.1 |  | Launch Readiness Assessment survey | 12 November 2024 08:00 | 12 November 2024 08:00 |  | 1615FS-50d
| 1874 | 3 | 10.3.2 |  | PPs submit survey responses | 12 November 2024 08:00 | 02 December 2024 17:00 |  | 1873
| 1875 | 3 | 10.3.3 |  | Analyse survey responses | 03 December 2024 08:00 | 23 December 2024 17:00 |  | 1874
| 1876 | 3 | 10.3.4 |  | Conduct deep-dive interviews (sample of PPs) | 03 December 2024 08:00 | 23 December 2024 17:00 |  | 1874
| 1877 | 3 | 10.3.5 |  | Produce Readiness Assessment Report | 24 December 2024 08:00 | 13 January 2025 17:00 |  | 1875,1876
1877 | 1878 | 3 | 10.3.6 | Tier 2 | Readiness Assessment 5 - Start of Qualification - Completed (incl. Readiness Assessment Report approval) | 17 January 2025 17:00 | 17 January 2025 17:00 | 1877 | 1877FS+4d
| 1879 | 2 | 10.4 |  | Readiness Assessment 6 - Start of Migration & CP3/CP4 check | 28 January 2025 08:00 | 04 April 2025 17:00
| 1880 | 3 | 10.4.1 |  | Launch Readiness Assessment survey | 28 January 2025 08:00 | 28 January 2025 08:00 |  | 1760FS-49d
| 1881 | 3 | 10.4.2 |  | PPs submit survey responses | 28 January 2025 08:00 | 17 February 2025 17:00 |  | 1880
| 1882 | 3 | 10.4.3 |  | Analyse survey responses | 18 February 2025 08:00 | 10 March 2025 17:00 |  | 1881
| 1883 | 3 | 10.4.4 |  | Conduct deep-dive interviews (sample of PPs) | 18 February 2025 08:00 | 10 March 2025 17:00 |  | 1881
| 1884 | 3 | 10.4.5 |  | Produce Readiness Assessment Report | 11 March 2025 08:00 | 31 March 2025 17:00 |  | 1882,1883
1884 | 1885 | 3 | 10.4.6 | Tier 2 | Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | 04 April 2025 17:00 | 04 April 2025 17:00 | 1884 | 1884FS+4d
| 1886 | 2 | 10.5 |  | Readiness Assessment 7 - Migration Checkpoint | 04 August 2025 08:00 | 09 October 2025 17:00
| 1887 | 3 | 10.5.1 |  | Launch Readiness Assessment survey | 04 August 2025 08:00 | 04 August 2025 08:00
| 1888 | 3 | 10.5.2 |  | PPs submit survey responses | 04 August 2025 08:00 | 22 August 2025 17:00 |  | 1887
| 1889 | 3 | 10.5.3 |  | Analyse survey responses | 25 August 2025 08:00 | 12 September 2025 17:00 |  | 1888
| 1890 | 3 | 10.5.4 |  | Conduct deep-dive interviews (sample of PPs) | 25 August 2025 08:00 | 12 September 2025 17:00 |  | 1888
| 1891 | 3 | 10.5.5 |  | Produce Readiness Assessment Report | 15 September 2025 08:00 | 03 October 2025 17:00 |  | 1889,1890
1891 | 1892 | 3 | 10.5.6 | Tier 2 | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 09 October 2025 17:00 | 09 October 2025 17:00 | 1891 | 1891FS+4d
| 1893 | 2 | 10.6 |  | Readiness Assessment 8 - Ready to Accept New MPANs | 06 January 2026 08:00 | 13 March 2026 17:00
| 1894 | 3 | 10.6.1 |  | Launch Readiness Assessment survey | 06 January 2026 08:00 | 06 January 2026 08:00 |  | 1764FS-50d
| 1895 | 3 | 10.6.2 |  | PPs submit survey responses | 06 January 2026 08:00 | 26 January 2026 17:00 |  | 1894
| 1896 | 3 | 10.6.3 |  | Analyse survey responses | 27 January 2026 08:00 | 16 February 2026 17:00 |  | 1895
| 1897 | 3 | 10.6.4 |  | Conduct deep-dive interviews (sample of PPs) | 27 January 2026 08:00 | 16 February 2026 17:00 |  | 1895
| 1898 | 3 | 10.6.5 |  | Produce Readiness Assessment Report | 17 February 2026 08:00 | 09 March 2026 17:00 |  | 1896,1897
1898 | 1899 | 3 | 10.6.6 | Tier 2 | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 13 March 2026 17:00 | 13 March 2026 17:00 | 1898 | 1898FS+4d
| 1900 | 2 | 10.7 |  | Readiness Assessment 9 - Ready for New Settlement Timetable and CP5 Check | 29 September 2026 08:00 | 04 December 2026 17:00
| 1901 | 3 | 10.7.1 |  | Launch Readiness Assessment survey | 29 September 2026 08:00 | 29 September 2026 08:00 |  | 1819FS-50d
| 1902 | 3 | 10.7.2 |  | PPs submit survey responses | 29 September 2026 08:00 | 19 October 2026 17:00 |  | 1901
| 1903 | 3 | 10.7.3 |  | Analyse survey responses | 20 October 2026 08:00 | 09 November 2026 17:00 |  | 1902
| 1904 | 3 | 10.7.4 |  | Conduct deep-dive interviews (sample of PPs) | 20 October 2026 08:00 | 09 November 2026 17:00 |  | 1902
| 1905 | 3 | 10.7.5 |  | Produce Readiness Assessment Report | 10 November 2026 08:00 | 30 November 2026 17:00 |  | 1903,1904
1905 | 1906 | 3 | 10.7.6 | Tier 2 | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 04 December 2026 17:00 | 04 December 2026 17:00 | 1905 | 1905FS+4d
| 1907 | 2 | 10.8 |  | Readiness Assessments - Tier 1 Milestones | 17 November 2023 17:00 | 04 December 2026 17:00
| 1908 | 3 | 10.8.1 |  | Readiness Assessment 4 - Start of Integration & Test - Completed (incl. Readiness Assessment Report approval) | 17 November 2023 17:00 | 17 November 2023 17:00 |  | 1863FS+5d
| 1909 | 3 | 10.8.2 |  | Readiness Assessment 5 - Design & Build Checkpoint 2 - Completed (incl. Readiness Assessment Report approval) | 13 June 2024 17:00 | 13 June 2024 17:00 |  | 1870FS+4d
| 1910 | 3 | 10.8.3 |  | Readiness Assessment 6 - Start of Qualification - Completed (incl. Readiness Assessment Report approval) | 17 January 2025 17:00 | 17 January 2025 17:00 |  | 1877FS+4d
| 1911 | 3 | 10.8.4 |  | Readiness Assessment 7 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | 04 April 2025 17:00 | 04 April 2025 17:00 |  | 1884FS+4d
| 1912 | 3 | 10.8.5 |  | Readiness Assessment 8 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 09 October 2025 17:00 | 09 October 2025 17:00 |  | 1891FS+4d
| 1913 | 3 | 10.8.6 |  | Readiness Assessment 9 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 13 March 2026 17:00 | 13 March 2026 17:00 |  | 1898FS+4d
| 1914 | 3 | 10.8.7 |  | Readiness Assessment 10 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 04 December 2026 17:00 | 04 December 2026 17:00 |  | 1905FS+4d
| 1915 | 1 | 11 |  | CONTROL POINTS | 10 November 2022 08:00 | 07 December 2026 17:00
| 1916 | 2 | 11.1 |  | Control Point 1 - Start of System Design, Build & Test | 10 November 2022 08:00 | 07 December 2022 17:00
| 1917 | 3 | 11.1.1 |  | Control Point 1 Preparation (incl. Control Point Report development and review) | 10 November 2022 08:00 | 30 November 2022 17:00 |  | 1918SS-20d
| 1918 | 3 | 11.1.2 | Tier 1 | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 07 December 2022 17:00 | 07 December 2022 17:00 | 1918
| 1919 | 2 | 11.2 |  | Control Point 2 - Start of Integration & Test | 02 October 2023 08:00 | 30 October 2023 08:00
| 1920 | 3 | 11.2.1 |  | Control Point 2 Preparation (incl. Control Point Report development and review) | 02 October 2023 08:00 | 20 October 2023 17:00 | 1921 | 1921SS-20d
| 1921 | 3 | 11.2.2 | Tier 1 | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 30 October 2023 08:00 | 30 October 2023 08:00 | 1198 | 1198
| 1922 | 2 | 11.3 |  | Control Point 3/4 - Readiness for Migration | 03 March 2025 08:00 | 28 March 2025 17:00
| 1923 | 3 | 11.3.1 |  | Control Point 3/4 Preparation (incl. Control Point Report development and review) | 03 March 2025 08:00 | 21 March 2025 17:00 | 1924 | 1924SS-20d
| 1924 | 3 | 11.3.2 | Tier 1 | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 28 March 2025 17:00 | 28 March 2025 17:00 | 1651 | 1651FS+10d
| 1925 | 2 | 11.4 |  | Control Point 5 - Cut Over to New Settlement Timetable | 10 November 2026 08:00 | 07 December 2026 17:00
| 1926 | 3 | 11.4.1 |  | Control Point 5 Preparation (incl. Control Point Report development and review) | 10 November 2026 08:00 | 30 November 2026 17:00 | 1927 | 1927SS-20d
| 1927 | 3 | 11.4.2 | Tier 1 | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 07 December 2026 17:00 | 07 December 2026 17:00 | 1819 | 1819
| 1928 | 2 | 11.5 |  | Control Points - Tier 1 Milestones | 07 December 2022 17:00 | 07 December 2026 17:00
| 1929 | 3 | 11.5.1 |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 07 December 2022 17:00 | 07 December 2022 17:00 | 1918 | 1918SS
| 1930 | 3 | 11.5.2 |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 30 October 2023 08:00 | 30 October 2023 08:00 | 1921 | 1921SS
| 1931 | 3 | 11.5.3 |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 28 March 2025 17:00 | 28 March 2025 17:00 | 1924 | 1924SS
| 1932 | 3 | 11.5.4 |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 07 December 2026 17:00 | 07 December 2026 17:00 | 1927 | 1927SS
| 1933 | 1 | 12 |  | MILESTONE RANGE CHECKPOINTS | 16 December 2024 08:00 | 15 September 2026 08:00
| 1934 | 2 | 12.1 |  | M10, M11, M12, M13 milestone checkpoint | 16 December 2024 08:00 | 16 December 2024 08:00
| 1935 | 3 | 12.1.1 | Tier 2 | M10, M11, M12, and M13 milestone checkpoint - date approval | 16 December 2024 08:00 | 16 December 2024 08:00 | 1756 | 1756FS-3mo
| 1936 | 2 | 12.2 |  | M14 milestone checkpoint | 23 December 2025 08:00 | 23 December 2025 08:00
| 1937 | 3 | 12.2.1 | Tier 2 | M14 milestone checkpoint - date approval | 23 December 2025 08:00 | 23 December 2025 08:00 | 1764 | 1764FS-3mo
| 1938 | 2 | 12.3 |  | M15 milestone checkpoint | 14 July 2026 08:00 | 14 July 2026 08:00
| 1939 | 3 | 12.3.1 | Tier 2 | M15 milestone checkpoint - date approval | 14 July 2026 08:00 | 14 July 2026 08:00 | 1766 | 1766FS-3mo
| 1940 | 2 | 12.4 |  | M16 milestone checkpoint | 15 September 2026 08:00 | 15 September 2026 08:00
| 1941 | 3 | 12.4.1 | Tier 2 | M16 milestone checkpoint - date approval | 15 September 2026 08:00 | 15 September 2026 08:00 | 1819 | 1819FS-3mo