## Outline Plan
Outline Level | WBS | Tier | Milestone ID | Approving Governance Forum | Artefact ID | Task Name | % Complete | Start | Finish | Duration | Baseline Start | Baseline Finish | Start Variance | Finish Variance | Duration Variance | Responsible | M/S Change Status | Update Version | Active | Resource Names | Notes | Notes3
1 | 1 |  |  |  |  | PROGRAMME PLAN. | 88% | Mon 31/10/22 | Thu 23/12/27 | 1344 days? | Mon 31/10/22 | Thu 23/12/27 | 0 days | 0 days | 149 days? | N/A |  | 5 | Yes
2 | 1.1 |  |  |  |  | MHHS Programme Start | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 | 0 days | -1 day | 0 days | N/A |  | 5.7 | Yes
2 | 1.2 |  |  |  |  | PROGRAMME MANAGEMENT | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
3 | 1.2.1 |  |  |  |  | Programme Management | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.1.1 |  |  |  |  | Sprint-based prioritisation planning and execution | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.2 |  |  |  |  | Programme governance secretariat | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.3 |  |  |  |  | RAID management and reporting | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.4 |  |  |  |  | Tracking against Programme outcomes and KPIs | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.5 |  |  |  |  | Change control and reporting | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.6 |  |  |  |  | Ongoing identification of lessons learned relating to the PMO and implementation of improvements | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
3 | 1.2.2 |  |  |  |  | Programme Internal Assurance Reviews | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.2.1 |  |  |  |  | Programme Internal Assurance Reviews | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.2.3 |  |  |  |  | Engagement with PPs | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.3.1 |  |  |  |  | Ongoing PP liaison activities | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.2 |  |  |  |  | Milestone and Control Point objective setting | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.3 |  |  |  |  | Reporting | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.4 |  |  |  |  | PP Engagement Events | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.2.3.4.1 |  |  |  |  | Bilateral meetings | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.4.2 |  |  |  |  | Monthly webinars | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.4.3 |  |  |  |  | Open days | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.5 |  |  |  |  | PP Communications | 78% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.2.3.5.1 |  |  |  |  | The Clock updates (weekly) | 78% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.5.2 |  |  |  |  | Maintain and update content on public-facing Portal (and ongoing feedback reviews to identify and implement Portal improvements) | 78% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
3 | 1.2.4 |  |  |  |  | Code Change Support / Other Programme Alignment | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.4.1 |  |  |  |  | Support DCC/BEIS on SEC change | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.2 |  |  |  |  | Support on Smart Meters Act changes | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.3 |  |  |  |  | Support DCC/RECCo on CSS change | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.4 |  |  |  |  | Support Elexon on BSC change | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.5 |  |  |  |  | Support code change inside & outside CCIAG | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.6 |  |  |  |  | Support code change inside & outside CCAG | 78% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.2.5 |  |  |  |  | Programme Replan Baseline | 100% | Mon 31/10/22 | Wed 14/06/23 | 163 days | Mon 31/10/22 | Wed 14/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.5.1 |  |  |  |  | Round 3 consultation preparation | 100% | Mon 31/10/22 | Tue 13/12/22 | 32 days | Mon 31/10/22 | Tue 13/12/22 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.2 |  |  |  |  | PSG decision to launch Round 3 consultation | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 0 days | -1 day | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.3 |  |  |  |  | Round 3 consultation (incl. walkthroughs and Q&A) | 100% | Wed 14/12/22 | Tue 31/01/23 | 35 days | Wed 14/12/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.2.5.4 |  |  |  |  | Review and uplift of foundational testing documents to align with replan approach | 100% | Wed 14/12/22 | Thu 20/04/23 | 92 days | Wed 14/12/22 | Thu 20/04/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.2.5.5 |  |  |  |  | Round 3 consultation responses analysis (incl. identification of SIT volunteers) | 100% | Wed 01/02/23 | Tue 14/02/23 | 10 days | Wed 01/02/23 | Tue 14/02/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.6 |  |  |  |  | Replan re-drafting and supporting artefact updates (incl. engagement with Ofgem) | 100% | Wed 15/02/23 | Wed 22/03/23 | 26 days | Wed 15/02/23 | Wed 22/03/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.7 |  |  |  |  | Draft Replan Change Request | 100% | Wed 15/02/23 | Wed 29/03/23 | 31 days | Wed 15/02/23 | Wed 29/03/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.8 |  |  |  |  | PSG decision to issue CR for industry impact assessment | 100% | Wed 05/04/23 | Wed 05/04/23 | 0 days | Wed 05/04/23 | Wed 05/04/23 | 1 day | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.9 |  |  |  |  | Industry impact assessment | 100% | Thu 06/04/23 | Wed 19/04/23 | 10 days | Thu 06/04/23 | Wed 19/04/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.2.5.10 |  |  |  |  | Replan playbacks (to assist PPs in impact assessment) | 100% | Tue 11/04/23 | Mon 17/04/23 | 5 days | Tue 11/04/23 | Mon 17/04/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.11 |  |  |  |  | Industry impact assessment responses analysis | 100% | Thu 20/04/23 | Wed 26/04/23 | 5 days | Thu 20/04/23 | Wed 26/04/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.12 |  |  |  |  | Extraordinary PSG decision to agree baseline recommendation | 100% | Wed 03/05/23 | Wed 03/05/23 | 0 days | Wed 03/05/23 | Wed 03/05/23 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.13 |  |  |  |  | Programme Replan playbacks and drop-in sessions | 100% | Thu 08/06/23 | Wed 14/06/23 | 5 days | Thu 08/06/23 | Wed 14/06/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
2 | 1.3 |  |  | DAG |  | DESIGN, BUILD & TEST (PIT) | 97% | Mon 31/10/22 | Mon 18/01/27 | 1101 days? | Mon 31/10/22 | Mon 05/07/27 | 0 days | -120 days | 0 days? | N/A |  |  | Yes
3 | 1.3.1 |  |  |  |  | Design Baseline & Enduring PP Support | 88% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.1.1 | T1 | T1-DB-1000 | PSG | MHHS-ART001 | Physical design baselined (M5) | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 | 0 days | -1 day | 0 days | SRO Design |  | 5 | Yes
4 | 1.3.1.2 |  |  |  |  | M5 Design Work-Off Plan Implementation & Approval | 100% | Mon 31/10/22 | Thu 16/02/23 | 79 days | Mon 31/10/22 | Thu 16/02/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.2.1 |  |  |  |  | Implementation of M5 design Work-Off Plan | 100% | Mon 31/10/22 | Thu 09/02/23 | 74 days | Mon 31/10/22 | Thu 09/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.2.2 | T3 | T3-DB-0014 | DAG |  | M5 design Work-Off Plan completion approved | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.3 |  |  |  |  | Enduring PP Design Support | 100% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.3.1 |  |  |  |  | Design playbacks and drop-in sessions | 100% | Mon 31/10/22 | Fri 30/12/22 | 45 days | Mon 31/10/22 | Fri 30/12/22 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.2 |  |  |  |  | Support participants on E2E MHHS Design | 100% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.3 |  |  |  |  | DIP Onboarding Support | 100% | Mon 14/11/22 | Fri 17/02/23 | 70 days | Mon 14/11/22 | Fri 17/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.4 |  |  |  |  | iServer Launch | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.4 |  |  |  |  | Establish Design Change Management Processes | 73% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.4.1 |  |  |  |  | Internal review of internal change management processes | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.3.1.4.2 |  |  |  |  | SRO approval of internal change management processes | 100% | Fri 16/12/22 | Fri 16/12/22 | 0 days | Fri 16/12/22 | Fri 16/12/22 | 1 day | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.3.1.4.3 |  |  |  |  | Change Process Webinar | 100% | Mon 16/01/23 | Mon 16/01/23 | 0 days | Mon 16/01/23 | Mon 16/01/23 | 0 days | -1 day | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.4.4 | T3 | T3-DB-0016 | DAG |  | Enduring change management process approved | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.4.5 |  |  |  |  | Maintain E2E MHHS Design (post-M5 design change management processes operational) | 72% | Fri 17/02/23 | Mon 18/01/27 | 1022 days | Fri 17/02/23 | Mon 18/01/27 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.5 |  |  |  |  | Design Authority Mobilisation | 100% | Wed 14/12/22 | Mon 23/01/23 | 29 days | Wed 14/12/22 | Mon 23/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.5.1 | T3 | T3-DB-0010 | DAG |  | Design Authority ToR approved | 100% | Wed 14/12/22 | Wed 14/12/22 | 0 days | Wed 14/12/22 | Wed 14/12/22 | 0 days | -1 day | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.5.2 |  |  |  |  | Inaugural Design Authority | 100% | Mon 23/01/23 | Mon 23/01/23 | 0 days | Mon 23/01/23 | Mon 23/01/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.6 |  |  |  |  | Network Operation Services Adaptor Procurement | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.6.1 | T3 | T3-DB-0020 | DAG |  | All SIT LDSOs have procured their adapter providers | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
3 | 1.3.2 |  |  |  |  | PP Mobilisation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.2.1 |  |  |  |  | Set up governance | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.2 |  |  |  |  | Set up reporting | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.3 |  |  |  |  | Obtain funding | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.4 |  |  |  |  | Earmark resources | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.5 |  |  |  |  | Mobilise initial team | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.3.3 |  |  |  |  | PIT Stub Specification and Delivery | 100% | Mon 31/10/22 | Fri 28/06/24 | 435 days | Mon 31/10/22 | Fri 28/06/24 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
4 | 1.3.3.1 |  |  |  |  | DIP Simulator | 100% | Mon 31/10/22 | Wed 29/03/23 | 108 days | Mon 31/10/22 | Wed 29/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.3.1.1 |  |  |  |  | Build & Test | 100% | Mon 31/10/22 | Fri 10/03/23 | 95 days | Mon 31/10/22 | Fri 10/03/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.1.2 |  |  |  |  | UAT | 100% | Mon 14/11/22 | Fri 10/03/23 | 85 days | Mon 14/11/22 | Fri 10/03/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.3.1.3 |  |  |  |  | Beta test | 100% | Mon 31/10/22 | Fri 10/03/23 | 95 days | Mon 31/10/22 | Fri 10/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.3.1.4 |  |  |  |  | Prepare for release | 100% | Mon 06/03/23 | Wed 29/03/23 | 18 days | Mon 06/03/23 | Wed 29/03/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.1.5 | T3 | T3-DB-0018 | SITAG |  | DIP Simulator released | 100% | Wed 29/03/23 | Wed 29/03/23 | 0 days | Wed 29/03/23 | Wed 29/03/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5 | Yes
4 | 1.3.3.2 |  |  |  |  | DIP Simulator Uplifts | 100% | Thu 06/07/23 | Fri 28/06/24 | 257 days | Thu 06/07/23 | Fri 28/06/24 | 0 days | 0 days | 5 days | N/A |  | 5.1 | Yes
5 | 1.3.3.2.1 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 06/07/23 | Fri 11/08/23 | 27 days | Thu 06/07/23 | Fri 11/08/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5.1 | Yes
5 | 1.3.3.2.2 | T3 | T3-DB-0035 | SITAG |  | DIP Simulator uplifted to align with Interim Release 2 | 100% | Fri 11/08/23 | Fri 11/08/23 | 0 days | Fri 11/08/23 | Fri 11/08/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5.1 | Yes
5 | 1.3.3.2.3 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Mon 09/10/23 | Fri 03/11/23 | 20 days | Mon 09/10/23 | Fri 03/11/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5.3 | Yes
5 | 1.3.3.2.4 | T3 | T3-DB-0039 | SITAG |  | DIP Simulator uplifted to align with Interim Release 5 | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5.11 | Yes
5 | 1.3.3.2.5 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 01/02/24 | Fri 22/03/24 | 37 days | Thu 01/02/24 | Fri 22/03/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.6 | T3 | T3-DB-0182 | SITAG |  | DIP Simulator uplifted to align with Interim Release 7 | 100% | Fri 22/03/24 | Fri 22/03/24 | 0 days | Fri 22/03/24 | Fri 22/03/24 | 1 day | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.7 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 04/04/24 | Fri 21/06/24 | 57 days | Thu 04/04/24 | Fri 21/06/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.8 | T3 | T3-DB-0183 | SITAG |  | DIP Simulator uplifted to align with Interim Release 8 | 100% | Fri 28/06/24 | Fri 28/06/24 | 0 days | Fri 28/06/24 | Fri 28/06/24 | 1 day | 0 days | 0 days | SI DevOps |  | 5.28 | Yes
4 | 1.3.3.3 |  |  |  |  | Data Generator | 100% | Thu 01/12/22 | Wed 31/05/23 | 130 days | Thu 01/12/22 | Wed 31/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.3.3.1 |  |  |  |  | Design | 100% | Thu 01/12/22 | Wed 21/12/22 | 15 days | Thu 01/12/22 | Wed 21/12/22 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.2 |  |  |  |  | Build & Test | 100% | Thu 16/02/23 | Wed 26/04/23 | 50 days | Thu 16/02/23 | Wed 26/04/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.3 |  |  |  |  | UAT | 100% | Thu 27/04/23 | Wed 10/05/23 | 10 days | Thu 27/04/23 | Wed 10/05/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.3.3.4 |  |  |  |  | Beta test | 100% | Thu 30/03/23 | Wed 31/05/23 | 45 days | Thu 30/03/23 | Wed 31/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.3.3.5 |  |  |  |  | Prepare for release | 100% | Thu 27/04/23 | Tue 30/05/23 | 24 days | Thu 27/04/23 | Tue 30/05/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.6 | T3 | T3-DB-0022 | SITAG |  | Data Generator released | 100% | Wed 31/05/23 | Wed 31/05/23 | 0 days | Wed 31/05/23 | Wed 31/05/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5 | Yes
3 | 1.3.4 |  |  | DAG |  | Design Artefact Releases | 100% | Wed 22/02/23 | Wed 23/04/25 | 566 days? | Wed 22/02/23 | Wed 13/11/24 | 0 days | 115 days | 168 days? | N/A |  | 5 | Yes
4 | 1.3.4.1 |  |  |  |  | Interim release 1 | 100% | Wed 22/02/23 | Mon 12/06/23 | 79 days | Wed 22/02/23 | Mon 12/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.1.1 |  |  |  |  | Prioritise DINs and CR | 100% | Wed 22/02/23 | Wed 22/02/23 | 1 day | Wed 22/02/23 | Wed 22/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.2 |  |  |  |  | Industry input session | 100% | Thu 23/02/23 | Fri 03/03/23 | 7 days | Thu 23/02/23 | Fri 03/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.2.1 |  |  |  |  | Raise a CR covering prioritized assessment cluster | 100% | Thu 23/02/23 | Thu 23/02/23 | 1 day | Thu 23/02/23 | Thu 23/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.2.2 |  |  |  |  | Organize Industry Input session to go through significant items to reach consensus | 100% | Thu 23/02/23 | Thu 23/02/23 | 1 day | Thu 23/02/23 | Thu 23/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.2.3 |  |  |  |  | Conduct Meeting | 100% | Fri 03/03/23 | Fri 03/03/23 | 1 day | Fri 03/03/23 | Fri 03/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.3 |  |  |  |  | Update baselined artefacts | 100% | Fri 24/03/23 | Thu 06/04/23 | 10 days | Fri 24/03/23 | Thu 06/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.4 |  |  |  |  | Participant review and impact assess changes | 100% | Fri 14/04/23 | Tue 09/05/23 | 18 days | Fri 14/04/23 | Tue 09/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.4.1 |  |  |  |  | Issue Redline Version of documents | 100% | Fri 14/04/23 | Fri 14/04/23 | 1 day | Fri 14/04/23 | Fri 14/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.4.2 |  |  |  |  | Participants provide review comments to common log | 100% | Mon 17/04/23 | Tue 09/05/23 | 17 days | Mon 17/04/23 | Tue 09/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.4.1.5 |  |  |  |  | Assurance review | 100% | Wed 10/05/23 | Mon 05/06/23 | 19 days | Wed 10/05/23 | Mon 05/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.5.1 |  |  |  |  | SI Design Review and Respond to Comments | 100% | Wed 10/05/23 | Tue 16/05/23 | 5 days | Wed 10/05/23 | Tue 16/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.2 |  |  |  |  | Prep for Assurance Review Meeting | 100% | Wed 17/05/23 | Thu 25/05/23 | 7 days | Wed 17/05/23 | Thu 25/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.3 |  |  |  |  | Conduct Assurance Review Meeting | 100% | Fri 26/05/23 | Fri 26/05/23 | 1 day | Fri 26/05/23 | Fri 26/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.4 |  |  |  |  | Update Artefacts following Assurance Review | 100% | Mon 29/05/23 | Mon 05/06/23 | 6 days | Mon 29/05/23 | Mon 05/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.6 |  |  |  |  | PSG Approval of interim release plan | 100% | Thu 08/06/23 | Thu 08/06/23 | 1 day | Thu 08/06/23 | Thu 08/06/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
5 | 1.3.4.1.7 |  |  |  |  | Publish updated baselined artefacts | 100% | Tue 06/06/23 | Tue 06/06/23 | 0 days | Tue 06/06/23 | Mon 12/06/23 | 0 days | -5 days | -5 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.8 | T3 | T3-DB-0095 | DAG |  | Interim release 1 Go live | 100% | Mon 12/06/23 | Mon 12/06/23 | 0 days | Mon 12/06/23 | Mon 12/06/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.2 |  |  |  |  | Interim release 2 | 100% | Tue 30/05/23 | Wed 05/07/23 | 27 days | Tue 30/05/23 | Wed 05/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.2.1 |  |  |  |  | Update baselined artefacts | 100% | Tue 30/05/23 | Wed 05/07/23 | 27 days | Tue 30/05/23 | Wed 05/07/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.2.2 | T3 | T3-DB-0096 | DAG |  | Interim release 2 Go live | 100% | Wed 05/07/23 | Wed 05/07/23 | 0 days | Wed 05/07/23 | Wed 05/07/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.3 |  |  |  |  | Interim release 3 | 100% | Thu 15/06/23 | Wed 02/08/23 | 35 days | Thu 15/06/23 | Wed 02/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.3.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 15/06/23 | Wed 02/08/23 | 35 days | Thu 15/06/23 | Wed 02/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.3.2 | T3 | T3-DB-0097 | DAG |  | Interim release 3 Go live | 100% | Wed 02/08/23 | Wed 02/08/23 | 0 days | Wed 02/08/23 | Wed 02/08/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.4 |  |  |  |  | Interim release 4 | 100% | Wed 12/07/23 | Wed 30/08/23 | 36 days | Wed 12/07/23 | Wed 30/08/23 | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.4.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 12/07/23 | Wed 30/08/23 | 36 days | Wed 12/07/23 | Wed 30/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.4.2 | T3 | T3-DB-0081 | DAG |  | Interim release 4 Go live | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 1 day | 0 days | 0 days | SI Design |  | 5.1 | Yes
4 | 1.3.4.5 |  |  |  |  | Interim release 5 | 100% | Thu 17/08/23 | Fri 08/03/24 | 147 days | Thu 17/08/23 | Fri 08/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.5.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 17/08/23 | Wed 04/10/23 | 35 days | Thu 17/08/23 | Wed 04/10/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.5.2 | T3 | T3-DB-0083 | DAG |  | Interim release 5 Go live | 100% | Wed 04/10/23 | Wed 04/10/23 | 0 days | Wed 04/10/23 | Wed 04/10/23 | 1 day | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.5.3 |  |  |  |  | Interim Release 5 Deployed to SIT | 100% | Mon 26/02/24 | Fri 08/03/24 | 10 days | Mon 26/02/24 | Fri 08/03/24 | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.6 |  |  |  |  | Interim release 6 | 100% | Thu 14/09/23 | Fri 07/06/24 | 192 days | Thu 14/09/23 | Fri 07/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.6.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 14/09/23 | Wed 01/11/23 | 35 days | Thu 14/09/23 | Wed 01/11/23 | 0 days | 0 days | 3 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.6.2 | T3 | T3-DB-0085 | DAG |  | Interim release 6 Go live | 100% | Wed 01/11/23 | Wed 01/11/23 | 0 days | Wed 01/11/23 | Wed 01/11/23 | 1 day | 0 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.4.6.3 |  |  |  |  | Interim Release 6 Deployed to SIT | 100% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 27/05/24 | Fri 07/06/24 | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.7 |  |  |  |  | Interim release 7 | 100% | Wed 18/10/23 | Fri 07/06/24 | 168 days | Wed 18/10/23 | Fri 07/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
5 | 1.3.4.7.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 18/10/23 | Wed 31/01/24 | 76 days | Wed 18/10/23 | Wed 31/01/24 | 0 days | 0 days | 0 days | SI Design |  | 5.5 | Yes
5 | 1.3.4.7.2 | T3 | T3-DB-0098 | DAG |  | Interim release 7 Go live | 100% | Wed 31/01/24 | Wed 31/01/24 | 0 days | Wed 31/01/24 | Wed 31/01/24 | 1 day | 0 days | 0 days | SI Design |  | 5.14 | Yes
5 | 1.3.4.7.3 |  |  |  |  | Interim Release 7 Deployed to SIT | 100% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 27/05/24 | Fri 07/06/24 | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.8 |  |  | DAG |  | Interim release 8 | 100% | Wed 14/02/24 | Wed 23/04/25 | 311 days? | Wed 14/02/24 | Wed 13/11/24 | 0 days | 115 days | 168 days? | N/A |  | 5.5 | Yes
5 | 1.3.4.8.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 14/02/24 | Wed 03/04/24 | 36 days | Wed 14/02/24 | Wed 03/04/24 | 0 days | 0 days | 0 days | SI Design |  | 5.5 | Yes
5 | 1.3.4.8.2 | T3 | T3-DB-0099 | DAG |  | Interim release 8 Go live | 100% | Wed 03/04/24 | Wed 03/04/24 | 0 days | Wed 03/04/24 | Wed 03/04/24 | 1 day | 0 days | 0 days | SI Design |  | 5.14 | Yes
5 | 1.3.4.8.3 |  |  |  |  | Interim Release 8.3 - Maintenance Window | 100% | Mon 07/10/24 | Mon 21/10/24 | 11 days | Mon 07/10/24 | Mon 21/10/24 | 0 days | 0 days | 11 days | Design |  | 6 | Yes
6 | 1.3.4.8.3.1 |  |  |  |  | Interim Release 8.3 'effective from date' to SIT A | 100% | Mon 21/10/24 | Mon 21/10/24 | 0 days | Mon 21/10/24 | Mon 21/10/24 | 1 day | 0 days | -10 days | SI Testing |  | 5.16 | Yes
6 | 1.3.4.8.3.2 |  |  |  |  | Interim Release 8.3 'effective from date' to SIT B | 100% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 0 days | -1 day | 0 days | Design |  | 5.16 | Yes
5 | 1.3.4.8.4 |  |  | DAG |  | Interim Release 8.4 | 100% | Wed 25/09/24 | Mon 02/12/24 | 49 days | Wed 25/09/24 | Wed 13/11/24 | 0 days | 13 days | 49 days | Design |  | 6.1 | Yes
6 | 1.3.4.8.4.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 25/09/24 | Fri 04/10/24 | 8 days | Wed 25/09/24 | Fri 04/10/24 | 0 days | 0 days | 8 days | Design |  | 6.1 | Yes
6 | 1.3.4.8.4.2 | T3 | T3-DB-0184 | DAG |  | Interim Release 8.4 Published | 100% | Wed 16/10/24 | Wed 16/10/24 | 0 days | Wed 16/10/24 | Wed 16/10/24 | 1 day | 0 days | 0 days | Design |  | 6.1 | Yes
6 | 1.3.4.8.4.3 |  |  |  |  | Interim Release 8.4 Deployed to SIT by Participants | 100% | Mon 25/11/24 | Mon 02/12/24 | 6 days | Wed 13/11/24 | Wed 13/11/24 | 8 days | 13 days | 6 days | Design |  | 6.12 | Yes
5 | 1.3.4.8.5 |  |  | DAG |  | Interim Release 8.5 | 100% | Wed 16/10/24 | Wed 22/01/25 | 71 days | Wed 16/10/24 | Wed 04/12/24 | 0 days | 35 days | 71 days | Design |  | 6.11 | Yes
6 | 1.3.4.8.5.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 16/10/24 | Fri 25/10/24 | 8 days | Wed 16/10/24 | Fri 25/10/24 | 0 days | 0 days | 8 days | Design |  | 6.11 | Yes
6 | 1.3.4.8.5.2 | T3 | T3-DB-0185 | DAG |  | Interim Release 8.5 Published | 100% | Wed 06/11/24 | Wed 06/11/24 | 0 days | Wed 06/11/24 | Wed 06/11/24 | 1 day | 0 days | 0 days | Design |  | 6.11 | Yes
6 | 1.3.4.8.5.3 |  |  |  |  | Interim Release 8.5 Deployed to SIT by Participants | 100% | Mon 20/01/25 | Wed 22/01/25 | 3 days | Wed 04/12/24 | Wed 04/12/24 | 33 days | 35 days | 3 days | Design |  | 6.12 | Yes
5 | 1.3.4.8.6 |  |  | DAG |  | Interim Release 8.6 | 100% | Thu 21/11/24 | Wed 22/01/25 | 45 days? | Thu 21/11/24 | Wed 22/01/25 | 0 days | 0 days | 45 days? | Design |  | 6.14 | Yes
6 | 1.3.4.8.6.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 21/11/24 | Fri 22/11/24 | 2 days? | Thu 21/11/24 | Fri 22/11/24 | 0 days | 0 days | 2 days? | Design |  | 6.14 | Yes
6 | 1.3.4.8.6.2 |  |  |  |  | Interim Release 8.6 Published | 100% | Mon 25/11/24 | Mon 25/11/24 | 1 day? | Mon 25/11/24 | Mon 25/11/24 | 0 days | 0 days | 1 day? | Design |  | 6.14 | Yes
6 | 1.3.4.8.6.3 | T3 | T3-TE-0187 | DAG |  | Interim Release 8.6 Deployed to SIT by Participants | 100% | Mon 20/01/25 | Wed 22/01/25 | 3 days | Mon 20/01/25 | Wed 22/01/25 | 0 days | 0 days | 3 days | Design |  | 6.14 | Yes
5 | 1.3.4.8.7 |  |  | DAG |  | Interim Release 8.7 | 100% | Mon 20/01/25 | Fri 24/01/25 | 5 days | Mon 20/01/25 | Mon 27/01/25 | 0 days | -1 day | 5 days | Design |  | 6.16 | Yes
6 | 1.3.4.8.7.1 |  |  |  |  | Update baselined artefacts | 100% | Mon 20/01/25 | Tue 21/01/25 | 2 days | Mon 20/01/25 | Tue 21/01/25 | 0 days | 0 days | 2 days | Design |  | 6.16 | Yes
6 | 1.3.4.8.7.2 |  |  |  |  | Interim Release 8.7 Published | 100% | Wed 22/01/25 | Wed 22/01/25 | 1 day | Wed 22/01/25 | Wed 22/01/25 | 0 days | 0 days | 1 day | Design |  | 6.16 | Yes
6 | 1.3.4.8.7.3 | T3 | T3-TE-0188 | DAG |  | Interim Release 8.7 Deployed to SIT by Participants | 100% | Wed 22/01/25 | Fri 24/01/25 | 3 days | Thu 23/01/25 | Mon 27/01/25 | -1 day | -1 day | 3 days | Design |  | 6.16 | Yes
5 | 1.3.4.8.8 |  |  | DAG |  | Interim Release 8.8 | 100% | Wed 05/02/25 | Wed 12/03/25 | 26 days | Wed 05/02/25 | Wed 12/03/25 | 0 days | 0 days | 26 days | Design |  | 6.18 | Yes
6 | 1.3.4.8.8.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 05/02/25 | Mon 10/02/25 | 4 days | Wed 05/02/25 | Mon 10/02/25 | 0 days | 0 days | 4 days | Design |  | 6.18 | Yes
6 | 1.3.4.8.8.2 |  |  |  |  | Interim Release 8.8 Published | 100% | Wed 12/02/25 | Wed 12/02/25 | 1 day | Wed 12/02/25 | Wed 12/02/25 | 0 days | 0 days | 1 day | Design |  | 6.18 | Yes
6 | 1.3.4.8.8.3 |  |  | DAG |  | Interim Release 8.8 Deployed to SIT by Participants | 100% | Thu 13/02/25 | Wed 12/03/25 | 20 days | Thu 13/02/25 | Wed 12/03/25 | 0 days | 0 days | 20 days | Design |  | 6.18 | Yes
5 | 1.3.4.8.9 |  |  | DAG |  | Interim Release 8.9 | 100% | Wed 05/02/25 | Tue 08/04/25 | 45 days | Wed 05/02/25 | Wed 12/03/25 | 0 days | 19 days | 45 days | Design |  | 6.21 | Yes
6 | 1.3.4.8.9.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 05/02/25 | Mon 10/02/25 | 4 days | Wed 05/02/25 | Mon 10/02/25 | 0 days | 0 days | 4 days | Design |  | 6.21 | Yes
6 | 1.3.4.8.9.2 |  |  |  |  | Interim Release 8.9 Published | 100% | Tue 11/03/25 | Tue 11/03/25 | 0 days | Wed 12/02/25 | Wed 12/02/25 | 20 days | 19 days | 0 days | Design |  | 6.21 | Yes
6 | 1.3.4.8.9.3 |  |  | DAG |  | Interim Release 8.9 Deployed to SIT by Participants | 100% | Wed 12/03/25 | Tue 08/04/25 | 20 days | Wed 12/03/25 | Tue 08/04/25 | 0 days | 0 days | 20 days | Design |  | 6.21 | Yes
5 | 1.3.4.8.10 |  |  | DAG |  | Interim Release 8.10 | 100% | Wed 05/02/25 | Wed 23/04/25 | 56 days | Wed 05/02/25 | Wed 12/03/25 | 0 days | 30 days | 56 days | Design |  | 6.21 | Yes
6 | 1.3.4.8.10.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 05/02/25 | Mon 10/02/25 | 4 days | Wed 05/02/25 | Mon 10/02/25 | 0 days | 0 days | 4 days | Design |  | 6.21 | Yes
6 | 1.3.4.8.10.2 |  |  |  |  | Interim Release 8.10 Published | 100% | Wed 26/03/25 | Wed 26/03/25 | 1 day | Wed 12/02/25 | Wed 12/02/25 | 30 days | 30 days | 1 day | Design |  | 6.21 | Yes
6 | 1.3.4.8.10.3 |  |  | DAG |  | Interim Release 8.10 Deployed to SIT by Participants | 100% | Thu 27/03/25 | Wed 23/04/25 | 20 days | Thu 27/03/25 | Wed 23/04/25 | 0 days | 0 days | 20 days | Design |  | 6.21 | Yes
3 | 1.3.5 |  |  |  |  | Queries Support / Knowledgebase & Tool Roll-Out (Systems) | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.5.1 |  |  |  |  | Query Management | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.1.1 |  |  |  |  | Respond to Participant Queries | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.1.2 |  |  |  |  | Respond to Programme Queries | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.5.2 |  |  |  |  | Query Support tooling (FreshDesk) | 100% | Thu 01/06/23 | Mon 03/07/23 | 23 days | Thu 01/06/23 | Mon 03/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.2.1 |  |  |  |  | Migrate to Standalone Freshdesk | 100% | Thu 01/06/23 | Wed 14/06/23 | 10 days | Thu 01/06/23 | Wed 14/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.2 |  |  |  |  | Develop reporting dashboard | 100% | Thu 15/06/23 | Wed 21/06/23 | 5 days | Thu 15/06/23 | Wed 21/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.3 |  |  |  |  | Issue to SRO for Review | 100% | Thu 22/06/23 | Wed 28/06/23 | 5 days | Thu 22/06/23 | Wed 28/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.4 |  |  |  |  | Update following review | 100% | Thu 29/06/23 | Fri 30/06/23 | 2 days | Thu 29/06/23 | Fri 30/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.5 |  |  |  |  | Sign off | 100% | Mon 03/07/23 | Mon 03/07/23 | 1 day | Mon 03/07/23 | Mon 03/07/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.5.3 |  |  |  |  | KnowledgeBase Development | 100% | Thu 01/06/23 | Fri 08/09/23 | 72 days | Thu 01/06/23 | Fri 08/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.3.1 |  |  |  |  | Define Scope of KB | 100% | Thu 01/06/23 | Thu 01/06/23 | 1 day | Thu 01/06/23 | Thu 01/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.2 |  |  |  |  | Capture Existing KB artefacts | 100% | Fri 02/06/23 | Thu 29/06/23 | 20 days | Fri 02/06/23 | Thu 29/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.3 |  |  |  |  | Tag artefacts | 100% | Fri 30/06/23 | Thu 06/07/23 | 5 days | Fri 30/06/23 | Thu 06/07/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.4 |  |  |  |  | Develop Participant Interfaces | 100% | Fri 07/07/23 | Thu 03/08/23 | 20 days | Fri 07/07/23 | Thu 03/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.5 |  |  |  |  | Promote to Collaboration Portal | 100% | Fri 04/08/23 | Fri 01/09/23 | 21 days | Fri 04/08/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.6 |  |  |  |  | Link into FreshDesk | 100% | Mon 04/09/23 | Fri 08/09/23 | 5 days | Mon 04/09/23 | Fri 08/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
3 | 1.3.6 |  |  | DAG |  | PP Design, Build & Test (DBT) | 100% | Mon 31/10/22 | Fri 21/02/25 | 605 days | Mon 31/10/22 | Mon 05/07/27 | 0 days | -616 days | 110 days | N/A |  | 5 | Yes
4 | 1.3.6.1 |  |  |  |  | PP Impact Assessment, Planning & Procurement | 100% | Mon 31/10/22 | Fri 31/03/23 | 110 days | Mon 31/10/22 | Fri 31/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.6.1.1 |  |  |  |  | PP Impact Assessment | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.1.1 |  |  |  |  | Develop heatmap for impact of MHHS | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.1.2 |  |  |  |  | Develop detailed impact assessment | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.6.1.2 |  |  |  |  | PP Planning | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.2.1 |  |  |  |  | Develop detailed short-term plan | 100% | Mon 31/10/22 | Wed 30/11/22 | 23 days | Mon 31/10/22 | Wed 30/11/22 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.2.2 |  |  |  |  | Develop overall project plan for implementation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.2.3 |  |  |  |  | Develop procurement plan | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.6.1.3 |  |  |  |  | PP Software/Service Procurement | 100% | Mon 31/10/22 | Fri 31/03/23 | 110 days | Mon 31/10/22 | Fri 31/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.3.1 |  |  |  |  | Run tender process | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.3.2 |  |  |  |  | Select provider & sign commercials | 100% | Wed 01/02/23 | Fri 31/03/23 | 43 days | Wed 01/02/23 | Fri 31/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.6.2 |  |  | DAG |  | Central Systems DBT | 100% | Mon 31/10/22 | Fri 26/01/24 | 325 days | Mon 31/10/22 | Fri 26/01/24 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
5 | 1.3.6.2.1 |  |  | DAG |  | Elexon Central Systems DBT CIT (Entering at Interval 1) | 100% | Mon 31/10/22 | Wed 11/10/23 | 248 days | Mon 31/10/22 | Wed 11/10/23 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
6 | 1.3.6.2.1.1 |  |  |  |  | Design and Build | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 22/09/23 | 0 days | 0 days | -5 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.1.1 |  |  |  |  | Helix Design and Build | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 22/09/23 | 0 days | 0 days | -5 days | PP |  | 5 | Yes
6 | 1.3.6.2.1.2 |  |  | DAG |  | Test Approach & Plan | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 22/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.2.1 |  |  |  |  | Develop Test Approach & Plan | 100% | Mon 31/10/22 | Fri 07/07/23 | 180 days | Mon 31/10/22 | Fri 07/07/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.2.2 | T3 | T3-DB-0029 | SITAG |  | Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Thu 13/07/23 | Thu 13/07/23 | 0 days | Thu 13/07/23 | Thu 13/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.2.3 |  |  |  |  | Elexon Central Systems Test Approach & Plan (PIT) V2 resubmitted to Programme for assurance | 100% | Thu 27/07/23 | Thu 27/07/23 | 0 days | Thu 27/07/23 | Thu 27/07/23 | 0 days | -1 day | 0 days | PP |  | 5.4 | Yes
7 | 1.3.6.2.1.2.4 |  |  |  |  | Elexon Central Systems Test Approach & Plan (PIT) V3 resubmitted to Programme for assurance | 100% | Fri 18/08/23 | Fri 18/08/23 | 0 days | Fri 18/08/23 | Fri 18/08/23 | 1 day | 0 days | 0 days | PP |  | 5.4 | Yes
7 | 1.3.6.2.1.2.5 | T3 | T3-DB-0106 | SITAG |  | Elexon Central Systems Test approach and plan MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.1.3 |  |  |  |  | Test Readiness Report | 100% | Fri 28/07/23 | Fri 18/08/23 | 16 days | Fri 28/07/23 | Fri 18/08/23 | 0 days | 0 days | -35 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.3.1 |  |  |  |  | Test readiness reporting | 100% | Fri 28/07/23 | Fri 18/08/23 | 16 days | Fri 28/07/23 | Fri 18/08/23 | 0 days | 0 days | -35 days | PP |  | 5 | Yes
6 | 1.3.6.2.1.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 04/08/23 | Fri 22/09/23 | 35 days | Fri 04/08/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.4.1 | T3 | T3-DB-0030 | SITAG | MHHS-ART009 | Elexon Central Systems RTTM submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.4.2 | T3 | T3-DB-0107 | SITAG |  | Elexon Central Systems RTTM MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.1.5 |  |  |  |  | Test Scenarios | 100% | Fri 04/08/23 | Fri 22/09/23 | 35 days | Fri 04/08/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.5.1 | T3 | T3-DB-0032 | SITAG |  | Elexon Central Systems test scenarios submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.5.2 | T3 | T3-DB-0108 | SITAG |  | Elexon Central Systems Test scenarios MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.1.6 |  |  |  |  | PIT Execution | 100% | Mon 21/08/23 | Wed 11/10/23 | 38 days | Mon 21/08/23 | Wed 11/10/23 | 0 days | 0 days | -210 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.6.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 04/09/23 | Wed 27/09/23 | 18 days | Mon 04/09/23 | Wed 27/09/23 | 0 days | 0 days | -217 days | PP |  | 5.1 | Yes
7 | 1.3.6.2.1.6.2 |  |  |  |  | Elexon Central Systems PIT Execution | 100% | Mon 21/08/23 | Wed 27/09/23 | 28 days | Mon 21/08/23 | Wed 27/09/23 | 0 days | 0 days | -212 days | PP |  | 5.1 | Yes
7 | 1.3.6.2.1.6.3 | T3 | T3-DB-0109 | SITAG |  | Elexon Central Systems PIT Completion Report submitted to Programme for assurance | 100% | Wed 27/09/23 | Wed 27/09/23 | 0 days | Wed 27/09/23 | Wed 27/09/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.2.1.6.4 | T3 | T3-DB-0110 | SITAG |  | Elexon Central Systems PIT Completion Report MHHS Review Completed | 100% | Wed 11/10/23 | Wed 11/10/23 | 0 days | Wed 11/10/23 | Wed 11/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
5 | 1.3.6.2.2 |  |  |  |  | DIP DBT CIT (Entering at Interval 1) | 100% | Mon 02/01/23 | Mon 06/11/23 | 221 days | Mon 02/01/23 | Mon 06/11/23 | 0 days | 0 days | -45 days | N/A |  | 5 | Yes
6 | 1.3.6.2.2.1 |  |  |  |  | Design | 100% | Mon 02/01/23 | Fri 21/04/23 | 80 days | Mon 02/01/23 | Fri 21/04/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.2.2.2 |  |  |  |  | Build | 100% | Mon 09/01/23 | Fri 11/08/23 | 155 days | Mon 09/01/23 | Fri 11/08/23 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
6 | 1.3.6.2.2.3 |  |  |  |  | Test Approach & Plan | 100% | Fri 07/07/23 | Thu 20/07/23 | 9 days | Fri 07/07/23 | Thu 20/07/23 | 1 day | 0 days | -181 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.3.1 | T3 | T3-DB-0026 | SITAG | MHHS-ART073 | DIP Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 07/07/23 | Fri 07/07/23 | 0 days | Fri 07/07/23 | Fri 07/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.2.3.2 |  |  |  |  | DIP Test Approach & Plan (PIT) MHHS Review Completed | 100% | Thu 20/07/23 | Thu 20/07/23 | 0 days | Thu 20/07/23 | Thu 20/07/23 | 1 day | 0 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.4 |  |  |  |  | PIT Test Readiness Report | 100% | Fri 21/07/23 | Fri 01/09/23 | 31 days | Fri 21/07/23 | Fri 01/09/23 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.4.1 |  |  |  |  | Test readiness reporting | 100% | Fri 21/07/23 | Fri 01/09/23 | 31 days | Fri 21/07/23 | Fri 01/09/23 | 0 days | 0 days | -20 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.5 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 04/08/23 | Wed 30/08/23 | 18 days | Fri 04/08/23 | Wed 30/08/23 | 1 day | 0 days | -192 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.5.1 | T3 | T3-DB-0034 | SITAG | MHHS-ART009 | DIP RTTM submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.2.5.2 |  |  |  |  | DIP RTTM MHHS Review Completed | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 1 day | 0 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.6 |  |  |  |  | Test Scenarios | 100% | Mon 31/07/23 | Wed 30/08/23 | 22 days | Mon 31/07/23 | Wed 30/08/23 | 1 day | 0 days | -184 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.6.1 | T3 | T3-DB-0036 | SITAG |  | DIP PIT test scenarios submitted to Programme for assurance | 100% | Mon 31/07/23 | Mon 31/07/23 | 0 days | Mon 31/07/23 | Mon 31/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.2.6.2 |  |  |  |  | DIP Test scenarios MHHS Review Completed | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 1 day | 0 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.7 |  |  |  |  | PIT execution | 100% | Tue 29/08/23 | Mon 06/11/23 | 50 days | Tue 29/08/23 | Mon 06/11/23 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.7.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Fri 01/09/23 | Mon 23/10/23 | 37 days | Fri 01/09/23 | Mon 23/10/23 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.2.7.2 |  |  |  |  | PIT Execution (Interim Release 1) | 100% | Tue 29/08/23 | Mon 09/10/23 | 30 days | Tue 29/08/23 | Mon 09/10/23 | 0 days | 0 days | 6 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.2.7.3 |  |  |  |  | PIT Execution (Interim Release 2) | 100% | Tue 10/10/23 | Mon 23/10/23 | 10 days | Tue 10/10/23 | Mon 23/10/23 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.2.7.4 | T3 | T3-DB-0111 | SITAG |  | DIP PIT Completion Report (Interim Release 1) submitted to Programme for assurance | 100% | Mon 09/10/23 | Mon 09/10/23 | 0 days | Mon 09/10/23 | Mon 09/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.2.2.7.5 | T3 | T3-DB-0112 | SITAG |  | DIP PIT Completion Report (Interim Release 1) MHHS Review Completed | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
7 | 1.3.6.2.2.7.6 | T3 | T3-DB-0113 | SITAG |  | DIP PIT Completion Report (Interim Release 2) submitted to Programme for assurance | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.3.6.2.2.7.7 | T3 | T3-DB-0114 | SITAG |  | DIP PIT Completion Report (Interim Release 2) MHHS Review Completed | 100% | Mon 06/11/23 | Mon 06/11/23 | 0 days | Mon 06/11/23 | Mon 06/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
5 | 1.3.6.2.3 |  |  |  |  | DCC (DSP) DBT SIT Functional (Entering at SIT Functional) | 100% | Mon 31/10/22 | Fri 26/01/24 | 325 days | Mon 31/10/22 | Fri 26/01/24 | 0 days | 0 days | -20 days | N/A |  | 5.18 | Yes
6 | 1.3.6.2.3.1 |  |  |  |  | Design | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5.18 | Yes
6 | 1.3.6.2.3.2 |  |  |  |  | Test Approach & Plan | 100% | Fri 17/11/23 | Fri 15/12/23 | 20 days | Fri 17/11/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.2.1 | T3 | T3-DB-0068 | SITAG |  | DCC Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5.18 | Yes
7 | 1.3.6.2.3.2.2 | T3 | T3-DB-0115 | SITAG |  | DCC Test Approach & Plan (PIT) MHHS Review Completed | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
6 | 1.3.6.2.3.3 |  |  |  |  | Test Readiness Report | 100% | Mon 04/12/23 | Tue 02/01/24 | 22 days | Mon 04/12/23 | Tue 02/01/24 | 0 days | 0 days | -29 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.3.1 |  |  |  |  | Test readiness reporting | 100% | Mon 04/12/23 | Tue 02/01/24 | 22 days | Mon 04/12/23 | Tue 02/01/24 | 0 days | 0 days | -29 days | PP |  | 5.18 | Yes
6 | 1.3.6.2.3.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 15/12/23 | Fri 26/01/24 | 30 days | Fri 15/12/23 | Fri 26/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.4.1 | T3 | T3-DB-0074 | SITAG |  | DCC RTTM submitted to Programme for assurance | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.18 | Yes
7 | 1.3.6.2.3.4.2 | T3 | T3-DB-0116 | SITAG |  | DCC RTTM MHHS Review Completed | 100% | Fri 26/01/24 | Fri 26/01/24 | 0 days | Fri 26/01/24 | Fri 26/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
6 | 1.3.6.2.3.5 |  |  |  |  | Test Scenarios | 100% | Fri 15/12/23 | Fri 26/01/24 | 30 days | Fri 15/12/23 | Fri 26/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.5.1 | T3 | T3-DB-0078 | SITAG |  | DCC test scenarios submitted to Programme for assurance | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.18 | Yes
7 | 1.3.6.2.3.5.2 | T3 | T3-DB-0117 | SITAG |  | DCC Test Scenarios MHHS Review Completed | 100% | Fri 26/01/24 | Fri 26/01/24 | 0 days | Fri 26/01/24 | Fri 26/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
5 | 1.3.6.2.4 |  |  |  |  | RECCo (EES) DBT CIT (Entering at Interval 6) | 100% | Fri 13/10/23 | Fri 19/01/24 | 71 days | Fri 13/10/23 | Fri 19/01/24 | 0 days | 0 days | -249 days | N/A |  | 5 | Yes
6 | 1.3.6.2.4.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 13/10/23 | Thu 09/11/23 | 20 days | Fri 13/10/23 | Thu 09/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.1.1 | T3 | T3-DB-0066 | SITAG |  | EES Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.2.4.1.2 | T3 | T3-DB-0119 | SITAG |  | EES Test approach and plan (PIT) MHHS Review Completed | 100% | Thu 09/11/23 | Thu 09/11/23 | 0 days | Thu 09/11/23 | Thu 09/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.4.2 |  |  |  |  | Test Readiness Report | 100% | Fri 27/10/23 | Thu 09/11/23 | 10 days | Fri 27/10/23 | Thu 09/11/23 | 0 days | 0 days | -41 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 27/10/23 | Thu 09/11/23 | 10 days | Fri 27/10/23 | Thu 09/11/23 | 0 days | 0 days | -41 days | PP |  | 5 | Yes
6 | 1.3.6.2.4.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 02/11/23 | Thu 30/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.3.1 | T3 | T3-DB-0072 | SITAG | MHHS-ART009 | EES RTTM submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.2.4.3.2 | T3 | T3-DB-0120 | SITAG |  | EES RTTM MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.2.4.4 |  |  |  |  | Test Scenarios | 100% | Thu 02/11/23 | Thu 30/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.4.1 | T3 | T3-DB-0031 | SITAG |  | EES test scenarios submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.2.4.4.2 | T3 | T3-DB-0121 | SITAG |  | EES Test scenarios MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.2.4.5 |  |  |  |  | PIT execution | 100% | Fri 10/11/23 | Fri 19/01/24 | 51 days | Fri 10/11/23 | Fri 19/01/24 | 0 days | 0 days | -269 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Fri 10/11/23 | Fri 05/01/24 | 41 days | Fri 10/11/23 | Fri 05/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.4.5.2 |  |  |  |  | PIT Execution | 100% | Fri 10/11/23 | Fri 05/01/24 | 41 days | Fri 10/11/23 | Fri 05/01/24 | 0 days | 0 days | -269 days | PP |  | 5 | Yes
7 | 1.3.6.2.4.5.3 | T3 | T3-DB-0122 | SITAG |  | EES PIT Completion Report submitted to Programme for assurance | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
7 | 1.3.6.2.4.5.4 | T3 | T3-DB-0123 | SITAG |  | EES PIT Completion Report MHHS Review Completed | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
5 | 1.3.6.2.5 |  |  |  |  | Registration Services DBT CIT (Entering at Interval 2) | 100% | Fri 28/07/23 | Fri 03/11/23 | 70 days | Fri 28/07/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.2.5.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 28/07/23 | Fri 22/09/23 | 40 days | Fri 28/07/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.1.1 | T3 | T3-DB-0028 | SITAG | MHHS-ART073 | Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 28/07/23 | Fri 28/07/23 | 0 days | Fri 28/07/23 | Fri 28/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.5.1.2 | T3 | T3-DB-0124 | SITAG |  | Registration Services Test approach and plan MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.5.2 |  |  |  |  | Test Readiness Report | 100% | Mon 14/08/23 | Fri 08/09/23 | 20 days | Mon 14/08/23 | Fri 08/09/23 | 0 days | 0 days | -31 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.2.1 |  |  |  |  | Test readiness reporting | 100% | Mon 14/08/23 | Fri 08/09/23 | 20 days | Mon 14/08/23 | Fri 08/09/23 | 0 days | 0 days | -31 days | PP |  | 5 | Yes
6 | 1.3.6.2.5.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 01/09/23 | Fri 29/09/23 | 20 days | Fri 01/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.3.1 | T3 | T3-DB-0042 | SITAG | MHHS-ART009 | Registration Services RTTM submitted to Programme for assurance | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.5.3.2 | T3 | T3-DB-0125 | SITAG |  | Registration Services RTTM MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.5.4 |  |  |  |  | Test Scenarios | 100% | Fri 01/09/23 | Fri 29/09/23 | 20 days | Fri 01/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.4.1 | T3 | T3-DB-0044 | SITAG |  | Registration Services test scenarios submitted to Programme for assurance | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.5.4.2 | T3 | T3-DB-0126 | SITAG |  | Registration Services Test scenarios MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.2.5.5 |  |  |  |  | PIT execution | 100% | Mon 11/09/23 | Fri 03/11/23 | 40 days | Mon 11/09/23 | Fri 03/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 11/09/23 | Wed 25/10/23 | 33 days | Mon 11/09/23 | Wed 25/10/23 | 0 days | 0 days | 3 days | PP |  | 5 | Yes
7 | 1.3.6.2.5.5.2 |  |  |  |  | PIT Execution | 100% | Mon 11/09/23 | Fri 20/10/23 | 30 days | Mon 11/09/23 | Fri 20/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.5.5.3 | T3 | T3-DB-0127 | SITAG |  | Registration Services PIT (CIT interval 2) Completion Report submitted to Programme for assurance | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Wed 25/10/23 | Wed 25/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.3.6.2.5.5.4 | T3 | T3-DB-0128 | SITAG |  | Registration Services PIT (CIT interval 2) Completion Report MHHS Review Completed | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
4 | 1.3.6.3 |  |  |  |  | SIT Participants DBT | 100% | Fri 11/08/23 | Fri 21/02/25 | 401 days | Fri 11/08/23 | Fri 20/12/24 | 0 days | 45 days | -94 days | N/A |  | 5 | Yes
5 | 1.3.6.3.1 |  |  |  |  | All Data Services DBT CIT (Entering at Interval 3) | 100% | Fri 11/08/23 | Fri 17/11/23 | 71 days | Fri 11/08/23 | Fri 17/11/23 | 0 days | 0 days | -204 days | N/A |  | 5 | Yes
6 | 1.3.6.3.1.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 11/08/23 | Thu 21/09/23 | 30 days | Fri 11/08/23 | Thu 21/09/23 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
7 | 1.3.6.3.1.1.1 | T3 | T3-DB-0038 | SITAG |  | All Data Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 11/08/23 | Fri 11/08/23 | 0 days | Fri 11/08/23 | Fri 11/08/23 | 0 days | -1 day | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.1.2 | T3 | T3-DB-0129 | SITAG |  | All Data Services Test approach and plans MHHS Review Completed | 100% | Thu 21/09/23 | Thu 21/09/23 | 0 days | Thu 21/09/23 | Thu 21/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.3.6.3.1.2 |  |  |  |  | Test Readiness Report | 100% | Fri 25/08/23 | Fri 08/09/23 | 11 days | Fri 25/08/23 | Fri 08/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 25/08/23 | Fri 08/09/23 | 11 days | Fri 25/08/23 | Fri 08/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.3.1.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Wed 20/09/23 | Fri 29/09/23 | 7 days | Wed 20/09/23 | Fri 29/09/23 | 1 day | 0 days | 2 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.3.1 | T3 | T3-DB-0058 | SITAG |  | All Data Services RTTMs submitted to Programme for assurance | 100% | Wed 20/09/23 | Wed 20/09/23 | 0 days | Wed 20/09/23 | Wed 20/09/23 | 1 day | 0 days | 0 days | PP |  | 5.7 | Yes
7 | 1.3.6.3.1.3.2 | T3 | T3-DB-0130 | SITAG |  | All Data Services RTTMs MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.1.4 |  |  |  |  | Test Scenarios | 100% | Wed 20/09/23 | Thu 28/09/23 | 6 days | Wed 20/09/23 | Thu 28/09/23 | 1 day | 0 days | 2 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.4.1 | T3 | T3-DB-0056 | SITAG |  | All Data Services test scenarios' submitted to Programme for assurance | 100% | Wed 20/09/23 | Wed 20/09/23 | 0 days | Wed 20/09/23 | Wed 20/09/23 | 1 day | 0 days | 0 days | PP |  | 5.7 | Yes
7 | 1.3.6.3.1.4.2 | T3 | T3-DB-0131 | SITAG |  | All Data Services Test scenarios' MHHS Review Completed | 100% | Thu 28/09/23 | Thu 28/09/23 | 0 days | Thu 28/09/23 | Thu 28/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.3.6.3.1.5 |  |  |  |  | PIT execution | 100% | Mon 11/09/23 | Fri 17/11/23 | 50 days | Mon 11/09/23 | Fri 17/11/23 | 0 days | 0 days | -225 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 11/09/23 | Fri 03/11/23 | 40 days | Mon 11/09/23 | Fri 03/11/23 | 0 days | 0 days | -220 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.5.2 |  |  |  |  | PIT Execution | 100% | Thu 28/09/23 | Fri 03/11/23 | 27 days | Thu 28/09/23 | Fri 03/11/23 | 0 days | 0 days | -238 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.5.3 | T3 | T3-DB-0132 | SITAG |  | All Data Services PIT Completion Reports submitted to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5.11 | Yes
7 | 1.3.6.3.1.5.4 | T3 | T3-DB-0133 | SITAG |  | All Data Services PIT Completion Reports MHHS Review Completed | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
5 | 1.3.6.3.2 |  |  |  |  | All Metering Services DBT CIT (Entering at Interval 4) | 100% | Fri 25/08/23 | Fri 01/12/23 | 70 days | Fri 25/08/23 | Fri 01/12/23 | 1 day | 0 days | -215 days | N/A |  | 5 | Yes
6 | 1.3.6.3.2.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 25/08/23 | Fri 20/10/23 | 40 days | Fri 25/08/23 | Fri 20/10/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.1.1 | T3 | T3-DB-0040 | SITAG |  | All Metering Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 25/08/23 | Fri 25/08/23 | 0 days | Fri 25/08/23 | Fri 25/08/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.2.1.2 | T3 | T3-DB-0134 | SITAG |  | All Metering Services Test approach and plans MHHS Review Completed | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.2.2 |  |  |  |  | Test Readiness Report | 100% | Mon 11/09/23 | Mon 25/09/23 | 11 days | Mon 11/09/23 | Mon 25/09/23 | 0 days | 0 days | -40 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.2.1 |  |  |  |  | Test readiness reporting | 100% | Mon 11/09/23 | Mon 25/09/23 | 11 days | Mon 11/09/23 | Mon 25/09/23 | 0 days | 0 days | -40 days | PP |  | 5 | Yes
6 | 1.3.6.3.2.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 15/09/23 | Fri 27/10/23 | 30 days | Fri 15/09/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.3.1 | T3 | T3-DB-0048 | SITAG | MHHS-ART009 | All Metering Services RTTMs submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.2.3.2 | T3 | T3-DB-0135 | SITAG |  | All Metering Services MHHS Reviews Completed | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
6 | 1.3.6.3.2.4 |  |  |  |  | Test Scenarios | 100% | Fri 15/09/23 | Fri 27/10/23 | 30 days | Fri 15/09/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.4.1 | T3 | T3-DB-0050 | SITAG |  | All Metering Services test scenarios' submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.2.4.2 | T3 | T3-DB-0136 | SITAG |  | All Metering Services Test scenarios' MHHS Review Completed | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
6 | 1.3.6.3.2.5 |  |  |  |  | PIT execution | 100% | Mon 25/09/23 | Fri 01/12/23 | 50 days | Mon 25/09/23 | Fri 01/12/23 | 0 days | 0 days | -235 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Tue 26/09/23 | Fri 17/11/23 | 39 days | Tue 26/09/23 | Fri 17/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.2.5.2 |  |  |  |  | PIT Execution | 100% | Mon 25/09/23 | Fri 17/11/23 | 40 days | Mon 25/09/23 | Fri 17/11/23 | 0 days | 0 days | -235 days | PP |  | 5 | Yes
7 | 1.3.6.3.2.5.3 | T3 | T3-DB-0137 | SITAG |  | All Metering Services PIT Completion Reports submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5.13 | Yes
7 | 1.3.6.3.2.5.4 | T3 | T3-DB-0138 | SITAG |  | All Metering Services PIT Completion Reports MHHS Review Completed | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
5 | 1.3.6.3.3 |  |  |  |  | All SIT Programme Participants PIT (SIT Functional) | 100% | Fri 17/11/23 | Fri 21/02/25 | 331 days | Fri 17/11/23 | Fri 20/12/24 | 0 days | 45 days | -120 days | N/A |  | 5 | Yes
6 | 1.3.6.3.3.1 |  |  |  |  | Test Approach & Plans | 100% | Fri 17/11/23 | Thu 11/01/24 | 40 days | Fri 17/11/23 | Thu 11/01/24 | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.1.1 | T3 | T3-DB-0093 | SITAG |  | SIT Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 0 days | -1 day | 0 days | PP |  | 5.16 | Yes
7 | 1.3.6.3.3.1.2 | T3 | T3-DB-0139 | SITAG |  | All SIT Functional Test approach and plans MHHS Reviews Completed | 100% | Thu 11/01/24 | Thu 11/01/24 | 0 days | Thu 11/01/24 | Thu 11/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.3.2 |  |  |  |  | Test Readiness Reports | 100% | Fri 01/12/23 | Fri 15/12/23 | 11 days | Fri 01/12/23 | Fri 15/12/23 | 0 days | 0 days | -40 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 01/12/23 | Fri 15/12/23 | 11 days | Fri 01/12/23 | Fri 15/12/23 | 0 days | 0 days | -40 days | PP |  | 5.2 | Yes
6 | 1.3.6.3.3.3 |  |  |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | Thu 07/12/23 | Thu 18/01/24 | 30 days | Thu 07/12/23 | Thu 18/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.3.1 | T3 | T3-DB-0091 | SITAG |  | SIT Functional PIT RTTM submitted to Programme for assurance | 100% | Thu 07/12/23 | Thu 07/12/23 | 0 days | Thu 07/12/23 | Thu 07/12/23 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
7 | 1.3.6.3.3.3.2 | T3 | T3-DB-0140 | SITAG |  | All SIT Functional RTTMs MHHS Reviews Completed | 100% | Thu 18/01/24 | Thu 18/01/24 | 0 days | Thu 18/01/24 | Thu 18/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.3.3.4 |  |  |  |  | Test Scenarios | 100% | Thu 07/12/23 | Thu 18/01/24 | 30 days | Thu 07/12/23 | Thu 18/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.4.1 | T3 | T3-DB-0089 | SITAG |  | SIT Functional PIT test scenarios submitted to Programme for assurance | 100% | Thu 07/12/23 | Thu 07/12/23 | 0 days | Thu 07/12/23 | Thu 07/12/23 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
7 | 1.3.6.3.3.4.2 | T3 | T3-DB-0141 | SITAG |  | All SIT Functional Test scenarios' MHHS Reviews Completed | 100% | Thu 18/01/24 | Thu 18/01/24 | 0 days | Thu 18/01/24 | Thu 18/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.3.3.5 |  |  |  |  | PIT execution | 100% | Fri 15/12/23 | Fri 23/02/24 | 51 days | Fri 15/12/23 | Fri 23/02/24 | 0 days | 0 days | -250 days | N/A |  | 5 | Yes
7 | 1.3.6.3.3.5.1 |  |  |  |  | PIT Test Execution Progress Reports | 100% | Mon 18/12/23 | Fri 09/02/24 | 40 days | Mon 18/12/23 | Fri 09/02/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.3.5.2 |  |  |  |  | PIT Execution | 100% | Fri 15/12/23 | Fri 09/02/24 | 41 days | Fri 15/12/23 | Fri 09/02/24 | 0 days | 0 days | -249 days | PP |  | 5 | Yes
7 | 1.3.6.3.3.5.3 | T3 | T3-DB-0087 | SITAG |  | All SIT Functional PIT Completion Reports submitted to Programme for Assurance | 100% | Fri 09/02/24 | Fri 09/02/24 | 0 days | Fri 09/02/24 | Fri 09/02/24 | 1 day | 0 days | 0 days | PP |  | 5.19 | Yes
7 | 1.3.6.3.3.5.4 | T3 | T3-DB-0142 | SITAG |  | All SIT Functional PIT Completion Reports MHHS Review Completed | 100% | Fri 23/02/24 | Fri 23/02/24 | 0 days | Fri 23/02/24 | Fri 23/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes
6 | 1.3.6.3.3.6 |  |  |  |  | All SIT Programme Participants PIT (SIT Migration) | 100% | Fri 16/02/24 | Fri 24/05/24 | 71 days | Fri 16/02/24 | Fri 24/05/24 | 0 days | 0 days | -230 days | N/A |  | 5.1 | Yes
7 | 1.3.6.3.3.6.1 |  |  |  |  | Test Approach & Plans | 100% | Fri 16/02/24 | Thu 11/04/24 | 40 days | Fri 16/02/24 | Thu 11/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.1.1 | T3 | T3-DB-0143 | SITAG |  | All SIT Migration PIT Test Approach & Plans submitted to Programme for assurance | 100% | Fri 16/02/24 | Fri 16/02/24 | 0 days | Fri 16/02/24 | Fri 16/02/24 | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.3.3.6.1.2 | T3 | T3-DB-0144 | SITAG |  | All SIT Migration PIT Test approach and plans MHHS Reviews Completed | 100% | Thu 11/04/24 | Thu 11/04/24 | 0 days | Thu 11/04/24 | Thu 11/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.23 | Yes
7 | 1.3.6.3.3.6.2 |  |  |  |  | Test Readiness Reports | 100% | Fri 01/03/24 | Fri 15/03/24 | 11 days | Fri 01/03/24 | Fri 15/03/24 | 0 days | 0 days | -40 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 01/03/24 | Fri 15/03/24 | 11 days | Fri 01/03/24 | Fri 15/03/24 | 0 days | 0 days | -40 days | PP |  | 5.2 | Yes
7 | 1.3.6.3.3.6.3 |  |  |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | Thu 07/03/24 | Thu 18/04/24 | 30 days | Thu 07/03/24 | Thu 18/04/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.3.1 | T3 | T3-DB-0145 | SITAG |  | All SIT Migration PIT RTTMs submitted to Programme for assurance | 100% | Thu 07/03/24 | Thu 07/03/24 | 0 days | Thu 07/03/24 | Thu 07/03/24 | 1 day | 0 days | 0 days | PP |  | 5.23 | Yes
8 | 1.3.6.3.3.6.3.2 | T3 | T3-DB-0146 | SITAG |  | All SIT Migration RTTMs MHHS Reviews Completed | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.25 | Yes
7 | 1.3.6.3.3.6.4 |  |  |  |  | Test Scenarios | 100% | Thu 07/03/24 | Thu 18/04/24 | 30 days | Thu 07/03/24 | Thu 18/04/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.4.1 | T3 | T3-DB-0147 | SITAG |  | All SIT Migration PIT test scenarios submitted to Programme for assurance | 100% | Thu 07/03/24 | Thu 07/03/24 | 0 days | Thu 07/03/24 | Thu 07/03/24 | 1 day | 0 days | 0 days | PP |  | 5.23 | Yes
8 | 1.3.6.3.3.6.4.2 | T3 | T3-DB-0148 | SITAG |  | All SIT Migration Test scenarios MHHS Reviews Completed | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.25 | Yes
7 | 1.3.6.3.3.6.5 |  |  |  |  | PIT execution | 100% | Fri 15/03/24 | Fri 24/05/24 | 51 days | Fri 15/03/24 | Fri 24/05/24 | 0 days | 0 days | -250 days | N/A |  | 5.1 | Yes
8 | 1.3.6.3.3.6.5.1 |  |  |  |  | PIT Test Execution Progress Reports | 100% | Mon 18/03/24 | Fri 10/05/24 | 40 days | Mon 18/03/24 | Fri 10/05/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.6.5.2 |  |  |  |  | PIT Execution | 100% | Fri 15/03/24 | Fri 10/05/24 | 41 days | Fri 15/03/24 | Fri 10/05/24 | 0 days | 0 days | -249 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.6.5.3 | T3 | T3-DB-0149 | SITAG |  | All SIT Migration PIT Completion Reports submitted to Programme for assurance | 100% | Fri 10/05/24 | Fri 10/05/24 | 0 days | Fri 10/05/24 | Fri 10/05/24 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.3.3.6.5.4 | T3 | T3-DB-0150 | SITAG |  | All SIT Migration PIT Completion Reports MHHS Review Completed | 100% | Fri 24/05/24 | Fri 24/05/24 | 0 days | Fri 24/05/24 | Fri 24/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.3.7 |  |  |  |  | All SIT Programme Participants PIT (SIT Non Functional) | 100% | Fri 12/07/24 | Fri 21/02/25 | 161 days | Fri 12/07/24 | Fri 20/12/24 | 0 days | 45 days | -140 days | N/A |  | 6 | Yes
7 | 1.3.6.3.3.7.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 27/09/24 | Fri 22/11/24 | 41 days | Fri 27/09/24 | Fri 22/11/24 | 0 days | 0 days | 1 day | N/A |  | 6 | Yes
8 | 1.3.6.3.3.7.1.1 | T3 | T3-DB-0151 | SITAG |  | SIT Non-Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 0 days | -1 day | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.7.1.2 | T3 | T3-DB-0152 | SITAG |  | SIT Non-Functional Test approach and plan MHHS Review Completed | 100% | Thu 21/11/24 | Fri 22/11/24 | 1 day | Thu 21/11/24 | Fri 22/11/24 | 0 days | 0 days | 1 day | SI Test |  | 6 | Yes
7 | 1.3.6.3.3.7.2 |  |  |  |  | Test Readiness Report | 100% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 04/10/24 | Tue 22/10/24 | 0 days | 0 days | -38 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.7.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 04/10/24 | Tue 22/10/24 | 0 days | 0 days | -38 days | PP |  | 6 | Yes
7 | 1.3.6.3.3.7.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Fri 01/11/24 | Fri 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.7.3.1 | T3 | T3-DB-0153 | SITAG |  | SIT Non-Functional PIT RTTM submitted to Programme for assurance | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.7.3.2 | T3 | T3-DB-0154 | SITAG |  | SIT Non-Functional RTTM MHHS Review Completed | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.3.6.3.3.7.4 |  |  |  |  | Test Scenarios | 100% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Fri 01/11/24 | Fri 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.7.4.1 | T3 | T3-DB-0155 | SITAG |  | SIT Non-Functional PIT test scenarios submitted to Programme for assurance | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.7.4.2 | T3 | T3-DB-0156 | SITAG |  | SIT Non-Functional Test scenarios MHHS Review Completed | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.3.6.3.3.7.5 |  |  |  |  | PIT execution | 100% | Fri 12/07/24 | Fri 21/02/25 | 161 days | Fri 12/07/24 | Fri 20/12/24 | 0 days | 45 days | -140 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.7.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 15/07/24 | Thu 21/11/24 | 50 days | Mon 15/07/24 | Thu 21/11/24 | 0 days | 0 days | 11 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.7.5.2 |  |  |  |  | PIT Execution | 100% | Fri 12/07/24 | Fri 29/11/24 | 44 days | Fri 12/07/24 | Fri 29/11/24 | 0 days | 0 days | -246 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.7.5.3 | T3 | T3-DB-0157 | SITAG |  | SIT Non-Functional PIT Completion Report submitted to Programme for assurance | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.7.5.4 | T3 | T3-DB-0158 | SITAG |  | SIT Non-Functional PIT Completion Report Theme 1 MHHS Review Completed | 100% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
8 | 1.3.6.3.3.7.5.5 | T3 | T3-DB-0186 | SITAG |  | SIT Non-Functional PIT Completion Report Theme 2 & 3 MHHS Review Completed | 100% | Fri 21/02/25 | Fri 21/02/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
6 | 1.3.6.3.3.8 |  |  |  |  | SIT Programme Participants PIT (SIT Operational Theme 1, 2, 3 (Batch 2)) | 100% | Fri 12/07/24 | Fri 31/01/25 | 146 days | Fri 12/07/24 | Fri 20/12/24 | 0 days | 30 days | 75 days | N/A |  | 6 | Yes
7 | 1.3.6.3.3.8.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 27/09/24 | Thu 21/11/24 | 40 days | Fri 27/09/24 | Thu 21/11/24 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.8.1.1 | T3 | T3-DB-0159 | SITAG |  | SIT Operational PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 0 days | -1 day | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.8.1.2 | T3 | T3-DB-0160 | SITAG |  | SIT Operational Test approach and plan MHHS Review Completed | 100% | Thu 21/11/24 | Thu 21/11/24 | 0 days | Thu 21/11/24 | Thu 21/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.3.6.3.3.8.2 |  |  |  |  | Test Readiness Report | 100% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 04/10/24 | Tue 22/10/24 | 0 days | 0 days | -38 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.8.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 04/10/24 | Tue 22/10/24 | 0 days | 0 days | -38 days | PP |  | 6 | Yes
7 | 1.3.6.3.3.8.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Fri 01/11/24 | Fri 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.8.3.1 | T3 | T3-DB-0161 | SITAG |  | SIT Operational PIT RTTM submitted to Programme for assurance | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.8.3.2 | T3 | T3-DB-0162 | SITAG |  | SIT Operational RTTM MHHS Review Completed | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.3.6.3.3.8.4 |  |  |  |  | Test Scenarios | 100% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Fri 01/11/24 | Fri 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.8.4.1 | T3 | T3-DB-0163 | SITAG |  | SIT Operational PIT test scenarios submitted to Programme for assurance | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.8.4.2 | T3 | T3-DB-0164 | SITAG |  | SIT Operational Test scenarios MHHS Review Completed | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.3.6.3.3.8.5 |  |  |  |  | PIT execution | 100% | Fri 12/07/24 | Fri 31/01/25 | 146 days | Fri 12/07/24 | Fri 20/12/24 | 0 days | 30 days | 95 days | N/A |  | 6 | Yes
8 | 1.3.6.3.3.8.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 15/07/24 | Thu 21/11/24 | 40 days | Mon 15/07/24 | Thu 21/11/24 | 0 days | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.8.5.2 |  |  |  |  | PIT Execution | 100% | Fri 12/07/24 | Fri 29/11/24 | 39 days | Fri 12/07/24 | Fri 29/11/24 | 0 days | 0 days | -2 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.8.5.3 | T3 | T3-DB-0165 | SITAG |  | SIT Operational Theme 1, 2, 3 (Batch 2) PIT Completion Report submitted to Programme for assurance | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 33 days | 32 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.3.3.8.5.4 | T3 | T3-DB-0166 | SITAG |  | SIT Operational Theme 1, 2, 3 (Batch 2) PIT Completion Report MHHS Review Completed | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.3.3.9 |  |  |  |  | SIT Programme Participants PIT (SIT Operational Theme 3 (Batch 1)) | 100% | Fri 27/09/24 | Fri 10/01/25 | 76 days | Fri 27/09/24 | Fri 10/01/25 | 0 days | 0 days | 76 days | SI Test |  | 6.17 | Yes
7 | 1.3.6.3.3.9.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 27/09/24 | Thu 21/11/24 | 40 days | Fri 27/09/24 | Thu 21/11/24 | 0 days | 0 days | 40 days | SI Test |  | 6.17 | Yes
7 | 1.3.6.3.3.9.2 |  |  |  |  | Test Readiness Report | 100% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 04/10/24 | Tue 22/10/24 | 0 days | 0 days | 13 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 04/10/24 | Tue 22/10/24 | 0 days | 0 days | 13 days | SI Test |  | 6.17 | Yes
7 | 1.3.6.3.3.9.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Fri 01/11/24 | Fri 29/11/24 | 1 day | 0 days | 20 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.3.1 |  |  |  |  | SIT Operational PIT RTTM submitted to Programme for assurance | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.3.2 |  |  |  |  | SIT Operational RTTM MHHS Review Completed | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.3.6.3.3.9.4 |  |  |  |  | Test Scenarios | 100% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Fri 01/11/24 | Fri 29/11/24 | 1 day | 0 days | 20 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.4.1 |  |  |  |  | SIT Operational PIT test scenarios submitted to Programme for assurance | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.4.2 |  |  |  |  | SIT Operational Test scenarios MHHS Review Completed | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.3.6.3.3.9.5 |  |  |  |  | PIT execution | 100% | Wed 23/10/24 | Fri 10/01/25 | 58 days | Wed 23/10/24 | Fri 10/01/25 | 0 days | 0 days | 58 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Wed 23/10/24 | Tue 17/12/24 | 40 days | Wed 23/10/24 | Tue 17/12/24 | 0 days | 0 days | 40 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.5.2 |  |  |  |  | PIT Execution | 100% | Mon 04/11/24 | Thu 26/12/24 | 39 days | Mon 04/11/24 | Thu 26/12/24 | 0 days | 0 days | 39 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.5.3 |  |  |  |  | SIT Operational Theme 3 (Batch 1) PIT Completion Report submitted to Programme for assurance | 100% | Fri 10/01/25 | Fri 10/01/25 | 0 days | Fri 10/01/25 | Fri 10/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.3.6.3.3.9.5.4 |  |  |  |  | SIT Operational Theme 3 (Batch 1) PIT Completion Report MHHS Review Completed | 100% | Fri 10/01/25 | Fri 10/01/25 | 0 days | Fri 10/01/25 | Fri 10/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
5 | 1.3.6.3.4 |  |  |  |  | All Suppliers DBT CIT (Entering at Interval 5) | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Fri 15/09/23 | Fri 22/12/23 | 0 days | 0 days | -229 days | N/A |  | 6 | Yes
6 | 1.3.6.3.4.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 15/09/23 | Thu 12/10/23 | 20 days | Fri 15/09/23 | Thu 12/10/23 | 0 days | 0 days | 1 day | N/A |  | 6 | Yes
7 | 1.3.6.3.4.1.1 | T3 | T3-DB-0046 | SITAG |  | All SIT Suppliers Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 0 days | -1 day | 0 days | PP |  | 6 | Yes
7 | 1.3.6.3.4.1.2 | T3 | T3-DB-0167 | SITAG |  | All SIT Suppliers Test Approach & Plans MHHS Review Completed | 100% | Thu 12/10/23 | Thu 12/10/23 | 0 days | Thu 12/10/23 | Thu 12/10/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.3.4.2 |  |  |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 13/10/23 | 0 days | 0 days | -40 days | N/A |  | 6 | Yes
7 | 1.3.6.3.4.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 13/10/23 | 0 days | 0 days | -40 days | PP |  | 6 | Yes
6 | 1.3.6.3.4.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 06/10/23 | Fri 03/11/23 | 20 days | Fri 06/10/23 | Fri 03/11/23 | 1 day | 0 days | -1 day | N/A |  | 6 | Yes
7 | 1.3.6.3.4.3.1 | T3 | T3-DB-0064 | SITAG | MHHS-ART009 | All SIT Suppliers RTTMs submitted to Programme for assurance | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 1 day | 0 days | -1 day | PP |  | 6 | Yes
7 | 1.3.6.3.4.3.2 | T3 | T3-DB-0168 | SITAG |  | All SIT Suppliers RTTMs MHHS Review Completed | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.3.4.4 |  |  |  |  | Test Scenarios | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | N/A |  | 6 | Yes
7 | 1.3.6.3.4.4.1 | T3 | T3-DB-0037 | SITAG |  | All SIT Suppliers test scenarios' submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
7 | 1.3.6.3.4.4.2 | T3 | T3-DB-0169 | SITAG |  | All SIT Suppliers Test scenarios' MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.3.4.5 |  |  |  |  | PIT execution | 100% | Fri 13/10/23 | Fri 22/12/23 | 51 days | Fri 13/10/23 | Fri 22/12/23 | 0 days | 0 days | -249 days | N/A |  | 6 | Yes
7 | 1.3.6.3.4.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 16/10/23 | Fri 08/12/23 | 40 days | Mon 16/10/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | PP |  | 6 | Yes
7 | 1.3.6.3.4.5.2 |  |  |  |  | PIT Execution | 100% | Fri 13/10/23 | Fri 08/12/23 | 41 days | Fri 13/10/23 | Fri 08/12/23 | 0 days | 0 days | -249 days | PP |  | 6 | Yes
7 | 1.3.6.3.4.5.3 | T3 | T3-DB-0170 | SITAG |  | All SIT Suppliers PIT Completion Reports submitted to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
7 | 1.3.6.3.4.5.4 | T3 | T3-DB-0171 | SITAG |  | All SIT Suppliers PIT Completion Reports MHHS Review Completed | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
5 | 1.3.6.3.5 |  |  |  |  | All LDSO Network Operations DBT CIT (Entering at Interval 5) | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Fri 15/09/23 | Fri 22/12/23 | 0 days | 0 days | -239 days | N/A |  | 5 | Yes
6 | 1.3.6.3.5.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Fri 15/09/23 | Fri 22/12/23 | 0 days | 0 days | -239 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.1.1 | T3 | T3-DB-0054 | SITAG |  | All Network Operation Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.5.1.2 | T3 | T3-DB-0172 | SITAG |  | All Network Operation Test Approach & Plans MHHS Review Completed | 100% | Thu 12/10/23 | Thu 12/10/23 | 0 days | Thu 12/10/23 | Thu 12/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
7 | 1.3.6.3.5.1.3 |  |  |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 13/10/23 | 0 days | 0 days | -40 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.3.1 |  |  |  |  | Test readiness reporting | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 13/10/23 | 0 days | 0 days | -40 days | PP |  | 5 | Yes
7 | 1.3.6.3.5.1.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.4.1 | T3 | T3-DB-0062 | SITAG | MHHS-ART009 | All Network Operation RTTMs submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.3.5.1.4.2 | T3 | T3-DB-0173 | SITAG |  | All Network Operation RTTMs MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.3.6.3.5.1.5 |  |  |  |  | Test Scenarios | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.5.1 | T3 | T3-DB-0011 | SITAG |  | All Network Operation test scenarios' submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.3.5.1.5.2 | T3 | T3-DB-0174 | SITAG |  | All Network Operation test scenarios' MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.3.6.3.5.1.6 |  |  |  |  | PIT execution | 100% | Fri 13/10/23 | Fri 22/12/23 | 51 days | Fri 13/10/23 | Fri 22/12/23 | 0 days | 0 days | -259 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.6.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 16/10/23 | Fri 08/12/23 | 40 days | Mon 16/10/23 | Fri 08/12/23 | 0 days | 0 days | -265 days | PP |  | 5 | Yes
8 | 1.3.6.3.5.1.6.2 |  |  |  |  | PIT Execution | 100% | Fri 13/10/23 | Fri 08/12/23 | 41 days | Fri 13/10/23 | Fri 08/12/23 | 0 days | 0 days | -269 days | PP |  | 5 | Yes
8 | 1.3.6.3.5.1.6.3 | T3 | T3-DB-0175 | SITAG |  | All Network Operation PIT (CIT interval 5) Completion Reports submitted to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.3.6.3.5.1.6.4 | T3 | T3-DB-0176 | SITAG |  | All Network Operation PIT (CIT interval 5) Completion Reports MHHS Review Completed | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.15 | Yes
5 | 1.3.6.3.6 |  |  |  |  | All UMSO DBT CIT (Entering at Interval 6) | 100% | Fri 29/09/23 | Fri 19/01/24 | 81 days | Fri 29/09/23 | Fri 19/01/24 | 0 days | 0 days | -239 days | N/A |  | 5 | Yes
6 | 1.3.6.3.6.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 13/10/23 | Thu 09/11/23 | 20 days | Fri 13/10/23 | Thu 09/11/23 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.1.1 | T3 | T3-DB-0052 | SITAG |  | All UMSO Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 | 0 days | -1 day | 0 days | PP |  | 5.11 | Yes
7 | 1.3.6.3.6.1.2 | T3 | T3-DB-0177 | SITAG |  | All UMSO Test Approach & Plans MHHS Review Completed | 100% | Thu 09/11/23 | Thu 09/11/23 | 0 days | Thu 09/11/23 | Thu 09/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
6 | 1.3.6.3.6.2 |  |  |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 13/10/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 27/10/23 | Fri 10/11/23 | 11 days | Fri 27/10/23 | Fri 10/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.3.6.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 05/10/23 | Wed 01/11/23 | 20 days | Thu 05/10/23 | Wed 01/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.3.1 | T3 | T3-DB-0060 | SITAG | MHHS-ART009 | All UMSO RTTMs submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
7 | 1.3.6.3.6.3.2 | T3 | T3-DB-0178 | SITAG |  | All UMSO RTTMs MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
6 | 1.3.6.3.6.4 |  |  |  |  | Test Scenarios | 100% | Thu 05/10/23 | Wed 01/11/23 | 20 days | Thu 05/10/23 | Wed 01/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.4.1 | T3 | T3-DB-0025 | SITAG |  | All UMSO test scenarios' submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
7 | 1.3.6.3.6.4.2 | T3 | T3-DB-0179 | SITAG |  | All UMSO Test scenarios' MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
6 | 1.3.6.3.6.5 |  |  |  |  | PIT execution | 100% | Fri 10/11/23 | Fri 19/01/24 | 51 days | Fri 10/11/23 | Fri 19/01/24 | 0 days | 0 days | -269 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 13/11/23 | Fri 05/01/24 | 40 days | Mon 13/11/23 | Fri 05/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.6.5.2 |  |  |  |  | PIT Execution | 100% | Fri 10/11/23 | Thu 04/01/24 | 40 days | Fri 10/11/23 | Thu 04/01/24 | 0 days | 0 days | -250 days | PP |  | 5 | Yes
7 | 1.3.6.3.6.5.3 | T3 | T3-DB-0180 | SITAG |  | All UMSO PIT (CIT interval 6) Completion Reports submitted to Programme for assurance | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.3.6.3.6.5.4 | T3 | T3-DB-0181 | SITAG |  | All UMSO PIT (CIT interval 6) Completion Reports MHHS Review Completed | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
3 | 1.3.7 |  |  |  |  | DBT Monitoring and Assurance | 99% | Mon 31/10/22 | Tue 20/01/26 | 842 days | Mon 31/10/22 | Tue 20/01/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.7.1 |  |  |  |  | Planning and DBT Progress Monitoring of PPs | 100% | Mon 31/10/22 | Mon 30/06/25 | 696 days | Mon 31/10/22 | Mon 30/06/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.1.1 |  |  |  |  | Monitor Non-SIT PPs Planning and DBT1 progress (to inform confirmation of Qualification Testing Tranche participants milestones) | 100% | Mon 31/10/22 | Mon 30/06/25 | 696 days | Mon 31/10/22 | Mon 30/06/25 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.3.7.2 |  |  |  |  | DBT Progress Monitoring of Consequential Change | 96% | Thu 02/02/23 | Tue 20/01/26 | 774 days | Thu 02/02/23 | Tue 20/01/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 28/01/26 - Activity was superseded, thus has been removed from the plan
5 | 1.3.7.2.1 |  |  |  |  | Monitor & report data cleanse progress | 96% | Thu 02/02/23 | Tue 20/01/26 | 774 days | Thu 02/02/23 | Tue 20/01/26 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 28/01/26 - Activity was superseded, thus has been removed from the plan
4 | 1.3.7.3 |  |  |  |  | Design Assurance | 100% | Mon 14/11/22 | Wed 06/08/25 | 713 days | Mon 14/11/22 | Wed 06/08/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.3.1 |  |  |  |  | Design Assurance Readiness Assessment Preparation | 100% | Tue 28/02/23 | Fri 21/04/23 | 39 days | Tue 28/02/23 | Fri 21/04/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.1.1 |  |  |  |  | Set up FTIG | 100% | Mon 03/04/23 | Fri 21/04/23 | 15 days | Mon 03/04/23 | Fri 21/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.2 |  |  |  |  | Produce Draft Questions | 100% | Tue 28/02/23 | Mon 13/03/23 | 10 days | Tue 28/02/23 | Mon 13/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.3 |  |  |  |  | Pilot with SRO | 100% | Tue 14/03/23 | Tue 14/03/23 | 1 day | Tue 14/03/23 | Tue 14/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.4 |  |  |  |  | Finalise questions | 100% | Wed 15/03/23 | Tue 28/03/23 | 10 days | Wed 15/03/23 | Tue 28/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.5 |  |  |  |  | Prepare on-line RA tooling | 100% | Wed 29/03/23 | Tue 11/04/23 | 10 days | Wed 29/03/23 | Tue 11/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.6 |  |  |  |  | Prepare webinar content | 100% | Mon 20/03/23 | Fri 24/03/23 | 5 days | Mon 20/03/23 | Fri 24/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.7 |  |  |  |  | Conduct webinar | 100% | Thu 30/03/23 | Thu 30/03/23 | 1 day | Thu 30/03/23 | Thu 30/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.7.3.2 |  |  |  |  | Participant Design Assurance Approach | 100% | Mon 14/11/22 | Wed 11/01/23 | 43 days | Mon 14/11/22 | Wed 11/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.2.1 |  |  |  |  | Develop document | 100% | Mon 14/11/22 | Fri 09/12/22 | 20 days | Mon 14/11/22 | Fri 09/12/22 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.2.2 |  |  |  |  | Review document | 100% | Mon 12/12/22 | Wed 04/01/23 | 18 days | Mon 12/12/22 | Wed 04/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.2.3 | T3 | T3-DB-0012 | DAG |  | Participant Design Assurance Approach approved | 100% | Wed 11/01/23 | Wed 11/01/23 | 0 days | Wed 11/01/23 | Wed 11/01/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.7.3.3 |  |  |  |  | Phase 1 - SIT Volunteers (Core Providers) | 100% | Mon 10/04/23 | Fri 27/10/23 | 145 days | Mon 10/04/23 | Fri 27/10/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.3.1 |  |  |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | Mon 10/04/23 | Mon 10/04/23 | 1 day | Mon 10/04/23 | Mon 10/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.2 |  |  |  |  | Participants Provide Responses to questionnaires | 100% | Tue 11/04/23 | Mon 01/05/23 | 15 days | Tue 11/04/23 | Mon 01/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.3.3 |  |  |  |  | Assess on-line responses and provided evidence | 100% | Tue 02/05/23 | Mon 08/05/23 | 5 days | Tue 02/05/23 | Mon 08/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.4 |  |  |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | Tue 09/05/23 | Tue 20/06/23 | 31 days | Tue 09/05/23 | Tue 20/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.5 |  |  |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | Wed 07/06/23 | Thu 31/08/23 | 62 days | Wed 07/06/23 | Thu 31/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.6 |  |  |  |  | SI endorsement of participants’ design – assurance reports | 100% | Wed 02/08/23 | Fri 29/09/23 | 43 days | Wed 02/08/23 | Fri 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.7 |  |  |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | Tue 29/08/23 | Fri 27/10/23 | 44 days | Tue 29/08/23 | Fri 27/10/23 | 0 days | 0 days | 24 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.8 | T2 | T2-DB-0100 | DAG | MHHS-ART002 | Phase 1 - SIT Volunteers (Core Providers) complete | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.7.3.4 |  |  |  |  | Phase 2 - SIT all other participants | 100% | Mon 08/05/23 | Wed 22/11/23 | 143 days | Mon 08/05/23 | Wed 22/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.4.1 |  |  |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | Mon 08/05/23 | Mon 08/05/23 | 1 day | Mon 08/05/23 | Mon 08/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.4.2 |  |  |  |  | Participants Provide Responses to questionnaires | 100% | Tue 09/05/23 | Mon 29/05/23 | 15 days | Tue 09/05/23 | Mon 29/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.4.3 |  |  |  |  | Assess on-line responses and provided evidence | 100% | Tue 30/05/23 | Mon 05/06/23 | 5 days | Tue 30/05/23 | Mon 05/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.4.4 |  |  |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | Tue 06/06/23 | Fri 29/09/23 | 84 days | Tue 06/06/23 | Fri 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.5 |  |  |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | Tue 27/06/23 | Fri 29/09/23 | 69 days | Tue 27/06/23 | Fri 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.6 |  |  |  |  | SI endorsement of participants’ design – assurance reports | 100% | Tue 18/07/23 | Fri 29/09/23 | 54 days | Tue 18/07/23 | Fri 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.7 |  |  |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | Mon 14/08/23 | Wed 22/11/23 | 73 days | Mon 14/08/23 | Wed 22/11/23 | 0 days | 0 days | 35 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.8 | T2 | T2-DB-0200 | DAG | MHHS-ART002 | SIT PPs design assurance (excl Migration/Reverse Migration) complete | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1 day | 0 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.7.3.5 |  |  |  |  | Non-SIT PPs design assurance | 100% | Thu 23/11/23 | Wed 06/08/25 | 445 days | Thu 23/11/23 | Wed 06/08/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.5.1 |  |  |  |  | Non-SIT PPs design assurance (risk-based sample) | 100% | Thu 23/11/23 | Wed 06/08/25 | 445 days | Thu 23/11/23 | Wed 06/08/25 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.7.4 |  |  |  |  | Test Assurance | 100% | Wed 01/02/23 | Mon 30/06/25 | 629 days | Wed 01/02/23 | Mon 30/06/25 | 0 days | 0 days | -67 days | N/A |  | 5 | Yes
5 | 1.3.7.4.1 |  |  |  |  | Non-SIT PPs test assurance | 100% | Wed 01/02/23 | Mon 30/06/25 | 629 days | Wed 01/02/23 | Mon 30/06/25 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.3.7.5 |  |  |  |  | Pre-Qualification Guidance (PIT Guidance) | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.5.1 |  |  |  |  | Develop document (incl. collaboration with code bodies, as required) | 100% | Mon 31/10/22 | Mon 16/01/23 | 56 days | Mon 31/10/22 | Mon 16/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.7.5.2 |  |  |  |  | Review, update and agree Pre-Qualification Guidance internally | 100% | Tue 17/01/23 | Tue 31/01/23 | 11 days | Tue 17/01/23 | Tue 31/01/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
4 | 1.3.7.6 |  |  |  |  | External Programme Dependency Management | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.6.1 |  |  |  |  | SLC47 | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.6.1.1 |  |  |  |  | SLC47 implementation date | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 | 0 days | -1 day | 0 days | Ofgem |  | 5 | Yes
2 | 1.4 |  |  | SITAG |  | SYSTEMS INTEGRATION TESTING (SIT) | 97% | Mon 31/10/22 | Fri 24/04/26 | 910 days? | Mon 31/10/22 | Fri 24/04/26 | 0 days | 0 days | 69 days? | N/A |  | 5 | Yes
3 | 1.4.1 |  |  | SITAG |  | SIT Preparation | 100% | Mon 31/10/22 | Fri 23/05/25 | 670 days? | Mon 31/10/22 | Fri 16/05/25 | 0 days | 5 days | 59 days? | N/A |  | 5 | Yes
4 | 1.4.1.1 |  |  |  |  | Test Artefact Development | 100% | Mon 31/10/22 | Wed 21/08/24 | 472 days | Mon 31/10/22 | Wed 21/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.1.1.1 |  |  |  |  | Environment Approach & Plan | 100% | Wed 16/11/22 | Wed 21/08/24 | 460 days | Wed 16/11/22 | Wed 21/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.1.1 | T3 | T3-TE-0010 | SITAG | MHHS-ART139 | Environment Approach & Plan approved | 100% | Wed 16/11/22 | Wed 16/11/22 | 0 days | Wed 16/11/22 | Wed 16/11/22 | 0 days | -1 day | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.2 |  |  |  |  | Environment Approach & Plan - Work Off | 100% | Thu 17/11/22 | Fri 23/06/23 | 157 days | Thu 17/11/22 | Fri 23/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.3 | T3 | T3-TE-0068 | SITAG | MHHS-ART139 | Environment Approach & Plan - Work Off Approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 0 days | -1 day | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.4 | T3 | T3-TE-0090 | SITAG | MHHS-DEL 618 | Environment Approach and Plan - SIT Functional | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Mon 20/11/23 | Mon 20/11/23 | 0 days | -1 day | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.1.1.5 |  |  |  |  | Define Approach to Simulator for Non-SIT LDSO | 100% | Wed 15/11/23 | Wed 15/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 | 0 days | -1 day | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.1.1.6 | T3 | T3-TE-0091 | SITAG/QAG | MHHS-DEL 619 | Environment Approach and Plan - Non SIT LDSO Testing | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 0 days | -1 day | 0 days | SI Test |  | 5.22 | Yes
6 | 1.4.1.1.1.7 | T3 | T3-TE-0120 | SITAG/QAG | MHHS-DEL 619 | Environment Approach and Plan - S and A Testing | 100% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 0 days | -1 day | 0 days | SI Test |  | 5.27 | Yes
6 | 1.4.1.1.1.8 | T3 | T3-TE-0092 | SITAG | MHHS-DEL 620 | Environment Approach and Plan - SIT Non Functional | 100% | Wed 19/06/24 | Wed 19/06/24 | 0 days | Wed 19/06/24 | Wed 19/06/24 | 0 days | -1 day | 0 days | SI Test |  | 5.27 | Yes
6 | 1.4.1.1.1.9 | T3 | T3-TE-0093 | SITAG/QAG | MHHS-DEL 621 | Environment Approach and Plan - Sandbox | 100% | Wed 21/08/24 | Wed 21/08/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 | 0 days | -1 day | 0 days | SI Test |  | 5.27 | Yes
5 | 1.4.1.1.2 |  |  |  |  | Overarching Test Scope (for all stages) | 100% | Mon 31/10/22 | Fri 27/01/23 | 65 days | Mon 31/10/22 | Fri 27/01/23 | 0 days | 0 days | -110 days | N/A |  | 5 | Yes
6 | 1.4.1.1.2.1 |  |  |  |  | Overarching Test Scope (excl. Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 31/10/22 | Fri 27/01/23 | 65 days | Mon 31/10/22 | Fri 27/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.1.2.1.1 |  |  |  |  | Develop document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 31/10/22 | Fri 13/01/23 | 55 days | Mon 31/10/22 | Fri 13/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.1.2.1.2 |  |  |  |  | Review, update & agree document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 16/01/23 | Fri 27/01/23 | 10 days | Mon 16/01/23 | Fri 27/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.3 |  |  |  |  | Configuration and Release Management Approach & Plan | 100% | Tue 01/11/22 | Fri 16/06/23 | 164 days | Tue 01/11/22 | Fri 16/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.3.1 |  |  |  |  | Develop document | 100% | Tue 01/11/22 | Fri 16/06/23 | 69 days | Tue 01/11/22 | Fri 16/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.3.2 |  |  |  |  | Review, update and agree Configuration and Release Management Approach & Plan internally | 100% | Wed 01/02/23 | Fri 28/04/23 | 63 days | Wed 01/02/23 | Fri 28/04/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
5 | 1.4.1.1.4 |  |  |  |  | Test Data Overarching Approach & Plan | 100% | Mon 14/11/22 | Thu 20/07/23 | 179 days | Mon 14/11/22 | Thu 20/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.4.1 |  |  |  |  | Develop document | 100% | Mon 14/11/22 | Fri 09/12/22 | 20 days | Mon 14/11/22 | Fri 09/12/22 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.4.2 |  |  |  |  | Document review and update | 100% | Mon 12/12/22 | Fri 14/07/23 | 155 days | Mon 12/12/22 | Fri 14/07/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.1.1.4.3 | T3 | T3-TE-0072 | SITAG |  | Test Data Overarching Approach & Plan approved by TMAG | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 1 day | 0 days | 0 days | SRO Test |  | 5 | Yes
6 | 1.4.1.1.4.4 |  |  |  |  | Document publication final version | 100% | Thu 20/07/23 | Thu 20/07/23 | 1 day | Thu 20/07/23 | Thu 20/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.5 |  |  |  |  | Interface Code of Connection (dates subject to DIP Service Provider's plan) | 100% | Wed 01/03/23 | Fri 05/05/23 | 48 days | Wed 01/03/23 | Fri 05/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.5.1 |  |  |  |  | Develop Interface Code of Connection with DIP Service Provider | 100% | Wed 01/03/23 | Fri 28/04/23 | 43 days | Wed 01/03/23 | Fri 28/04/23 | 0 days | 0 days | 0 days | DIP Provider |  | 5 | Yes
6 | 1.4.1.1.5.2 |  |  |  |  | Interface Code of Connection approved at SDWG | 100% | Fri 05/05/23 | Fri 05/05/23 | 0 days | Fri 05/05/23 | Fri 05/05/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.6 |  |  |  |  | Test Traceability | 100% | Thu 01/06/23 | Wed 17/01/24 | 165 days | Thu 01/06/23 | Wed 17/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.6.1 |  |  |  |  | RTM containing Method Statement Implied Requirements into Azure DevOps | 100% | Thu 01/06/23 | Fri 30/06/23 | 22 days | Thu 01/06/23 | Fri 30/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.2 |  |  |  |  | RTM Containing Interface Catalogue Implied Requirements | 100% | Thu 01/06/23 | Fri 07/07/23 | 27 days | Thu 01/06/23 | Fri 07/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.3 |  |  |  |  | SIT CIT Full Traceability & Coverage complete | 100% | Mon 10/07/23 | Wed 20/12/23 | 118 days | Mon 10/07/23 | Wed 20/12/23 | 0 days | 0 days | 8 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.4 |  |  |  |  | SIT Functional Full Traceability & Coverage complete | 100% | Mon 10/07/23 | Wed 17/01/24 | 138 days | Mon 10/07/23 | Wed 17/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.1.2 |  |  |  |  | Test Tool Development | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days? | Mon 31/10/22 | Mon 23/10/23 | 0 days | 0 days | 81 days? | N/A |  | 5 | Yes
5 | 1.4.1.2.1 |  |  |  |  | Test Management Tool | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Mon 23/10/23 | 0 days | 0 days | 81 days | N/A |  | 5 | Yes
6 | 1.4.1.2.1.1 |  |  |  |  | Test Management Tool Implementation | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Mon 23/10/23 | 0 days | 0 days | 81 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.1.1 |  |  |  |  | Requirements identification | 100% | Mon 31/10/22 | Fri 23/12/22 | 40 days | Mon 31/10/22 | Fri 23/12/22 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.2 |  |  |  |  | Development | 100% | Mon 02/01/23 | Fri 23/06/23 | 125 days | Mon 02/01/23 | Fri 23/06/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.3 |  |  |  |  | Testing | 100% | Mon 02/01/23 | Fri 23/06/23 | 125 days | Mon 02/01/23 | Fri 23/06/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.4 |  |  |  |  | Accept tool | 100% | Fri 23/06/23 | Fri 23/06/23 | 0 days | Fri 23/06/23 | Fri 23/06/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.5 |  |  |  |  | Implementation | 100% | Mon 23/10/23 | Mon 23/10/23 | 1 day | Mon 23/10/23 | Mon 23/10/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.1.2.1.2 |  |  |  |  | Test Management Tool User Guide | 100% | Mon 02/01/23 | Fri 09/06/23 | 115 days | Mon 02/01/23 | Fri 09/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.2.1 |  |  |  |  | Develop document | 100% | Mon 02/01/23 | Fri 19/05/23 | 100 days | Mon 02/01/23 | Fri 19/05/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.2.2 |  |  |  |  | Review, update and agree Test Management Tool User Guide internally | 100% | Mon 22/05/23 | Fri 09/06/23 | 15 days | Mon 22/05/23 | Fri 09/06/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
6 | 1.4.1.2.1.3 |  |  |  |  | Test Management Tool Configuration Guide | 100% | Mon 02/01/23 | Fri 24/03/23 | 60 days | Mon 02/01/23 | Fri 24/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.3.1 |  |  |  |  | Develop document | 100% | Mon 02/01/23 | Fri 03/03/23 | 45 days | Mon 02/01/23 | Fri 03/03/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.3.2 |  |  |  |  | Review, update and agree Test Management Tool Configuration Guide internally | 100% | Mon 06/03/23 | Fri 24/03/23 | 15 days | Mon 06/03/23 | Fri 24/03/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
5 | 1.4.1.2.2 |  |  |  |  | Secure Volunteer SIT Participants | 100% | Tue 31/01/23 | Thu 14/09/23 | 163 days? | Tue 31/01/23 | Thu 14/09/23 | 0 days | 0 days | 163 days? |  |  | 6 | Yes
6 | 1.4.1.2.2.1 |  |  |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 100% | Tue 31/01/23 | Tue 31/01/23 | 1 day? | Tue 31/01/23 | Tue 31/01/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.2 |  |  |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 100% | Tue 14/02/23 | Tue 14/02/23 | 1 day? | Tue 14/02/23 | Tue 14/02/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.3 |  |  |  |  | SIT Participant Volunteers Identified | 100% | Tue 14/02/23 | Tue 14/02/23 | 1 day? | Tue 14/02/23 | Tue 14/02/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.4 |  |  |  |  | Engagement with SIT volunteers | 100% | Tue 23/05/23 | Tue 23/05/23 | 1 day? | Tue 23/05/23 | Tue 23/05/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.5 |  |  |  |  | SIT Participants Agreed | 100% | Tue 23/05/23 | Tue 23/05/23 | 1 day? | Tue 23/05/23 | Tue 23/05/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.6 |  |  |  |  | Data Protection Impact Assessment (DPIA) | 100% | Fri 30/06/23 | Fri 14/07/23 | 11 days? | Fri 30/06/23 | Fri 14/07/23 | 0 days | 0 days | 11 days? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.6.1 |  |  |  |  | Conduct DPIA on Overall Test Data Approach | 100% | Fri 30/06/23 | Fri 30/06/23 | 1 day? | Fri 30/06/23 | Fri 30/06/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.6.2 |  |  |  |  | Revise Overarching Test Data Approach& plan for DPIA (if required), including engagement with DWG | 100% | Thu 13/07/23 | Thu 13/07/23 | 1 day? | Thu 13/07/23 | Thu 13/07/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.6.3 |  |  |  |  | Review (internal), update and approve revised Overarching Test Data Approach& Plan (if required) | 100% | Fri 14/07/23 | Fri 14/07/23 | 1 day? | Fri 14/07/23 | Fri 14/07/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.7 |  |  |  |  | Data Sharing Agreements | 100% | Fri 04/08/23 | Thu 14/09/23 | 30 days? | Fri 04/08/23 | Thu 14/09/23 | 0 days | 0 days | 30 days? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.7.1 |  |  |  |  | Produce Data Sharing Agreement for Industry Review | 100% | Fri 04/08/23 | Fri 04/08/23 | 1 day? | Fri 04/08/23 | Fri 04/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.7.2 |  |  |  |  | Manage Participant Queries and Contract Agreement Execution | 100% | Thu 14/09/23 | Thu 14/09/23 | 1 day? | Thu 14/09/23 | Thu 14/09/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.7.3 |  |  |  |  | Data Sharing Agreements Complete | 100% | Thu 14/09/23 | Thu 14/09/23 | 1 day? | Thu 14/09/23 | Thu 14/09/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.8 |  |  |  |  | Production Data Cut & Data Obfuscation | 100% | Mon 19/06/23 | Fri 01/09/23 | 55 days? | Mon 19/06/23 | Fri 01/09/23 | 0 days | 0 days | 55 days? |  |  | 6 | Yes
7 | 1.4.1.2.2.8.1 |  |  |  |  | SI Data Cut Preparation& Infrastructure | 100% | Mon 19/06/23 | Fri 18/08/23 | 45 days? | Mon 19/06/23 | Fri 18/08/23 | 0 days | 0 days | 45 days? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.1 |  |  |  |  | SI Data Cut Planning activities (incl. pre-cut and post-cut cleansing and population approach) | 100% | Mon 19/06/23 | Mon 19/06/23 | 1 day? | Mon 19/06/23 | Mon 19/06/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.1.2 |  |  |  |  | Set up SI database and transmission structure | 100% | Thu 17/08/23 | Thu 17/08/23 | 1 day? | Thu 17/08/23 | Thu 17/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.1.3 |  |  |  |  | Mechanism for transfer of data in place | 100% | Fri 18/08/23 | Fri 18/08/23 | 1 day? | Fri 18/08/23 | Fri 18/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.1.4 |  |  |  |  | SI Data Cut Preparation& Infrastructure Complete | 100% | Fri 18/08/23 | Fri 18/08/23 | 1 day? | Fri 18/08/23 | Fri 18/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.8.2 |  |  |  |  | Production Data Cut | 100% | Mon 19/06/23 | Fri 01/09/23 | 55 days? | Mon 19/06/23 | Fri 01/09/23 | 0 days | 0 days | 55 days? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.1 |  |  |  |  | Notification of Production Data Cut issued to relevant participants | 100% | Mon 19/06/23 | Mon 19/06/23 | 1 day? | Mon 19/06/23 | Mon 19/06/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.2 |  |  |  |  | Coordinate relevant participants taking data cut from production systems | 100% | Fri 11/08/23 | Fri 11/08/23 | 1 day? | Fri 11/08/23 | Fri 11/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.3 |  |  |  |  | Production data cut GONG decision | 100% | Wed 16/08/23 | Wed 16/08/23 | 1 day? | Wed 16/08/23 | Wed 16/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.4 |  |  |  |  | Relevant participants take data cut from production systems (Saturday 19 August) | 100% | Mon 21/08/23 | Mon 21/08/23 | 1 day? | Mon 21/08/23 | Mon 21/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.5 |  |  |  |  | EES transmit request data to SI | 100% | Fri 25/08/23 | Fri 25/08/23 | 1 day? | Fri 25/08/23 | Fri 25/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.6 |  |  |  |  | Check data alignment and integrity of data cut | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day? | Fri 01/09/23 | Fri 01/09/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.7 |  |  |  |  | Data cut from relevant participants' production systems completed (Saturday 19 August) | 100% | Mon 21/08/23 | Mon 21/08/23 | 1 day? | Mon 21/08/23 | Mon 21/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.2.2.8.2.8 |  |  |  |  | Production Data Cut Complete | 100% | Mon 21/08/23 | Mon 21/08/23 | 1 day? | Mon 21/08/23 | Mon 21/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
4 | 1.4.1.3 |  |  |  |  | SIT Participation | 100% | Mon 31/10/22 | Tue 23/05/23 | 147 days | Mon 31/10/22 | Tue 23/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.1.3.1 |  |  |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.4.1.3.2 |  |  |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 100% | Wed 01/02/23 | Tue 14/02/23 | 10 days | Wed 01/02/23 | Tue 14/02/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.3 | T2 | T2-TE-0100 | SITAG |  | SIT Participant Volunteers Identified | 100% | Tue 14/02/23 | Tue 14/02/23 | 0 days | Tue 14/02/23 | Tue 14/02/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.4 |  |  |  |  | Engagement with SIT volunteers | 100% | Mon 31/10/22 | Tue 23/05/23 | 147 days | Mon 31/10/22 | Tue 23/05/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.5 | T2 | T2-TE-0150 | SITAG |  | SIT Participants Agreed | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.1.4 |  |  | SITAG |  | SIT Stage-Specific Preparation | 100% | Mon 31/10/22 | Fri 23/05/25 | 670 days? | Mon 31/10/22 | Fri 16/05/25 | 0 days | 5 days | 59 days? | N/A |  | 5 | Yes
5 | 1.4.1.4.1 |  |  |  |  | SIT Component Integration Preparation | 100% | Mon 31/10/22 | Fri 19/01/24 | 320 days | Mon 31/10/22 | Fri 19/01/24 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
6 | 1.4.1.4.1.1 |  |  |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Wed 19/07/23 | 188 days | Mon 31/10/22 | Wed 19/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.1.1 |  |  |  |  | Develop document with SITWG | 100% | Mon 31/10/22 | Thu 08/06/23 | 159 days | Mon 31/10/22 | Thu 08/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.1.2 |  |  |  |  | Industry consultation | 100% | Fri 09/06/23 | Thu 22/06/23 | 10 days | Fri 09/06/23 | Thu 22/06/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.1.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 23/06/23 | Wed 19/07/23 | 19 days | Fri 23/06/23 | Wed 19/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.1.4 | T3 | T3-TE-0012 | SITAG | MHHS-ART073 | SIT Component Integration Testing Test Approach & Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.1.2 |  |  |  |  | Test Data Approach & Plan | 100% | Fri 09/06/23 | Wed 19/07/23 | 29 days | Fri 09/06/23 | Wed 19/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.2.1 |  |  |  |  | Industry consultation | 100% | Fri 09/06/23 | Thu 22/06/23 | 10 days | Fri 09/06/23 | Thu 22/06/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 23/06/23 | Wed 19/07/23 | 19 days | Fri 23/06/23 | Wed 19/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.2.3 |  |  |  |  | SIT Component Integration Testing Test Data Approach & Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.1.3 |  |  |  |  | Test scenarios | 100% | Mon 02/01/23 | Wed 30/08/23 | 173 days | Mon 02/01/23 | Wed 30/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.3.1 |  |  |  |  | Development of test scenarios | 100% | Mon 02/01/23 | Mon 02/01/23 | 0 days | Mon 02/01/23 | Fri 28/04/23 | 0 days | -85 days | -85 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.3.2 |  |  |  |  | Review test scenarios with SIT Working Group | 100% | Wed 01/02/23 | Wed 15/02/23 | 11 days | Wed 01/02/23 | Wed 09/08/23 | 0 days | -125 days | -125 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.3.3 | T3 | T3-TE-0014 | SITAG | MHHS-ART148 | SIT Component Integration Testing Test scenarios approved | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 1 day | 0 days | 0 days | SI Test |  | 5.6 | Yes
6 | 1.4.1.4.1.4 |  |  |  |  | Test cases | 100% | Mon 01/05/23 | Fri 08/12/23 | 160 days | Mon 01/05/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
7 | 1.4.1.4.1.4.1 |  |  |  |  | SI Test cases | 100% | Mon 01/05/23 | Fri 08/12/23 | 160 days | Mon 01/05/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
8 | 1.4.1.4.1.4.1.1 |  |  |  |  | Batch 1 (CIT Intervals 1 and 2) | 100% | Mon 01/05/23 | Fri 29/09/23 | 110 days | Mon 01/05/23 | Fri 29/09/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.1.1 |  |  |  |  | Develop Test cases | 100% | Mon 01/05/23 | Fri 15/09/23 | 100 days | Mon 01/05/23 | Fri 15/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.1.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 18/09/23 | Thu 28/09/23 | 9 days | Mon 18/09/23 | Thu 28/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.1.3 | T3 | T3-TE-0069 | SITAG | MHHS-ART073 | SIT Component Integration Testing Test cases Batch 1 (CIT Intervals 1 and 2) approved at ETMAG | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.6 | Yes
8 | 1.4.1.4.1.4.1.2 |  |  |  |  | Batch 2 (CIT Intervals 3 and 4) | 100% | Mon 02/10/23 | Fri 03/11/23 | 25 days | Mon 02/10/23 | Fri 03/11/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.2.1 |  |  |  |  | Develop Test cases | 100% | Mon 02/10/23 | Fri 20/10/23 | 15 days | Mon 02/10/23 | Fri 20/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.2.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 23/10/23 | Thu 02/11/23 | 9 days | Mon 23/10/23 | Thu 02/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.2.3 | T3 | T3-TE-0104 | SITAG |  | SIT Component Integration Testing Test cases Batch 2 (CIT Intervals 3 and 4) approved at ETMAG | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
8 | 1.4.1.4.1.4.1.3 |  |  |  |  | Batch 3 (CIT Intervals 5 and 6) | 100% | Fri 03/11/23 | Fri 08/12/23 | 25 days | Fri 03/11/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | N/A |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.3.1 |  |  |  |  | Develop Test cases | 100% | Fri 03/11/23 | Fri 24/11/23 | 15 days | Fri 03/11/23 | Fri 24/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.3.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 27/11/23 | Thu 07/12/23 | 9 days | Mon 27/11/23 | Thu 07/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.3.3 | T3 | T3-TE-0105 | SITAG |  | SIT Component Integration Testing Test cases Batch 3 (CIT Intervals 5 and 6) approved at ETMAG | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.4.1.4.1.5 |  |  |  |  | CIT Interval 1 Preparation | 100% | Wed 16/11/22 | Fri 15/12/23 | 283 days | Wed 16/11/22 | Fri 15/12/23 | 0 days | 0 days | 5 days | N/A |  | 5.6 | Yes
7 | 1.4.1.4.1.5.1 |  |  |  |  | Environments (SIT A) | 100% | Wed 16/11/22 | Wed 25/10/23 | 246 days | Wed 16/11/22 | Wed 25/10/23 | 0 days | 0 days | 7 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.1.1 |  |  |  |  | PPs register PKI Officers and request PKI certificates | 100% | Mon 09/10/23 | Fri 13/10/23 | 5 days | Mon 09/10/23 | Fri 13/10/23 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
8 | 1.4.1.4.1.5.1.2 | T3 | T3-TE-0094 | SITAG |  | PPs register PKI Officers and request PKI certificates Complete - Interval 1 | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Wed 25/10/23 | Wed 25/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.5.1.3 |  |  |  |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 100% | Wed 16/11/22 | Fri 13/10/23 | 238 days | Wed 16/11/22 | Fri 13/10/23 | 0 days | 0 days | 30 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.4 |  |  |  |  | SI coordinate SIT Participants' SIT A environment preparation | 100% | Wed 16/11/22 | Fri 13/10/23 | 238 days | Wed 16/11/22 | Fri 13/10/23 | 0 days | 0 days | 30 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.5 |  |  |  |  | PP submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.6 |  |  |  |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | Mon 16/10/23 | Fri 20/10/23 | 5 days | Mon 16/10/23 | Fri 20/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.7 | T3 | T3-TE-0019 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 1 | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.5.1.8 |  |  |  |  | PP SIT A environment connectivity proving | 100% | Mon 04/09/23 | Fri 15/09/23 | 10 days | Mon 04/09/23 | Fri 15/09/23 | 0 days | 0 days | -10 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.9 |  |  |  |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 100% | Mon 04/09/23 | Fri 15/09/23 | 10 days | Mon 04/09/23 | Fri 15/09/23 | 0 days | 0 days | -10 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.10 |  |  |  |  | PP deployment of MHHS solution code to SIT A environments | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Mon 25/09/23 | Fri 06/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.1.11 |  |  |  |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Mon 25/09/23 | Fri 06/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.1.12 |  |  |  |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 100% | Mon 04/09/23 | Fri 13/10/23 | 30 days | Mon 04/09/23 | Fri 13/10/23 | 0 days | 0 days | 10 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.13 |  |  |  |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 100% | Mon 18/09/23 | Fri 20/10/23 | 25 days | Mon 18/09/23 | Fri 20/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes
7 | 1.4.1.4.1.5.2 |  |  |  |  | Test Data - ISD Creation | 100% | Tue 22/08/23 | Fri 01/09/23 | 9 days | Tue 22/08/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.2.1 |  |  |  |  | Set-up Market Participants and DIP ID Data | 100% | Tue 22/08/23 | Thu 31/08/23 | 8 days | Tue 22/08/23 | Thu 31/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.2.2 |  |  |  |  | Distribute ISD Data to Participants | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.2.3 | T3 | T3-TE-0083 | SITAG |  | Test Data - ISD Creation Complete | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
7 | 1.4.1.4.1.5.3 |  |  |  |  | Test Data - SFTP Onboarding | 100% | Mon 21/08/23 | Fri 24/11/23 | 70 days | Mon 21/08/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.1 |  |  |  |  | Create Containers and Keys for Participants | 100% | Mon 21/08/23 | Wed 23/08/23 | 3 days | Mon 21/08/23 | Wed 23/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.2 |  |  |  |  | Share SFTP Access with Participants | 100% | Thu 24/08/23 | Wed 30/08/23 | 5 days | Thu 24/08/23 | Wed 30/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.3 |  |  |  |  | Test SFTP Connectivity | 100% | Thu 31/08/23 | Wed 06/09/23 | 5 days | Thu 31/08/23 | Wed 06/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.4 | T3 | T3-TE-0084 | SITAG |  | Test Data - SFTP Onboarding Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.13 | Yes
7 | 1.4.1.4.1.5.4 |  |  |  |  | Test Data - Provide Sample Files | 100% | Mon 21/08/23 | Fri 01/09/23 | 10 days | Mon 21/08/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.4.1 |  |  |  |  | Generate Sample Files off IF Messages | 100% | Mon 21/08/23 | Wed 30/08/23 | 8 days | Mon 21/08/23 | Wed 30/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.4.2 |  |  |  |  | Transmit Sample Files off IF Messages to Participants (More detail needs to be planned for a POC) | 100% | Thu 31/08/23 | Fri 01/09/23 | 2 days | Thu 31/08/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.4.3 | T3 | T3-TE-0085 | SITAG |  | Test Data - Provide Sample Files Complete | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
7 | 1.4.1.4.1.5.5 |  |  |  |  | Test Data - Detailed SIT Data Load Guidance | 100% | Thu 07/09/23 | Wed 06/12/23 | 65 days | Thu 07/09/23 | Wed 06/12/23 | 0 days | 0 days | 3 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.5.1 |  |  |  |  | Document Guidance | 100% | Thu 07/09/23 | Thu 05/10/23 | 21 days | Thu 07/09/23 | Thu 05/10/23 | 0 days | 0 days | 5 days | SI Test Data |  | 5.9 | Yes
8 | 1.4.1.4.1.5.5.2 |  |  |  |  | Provide Guidance to PPs | 100% | Fri 06/10/23 | Fri 06/10/23 | 1 day | Fri 06/10/23 | Fri 06/10/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.9 | Yes
8 | 1.4.1.4.1.5.5.3 | T3 | T3-TE-0095 | SITAG | MHHS-DEL 1545 | Test Data - Detailed SIT Functional Data Load Guidance Complete | 100% | Wed 06/12/23 | Wed 06/12/23 | 0 days | Wed 06/12/23 | Wed 06/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.13 | Yes
7 | 1.4.1.4.1.5.6 |  |  |  |  | Test Data - Population of Data Items for Testing Guidance - Draft | 100% | Thu 17/08/23 | Wed 06/12/23 | 80 days | Thu 17/08/23 | Wed 06/12/23 | 0 days | 0 days | 3 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.6.1 |  |  |  |  | Document Guidance - Draft | 100% | Thu 17/08/23 | Thu 31/08/23 | 11 days | Thu 17/08/23 | Thu 31/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.6 | Yes
8 | 1.4.1.4.1.5.6.2 |  |  |  |  | Provide Guidance to PPs - Draft | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.6 | Yes
8 | 1.4.1.4.1.5.6.3 | T3 | T3-TE-0096 | SITAG | MHHS-DEL 816 | Test Data - Population of Data Items for Testing Guidance - Draft Complete | 100% | Wed 06/12/23 | Wed 06/12/23 | 0 days | Wed 06/12/23 | Wed 06/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.13 | Yes
7 | 1.4.1.4.1.5.7 |  |  |  |  | Test Data - Population of Data Items for Testing Guidance - Final | 100% | Thu 17/08/23 | Fri 15/12/23 | 87 days | Thu 17/08/23 | Fri 15/12/23 | 0 days | 0 days | 42 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.7.1 |  |  |  |  | Update Document Guidance With PPS Feedback | 100% | Thu 17/08/23 | Thu 07/12/23 | 81 days | Thu 17/08/23 | Thu 07/12/23 | 0 days | 0 days | 37 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.7.2 |  |  |  |  | Provide Final Guidance to PPs | 100% | Fri 08/12/23 | Fri 08/12/23 | 1 day | Fri 08/12/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.7.3 | T3 | T3-TE-0097 | SITAG | MHHS-DEL 816 | Test Data - Population of Data Items for Testing Guidance - Final Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
7 | 1.4.1.4.1.5.8 |  |  |  |  | Test Data (SIT A) Interval 1 | 100% | Mon 04/09/23 | Fri 27/10/23 | 40 days | Mon 04/09/23 | Fri 27/10/23 | 0 days | 0 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.8.1 |  |  |  |  | Run data allocation | 100% | Mon 04/09/23 | Thu 07/09/23 | 4 days | Mon 04/09/23 | Thu 07/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.2 |  |  |  |  | Cleanse, anonymise and populate data post cut | 100% | Fri 08/09/23 | Wed 13/09/23 | 4 days | Fri 08/09/23 | Wed 13/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.3 |  |  |  |  | Transmit data sets to PPs | 100% | Fri 15/09/23 | Tue 19/09/23 | 3 days | Fri 15/09/23 | Tue 19/09/23 | 0 days | 0 days | 2 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 20/09/23 | Thu 28/09/23 | 7 days | Wed 20/09/23 | Thu 28/09/23 | 0 days | 0 days | 2 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Fri 29/09/23 | Fri 29/09/23 | 1 day | Fri 29/09/23 | Fri 29/09/23 | 0 days | 0 days | -4 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.7 | T3 | T3-TE-0073 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 1 Complete | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
7 | 1.4.1.4.1.5.9 |  |  |  |  | Other Preparation | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.9.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.9.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.5.10 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Thu 14/09/23 | Mon 23/10/23 | 28 days | Thu 14/09/23 | Mon 23/10/23 | 0 days | 0 days | 19 days | N/A |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 23/10/23 | Mon 23/10/23 | 1 day | Mon 23/10/23 | Mon 23/10/23 | 0 days | 0 days | -4 days | SI Test |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Thu 14/09/23 | Mon 16/10/23 | 23 days | Thu 14/09/23 | Mon 16/10/23 | 0 days | 0 days | 19 days | SI Test |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Tue 17/10/23 | Fri 20/10/23 | 4 days | Tue 17/10/23 | Fri 20/10/23 | 0 days | 0 days | -1 day | SI Test |  | 5.6 | Yes
7 | 1.4.1.4.1.5.11 | T2 | T2-TE-0250 | SITAG | MHHS-ART071 | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.4.1.4.1.6 |  |  |  |  | CIT Interval 2 Preparation | 100% | Mon 03/07/23 | Wed 22/11/23 | 103 days | Mon 03/07/23 | Wed 22/11/23 | 0 days | 0 days | 8 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.6.1 |  |  |  |  | Environments (SIT A) | 100% | Fri 22/09/23 | Wed 22/11/23 | 43 days | Fri 22/09/23 | Wed 22/11/23 | 1 day | 0 days | 8 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.1.1 | T3 | T3-TE-0020 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 2 | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.6.1.2 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Mon 25/09/23 | Fri 06/10/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 16/10/23 | Wed 22/11/23 | 28 days | Mon 16/10/23 | Wed 22/11/23 | 0 days | 0 days | 8 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.6 |  |  |  |  | DIP Onboarding Complete | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.7 | T3 | T3-TE-0098 | SITAG |  | PPs Register PKI Officers and request PKI certificates Complete - Interval 2 | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
8 | 1.4.1.4.1.6.1.8 |  |  |  |  | PP Code Deployment | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.6.2 |  |  |  |  | Test Data (SIT A) Interval 2 | 100% | Wed 20/09/23 | Fri 17/11/23 | 43 days | Wed 20/09/23 | Fri 17/11/23 | 0 days | 0 days | 18 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.2.1 |  |  |  |  | Run data allocation | 100% | Wed 20/09/23 | Thu 28/09/23 | 7 days | Wed 20/09/23 | Thu 28/09/23 | 0 days | 0 days | 2 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Fri 29/09/23 | Mon 02/10/23 | 2 days | Fri 29/09/23 | Mon 02/10/23 | 0 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.3 |  |  |  |  | Transmit data sets to PPs | 100% | Tue 03/10/23 | Tue 03/10/23 | 1 day | Tue 03/10/23 | Tue 03/10/23 | 0 days | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 04/10/23 | Fri 17/11/23 | 33 days | Wed 04/10/23 | Fri 17/11/23 | 0 days | 0 days | 25 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 23/10/23 | Fri 17/11/23 | 15 days | Mon 23/10/23 | Fri 17/11/23 | 0 days | 0 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.7 | T3 | T3-TE-0074 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 2 Complete | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
7 | 1.4.1.4.1.6.3 |  |  |  |  | Other Preparation | 100% | Mon 03/07/23 | Tue 31/10/23 | 87 days | Mon 03/07/23 | Tue 31/10/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.3.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 03/07/23 | Fri 22/09/23 | 60 days | Mon 03/07/23 | Fri 22/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.3.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 25/09/23 | Tue 31/10/23 | 27 days | Mon 25/09/23 | Tue 31/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.6.4 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 02/10/23 | Fri 03/11/23 | 25 days | Mon 02/10/23 | Fri 03/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.4.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Wed 25/10/23 | Wed 25/10/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.4.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Thu 26/10/23 | Fri 27/10/23 | 2 days | Thu 26/10/23 | Fri 27/10/23 | 0 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.4.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 02/10/23 | Fri 27/10/23 | 20 days | Mon 02/10/23 | Fri 27/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.4.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 30/10/23 | Fri 03/11/23 | 5 days | Mon 30/10/23 | Fri 03/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.6.5 | T2 | T2-TE-0300 | SITAG | MHHS-ART071 | SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 06/11/23 | Mon 06/11/23 | 0 days | Mon 06/11/23 | Mon 06/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.4.1.4.1.7 |  |  |  |  | CIT Interval 3 Preparation | 100% | Tue 03/10/23 | Fri 15/12/23 | 54 days | Tue 03/10/23 | Fri 15/12/23 | 0 days | 0 days | -37 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.7.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 13/10/23 | Fri 17/11/23 | 26 days | Fri 13/10/23 | Fri 17/11/23 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 13/10/23 | Fri 27/10/23 | 11 days | Fri 13/10/23 | Fri 27/10/23 | 0 days | 0 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 30/10/23 | Fri 03/11/23 | 5 days | Mon 30/10/23 | Fri 03/11/23 | 0 days | 0 days | -10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.1.3 | T3 | T3-DB-0017 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5.11 | Yes
8 | 1.4.1.4.1.7.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 06/11/23 | Fri 17/11/23 | 10 days | Mon 06/11/23 | Fri 17/11/23 | 0 days | 0 days | 5 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.7.2 |  |  |  |  | Environments (SIT A) | 100% | Fri 06/10/23 | Fri 15/12/23 | 51 days | Fri 06/10/23 | Fri 15/12/23 | 0 days | 0 days | 25 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.2 | T3 | T3-TE-0021 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 3 | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 09/10/23 | Fri 20/10/23 | 10 days | Mon 09/10/23 | Fri 20/10/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 30/10/23 | Fri 15/12/23 | 35 days | Mon 30/10/23 | Fri 15/12/23 | 0 days | 0 days | 25 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.7 | T3 | T3-TE-0099 | SITAG |  | PPs Register PKI Officers and Request PKI certificates Complete - Interval 3 | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.13 | Yes
8 | 1.4.1.4.1.7.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.7.3 |  |  |  |  | Test Data (SIT A) Interval 3 | 100% | Tue 03/10/23 | Fri 17/11/23 | 34 days | Tue 03/10/23 | Fri 17/11/23 | 0 days | 0 days | 9 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.3.1 |  |  |  |  | Run data allocation | 100% | Tue 03/10/23 | Fri 06/10/23 | 4 days | Tue 03/10/23 | Fri 06/10/23 | 0 days | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Mon 09/10/23 | Fri 13/10/23 | 5 days | Mon 09/10/23 | Fri 13/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Mon 16/10/23 | Tue 17/10/23 | 2 days | Mon 16/10/23 | Tue 17/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 18/10/23 | Fri 27/10/23 | 8 days | Wed 18/10/23 | Fri 27/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 30/10/23 | Fri 17/11/23 | 15 days | Mon 30/10/23 | Fri 17/11/23 | 0 days | 0 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.7 | T3 | T3-TE-0075 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 3 Complete | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
7 | 1.4.1.4.1.7.4 |  |  |  |  | Other Preparation | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 16/10/23 | Fri 17/11/23 | 0 days | 0 days | -35 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 16/10/23 | Fri 17/11/23 | 0 days | 0 days | -35 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 16/10/23 | Fri 17/11/23 | 0 days | 0 days | -35 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.7.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 16/10/23 | Fri 17/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 06/11/23 | Fri 10/11/23 | 5 days | Mon 06/11/23 | Fri 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 10/11/23 | 20 days | Mon 16/10/23 | Fri 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.5.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 13/11/23 | Fri 17/11/23 | 5 days | Mon 13/11/23 | Fri 17/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.7.6 | T2 | T2-TE-0350 | SITAG | MHHS-ART071 | SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Mon 20/11/23 | Mon 20/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.4.1.8 |  |  |  |  | CIT Interval 4 Preparation | 100% | Mon 16/10/23 | Mon 04/12/23 | 36 days | Mon 16/10/23 | Mon 04/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.8.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 27/10/23 | Fri 24/11/23 | 21 days | Fri 27/10/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 27/10/23 | Fri 27/10/23 | 1 day | Fri 27/10/23 | Fri 27/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 30/10/23 | Fri 17/11/23 | 15 days | Mon 30/10/23 | Fri 17/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.1.3 | T3 | T3-DB-0019 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5.13 | Yes
8 | 1.4.1.4.1.8.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 20/11/23 | Fri 24/11/23 | 5 days | Mon 20/11/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.8.2 |  |  |  |  | Environments (SIT A) | 100% | Mon 23/10/23 | Fri 24/11/23 | 25 days | Mon 23/10/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.2 | T3 | T3-TE-0022 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 4 | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 23/10/23 | Fri 03/11/23 | 10 days | Mon 23/10/23 | Fri 03/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 13/11/23 | Fri 24/11/23 | 10 days | Mon 13/11/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.7 | T3 | T3-TE-0100 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 4 | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 1 day | 0 days | 0 days | PP |  | 5.16 | Yes
8 | 1.4.1.4.1.8.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.8.3 |  |  |  |  | Test Data (SIT A) Interval 4 | 100% | Mon 23/10/23 | Fri 01/12/23 | 30 days | Mon 23/10/23 | Fri 01/12/23 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.3.1 |  |  |  |  | Run data allocation | 100% | Mon 23/10/23 | Fri 27/10/23 | 5 days | Mon 23/10/23 | Fri 27/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Mon 30/10/23 | Tue 31/10/23 | 2 days | Mon 30/10/23 | Tue 31/10/23 | 0 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Wed 01/11/23 | Tue 07/11/23 | 5 days | Wed 01/11/23 | Tue 07/11/23 | 0 days | 0 days | 3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 08/11/23 | Tue 14/11/23 | 5 days | Wed 08/11/23 | Tue 14/11/23 | 0 days | 0 days | -3 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Wed 15/11/23 | Fri 01/12/23 | 13 days | Wed 15/11/23 | Fri 01/12/23 | 0 days | 0 days | 8 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.7 | T3 | T3-TE-0076 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 4 Complete | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
7 | 1.4.1.4.1.8.4 |  |  |  |  | Other Preparation | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.8.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Tue 21/11/23 | 27 days | Mon 16/10/23 | Tue 21/11/23 | 0 days | 0 days | 2 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 06/11/23 | Fri 10/11/23 | 5 days | Mon 06/11/23 | Fri 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 10/11/23 | 20 days | Mon 16/10/23 | Fri 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.5.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Mon 13/11/23 | Tue 21/11/23 | 7 days | Mon 13/11/23 | Tue 21/11/23 | 0 days | 0 days | 2 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.8.6 | T2 | T2-TE-0400 | SITAG | MHHS-ART071 | SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 04/12/23 | Mon 04/12/23 | 0 days | Mon 04/12/23 | Mon 04/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
6 | 1.4.1.4.1.9 |  |  |  |  | CIT Interval 5 Preparation | 100% | Wed 01/11/23 | Fri 12/01/24 | 53 days | Wed 01/11/23 | Fri 12/01/24 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.9.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 17/11/23 | Fri 15/12/23 | 21 days | Fri 17/11/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 1 day | Fri 17/11/23 | Fri 17/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 20/11/23 | Fri 08/12/23 | 15 days | Mon 20/11/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.1.3 | T3 | T3-DB-0021 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.1.9.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.9.2 |  |  |  |  | Environments (SIT A) | 100% | Fri 10/11/23 | Fri 08/12/23 | 21 days | Fri 10/11/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.2 | T3 | T3-TE-0023 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 5 | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 0 days | -1 day | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.9.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 13/11/23 | Fri 24/11/23 | 10 days | Mon 13/11/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 27/11/23 | Fri 08/12/23 | 10 days | Mon 27/11/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.7 | T3 | T3-TE-0101 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 5 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.17 | Yes
8 | 1.4.1.4.1.9.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.9.3 |  |  |  |  | Test Data (SIT A) Interval 5 | 100% | Wed 01/11/23 | Fri 15/12/23 | 33 days | Wed 01/11/23 | Fri 15/12/23 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.3.1 |  |  |  |  | Run data allocation | 100% | Wed 01/11/23 | Tue 07/11/23 | 5 days | Wed 01/11/23 | Tue 07/11/23 | 0 days | 0 days | -5 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Wed 08/11/23 | Fri 17/11/23 | 8 days | Wed 08/11/23 | Fri 17/11/23 | 0 days | 0 days | 3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Mon 20/11/23 | Tue 21/11/23 | 2 days | Mon 20/11/23 | Tue 21/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 22/11/23 | Fri 01/12/23 | 8 days | Wed 22/11/23 | Fri 01/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 5 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.7 | T3 | T3-TE-0077 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 5 Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.4.1.4.1.9.4 |  |  |  |  | Other Preparation | 100% | Mon 20/11/23 | Fri 12/01/24 | 40 days | Mon 20/11/23 | Fri 12/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 20/11/23 | Fri 12/01/24 | 40 days | Mon 20/11/23 | Fri 12/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 20/11/23 | Mon 08/01/24 | 36 days | Mon 20/11/23 | Mon 08/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.9.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 05/01/24 | 35 days | Mon 20/11/23 | Fri 05/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 15/12/23 | 20 days | Mon 20/11/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.5.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Mon 18/12/23 | Fri 05/01/24 | 15 days | Mon 18/12/23 | Fri 05/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.9.6 | T2 | T2-TE-0450 | SITAG | MHHS-ART071 | SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 08/01/24 | Mon 08/01/24 | 0 days | Mon 08/01/24 | Mon 08/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.15 | Yes
6 | 1.4.1.4.1.10 |  |  |  |  | CIT Interval 6 Preparation | 100% | Mon 20/11/23 | Fri 19/01/24 | 45 days | Mon 20/11/23 | Fri 19/01/24 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
7 | 1.4.1.4.1.10.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 01/12/23 | Fri 12/01/24 | 31 days | Fri 01/12/23 | Fri 12/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 01/12/23 | Fri 01/12/23 | 1 day | Fri 01/12/23 | Fri 01/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 04/12/23 | Fri 05/01/24 | 25 days | Mon 04/12/23 | Fri 05/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.1.3 | T3 | T3-DB-0023 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 1 day | 0 days | 0 days | PP |  | 5.19 | Yes
8 | 1.4.1.4.1.10.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 08/01/24 | Fri 12/01/24 | 5 days | Mon 08/01/24 | Fri 12/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
7 | 1.4.1.4.1.10.2 |  |  |  |  | Environments (SIT A) | 100% | Fri 24/11/23 | Fri 05/01/24 | 30 days | Fri 24/11/23 | Fri 05/01/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.2 | T3 | T3-TE-0024 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 6 | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 0 days | -1 day | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.10.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 27/11/23 | Fri 08/12/23 | 10 days | Mon 27/11/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 04/12/23 | Fri 08/12/23 | 5 days | Mon 04/12/23 | Fri 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.7 | T3 | T3-TE-0102 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 6 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.17 | Yes
8 | 1.4.1.4.1.10.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.10.3 |  |  |  |  | Test Data (SIT A) Interval 6 | 100% | Mon 20/11/23 | Fri 22/12/23 | 25 days | Mon 20/11/23 | Fri 22/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.3.1 |  |  |  |  | Run data allocation | 100% | Mon 20/11/23 | Fri 01/12/23 | 10 days | Mon 20/11/23 | Fri 01/12/23 | 0 days | 0 days | 5 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Mon 04/12/23 | Mon 04/12/23 | 1 day | Mon 04/12/23 | Mon 04/12/23 | 0 days | 0 days | -4 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Tue 05/12/23 | Tue 05/12/23 | 1 day | Tue 05/12/23 | Tue 05/12/23 | 0 days | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 06/12/23 | Fri 15/12/23 | 8 days | Wed 06/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 18/12/23 | Fri 22/12/23 | 5 days | Mon 18/12/23 | Fri 22/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.7 | T3 | T3-TE-0078 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 6 Complete | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.1.10.4 |  |  |  |  | Other Preparation | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.10.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 22/12/23 | 25 days | Mon 20/11/23 | Fri 22/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 15/12/23 | 20 days | Mon 20/11/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.5.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 18/12/23 | Fri 22/12/23 | 5 days | Mon 18/12/23 | Fri 22/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.10.6 | T2 | T2-TE-0500 | SITAG | MHHS-ART071 | SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.15 | Yes
5 | 1.4.1.4.2 |  |  | SITAG |  | SIT Functional Preparation | 100% | Mon 31/10/22 | Fri 07/02/25 | 595 days? | Mon 31/10/22 | Mon 07/04/25 | 0 days | -41 days | 75 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.2.1 |  |  |  |  | Environment Approach and Plan - SIT Functional | 100% | Mon 20/11/23 | Mon 20/11/23 | 1 day? | Mon 20/11/23 | Mon 20/11/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.4.2.2 |  |  |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Wed 16/08/23 | 208 days | Mon 31/10/22 | Wed 16/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.2.1 |  |  |  |  | Develop document with SITWG | 100% | Mon 31/10/22 | Thu 06/07/23 | 179 days | Mon 31/10/22 | Thu 06/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.2.2 |  |  |  |  | Industry Consultation | 100% | Fri 07/07/23 | Thu 20/07/23 | 10 days | Fri 07/07/23 | Thu 20/07/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.2.2.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 21/07/23 | Wed 16/08/23 | 19 days | Fri 21/07/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.2.2.4 | T3 | T3-TE-0013 | SITAG | MHHS-ART073 | SIT Functional Test Approach & Plan approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.2.3 |  |  |  |  | Test Data Approach & Plan | 100% | Fri 07/07/23 | Wed 16/08/23 | 29 days | Fri 07/07/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.3.1 |  |  |  |  | Industry Consultation | 100% | Fri 07/07/23 | Thu 20/07/23 | 10 days | Fri 07/07/23 | Thu 20/07/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.2.3.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 21/07/23 | Wed 16/08/23 | 19 days | Fri 21/07/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.2.3.3 |  |  |  |  | SIT Functional Testing Test Data Approach & Plan approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 1 day | 0 days | 0 days | SI Test |  | 5.5 | Yes
6 | 1.4.1.4.2.4 |  |  |  |  | Test scenarios | 100% | Mon 02/01/23 | Wed 21/02/24 | 298 days | Mon 02/01/23 | Wed 21/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.4.1 |  |  |  |  | Development of test scenarios | 100% | Mon 02/01/23 | Fri 28/04/23 | 85 days | Mon 02/01/23 | Fri 28/04/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.4.2 |  |  |  |  | Review test scenarios with SIT Working Group | 100% | Thu 17/08/23 | Wed 15/11/23 | 65 days | Thu 17/08/23 | Wed 15/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.4.3 | T3 | T3-TE-0015 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (themes 1-5) approved | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.4.1.4.2.4.4 | T3 | T3-TE-0106 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (themes 6,7,9) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.16 | Yes
7 | 1.4.1.4.2.4.5 | T3 | T3-TE-0107 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (theme 8) approved | 100% | Wed 21/02/24 | Wed 21/02/24 | 0 days | Wed 21/02/24 | Wed 21/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.4.1.4.2.5 |  |  |  |  | Test cases | 100% | Mon 01/05/23 | Fri 07/02/25 | 465 days? | Mon 01/05/23 | Fri 07/02/25 | 0 days | 0 days | 252 days? | N/A |  | 5 | Yes
7 | 1.4.1.4.2.5.1 |  |  |  |  | SI Test cases | 100% | Mon 01/05/23 | Wed 21/02/24 | 213 days | Mon 01/05/23 | Wed 21/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.5.1.1 |  |  |  |  | Development of Test cases | 100% | Mon 01/05/23 | Fri 24/11/23 | 150 days | Mon 01/05/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.5.1.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 25/09/23 | Wed 10/01/24 | 78 days | Mon 25/09/23 | Wed 10/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.5.1.3 | T3 | T3-TE-0070 | SITAG | MHHS-ART140 | SIT Functional Testing Test Cases (themes 1-5) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
8 | 1.4.1.4.2.5.1.4 | T3 | T3-TE-0108 | SITAG | MHHS-ART140 | SIT Functional Testing Test cases (themes 6,7,9) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
8 | 1.4.1.4.2.5.1.5 | T3 | T3-TE-0109 | SITAG | MHHS-ART140 | SIT Functional Testing Test cases (theme 8) approved | 100% | Wed 21/02/24 | Wed 21/02/24 | 0 days | Wed 21/02/24 | Wed 21/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.4.1.4.2.5.2 |  |  | SITAG |  | SIT Functional Programme RTTM | 100% | Mon 29/07/24 | Thu 07/11/24 | 74 days? | Mon 29/07/24 | Fri 11/10/24 | 0 days | 19 days | 74 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.2.1 |  |  | SITAG |  | RTTM Development | 100% | Mon 29/07/24 | Fri 06/09/24 | 30 days? | Mon 29/07/24 | Fri 20/09/24 | 0 days | -10 days | 30 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.1.1 |  |  | SITAG |  | Development of Manual SIT Functional RTTM | 100% | Mon 29/07/24 | Fri 06/09/24 | 30 days? | Mon 29/07/24 | Fri 06/09/24 | 0 days | 0 days | 30 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.1.2 |  |  | SITAG |  | Manual SIT Functional RTTM Complete | 100% | Fri 06/09/24 | Fri 06/09/24 | 0 days? | Fri 06/09/24 | Fri 06/09/24 | 1 day | 0 days | 0 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.2.2 |  |  | SITAG |  | Gap analysis | 100% | Mon 26/08/24 | Thu 07/11/24 | 54 days? | Mon 26/08/24 | Fri 11/10/24 | 0 days | 19 days | 54 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.2.1 |  |  | SITAG |  | Identify gaps in test case coverage following RTTM review | 100% | Mon 26/08/24 | Fri 20/09/24 | 20 days? | Mon 26/08/24 | Fri 20/09/24 | 0 days | 0 days | 20 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.2.2 |  |  | SITAG |  | Address gaps in test case coverage following RTTM review | 100% | Mon 09/09/24 | Fri 11/10/24 | 25 days | Mon 09/09/24 | Fri 04/10/24 | 0 days | 5 days | 25 days | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.2.3 |  |  | SITAG |  | Gap analysis complete | 100% | Fri 11/10/24 | Fri 11/10/24 | 0 days | Fri 11/10/24 | Fri 11/10/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.4 |  |  | SITAG |  | Test Script updates identified | 100% | Mon 14/10/24 | Mon 14/10/24 | 1 day? | Mon 14/10/24 | Mon 14/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.5 |  |  | SITAG |  | Test Scripts updates | 100% | Tue 15/10/24 | Tue 15/10/24 | 1 day | Tue 15/10/24 | Tue 15/10/24 | 0 days | 0 days | 1 day | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.6 |  |  | SITAG |  | RTTM Updated Additional Static RTTM WBS items | 100% | Mon 14/10/24 | Fri 25/10/24 | 10 days | Mon 14/10/24 | Fri 25/10/24 | 0 days | 0 days | 10 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.7 |  |  | SITAG |  | Removal of de-scoped TCs from the RTTMs | 100% | Mon 21/10/24 | Fri 25/10/24 | 5 days | Mon 21/10/24 | Fri 25/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.8 |  |  | SITAG |  | Update and stabilisation of all TC ADO IDs | 100% | Mon 21/10/24 | Thu 07/11/24 | 14 days | Mon 21/10/24 | Fri 25/10/24 | 0 days | 9 days | 14 days | SI Test |  | 6.12 | Yes
9 | 1.4.1.4.2.5.2.2.9 |  |  | SITAG |  | Addition and integration of Role tags to reqs in the Role RTTMs | 100% | Mon 21/10/24 | Fri 25/10/24 | 5 days | Mon 21/10/24 | Fri 25/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.10 |  |  | SITAG |  | Update of the RTTM All sheet (porting of the individual RTTMs) | 100% | Thu 24/10/24 | Fri 01/11/24 | 7 days | Thu 24/10/24 | Fri 25/10/24 | 0 days | 5 days | 7 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.11 |  |  | SITAG |  | Define Additional ADO Tags | 100% | Wed 23/10/24 | Wed 23/10/24 | 1 day | Wed 23/10/24 | Wed 23/10/24 | 0 days | 0 days | 1 day | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.12 |  |  | SITAG |  | Functional RTTM ready for import into ADO | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 25/10/24 | Fri 25/10/24 | 6 days | 5 days | 0 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.13 |  |  | SITAG |  | Further Interative Deepdive on the requirements to testcase mapping | 100% | Mon 21/10/24 | Thu 31/10/24 | 9 days | Mon 21/10/24 | Thu 31/10/24 | 0 days | 0 days | 9 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.14 |  |  | SITAG |  | Internal review | 100% | Mon 21/10/24 | Fri 25/10/24 | 5 days | Fri 01/11/24 | Tue 05/11/24 | -9 days | -7 days | 5 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.15 |  |  | SITAG |  | Issue Static RTTM to Code Bodies | 100% | Tue 29/10/24 | Tue 29/10/24 | 1 day? | Wed 06/11/24 | Wed 06/11/24 | -6 days | -6 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.16 |  |  | SITAG |  | Code Body Acceptance of RTTM | 100% | Wed 30/10/24 | Tue 05/11/24 | 5 days | Thu 07/11/24 | Wed 13/11/24 | -6 days | -6 days | 5 days | Code Bodies |  | 6.11 | Yes
7 | 1.4.1.4.2.5.3 |  |  | SITAG |  | Cycle 3 Test Evidence Capturing Approach | 100% | Mon 16/09/24 | Fri 18/10/24 | 25 days? | Mon 16/09/24 | Fri 18/10/24 | 0 days | 0 days | 25 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.1 |  |  | SITAG |  | Define guiding principles and proof of concept | 100% | Mon 16/09/24 | Fri 27/09/24 | 10 days | Mon 16/09/24 | Fri 27/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.2 |  |  | SITAG |  | Draft proposed test evidence capturing approach | 100% | Mon 30/09/24 | Wed 02/10/24 | 3 days | Mon 30/09/24 | Wed 02/10/24 | 0 days | 0 days | 3 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.3 |  |  | SITAG |  | SRO review | 100% | Thu 03/10/24 | Wed 09/10/24 | 5 days | Thu 03/10/24 | Wed 09/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.4 |  |  | SITAG |  | Present proposed approach | 100% | Fri 11/10/24 | Fri 11/10/24 | 1 day? | Fri 11/10/24 | Fri 11/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.5 |  |  | SITAG |  | Incorporate feedback | 100% | Mon 14/10/24 | Thu 17/10/24 | 4 days | Mon 14/10/24 | Thu 17/10/24 | 0 days | 0 days | 4 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.6 |  |  | SITAG |  | Publish proposed approach ahead of Cycle 3 start | 100% | Fri 18/10/24 | Fri 18/10/24 | 1 day? | Fri 18/10/24 | Fri 18/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.4.2.5.4 |  |  | SITAG |  | DITL Cycle 3 Pack Development | 100% | Tue 08/10/24 | Thu 17/10/24 | 8 days? | Tue 08/10/24 | Thu 17/10/24 | 0 days | 0 days | 8 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.1 |  |  | SITAG |  | Programme Cycle 2 Retro | 100% | Tue 08/10/24 | Tue 08/10/24 | 1 day? | Tue 08/10/24 | Tue 08/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.2 |  |  | SITAG |  | Post-retro DITL Changes | 100% | Wed 09/10/24 | Fri 11/10/24 | 3 days | Wed 09/10/24 | Fri 11/10/24 | 0 days | 0 days | 3 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.3 |  |  | SITAG |  | SRO Review | 100% | Mon 14/10/24 | Tue 15/10/24 | 2 days | Mon 14/10/24 | Tue 15/10/24 | 0 days | 0 days | 2 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.4 |  |  | SITAG |  | Post-SRO Review Changes | 100% | Wed 16/10/24 | Wed 16/10/24 | 1 day? | Wed 16/10/24 | Wed 16/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.5 |  |  | SITAG |  | Publish Cycle 3 DITL / Cycle 3 DITL Online Sessions for SIT PPs | 100% | Thu 17/10/24 | Thu 17/10/24 | 1 day? | Thu 17/10/24 | Thu 17/10/24 | 0 days | 0 days | 1 day? | SI Test, PPs |  | 6 | Yes
7 | 1.4.1.4.2.5.5 |  |  | SITAG |  | Test Script Exit Points | 100% | Mon 14/10/24 | Fri 07/02/25 | 85 days | Mon 14/10/24 | Fri 07/02/25 | 0 days | 0 days | 85 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.1 |  |  | SITAG |  | Implement exit points for Sprint 5 | 100% | Mon 14/10/24 | Fri 18/10/24 | 5 days | Mon 14/10/24 | Fri 18/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.2 |  |  | SITAG |  | Identify exit points for Sprint 6 | 100% | Thu 07/11/24 | Wed 13/11/24 | 5 days | Mon 21/10/24 | Fri 25/10/24 | 13 days | 13 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.3 |  |  | SITAG |  | Identify exit points for Sprint 7 | 100% | Fri 08/11/24 | Thu 14/11/24 | 5 days | Mon 04/11/24 | Fri 08/11/24 | 4 days | 4 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.4 |  |  | SITAG |  | Identify exit points for Sprint 8 | 100% | Mon 18/11/24 | Fri 22/11/24 | 5 days | Mon 18/11/24 | Fri 22/11/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.5 |  |  | SITAG |  | Identify exit points for Sprint 9 | 100% | Mon 02/12/24 | Fri 06/12/24 | 5 days | Mon 02/12/24 | Fri 06/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.6 |  |  | SITAG |  | Identify exit points for Sprint 10 | 100% | Mon 23/12/24 | Fri 27/12/24 | 5 days | Mon 23/12/24 | Fri 27/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.7 |  |  | SITAG |  | Identify exit points for Sprint 11 | 100% | Mon 06/01/25 | Fri 10/01/25 | 5 days | Mon 06/01/25 | Fri 10/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.8 |  |  | SITAG |  | Identify exit points for Sprint 12 | 100% | Mon 20/01/25 | Fri 24/01/25 | 5 days | Mon 20/01/25 | Fri 24/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.9 |  |  | SITAG |  | Identify exit points for Sprint 13 | 100% | Mon 03/02/25 | Fri 07/02/25 | 5 days | Mon 03/02/25 | Fri 07/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.10 | T3 | T3-TE-0125 | SITAG |  | Exit point identified and evidence capture flags updated | 100% | Fri 07/02/25 | Fri 07/02/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
6 | 1.4.1.4.2.6 |  |  | SITAG |  | Environments (SIT-Staging) | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | -313 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.6.1 |  |  | SITAG |  | SIT Functional pre-requisites | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
8 | 1.4.1.4.2.6.1.1 |  |  | SITAG |  | DCC | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
9 | 1.4.1.4.2.6.1.1.1 |  |  | SITAG |  | CSS | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.1.1 |  |  | SITAG |  | SIT participants have requested DCC CSS PKI certificates for access to UIT-B environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.1.2 | T3 | T3-TE-0088 | SITAG |  | SIT participants have received DCC CSS PKI certificates for UIT-B environment | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) |  | 5.5 | Yes
9 | 1.4.1.4.2.6.1.1.2 |  |  | SITAG |  | DSP | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.2.1 |  |  | SITAG |  | SIT participants have requested DCC DSP PKI certificates for access to UIT-B environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 | 0 days | 0 days | 0 days | PPs in SDS Market Role |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.2.2 | T3 | T3-TE-0089 | SITAG |  | SIT participants have received DCC DSP PKI certificates for UIT-B environment | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 1 day | 0 days | 0 days | PPs in SDS Market Role |  | 5.5 | Yes
6 | 1.4.1.4.2.7 |  |  | SITAG |  | Stand up SIT A Environment | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 08/03/24 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
7 | 1.4.1.4.2.7.1 |  |  | SITAG |  | SIT Functional Connectivity Proving | 100% | Mon 12/02/24 | Fri 01/03/24 | 15 days | Mon 12/02/24 | Fri 01/03/24 | 0 days | 0 days | -5 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.2.7.1.1 |  |  | SITAG |  | SIT Functional Connectivity Proving Period | 100% | Mon 12/02/24 | Fri 01/03/24 | 15 days | Mon 12/02/24 | Fri 01/03/24 | 0 days | 0 days | -5 days | SI Test |  | 5.19 | Yes
8 | 1.4.1.4.2.7.1.2 | T3 | T3-TE-0103 | SITAG |  | SIT Functional Connectivity Proving Complete | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes
7 | 1.4.1.4.2.7.2 |  |  | SITAG |  | PP Environments (SIT A) | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 08/03/24 | 0 days | 0 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.7.2.1 |  |  | SITAG |  | Deployment of MHHS solution code to SIT A environments | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 08/03/24 | 0 days | 0 days | 20 days | PP |  | 5 | Yes
7 | 1.4.1.4.2.7.3 |  |  | SITAG |  | SI Environments (SIT A) | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 08/03/24 | 0 days | 0 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.7.3.1 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 08/03/24 | 0 days | 0 days | 20 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.2.8 |  |  | SITAG |  | Test data (SIT A) | 100% | Mon 18/12/23 | Mon 21/10/24 | 221 days? | Mon 18/12/23 | Mon 07/04/25 | 0 days | -120 days | -4 days? | N/A |  | 5.4 | Yes
7 | 1.4.1.4.2.8.1 |  |  | SITAG |  | Cycle 1 Test data (SIT A) | 100% | Mon 18/12/23 | Fri 01/03/24 | 55 days | Mon 18/12/23 | Fri 01/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.1.1 |  |  | SITAG |  | Prepare, Generate and Allocate Test Data | 100% | Mon 18/12/23 | Wed 24/01/24 | 28 days | Mon 18/12/23 | Wed 24/01/24 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.2 |  |  | SITAG |  | Transmit Data Sets to PPs | 100% | Fri 26/01/24 | Wed 31/01/24 | 4 days | Fri 26/01/24 | Wed 31/01/24 | 0 days | 0 days | 2 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.3 |  |  | SITAG |  | PP's Iterative load and data integrity check | 100% | Thu 01/02/24 | Fri 01/03/24 | 22 days | Thu 01/02/24 | Fri 01/03/24 | 0 days | 0 days | 12 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.4 | T3 | T3-TE-0079 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 1 - PP's confirmation that test data is ready for SIT Functional | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 1 day | 0 days | 0 days | SI Test Data |  | 5.18 | Yes
7 | 1.4.1.4.2.8.2 |  |  | SITAG |  | Cycle 2 Test data (inc. Settlement Data) (SIT A) | 100% | Thu 28/03/24 | Fri 14/06/24 | 57 days | Thu 28/03/24 | Fri 14/06/24 | 0 days | 0 days | 10 days | N/A |  | 6 | Yes
8 | 1.4.1.4.2.8.2.1 |  |  | SITAG |  | Prepare, Generate and Allocate Test Data | 100% | Thu 28/03/24 | Thu 09/05/24 | 31 days | Thu 28/03/24 | Thu 09/05/24 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.2 |  |  | SITAG |  | Transmit Data Sets to PPs | 100% | Fri 10/05/24 | Tue 14/05/24 | 3 days | Fri 10/05/24 | Tue 14/05/24 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.3 |  |  | SITAG |  | PP's Iterative load and data integrity check | 100% | Wed 15/05/24 | Fri 31/05/24 | 13 days | Wed 15/05/24 | Fri 31/05/24 | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.4 | T3 | T3-TE-0080 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 2 - PP's confirmation that test data is ready for SIT Functional | 100% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Fri 14/06/24 | Fri 14/06/24 | 1 day | 0 days | 0 days | SI Test Data |  | 5.27 | Yes
7 | 1.4.1.4.2.8.3 |  |  | SITAG |  | Cycle 3 Test data (SIT A) (2) | 100% | Mon 15/07/24 | Mon 21/10/24 | 71 days? | Mon 15/07/24 | Mon 21/10/24 | 0 days | 0 days | 30 days? | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.3.1 |  |  | SITAG |  | Cycle 3 data requirments analysis - check Cycle 2 data for gaps Check blocked test cases | 100% | Mon 15/07/24 | Fri 26/07/24 | 10 days? | Mon 15/07/24 | Fri 26/07/24 | 0 days | 0 days | 10 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.2 |  |  | SITAG |  | Provide DCC with MPANS for deletion secure file with password | 100% | Mon 12/08/24 | Mon 12/08/24 | 1 day? | Mon 12/08/24 | Mon 12/08/24 | 0 days | 0 days | 1 day? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.3 |  |  | SITAG |  | Receive MPANS from DCC to exclude | 100% | Fri 09/08/24 | Fri 09/08/24 | 1 day? | Fri 09/08/24 | Fri 09/08/24 | 0 days | 0 days | 1 day? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.4 |  |  | SITAG |  | Exclude MPANS from allocation | 100% | Fri 16/08/24 | Fri 16/08/24 | 1 day | Fri 16/08/24 | Fri 16/08/24 | 0 days | 0 days | 1 day | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.5 |  |  | SITAG |  | Allocate Cycle 3 MPANS | 100% | Tue 06/08/24 | Tue 27/08/24 | 16 days? | Tue 06/08/24 | Tue 27/08/24 | 0 days | 0 days | 16 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.6 |  |  | SITAG |  | Generate Cycle 3 Data | 100% | Tue 27/08/24 | Wed 28/08/24 | 2 days? | Tue 27/08/24 | Wed 28/08/24 | 0 days | 0 days | 2 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.7 |  |  | SITAG |  | Check data prior to sending to DCC | 100% | Thu 22/08/24 | Wed 28/08/24 | 5 days? | Thu 22/08/24 | Wed 28/08/24 | 0 days | 0 days | 5 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.8 |  |  | SITAG |  | Share Cycle 3 MPAN data with DCC | 100% | Thu 29/08/24 | Thu 29/08/24 | 1 day? | Thu 29/08/24 | Thu 29/08/24 | 0 days | 0 days | 1 day? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.9 |  |  | SITAG |  | DCC - load data and create registration Id's for Cycle 3 data | 100% | Tue 27/08/24 | Thu 12/09/24 | 13 days? | Tue 27/08/24 | Thu 12/09/24 | 0 days | 0 days | 13 days? | DCC |  | 6 | Yes
8 | 1.4.1.4.2.8.3.10 |  |  | SITAG |  | Add registration ID's to Cycle 3 Data | 100% | Thu 12/09/24 | Fri 13/09/24 | 2 days? | Thu 12/09/24 | Fri 13/09/24 | 0 days | 0 days | 2 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.11 |  |  | SITAG |  | Share subset of data with St Cls for data load | 100% | Thu 12/09/24 | Fri 13/09/24 | 2 days? | Thu 12/09/24 | Fri 13/09/24 | 0 days | 0 days | 2 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.12 |  |  | SITAG |  | St Clements to run test with Subset of data - MPRS business process checks including Import/Export MPANS | 100% | Mon 16/09/24 | Fri 20/09/24 | 5 days? | Mon 16/09/24 | Fri 20/09/24 | 0 days | 0 days | 5 days? | SCS |  | 6 | Yes
8 | 1.4.1.4.2.8.3.13 |  |  | SITAG |  | Send Cycle 3 data to partcipants for early sight of data | 100% | Wed 25/09/24 | Fri 27/09/24 | 3 days? | Wed 25/09/24 | Fri 27/09/24 | 0 days | 0 days | 3 days? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.14 |  |  | SITAG |  | St Clements MPRS data load bulk files for Cycle 3 | 100% | Mon 23/09/24 | Fri 11/10/24 | 15 days? | Mon 23/09/24 | Fri 11/10/24 | 0 days | 0 days | 15 days? | SCS |  | 6 | Yes
8 | 1.4.1.4.2.8.3.15 |  |  | SITAG |  | New MPAN creation and load through DCC and St Clements | 100% | Fri 11/10/24 | Fri 11/10/24 | 1 day? | Fri 11/10/24 | Fri 11/10/24 | 0 days | 0 days | 1 day? | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.16 |  |  | SITAG |  | Share files with PP's and central parties | 100% | Fri 11/10/24 | Fri 11/10/24 | 1 day | Fri 11/10/24 | Fri 11/10/24 | 0 days | 0 days | 1 day | SI Test Data |  | 6 | Yes
8 | 1.4.1.4.2.8.3.17 |  |  | SITAG |  | Avanade to load data | 100% | Mon 14/10/24 | Mon 21/10/24 | 6 days | Mon 14/10/24 | Mon 21/10/24 | 0 days | 0 days | 6 days | DIP Provider |  | 6 | Yes
8 | 1.4.1.4.2.8.3.18 |  |  | SITAG |  | Helix to load data | 100% | Mon 14/10/24 | Mon 21/10/24 | 6 days | Mon 14/10/24 | Mon 21/10/24 | 0 days | 0 days | 6 days | Helix |  | 6 | Yes
8 | 1.4.1.4.2.8.3.19 |  |  | SITAG |  | PP's and central parties to load all Cycle 3 data | 100% | Mon 14/10/24 | Mon 21/10/24 | 6 days | Mon 14/10/24 | Mon 21/10/24 | 0 days | 0 days | 6 days | PPs |  | 6 | Yes
8 | 1.4.1.4.2.8.3.20 | T3 | T3-TE-0081 | SITAG |  | All parties to finalise data load | 100% | Mon 21/10/24 | Mon 21/10/24 | 1 day? | Mon 21/10/24 | Mon 21/10/24 | 0 days | 0 days | 1 day? | SI Data |  | 6 | Yes
6 | 1.4.1.4.2.9 |  |  | SITAG |  | SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Fri 01/03/24 | 45 days | Mon 01/01/24 | Fri 01/03/24 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
7 | 1.4.1.4.2.9.1 |  |  | SITAG |  | PP SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Thu 29/02/24 | 44 days | Mon 01/01/24 | Thu 29/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.9.1.1 |  |  | SITAG |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | Mon 01/01/24 | Mon 29/01/24 | 21 days | Mon 01/01/24 | Mon 29/01/24 | 0 days | 0 days | 1 day | PP |  | 5 | Yes
8 | 1.4.1.4.2.9.1.2 |  |  | SITAG |  | Placing Reliance Stage 2 Review | 100% | Mon 15/01/24 | Thu 29/02/24 | 34 days | Mon 15/01/24 | Thu 29/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.2.9.1.3 |  |  | SITAG |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | Tue 30/01/24 | Fri 09/02/24 | 9 days | Tue 30/01/24 | Fri 09/02/24 | 0 days | 0 days | -1 day | PP |  | 5 | Yes
7 | 1.4.1.4.2.9.2 |  |  | SITAG |  | SI SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Fri 23/02/24 | 40 days | Mon 01/01/24 | Fri 23/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.9.2.1 |  |  | SITAG |  | Assure Test Participants' Test Readiness Reports | 100% | Mon 01/01/24 | Fri 16/02/24 | 35 days | Mon 01/01/24 | Fri 16/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.9.2.2 |  |  | SITAG |  | Develop Overarching SIT Functional Test Readiness Report | 100% | Mon 22/01/24 | Fri 16/02/24 | 20 days | Mon 22/01/24 | Fri 16/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.9.2.3 |  |  | SITAG |  | Artefact review (via TMAG) and updates | 100% | Mon 19/02/24 | Fri 23/02/24 | 5 days | Mon 19/02/24 | Fri 23/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.9.3 | T2 | T2-TE-0550 | SITAG |  | SIT Functional Testing Preparation Complete | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.4.3 |  |  | SITAG |  | SIT Migration Testing Preparation | 100% | Mon 31/10/22 | Fri 07/02/25 | 595 days? | Mon 31/10/22 | Fri 04/10/24 | 0 days | 90 days | 175 days? | N/A |  | 5.21 | Yes
6 | 1.4.1.4.3.1 |  |  | SITAG |  | Test Approach & Plan | 100% | Thu 07/09/23 | Wed 20/12/23 | 75 days | Thu 07/09/23 | Wed 20/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.1.1 |  |  | SITAG |  | Develop document with SITWG | 100% | Thu 07/09/23 | Fri 20/10/23 | 32 days | Thu 07/09/23 | Fri 20/10/23 | 0 days | 0 days | 7 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.2 |  |  | SITAG |  | Draft document review with Code Bodies | 100% | Mon 23/10/23 | Wed 01/11/23 | 8 days | Mon 23/10/23 | Wed 01/11/23 | 0 days | 0 days | -2 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.3 |  |  | SITAG |  | Industry Consultation | 100% | Thu 02/11/23 | Wed 15/11/23 | 10 days | Thu 02/11/23 | Wed 15/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.3.1.4 |  |  | SITAG |  | Artefact review (via TMAG) and updates | 100% | Thu 16/11/23 | Wed 20/12/23 | 25 days | Thu 16/11/23 | Wed 20/12/23 | 0 days | 0 days | -5 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.5 | T3 | T3-TE-0018 | SITAG | MHHS-ART073 | SIT Migration Testing Test Approach & Plan approved | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 1 day | 0 days | -1 day | SI Test |  | 5.14 | Yes
6 | 1.4.1.4.3.2 |  |  | SITAG |  | Test Data Approach & Plan | 100% | Thu 02/11/23 | Wed 20/12/23 | 35 days | Thu 02/11/23 | Wed 20/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.2.1 |  |  | SITAG |  | Industry Consultation | 100% | Thu 02/11/23 | Wed 15/11/23 | 10 days | Thu 02/11/23 | Wed 15/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.3.2.2 |  |  | SITAG |  | Artefact review (via TMAG) and updates | 100% | Thu 16/11/23 | Wed 20/12/23 | 25 days | Thu 16/11/23 | Wed 20/12/23 | 0 days | 0 days | -5 days | SI Test Data |  | 5 | Yes
7 | 1.4.1.4.3.2.3 |  |  | SITAG |  | SIT Migration Test Data Test Approach & Plan approved | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
6 | 1.4.1.4.3.3 |  |  | SITAG |  | Test scenarios & Test Cases | 100% | Thu 21/12/23 | Fri 07/02/25 | 297 days? | Thu 21/12/23 | Fri 04/10/24 | 0 days | 90 days | 232 days? | N/A |  | 5.16 | Yes
7 | 1.4.1.4.3.3.1 |  |  | SITAG |  | Theme 1 | 100% | Thu 21/12/23 | Wed 20/03/24 | 65 days | Thu 21/12/23 | Wed 20/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 24/01/24 | 25 days | Thu 21/12/23 | Wed 24/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Thu 25/01/24 | Thu 25/01/24 | 1 day | Thu 25/01/24 | Thu 25/01/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Mon 05/02/24 | Mon 12/02/24 | 6 days | Mon 05/02/24 | Mon 12/02/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | Thu 29/02/24 | Wed 06/03/24 | 5 days | Thu 29/02/24 | Wed 06/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.19 | Yes
8 | 1.4.1.4.3.3.1.5 | T3 | T3-TE-0110 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 1 | 100% | Wed 20/03/24 | Wed 20/03/24 | 0 days | Wed 20/03/24 | Wed 20/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5.21 | Yes
7 | 1.4.1.4.3.3.2 |  |  | SITAG |  | Theme 2 | 100% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 17/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 14/02/24 | 40 days | Thu 21/12/23 | Wed 14/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Thu 15/02/24 | Thu 15/02/24 | 1 day | Thu 15/02/24 | Thu 15/02/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Mon 26/02/24 | Mon 04/03/24 | 6 days | Mon 26/02/24 | Mon 04/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.19 | Yes
8 | 1.4.1.4.3.3.2.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | Thu 28/03/24 | Wed 03/04/24 | 5 days | Thu 28/03/24 | Wed 03/04/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.5 | T3 | T3-TE-0111 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 2 | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.22 | Yes
7 | 1.4.1.4.3.3.3 |  |  | SITAG |  | Theme 3 | 100% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 17/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 06/03/24 | 55 days | Thu 21/12/23 | Wed 06/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
8 | 1.4.1.4.3.3.3.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Thu 07/03/24 | Thu 07/03/24 | 1 day | Thu 07/03/24 | Thu 07/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Wed 13/03/24 | Wed 20/03/24 | 6 days | Wed 13/03/24 | Wed 20/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | Thu 28/03/24 | Wed 03/04/24 | 5 days | Thu 28/03/24 | Wed 03/04/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.5 | T3 | T3-TE-0112 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 3 | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.22 | Yes
7 | 1.4.1.4.3.3.4 |  |  | SITAG |  | RTTM Development | 100% | Thu 29/08/24 | Fri 20/09/24 | 17 days | Thu 29/08/24 | Fri 04/10/24 | 0 days | -10 days | 17 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.4.1 |  |  | SITAG |  | Develop Manual SIT Migration RTTM | 100% | Thu 29/08/24 | Fri 20/09/24 | 17 days | Thu 29/08/24 | Fri 20/09/24 | 0 days | 0 days | 17 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.4.2 |  |  | SITAG |  | Manual SIT Migration RTTM Complete | 100% | Fri 20/09/24 | Fri 20/09/24 | 0 days | Fri 20/09/24 | Fri 20/09/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.1.4.3.3.5 |  |  | SITAG |  | Gap analysis | 100% | Thu 12/09/24 | Fri 07/02/25 | 107 days? | Thu 12/09/24 | Fri 04/10/24 | 0 days | 90 days | 107 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.1 |  |  | SITAG |  | Identify gaps in test case coverage following RTTM review. | 100% | Thu 12/09/24 | Fri 27/09/24 | 12 days | Thu 12/09/24 | Fri 27/09/24 | 0 days | 0 days | 12 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.2 |  |  | SITAG |  | Address gaps in test case coverage following RTTM review. | 100% | Thu 19/09/24 | Fri 11/10/24 | 17 days | Thu 19/09/24 | Fri 04/10/24 | 0 days | 5 days | 17 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.3 |  |  | SITAG |  | Gap analysis complete | 100% | Fri 11/10/24 | Fri 11/10/24 | 0 days? | Fri 04/10/24 | Fri 04/10/24 | 6 days | 5 days | 0 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.4 |  |  | SITAG |  | Test Script updates identified | 100% | Mon 14/10/24 | Mon 14/10/24 | 1 day? | Mon 14/10/24 | Mon 14/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.5 |  |  | SITAG |  | Test Scripts updates | 100% | Mon 14/10/24 | Mon 04/11/24 | 16 days? | Mon 14/10/24 | Mon 04/11/24 | 0 days | 0 days | 16 days? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.6 |  |  | SITAG |  | RTTM Updated | 100% | Tue 29/10/24 | Tue 29/10/24 | 1 day? | Tue 29/10/24 | Tue 29/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.7 |  |  | SITAG |  | Removal of de-scoped TCs from the RTTMs | 100% | Thu 31/10/24 | Fri 01/11/24 | 2 days | Thu 31/10/24 | Fri 01/11/24 | 0 days | 0 days | 2 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.8 |  |  | SITAG |  | Update and stabilisation of all TC ADO IDs | 100% | Thu 31/10/24 | Fri 01/11/24 | 2 days | Thu 31/10/24 | Fri 01/11/24 | 0 days | 0 days | 2 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.9 |  |  | SITAG |  | Addition and integration of Role tags to reqs in the Role RTTMs | 100% | Wed 30/10/24 | Fri 01/11/24 | 3 days | Wed 30/10/24 | Fri 01/11/24 | 0 days | 0 days | 3 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.10 |  |  | SITAG |  | Update of the RTTM All sheet (porting of the individual RTTMs) | 100% | Thu 31/10/24 | Fri 01/11/24 | 2 days | Thu 31/10/24 | Fri 01/11/24 | 0 days | 0 days | 2 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.11 |  |  | SITAG |  | ADO IDs corrected | 100% | Mon 04/11/24 | Mon 04/11/24 | 1 day? | Mon 04/11/24 | Mon 04/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.12 |  |  | SITAG |  | Migration RTTM ready for import into ADO | 100% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.13 |  |  | SITAG |  | Issue Static RTTM to Code Bodies | 100% | Tue 05/11/24 | Tue 05/11/24 | 1 day? | Tue 05/11/24 | Tue 05/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.14 |  |  | SITAG |  | Implement Code Bodies feedback on RTTM | 100% | Wed 06/11/24 | Wed 13/11/24 | 6 days | Wed 06/11/24 | Wed 13/11/24 | 0 days | 0 days | 6 days | SI Test |  | 6.12 | Yes
8 | 1.4.1.4.3.3.5.15 |  |  | SITAG |  | Code Body Acceptance of RTTM | 100% | Wed 13/11/24 | Wed 13/11/24 | 0 days | Wed 06/11/24 | Wed 13/11/24 | 6 days | 0 days | 0 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.16 |  |  | SITAG |  | ADO Clean-up | 100% | Thu 24/10/24 | Fri 15/11/24 | 17 days? | Thu 24/10/24 | Fri 15/11/24 | 0 days | 0 days | 17 days? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.1 |  |  | SITAG |  | Theme alignment | 100% | Mon 28/10/24 | Mon 28/10/24 | 1 day? | Mon 28/10/24 | Mon 28/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.2 |  |  | SITAG |  | Understand Additional suffix Fields in ADO as defined by Kevin | 100% | Fri 25/10/24 | Fri 25/10/24 | 1 day? | Fri 25/10/24 | Fri 25/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.3 |  |  | SITAG |  | Correct Missing Test Case References | 100% | Mon 28/10/24 | Mon 28/10/24 | 1 day? | Mon 28/10/24 | Mon 28/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.4 |  |  | SITAG |  | Load Functional RTTMs into ADO | 100% | Mon 28/10/24 | Mon 28/10/24 | 1 day? | Mon 28/10/24 | Mon 28/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.5 |  |  | SITAG |  | Load Migration RTTMs into ADO | 100% | Wed 06/11/24 | Wed 06/11/24 | 1 day? | Wed 06/11/24 | Wed 06/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.6 |  |  | SITAG |  | Confirm Missing fields in ADO are resolved | 100% | Thu 07/11/24 | Thu 07/11/24 | 1 day? | Thu 07/11/24 | Thu 07/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.7 |  |  | SITAG |  | Reload Functional RTTM into ADO | 100% | Thu 07/11/24 | Thu 07/11/24 | 1 day? | Thu 07/11/24 | Thu 07/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.8 |  |  | SITAG |  | ADO Design Documentation | 100% | Mon 04/11/24 | Fri 15/11/24 | 10 days? | Mon 04/11/24 | Fri 15/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.11 | Yes
10 | 1.4.1.4.3.3.5.16.8.1 |  |  | SITAG |  | Produce ADO high Level Design and Data Model | 100% | Fri 15/11/24 | Fri 15/11/24 | 1 day? | Fri 15/11/24 | Fri 15/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
10 | 1.4.1.4.3.3.5.16.8.2 |  |  | SITAG |  | Produce Report derivation document | 100% | Fri 15/11/24 | Fri 15/11/24 | 1 day? | Fri 15/11/24 | Fri 15/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.17 |  |  | SITAG |  | Test Case Rationalisation (Functional + Migration) | 100% | Thu 07/11/24 | Fri 07/02/25 | 67 days | Thu 07/11/24 | Fri 20/12/24 | 0 days | 35 days | 67 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.1 |  |  | SITAG |  | Internal preliminary rationalisation workshop 1 | 100% | Thu 07/11/24 | Thu 07/11/24 | 1 day | Thu 07/11/24 | Thu 07/11/24 | 0 days | 0 days | 1 day | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.2 |  |  | SITAG |  | Baseline RTTMs | 100% | Wed 13/11/24 | Wed 13/11/24 | 0 days | Wed 13/11/24 | Wed 13/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.3 |  |  | SITAG |  | Baseline test cases | 100% | Wed 13/11/24 | Wed 13/11/24 | 0 days | Wed 13/11/24 | Wed 13/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.4 |  |  | SITAG |  | Produce requirements / test case analysis doc | 100% | Thu 14/11/24 | Thu 14/11/24 | 1 day | Thu 14/11/24 | Thu 14/11/24 | 0 days | 0 days | 1 day | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.5 |  |  | SITAG |  | Internal finalisation rationalisation workshop 2 | 100% | Fri 15/11/24 | Tue 03/12/24 | 13 days | Fri 15/11/24 | Tue 03/12/24 | 0 days | 0 days | 13 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.6 |  |  | SITAG |  | SRO walkthrough | 100% | Wed 04/12/24 | Wed 04/12/24 | 1 day | Wed 04/12/24 | Wed 04/12/24 | 0 days | 0 days | 1 day | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.7 |  |  | SITAG |  | Code Bodies walkthrough | 100% | Wed 04/12/24 | Wed 04/12/24 | 1 day | Wed 04/12/24 | Wed 04/12/24 | 0 days | 0 days | 1 day | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.8 |  |  | SITAG |  | Send invites to PPs for walkthrough | 100% | Wed 04/12/24 | Wed 04/12/24 | 1 day | Wed 04/12/24 | Wed 04/12/24 | 0 days | 0 days | 1 day | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.9 |  |  | SITAG |  | PP walkthrough | 100% | Tue 17/12/24 | Tue 17/12/24 | 1 day | Tue 17/12/24 | Tue 17/12/24 | 0 days | 0 days | 1 day | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.10 |  |  | SITAG |  | Update requirements / test case analysis doc | 100% | Thu 05/12/24 | Tue 14/01/25 | 29 days | Thu 05/12/24 | Tue 14/01/25 | 0 days | 0 days | 29 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.11 |  |  | SITAG |  | SITWG Paper Day | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.12 |  |  | SITAG |  | SITWG recommendation on requirements / test case analysis doc | 100% | Tue 21/01/25 | Tue 21/01/25 | 0 days | Tue 21/01/25 | Tue 21/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.13 |  |  | SITAG |  | Issue to SITAG / SITAG paper day | 100% | Wed 22/01/25 | Wed 22/01/25 | 0 days | Wed 22/01/25 | Wed 22/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.14 |  |  | SITAG |  | Prepare ADO update | 100% | Wed 22/01/25 | Wed 29/01/25 | 6 days | Wed 22/01/25 | Wed 29/01/25 | 0 days | 0 days | 6 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.15 |  |  | SITAG |  | Sign off by SITAG | 100% | Wed 29/01/25 | Wed 29/01/25 | 0 days | Wed 29/01/25 | Wed 29/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.16 |  |  | SITAG |  | Update ADO | 100% | Thu 30/01/25 | Fri 07/02/25 | 7 days | Thu 30/01/25 | Fri 07/02/25 | 0 days | 0 days | 7 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.17 |  |  | SITAG |  | Update all ADO reporting | 100% | Thu 30/01/25 | Fri 07/02/25 | 7 days | Thu 30/01/25 | Fri 07/02/25 | 0 days | 0 days | 7 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.18 |  |  | SITAG |  | Update test cases | 100% | Thu 30/01/25 | Fri 07/02/25 | 7 days | Thu 30/01/25 | Fri 07/02/25 | 0 days | 0 days | 7 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.19 |  |  | SITAG |  | Update RTTM | 100% | Thu 30/01/25 | Fri 07/02/25 | 7 days | Thu 30/01/25 | Fri 07/02/25 | 0 days | 0 days | 7 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.20 |  |  | SITAG |  | Update master test case spreadsheet | 100% | Thu 30/01/25 | Fri 07/02/25 | 7 days | Thu 30/01/25 | Fri 07/02/25 | 0 days | 0 days | 7 days | SI Test |  | 6.17 | Yes
9 | 1.4.1.4.3.3.5.17.21 | T3 | T3-TE-0141 | SITAG |  | Test Case Rationalisation complete | 100% | Fri 07/02/25 | Fri 07/02/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.3.4 |  |  | SITAG |  | Environments (SIT B) | 100% | Mon 31/10/22 | Fri 28/06/24 | 435 days | Mon 31/10/22 | Fri 28/06/24 | 0 days | 0 days | 15 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.4.1 |  |  | SITAG |  | PP Environments (SIT B) | 100% | Fri 03/05/24 | Fri 28/06/24 | 41 days | Fri 03/05/24 | Fri 28/06/24 | 0 days | 0 days | 15 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.4.1.1 |  |  | SITAG |  | PP Environments available | 100% | Fri 03/05/24 | Fri 03/05/24 | 0 days | Fri 03/05/24 | Fri 03/05/24 | 0 days | -1 day | 0 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.2 |  |  | SITAG |  | PP Onboarding / Smoke test | 100% | Mon 13/05/24 | Fri 28/06/24 | 35 days | Mon 13/05/24 | Fri 28/06/24 | 0 days | 0 days | 15 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.3 |  |  | SITAG |  | DTN Connectivity Proving Complete | 100% | Mon 10/06/24 | Fri 14/06/24 | 5 days | Mon 10/06/24 | Fri 14/06/24 | 0 days | 0 days | 5 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.4 |  |  | SITAG |  | PP Code Deployment | 100% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Fri 14/06/24 | Fri 14/06/24 | 1 day | 0 days | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.3.4.2 |  |  | SITAG |  | SI Environments (SIT B) | 100% | Mon 31/10/22 | Fri 14/06/24 | 425 days | Mon 31/10/22 | Fri 14/06/24 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.4.2.1 |  |  | SITAG |  | Coordinate SIT Participants' SIT B environment preparation | 100% | Mon 31/10/22 | Fri 07/06/24 | 420 days | Mon 31/10/22 | Fri 07/06/24 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.2 |  |  | SITAG |  | Assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | Fri 07/06/24 | Fri 07/06/24 | 0 days | Fri 07/06/24 | Fri 07/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.3 | T3 | T3-TE-0033 | SITAG |  | SIT Participants' SIT B environments ready to start connectivity proving (incl. certificates and security compliance) | 100% | Wed 05/06/24 | Wed 05/06/24 | 0 days | Wed 05/06/24 | Wed 05/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5.26 | Yes
8 | 1.4.1.4.3.4.2.4 |  |  | SITAG |  | Coordinate SIT Participants' SIT B environment connectivity proving | 100% | Thu 06/06/24 | Fri 07/06/24 | 2 days | Thu 06/06/24 | Fri 07/06/24 | 0 days | 0 days | -17 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.5 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Fri 14/06/24 | Fri 14/06/24 | 1 day | 0 days | -4 days | SI Test |  | 5.21 | Yes
6 | 1.4.1.4.3.5 |  |  | SITAG |  | SIT Migration Test Readiness Report | 100% | Tue 02/04/24 | Fri 31/05/24 | 44 days | Tue 02/04/24 | Fri 31/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.5.1 |  |  | SITAG |  | PP SIT Migration Test Readiness Report | 100% | Tue 02/04/24 | Fri 31/05/24 | 44 days | Tue 02/04/24 | Fri 31/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.5.1.1 |  |  | SITAG |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | Tue 02/04/24 | Mon 29/04/24 | 20 days | Tue 02/04/24 | Mon 29/04/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.3.5.1.2 |  |  | SITAG |  | Placing Reliance Stage 2 Review | 100% | Mon 15/04/24 | Fri 31/05/24 | 35 days | Mon 15/04/24 | Fri 31/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.3.5.1.3 |  |  | SITAG |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | Tue 30/04/24 | Mon 13/05/24 | 10 days | Tue 30/04/24 | Mon 13/05/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.3.5.2 |  |  | SITAG |  | SI SIT Migration Test Readiness Report | 100% | Tue 02/04/24 | Mon 27/05/24 | 40 days | Tue 02/04/24 | Mon 27/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.5.2.1 |  |  | SITAG |  | Assure Test Participants' Test Readiness Reports | 100% | Tue 02/04/24 | Mon 20/05/24 | 35 days | Tue 02/04/24 | Mon 20/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.3.5.2.2 |  |  | SITAG |  | Develop Overarching SIT Migration Test Readiness Report | 100% | Tue 23/04/24 | Mon 20/05/24 | 20 days | Tue 23/04/24 | Mon 20/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.3.5.2.3 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | Tue 21/05/24 | Mon 27/05/24 | 5 days | Tue 21/05/24 | Mon 27/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.3.6 | T2 | T2-TE-0650 | SITAG |  | SIT Migration Testing Preparation Complete | 100% | Mon 03/06/24 | Mon 03/06/24 | 0 days | Mon 03/06/24 | Mon 03/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.4.4 |  |  | SITAG |  | SIT Non-Functional Preparation | 100% | Thu 30/11/23 | Fri 28/03/25 | 347 days? | Thu 30/11/23 | Fri 14/03/25 | 0 days | 10 days | 154 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.4.1 |  |  | SITAG |  | Test Approach & Plan | 100% | Thu 30/11/23 | Wed 15/05/24 | 120 days | Thu 30/11/23 | Wed 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.1.1 |  |  | SITAG |  | Develop document with SITWG | 100% | Thu 30/11/23 | Fri 01/03/24 | 67 days | Thu 30/11/23 | Fri 01/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.1.2 |  |  | SITAG |  | Draft document review with Code Bodies | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.1.3 |  |  | SITAG |  | Industry Consultation | 100% | Mon 18/03/24 | Fri 29/03/24 | 10 days | Mon 18/03/24 | Fri 29/03/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.4.1.4 |  |  | SITAG |  | Industry Assurance Review | 100% | Thu 11/04/24 | Wed 17/04/24 | 5 days | Thu 11/04/24 | Wed 17/04/24 | 0 days | 0 days | 0 days |  |  | 5.16 | Yes
7 | 1.4.1.4.4.1.5 | T3 | T3-TE-0026 | SITAG | MHHS-ART073 | SIT Non-Functional Testing Test Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.3 | Yes
6 | 1.4.1.4.4.2 |  |  | SITAG |  | Test Data Approach & Plan | 100% | Wed 20/03/24 | Wed 15/05/24 | 41 days | Wed 20/03/24 | Wed 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.2.1 |  |  | SITAG |  | Industry Consultation | 100% | Wed 20/03/24 | Mon 08/04/24 | 14 days | Wed 20/03/24 | Mon 08/04/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.4.2.2 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | Tue 09/04/24 | Wed 15/05/24 | 27 days | Tue 09/04/24 | Wed 15/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.2.3 | T3 | T3-TE-0113 | SITAG |  | SIT Non-Functional Testing Test Data Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.24 | Yes
6 | 1.4.1.4.4.3 |  |  | SITAG |  | Test scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 17/07/24 | 98 days? | Mon 04/03/24 | Wed 17/07/24 | 0 days | 0 days | -25 days? | N/A |  | 5.21 | Yes
7 | 1.4.1.4.4.3.1 |  |  | SITAG |  | Theme 1 | 100% | Mon 04/03/24 | Wed 19/06/24 | 78 days | Mon 04/03/24 | Wed 19/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 17/04/24 | 33 days | Mon 04/03/24 | Wed 17/04/24 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Thu 18/04/24 | Thu 18/04/24 | 1 day | Thu 18/04/24 | Thu 18/04/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Thu 02/05/24 | Fri 10/05/24 | 7 days | Thu 02/05/24 | Fri 10/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.4 |  |  | SITAG |  | Review with NFT Working Group | 100% | Fri 31/05/24 | Thu 06/06/24 | 5 days | Fri 31/05/24 | Thu 06/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.5 | T3 | T3-TE-0114 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 1 | 100% | Wed 19/06/24 | Wed 19/06/24 | 0 days | Wed 19/06/24 | Wed 19/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5.3 | Yes
7 | 1.4.1.4.4.3.2 |  |  | SITAG |  | Theme 2 | 100% | Mon 04/03/24 | Wed 17/07/24 | 98 days | Mon 04/03/24 | Wed 17/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 15/05/24 | 53 days | Mon 04/03/24 | Wed 15/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Thu 16/05/24 | Thu 16/05/24 | 1 day | Thu 16/05/24 | Thu 16/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Mon 20/05/24 | Tue 28/05/24 | 7 days | Mon 20/05/24 | Tue 28/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.4 |  |  | SITAG |  | Review with NFT Working Group | 100% | Fri 28/06/24 | Thu 04/07/24 | 5 days | Fri 28/06/24 | Thu 04/07/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.5 | T3 | T3-TE-0115 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 2 | 100% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 1 day | 0 days | 0 days | SI Test |  | 5.22 | Yes
7 | 1.4.1.4.4.3.3 |  |  | SITAG |  | Theme 3 | 100% | Mon 04/03/24 | Wed 17/07/24 | 98 days? | Mon 04/03/24 | Wed 17/07/24 | 0 days | 0 days | -25 days? | N/A |  | 6 | Yes
8 | 1.4.1.4.4.3.3.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 29/05/24 | 63 days | Mon 04/03/24 | Wed 29/05/24 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.4.3.3.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Thu 30/05/24 | Thu 30/05/24 | 1 day | Thu 30/05/24 | Thu 30/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Mon 10/06/24 | Mon 17/06/24 | 6 days | Mon 10/06/24 | Mon 17/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.4 |  |  | SITAG |  | Review with NFT Working Group | 100% | Fri 28/06/24 | Thu 04/07/24 | 5 days | Fri 28/06/24 | Thu 04/07/24 | 0 days | 0 days | -25 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.5 | T3 | T3-TE-0116 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 3 | 100% | Wed 18/09/24 | Wed 18/09/24 | 0 days | Wed 18/09/24 | Wed 18/09/24 | 0 days | -1 day | 0 days | SI Test |  | 5.3 | Yes
6 | 1.4.1.4.4.4 |  |  | SITAG |  | SIT NFT Programme RTTM | 100% | Wed 18/09/24 | Tue 19/11/24 | 45 days | Wed 18/09/24 | Wed 16/10/24 | 0 days | 24 days | 45 days | SI Test |  | 6.11 | Yes
7 | 1.4.1.4.4.4.1 |  |  | SITAG |  | Develop Manual SIT NFT RTTM | 100% | Wed 18/09/24 | Tue 29/10/24 | 30 days | Wed 18/09/24 | Tue 29/10/24 | 0 days | 0 days | 30 days | SI Test |  | 6.11 | Yes
7 | 1.4.1.4.4.4.2 |  |  | SITAG |  | LDP peer review | 100% | Wed 30/10/24 | Tue 12/11/24 | 10 days | Wed 30/10/24 | Tue 12/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6.11 | Yes
7 | 1.4.1.4.4.4.3 |  |  | SITAG |  | Review with SRO | 100% | Wed 13/11/24 | Tue 19/11/24 | 5 days | Wed 13/11/24 | Tue 19/11/24 | 0 days | 0 days | 5 days | SI Test |  | 6.11 | Yes
7 | 1.4.1.4.4.4.4 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO to review | 100% | Wed 13/11/24 | Tue 19/11/24 | 5 days | Wed 13/11/24 | Tue 19/11/24 | 0 days | 0 days | 5 days | SI Test |  | 6.12 | Yes
7 | 1.4.1.4.4.4.5 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO acceptance of RTTM | 100% | Tue 19/11/24 | Tue 19/11/24 | 0 days | Tue 19/11/24 | Tue 19/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.4.4.6 |  |  | SITAG |  | Manual SIT NFT RTTM Complete | 100% | Tue 19/11/24 | Tue 19/11/24 | 0 days | Tue 19/11/24 | Tue 19/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
6 | 1.4.1.4.4.5 |  |  | SITAG |  | NFT (Theme 1, 2 and 3) DITL | 100% | Mon 03/02/25 | Wed 26/02/25 | 18 days | Tue 08/10/24 | Thu 17/10/24 | 84 days | 94 days | 18 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.4.5.1 |  |  | SITAG |  | DITL Development | 100% | Mon 03/02/25 | Fri 14/02/25 | 10 days | Mon 03/02/25 | Fri 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.4.5.2 |  |  | SITAG |  | SRO Review | 100% | Mon 17/02/25 | Fri 21/02/25 | 5 days | Mon 17/02/25 | Fri 21/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.4.5.3 |  |  | SITAG |  | Post-SRO Review Changes | 100% | Mon 24/02/25 | Wed 26/02/25 | 3 days | Mon 24/02/25 | Wed 26/02/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.4.5.4 |  |  | SITAG |  | Programme DITL walkthrough with PPs on Theme 1, 2 and 3 | 100% | Wed 26/02/25 | Wed 26/02/25 | 0 days | Wed 26/02/25 | Wed 26/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.4.6 |  |  | SITAG |  | NFT Performance Tool Theme 1 Setup | 100% | Mon 04/03/24 | Wed 12/03/25 | 268 days? | Mon 04/03/24 | Fri 10/01/25 | 0 days | 43 days | 268 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.4.6.1 |  |  | SITAG |  | Theme 1 injection tool initial POC | 100% | Mon 04/03/24 | Fri 28/06/24 | 85 days? | Mon 04/03/24 | Fri 28/06/24 | 0 days | 0 days | 85 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.4.6.2 |  |  | SITAG |  | Theme 1 injection tool configuration and validation against DIP SIM (IR7.1) | 100% | Mon 01/07/24 | Wed 21/08/24 | 38 days | Mon 01/07/24 | Wed 21/08/24 | 0 days | 0 days | 38 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.4.6.3 |  |  | SITAG |  | Theme 1 injection tool configuration and validation against DIP SIM (IR8.1) | 100% | Thu 22/08/24 | Tue 01/10/24 | 29 days | Thu 22/08/24 | Tue 01/10/24 | 0 days | 0 days | 29 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.4.6.4 |  |  | SITAG |  | Theme 1 injection tool configuration and validation againast UIT DIP (IR8.1) | 100% | Wed 02/10/24 | Wed 16/10/24 | 11 days | Wed 02/10/24 | Wed 16/10/24 | 0 days | 0 days | 11 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.4.6.5 |  |  | SITAG |  | Theme 1 injection tool configuration and validation against SIT-B DIP (IR8.4) | 100% | Mon 10/03/25 | Wed 12/03/25 | 3 days? | Mon 06/01/25 | Wed 08/01/25 | 45 days | 45 days | 3 days? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.4.7 |  |  | SITAG |  | Environments (SIT B) | 100% | Tue 27/08/24 | Fri 28/02/25 | 134 days | Tue 27/08/24 | Fri 03/01/25 | 0 days | 40 days | 134 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.7.1 |  |  | SITAG |  | PP Environments (SIT B) | 100% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.7.1.1 |  |  | SITAG |  | Deployment of MHHS solution code to SIT B environments | 100% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 0 days | -1 day | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.4.7.2 |  |  | SITAG |  | SI Environments (SIT B) | 100% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.7.2.1 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 0 days | -1 day | 0 days | SI Test |  | 5.21 | Yes
7 | 1.4.1.4.4.7.3 |  |  | SITAG |  | Helix and Avanade Environments Upscale | 100% | Mon 24/02/25 | Fri 28/02/25 | 5 days | Mon 23/12/24 | Fri 03/01/25 | 45 days | 40 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.4.7.3.1 |  |  | SITAG |  | Environment Uplift Window (Technical Check) | 100% | Mon 24/02/25 | Fri 28/02/25 | 5 days | Mon 24/02/25 | Fri 28/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.19 | Yes
6 | 1.4.1.4.4.8 |  |  | SITAG |  | SIT Non-Functional Execution Model | 100% | Mon 20/01/25 | Tue 18/03/25 | 42 days | Mon 20/01/25 | Wed 12/02/25 | 0 days | 24 days | 42 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.4.8.1 |  |  | SITAG |  | Theme 1 | 100% | Mon 20/01/25 | Tue 18/02/25 | 22 days | Mon 20/01/25 | Wed 12/02/25 | 0 days | 4 days | 22 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.1.1 |  |  | SITAG |  | Develop execution model Theme 1 | 100% | Mon 20/01/25 | Wed 22/01/25 | 3 days | Mon 20/01/25 | Wed 22/01/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.1.2 |  |  | SITAG |  | SRO provide feedback | 100% | Thu 23/01/25 | Wed 29/01/25 | 5 days | Thu 23/01/25 | Wed 29/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.1.3 |  |  | SITAG |  | Address SRO feedback on execution model | 100% | Thu 30/01/25 | Fri 31/01/25 | 2 days | Thu 30/01/25 | Fri 31/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.1.4 |  |  | SITAG |  | Finalise execution model | 100% | Mon 03/02/25 | Wed 05/02/25 | 3 days | Mon 03/02/25 | Wed 05/02/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.1.5 |  |  | SITAG |  | NFTWG paper day | 100% | Tue 11/02/25 | Tue 11/02/25 | 0 days | Wed 05/02/25 | Wed 05/02/25 | 5 days | 4 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.8.1.6 |  |  | SITAG |  | NFTWG update on execution model | 100% | Tue 18/02/25 | Tue 18/02/25 | 0 days | Tue 18/02/25 | Tue 18/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.4.8.2 |  |  | SITAG |  | Theme 2 & 3 | 100% | Mon 20/01/25 | Tue 18/03/25 | 42 days | Mon 20/01/25 | Wed 12/02/25 | 0 days | 24 days | 42 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.2.1 |  |  | SITAG |  | Develop execution model Theme 2 & 3 | 100% | Mon 20/01/25 | Wed 22/01/25 | 3 days | Mon 20/01/25 | Wed 22/01/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.2.2 |  |  | SITAG |  | SRO provide feedback | 100% | Thu 23/01/25 | Wed 29/01/25 | 5 days | Thu 23/01/25 | Wed 29/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.2.3 |  |  | SITAG |  | Address SRO feedback on execution model | 100% | Thu 30/01/25 | Fri 31/01/25 | 2 days | Thu 30/01/25 | Fri 31/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.2.4 |  |  | SITAG |  | Finalise execution model | 100% | Mon 03/02/25 | Wed 05/02/25 | 3 days | Mon 03/02/25 | Wed 05/02/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.8.2.5 |  |  | SITAG |  | NFTWG paper day | 100% | Tue 11/03/25 | Tue 11/03/25 | 0 days | Tue 11/03/25 | Tue 11/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.8.2.6 |  |  | SITAG |  | NFTWG update on execution model | 100% | Tue 18/03/25 | Tue 18/03/25 | 0 days | Tue 18/03/25 | Tue 18/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.4.9 |  |  | SITAG |  | SIT Non-Functional Progress reporting | 100% | Thu 23/01/25 | Fri 21/02/25 | 22 days | Mon 30/12/24 | Fri 24/01/25 | 18 days | 20 days | 22 days | SI Test |  | 6.14 | Yes
7 | 1.4.1.4.4.9.1 |  |  | SITAG |  | Determine reporting methodology | 100% | Thu 23/01/25 | Fri 24/01/25 | 2 days | Thu 23/01/25 | Fri 24/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.14 | Yes
7 | 1.4.1.4.4.9.2 | T2 |  | SITAG |  | Implement reporting | 100% | Mon 27/01/25 | Fri 21/02/25 | 20 days | Mon 27/01/25 | Fri 14/02/25 | 0 days | 5 days | 20 days | SI Test |  | 6.14 | Yes
6 | 1.4.1.4.4.10 |  |  | SITAG |  | SIT Non-Functional Test Readiness Report | 100% | Tue 21/01/25 | Fri 28/03/25 | 48 days | Tue 25/06/24 | Fri 07/03/25 | 150 days | 14 days | 4 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.10.1 |  |  | SITAG |  | SIT Non-Functional Theme 1 Overarching Test Readiness Report | 100% | Tue 21/01/25 | Fri 28/02/25 | 29 days | Tue 25/06/24 | Fri 10/01/25 | 150 days | 35 days | -11 days | N/A |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.1 |  |  | SITAG |  | Develop Overarching SIT Non-Functional Theme 1 Overarching Test Readiness Report | 100% | Tue 21/01/25 | Tue 04/02/25 | 11 days | Tue 21/01/25 | Tue 04/02/25 | 0 days | 0 days | -9 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.2 |  |  | SITAG |  | SRO review | 100% | Wed 05/02/25 | Tue 11/02/25 | 5 days | Wed 05/02/25 | Tue 11/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.3 |  |  | SITAG |  | NFTWG paper day | 100% | Tue 11/02/25 | Tue 11/02/25 | 0 days | Tue 11/02/25 | Tue 11/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.4 |  |  | SITAG |  | NFTWG review the Non-Functional Theme 1 Overarching Test Readiness Report | 100% | Tue 18/02/25 | Tue 18/02/25 | 0 days | Tue 18/02/25 | Tue 18/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.5 |  |  | SITAG |  | Update Non-Functional Theme 1 Overarching Test Readiness Report following SRO / NFTWG feedback | 100% | Wed 19/02/25 | Wed 26/02/25 | 6 days | Wed 19/02/25 | Wed 26/02/25 | 0 days | 0 days | 6 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.6 |  |  |  |  | FTIG Recommendation | 100% | Fri 21/02/25 | Fri 21/02/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.7 |  |  | SITAG |  | eSITAG paper day | 100% | Wed 26/02/25 | Wed 26/02/25 | 0 days | Wed 26/02/25 | Wed 26/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.1.8 | T3 | T3-TE-0190 | SITAG |  | eSITAG approve Non-Functional Theme 1 Overarching Test Readiness Report | 100% | Fri 28/02/25 | Fri 28/02/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.4.10.2 |  |  | SITAG |  | SIT Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 100% | Tue 18/02/25 | Fri 28/03/25 | 28 days | Tue 18/02/25 | Fri 28/03/25 | 0 days | -1 day | 28 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.1 |  |  | SITAG |  | Develop Overarching SIT Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 100% | Tue 18/02/25 | Tue 04/03/25 | 11 days | Tue 18/02/25 | Tue 04/03/25 | 0 days | 0 days | 11 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.2 |  |  | SITAG |  | SRO review | 100% | Wed 05/03/25 | Tue 11/03/25 | 5 days | Wed 05/03/25 | Tue 11/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.3 |  |  | SITAG |  | NFTWG paper day | 100% | Tue 11/03/25 | Tue 11/03/25 | 0 days | Tue 11/03/25 | Tue 11/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.4 |  |  | SITAG |  | NFTWG review the Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 100% | Tue 18/03/25 | Tue 18/03/25 | 0 days | Tue 18/03/25 | Tue 18/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.5 |  |  | SITAG |  | Update Non-Functional Overarching Test Readiness Report Theme 2 & 3 following SRO / NFTWG feedback | 100% | Wed 19/03/25 | Wed 26/03/25 | 6 days | Wed 19/03/25 | Wed 26/03/25 | 0 days | 0 days | 6 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.6 |  |  |  |  | GLIG Recommendation | 100% | Fri 21/03/25 | Fri 21/03/25 | 0 days | Fri 21/03/25 | Fri 21/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.7 |  |  | SITAG |  | eSITAG paper day | 100% | Wed 26/03/25 | Wed 26/03/25 | 0 days | Wed 26/03/25 | Wed 26/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.4.10.2.8 | T3 | T3-TE-0191 | SITAG |  | eSITAG approve Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 100% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 0 days | -1 day | 0 days | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.4.11 | T2 | T2-TE-0700 | SITAG |  | SIT Non-Functional Testing Preparation Complete Theme 1 | 100% | Fri 28/02/25 | Fri 28/02/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.4.12 | T2 | T2-TE-1100 | SITAG |  | SIT Non-Functional Testing Preparation Complete Theme 2 & 3 | 100% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
5 | 1.4.1.4.5 |  |  | SITAG |  | SIT Operational Preparation | 100% | Mon 31/10/22 | Fri 23/05/25 | 670 days? | Thu 01/02/24 | Fri 31/01/25 | -328 days | 80 days | 387 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.5.1 |  |  | SITAG |  | Test Approach & Plan | 100% | Thu 01/02/24 | Wed 15/05/24 | 75 days | Thu 01/02/24 | Wed 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.1.1 |  |  | SITAG |  | Develop document with SITWG | 100% | Thu 01/02/24 | Wed 06/03/24 | 25 days | Thu 01/02/24 | Wed 06/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.2 |  |  | SITAG |  | Draft document review with Code Bodies | 100% | Thu 21/03/24 | Tue 26/03/24 | 4 days | Thu 21/03/24 | Tue 26/03/24 | 0 days | 0 days | -6 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.3 |  |  | SITAG |  | Industry Consultation | 100% | Wed 27/03/24 | Tue 09/04/24 | 10 days | Wed 27/03/24 | Tue 09/04/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.5.1.4 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | Wed 10/04/24 | Wed 15/05/24 | 26 days | Wed 10/04/24 | Wed 15/05/24 | 0 days | 0 days | -4 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.5 | T3 | T3-TE-0029 | SITAG | MHHS-ART073 | SIT Operational Testing Test Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.24 | Yes
6 | 1.4.1.4.5.2 |  |  | SITAG |  | Test Data Approach & Plan | 100% | Wed 27/03/24 | Wed 15/05/24 | 36 days | Wed 27/03/24 | Wed 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.2.1 |  |  | SITAG |  | Industry Consultation | 100% | Wed 27/03/24 | Tue 09/04/24 | 10 days | Wed 27/03/24 | Tue 09/04/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.5.2.2 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | Wed 10/04/24 | Wed 15/05/24 | 26 days | Wed 10/04/24 | Wed 15/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.2.3 |  |  | SITAG |  | SIT Operational Testing Test Data Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.5.3 |  |  | SITAG |  | Theme 1 & 2 Test Cases Approved | 100% | Wed 10/04/24 | Fri 06/09/24 | 108 days | Wed 10/04/24 | Fri 31/01/25 | 0 days | -105 days | -8 days | N/A |  | 6.18 | Yes
7 | 1.4.1.4.5.3.1 |  |  | SITAG |  | Theme 1 | 100% | Wed 10/04/24 | Fri 06/09/24 | 108 days | Wed 10/04/24 | Fri 06/09/24 | 0 days | 0 days | 12 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.1.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Wed 10/04/24 | Fri 21/06/24 | 53 days | Wed 10/04/24 | Fri 21/06/24 | 0 days | 0 days | 37 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.3.1.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Mon 24/06/24 | Mon 24/06/24 | 1 day | Mon 24/06/24 | Mon 24/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.1.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Tue 02/07/24 | Tue 09/07/24 | 6 days | Tue 02/07/24 | Tue 09/07/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.1.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | Mon 19/08/24 | Fri 23/08/24 | 5 days | Mon 19/08/24 | Fri 23/08/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.1.5 | T3 | T3-TE-0117 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 1 | 100% | Fri 06/09/24 | Fri 06/09/24 | 0 days | Fri 06/09/24 | Fri 06/09/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.1.4.5.3.2 |  |  | SITAG |  | Theme 2 | 100% | Wed 10/04/24 | Fri 06/09/24 | 107 days | Wed 10/04/24 | Fri 06/09/24 | 0 days | -1 day | 36 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | Wed 10/04/24 | Fri 21/06/24 | 53 days | Wed 10/04/24 | Fri 21/06/24 | 0 days | 0 days | 22 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.3.2.2 |  |  | SITAG |  | Industry Review Workshop | 100% | Mon 24/06/24 | Mon 24/06/24 | 1 day | Mon 24/06/24 | Mon 24/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.2.3 |  |  | SITAG |  | Industry Consultation Review | 100% | Tue 02/07/24 | Tue 09/07/24 | 6 days | Tue 02/07/24 | Tue 09/07/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.2.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | Mon 19/08/24 | Fri 23/08/24 | 5 days | Mon 19/08/24 | Fri 23/08/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.2.5 | T3 | T3-TE-0118 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 2 | 100% | Fri 06/09/24 | Fri 06/09/24 | 0 days | Fri 06/09/24 | Fri 06/09/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
6 | 1.4.1.4.5.4 |  |  | SITAG |  | Environments (SIT B) | 100% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 0 days | -1 day | 0 days | N/A |  | 5.31 | Yes
7 | 1.4.1.4.5.4.1 |  |  | SITAG |  | PP Environments (SIT B) | 100% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 0 days | -1 day | 0 days | N/A |  | 5.31 | Yes
8 | 1.4.1.4.5.4.1.1 |  |  | SITAG |  | Deployment of MHHS solution code to SIT B environments | 100% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 0 days | -1 day | 0 days | PP |  | 5.31 | Yes
7 | 1.4.1.4.5.4.2 |  |  | SITAG |  | SI Environments (SIT B) | 100% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 0 days | -1 day | 0 days | N/A |  | 5.31 | Yes
8 | 1.4.1.4.5.4.2.1 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 0 days | -1 day | 0 days | SI Test |  | 5.31 | Yes
6 | 1.4.1.4.5.5 |  |  |  |  | SIT Operations Manual | 100% | Mon 31/10/22 | Fri 31/01/25 | 590 days? | Mon 31/10/22 | Fri 31/01/25 | 0 days | 0 days | 590 days? | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.1 |  |  |  |  | Version 1 SIT Operations Manual | 100% | Mon 07/10/24 | Fri 22/11/24 | 35 days | Mon 07/10/24 | Fri 22/11/24 | 0 days | 0 days | 35 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.1 |  |  |  |  | Creation of SIT Operations Manual Template | 100% | Mon 07/10/24 | Wed 16/10/24 | 8 days | Mon 07/10/24 | Wed 16/10/24 | 0 days | 0 days | 8 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.2 |  |  |  |  | November TORWG Paper Day | 100% | Thu 07/11/24 | Thu 07/11/24 | 0 days | Thu 07/11/24 | Thu 07/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.3 |  |  |  |  | November TORWG (Timeline and Next Steps for SIT Operations Manual) | 100% | Thu 14/11/24 | Thu 14/11/24 | 0 days | Thu 14/11/24 | Thu 14/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.4 |  |  |  |  | SIT Operations Manual Version 1 Shared with MHHSP | 100% | Mon 11/11/24 | Mon 11/11/24 | 0 days | Mon 11/11/24 | Mon 11/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.5 |  |  |  |  | MHHSP provide feedback on SIT Operations Manual Version 1 | 100% | Tue 12/11/24 | Fri 22/11/24 | 9 days | Tue 12/11/24 | Fri 22/11/24 | 0 days | 0 days | 9 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.6 |  |  |  |  | SIT Operations Manual Version 1 Shared with Programme Participants | 100% | Wed 13/11/24 | Wed 13/11/24 | 0 days | Wed 13/11/24 | Wed 13/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.7 |  |  |  |  | PPs provide feedback on SIT Operations Manual Version 1 | 100% | Thu 14/11/24 | Fri 22/11/24 | 7 days | Thu 14/11/24 | Fri 22/11/24 | 0 days | 0 days | 7 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.1.8 |  |  |  |  | Programme Participants and MHHSP Feedback and Actions Received (SIT Ops Manual Version 1) | 100% | Fri 22/11/24 | Fri 22/11/24 | 0 days | Fri 22/11/24 | Fri 22/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.2 |  |  |  |  | Version 2 SIT Operations Manual | 100% | Tue 12/11/24 | Wed 18/12/24 | 27 days | Tue 12/11/24 | Wed 18/12/24 | 0 days | 0 days | 27 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.1 |  |  |  |  | Version 2 SIT Operations Manual (Composition) | 100% | Tue 12/11/24 | Wed 27/11/24 | 12 days | Tue 12/11/24 | Wed 27/11/24 | 0 days | 0 days | 12 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.2 | T3 | T3-TE-0132 | MCAG |  | Version 2 SIT Operations Manual Completed | 100% | Wed 27/11/24 | Wed 27/11/24 | 0 days | Wed 27/11/24 | Wed 27/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.3 |  |  |  |  | Version 2 SIT Operations Manual Shared with MHHSP & PPs for TORWG (Consultation Starts) | 100% | Wed 27/11/24 | Wed 27/11/24 | 0 days | Wed 27/11/24 | Wed 27/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.4 |  |  |  |  | Version 2 SIT Ops Manual - PP Consultation (Iterative Feedback Process) | 100% | Thu 28/11/24 | Wed 11/12/24 | 10 days | Thu 28/11/24 | Wed 11/12/24 | 0 days | 0 days | 10 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.5 |  |  |  |  | Version 2 SIT Ops Manual - PP Consultation Completed | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.6 |  |  |  |  | December TORWG Paper Day | 100% | Wed 04/12/24 | Wed 04/12/24 | 0 days | Wed 04/12/24 | Wed 04/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.7 |  |  |  |  | December TORWG (Initial Feedback, Common Themes and Comments) | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.8 |  |  |  |  | December Extraordinary TORWG Paper Day | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.2.9 |  |  |  |  | Publication of key themes from consultation to eTORWG | 100% | Thu 12/12/24 | Fri 13/12/24 | 2 days | Thu 12/12/24 | Fri 13/12/24 | 0 days | 0 days | 2 days | Helix |  | 6.14 | Yes
8 | 1.4.1.4.5.5.2.10 |  |  |  |  | December Extraordinary TORWG (Summary of Version 2 Feedback and Response Approach Shared with PPs) | 100% | Wed 18/12/24 | Wed 18/12/24 | 0 days | Wed 18/12/24 | Wed 18/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.3 |  |  |  |  | Version 3 (Final) SIT Operations Manual | 100% | Thu 28/11/24 | Tue 28/01/25 | 44 days | Thu 28/11/24 | Tue 28/01/25 | 0 days | 0 days | 44 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.1 |  |  |  |  | Update SIT Operations Manual (Final) Version 3 (with Comments Received From Version 2) [Pre-Christmas Furlough] | 100% | Thu 28/11/24 | Fri 20/12/24 | 17 days | Thu 28/11/24 | Fri 20/12/24 | 0 days | 0 days | 17 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.2 |  |  |  |  | Update SIT Operations Manual (Final) Version 3 (with Comments Received From Version 2) [Post-Christmas Furlough] | 100% | Thu 02/01/25 | Wed 08/01/25 | 5 days | Thu 02/01/25 | Wed 08/01/25 | 0 days | 0 days | 5 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.3 | T3 | T3-TE-0133 | MCAG |  | SIT Operations Manual (Final) Version 3 Completed | 100% | Wed 08/01/25 | Wed 08/01/25 | 0 days | Wed 08/01/25 | Wed 08/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.4 |  |  |  |  | January TORWG Paper Day | 100% | Wed 08/01/25 | Wed 08/01/25 | 0 days | Wed 08/01/25 | Wed 08/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.5 |  |  |  |  | January TORWG (SIT Operations Manual Agreement) [Assurance Meeting] | 100% | Wed 15/01/25 | Wed 15/01/25 | 0 days | Wed 15/01/25 | Wed 15/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.6 |  |  |  |  | January MCAG Paper Day (Final SIT Operations Manual Submitted) | 100% | Tue 21/01/25 | Tue 21/01/25 | 0 days | Tue 21/01/25 | Tue 21/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.3.7 | T3 | T3-TE-0135 | MCAG |  | January MCAG (Final SIT Operations Manual Endorsement) [Advisory Group Sign-off] | 100% | Tue 28/01/25 | Tue 28/01/25 | 0 days | Tue 28/01/25 | Tue 28/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.4 |  |  |  |  | Elexon / Helix Service Now Test Prep | 100% | Thu 01/08/24 | Tue 14/01/25 | 119 days? | Mon 15/07/24 | Fri 31/01/25 | 13 days | -13 days | 119 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.1 |  |  |  |  | Incident Management Build | 100% | Mon 05/08/24 | Fri 15/11/24 | 75 days? | Mon 05/08/24 | Fri 15/11/24 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.1.1 |  |  |  |  | Build | 100% | Mon 05/08/24 | Fri 27/09/24 | 40 days | Fri 27/09/24 | Fri 27/09/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.1.2 |  |  |  |  | Test | 100% | Mon 30/09/24 | Fri 18/10/24 | 15 days | Fri 18/10/24 | Fri 18/10/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.1.3 |  |  |  |  | Deploy | 100% | Mon 21/10/24 | Fri 15/11/24 | 20 days | Fri 15/11/24 | Fri 15/11/24 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.1.4 |  |  |  |  | Incident Management Build & Configuration Complete | 100% | Fri 15/11/24 | Fri 15/11/24 | 0 days | Fri 15/11/24 | Fri 15/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.2 |  |  |  |  | Major Incident Management Build & Configuration | 100% | Fri 15/11/24 | Fri 15/11/24 | 0 days? | Wed 02/10/24 | Tue 14/01/25 | 32 days | -43 days | 0 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.2.1 |  |  |  |  | Build | 100% | Wed 02/10/24 | Tue 26/11/24 | 40 days | Tue 26/11/24 | Tue 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.2.2 |  |  |  |  | Test | 100% | Wed 27/11/24 | Tue 17/12/24 | 15 days | Tue 17/12/24 | Tue 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.2.3 |  |  |  |  | Deploy | 100% | Wed 18/12/24 | Tue 14/01/25 | 20 days | Tue 14/01/25 | Tue 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.2.4 |  |  |  |  | Major Incident Management Build & Configuration Complete | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.3 |  |  |  |  | Knowledge Management Build & Configuration | 100% | Wed 02/10/24 | Tue 14/01/25 | 75 days? | Wed 02/10/24 | Tue 14/01/25 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.3.1 |  |  |  |  | Build | 100% | Wed 02/10/24 | Tue 26/11/24 | 40 days | Tue 26/11/24 | Tue 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.3.2 |  |  |  |  | Test | 100% | Wed 27/11/24 | Tue 17/12/24 | 15 days | Tue 17/12/24 | Tue 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.3.3 |  |  |  |  | Deploy | 100% | Wed 18/12/24 | Tue 14/01/25 | 20 days | Tue 14/01/25 | Tue 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.3.4 |  |  |  |  | Knowledge Management Build & Configuration Complete | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.4 |  |  |  |  | Problem Management Build & Configuration | 100% | Thu 01/08/24 | Thu 01/08/24 | 1 day? | Wed 02/10/24 | Tue 14/01/25 | -44 days | -118 days | 1 day? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.4.1 |  |  |  |  | Build | 100% | Wed 02/10/24 | Tue 26/11/24 | 40 days | Tue 26/11/24 | Tue 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.4.2 |  |  |  |  | Test | 100% | Wed 27/11/24 | Tue 17/12/24 | 15 days | Tue 17/12/24 | Tue 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.4.3 |  |  |  |  | Deploy | 100% | Wed 18/12/24 | Tue 14/01/25 | 20 days | Tue 14/01/25 | Tue 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.4.4 |  |  |  |  | Problem Management Build & Configuration Complete | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.5 |  |  |  |  | Change Management Build & Configuration | 100% | Wed 02/10/24 | Tue 14/01/25 | 75 days? | Wed 02/10/24 | Tue 14/01/25 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.5.1 |  |  |  |  | Build | 100% | Wed 02/10/24 | Tue 26/11/24 | 40 days | Tue 26/11/24 | Tue 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.5.2 |  |  |  |  | Test | 100% | Wed 27/11/24 | Tue 17/12/24 | 15 days | Tue 17/12/24 | Tue 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.5.3 |  |  |  |  | Deploy | 100% | Wed 18/12/24 | Tue 14/01/25 | 20 days | Tue 14/01/25 | Tue 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.5.4 |  |  |  |  | Change Management Build & Configuration Complete | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.6 |  |  |  |  | Service Catalogue Management Build & Configuration | 100% | Wed 02/10/24 | Tue 14/01/25 | 75 days? | Wed 02/10/24 | Tue 14/01/25 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.6.1 |  |  |  |  | Build | 100% | Wed 02/10/24 | Tue 26/11/24 | 40 days | Tue 26/11/24 | Tue 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.6.2 |  |  |  |  | Test | 100% | Wed 27/11/24 | Tue 17/12/24 | 15 days | Tue 17/12/24 | Tue 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.6.3 |  |  |  |  | Deploy | 100% | Wed 18/12/24 | Tue 14/01/25 | 20 days | Tue 14/01/25 | Tue 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.4.6.4 |  |  |  |  | Service Catalogue Management Build & Configuration Complete | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.7 | T3 | T3-TE-0136 | SITAG |  | ServiceNow SIT Ops Available | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days? | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.4.8 |  |  |  |  | Helix Service Management Documentation (Service Design Pack) | 100% | Thu 01/08/24 | Wed 08/01/25 | 115 days | Mon 09/09/24 | Fri 31/01/25 | -27 days | -17 days | 115 days | Helix |  | 6 | Yes
9 | 1.4.1.4.5.5.4.8.1 |  |  |  |  | Document Drafting | 100% | Thu 01/08/24 | Wed 11/12/24 | 95 days | Thu 01/08/24 | Wed 11/12/24 | 0 days | 0 days | 95 days | Helix |  | 6.11 | Yes
9 | 1.4.1.4.5.5.4.8.2 |  |  |  |  | Internal Elexon Review | 100% | Mon 06/01/25 | Wed 08/01/25 | 3 days | Thu 12/12/24 | Mon 16/12/24 | 17 days | 17 days | 3 days | Helix |  | 6.11 | Yes
9 | 1.4.1.4.5.5.4.8.3 |  |  |  |  | Elexon Service Panel Sign off | 100% | Wed 08/01/25 | Wed 08/01/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 13 days | 12 days | 0 days | Helix |  | 6.11 | Yes
7 | 1.4.1.4.5.5.5 |  |  |  |  | Incident Management Support | 100% | Mon 31/10/22 | Mon 31/10/22 | 1 day? | Mon 31/10/22 | Mon 31/10/22 | 0 days | 0 days | 1 day? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.5.1 |  |  |  |  | Identify Relevant Stakeholders to Support Incident Management Process | 100% | Mon 02/12/24 | Fri 13/12/24 | 10 days | Mon 18/11/24 | Fri 29/11/24 | 10 days | 10 days | 10 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.5.2 |  |  |  |  | Schedule Time to Upskill Stakeholders | 100% | Mon 16/12/24 | Fri 20/12/24 | 5 days | Mon 02/12/24 | Fri 06/12/24 | 10 days | 10 days | 5 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.5.3 |  |  |  |  | Helix Stakeholders Attendance at MHHS Defect Triage Meetings [Meeting Dates to be Confirmed] | 100% | Mon 06/01/25 | Fri 17/01/25 | 10 days | Mon 09/12/24 | Fri 20/12/24 | 20 days | 20 days | 10 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.6 |  |  |  |  | SIT Service Readiness (Elexon & Helix) Completed | 100% | Fri 17/01/25 | Fri 17/01/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 21 days | 20 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.7 |  |  |  |  | SIT Service Readiness (External Parties) | 100% | Mon 07/10/24 | Fri 31/01/25 | 85 days | Mon 30/09/24 | Mon 06/01/25 | 5 days | 19 days | 85 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.7.1 |  |  |  |  | Helix Engagement & Comms | 100% | Mon 07/10/24 | Mon 13/01/25 | 71 days | Mon 30/09/24 | Mon 06/01/25 | 5 days | 5 days | 71 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.7.1.1 |  |  |  |  | Engagement Execution | 100% | Mon 07/10/24 | Mon 13/01/25 | 71 days | Mon 07/10/24 | Mon 06/01/25 | 0 days | 5 days | 71 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.7.1.2 |  |  |  |  | Information Gathering | 100% | Fri 29/11/24 | Mon 13/01/25 | 32 days | Thu 31/10/24 | Wed 27/11/24 | 21 days | 33 days | 32 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.7.1.3 |  |  |  |  | SIT Participants Preparation | 100% | Thu 28/11/24 | Tue 10/12/24 | 9 days | Fri 22/11/24 | Mon 06/01/25 | 4 days | -19 days | 9 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.7.2 |  |  |  |  | SIT Service Readiness (External Parties) Completed | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Mon 06/01/25 | Mon 06/01/25 | 20 days | 19 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.8 |  |  |  |  | ServiceNow Support Portal Onboarding (Helix Suppliers & SIT Participants) | 100% | Wed 02/10/24 | Fri 17/01/25 | 78 days? | Wed 02/10/24 | Fri 17/01/25 | 0 days | 0 days | 78 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.8.1 |  |  |  |  | ServiceNow Portal Preparation and Planning | 100% | Wed 02/10/24 | Tue 26/11/24 | 40 days? | Wed 02/10/24 | Tue 26/11/24 | 0 days | 0 days | 40 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.1.1 |  |  |  |  | Define Supplier Requirements | 100% | Wed 02/10/24 | Tue 12/11/24 | 30 days? | Wed 02/10/24 | Tue 12/11/24 | 0 days | 0 days | 30 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.1.2 |  |  |  |  | Determine Supplier ServiceNow modules | 100% | Wed 13/11/24 | Tue 26/11/24 | 10 days? | Wed 13/11/24 | Tue 26/11/24 | 0 days | 0 days | 10 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.1.3 |  |  |  |  | Review compliance requirements, including data privacy and access limitations. | 100% | Wed 13/11/24 | Tue 26/11/24 | 10 days? | Wed 13/11/24 | Tue 26/11/24 | 0 days | 0 days | 10 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.1.4 |  |  |  |  | Conduct a security assessment to ensure the supplier complies with organisational policies. | 100% | Wed 13/11/24 | Tue 26/11/24 | 10 days? | Wed 13/11/24 | Tue 26/11/24 | 0 days | 0 days | 10 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.8.2 |  |  |  |  | ServiceNow Portal System Configuration | 100% | Wed 27/11/24 | Fri 31/01/25 | 48 days? | Wed 27/11/24 | Tue 07/01/25 | 0 days | 18 days | 48 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.2.1 |  |  |  |  | Create Supplier User Accounts | 100% | Wed 27/11/24 | Fri 31/01/25 | 48 days | Wed 27/11/24 | Tue 10/12/24 | 0 days | 38 days | 48 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.2.2 |  |  |  |  | Assign appropriate access based on the supplier’s needs and security requirements (e.g., read-only access, submit requests, etc.). | 100% | Mon 30/12/24 | Fri 31/01/25 | 25 days? | Wed 11/12/24 | Tue 24/12/24 | 13 days | 28 days | 25 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.2.3 |  |  |  |  | Configure Access Controls | 100% | Mon 30/12/24 | Fri 31/01/25 | 25 days? | Wed 25/12/24 | Tue 07/01/25 | 3 days | 18 days | 25 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.8.3 |  |  |  |  | ServiceNow Portal Training and Documentation | 100% | Mon 06/01/25 | Fri 31/01/25 | 20 days? | Mon 06/01/25 | Fri 10/01/25 | 0 days | 15 days | 20 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.3.1 |  |  |  |  | Provide Training to the Supplier | 100% | Fri 31/01/25 | Fri 31/01/25 | 1 day | Mon 06/01/25 | Fri 10/01/25 | 19 days | 15 days | 1 day | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.3.2 |  |  |  |  | Create Supplier Training Documentation | 100% | Mon 06/01/25 | Fri 31/01/25 | 20 days | Mon 06/01/25 | Fri 10/01/25 | 0 days | 15 days | 20 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.8.4 |  |  |  |  | ServiceNow Portal Testing and Validation | 100% | Wed 08/01/25 | Fri 31/01/25 | 18 days | Wed 08/01/25 | Fri 17/01/25 | 0 days | 10 days | 18 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.4.1 |  |  |  |  | Conduct User Acceptance Testing (UAT) | 100% | Fri 31/01/25 | Fri 31/01/25 | 1 day | Mon 13/01/25 | Fri 17/01/25 | 14 days | 10 days | 1 day | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.5.8.4.2 |  |  |  |  | Validate Access and Security Controls | 100% | Tue 28/01/25 | Fri 31/01/25 | 4 days | Mon 13/01/25 | Fri 17/01/25 | 11 days | 10 days | 4 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.5.8.5 |  |  |  |  | ServiceNow Support Portal Onboarding (Helix Suppliers& SIT Participants) Completed | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 11 days | 10 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.5.9 | T3 | T3-TE-0137 | SITAG |  | Stage 1 - Helix SIT Operational Readiness Completed | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
6 | 1.4.1.4.5.6 |  |  |  |  | Theme 3 Test Cases Approved | 100% | Wed 10/04/24 | Wed 19/03/25 | 246 days? | NA | NA | 0 days | 0 days | 246 days? |  |  | 6.18 | Yes
7 | 1.4.1.4.5.6.1 |  |  | SITAG |  | Theme 3 (Batch 2) | 100% | Thu 19/09/24 | Wed 18/12/24 | 64 days | Thu 19/09/24 | Wed 11/12/24 | 0 days | 4 days | -52 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.6.1.1 |  |  | SITAG |  | Conclude BCDR Scope with SRO, Code Bodies and DIP Manager | 100% | Thu 19/09/24 | Fri 18/10/24 | 22 days | Thu 19/09/24 | Fri 18/10/24 | 0 days | 0 days | 22 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.1.2 |  |  | SITAG |  | Develop BDCR Test Scenarios & Test Cases (Batch 2) | 100% | Mon 14/10/24 | Fri 25/10/24 | 10 days | Mon 14/10/24 | Fri 25/10/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.1.3 |  |  | SITAG |  | Develop DIP Test Scenarios and Test Cases (Batch 2) | 100% | Thu 19/09/24 | Fri 25/10/24 | 27 days | Thu 19/09/24 | Fri 25/10/24 | 0 days | 0 days | 27 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.1.4 |  |  | SITAG |  | SRO Review | 100% | Mon 28/10/24 | Fri 01/11/24 | 5 days | Mon 28/10/24 | Fri 01/11/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.1.5 |  |  | SITAG |  | Industry Consultation (Batch 2) | 100% | Mon 11/11/24 | Fri 22/11/24 | 10 days | Mon 11/11/24 | Fri 22/11/24 | 0 days | 0 days | 9 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.6.1.6 |  |  | SITAG |  | Review Feedback and Update | 100% | Mon 25/11/24 | Thu 28/11/24 | 4 days | Mon 25/11/24 | Fri 29/11/24 | 0 days | -1 day | 4 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.1.7 |  |  | SITAG |  | SITWG paper day | 100% | Thu 28/11/24 | Thu 28/11/24 | 0 days | Thu 28/11/24 | Thu 28/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.1.8 |  |  | SITAG |  | Review with SIT WG (Batch 2) | 100% | Fri 29/11/24 | Thu 05/12/24 | 5 days | Fri 29/11/24 | Thu 05/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.1.9 |  |  | SITAG |  | SITWG endorse Theme 3 (Batch 2) | 100% | Thu 05/12/24 | Thu 05/12/24 | 0 days | Thu 05/12/24 | Thu 05/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.1.10 |  |  | SITAG |  | SITAG paper day | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.1.11 | T3 | T3-TE-0138 | SITAG |  | SITAG approve Theme 3 (Batch 2) | 100% | Wed 18/12/24 | Wed 18/12/24 | 0 days | Wed 18/12/24 | Wed 18/12/24 | 0 days | -1 day | 0 days | SI Test |  | 6.13 | Yes
7 | 1.4.1.4.5.6.2 |  |  | SITAG |  | Theme 3 (Batch 1) | 100% | Wed 10/04/24 | Wed 18/12/24 | 181 days? | Wed 10/04/24 | Wed 11/12/24 | 0 days | 5 days | 181 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases (Batch 1) | 100% | Wed 10/04/24 | Fri 26/07/24 | 78 days | Wed 10/04/24 | Fri 26/07/24 | 0 days | 0 days | 32 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.2 |  |  | SITAG |  | Conclude Industry Consultation (Batch 1) | 100% | Thu 05/09/24 | Thu 19/09/24 | 11 days | Thu 05/09/24 | Thu 19/09/24 | 0 days | 0 days | 11 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.3 |  |  | SITAG |  | Review Feedback and Update | 100% | Fri 20/09/24 | Thu 26/09/24 | 5 days | Fri 20/09/24 | Thu 26/09/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.4 |  |  | SITAG |  | Draft Test Cases from Feedback and LLSD | 100% | Mon 30/09/24 | Fri 18/10/24 | 15 days? | Mon 30/09/24 | Fri 18/10/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.5 |  |  | SITAG |  | SRO Review | 100% | Mon 21/10/24 | Fri 25/10/24 | 5 days? | Mon 21/10/24 | Fri 25/10/24 | 0 days | 0 days | 5 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.6 |  |  | SITAG |  | Industry Consultation | 100% | Mon 28/10/24 | Fri 08/11/24 | 10 days? | Mon 28/10/24 | Fri 08/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.7 |  |  | SITAG |  | Review Feedback and Update | 100% | Mon 11/11/24 | Fri 22/11/24 | 10 days | Mon 11/11/24 | Fri 15/11/24 | 0 days | 5 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.6.2.8 |  |  | SITAG |  | SITWG paper day | 100% | Thu 28/11/24 | Thu 28/11/24 | 0 days | Thu 28/11/24 | Thu 28/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.2.9 |  |  | SITAG |  | Review with SITWG (Batch 1) | 100% | Fri 29/11/24 | Thu 05/12/24 | 5 days | Fri 29/11/24 | Thu 05/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.2.10 |  |  | SITAG |  | SITWG endorse Theme 3 (Batch 1) | 100% | Thu 05/12/24 | Thu 05/12/24 | 0 days | Thu 05/12/24 | Thu 05/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.2.11 |  |  | SITAG |  | SITAG paper day | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.2.12 | T3 | T3-TE-0139 | SITAG |  | SITAG approve Theme 3 (Batch 1) | 100% | Wed 18/12/24 | Wed 18/12/24 | 0 days | Wed 18/12/24 | Wed 18/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.6.2.13 | T3 | T3-TE-0119 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 3 (Batch 1 + 2) | 100% | Wed 18/12/24 | Wed 18/12/24 | 0 days | Wed 18/12/24 | Wed 18/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
7 | 1.4.1.4.5.6.3 |  |  | SITAG |  | Theme 3 (Batch 2) Supplementary | 100% | Mon 03/02/25 | Wed 19/03/25 | 33 days | Mon 03/02/25 | Wed 19/03/25 | 0 days | 0 days | 33 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.1 |  |  | SITAG |  | Conclude DIP Onboarding / Offboarding Scope with DIP Manager | 100% | Mon 03/02/25 | Fri 07/02/25 | 5 days | Mon 03/02/25 | Fri 07/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.2 |  |  | SITAG |  | Develop DIP Onboarding / Offboarding Test Scenarios & Test Cases (Batch 2) Supplementary | 100% | Mon 10/02/25 | Tue 11/02/25 | 2 days | Mon 10/02/25 | Tue 11/02/25 | 0 days | 0 days | 2 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.3 |  |  | SITAG |  | SRO Review | 100% | Wed 12/02/25 | Tue 18/02/25 | 5 days | Wed 12/02/25 | Tue 18/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.4 |  |  | SITAG |  | Industry Consultation (Batch 2) Supplementary | 100% | Wed 19/02/25 | Tue 04/03/25 | 10 days | Wed 19/02/25 | Tue 04/03/25 | 0 days | 0 days | 10 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.5 |  |  | SITAG |  | SITWG Paper Day | 100% | Thu 27/02/25 | Thu 27/02/25 | 0 days | Thu 27/02/25 | Thu 27/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.6 |  |  | SITAG |  | Review Feedback and Update | 100% | Wed 05/03/25 | Wed 05/03/25 | 1 day | Wed 05/03/25 | Wed 05/03/25 | 0 days | 0 days | 1 day | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.7 |  |  | SITAG |  | SITWG endorse Theme 3 (Batch 2) Supplementary | 100% | Thu 06/03/25 | Thu 06/03/25 | 0 days | Thu 06/03/25 | Thu 06/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.8 |  |  | SITAG |  | SITAG paper day | 100% | Wed 12/03/25 | Wed 12/03/25 | 0 days | Wed 12/03/25 | Wed 12/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.18 | Yes
8 | 1.4.1.4.5.6.3.9 |  |  | SITAG |  | SITAG approve Theme 3 (Batch 2) Supplementary | 100% | Wed 19/03/25 | Wed 19/03/25 | 0 days | Wed 19/03/25 | Wed 19/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.18 | Yes
6 | 1.4.1.4.5.7 |  |  | SITAG |  | Helix SDD and LLSD Development and Approval | 100% | Fri 27/09/24 | Mon 30/09/24 | 1 day | Fri 27/09/24 | Mon 30/09/24 | 0 days | -1 day | 1 day | SI Test |  | 6 | Yes
7 | 1.4.1.4.5.7.1 |  |  | SITAG |  | Development | 100% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
7 | 1.4.1.4.5.7.2 |  |  | SITAG |  | Approval | 100% | Mon 30/09/24 | Mon 30/09/24 | 0 days | Mon 30/09/24 | Mon 30/09/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
6 | 1.4.1.4.5.8 |  |  | SITAG |  | SIT Operational Programme RTTM (Theme 3 (Batch 1)) | 100% | Mon 09/12/24 | Fri 24/01/25 | 35 days | Thu 12/12/24 | Fri 17/01/25 | -3 days | 5 days | 35 days | SI Test |  | 6.12 | Yes
7 | 1.4.1.4.5.8.1 |  |  | SITAG |  | Develop SIT Operational Theme 3 (Batch 1) RTTM | 100% | Mon 09/12/24 | Fri 10/01/25 | 25 days | Thu 12/12/24 | Fri 10/01/25 | -3 days | 0 days | 25 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.5.8.2 |  |  | SITAG |  | SRO review of SIT Operational Theme 3 (Batch 1) RTTM | 100% | Mon 13/01/25 | Fri 17/01/25 | 5 days | Mon 13/01/25 | Fri 17/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.5.8.3 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO to review | 100% | Mon 20/01/25 | Fri 24/01/25 | 5 days | Mon 20/01/25 | Fri 24/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.5.8.4 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO acceptance of Theme 3 (Batch 1) Operational RTTM | 100% | Fri 24/01/25 | Fri 24/01/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.5.8.5 |  |  | SITAG |  | SIT Operational Theme 3 (Batch 1) RTTM Complete | 100% | Fri 24/01/25 | Fri 24/01/25 | 0 days | Fri 10/01/25 | Fri 10/01/25 | 11 days | 10 days | 0 days | SI Test |  | 6.12 | Yes
6 | 1.4.1.4.5.9 |  |  | SITAG |  | SIT Operational Programme RTTM (Theme 1, 2 & 3 (Batch 2)) | 100% | Mon 06/01/25 | Fri 23/05/25 | 100 days | Mon 06/01/25 | Fri 07/03/25 | 0 days | 55 days | 100 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.9.1 |  |  | SITAG |  | Develop SIT Operational (Theme 1, 2 & 3 (Batch 2)) RTTM | 100% | Mon 06/01/25 | Mon 24/02/25 | 36 days | Mon 06/01/25 | Fri 07/02/25 | 0 days | 11 days | 36 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.9.2 |  |  | SITAG |  | SRO review of SIT Operational (Theme 1, 2 & 3 (Batch 2)) RTTM | 100% | Tue 25/02/25 | Fri 07/03/25 | 9 days | Tue 25/02/25 | Fri 07/03/25 | 0 days | 0 days | 9 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.9.3 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO to review | 100% | Mon 10/03/25 | Thu 24/04/25 | 34 days | Mon 10/03/25 | Fri 21/03/25 | 0 days | 24 days | 34 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.9.4 |  |  | SITAG |  | Incorporate feedback | 100% | Mon 10/03/25 | Thu 24/04/25 | 34 days | Mon 10/03/25 | Fri 21/03/25 | 0 days | 24 days | 34 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.9.5 |  |  | SITAG |  | DIP Manager / Code Bodies / SRO acceptance of (Theme 1, 2 & 3 (Batch 2)) Operational RTTM | 100% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 25 days | 24 days | 0 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.9.6 |  |  | SITAG |  | SIT Operational (Theme 1, 2 & 3 (Batch 2)) RTTM Complete | 100% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 45 days | 44 days | 0 days | SI Test |  | 6.18 | Yes
6 | 1.4.1.4.5.10 |  |  | SITAG |  | SIT Operational Theme 3 (Batch 1) DITL | 100% | Mon 06/01/25 | Tue 28/01/25 | 17 days | Tue 08/10/24 | Thu 17/10/24 | 64 days | 73 days | 17 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.5.10.1 |  |  | SITAG |  | DITL + Familiarisation session development | 100% | Mon 06/01/25 | Wed 15/01/25 | 8 days | Mon 06/01/25 | Fri 17/01/25 | 0 days | -2 days | 8 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.5.10.2 |  |  | SITAG |  | SRO Review | 100% | Thu 16/01/25 | Wed 22/01/25 | 5 days | Mon 20/01/25 | Fri 24/01/25 | -2 days | -2 days | 5 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.5.10.3 |  |  | SITAG |  | Post-SRO Review Changes | 100% | Thu 23/01/25 | Fri 24/01/25 | 2 days | Thu 23/01/25 | Fri 24/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.5.10.4 |  |  | SITAG |  | Familiarisation session Service Management test case schedule + mapping | 100% | Fri 24/01/25 | Fri 24/01/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.16 | Yes
7 | 1.4.1.4.5.10.5 |  |  | SITAG |  | Publish Cycle 3 DITL / Cycle 3 DITL Online Sessions for SIT PPs | 100% | Tue 28/01/25 | Tue 28/01/25 | 0 days | Tue 28/01/25 | Tue 28/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.16 | Yes
6 | 1.4.1.4.5.11 |  |  | SITAG |  | SIT Operational Theme 1, 2 & 3 (Batch 2) DITL | 100% | Mon 24/02/25 | Wed 26/03/25 | 23 days | Mon 24/02/25 | Wed 26/03/25 | 0 days | 0 days | 23 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.11.1 |  |  | SITAG |  | DITL + Familiarisation session development | 100% | Mon 24/02/25 | Fri 14/03/25 | 15 days | Mon 24/02/25 | Fri 14/03/25 | 0 days | 0 days | 15 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.11.2 |  |  | SITAG |  | SRO Review | 100% | Mon 17/03/25 | Fri 21/03/25 | 5 days | Mon 17/03/25 | Fri 21/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.11.3 |  |  | SITAG |  | Post-SRO Review Changes | 100% | Mon 24/03/25 | Wed 26/03/25 | 3 days | Mon 24/03/25 | Wed 26/03/25 | 0 days | 0 days | 3 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.11.4 |  |  | SITAG |  | Familiarisation session Service Management test case schedule + mapping | 100% | Wed 26/03/25 | Wed 26/03/25 | 0 days | Wed 26/03/25 | Wed 26/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.18 | Yes
7 | 1.4.1.4.5.11.5 |  |  | SITAG |  | Publish Cycle 3 DITL / Cycle 3 DITL Online Sessions for SIT PPs | 100% | Wed 26/03/25 | Wed 26/03/25 | 0 days | Wed 26/03/25 | Wed 26/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.18 | Yes
6 | 1.4.1.4.5.12 |  |  | SITAG |  | SIT Operational Defect Management | 100% | Mon 06/01/25 | Fri 24/01/25 | 15 days? | Mon 06/01/25 | Fri 24/01/25 | 0 days | 0 days | 15 days? | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.5.12.1 |  |  | SITAG |  | Develop defect management approach | 100% | Mon 06/01/25 | Fri 17/01/25 | 10 days? | Mon 06/01/25 | Fri 17/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.5.12.2 |  |  | SITAG |  | Defect management approach agreed | 100% | Mon 20/01/25 | Fri 24/01/25 | 5 days? | Mon 20/01/25 | Fri 24/01/25 | 0 days | 0 days | 5 days? | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.5.13 |  |  | SITAG |  | SIT Operational Execution Model | 100% | Mon 05/08/24 | Wed 02/10/24 | 43 days? | Mon 05/08/24 | Wed 02/10/24 | 0 days | 0 days | 43 days? | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.5.13.1 |  |  | SITAG |  | Theme 3 (Batch 1) | 100% | Mon 05/08/24 | Tue 10/09/24 | 27 days | Mon 05/08/24 | Tue 10/09/24 | 0 days | 0 days | 27 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.1.1 |  |  | SITAG |  | Develop execution model Theme 3 (Batch 1) | 100% | Mon 16/12/24 | Wed 18/12/24 | 3 days | Mon 16/12/24 | Wed 18/12/24 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.1.2 |  |  | SITAG |  | SRO provide feedback | 100% | Thu 19/12/24 | Tue 07/01/25 | 14 days | Thu 19/12/24 | Tue 07/01/25 | 0 days | 0 days | 14 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.1.3 |  |  | SITAG |  | Address SRO feedback on execution model | 100% | Wed 08/01/25 | Thu 09/01/25 | 2 days | Wed 08/01/25 | Thu 09/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.1.4 |  |  | SITAG |  | Finalise execution model | 100% | Fri 10/01/25 | Tue 14/01/25 | 3 days | Fri 10/01/25 | Tue 14/01/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.1.5 |  |  | SITAG |  | SITWG paper day | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.1.6 |  |  | SITAG |  | SITWG update on execution model | 100% | Tue 21/01/25 | Tue 21/01/25 | 0 days | Tue 21/01/25 | Tue 21/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.5.13.2 |  |  | SITAG |  | Theme 1, 2 and 3 (Batch 2) | 100% | Mon 05/08/24 | Wed 04/09/24 | 23 days? | Mon 05/08/24 | Wed 04/09/24 | 0 days | 0 days | 23 days? | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.2.1 |  |  | SITAG |  | Develop execution model Theme 1, 2 and 3 (Batch 2) | 100% | Mon 03/02/25 | Fri 14/02/25 | 10 days | Mon 03/02/25 | Fri 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.2.2 |  |  | SITAG |  | SRO provide feedback | 100% | Tue 25/02/25 | Mon 03/03/25 | 5 days | Mon 17/02/25 | Fri 21/02/25 | 6 days | 6 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.2.3 |  |  | SITAG |  | Address SRO feedback on execution model | 100% | Tue 04/03/25 | Mon 10/03/25 | 5 days | Mon 17/02/25 | Fri 21/02/25 | 11 days | 11 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.2.4 |  |  | SITAG |  | Finalise execution model | 100% | Tue 11/03/25 | Mon 17/03/25 | 5 days | Mon 24/02/25 | Thu 27/02/25 | 11 days | 12 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.13.2.5 |  |  | SITAG |  | Execution Model shared with industry | 100% | Mon 17/03/25 | Mon 17/03/25 | 0 days | Thu 27/02/25 | Thu 27/02/25 | 13 days | 12 days | 0 days | SI Test |  | 6.2 | Yes
7 | 1.4.1.4.5.13.3 |  |  | SITAG |  | SIT Operational Theme 3 (Batch 1) progress reporting | 100% | Thu 19/12/24 | Tue 28/01/25 | 29 days? | Thu 19/12/24 | Fri 31/01/25 | 0 days | -3 days | 29 days? | SI Test |  | 6.14 | Yes
8 | 1.4.1.4.5.13.3.1 |  |  | SITAG |  | Determine reporting methodology | 100% | Thu 19/12/24 | Fri 20/12/24 | 2 days? | Thu 19/12/24 | Fri 17/01/25 | 0 days | -20 days | 2 days? | SI Test |  | 6.14 | Yes
8 | 1.4.1.4.5.13.3.2 |  |  | SITAG |  | Implement reporting | 100% | Mon 23/12/24 | Fri 24/01/25 | 25 days | Mon 20/01/25 | Fri 31/01/25 | -20 days | -5 days | 25 days | SI Test |  | 6.14 | Yes
6 | 1.4.1.4.5.14 |  |  | SITAG |  | SIT Operational Overarching Test Readiness Reports | 100% | Mon 05/08/24 | Wed 18/09/24 | 33 days? | Mon 05/08/24 | Wed 18/09/24 | 0 days | 0 days | -118 days? | N/A |  | 6 | Yes
7 | 1.4.1.4.5.14.1 |  |  | SITAG |  | SI SIT Operational Theme 3 (Batch 1) Overarching Test Readiness Report | 100% | Wed 18/12/24 | Wed 29/01/25 | 31 days? | Mon 23/12/24 | Wed 29/01/25 | -3 days | 0 days | 31 days? | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.1 |  |  | SITAG |  | Develop Overarching SIT Operational Theme 3 (Batch 1) Overarching Test Readiness Report | 100% | Wed 18/12/24 | Tue 14/01/25 | 20 days | Wed 18/12/24 | Tue 14/01/25 | 0 days | 0 days | 20 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.2 |  |  | SITAG |  | SRO review | 100% | Wed 08/01/25 | Tue 14/01/25 | 5 days | Wed 08/01/25 | Tue 14/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.3 |  |  | SITAG |  | SITWG Paper day | 100% | Tue 14/01/25 | Tue 14/01/25 | 0 days | Tue 14/01/25 | Tue 14/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.4 |  |  | SITAG |  | SITWG review the Operational Theme 3 (Batch 1) Overarching Test Readiness Report | 100% | Tue 21/01/25 | Tue 21/01/25 | 0 days | Tue 21/01/25 | Tue 21/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.5 |  |  | SITAG |  | Update Operational Theme 3 (Batch 1) Overarching Test Readiness Report following SRO / SITWG feedback | 100% | Wed 22/01/25 | Wed 22/01/25 | 1 day | Wed 22/01/25 | Wed 22/01/25 | 0 days | 0 days | 1 day | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.6 |  |  | SITAG |  | SITAG paper day | 100% | Wed 22/01/25 | Wed 22/01/25 | 0 days | Wed 22/01/25 | Wed 22/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.7 |  |  | SITAG |  | FTIG recommendation | 100% | Fri 24/01/25 | Fri 24/01/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.8 |  |  | SITAG |  | Republish Operational Theme 3 (Batch 1) Overarching Test Readiness Report with latest data and evidence | 100% | Mon 27/01/25 | Mon 27/01/25 | 1 day? | Mon 27/01/25 | Mon 27/01/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.1.9 | T3 | T3-TE-0192 | SITAG |  | SITAG approve Theme 3 (Batch 1) Test Readiness Report | 100% | Wed 29/01/25 | Wed 29/01/25 | 0 days | Wed 29/01/25 | Wed 29/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.5.14.2 |  |  | SITAG |  | SI SIT Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 100% | Mon 27/01/25 | Fri 28/03/25 | 45 days | Mon 27/01/25 | Fri 28/03/25 | 0 days | 0 days | 45 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.1 |  |  | SITAG |  | Develop Overarching SIT Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 100% | Mon 27/01/25 | Fri 21/02/25 | 20 days | Mon 27/01/25 | Fri 21/02/25 | 0 days | 0 days | 20 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.2 |  |  | SITAG |  | SRO review | 100% | Mon 24/02/25 | Fri 28/02/25 | 5 days | Mon 24/02/25 | Fri 28/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.3 |  |  | SITAG |  | SITWG Paper day | 100% | Thu 27/02/25 | Thu 27/02/25 | 0 days | Thu 27/02/25 | Thu 27/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.4 |  |  | SITAG |  | SITWG review the Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 100% | Thu 06/03/25 | Thu 06/03/25 | 0 days | Thu 06/03/25 | Thu 06/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.5 |  |  | SITAG |  | Update Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report following SRO feedback | 100% | Fri 07/03/25 | Tue 25/03/25 | 13 days | Fri 07/03/25 | Tue 25/03/25 | 0 days | 0 days | 13 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.6 |  |  | SITAG |  | GLIG recommendation | 100% | Fri 21/03/25 | Fri 21/03/25 | 0 days | Fri 21/03/25 | Fri 21/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.7 |  |  | SITAG |  | eSITAG paper day | 100% | Wed 26/03/25 | Wed 26/03/25 | 0 days | Wed 26/03/25 | Wed 26/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
8 | 1.4.1.4.5.14.2.8 | T3 | T3-TE-0193 | SITAG |  | eSITAG approve Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 100% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.5.15 | T2 | T2-TE-0750 | SITAG |  | SIT Operational Theme 3 (Batch 1) Testing Preparation Complete | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.5.16 | T2 | T2-TE-1300 | SITAG |  | SIT Operational Theme 1, 2, 3 (Batch 2) Testing Preparation Complete | 100% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Mon 31/03/25 | Fri 25/04/25 | 0 days | -20 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.5.17 |  |  | SITAG |  | Test Data - Non-Functional and Operational (SIT B) | 100% | Mon 24/02/25 | Fri 28/03/25 | 25 days? | Mon 06/01/25 | Fri 14/03/25 | 35 days | 10 days | 25 days? | SI Test |  | 6 | Yes
7 | 1.4.1.4.5.17.1 |  |  | SITAG |  | Data Load | 100% | Mon 24/02/25 | Fri 28/03/25 | 25 days? | Mon 06/01/25 | Fri 14/03/25 | 35 days | 10 days | 25 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.17.1.1 | T3 | T3-TE-0126 | SITAG |  | Non-Functional Theme 1 (Avenade) Data Load | 100% | Mon 24/02/25 | Fri 28/02/25 | 5 days? | Mon 24/02/25 | Fri 28/02/25 | 0 days | 0 days | 5 days? | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.17.1.2 | T3 | T3-TE-0127 | SITAG |  | Non-Functional Theme 2 & 3 (Helix, Avenade & PPs) Data Load | 100% | Mon 24/03/25 | Fri 28/03/25 | 5 days | Mon 24/03/25 | Fri 28/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.17.1.3 | T3 | T3-TE-0128 | SITAG |  | Non-Functional Themes 2 & 3 (LDSO's) Data Load | 100% | Mon 03/03/25 | Fri 21/03/25 | 15 days | Mon 03/03/25 | Fri 21/03/25 | 0 days | 0 days | 15 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.17.1.4 | T3 | T3-TE-0129 | SITAG |  | Operational Themes 1, 2 & 3 (Batch 2) (LDSO's) Data Load | 100% | Mon 03/03/25 | Fri 28/03/25 | 20 days? | Mon 03/03/25 | Fri 28/03/25 | 0 days | 0 days | 20 days? | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.17.1.5 | T3 | T3-TE-0130 | SITAG |  | Operational Themes 1, 2 & 3 (Batch 2) (Helix, Avenade & PPs) Data Load | 100% | Mon 24/03/25 | Fri 28/03/25 | 5 days | Mon 24/03/25 | Fri 28/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.17.1.6 | T3 | T3-TE-0131 | SITAG |  | Non-Functional and Operational Test Data Preparation Complete | 100% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
5 | 1.4.1.4.6 |  |  | SITAG |  | Regression Test Preparation | 100% | Mon 18/11/24 | Tue 19/11/24 | 2 days? | Mon 18/11/24 | Tue 19/11/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.6.1 |  |  | SITAG |  | Regression Test Approach | 100% | Mon 18/11/24 | Fri 29/11/24 | 10 days | Mon 18/11/24 | Fri 29/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.1 |  |  | SITAG |  | Develop approach doc | 100% | Mon 18/11/24 | Fri 17/01/25 | 45 days | Mon 18/11/24 | Fri 17/01/25 | 0 days | 0 days | 45 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.2 |  |  | SITAG |  | SRO / LDP review of approach doc | 100% | Mon 20/01/25 | Fri 24/01/25 | 5 days | Mon 20/01/25 | Fri 24/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.3 |  |  | SITAG |  | Incorporate SRO feedback into approach doc | 100% | Mon 20/01/25 | Fri 24/01/25 | 5 days | Mon 20/01/25 | Fri 24/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.4 |  |  | SITAG |  | Industry review of approach | 100% | Mon 27/01/25 | Fri 07/02/25 | 10 days | Mon 27/01/25 | Fri 07/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.5 |  |  | SITAG |  | Updates to approach doc on back of industry feedback | 100% | Mon 10/02/25 | Tue 11/02/25 | 2 days | Mon 10/02/25 | Tue 11/02/25 | 0 days | 0 days | 2 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.6 |  |  | SITAG |  | eSITWG paper day | 100% | Tue 11/02/25 | Tue 11/02/25 | 0 days | Tue 11/02/25 | Tue 11/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.7 |  |  | SITAG |  | eSITWG Recommendation | 100% | Tue 18/02/25 | Tue 18/02/25 | 0 days | Tue 18/02/25 | Tue 18/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.8 |  |  | SITAG |  | Incorporate eSITWG feedback into approach doc | 100% | Wed 19/02/25 | Thu 20/02/25 | 2 days | Wed 19/02/25 | Thu 20/02/25 | 0 days | 0 days | 2 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.9 |  |  | SITAG |  | eSITAG paper day | 100% | Thu 20/02/25 | Thu 20/02/25 | 0 days | Thu 20/02/25 | Thu 20/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.10 |  |  | SITAG |  | eSITAG (inc SRO) Approval | 100% | Fri 28/02/25 | Fri 28/02/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.1.11 | T3 | T3-TE-0123 | SITAG |  | SIT Regression Testing Approach and Plan Approval | 100% | Fri 28/02/25 | Fri 28/02/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
6 | 1.4.1.4.6.2 |  |  | SITAG |  | Regression Core Test Pack | 100% | Wed 12/02/25 | Thu 24/04/25 | 52 days? | Wed 12/02/25 | Wed 16/04/25 | 0 days | 6 days | 52 days? | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.2.1 |  |  | SITAG |  | Build Regression Core Pack | 100% | Wed 12/02/25 | Thu 06/03/25 | 17 days | NA | NA | 0 days | 0 days | 17 days | SI Test |  | 6.19 | Yes
7 | 1.4.1.4.6.2.2 |  |  | SITAG |  | Build Regression Framework | 100% | Wed 12/02/25 | Thu 27/02/25 | 12 days | Wed 12/02/25 | Fri 28/02/25 | 0 days | -1 day | 12 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.2.3 |  |  | SITAG |  | SITWG paper day | 100% | Thu 27/02/25 | Thu 27/02/25 | 0 days | Thu 27/02/25 | Thu 27/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.2.4 |  |  | SITAG |  | SITWG provides feedback on Regression Framework approach | 100% | Thu 06/03/25 | Thu 06/03/25 | 0 days | Thu 06/03/25 | Thu 06/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.2.5 |  |  | SITAG |  | LDP walkthrough of Regression Core Pack | 100% | Thu 27/02/25 | Mon 03/03/25 | 3 days | Fri 28/02/25 | Fri 28/02/25 | -1 day | 1 day | 3 days | SI Test |  | 6.17 | Yes
7 | 1.4.1.4.6.2.6 |  |  | SITAG |  | SRO Review of Regression Core Pack | 100% | Fri 07/03/25 | Fri 14/03/25 | 6 days | Mon 03/03/25 | Fri 07/03/25 | 4 days | 5 days | 6 days | SI Test |  | 6.2 | Yes
7 | 1.4.1.4.6.2.7 |  |  | SITAG |  | Incorporate SRO feedback into Regression Core Pack | 100% | Fri 07/03/25 | Fri 14/03/25 | 6 days | Mon 03/03/25 | Fri 07/03/25 | 4 days | 5 days | 6 days | SI Test |  | 6.2 | Yes
7 | 1.4.1.4.6.2.8 |  |  | SITAG |  | Industry review of Regression Core Pack | 100% | Mon 17/03/25 | Fri 28/03/25 | 10 days | Mon 17/03/25 | Fri 28/03/25 | 0 days | 0 days | 10 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.9 |  |  | SITAG |  | Regression Test Framework Core Pack - PP Walkthrough | 100% | Thu 20/03/25 | Thu 20/03/25 | 1 day? | Thu 20/03/25 | Thu 20/03/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.2 | Yes
7 | 1.4.1.4.6.2.10 |  |  | SITAG |  | Regression Test Framework Core Pack - Q&A Drop in session | 100% | Thu 27/03/25 | Thu 27/03/25 | 1 day? | Thu 27/03/25 | Thu 27/03/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.11 |  |  | SITAG |  | Incorporate Industry feedback into Regression Core Pack | 100% | Mon 31/03/25 | Wed 02/04/25 | 3 days | Mon 31/03/25 | Wed 02/04/25 | 0 days | 0 days | 3 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.12 |  |  | SITAG |  | Second industry review of Regression Core Pack | 100% | Thu 03/04/25 | Wed 09/04/25 | 5 days | Thu 03/04/25 | Wed 09/04/25 | 0 days | 0 days | 5 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.13 |  |  | SITAG |  | Incorporate industry feedback into regression Core Pack | 100% | Thu 10/04/25 | Thu 10/04/25 | 1 day | Thu 10/04/25 | Thu 10/04/25 | 0 days | 0 days | 1 day | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.14 |  |  | SITAG |  | SITWG paper day | 100% | Tue 08/04/25 | Tue 08/04/25 | 0 days | Thu 10/04/25 | Thu 10/04/25 | -1 day | -2 days | 0 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.15 |  |  | SITAG |  | SITWG endorses regression Core Pack | 100% | Tue 15/04/25 | Tue 15/04/25 | 0 days | Tue 15/04/25 | Tue 15/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.16 |  |  | SITAG |  | Incorporate SITWG feedback into regression Core Pack | 100% | Wed 16/04/25 | Thu 17/04/25 | 2 days | Wed 16/04/25 | Thu 17/04/25 | 0 days | 0 days | 2 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.17 |  |  | SITAG |  | Regression Test Approach and Plan Uplift | 100% | Wed 16/04/25 | Wed 16/04/25 | 0 days | Wed 16/04/25 | Wed 16/04/25 | 0 days | -1 day | 0 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.18 |  |  | SITAG |  | Industry Review on the Uplifted Test Approach and Plan | 100% | Thu 17/04/25 | Wed 23/04/25 | 5 days | Thu 17/04/25 | Wed 23/04/25 | 0 days | 0 days | 5 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.19 |  |  | SITAG |  | SITAG paper day | 100% | Thu 17/04/25 | Thu 17/04/25 | 0 days | Thu 17/04/25 | Thu 17/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
7 | 1.4.1.4.6.2.20 |  |  | SITAG |  | SITAG (inc SRO) Approval of regression Core Pack | 100% | Thu 24/04/25 | Thu 24/04/25 | 0 days | Thu 24/04/25 | Thu 24/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.21 | Yes
7 | 1.4.1.4.6.2.21 | T3 | T3-TE-0122 | SITAG |  | SIT Regression Approval | 100% | Thu 24/04/25 | Thu 24/04/25 | 0 days | Thu 24/04/25 | Thu 24/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
6 | 1.4.1.4.6.3 |  |  | SITAG |  | Regression Test Data Load Window (SIT Functional and Migration) - SIT A | 100% | Mon 28/04/25 | Tue 29/04/25 | 1 day? | Fri 14/03/25 | Mon 17/03/25 | 32 days | 31 days | 1 day? | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.6.3.1 |  |  | SITAG |  | Data Load preparation activities | 100% | Mon 31/03/25 | Fri 25/04/25 | 20 days | Mon 31/03/25 | Fri 25/04/25 | 0 days | 0 days | 20 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.6.3.2 | T2 | T2-TE-1000 | SITAG |  | Regression Test Data Load Start | 100% | Mon 28/04/25 | Mon 28/04/25 | 0 days | Mon 28/04/25 | Mon 28/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.6.3.3 |  |  | SITAG |  | Regression Test Data Load Window | 100% | Tue 29/04/25 | Fri 16/05/25 | 14 days | Mon 28/04/25 | Fri 16/05/25 | 1 day | 0 days | 14 days | SI Test |  | 6.15 | Yes
5 | 1.4.1.4.7 |  |  | SITAG |  | Single Instance ADO | 100% | Wed 21/08/24 | Thu 03/10/24 | 32 days? | Wed 21/08/24 | Thu 03/10/24 | 0 days | 0 days | 32 days? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.1 |  |  | SITAG |  | Single ADO Project for all Cohorts - Implementation and Test Phase | 100% | Wed 21/08/24 | Tue 01/10/24 | 30 days? | Wed 21/08/24 | Tue 01/10/24 | 0 days | 0 days | 30 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.1 |  |  | SITAG |  | Create test plans and suites in master project | 100% | Wed 21/08/24 | Thu 22/08/24 | 2 days? | Wed 21/08/24 | Thu 22/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.2 |  |  | SITAG |  | Create area paths / iterations | 100% | Wed 21/08/24 | Thu 22/08/24 | 2 days? | Wed 21/08/24 | Thu 22/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.3 |  |  | SITAG |  | Create IAM roles | 100% | Wed 21/08/24 | Thu 22/08/24 | 2 days? | Wed 21/08/24 | Thu 22/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.4 |  |  | SITAG |  | Add users to roles | 100% | Fri 23/08/24 | Fri 23/08/24 | 1 day? | Fri 23/08/24 | Fri 23/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.5 |  |  | SITAG |  | Testing permissions | 100% | Tue 27/08/24 | Wed 28/08/24 | 2 days? | Tue 27/08/24 | Wed 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.7.1.5.1 |  |  | SITAG |  | Adding tests | 100% | Tue 27/08/24 | Wed 28/08/24 | 2 days? | Tue 27/08/24 | Wed 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.7.1.5.2 |  |  | SITAG |  | Deleting tests | 100% | Tue 27/08/24 | Wed 28/08/24 | 2 days? | Tue 27/08/24 | Wed 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.7.1.5.3 |  |  | SITAG |  | Adding tests to incorrect Cohort | 100% | Tue 27/08/24 | Wed 28/08/24 | 2 days? | Tue 27/08/24 | Wed 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.7.1.5.4 |  |  | SITAG |  | Add / delete defects | 100% | Tue 27/08/24 | Wed 28/08/24 | 2 days? | Tue 27/08/24 | Wed 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.6 |  |  | SITAG |  | Migrate defects from cohort project to master - Option 2 | 100% | Mon 23/09/24 | Wed 25/09/24 | 3 days | Mon 23/09/24 | Wed 25/09/24 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.1.7 |  |  | SITAG |  | Testing Permissions - Evidence attachment security | 100% | Wed 18/09/24 | Tue 01/10/24 | 10 days? | Wed 18/09/24 | Tue 01/10/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.2 |  |  | SITAG |  | ADO Dashboard Updates | 100% | Tue 03/09/24 | Mon 30/09/24 | 20 days? | Tue 03/09/24 | Mon 30/09/24 | 0 days | 0 days | 20 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.2.1 |  |  | SITAG |  | Update reporting dashboards in ADO | 100% | Tue 03/09/24 | Thu 05/09/24 | 3 days | Tue 03/09/24 | Thu 05/09/24 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.2.2 |  |  | SITAG |  | Review dashboards with SI LDP leads | 100% | Fri 06/09/24 | Fri 27/09/24 | 16 days | Fri 06/09/24 | Fri 27/09/24 | 0 days | 0 days | 16 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.2.3 |  |  | SITAG |  | Review dashboards with SRO | 100% | Mon 09/09/24 | Mon 30/09/24 | 16 days | Mon 09/09/24 | Mon 30/09/24 | 0 days | 0 days | 16 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.2.4 |  |  | SITAG |  | Update dashboards following review | 100% | Thu 12/09/24 | Fri 13/09/24 | 2 days | Thu 12/09/24 | Fri 13/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.2.5 |  |  | SITAG |  | Document changes to dashboard creation process | 100% | Mon 16/09/24 | Thu 19/09/24 | 4 days | Mon 16/09/24 | Thu 19/09/24 | 0 days | 0 days | 4 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.2.6 |  |  | SITAG |  | Update SIT Dashboards for Sprints 4.1 & 4.2 across all Cohorts | 100% | Tue 03/09/24 | Tue 03/09/24 | 1 day? | Tue 03/09/24 | Tue 03/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.3 |  |  | SITAG |  | Reporting Changes - PowerBI & QIP | 100% | Fri 23/08/24 | Tue 24/09/24 | 23 days? | Fri 23/08/24 | Tue 24/09/24 | 0 days | 0 days | 23 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.1 |  |  | SITAG |  | Design, Create and ETL ADO Entities into PowerBI Data Model | 100% | Fri 23/08/24 | Fri 23/08/24 | 1 day? | Fri 23/08/24 | Fri 23/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.2 |  |  | SITAG |  | Determine Relationships between ADO Entities & Attributes | 100% | Tue 27/08/24 | Tue 27/08/24 | 1 day? | Tue 27/08/24 | Tue 27/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.3 |  |  | SITAG |  | Create Relevant Dax Measures | 100% | Wed 28/08/24 | Wed 28/08/24 | 1 day? | Wed 28/08/24 | Wed 28/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.4 |  |  | SITAG |  | Design & Build Visualisations (Graphs) | 100% | Thu 29/08/24 | Thu 29/08/24 | 1 day? | Thu 29/08/24 | Thu 29/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.5 |  |  | SITAG |  | Implement Filters | 100% | Mon 23/09/24 | Mon 23/09/24 | 1 day? | Mon 23/09/24 | Mon 23/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.6 |  |  | SITAG |  | Check Data Quality & Integrity | 100% | Tue 24/09/24 | Tue 24/09/24 | 1 day? | Tue 24/09/24 | Tue 24/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.3.7 |  |  | SITAG |  | Performance Optimisation | 100% | Tue 24/09/24 | Tue 24/09/24 | 1 day? | Tue 24/09/24 | Tue 24/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.4 |  |  | SITAG |  | Reporting Changes - Daily Excel Extract & PDF | 100% | Thu 05/09/24 | Fri 06/09/24 | 2 days | Thu 05/09/24 | Fri 06/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.4.1 |  |  | SITAG |  | Excel Daily Report changes (Refer to above) | 100% | Thu 05/09/24 | Fri 06/09/24 | 2 days | Thu 05/09/24 | Fri 06/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.4.2 |  |  | SITAG |  | PDF Daily Report changes (Refer to Above) | 100% | Thu 05/09/24 | Fri 06/09/24 | 2 days | Thu 05/09/24 | Fri 06/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.5 |  |  | SITAG |  | Documentation Updates | 100% | Mon 02/09/24 | Wed 02/10/24 | 23 days? | Mon 02/09/24 | Wed 02/10/24 | 0 days | 0 days | 23 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.5.1 |  |  | SITAG |  | Changes to onboarding process (security) | 100% | Mon 02/09/24 | Fri 13/09/24 | 10 days | Mon 02/09/24 | Fri 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.5.2 |  |  | SITAG |  | Update the documents on loading tests into ADO? | 100% | Mon 02/09/24 | Fri 13/09/24 | 10 days | Mon 02/09/24 | Fri 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.5.3 |  |  | SITAG |  | Update ADO Training material | 100% | Mon 02/09/24 | Fri 13/09/24 | 10 days | Mon 02/09/24 | Fri 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.5.4 |  |  | SITAG |  | Update ADO User Guide | 100% | Mon 02/09/24 | Fri 13/09/24 | 10 days | Mon 02/09/24 | Fri 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.5.5 |  |  | SITAG |  | Update ADO Configuration document | 100% | Mon 02/09/24 | Fri 13/09/24 | 10 days | Mon 02/09/24 | Fri 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.5.6 |  |  | SITAG |  | Update ADO Training Material and User Guide following SRO review | 100% | Wed 02/10/24 | Wed 02/10/24 | 1 day? | Wed 02/10/24 | Wed 02/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.6 |  |  | SITAG |  | ADO Changes - Review Stage | 100% | Mon 09/09/24 | Thu 03/10/24 | 19 days? | Mon 09/09/24 | Thu 03/10/24 | 0 days | 0 days | 19 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.1 |  |  | SITAG |  | Review implementation with SI LDP leads | 100% | Fri 27/09/24 | Fri 27/09/24 | 1 day? | Fri 27/09/24 | Fri 27/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.2 |  |  | SITAG |  | Review implementation with SRO | 100% | Mon 30/09/24 | Mon 30/09/24 | 1 day? | Mon 30/09/24 | Mon 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.3 |  |  | SITAG |  | LDP Review - ADO User Guide, Training Materials | 100% | Mon 09/09/24 | Fri 13/09/24 | 5 days | Mon 09/09/24 | Fri 13/09/24 | 0 days | 0 days | 5 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.4 |  |  | SITAG |  | SRO Review - ADO User Guide, Training Materials | 100% | Mon 30/09/24 | Mon 30/09/24 | 1 day? | Mon 30/09/24 | Mon 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.5 |  |  | SITAG |  | LDP Review - Config doc | 100% | Mon 30/09/24 | Mon 30/09/24 | 1 day? | Mon 30/09/24 | Mon 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.6 |  |  | SITAG |  | SRO Review - Config doc | 100% | Mon 30/09/24 | Mon 30/09/24 | 1 day? | Mon 30/09/24 | Mon 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.6.7 |  |  | SITAG |  | SRO Sign-off of all changes | 100% | Thu 03/10/24 | Thu 03/10/24 | 1 day? | Thu 03/10/24 | Thu 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.7.7 |  |  | SITAG |  | Azure DevOps Changes - Final Implementation | 100% | Thu 03/10/24 | Thu 03/10/24 | 1 day? | Thu 03/10/24 | Thu 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.7.1 |  |  | SITAG |  | Final task rollout | 100% | Thu 03/10/24 | Thu 03/10/24 | 1 day? | Thu 03/10/24 | Thu 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.7.7.2 |  |  | SITAG |  | ADO Training Drop-in Session ahead of Cycle 3 | 100% | Thu 03/10/24 | Thu 03/10/24 | 1 day? | Thu 03/10/24 | Thu 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
3 | 1.4.2 |  |  | SITAG |  | SIT Execution | 100% | Mon 30/10/23 | Fri 19/09/25 | 495 days? | Mon 31/10/22 | Thu 27/11/25 | 260 days | -49 days | 105 days? | N/A |  | 5 | Yes
4 | 1.4.2.1 | T1 | T1-TE-1000 | SITAG | MHHS-ART071 | System Integration Testing Start (M9) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 0 days | -1 day | 0 days | CPT |  | 5.11 | Yes
4 | 1.4.2.2 |  |  | SITAG |  | SIT Component Integration Testing | 100% | Mon 30/10/23 | Mon 11/03/24 | 96 days | Mon 30/10/23 | Mon 11/03/24 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
5 | 1.4.2.2.1 |  |  | SITAG |  | SIT Component Integration Testing Start | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 0 days | -1 day | 0 days | SI Test |  | 5.11 | Yes
5 | 1.4.2.2.2 | T3 | T3-TE-0060 | SITAG | MHHS-ART071 | Component Integration Testing Interval 1 Start | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
5 | 1.4.2.2.3 | T3 | T3-TE-0061 | SITAG |  | Component Integration Testing Interval 2 Start | 100% | Mon 13/11/23 | Mon 13/11/23 | 0 days | Mon 13/11/23 | Mon 13/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
5 | 1.4.2.2.4 | T3 | T3-TE-0062 | SITAG |  | Component Integration Testing Interval 3 Start | 100% | Mon 27/11/23 | Mon 27/11/23 | 0 days | Mon 27/11/23 | Mon 27/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.5 | T3 | T3-TE-0063 | SITAG |  | Component Integration Testing Interval 4 Start | 100% | Mon 11/12/23 | Mon 11/12/23 | 0 days | Mon 11/12/23 | Mon 11/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.6 | T3 | T3-TE-0064 | SITAG |  | Component Integration Testing Interval 5 Start | 100% | Mon 15/01/24 | Mon 15/01/24 | 0 days | Mon 15/01/24 | Mon 15/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.7 | T3 | T3-TE-0065 | SITAG |  | Component Integration Testing Interval 6 Start | 100% | Mon 29/01/24 | Mon 29/01/24 | 0 days | Mon 29/01/24 | Mon 29/01/24 | 0 days | -1 day | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.8 |  |  | SITAG |  | SIT Component Integration Testing Execution | 100% | Mon 30/10/23 | Fri 23/02/24 | 85 days | Mon 30/10/23 | Fri 23/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.9 | T3 | T3-TE-0032 | SITAG | MHHS-ART074 | SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 100% | Fri 23/02/24 | Fri 23/02/24 | 0 days | Fri 23/02/24 | Fri 23/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.10 |  |  | SITAG |  | Assurance of PPs Test Completion Reports | 100% | Mon 22/01/24 | Fri 01/03/24 | 30 days | Mon 22/01/24 | Fri 01/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.11 |  |  | SITAG |  | SIT CI Test Completion Report | 100% | Wed 07/02/24 | Fri 01/03/24 | 18 days | Wed 07/02/24 | Fri 01/03/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.2.2.11.1 |  |  | SITAG |  | Develop document | 100% | Wed 07/02/24 | Fri 23/02/24 | 13 days | Wed 07/02/24 | Fri 23/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
6 | 1.4.2.2.11.2 |  |  | SITAG |  | Review & agree document | 100% | Mon 26/02/24 | Fri 01/03/24 | 5 days | Mon 26/02/24 | Fri 01/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.12 | T2 | T2-TE-0600 | SITAG | MHHS-ART074 | SIT Component Integration Testing Test Completion Report Approved | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days | Mon 11/03/24 | Mon 11/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
4 | 1.4.2.3 |  |  | SITAG |  | SIT | 100% | Mon 11/03/24 | Fri 19/09/25 | 400 days? | Mon 31/10/22 | Fri 22/08/25 | 355 days | 20 days | 160 days? | N/A |  | 6.24 | Yes
5 | 1.4.2.3.1 |  |  | SITAG |  | SIT Functional Testing (MVC) | 100% | Mon 11/03/24 | Fri 19/09/25 | 400 days? | Mon 31/10/22 | Fri 15/08/25 | 355 days | 25 days | 175 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.1.1 | T3 | T3-TE-0034 | SITAG | MHHS-ART073 | SIT Functional Testing Start | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days | Mon 11/03/24 | Mon 11/03/24 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.2.3.1.2 |  |  | SITAG |  | SIT Functional Testing Execution (Minimum Viable Cohort) | 100% | Mon 11/03/24 | Mon 28/04/25 | 295 days? | Mon 31/10/22 | Fri 15/08/25 | 355 days | -80 days | 70 days? | N/A |  | 5 | Yes
7 | 1.4.2.3.1.2.1 |  |  | SITAG |  | Cycle 1 (Full Cycle) | 100% | Mon 11/03/24 | Fri 14/06/24 | 70 days | Mon 11/03/24 | Fri 14/06/24 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.1.1 |  |  | SITAG |  | Test Execution | 100% | Mon 11/03/24 | Fri 24/05/24 | 55 days | Mon 11/03/24 | Fri 24/05/24 | 0 days | 0 days | -25 days | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.1.2 |  |  | SITAG |  | Defect resolution, assurance, review, data & environments maintenance | 100% | Mon 27/05/24 | Fri 14/06/24 | 15 days | Mon 27/05/24 | Fri 14/06/24 | 0 days | 0 days | 5 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.2 |  |  | SITAG |  | Cycle 2 (Defect retests and targeted regression testing) | 100% | Mon 17/06/24 | Fri 04/10/24 | 80 days | Mon 17/06/24 | Fri 04/10/24 | 0 days | 0 days | 30 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.2.1 |  |  | SITAG |  | Test Execution | 100% | Mon 17/06/24 | Fri 20/09/24 | 70 days | Mon 17/06/24 | Fri 20/09/24 | 0 days | 0 days | 30 days | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.2.2 |  |  | SITAG |  | Defect resolution, assurance, review, data & environments maintenance | 100% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 23/09/24 | Fri 04/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.3 |  |  | SITAG |  | SIT Functional Testing back-up progress risk-assessment | 100% | Mon 07/10/24 | Tue 15/10/24 | 7 days? | Mon 31/10/22 | Mon 31/10/22 | 505 days | 511 days | -13 days? | N/A |  | 5.31 | Yes
8 | 1.4.2.3.1.2.3.1 |  |  | SITAG |  | Back-up risk-assessment of SIT Functional progress to assess whether Qualification Execution can start early | 100% | Mon 07/10/24 | Mon 07/10/24 | 1 day? | Mon 07/10/24 | Mon 07/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 5.31 | Yes
8 | 1.4.2.3.1.2.3.2 |  |  | SITAG |  | Back-up SITAG decision on early Qualification Testing Execution start | 100% | Tue 15/10/24 | Tue 15/10/24 | 1 day? | Tue 15/10/24 | Tue 15/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 5.31 | Yes
7 | 1.4.2.3.1.2.4 |  |  | SITAG |  | Cycle 3 (Defect retests and targeted regression testing) | 100% | Mon 21/10/24 | Fri 14/03/25 | 105 days? | Mon 21/10/24 | Fri 14/03/25 | 0 days | 0 days | 75 days? | SI Test |  | 5 | Yes
8 | 1.4.2.3.1.2.4.1 |  |  | SITAG |  | Sprint 5 | 100% | Mon 21/10/24 | Fri 01/11/24 | 10 days? | Mon 21/10/24 | Fri 01/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.2 |  |  | SITAG |  | Sprint 6 | 100% | Mon 04/11/24 | Fri 15/11/24 | 10 days? | Mon 04/11/24 | Fri 15/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.3 |  |  | SITAG |  | Sprint 7 | 100% | Mon 18/11/24 | Fri 29/11/24 | 10 days? | Mon 18/11/24 | Fri 29/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.4 |  |  | SITAG |  | Sprint 8 | 100% | Mon 02/12/24 | Fri 20/12/24 | 15 days? | Mon 02/12/24 | Fri 20/12/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.5 |  |  | SITAG |  | Christmas downtime | 100% | Mon 23/12/24 | Fri 03/01/25 | 10 days? | Mon 23/12/24 | Fri 03/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.6 |  |  | SITAG |  | Sprint 9 | 100% | Mon 06/01/25 | Fri 17/01/25 | 10 days? | Mon 06/01/25 | Fri 17/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.7 |  |  | SITAG |  | Sprint 10 | 100% | Mon 20/01/25 | Fri 31/01/25 | 10 days? | Mon 20/01/25 | Fri 31/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.8 |  |  | SITAG |  | Sprint 11 | 100% | Mon 03/02/25 | Fri 14/02/25 | 10 days? | Mon 03/02/25 | Fri 14/02/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.9 |  |  | SITAG |  | Sprint 12 | 100% | Mon 17/02/25 | Fri 28/02/25 | 10 days? | Mon 17/02/25 | Fri 28/02/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.10 |  |  | SITAG |  | Sprint 13 (RTTM Gap Analysis + CR056) | 100% | Mon 03/03/25 | Fri 14/03/25 | 10 days? | Mon 03/03/25 | Fri 14/03/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.11 |  |  | SITAG |  | Sprint 14 (RTTM Gap Analysis + CR056) | 100% | Mon 17/03/25 | Fri 28/03/25 | 10 days? | Mon 17/03/25 | Fri 28/03/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.4.12 |  |  | SITAG |  | Sprint 15 (Contingency 1) | 100% | Mon 31/03/25 | Fri 11/04/25 | 10 days? | Mon 31/03/25 | Fri 11/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.4.13 |  |  | SITAG |  | Sprint 16 (Contingency 2) | 100% | Mon 14/04/25 | Fri 25/04/25 | 10 days? | Mon 14/04/25 | Fri 25/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.4.14 | T2 | T2-TE-1150 | SITAG |  | SIT Functional Cycle 3 Complete | 100% | Mon 28/04/25 | Mon 28/04/25 | 0 days | Mon 28/04/25 | Mon 28/04/25 | 0 days | -1 day | 0 days | SI Test |  | 6.13 | Yes
6 | 1.4.2.3.1.3 |  |  | SITAG |  | SIT Scope Traceability | 100% | Mon 27/01/25 | Thu 24/04/25 | 64 days | Mon 27/01/25 | Wed 19/03/25 | 0 days | 26 days | 64 days | SI Test |  | 6.17 | Yes
7 | 1.4.2.3.1.3.1 |  |  | SITAG |  | Draft Scope Tracability document | 100% | Mon 27/01/25 | Fri 07/02/25 | 10 days | Mon 27/01/25 | Fri 07/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.17 | Yes
7 | 1.4.2.3.1.3.2 |  |  | SITAG |  | LDP review | 100% | Mon 10/02/25 | Tue 11/02/25 | 2 days | Mon 10/02/25 | Tue 11/02/25 | 0 days | 0 days | 2 days | SI Test |  | 6.17 | Yes
7 | 1.4.2.3.1.3.3 |  |  | SITAG |  | SRO review | 100% | Wed 12/02/25 | Tue 18/02/25 | 5 days | Wed 12/02/25 | Tue 18/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
7 | 1.4.2.3.1.3.4 |  |  | SITAG |  | Updates to reflect SRO feedback | 100% | Wed 12/02/25 | Tue 18/02/25 | 5 days | Wed 12/02/25 | Tue 18/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.17 | Yes
7 | 1.4.2.3.1.3.5 |  |  | SITAG |  | Industry Review | 100% | Wed 19/02/25 | Tue 04/03/25 | 10 days | Wed 19/02/25 | Tue 04/03/25 | 0 days | 0 days | 10 days | SI Test |  | 6.17 | Yes
7 | 1.4.2.3.1.3.6 |  |  | SITAG |  | SITWG paper day | 100% | Tue 08/04/25 | Tue 08/04/25 | 0 days | Tue 08/04/25 | Tue 08/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
7 | 1.4.2.3.1.3.7 |  |  | SITAG |  | SITWG recommends Scope Tracability document | 100% | Tue 15/04/25 | Tue 15/04/25 | 0 days | Tue 15/04/25 | Tue 15/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
7 | 1.4.2.3.1.3.8 |  |  | SITAG |  | Update document to reflect industry consultation views | 100% | Wed 05/03/25 | Fri 14/03/25 | 8 days | Wed 05/03/25 | Fri 14/03/25 | 0 days | 0 days | 8 days | SI Test |  | 6.2 | Yes
7 | 1.4.2.3.1.3.9 |  |  | SITAG |  | SITAG paper day | 100% | Thu 17/04/25 | Thu 17/04/25 | 0 days | Thu 17/04/25 | Thu 17/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
7 | 1.4.2.3.1.3.10 |  |  | SITAG |  | SITAG approve SIT Scope Traceability document | 100% | Thu 24/04/25 | Thu 24/04/25 | 0 days | Thu 24/04/25 | Thu 24/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
7 | 1.4.2.3.1.3.11 |  |  | SITAG |  | SIT Scope Traceability Approved | 100% | Thu 24/04/25 | Thu 24/04/25 | 0 days | Thu 24/04/25 | Thu 24/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
6 | 1.4.2.3.1.4 |  |  | SITAG |  | SIT Functional Settlement Testing | 100% | Mon 17/06/24 | Fri 02/05/25 | 230 days? | Mon 17/06/24 | Fri 02/05/25 | 0 days | 0 days | 230 days? | SI Test |  | 6.12 | Yes
7 | 1.4.2.3.1.4.1 |  |  | SITAG |  | SIT-B Settlement Testing Cycle 2 | 100% | Mon 10/03/25 | Fri 13/06/25 | 70 days | Mon 10/03/25 | Fri 13/06/25 | 0 days | 0 days | 70 days | SI Test |  | 6.12 | Yes
7 | 1.4.2.3.1.4.2 |  |  | SITAG |  | SIT-B Settlement Testing Cycle 3 | 100% | Mon 07/10/24 | Fri 21/02/25 | 100 days? | Mon 07/10/24 | Fri 20/12/24 | 0 days | 45 days | 100 days? | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.1 |  |  | SITAG |  | Sprint 5 | 100% | Mon 07/10/24 | Fri 01/11/24 | 20 days? | Mon 07/10/24 | Fri 01/11/24 | 0 days | 0 days | 20 days? | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.2 |  |  | SITAG |  | Sprint 5 Review (Flexibility Window Checkpoint) | 100% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.3 |  |  | SITAG |  | Sprint 6 | 100% | Mon 04/11/24 | Fri 15/11/24 | 10 days? | Mon 04/11/24 | Fri 15/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.4 |  |  | SITAG |  | Sprint 6 Review (Pre Christmas Contingency Decision Point) | 100% | Mon 18/11/24 | Mon 18/11/24 | 0 days | Mon 18/11/24 | Mon 18/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.5 |  |  | SITAG |  | Sprint 7 | 100% | Mon 18/11/24 | Fri 29/11/24 | 10 days? | Mon 18/11/24 | Fri 29/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.6 |  |  | SITAG |  | Sprint 7 Review (Post Christmas Contingency Decision Point) | 100% | Mon 02/12/24 | Mon 02/12/24 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.4.2.7 |  |  | SITAG |  | Sprint 8 | 100% | Mon 02/12/24 | Fri 20/12/24 | 15 days | Mon 02/12/24 | Fri 20/12/24 | 0 days | 0 days | 15 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.8 |  |  | SITAG |  | Post-Christmas Stabilisation | 100% | Mon 06/01/25 | Fri 10/01/25 | 5 days | Mon 06/01/25 | Fri 10/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.9 |  |  | SITAG |  | Sprint 9 | 100% | Mon 06/01/25 | Fri 17/01/25 | 10 days | Mon 13/01/25 | Fri 17/01/25 | -5 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.10 |  |  | SITAG |  | Sprint 9 Review | 100% | Mon 20/01/25 | Mon 20/01/25 | 0 days | Mon 20/01/25 | Mon 20/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.11 |  |  | SITAG |  | Sprint 10 | 100% | Mon 20/01/25 | Fri 31/01/25 | 10 days | Mon 20/01/25 | Fri 31/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.12 |  |  | SITAG |  | Sprint 10 Review | 100% | Mon 03/02/25 | Mon 03/02/25 | 0 days | Mon 03/02/25 | Mon 03/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.13 |  |  | SITAG |  | Sprint 11 | 100% | Mon 03/02/25 | Fri 14/02/25 | 10 days | Mon 03/02/25 | Fri 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.14 |  |  | SITAG |  | Sprint 11 Review | 100% | Fri 14/02/25 | Fri 14/02/25 | 0 days | Fri 14/02/25 | Fri 14/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.15 |  |  | SITAG |  | Sprint 12 | 100% | Mon 17/02/25 | Fri 21/02/25 | 5 days | Mon 17/02/25 | Fri 21/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.4.2.16 | T3 | T3-TE-0140 | SITAG |  | End of Settlement Testing Cycle 3 | 100% | Fri 21/02/25 | Fri 21/02/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.1.4.3 |  |  | SITAG |  | SIT-A Settlement Testing | 100% | Mon 19/05/25 | Fri 27/06/25 | 30 days | Mon 19/05/25 | Fri 13/06/25 | 0 days | 10 days | 30 days | SI Test |  | 6.19 | Yes
8 | 1.4.2.3.1.4.3.1 |  |  | SITAG |  | SIT-A Settlement Testing Start | 100% | Mon 19/05/25 | Mon 19/05/25 | 0 days | Mon 19/05/25 | Mon 19/05/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
8 | 1.4.2.3.1.4.3.2 |  |  | SITAG |  | SIT-A Settlement Testing | 100% | Mon 19/05/25 | Fri 27/06/25 | 30 days | Mon 19/05/25 | Fri 27/06/25 | 0 days | 0 days | 30 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.3.3 |  |  | SITAG |  | eSITAG decision point on end of SIT A testing | 100% | Thu 26/06/25 | Thu 26/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | 12 days | 11 days | 0 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.3.4 |  |  | SITAG |  | SIT-A Settlement Decision Point Exit Criteria | 100% | Fri 27/06/25 | Fri 27/06/25 | 0 days | Fri 27/06/25 | Fri 27/06/25 | 0 days | -1 day | 0 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.3.5 |  |  | SITAG |  | SIT-A Settlement Testing Completed | 100% | Fri 27/06/25 | Fri 27/06/25 | 0 days | Fri 27/06/25 | Fri 27/06/25 | 0 days | -1 day | 0 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.1.4.4 |  |  | SITAG |  | SIT Functional & Migration Regression Testing (code freeze) | 100% | Mon 30/06/25 | Fri 12/09/25 | 55 days? | Mon 16/06/25 | Fri 08/08/25 | 10 days | 25 days | 10 days? | PP |  | 6.28 | Yes
8 | 1.4.2.3.1.4.4.1 | T2 | T2-TE-1250 | SITAG |  | Regression Test Execution Start | 100% | Mon 30/06/25 | Mon 30/06/25 | 0 days | Mon 30/06/25 | Mon 30/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.4.2 |  |  | SITAG |  | Regression Execution | 100% | Mon 30/06/25 | Fri 04/07/25 | 5 days | Mon 30/06/25 | Fri 04/07/25 | 0 days | 0 days | 5 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.4.3 |  |  | SITAG |  | Regression Sprint 1 | 100% | Mon 07/07/25 | Fri 18/07/25 | 10 days? | Mon 07/07/25 | Fri 18/07/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.4.4 |  |  | SITAG |  | Regression Sprint 2 | 100% | Mon 21/07/25 | Fri 08/08/25 | 15 days | Mon 21/07/25 | Fri 08/08/25 | 0 days | 0 days | 15 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.4.5 |  |  | SITAG |  | Cycle 1 SAT Regression | 100% | Mon 21/07/25 | Fri 01/08/25 | 10 days | Mon 21/07/25 | Fri 01/08/25 | 0 days | 0 days | 10 days | SI Test |  | 6.29 | Yes
8 | 1.4.2.3.1.4.4.6 |  |  | SITAG |  | Supplementary Regression Testing | 100% | Mon 21/07/25 | Fri 15/08/25 | 20 days | Mon 21/07/25 | Fri 15/08/25 | 0 days | 0 days | 20 days | SI Test |  | 6.3 | Yes
8 | 1.4.2.3.1.4.4.7 |  |  | SITAG |  | Cycle 2 SAT Regression | 100% | Mon 04/08/25 | Fri 08/08/25 | 5 days | Mon 04/08/25 | Fri 08/08/25 | 0 days | 0 days | 5 days | SI Test |  | 6.29 | Yes
8 | 1.4.2.3.1.4.4.8 |  |  | SITAG |  | Regression Sprint 3 | 100% | Mon 11/08/25 | Fri 22/08/25 | 10 days | Mon 11/08/25 | Fri 22/08/25 | 0 days | 0 days | 10 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.4.9 |  |  | SITAG |  | Regression Sprint 4 | 100% | Mon 25/08/25 | Fri 12/09/25 | 15 days | Mon 25/08/25 | Fri 12/09/25 | 0 days | 0 days | 15 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.1.4.5 |  |  | SITAG |  | SIT Functional & Migration Overarching Exit Report | 100% | Mon 28/04/25 | Thu 17/07/25 | 59 days | Mon 21/07/25 | Fri 15/08/25 | -60 days | -21 days | 39 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.4.5.1 |  |  | SITAG |  | Programme drafts Functional & Migration PP Exit Report | 100% | Mon 28/04/25 | Tue 10/06/25 | 32 days | Mon 28/04/25 | Tue 10/06/25 | 0 days | 0 days | 32 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.5.2 |  |  | SITAG |  | SRO Review PP Exit Reports | 100% | Thu 22/05/25 | Wed 04/06/25 | 10 days | Thu 22/05/25 | Wed 04/06/25 | 0 days | 0 days | 10 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.5.3 |  |  | SITAG |  | Functional & Migration PP Exit Reports shared with PPs | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.5.4 |  |  | SITAG |  | PPs review Exit Report and sign Functional & Migration Exit Declaration | 100% | Wed 11/06/25 | Tue 24/06/25 | 10 days | Wed 11/06/25 | Tue 24/06/25 | 0 days | 0 days | 10 days | PP |  | 6.28 | Yes
8 | 1.4.2.3.1.4.5.5 |  |  | SITAG |  | Programme drafts SI SIT Functional & Migration Overarching Exit Report | 100% | Wed 11/06/25 | Fri 27/06/25 | 13 days | Wed 11/06/25 | Fri 27/06/25 | 0 days | 0 days | 13 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.5.6 |  |  | SITAG |  | SRO/Code Bodies Review SI SIT Funcational & Migration Overarching Exit Report | 100% | Thu 26/06/25 | Wed 02/07/25 | 5 days | Mon 30/06/25 | Thu 03/07/25 | -2 days | -1 day | 5 days | SRO, Code Bodies |  |  | Yes
8 | 1.4.2.3.1.4.5.7 |  |  | SITAG |  | SITWG Review status of SI SIT Functional & Migration Overarching Exit Report | 100% | Thu 03/07/25 | Thu 03/07/25 | 0 days | Thu 03/07/25 | Thu 03/07/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.5.8 |  |  | SITAG |  | SI SIT Functional & Migration Overarching Exit Report Industry Review | 100% | Fri 04/07/25 | Thu 17/07/25 | 10 days | Fri 04/07/25 | Thu 17/07/25 | 0 days | 0 days | 10 days | PP |  | 6.28 | Yes
7 | 1.4.2.3.1.4.6 |  |  | SITAG |  | SIT Settlement and Regression Test Exit Report | 100% | Mon 07/07/25 | Fri 19/09/25 | 55 days | Mon 30/06/25 | Fri 15/08/25 | 5 days | 25 days | 55 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.1 |  |  | SITAG |  | Programme drafts Settlement and Regression Pathway 2 PP Exit Reports | 100% | Mon 07/07/25 | Wed 23/07/25 | 13 days | Mon 30/06/25 | Fri 08/08/25 | 5 days | -12 days | 13 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.2 |  |  | SITAG |  | SRO Review Settlement and Regression Pathway 2 PP Exit Reports | 100% | Thu 17/07/25 | Wed 23/07/25 | 5 days | Thu 17/07/25 | Wed 23/07/25 | 0 days | 0 days | 5 days | SRO |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.3 |  |  | SITAG |  | Pathway 2 PPs review and sign off Regression Exit Declaration | 100% | Mon 21/07/25 | Mon 28/07/25 | 6 days | Mon 07/07/25 | Fri 08/08/25 | 10 days | -9 days | 6 days | PP |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.4 |  |  | SITAG |  | Programme drafts Settlement and Regression Pathway 3 PP Exit Reports | 100% | Mon 28/07/25 | Wed 13/08/25 | 13 days | Mon 28/07/25 | Wed 13/08/25 | 0 days | 0 days | 13 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.5 |  |  | SITAG |  | SRO Review Settlement and Regression Pathway 3 PP Exit Reports | 100% | Thu 07/08/25 | Wed 13/08/25 | 5 days | Thu 07/08/25 | Wed 13/08/25 | 0 days | 0 days | 5 days | SRO |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.6 |  |  | SITAG |  | Pathway 3 PPs review and sign off Exit Reports | 100% | Mon 11/08/25 | Fri 15/08/25 | 5 days | Mon 11/08/25 | Fri 15/08/25 | 0 days | 0 days | 5 days | PP |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.7 |  |  | SITAG |  | Programme drafts Settlement and Regression Pathway 4, 5 & 6 PP Exit Reports | 100% | Mon 18/08/25 | Fri 19/09/25 | 25 days | Mon 18/08/25 | Fri 19/09/25 | 0 days | 0 days | 25 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.8 |  |  | SITAG |  | Programme drafts SI SIT Settlement and Regression Addendum | 100% | Mon 21/07/25 | Fri 08/08/25 | 15 days | Mon 07/07/25 | Fri 08/08/25 | 10 days | 0 days | 15 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.9 |  |  | SITAG |  | SRO/Code Bodies Review SI SIT Settlement and Regression Addendum | 100% | Mon 04/08/25 | Fri 08/08/25 | 5 days | Mon 04/08/25 | Fri 08/08/25 | 0 days | 0 days | 5 days | SRO, Code Bodies |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.10 | T2 | T2-TE-0800 | SITAG |  | SI SIT Migration Testing Test Exit Report Approved | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Wed 20/08/25 | Wed 20/08/25 | -3 days | -4 days | -45 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.11 | T2 | T2-TE-0850 | SITAG | MHHS-ART072 | SI SIT Functional Testing Test Exit Report Approved | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Wed 20/08/25 | Wed 20/08/25 | -2 days | -3 days | 0 days | SI Test |  | 6.28 | Yes
8 | 1.4.2.3.1.4.6.12 |  |  | SITAG |  | eSITAG Approves SI SIT Functional & Migration (Post-Regression) Overarching Test Exit Report | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Wed 20/08/25 | Wed 20/08/25 | -3 days | -4 days | 0 days | SI Test |  | 6.28 | Yes
5 | 1.4.2.3.2 |  |  | SITAG |  | SIT Migration Testing | 100% | Mon 11/03/24 | Fri 25/04/25 | 295 days? | Mon 11/03/24 | Fri 22/08/25 | 0 days | -85 days | 140 days? | SI Test |  | 6 | Yes
6 | 1.4.2.3.2.1 |  |  |  |  | SIT Migration Testing Start | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days? | Mon 11/03/24 | Mon 11/03/24 | 0 days | -1 day | 0 days? | SI Test |  | 6 | Yes
6 | 1.4.2.3.2.2 |  |  | SITAG |  | SIT Migration Testing Execution | 100% | Mon 11/03/24 | Fri 25/04/25 | 295 days? | Mon 11/03/24 | Fri 22/08/25 | 0 days | -85 days | 295 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.2.2.1 |  |  |  |  | Cycle 1 (Full Cycle) | 100% | Mon 11/03/24 | Fri 14/06/24 | 70 days? | Mon 11/03/24 | Fri 14/06/24 | 0 days | 0 days | 70 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.1.1 |  |  |  |  | Test Execution | 100% | Mon 11/03/24 | Fri 24/05/24 | 55 days? | Mon 11/03/24 | Fri 24/05/24 | 0 days | 0 days | 55 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.1.2 |  |  |  |  | Defect resolution, assurance, review, data& environments maintenance | 100% | Mon 27/05/24 | Fri 14/06/24 | 15 days? | Mon 27/05/24 | Fri 14/06/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.2.2.2 |  |  |  |  | Cycle 2 (Defect retests and targeted regression testing) | 100% | Mon 11/03/24 | Fri 28/06/24 | 80 days? | Mon 11/03/24 | Fri 28/06/24 | 0 days | 0 days | 80 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.2.1 |  |  |  |  | Test Execution | 100% | Mon 17/06/24 | Fri 20/09/24 | 70 days? | Mon 17/06/24 | Fri 20/09/24 | 0 days | 0 days | 70 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.2.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 100% | Mon 23/09/24 | Fri 04/10/24 | 10 days? | Mon 23/09/24 | Fri 04/10/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.2.2.3 |  |  |  |  | SIT Migration Testing back-up progress risk-assessment | 100% | Mon 17/06/24 | Fri 20/09/24 | 70 days? | Mon 17/06/24 | Fri 20/09/24 | 0 days | 0 days | 70 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.3.1 |  |  |  |  | Back-up risk-assessment of SIT Migration progress to assess whether Qualification Execution can start early | 100% | Mon 07/10/24 | Fri 25/10/24 | 15 days? | Mon 07/10/24 | Fri 25/10/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.3.2 |  |  |  |  | Back-up SITAG decision on early Qualification Testing Execution start | 100% | Fri 01/11/24 | Fri 01/11/24 | 0 days? | Fri 01/11/24 | Fri 01/11/24 | 1 day | 0 days | 0 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.2.2.4 |  |  | SITAG |  | Cycle 3 (Defect retests and targeted regression testing) | 100% | Mon 21/10/24 | Fri 25/04/25 | 135 days? | Mon 21/10/24 | Fri 25/04/25 | 0 days | 0 days | 135 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.1 |  |  |  |  | Sprint 5 | 100% | Mon 21/10/24 | Fri 01/11/24 | 10 days | Mon 21/10/24 | Fri 01/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.2 |  |  |  |  | Sprint 6 | 100% | Mon 04/11/24 | Fri 15/11/24 | 10 days | Mon 04/11/24 | Fri 15/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.3 |  |  |  |  | Sprint 7 | 100% | Mon 18/11/24 | Fri 29/11/24 | 10 days | Mon 18/11/24 | Fri 29/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.4 |  |  |  |  | Sprint 8 | 100% | Mon 02/12/24 | Fri 20/12/24 | 15 days | Mon 02/12/24 | Fri 20/12/24 | 0 days | 0 days | 15 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.5 |  |  |  |  | Christmas downtime | 100% | Mon 23/12/24 | Fri 03/01/25 | 10 days | Mon 23/12/24 | Fri 03/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.6 |  |  |  |  | Sprint 9 | 100% | Mon 06/01/25 | Fri 17/01/25 | 10 days | Mon 06/01/25 | Fri 17/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.7 |  |  |  |  | Sprint 10 | 100% | Mon 20/01/25 | Fri 31/01/25 | 10 days | Mon 20/01/25 | Fri 31/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.8 |  |  |  |  | Sprint 11 | 100% | Mon 03/02/25 | Fri 14/02/25 | 10 days | Mon 03/02/25 | Fri 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.9 |  |  |  |  | Sprint 12 | 100% | Mon 17/02/25 | Fri 28/02/25 | 10 days | Mon 17/02/25 | Fri 28/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.2.2.4.10 |  |  |  |  | Sprint 13 | 100% | Mon 03/03/25 | Fri 14/03/25 | 10 days | Mon 03/03/25 | Fri 14/03/25 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.2.2.4.11 |  |  |  |  | Sprint 14 (RTTM Gap Analysis + CR056) | 100% | Mon 17/03/25 | Fri 28/03/25 | 10 days? | Mon 17/03/25 | Fri 28/03/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.2.2.4.12 |  |  | SITAG |  | Sprint 15 (Contingency 1) | 100% | Mon 31/03/25 | Fri 11/04/25 | 10 days? | Mon 31/03/25 | Fri 11/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.2.2.4.13 |  |  | SITAG |  | Sprint 16 (Contingency 2) | 100% | Mon 14/04/25 | Fri 25/04/25 | 10 days? | Mon 14/04/25 | Fri 25/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.2.2.4.14 | T2 | T2-TE-1200 | SITAG |  | SIT Migration Cycle 3 Complete | 100% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
5 | 1.4.2.3.3 |  |  | SITAG |  | SIT Non-Functional Testing (all SIT PPs) | 100% | Mon 03/03/25 | Wed 06/08/25 | 112 days? | Fri 28/02/25 | Thu 10/07/25 | 1 day | 18 days | 12 days? | N/A |  | 6.1 | Yes
6 | 1.4.2.3.3.1 | T3 | T3-TE-0124 | SITAG |  | Theme 1 (Helix and DIP Volume Testing) Start | 100% | Mon 03/03/25 | Mon 03/03/25 | 0 days? | Mon 03/03/25 | Mon 03/03/25 | 1 day | 0 days | 0 days? | SIT Participant |  | 6.15 | Yes
6 | 1.4.2.3.3.2 |  |  |  |  | Theme 1 (Helix and DIP Volume Testing) Execution | 100% | Mon 03/03/25 | Fri 21/03/25 | 15 days? | Mon 03/03/25 | Fri 21/03/25 | 0 days | 0 days | 15 days? | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.3.3 | T3 | T3-TE-0040 | SITAG | MHHS-ART079 | Theme 2 & 3 SIT Non-Functional Testing Start | 100% | Mon 31/03/25 | Mon 31/03/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.21 | Yes
6 | 1.4.2.3.3.4 |  |  |  |  | Theme 2 & 3 SIT Non-Functional Testing Execution | 100% | Mon 31/03/25 | Fri 23/05/25 | 40 days | Mon 31/03/25 | Fri 23/05/25 | 0 days | 0 days | -50 days | SI Test |  | 6.21 | Yes
6 | 1.4.2.3.3.5 | T3 | T3-TE-0047 | SITAG | MHHS-ART079 | SIT Non-Functional Testing Execution End (all SIT PPs) | 100% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Fri 23/05/25 | Fri 23/05/25 | 1 day | 0 days | 0 days | SI Test |  | 6.26 | Yes
6 | 1.4.2.3.3.6 |  |  |  |  | SIT Non-Functional Testing Test Exit Report (all SIT PPs) | 100% | Mon 26/05/25 | Wed 06/08/25 | 52 days | Fri 02/05/25 | Thu 29/05/25 | 16 days | 48 days | 32 days | N/A |  | 6.15 | Yes
7 | 1.4.2.3.3.6.1 |  |  | SITAG |  | Programme drafts Non-Functional PP Exit Report | 100% | Mon 26/05/25 | Fri 27/06/25 | 25 days | Mon 26/05/25 | Fri 27/06/25 | 0 days | 0 days | 25 days | SI Test |  | 6.25 | Yes
7 | 1.4.2.3.3.6.2 |  |  | SITAG |  | Non-Functional PP Exit Reports shared with PPs | 100% | Fri 27/06/25 | Fri 27/06/25 | 0 days | Fri 27/06/25 | Fri 27/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
7 | 1.4.2.3.3.6.3 |  |  | SITAG |  | PPs review Exit Report and Sign PP Exit Declaration | 100% | Fri 27/06/25 | Fri 11/07/25 | 11 days | Fri 27/06/25 | Fri 11/07/25 | 0 days | 0 days | 11 days | PP |  | 6.28 | Yes
7 | 1.4.2.3.3.6.4 |  |  | SITAG |  | Programme drafts SI SIT Non-Functional Overarching Exit Report | 100% | Fri 27/06/25 | Fri 18/07/25 | 16 days | Fri 27/06/25 | Fri 18/07/25 | 0 days | 0 days | 16 days | SI Test |  | 6.25 | Yes
7 | 1.4.2.3.3.6.5 |  |  | SITAG |  | Draft of SI SIT Non-Functional Overarching Exit Report available for SRO review | 100% | Mon 07/07/25 | Fri 11/07/25 | 5 days | Mon 07/07/25 | Fri 11/07/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
7 | 1.4.2.3.3.6.6 |  |  | SITAG |  | SRO / Code Bodies / DIP Manager formal review SI SIT Non-Functional Overarching Exit Report | 100% | Mon 14/07/25 | Fri 18/07/25 | 5 days | Mon 14/07/25 | Fri 18/07/25 | 0 days | 0 days | 5 days | SRO, Code Bodies, DIP Manager |  | 6.28 | Yes
7 | 1.4.2.3.3.6.7 |  |  | SITAG |  | eSITWG Review status of SI SIT Non-Functional Overarching Exit Report | 100% | Fri 18/07/25 | Fri 18/07/25 | 0 days | Fri 18/07/25 | Fri 18/07/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
7 | 1.4.2.3.3.6.8 |  |  | SITAG |  | SI SIT Non-Functional Overarching Exit Report published to PPs for industry review | 100% | Fri 18/07/25 | Fri 18/07/25 | 0 days | Fri 18/07/25 | Fri 18/07/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.3.6.9 |  |  | SITAG |  | SI SIT Non-Functional Overarching Exit Report industry review | 100% | Mon 21/07/25 | Fri 01/08/25 | 10 days | Mon 21/07/25 | Fri 01/08/25 | 0 days | 0 days | 10 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.3.6.10 | T2 | T2-TE-0900 | SITAG | MHHS-ART079 | SIT Non-Functional Testing Test Exit Report (all SIT PPs) Approved | 100% | Wed 06/08/25 | Wed 06/08/25 | 0 days | Wed 06/08/25 | Wed 06/08/25 | 0 days | -1 day | 0 days | SI Test |  | 6.25 | Yes
7 | 1.4.2.3.3.6.11 |  |  | SITAG |  | eSITAG Approves SI SIT Non-Functional Overarching Test Exit Report | 100% | Wed 06/08/25 | Wed 06/08/25 | 0 days | Wed 06/08/25 | Wed 06/08/25 | 0 days | -1 day | 0 days | SI Test |  | 6.25 | Yes
5 | 1.4.2.3.4 |  |  | SITAG |  | SIT Operational Testing (all SIT PPs) | 100% | Mon 03/02/25 | Fri 29/08/25 | 150 days? | Mon 03/02/25 | Fri 06/06/25 | 0 days | 60 days | 60 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.4.1 |  |  | SITAG |  | Non-SIT B Testing | 100% | Mon 03/02/25 | Fri 07/03/25 | 25 days? | Mon 03/02/25 | Fri 07/03/25 | 0 days | 0 days | 25 days? |  |  |  | Yes
7 | 1.4.2.3.4.1.1 | T3 | T3-TE-0121 | SITAG |  | SIT Operational Testing Start (Theme 3 - Batch 1 (Service Management)) | 100% | Mon 03/02/25 | Mon 03/02/25 | 0 days? | Mon 03/02/25 | Mon 03/02/25 | 0 days | -1 day | 0 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.4.1.2 |  |  | SITAG |  | SIT Operational Testing Execution Window (Theme 3 - Batch 1 (Service Management)) | 100% | Mon 03/02/25 | Fri 07/03/25 | 25 days? | Mon 03/02/25 | Fri 07/03/25 | 0 days | 0 days | 25 days? | SI Test |  | 6 | Yes
6 | 1.4.2.3.4.2 |  |  | SITAG |  | SIT B Testing | 100% | Mon 31/03/25 | Fri 04/07/25 | 70 days | Fri 07/02/25 | Fri 16/05/25 | 36 days | 35 days | 70 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.4.2.1 | T3 | T3-TE-0042 | SITAG | MHHS-ART073 MHHS-ART143 | SIT Operational Testing Start (SIT B) | 100% | Mon 31/03/25 | Mon 31/03/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.4.2.2 |  |  | SITAG |  | SIT Operational Testing Execution Theme 1 | 100% | Mon 31/03/25 | Fri 04/07/25 | 70 days | Mon 31/03/25 | Fri 04/07/25 | 0 days | 0 days | 70 days | SI Test |  | 6.22 | Yes
7 | 1.4.2.3.4.2.3 |  |  | SITAG |  | SIT Operational Testing Execution Theme 2 | 100% | Mon 05/05/25 | Fri 04/07/25 | 45 days | Mon 05/05/25 | Fri 04/07/25 | 0 days | 0 days | 45 days | SI Test |  | 6.22 | Yes
7 | 1.4.2.3.4.2.4 |  |  | SITAG |  | SIT Operational Testing Execution Theme 3 Batch 2 | 100% | Mon 09/06/25 | Fri 04/07/25 | 20 days | Mon 09/06/25 | Fri 04/07/25 | 0 days | 0 days | 20 days | SI Test |  | 6.22 | Yes
7 | 1.4.2.3.4.2.5 |  |  | SITAG |  | SIT Operational Testing Re-test Theme 3 (Batch 1) | 100% | Mon 05/05/25 | Fri 13/06/25 | 30 days | Mon 09/06/25 | Fri 13/06/25 | -25 days | 0 days | 30 days | SI Test |  | 6.25 | Yes
8 | 1.4.2.3.4.2.5.1 |  |  | SITAG |  | SRO Review of re-testing approach | 100% | Mon 05/05/25 | Fri 16/05/25 | 10 days | Mon 05/05/25 | Fri 16/05/25 | 0 days | 0 days | 10 days | SI Test |  | 6.25 | Yes
8 | 1.4.2.3.4.2.5.2 |  |  | SITAG |  | Scripts uploaded to ADO / Project Created | 100% | Mon 19/05/25 | Fri 23/05/25 | 5 days | Mon 19/05/25 | Fri 23/05/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
8 | 1.4.2.3.4.2.5.3 |  |  | SITAG |  | SIT Operational Testing Re-test Execution Theme 3 (Batch 1) | 100% | Mon 09/06/25 | Fri 13/06/25 | 5 days | Mon 09/06/25 | Fri 13/06/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
6 | 1.4.2.3.4.3 | T3 | T3-TE-0050 | SITAG | MHHS-ART081 | SIT Operational Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 100% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 11/07/25 | Fri 11/07/25 | -4 days | -5 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.2.3.4.4 |  |  | SITAG |  | SIT Operational Testing Test Exit Report (all SIT PPs) | 100% | Mon 23/06/25 | Fri 29/08/25 | 50 days | Mon 23/06/25 | Fri 18/07/25 | 0 days | 30 days | 30 days | N/A |  | 6.15 | Yes
7 | 1.4.2.3.4.4.1 |  |  | SITAG |  | Programme drafts Pathway 2 PP Exit Report (when Participant completes Operational testing) | 100% | Mon 30/06/25 | Fri 18/07/25 | 15 days | Mon 30/06/25 | Fri 18/07/25 | 0 days | 0 days | 15 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.2 |  |  | SITAG |  | All Pathway 2 Operational Exit Reports and Exit Declarations shared with PPs | 100% | Mon 21/07/25 | Mon 21/07/25 | 0 days | Mon 21/07/25 | Mon 21/07/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.3 |  |  | SITAG |  | Pathway 2 PPs have reviewed Exit Report and signed Exit Declaration | 100% | Mon 21/07/25 | Fri 25/07/25 | 5 days | Mon 21/07/25 | Fri 25/07/25 | 0 days | 0 days | 5 days | PP |  | 6.25 | Yes
7 | 1.4.2.3.4.4.4 |  |  | SITAG |  | Programme drafts Pathway 3 PP Exit Report (when Participant completes Operational testing) | 100% | Mon 21/07/25 | Fri 08/08/25 | 15 days | Mon 21/07/25 | Fri 08/08/25 | 0 days | 0 days | 15 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.5 |  |  | SITAG |  | All Pathway 3 Operational Exit Reports and Exit Declarations shared with PPs | 100% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 08/08/25 | Fri 08/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.6 |  |  | SITAG |  | Pathway 3 PPs have reviewed Exit Report and signed Exit Declaration | 100% | Mon 11/08/25 | Fri 15/08/25 | 5 days | Mon 11/08/25 | Fri 15/08/25 | 0 days | 0 days | 5 days | PP |  | 6.28 | Yes
7 | 1.4.2.3.4.4.7 |  |  | SITAG |  | Programme drafts Pathway 4 PP Exit Report (when Participant completes Operational testing) | 100% | Mon 04/08/25 | Fri 15/08/25 | 10 days | NA | NA | 0 days | 0 days | 10 days | SI Test |  | 6.29 | Yes
7 | 1.4.2.3.4.4.8 |  |  | SITAG |  | All Pathway 4 Operational Exit Reports and Exit Declarations shared with PPs | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | NA | NA | 0 days | 0 days | 0 days | SI Test |  | 6.29 | Yes
7 | 1.4.2.3.4.4.9 |  |  | SITAG |  | Pathway 4 PPs have reviewed Exit Report and signed Exit Declaration | 100% | Mon 18/08/25 | Fri 22/08/25 | 5 days | NA | NA | 0 days | 0 days | 5 days | PP |  | 6.29 | Yes
7 | 1.4.2.3.4.4.10 |  |  | SITAG |  | Programme drafts Pathway 5 & 6 PP Exit Report (when Participant completes Operational testing) | 100% | Mon 11/08/25 | Fri 29/08/25 | 15 days | Mon 11/08/25 | Fri 29/08/25 | 0 days | 0 days | 15 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.11 |  |  | SITAG |  | Programme drafts SI SIT Operational Overarching Exit Report | 100% | Mon 23/06/25 | Fri 01/08/25 | 30 days | Mon 23/06/25 | Fri 01/08/25 | 0 days | 0 days | 30 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.12 |  |  | SITAG |  | SRO/Code Bodies/DIP Manager Review SI SIT Operational Overarching Exit Report | 100% | Mon 28/07/25 | Fri 01/08/25 | 5 days | Mon 28/07/25 | Fri 01/08/25 | 0 days | 0 days | 5 days | SRO, Code Bodies, DIP Manager |  | 6.28 | Yes
7 | 1.4.2.3.4.4.13 |  |  | SITAG |  | eSITWG Review SI SIT Operational Overarching Exit Report | 100% | Fri 01/08/25 | Fri 01/08/25 | 0 days | Fri 01/08/25 | Fri 01/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.14 |  |  | SITAG |  | SI SIT Operational Overarching Exit Report industry review | 100% | Tue 05/08/25 | Tue 12/08/25 | 6 days | Mon 04/08/25 | Fri 15/08/25 | 1 day | -3 days | 6 days | PP |  | 6.28 | Yes
7 | 1.4.2.3.4.4.15 | T2 | T2-TE-0950 | SITAG | MHHS-ART081 | SIT Operational Testing Test Exit Report (all SIT PPs) Approved | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Fri 15/08/25 | Fri 15/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
7 | 1.4.2.3.4.4.16 |  |  | SITAG |  | eSITAG Approves SI SIT Operational Testing Test Exit Report | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Fri 15/08/25 | Fri 15/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
5 | 1.4.2.3.5 | T1 | T1-TE-2000 | PSG | MHHS-ART081 | SIT Complete (SIT Test Exit Report Approved) | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | 0 days | CPT |  | 6.25 | Yes
3 | 1.4.3 |  |  | SITAG |  | UIT Environment Preparation | 93% | Wed 16/11/22 | Fri 28/08/26 | 988 days | Mon 31/10/22 | Fri 04/07/25 | 12 days | 300 days | 308 days | N/A |  | 6 | Yes
4 | 1.4.3.1 |  |  | QAG |  | Test Artefact Development | 100% | Wed 01/03/23 | Thu 19/06/25 | 602 days | Wed 01/03/23 | Thu 18/07/24 | 0 days | 240 days | 241 days | N/A |  | 6 | Yes
5 | 1.4.3.1.1 |  |  | QAG |  | E2E Sandbox Guidance | 100% | Wed 01/03/23 | Thu 19/06/25 | 602 days | Wed 01/03/23 | Thu 18/07/24 | 0 days | 240 days | 241 days | N/A |  | 6 | Yes
6 | 1.4.3.1.1.1 |  |  | QAG |  | Develop document | 100% | Wed 01/03/23 | Fri 23/06/23 | 83 days | Wed 01/03/23 | Fri 23/06/23 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.3.1.1.2 |  |  | QAG |  | Artefact review (via SITAG) and updates | 100% | Mon 26/06/23 | Fri 28/07/23 | 25 days | Mon 26/06/23 | Fri 28/07/23 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.3.1.1.3 | T3 | T3-TE-0067 | QAG | MHHS-ART154 | E2E Sandbox Guidance approved | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
6 | 1.4.3.1.1.4 |  |  | QAG |  | Update E2E Sandbox guidance to reflect CR055 | 100% | Mon 17/03/25 | Fri 16/05/25 | 45 days | Mon 17/03/25 | Fri 16/05/25 | 0 days | 0 days | 45 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.5 |  |  | QAG |  | Internal SI review | 100% | Mon 19/05/25 | Fri 23/05/25 | 5 days | Mon 19/05/25 | Fri 23/05/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.6 |  |  | QAG |  | SRO / Code Bodies review | 100% | Mon 19/05/25 | Fri 23/05/25 | 5 days | Mon 19/05/25 | Fri 23/05/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.7 |  |  | QAG |  | Submit version to QWG | 100% | Tue 03/06/25 | Tue 03/06/25 | 0 days | Tue 03/06/25 | Tue 03/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.8 |  |  | QAG |  | Artefact Recommendation for Approval (via QWG) | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.9 |  |  | QAG |  | Final Document updates post QWG review | 100% | Wed 11/06/25 | Wed 11/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.10 |  |  | QAG |  | Submit final version to QAG | 100% | Thu 12/06/25 | Thu 12/06/25 | 0 days | Thu 12/06/25 | Thu 12/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.1.11 |  |  | QAG |  | E2E Sandbox guidance update approved at QAG | 100% | Thu 19/06/25 | Thu 19/06/25 | 0 days | Thu 19/06/25 | Thu 19/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
5 | 1.4.3.1.2 |  |  | QAG |  | E2E Sandbox Test Data Approach & Plan | 100% | Mon 10/03/25 | Thu 19/06/25 | 73 days | Tue 05/12/23 | Thu 09/05/24 | 329 days | 289 days | -20 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.1 |  |  | QAG |  | Discussion at QWG to reconfirm value provided from E2E Sandbox (UIT) | 100% | Tue 11/03/25 | Tue 11/03/25 | 0 days | Tue 11/03/25 | Tue 11/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.2 | Yes
6 | 1.4.3.1.2.2 |  |  | QAG |  | Create PPIR to request PP responses on subject to gather views | 100% | Mon 10/03/25 | Fri 14/03/25 | 5 days | Mon 10/03/25 | Fri 14/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.2 | Yes
6 | 1.4.3.1.2.3 |  |  | QAG |  | PPIR shared to industry | 100% | Mon 24/03/25 | Thu 03/04/25 | 9 days | Mon 24/03/25 | Thu 03/04/25 | 0 days | 0 days | 9 days | SI Test |  | 6.22 | Yes
6 | 1.4.3.1.2.4 |  |  | QAG |  | Evaluate PPIR responses | 100% | Fri 04/04/25 | Mon 07/04/25 | 2 days | Fri 04/04/25 | Mon 07/04/25 | 0 days | 0 days | 2 days | SI Test |  | 6.22 | Yes
6 | 1.4.3.1.2.5 |  |  | QAG |  | Discuss PPIR results at QWG | 100% | Tue 08/04/25 | Tue 08/04/25 | 1 day | Tue 08/04/25 | Tue 08/04/25 | 0 days | 0 days | 1 day | SI Test |  | 6.2 | Yes
6 | 1.4.3.1.2.6 |  |  | QAG |  | Develop document | 100% | Thu 10/04/25 | Fri 16/05/25 | 27 days | Thu 10/04/25 | Fri 16/05/25 | 0 days | 0 days | -41 days | SI Test |  | 5 | Yes
6 | 1.4.3.1.2.7 |  |  | QAG |  | Internal SI review and updates | 100% | Mon 19/05/25 | Fri 23/05/25 | 5 days | Mon 19/05/25 | Fri 23/05/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.8 |  |  | QAG |  | SRO / Code Bodies review | 100% | Mon 19/05/25 | Fri 23/05/25 | 5 days | Mon 19/05/25 | Fri 23/05/25 | 0 days | 0 days | 5 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.9 |  |  | QAG |  | Final updates prior to consultation | 100% | Mon 26/05/25 | Mon 26/05/25 | 1 day | Mon 26/05/25 | Mon 26/05/25 | 0 days | 0 days | 1 day | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.10 |  |  | QAG |  | Industry Consultation for E2E Sandbox Test Data Approach and Plan document | 100% | Tue 27/05/25 | Fri 06/06/25 | 9 days | Mon 26/05/25 | Fri 06/06/25 | 1 day | 0 days | 9 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.11 |  |  | QAG |  | Document updates post Industry Consultation | 100% | Fri 06/06/25 | Mon 09/06/25 | 2 days | Sat 07/06/25 | Mon 09/06/25 | -1 day | 0 days | 2 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.12 |  |  | QAG |  | Submit Proposed Version to QWG | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.13 |  |  | QAG |  | Artefact Approval (via QWG) | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.14 |  |  | QAG |  | Final Document updates post QWG review | 100% | Wed 11/06/25 | Wed 11/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.15 |  |  | QAG |  | Submit final version to QAG | 100% | Thu 12/06/25 | Thu 12/06/25 | 0 days | Thu 12/06/25 | Thu 12/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
6 | 1.4.3.1.2.16 | T3 | T3-QU-0124 | QAG |  | E2E Sandbox Test Data Approach and Plan Approved at QAG | 100% | Thu 19/06/25 | Thu 19/06/25 | 0 days | Wed 16/04/25 | Wed 16/04/25 | 46 days | 45 days | 0 days | SI Test |  | 6.25 | Yes
4 | 1.4.3.2 |  |  | QAG |  | UIT Stub Specification and Delivery | 100% | Mon 04/12/23 | Fri 29/11/24 | 260 days | Mon 04/12/23 | Fri 18/10/24 | 0 days | 30 days | 70 days | N/A |  | 5 | Yes
5 | 1.4.3.2.1 |  |  | QAG |  | Qualification Test Stubs | 100% | Mon 04/12/23 | Fri 29/11/24 | 260 days | Mon 04/12/23 | Fri 18/10/24 | 0 days | 30 days | 70 days | N/A |  | 5.16 | Yes
6 | 1.4.3.2.1.1 |  |  | QAG |  | Specify | 100% | Mon 04/12/23 | Thu 01/02/24 | 44 days | Mon 04/12/23 | Thu 01/02/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.3.2.1.2 |  |  | QAG |  | Build & Test | 100% | Fri 02/02/24 | Fri 16/08/24 | 141 days | Fri 02/02/24 | Fri 16/08/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5.23 | Yes
6 | 1.4.3.2.1.3 |  |  | QAG |  | Prepare for release | 100% | Mon 19/08/24 | Fri 29/11/24 | 75 days | Mon 19/08/24 | Fri 29/11/24 | 0 days | 0 days | 70 days | SI DevOps |  | 5 | Yes
6 | 1.4.3.2.1.4 | T3 | T3-TE-0035 | QAG | MHHS-ART080 | Non-SIT LDSO Test Harness Released | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | SI DevOps |  | 5.27 | Yes
4 | 1.4.3.3 |  |  | QAG |  | Environments (UIT) | 100% | Wed 16/11/22 | Mon 30/09/24 | 489 days | Mon 31/10/22 | Fri 04/07/25 | 12 days | -199 days | -191 days | N/A |  | 5 | Yes
5 | 1.4.3.3.1 |  |  | QAG |  | Central Party (Avanade) Environments (UIT) | 100% | Wed 16/11/22 | Fri 27/09/24 | 488 days | Wed 16/11/22 | Fri 27/09/24 | 0 days | 0 days | -5 days | N/A |  | 5.28 | Yes
6 | 1.4.3.3.1.1 |  |  | QAG |  | Central Party (Avandae) environment preparation (incl. security certificates and security compliance) | 100% | Wed 16/11/22 | Thu 01/08/24 | 447 days | Wed 16/11/22 | Thu 01/08/24 | 0 days | 0 days | -16 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.2 |  |  | QAG |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | Wed 16/11/22 | Thu 01/08/24 | 447 days | Wed 16/11/22 | Thu 01/08/24 | 0 days | 0 days | -16 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.3 |  |  | QAG |  | Central Party (Avanade) UIT environment connectivity proving | 100% | Mon 26/08/24 | Fri 27/09/24 | 25 days | Mon 26/08/24 | Fri 27/09/24 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.4 |  |  | QAG |  | Deployment of MHHS solution code to UIT environments | 100% | Mon 29/07/24 | Tue 30/07/24 | 2 days | Mon 29/07/24 | Tue 30/07/24 | 0 days | 0 days | -8 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.5 |  |  | QAG |  | Central Party (Avanade) UIT environment Regression Testing | 100% | Wed 31/07/24 | Wed 31/07/24 | 1 day | Wed 31/07/24 | Wed 31/07/24 | 0 days | 0 days | -9 days | PP |  | 5.28 | Yes
5 | 1.4.3.3.2 |  |  | QAG |  | SI Environments (UIT) | 100% | Wed 16/11/22 | Mon 30/09/24 | 489 days | Wed 16/11/22 | Fri 04/07/25 | 0 days | -199 days | -191 days | N/A |  | 5 | Yes
6 | 1.4.3.3.2.1 |  |  | QAG |  | Coordinate Central Parties' UIT environment preparation | 100% | Wed 16/11/22 | Thu 01/08/24 | 447 days | Wed 16/11/22 | Thu 01/08/24 | 0 days | 0 days | -16 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.2.2 |  |  | QAG |  | Assure Central Parties' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | Wed 16/11/22 | Fri 23/08/24 | 463 days | Wed 16/11/22 | Fri 23/08/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.2.3 | T3 | T3-TE-0044 | QAG |  | Central Parties' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 100% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.2.4 |  |  | QAG |  | Coordinate Central Parties' UIT environment connectivity proving | 100% | Mon 26/08/24 | Mon 30/09/24 | 26 days | Mon 26/08/24 | Mon 30/09/24 | 0 days | 0 days | 7 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.2.5 |  |  | QAG |  | Coordinate deployment of MHHS solution code to Central Parties' UIT environments | 100% | Mon 29/07/24 | Tue 30/07/24 | 2 days | Mon 29/07/24 | Tue 30/07/24 | 0 days | 0 days | -8 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.2.6 |  |  | QAG |  | Coordinate Central Parties' UIT environment Regression Testing | 100% | Wed 31/07/24 | Wed 31/07/24 | 1 day | Wed 31/07/24 | Wed 31/07/24 | 0 days | 0 days | -9 days | SI Test |  | 5 | Yes
4 | 1.4.3.4 |  |  | QAG |  | Onboarding and Test Data (Sandbox UIT) | 58% | Mon 02/06/25 | Fri 28/08/26 | 325 days | Mon 26/08/24 | Fri 04/10/24 | 200 days | 495 days | 295 days | N/A |  | 5 | Yes
5 | 1.4.3.4.1 |  |  | QAG |  | LDSO Onboarding and Test Data Creation and Support | 100% | Mon 02/06/25 | Thu 22/01/26 | 169 days | Mon 02/06/25 | Thu 22/01/26 | 0 days | 0 days | 169 days | SI Test |  | 6.28 | Yes
5 | 1.4.3.4.2 |  |  | QAG |  | Supplier & Agent Onboarding and Test Data Creation and Support | 30% | Mon 01/09/25 | Fri 28/08/26 | 260 days | Mon 01/09/25 | Fri 28/08/26 | 0 days | 0 days | 260 days | S&A Qualification |  | 6.28 | Yes
3 | 1.4.4 |  |  | QAG |  | Sandbox Execution | 60% | Mon 26/05/25 | Fri 28/08/26 | 330 days | NA | NA | 0 days | 0 days | 330 days | N/A |  | 6.28 | Yes
4 | 1.4.4.1 |  |  | QAG |  | SIT PPs Early Sandbox Testing Execution (SIT-A) | 100% | Fri 08/08/25 | Fri 24/10/25 | 56 days | Fri 08/08/25 | Fri 24/10/25 | 0 days | 0 days | -260 days | N/A |  | 6.15 | Yes
5 | 1.4.4.1.1 | T3 | T3-QU-0128 | QAG | MHHS-ART018 MHHS-ART154 MHHS-ART147 | SIT PPs E2E Sandbox Testing Start | 100% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 08/08/25 | Fri 08/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
5 | 1.4.4.1.2 |  |  | QAG |  | SIT PPs E2E Sandbox Testing Execution | 100% | Fri 08/08/25 | Fri 24/10/25 | 56 days | Fri 08/08/25 | Fri 24/10/25 | 0 days | 0 days | -260 days | PP |  | 6.28 | Yes
5 | 1.4.4.1.3 |  | T3-QU-0129 | QAG |  | SIT PPs E2E Sandbox Testing End | 100% | Fri 24/10/25 | Fri 24/10/25 | 0 days | Fri 24/10/25 | Fri 24/10/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
4 | 1.4.4.2 |  |  | QAG |  | Sandbox Testing Execution (UIT) - LDSO Participants | 100% | Mon 26/05/25 | Thu 22/01/26 | 174 days | Mon 26/05/25 | Thu 22/01/26 | 0 days | 0 days | -142 days | N/A |  | 6.15 | Yes
5 | 1.4.4.2.1 | T3 | T3-QU-0125 | QAG | MHHS-ART154 MHHS-ART147 | UIT E2E Sandbox Preparation Complete | 100% | Mon 26/05/25 | Mon 26/05/25 | 0 days | Mon 26/05/25 | Mon 26/05/25 | 0 days | -1 day | 0 days | SI Test |  | 6.28 | Yes
5 | 1.4.4.2.2 | T3 | T3-QU-0130 | QAG | MHHS-ART018 MHHS-ART154 MHHS-ART147 | Sandbox Testing Start (UIT) - LDSO Participants | 100% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
5 | 1.4.4.2.3 |  |  | QAG |  | Sandbox Testing Execution (UIT) - LDSO Participants | 100% | Mon 02/06/25 | Thu 22/01/26 | 169 days | Mon 02/06/25 | Thu 22/01/26 | 0 days | 0 days | -147 days | PP |  | 6.25 | Yes
5 | 1.4.4.2.4 |  | T3-QU-0131 | QAG |  | Sandbox Testing End (UIT) - LDSO Participants | 100% | Thu 22/01/26 | Thu 22/01/26 | 0 days | Thu 22/01/26 | Thu 22/01/26 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
4 | 1.4.4.3 |  |  | QAG |  | Sandbox Testing Execution (UIT) - Supplier & Agent Participants | 26% | Mon 01/09/25 | Fri 28/08/26 | 260 days | Mon 01/09/25 | Fri 28/08/26 | 0 days | 0 days | -56 days | N/A |  | 6.15 | Yes
5 | 1.4.4.3.1 | T3 | T3-QU-0132 | QAG |  | UIT E2E Sandbox Preparation Complete - Supplier and Agent | 100% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | 1 day | 0 days | 0 days | SI Test |  | 6.28 | Yes
5 | 1.4.4.3.2 | T3 | T3-QU-0126 | QAG | MHHS-ART018 MHHS-ART154 MHHS-ART147 | Sandbox Testing Start (UIT) - Supplier & Agent Participants | 100% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
5 | 1.4.4.3.3 |  |  | QAG |  | Sandbox Testing Execution (UIT) - Supplier & Agent Participants | 26% | Mon 01/09/25 | Fri 28/08/26 | 260 days | Mon 01/09/25 | Fri 28/08/26 | 0 days | 0 days | -56 days | PP |  | 6.25 | Yes
5 | 1.4.4.3.4 |  | T3-QU-0127 | QAG |  | Sandbox Testing End (UIT) - Supplier & Agent Participants | 0% | Fri 28/08/26 | Fri 28/08/26 | 0 days | Fri 28/08/26 | Fri 28/08/26 | 1 day | 0 days | 0 days | SI Test |  | 6.25 | Yes
3 | 1.4.5 |  |  | SITAG |  | System Integration Testing - Tier 1 Milestones | 100% | Tue 28/05/24 | Wed 24/12/25 | 411 days? | Fri 28/02/25 | Wed 24/12/25 | -197 days | 0 days | 411 days? |  |  | 6.15 | Yes
4 | 1.4.5.1 | T3 |  | PSG |  | M10 Checkpoint 1 | 100% | Mon 06/01/25 | Wed 02/04/25 | 63 days? | Fri 28/02/25 | Fri 28/02/25 | -39 days | 23 days | 63 days? | CPT |  | 6.1 | Yes
5 | 1.4.5.1.1 |  |  | PSG |  | M10 Readiness | 100% | Mon 06/01/25 | Fri 14/03/25 | 50 days? | Mon 06/01/25 | Fri 14/03/25 | 0 days | 0 days | 50 days? | CPT |  | 6.18 | Yes
6 | 1.4.5.1.1.1 |  |  | PSG |  | Define guiding principles and approach | 100% | Mon 06/01/25 | Fri 24/01/25 | 15 days? | Mon 06/01/25 | Fri 24/01/25 | 0 days | 0 days | 15 days? | CPT |  | 6.18 | Yes
6 | 1.4.5.1.1.2 |  |  | PSG |  | Engage IPA | 100% | Mon 13/01/25 | Fri 24/01/25 | 10 days | Mon 13/01/25 | Fri 24/01/25 | 0 days | 0 days | 10 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.1.3 |  |  | PSG |  | Mobilise Get to Go-Live Group | 100% | Mon 27/01/25 | Fri 07/02/25 | 10 days | Mon 27/01/25 | Fri 07/02/25 | 0 days | 0 days | 10 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.1.4 |  |  | PSG |  | Progress against the M10 Readiness Criteria | 100% | Mon 10/02/25 | Fri 14/03/25 | 25 days? | Mon 10/02/25 | Fri 14/03/25 | 0 days | 0 days | 25 days? | CPT |  | 6.18 | Yes
5 | 1.4.5.1.2 |  |  | PSG |  | Downstream milestone feasibility assessment | 100% | Mon 06/01/25 | Fri 14/03/25 | 50 days? | Mon 06/01/25 | Fri 14/03/25 | 0 days | 0 days | 50 days? | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.1 |  |  | PSG |  | Define guiding principles and approach to addressing points 1 - 3 | 100% | Mon 06/01/25 | Fri 31/01/25 | 20 days? | Mon 06/01/25 | Fri 31/01/25 | 0 days | 0 days | 20 days? | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.2 |  |  | PSG |  | Assess capacity within migration envelopes (Point 1 - Bringing M15 forwards) | 100% | Mon 20/01/25 | Fri 14/02/25 | 20 days | Mon 20/01/25 | Fri 14/02/25 | 0 days | 0 days | 20 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.3 |  |  | PSG |  | Review M16 process (Point 3 - Bringing M16 forwards) | 100% | Mon 20/01/25 | Fri 21/02/25 | 25 days? | Mon 20/01/25 | Fri 21/02/25 | 0 days | 0 days | 25 days? | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.4 |  |  | PSG |  | Develop M16 process review findings | 100% | Mon 24/02/25 | Fri 07/03/25 | 10 days | Mon 24/02/25 | Fri 07/03/25 | 0 days | 0 days | 10 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.5 |  |  | PSG |  | Agree M16 process review findings with Code Bodies | 100% | Mon 10/03/25 | Fri 14/03/25 | 5 days | Mon 10/03/25 | Fri 14/03/25 | 0 days | 0 days | 5 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.6 |  |  | PSG |  | Agree M16 process review findings with PAB | 100% | Mon 10/03/25 | Fri 14/03/25 | 5 days | Mon 10/03/25 | Fri 14/03/25 | 0 days | 0 days | 5 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.2.7 |  |  | PSG |  | Run PPIR with impacted parties (Point 2 - Bringing M14 forwards) | 100% | Mon 03/03/25 | Fri 14/03/25 | 10 days | Mon 03/03/25 | Fri 14/03/25 | 0 days | 0 days | 10 days | CPT |  | 6.18 | Yes
5 | 1.4.5.1.3 |  |  | PSG |  | Checkpoint governance | 100% | Wed 05/03/25 | Wed 02/04/25 | 21 days | Mon 31/10/22 | Wed 02/04/25 | 612 days | 0 days | 21 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.1 |  |  | PSG |  | PSG Updated on progress | 100% | Wed 05/03/25 | Wed 05/03/25 | 0 days | Wed 05/03/25 | Wed 05/03/25 | 0 days | -1 day | 0 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.2 |  |  | PSG |  | Review final M10 Readiness outputs with IPA | 100% | Mon 17/03/25 | Fri 21/03/25 | 5 days | Mon 17/03/25 | Fri 21/03/25 | 0 days | 0 days | 5 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.3 |  |  | PSG |  | Review final M10 Readiness outputs with Ofgem | 100% | Mon 17/03/25 | Wed 26/03/25 | 8 days | Mon 17/03/25 | Wed 26/03/25 | 0 days | 0 days | 8 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.4 |  |  | PSG |  | QAG paper day | 100% | Thu 13/03/25 | Thu 13/03/25 | 0 days | Thu 13/03/25 | Thu 13/03/25 | 0 days | -1 day | 0 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.5 |  |  | PSG |  | QAG recommend M10 Checkpoint | 100% | Thu 20/03/25 | Thu 20/03/25 | 0 days | Thu 20/03/25 | Thu 20/03/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.6 |  |  | PSG |  | MCAG paper day | 100% | Mon 24/03/25 | Mon 24/03/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.7 |  |  | PSG |  | MCAG recommend M10 Checkpoint | 100% | Tue 01/04/25 | Tue 01/04/25 | 0 days | Tue 01/04/25 | Tue 01/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.8 |  |  | PSG |  | PSG paper day | 100% | Wed 26/03/25 | Wed 26/03/25 | 0 days | Wed 26/03/25 | Wed 26/03/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
6 | 1.4.5.1.3.9 |  |  | PSG |  | PSG M10 Checkpoint Meeting | 100% | Wed 02/04/25 | Wed 02/04/25 | 0 days | Wed 02/04/25 | Wed 02/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
5 | 1.4.5.1.4 | T3 | T3-MI-0040 | PSG |  | M10 Checkpoint 1 complete | 100% | Wed 02/04/25 | Wed 02/04/25 | 0 days | Wed 02/04/25 | Wed 02/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
4 | 1.4.5.2 |  | T3-MI-0046 | PSG |  | M10 Checkpoint 2 Complete | 100% | Wed 02/07/25 | Wed 02/07/25 | 0 days | Wed 02/07/25 | Wed 02/07/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
4 | 1.4.5.3 |  |  | PSG |  | M10 Acceptance Criteria | 100% | Tue 28/05/24 | Fri 10/10/25 | 358 days | Tue 28/05/24 | Fri 10/10/25 | 1 day | 0 days | 358 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.1 |  |  | PSG |  | End of SIT MVC testing | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.2 |  |  | PSG |  | IPA M10 Assurance Report developed and agreed | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.3 |  |  | PSG |  | Non-SIT LDSO Qualification Testing complete | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.4 |  |  | PSG |  | A minimum of 1 supplier & required contracted agents are qualified and ready to operate under new MHHS arrangements | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.5 |  |  | PSG |  | All LDSOs qualified | 100% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Wed 10/09/25 | Wed 10/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.6 |  |  | PSG |  | All pre-migration data cleanse activities complete | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | CPT |  | 6.33 | Yes
5 | 1.4.5.3.7 |  |  | PSG |  | All data migration activities set out in the cutover plan complete | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.8 |  |  | PSG |  | ISD fully populated by Elexon | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.9 |  |  | PSG |  | Significant Code Review Powers (SCR) enacted by Ofgem (M7) and updates to regulatory code ready to be implemented at M8 | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.10 |  |  | PSG |  | Migration Schedule approved | 100% | Tue 19/08/25 | Tue 19/08/25 | 0 days | Tue 19/08/25 | Tue 19/08/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.11 |  |  | PSG |  | Migration Framework approved | 100% | Wed 30/04/25 | Wed 30/04/25 | 0 days | Wed 30/04/25 | Wed 30/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.12 |  |  | PSG |  | Migration Control Centre (MCC) delegation of authority approved | 100% | Wed 30/04/25 | Wed 30/04/25 | 0 days | Wed 30/04/25 | Wed 30/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.13 |  |  | PSG |  | Migration incentives implemented | 100% | Wed 30/04/25 | Wed 30/04/25 | 0 days | Wed 30/04/25 | Wed 30/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.14 |  |  | PSG |  | MCC tested and ready to operate | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.15 |  |  | PSG |  | Service Delivery Operating Model in place | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.16 |  |  | PSG |  | Service Delivery Operating Model in place (Self-Certification) | 100% | Thu 03/07/25 | Thu 03/07/25 | 0 days | Thu 03/07/25 | Thu 03/07/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.17 |  |  | PSG |  | Early Life Support Model defined | 100% | Tue 29/04/25 | Tue 29/04/25 | 0 days | Tue 29/04/25 | Tue 29/04/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.18 |  |  | PSG |  | Early Life Support Model arrangements in place and operational | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.19 |  |  | PSG |  | Early Life Support Model arrangements in place and operational (Self-Certification) | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.20 |  |  | PSG |  | M10/M11 Cutover Plan in place | 100% | Tue 28/05/24 | Tue 28/05/24 | 0 days | Tue 28/05/24 | Tue 28/05/24 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.21 |  |  | PSG |  | Central Programme Party Cutover Plans in place | 100% | Tue 15/07/25 | Tue 15/07/25 | 0 days | Tue 15/07/25 | Tue 15/07/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.22 |  |  | PSG |  | Production environment in place for LDSOs and Central Parties | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.23 |  |  | PSG |  | Service activation complete to DIP Production environment for Central Parties and LDSOs | 100% | Fri 10/10/25 | Fri 10/10/25 | 0 days | Fri 10/10/25 | Fri 10/10/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.24 |  |  | PSG |  | Cutover Plan executed | 100% | Tue 23/09/25 | Tue 23/09/25 | 0 days | Tue 23/09/25 | Tue 23/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.25 |  |  | PSG |  | M10 Risk Assessment undertaken | 100% | Wed 03/09/25 | Wed 03/09/25 | 0 days | Wed 03/09/25 | Wed 03/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.26 |  |  | PSG |  | Roles and responsibilities post-M10 agreed and accepted | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.27 |  |  | PSG |  | M10 Work off plan agreed (if required) | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.28 |  |  | PSG |  | Qualification Operating Model in place and operational for all post-M10 activities | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.29 |  |  | PSG |  | Programme Governance updated to reflect required changes to support Programme delivery post-M10. | 100% | Wed 03/09/25 | Wed 03/09/25 | 0 days | Wed 03/09/25 | Wed 03/09/25 | 0 days | -1 day | 0 days | CPT |  | 6.32 | Yes
5 | 1.4.5.3.30 |  |  | PSG |  | All Suppliers and Agents have made the necessary changes to support losing an MPAN via the Forward Migration Process and gaining an MPAN via the Reverse Migration Process. | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.31 |  |  | PSG |  | Performance Assurance measures are understood and in place to maintain BAU performance during the Migration period. | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
5 | 1.4.5.3.32 |  |  | PSG |  | Programme monitoring, assurance and escalation process for beyond M10 is in place and operational | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.22 | Yes
4 | 1.4.5.4 | T1 | T1-MI-1000 | PSG |  | Central systems ready for migrating MPANs (M10) | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.26 | Yes
4 | 1.4.5.5 | T3 | T3-MI-0047 | PSG |  | M10 Acceptance Criteria Ratification | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.26 | Yes
4 | 1.4.5.6 | T1 | T2-MI-1500 | PSG |  | Central systems ready for migrating MPANs (M10*) - Late Exit | 100% | Wed 24/12/25 | Wed 24/12/25 | 0 days | Wed 24/12/25 | Wed 24/12/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes |  | 06/01/26 - Not required as M10 was met
3 | 1.4.6 |  |  |  |  | External Programme Dependency Management | 100% | Mon 31/10/22 | Fri 30/06/23 | 174 days | Mon 31/10/22 | Fri 30/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.4.6.1 |  |  |  |  | BSC CP1558 | 100% | Mon 31/10/22 | Thu 29/06/23 | 173 days | Mon 31/10/22 | Thu 29/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.6.1.1 |  |  |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Wed 28/06/23 | 173 days | Mon 31/10/22 | Wed 28/06/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.6.1.2 |  |  |  |  | BSC CP1558 Implementation Date | 100% | Thu 29/06/23 | Thu 29/06/23 | 0 days | Thu 29/06/23 | Thu 29/06/23 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
4 | 1.4.6.2 |  |  |  |  | REC CP R0032 | 100% | Mon 31/10/22 | Fri 30/06/23 | 174 days | Mon 31/10/22 | Fri 30/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.6.2.1 |  |  |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Thu 29/06/23 | 174 days | Mon 31/10/22 | Thu 29/06/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.6.2.2 |  |  |  |  | REC CP R0032 Implementation Date | 100% | Fri 30/06/23 | Fri 30/06/23 | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
4 | 1.4.6.3 |  |  |  |  | REC CP R0044 | 100% | Mon 31/10/22 | Thu 29/06/23 | 173 days | Mon 31/10/22 | Thu 29/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.6.3.1 |  |  |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Wed 28/06/23 | 173 days | Mon 31/10/22 | Wed 28/06/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.6.3.2 |  |  |  |  | REC CP R0044 Implementation Date | 100% | Thu 29/06/23 | Thu 29/06/23 | 0 days | Thu 29/06/23 | Thu 29/06/23 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
2 | 1.5 |  |  | QAG |  | NON SIT LDSO QUALIFICATION | 100% | Tue 07/11/23 | Fri 22/08/25 | 469 days? | Tue 07/11/23 | Fri 22/08/25 | 0 days | 0 days | 126 days? | N/A |  |  | Yes
3 | 1.5.1 |  |  |  |  | Approach Planning | 100% | Tue 07/11/23 | Thu 22/08/24 | 208 days | Tue 07/11/23 | Thu 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.1.1 |  |  |  |  | Develop Draft Testing Approach & Plan | 100% | Tue 07/11/23 | Tue 30/01/24 | 61 days | Tue 07/11/23 | Tue 30/01/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.2 |  |  |  |  | Draft Testing Approach & Plan Issued to LDSO for Review | 100% | Wed 31/01/24 | Wed 31/01/24 | 1 day | Wed 31/01/24 | Wed 31/01/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.3 |  |  |  |  | LDSO Review Complete | 100% | Thu 01/02/24 | Wed 14/02/24 | 10 days | Thu 01/02/24 | Wed 14/02/24 | 0 days | 0 days | 0 days | LDSOs |  | 5.24 | Yes
4 | 1.5.1.4 |  |  |  |  | Update Following LDSO Review | 100% | Thu 15/02/24 | Tue 05/03/24 | 14 days | Thu 15/02/24 | Tue 05/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.5 |  |  |  |  | QWG Review of Approach & Plan | 100% | Tue 12/03/24 | Tue 12/03/24 | 1 day | Tue 12/03/24 | Tue 12/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.1.6 |  |  |  |  | QAG Approval for Approach & Plan | 100% | Thu 21/03/24 | Thu 21/03/24 | 0 days | Thu 21/03/24 | Thu 21/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.1.7 | T3 | T3-QU-0011 | QAG (Non-SIT LDSO) |  | Confirmation of Participants for Non-SIT LDSO Qualification Testing | 100% | Thu 21/03/24 | Thu 21/03/24 | 0 days | Thu 21/03/24 | Thu 21/03/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.8 |  |  |  |  | Update to Annex 1 for internal review (NF, Not Operational) | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | Mon 18/03/24 | Fri 05/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.9 |  |  |  |  | Non-Functional, Operational & Migration Approaches Socialised with Code Bodies & LDSO & Feedback Actioned | 100% | Mon 08/04/24 | Mon 05/08/24 | 86 days | Mon 08/04/24 | Mon 05/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.1.10 |  |  |  |  | QWG Review Operational, Non-Functional & Migration Annexes of Approach & Plan | 100% | Tue 13/08/24 | Tue 13/08/24 | 1 day | Tue 13/08/24 | Tue 13/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.27 | Yes
4 | 1.5.1.11 |  |  |  |  | Update Following QWG Review | 100% | Wed 14/08/24 | Wed 21/08/24 | 6 days | Wed 14/08/24 | Wed 21/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.27 | Yes
4 | 1.5.1.12 | T3 | T3-QU-0110 | QAG (Non-SIT LDSO) |  | QAG Approval for Operational, Non-Functional & Migration Annexes of Approach & Plan | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.29 | Yes
3 | 1.5.2 |  |  |  |  | Functional Test Cases & Scenarios | 100% | Tue 30/01/24 | Thu 18/04/24 | 58 days | Tue 30/01/24 | Thu 18/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.2.1 |  |  |  |  | Functional Test Cases & Scenarios Batch 1 | 100% | Tue 30/01/24 | Thu 08/02/24 | 8 days | Tue 30/01/24 | Thu 08/02/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.1.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 1 with Code Bodies | 100% | Tue 30/01/24 | Tue 30/01/24 | 1 day | Tue 30/01/24 | Tue 30/01/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.1.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 1 with LDSO | 100% | Thu 01/02/24 | Thu 01/02/24 | 1 day | Thu 01/02/24 | Thu 01/02/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.1.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 1 | 100% | Fri 02/02/24 | Thu 08/02/24 | 5 days | Fri 02/02/24 | Thu 08/02/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.2 |  |  |  |  | Functional Test Cases & Scenarios Batch 2 | 100% | Tue 20/02/24 | Fri 08/03/24 | 14 days | Tue 20/02/24 | Fri 08/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.2.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 2 with Code Bodies | 100% | Tue 20/02/24 | Tue 20/02/24 | 1 day | Tue 20/02/24 | Tue 20/02/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.2.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 2 with LDSO | 100% | Fri 01/03/24 | Fri 01/03/24 | 1 day | Fri 01/03/24 | Fri 01/03/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.2.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 2 | 100% | Mon 04/03/24 | Fri 08/03/24 | 5 days | Mon 04/03/24 | Fri 08/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.3 |  |  |  |  | Functional Test Cases & Scenarios Batch 3 | 100% | Wed 20/03/24 | Fri 05/04/24 | 13 days | Wed 20/03/24 | Fri 05/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.3.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 3 with Code Bodies | 100% | Wed 20/03/24 | Wed 20/03/24 | 1 day | Wed 20/03/24 | Wed 20/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.3.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 3 with LDSO | 100% | Thu 28/03/24 | Thu 28/03/24 | 1 day | Thu 28/03/24 | Thu 28/03/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.3.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 3 | 100% | Fri 29/03/24 | Fri 05/04/24 | 6 days | Fri 29/03/24 | Fri 05/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.4 |  |  |  |  | Test Cases & Scenarios Batch 1-3 Discussion at QWG | 100% | Tue 09/04/24 | Tue 09/04/24 | 1 day | Tue 09/04/24 | Tue 09/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.2.5 |  |  |  |  | Action QWG Feedback on Test Cases & Scenarios Batch 1-3 | 100% | Wed 10/04/24 | Thu 11/04/24 | 2 days | Wed 10/04/24 | Thu 11/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.6 | T3 | T3-QU-0069 | QAG (Non-SIT LDSO) |  | Batch 1-3 Non-SIT LDSO QT Functional Test Scenarios and Test Cases approved | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
3 | 1.5.3 |  |  |  |  | Test Execution Schedule | 100% | Fri 19/04/24 | Fri 29/11/24 | 161 days | Fri 19/04/24 | Fri 29/11/24 | 0 days | 0 days | 71 days | N/A |  | 5.24 | Yes
4 | 1.5.3.1 |  |  |  |  | Draft Test Delivery Schedule for Functional and Operational Testing | 100% | Fri 19/04/24 | Thu 16/05/24 | 20 days | Fri 19/04/24 | Thu 16/05/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.3.2 |  |  |  |  | Socialise Test Delivery Schedule with Code Bodies & LDSO for Review & Action Feedback | 100% | Fri 17/05/24 | Mon 08/07/24 | 37 days | Fri 17/05/24 | Mon 08/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.3.3 |  |  |  |  | Agree Test Execution Timetable Format at QWG, Including Anonymisation Requirements | 100% | Tue 09/07/24 | Tue 09/07/24 | 1 day | Tue 09/07/24 | Tue 09/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.3.4 |  |  |  |  | Action QWG Feedback | 100% | Wed 10/07/24 | Fri 12/07/24 | 3 days | Wed 10/07/24 | Fri 12/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.3.5 | T3 | T3-QU-0111 | QAG (Non-SIT LDSO) |  | Agree Test Execution Timetable Format at QAG, Including Anonymisation Requirements | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.29 | Yes
4 | 1.5.3.6 | T3 | T3-QU-0008 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Execution Schedule Complete | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
3 | 1.5.4 |  |  |  |  | Functional, Non-Functional, Operational & Migration Test Scenarios & Cases | 100% | Fri 22/03/24 | Thu 22/08/24 | 110 days | Fri 22/03/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.4.1 |  |  |  |  | Test Scenarios & Cases - Functional - Drafted, Reviewed | 100% | Mon 01/04/24 | Thu 18/04/24 | 14 days | Mon 01/04/24 | Thu 18/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.2 | T3 | T3-QU-0070 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases- Functional - Approved at QAG | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.3 |  |  |  |  | Test Scenarios & Cases - Non-Functional - Drafted, Reviewed | 100% | Fri 22/03/24 | Thu 22/08/24 | 110 days | Fri 22/03/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.4 | T3 | T3-QU-0071 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Non-Functional - Approved at QAG | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
4 | 1.5.4.5 |  |  |  |  | Test Scenarios & Cases - Migration - Drafted, Reviewed | 100% | Fri 22/03/24 | Thu 23/05/24 | 45 days | Fri 22/03/24 | Thu 23/05/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.6 | T3 | T3-QU-0072 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Migration - Approved at QAG | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.7 |  |  |  |  | Test Scenarios & Cases - Operational - Drafted, Reviewed | 100% | Mon 03/06/24 | Thu 22/08/24 | 59 days | Mon 03/06/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.8 | T3 | T3-QU-0073 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Operational - Approved at QAG | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
3 | 1.5.5 |  |  |  |  | Test Data | 100% | Mon 22/01/24 | Fri 16/05/25 | 345 days | Mon 22/01/24 | Fri 16/05/25 | 0 days | 0 days | 104 days | N/A |  | 5.24 | Yes
4 | 1.5.5.1 |  |  |  |  | Test Data Plan Drafted & Reviewed | 100% | Mon 22/01/24 | Thu 23/05/24 | 89 days | Mon 22/01/24 | Thu 23/05/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.5.2 | T3 | T3-QU-0074 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO QT Test Data Plan Approved by QAG | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.5.3 |  |  |  |  | Develop Test Data Matrices | 100% | Fri 24/05/24 | Thu 06/06/24 | 10 days | Fri 24/05/24 | Thu 06/06/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.4 |  |  |  |  | Test Data Cut | 100% | Fri 24/05/24 | Mon 17/06/24 | 17 days | Fri 24/05/24 | Mon 17/06/24 | 0 days | 0 days | 0 days | PP, Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.5 | T3 | T3-QU-0112 | QAG (Non-SIT LDSO) |  | Test Data Cut Complete | 100% | Mon 17/06/24 | Mon 17/06/24 | 0 days | Mon 17/06/24 | Mon 17/06/24 | 1 day | 0 days | 0 days | PP, Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.5.6 |  |  |  |  | Test Data Reviewed by the Programme | 100% | Tue 18/06/24 | Fri 09/08/24 | 39 days | Tue 18/06/24 | Fri 09/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.7 |  |  |  |  | Test Data Loaded | 100% | Mon 12/08/24 | Fri 06/12/24 | 85 days | Mon 12/08/24 | Fri 06/12/24 | 0 days | 0 days | 68 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.8 | T3 | T3-QU-0113 | QAG (Non-SIT LDSO) |  | Test Data Signed Off | 100% | Fri 06/12/24 | Fri 06/12/24 | 0 days | Fri 06/12/24 | Fri 06/12/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.25 | Yes
4 | 1.5.5.9 |  |  |  |  | Test Execution Data Support | 100% | Mon 09/12/24 | Fri 16/05/25 | 115 days | Mon 09/12/24 | Fri 16/05/25 | 0 days | 0 days | 36 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.6 |  |  |  |  | Tooling | 100% | Wed 31/01/24 | Fri 23/08/24 | 148 days | Wed 31/01/24 | Fri 23/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.6.1 |  |  |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 100% | Wed 31/01/24 | Fri 12/04/24 | 53 days | Wed 31/01/24 | Fri 12/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.6.2 |  |  |  |  | Develop Training Requirements & Materials Inc. Day in the Life | 100% | Mon 15/04/24 | Tue 13/08/24 | 87 days | Mon 15/04/24 | Tue 13/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.6.3 |  |  |  |  | ADO Launch complete | 100% | Fri 23/08/24 | Fri 23/08/24 | 1 day | Fri 23/08/24 | Fri 23/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.7 |  |  |  |  | Pre-Integration Testing | 100% | Wed 31/01/24 | Fri 31/01/25 | 263 days | Wed 31/01/24 | Fri 29/11/24 | 0 days | 45 days | 89 days | N/A |  | 5.24 | Yes
4 | 1.5.7.1 |  |  |  |  | PIT Guidance & Templates & Approach & Plans Developed | 100% | Mon 05/02/24 | Mon 01/07/24 | 106 days | Mon 05/02/24 | Mon 01/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.7.2 | T3 | T3-QU-0075 | QAG (Non-SIT LDSO) |  | PIT Test Approach & Plan Deadline for Submission for Non-SIT LDSO​ QT | 100% | Mon 01/07/24 | Mon 01/07/24 | 0 days | Mon 01/07/24 | Mon 01/07/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.28 | Yes
4 | 1.5.7.3 |  |  |  |  | Develop and agree PIT Test Scenarios | 100% | Tue 02/07/24 | Mon 29/07/24 | 20 days | Tue 02/07/24 | Mon 29/07/24 | 0 days | 0 days | -11 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.4 |  |  |  |  | PIT Execution (Functional and Migration) | 100% | Mon 30/09/24 | Fri 29/11/24 | 45 days | Mon 30/09/24 | Fri 29/11/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.5 |  |  |  |  | PIT Execution (Non-Functional and Operational) | 100% | Mon 23/09/24 | Fri 31/01/25 | 95 days | Mon 23/09/24 | Fri 31/01/25 | 0 days | 0 days | 95 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.6 | T3 | T3-QU-0076 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Participants have submitted functional PIT Test Completion Report & evidence for QT Entry​ | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.7 |  |  |  |  | Non-SIT LDSO Participants have submitted non-functional PIT Test Completion Report | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.8 |  |  |  |  | Placing Reliance - Code Body & LDSO Functional and Migration | 100% | Wed 31/01/24 | Thu 22/08/24 | 147 days | Wed 31/01/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.7.8.1 |  |  |  |  | Placing Reliance Submitted & Reviewed | 100% | Wed 31/01/24 | Wed 28/02/24 | 21 days | Wed 31/01/24 | Wed 28/02/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.8.2 |  |  |  |  | Define & Agree QT Testing for Each LDSO | 100% | Thu 29/02/24 | Fri 29/03/24 | 22 days | Thu 29/02/24 | Fri 29/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.8.3 |  |  |  |  | Develop Test Scope & Reliance Submissions | 100% | Mon 01/04/24 | Fri 26/04/24 | 20 days | Mon 01/04/24 | Fri 26/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.8.4 |  |  |  |  | Review and Consultation | 100% | Mon 29/04/24 | Thu 22/08/24 | 84 days | Mon 29/04/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.7.9 |  |  |  |  | Placing Reliance - Code Body & LDSO Non Functional and Operational | 100% | Mon 17/06/24 | Thu 22/08/24 | 49 days | Mon 17/06/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.25 | Yes
5 | 1.5.7.9.1 |  |  |  |  | Placing Reliance Submitted & Reviewed | 100% | Mon 17/06/24 | Tue 30/07/24 | 32 days | Mon 17/06/24 | Tue 30/07/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.27 | Yes
5 | 1.5.7.9.2 |  |  |  |  | Review and Consultation | 100% | Wed 31/07/24 | Thu 22/08/24 | 17 days | Wed 31/07/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
5 | 1.5.7.9.3 | T3 | T3-QU-0077 | QAG (Non-SIT LDSO) |  | PP Test Scope Presented at QAG | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
3 | 1.5.8 |  |  |  |  | LDSO Test Readiness Reporting | 100% | Fri 19/04/24 | Fri 26/07/24 | 71 days | Fri 19/04/24 | Fri 26/07/24 | 0 days | 0 days | -47 days | N/A |  | 5.24 | Yes
4 | 1.5.8.1 |  |  |  |  | Interim Test Readiness Report & Plan Developed & Reviewed | 100% | Fri 19/04/24 | Fri 26/07/24 | 71 days | Fri 19/04/24 | Fri 26/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, LDSO |  | 5.24 | Yes
4 | 1.5.8.2 | T3 | T3-QU-0114 | QAG (Non-SIT LDSO) |  | Test Plan Submission to MHHS Programme For Review | 100% | Fri 26/07/24 | Fri 26/07/24 | 0 days | Fri 26/07/24 | Fri 26/07/24 | 1 day | 0 days | 0 days | LDSO |  | 5.3 | Yes
3 | 1.5.9 |  |  |  |  | Test Environment | 100% | Wed 17/04/24 | Fri 29/11/24 | 163 days | Wed 17/04/24 | Fri 29/11/24 | 0 days | 0 days | 52 days | N/A |  | 5.24 | Yes
4 | 1.5.9.1 |  |  |  |  | Define Test Harness Requirements and Sign-Off with SRO | 100% | Wed 17/04/24 | Fri 03/05/24 | 13 days | Wed 17/04/24 | Fri 03/05/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.9.2 |  |  |  |  | Central System (DIP Env & Helix Test Harness) Test Environment DBT | 100% | Wed 17/04/24 | Fri 29/11/24 | 163 days | Wed 17/04/24 | Fri 29/11/24 | 0 days | 0 days | 71 days | LDSO |  | 5.24 | Yes
4 | 1.5.9.3 |  |  |  |  | Coordinate LDSO Environment Preparation | 100% | Fri 12/07/24 | Fri 29/11/24 | 101 days | Fri 12/07/24 | Fri 29/11/24 | 0 days | 0 days | 71 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.9.4 |  |  |  |  | DIP available for Onboarding | 100% | Thu 01/08/24 | Thu 01/08/24 | 1 day | Thu 01/08/24 | Thu 01/08/24 | 0 days | 0 days | 0 days | Test Env |  | 5.24 | Yes
4 | 1.5.9.5 | T3 | T3-QU-0009 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs Participants' environments) Ready to start DIP onboarding (incl. certificates and security compliance) | 100% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Mon 05/08/24 | Mon 05/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.3 | Yes
4 | 1.5.9.6 | T3 | T3-QU-0078 | QAG (Non-SIT LDSO) |  | LDSO Test Environments Connection Confirmed to UIT Environment | 100% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.10 |  |  |  |  | Test Readiness | 100% | Tue 02/07/24 | Fri 20/12/24 | 124 days | Tue 02/07/24 | Fri 20/12/24 | 0 days | 0 days | 48 days | N/A |  | 5.24 | Yes
4 | 1.5.10.1 |  |  |  |  | Preparation for Interim Test Readiness Report | 100% | Tue 02/07/24 | Fri 26/07/24 | 19 days | Tue 02/07/24 | Fri 26/07/24 | 0 days | 0 days | -11 days | LDSO |  | 5.24 | Yes
4 | 1.5.10.2 | T3 | T3-QU-0116 | QAG (Non-SIT LDSO) |  | Interim Test Readiness Report Submission to MHHS Programme for Review | 100% | Fri 26/07/24 | Fri 26/07/24 | 0 days | Fri 26/07/24 | Fri 26/07/24 | 1 day | 0 days | 0 days | LDSO |  | 5.25 | Yes
4 | 1.5.10.3 |  |  |  |  | LDSO Update Readiness Report & Final Assurance by Programme | 100% | Mon 29/07/24 | Thu 12/12/24 | 99 days | Mon 29/07/24 | Thu 12/12/24 | 0 days | 0 days | 74 days | Non-SIT LDSO, LDSO |  | 5.24 | Yes
4 | 1.5.10.4 |  |  |  |  | Final Test Readiness Report Submitted to MHHS Programme | 100% | Fri 13/12/24 | Fri 13/12/24 | 1 day | Fri 13/12/24 | Fri 13/12/24 | 0 days | 0 days | 0 days | LDSO |  | 5.24 | Yes
4 | 1.5.10.5 |  |  |  |  | Final Programme Assurance of LDSO Test Readiness | 100% | Fri 13/12/24 | Fri 20/12/24 | 6 days | Fri 13/12/24 | Fri 20/12/24 | 0 days | 0 days | -15 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.10.6 | T3 | T3-QU-0007 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Programme Test Readiness confirmed | 100% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.10.7 | T2 | T2-QU-0550 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed (Final Test Readiness Review for LDSO) | 100% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1 day | 0 days | 0 days | LDSO |  | 5.24 | Yes
3 | 1.5.11 |  |  | QAG (Non-SIT LDSO) |  | Test Window | 100% | Mon 06/01/25 | Fri 22/08/25 | 165 days? | Mon 06/01/25 | Fri 16/05/25 | 0 days | 70 days | 106 days? | N/A |  | 6 | Yes
4 | 1.5.11.1 |  |  | QAG (Non-SIT LDSO) |  | All Non-SIT LDSOs Qualification Testing | 100% | Mon 06/01/25 | Fri 16/05/25 | 94 days | Mon 06/01/25 | Fri 16/05/25 | 0 days | -1 day | 35 days | LDSO |  | 6 | Yes
5 | 1.5.11.1.1 | T3 | T3-QU-0115 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO QT Test Execution Starts | 100% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Mon 06/01/25 | Mon 06/01/25 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 6 | Yes
5 | 1.5.11.1.2 |  |  | QAG (Non-SIT LDSO) |  | LDSO Alpha | 100% | Mon 06/01/25 | Mon 05/05/25 | 86 days | Mon 06/01/25 | Mon 05/05/25 | 0 days | 0 days | 86 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.3 |  |  | QAG (Non-SIT LDSO) |  | LDSO Bravo | 100% | Mon 06/01/25 | Mon 05/05/25 | 86 days | Mon 06/01/25 | Mon 05/05/25 | 0 days | 0 days | 86 days | LDSO |  | 6.21 | Yes
5 | 1.5.11.1.4 |  |  | QAG (Non-SIT LDSO) |  | LDSO Charlie | 100% | Mon 06/01/25 | Wed 07/05/25 | 88 days | Mon 06/01/25 | Wed 07/05/25 | 0 days | 0 days | 88 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.5 |  |  | QAG (Non-SIT LDSO) |  | LDSO Delta | 100% | Mon 06/01/25 | Wed 30/04/25 | 83 days | Mon 06/01/25 | Wed 30/04/25 | 0 days | 0 days | 83 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.6 |  |  | QAG (Non-SIT LDSO) |  | LDSO Echo | 100% | Mon 06/01/25 | Thu 10/04/25 | 69 days | Mon 06/01/25 | Thu 10/04/25 | 0 days | 0 days | 69 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.7 |  |  | QAG (Non-SIT LDSO) |  | LDSO Foxtrot | 100% | Mon 20/01/25 | Thu 15/05/25 | 84 days | Mon 20/01/25 | Thu 15/05/25 | 0 days | 0 days | 84 days | LDSO |  | 6.21 | Yes
5 | 1.5.11.1.8 |  |  | QAG (Non-SIT LDSO) |  | LDSO Golf | 100% | Mon 06/01/25 | Fri 25/04/25 | 80 days | Mon 06/01/25 | Fri 25/04/25 | 0 days | 0 days | 80 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.9 |  |  | QAG (Non-SIT LDSO) |  | LDSO Hotel | 100% | Mon 06/01/25 | Mon 05/05/25 | 86 days | Mon 06/01/25 | Mon 05/05/25 | 0 days | 0 days | 86 days | LDSO |  | 6.21 | Yes
5 | 1.5.11.1.10 |  |  | QAG (Non-SIT LDSO) |  | LDSO India | 100% | Mon 06/01/25 | Mon 05/05/25 | 86 days | Mon 06/01/25 | Mon 05/05/25 | 0 days | 0 days | 86 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.11 | T3 | T3-QU-0010 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 0 days | -1 day | 0 days | LDSO |  | 6 | Yes
4 | 1.5.11.2 |  |  | QAG (Non-SIT LDSO) |  | Potential for non-SIT LDSO QT Regression for Qualification | 100% | Mon 19/05/25 | Fri 22/08/25 | 70 days? | Mon 19/05/25 | Fri 22/08/25 | 0 days | 0 days | 70 days? | Non-SIT LDSO |  | 6.12 | Yes
3 | 1.5.12 |  |  | QAG (Non-SIT LDSO) |  | Test Result Assurance | 100% | Fri 04/04/25 | Fri 16/05/25 | 30 days | Mon 21/04/25 | Thu 29/05/25 | -11 days | -10 days | -30 days | N/A |  | 6 | Yes
4 | 1.5.12.1 |  |  | QAG (Non-SIT LDSO) |  | Test Reports Reviewed By MHHS & Code Bodies & Finalised | 100% | Fri 04/04/25 | Fri 16/05/25 | 30 days | Fri 04/04/25 | Fri 16/05/25 | 0 days | -1 day | 14 days | Non-SIT LDSO |  | 6 | Yes
4 | 1.5.12.2 | T3 | T3-QU-0079 | QAG (Non-SIT LDSO) |  | Non-SIT LDSOs submission deadline for their QT Test Completion Report to MHHS Programme | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 0 days | -1 day | 0 days | Non-SIT LDSO |  | 6.23 | Yes
3 | 1.5.13 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Qualification Closure | 100% | Fri 16/05/25 | Fri 27/06/25 | 31 days | Fri 30/05/25 | Fri 22/08/25 | -10 days | -40 days | -18 days | N/A |  | 6 | Yes
4 | 1.5.13.1 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Qualification Learned Captured | 100% | Fri 16/05/25 | Thu 29/05/25 | 10 days | Fri 16/05/25 | Thu 29/05/25 | 0 days | 0 days | -5 days | Non-SIT LDSO |  | 6.23 | Yes
4 | 1.5.13.2 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Regression Testing | 100% | Fri 16/05/25 | Fri 20/06/25 | 26 days | Fri 16/05/25 | Fri 20/06/25 | 0 days | 0 days | 26 days | Non-SIT LDSO |  | 6.23 | Yes
4 | 1.5.13.3 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Qualification Closure Down | 100% | Mon 23/06/25 | Fri 27/06/25 | 5 days | Mon 23/06/25 | Fri 27/06/25 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 6.23 | Yes
2 | 1.6 |  |  | Helix Programme Board |  | HELIX / ELEXON M10 READINESS | 100% | Mon 31/10/22 | Tue 13/01/26 | 837 days? | Mon 03/03/25 | Mon 01/09/25 | -610 days | 96 days | 837 days? | Helix |  | 6.26 | Yes
3 | 1.6.1 |  |  | Helix Programme Board |  | Service Management - M10 Readiness | 100% | Mon 03/03/25 | Wed 24/09/25 | 147 days | Mon 03/03/25 | Mon 01/09/25 | 0 days | 16 days | 147 days | Helix |  | 6.24 | Yes
4 | 1.6.1.1 |  |  | Helix Programme Board |  | Service Model Design (Cross Party Service Desk) | 100% | Mon 03/03/25 | Fri 05/09/25 | 135 days | Mon 03/03/25 | Tue 15/07/25 | 0 days | 38 days | 135 days | Helix |  | 6.24 | Yes
5 | 1.6.1.1.1 |  |  | Helix Programme Board |  | Cross Party Service Desk | 100% | Mon 03/03/25 | Mon 19/05/25 | 55 days | Mon 03/03/25 | Tue 01/07/25 | 0 days | -32 days | 55 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.1.1 |  |  | Helix Programme Board |  | Cross Party Service Desk Definition and Design | 100% | Mon 03/03/25 | Thu 03/04/25 | 24 days | Mon 03/03/25 | Thu 03/04/25 | 0 days | 0 days | 24 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.1.2 |  |  | Helix Programme Board |  | Cross Party Service Desk Design Document MHHS Review | 100% | Thu 03/04/25 | Thu 03/04/25 | 0 days | Thu 03/04/25 | Thu 03/04/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.1.3 |  |  | Helix Programme Board |  | Cross Party Service Desk Model Issued | 100% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.1.4 |  |  | Helix Programme Board |  | Cross Party Service Desk Model Reissued | 100% | Tue 15/04/25 | Tue 15/04/25 | 0 days | Tue 15/04/25 | Tue 15/04/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.1.5 |  |  | Helix Programme Board |  | Cross Party Service Desk Consultation | 100% | Mon 07/04/25 | Mon 19/05/25 | 30 days | Mon 07/04/25 | Tue 01/07/25 | 0 days | -32 days | 30 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.1 |  |  | Helix Programme Board |  | Cross Party Service Desk Consultation | 100% | Mon 07/04/25 | Mon 28/04/25 | 16 days | Mon 07/04/25 | Mon 28/04/25 | 0 days | 0 days | 16 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.2 |  |  | Helix Programme Board |  | Cross Party Service Desk Consultation Completed | 100% | Mon 28/04/25 | Mon 28/04/25 | 0 days | Mon 28/04/25 | Mon 28/04/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.3 |  |  | Helix Programme Board |  | Cross Party Service Desk Model Updates (Feedback Review) | 100% | Tue 29/04/25 | Thu 08/05/25 | 8 days | Tue 29/04/25 | Thu 08/05/25 | 0 days | 0 days | 8 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.4 |  |  | Helix Programme Board |  | Cross Party Service Desk Model Spotlight at Elexon Service Management Steering Group | 100% | Wed 07/05/25 | Wed 07/05/25 | 0 days | Wed 07/05/25 | Wed 07/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.5 |  |  | Helix Programme Board |  | Updated Consultation Documents Shared with MHHS and Industry | 100% | Thu 08/05/25 | Thu 08/05/25 | 0 days | Thu 08/05/25 | Thu 08/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.6 |  |  | Helix Programme Board |  | TORWG Post-Consultation Update (CPSD) | 100% | Wed 14/05/25 | Wed 14/05/25 | 0 days | Wed 14/05/25 | Wed 14/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.7 |  |  | Helix Programme Board |  | Updated Consultation Documents Released to Industry for eTORWG | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.1.1.5.8 |  |  | Helix Programme Board |  | CPSD, Operating Hours & Triage Updates Endorsement (eTORWG) | 100% | Mon 19/05/25 | Mon 19/05/25 | 0 days | Tue 20/05/25 | Tue 20/05/25 | -1 day | -2 days | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.1.6 |  |  | Helix Programme Board |  | Cross Party Service Desk Model Completed | 100% | Mon 19/05/25 | Mon 19/05/25 | 0 days | Tue 20/05/25 | Tue 20/05/25 | -1 day | -2 days | 0 days | Helix |  | 6.24 | Yes
5 | 1.6.1.1.2 |  |  | Helix Programme Board |  | Service Documentation | 100% | Tue 29/04/25 | Wed 13/08/25 | 77 days | Tue 29/04/25 | Tue 15/07/25 | 0 days | 21 days | 77 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.2.1 |  |  | Helix Programme Board |  | Operations Manual Updates Post-Consultation | 100% | Tue 29/04/25 | Thu 15/05/25 | 13 days | Tue 29/04/25 | Thu 15/05/25 | 0 days | 0 days | 13 days | Helix |  | 6.24 | Yes
6 | 1.6.1.1.2.2 |  |  | Helix Programme Board |  | Operations Manual Version 1.3 (TORWG) | 100% | Thu 15/05/25 | Thu 15/05/25 | 0 days | Thu 15/05/25 | Thu 15/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
6 | 1.6.1.1.2.3 |  |  | Helix Programme Board |  | Operations Manual Updates Pre-ORT | 100% | Fri 16/05/25 | Wed 04/06/25 | 14 days | Wed 04/06/25 | Wed 04/06/25 | -13 days | 0 days | 14 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.4 |  |  | Helix Programme Board |  | Operations Manual version 1.4 (ORT) (TORWG Paper Day) | 100% | Wed 04/06/25 | Wed 04/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | -5 days | -6 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.5 |  |  | Helix Programme Board |  | Service User LLSD Updates Post Consultation | 100% | Mon 19/05/25 | Wed 04/06/25 | 13 days | Mon 19/05/25 | Wed 04/06/25 | 0 days | 0 days | 13 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.6 |  |  | Helix Programme Board |  | Service User LLSD Version 1.2 (ORT) (TORWG Paper Day) | 100% | Wed 04/06/25 | Wed 04/06/25 | 0 days | Wed 04/06/25 | Wed 04/06/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.7 |  |  | Helix Programme Board |  | CPSD Scenarios and Runbook | 100% | Tue 29/04/25 | Fri 23/05/25 | 19 days | Tue 29/04/25 | Fri 23/05/25 | 0 days | 0 days | 19 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.8 |  |  | Helix Programme Board |  | CPSD Scenarios and Runbook Shared with MHHS Team for Review | 100% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Fri 23/05/25 | Fri 23/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.9 |  |  | Helix Programme Board |  | CPSD Scenarios and Runbook Review Window | 100% | Mon 26/05/25 | Wed 04/06/25 | 8 days | Mon 26/05/25 | Wed 04/06/25 | 0 days | 0 days | 8 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.10 |  |  | Helix Programme Board |  | CPSD Scenarios and Runbook Released for TORWG (Paper Day) | 100% | Wed 04/06/25 | Wed 04/06/25 | 0 days | Wed 04/06/25 | Wed 04/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.11 |  |  | Helix Programme Board |  | Parent/Child Industry Engagement Session | 100% | Fri 06/06/25 | Fri 06/06/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.12 |  |  | Helix Programme Board |  | CPSD Runbook Completed | 100% | Wed 11/06/25 | Wed 11/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.1.2.13 |  |  | Helix Programme Board |  | Service Documentation V2 | 100% | Mon 14/07/25 | Wed 13/08/25 | 23 days | Mon 14/07/25 | Wed 13/08/25 | 0 days | 0 days | 23 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.1 |  |  | Helix Programme Board |  | Post-ORT Operations Manual and LLSD Updates | 100% | Mon 14/07/25 | Wed 16/07/25 | 3 days | Mon 14/07/25 | Wed 16/07/25 | 0 days | 0 days | 3 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.2 |  |  | Helix Programme Board |  | M10 Operations Manual Version 2.0 & LLSD Issued for Consultation | 100% | Wed 16/07/25 | Wed 16/07/25 | 0 days | Wed 16/07/25 | Wed 16/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.3 |  |  | Helix Programme Board |  | Operations Manual and LLSD v2 Consultation | 100% | Thu 17/07/25 | Wed 30/07/25 | 10 days | Thu 17/07/25 | Wed 30/07/25 | 0 days | 0 days | 10 days | PP |  | 6.28 | Yes
7 | 1.6.1.1.2.13.4 |  |  | Helix Programme Board |  | Operations Manual and LLSD v2 Consultation Completed | 100% | Wed 30/07/25 | Wed 30/07/25 | 0 days | Wed 30/07/25 | Wed 30/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.5 |  |  | Helix Programme Board |  | Consultation Feedback Implemented Operations Manual and LLSD v2 | 100% | Thu 31/07/25 | Wed 06/08/25 | 5 days | Thu 31/07/25 | Wed 06/08/25 | 0 days | 0 days | 5 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.6 |  |  | Helix Programme Board |  | Operations Manual and LLSD v2 Feedback Implemented | 100% | Wed 06/08/25 | Wed 06/08/25 | 0 days | Wed 06/08/25 | Wed 06/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.7 |  |  | Helix Programme Board |  | TORWG Paper Day | 100% | Wed 06/08/25 | Wed 06/08/25 | 0 days | Wed 06/08/25 | Wed 06/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.8 |  |  | Helix Programme Board |  | TORWG Operations Manual and LLSD v2 Approval | 100% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Wed 13/08/25 | Wed 13/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
7 | 1.6.1.1.2.13.9 |  |  | Helix Programme Board |  | Operations Manual and LLSD v2 Approved and Completed | 100% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Wed 13/08/25 | Wed 13/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
5 | 1.6.1.1.3 |  |  | Helix Programme Board |  | LDSO Onboarding - Phase 1 | 100% | Mon 23/06/25 | Wed 30/07/25 | 28 days | Mon 23/06/25 | Wed 30/07/25 | 0 days | 0 days | 28 days | Helix |  | 6.29 | Yes
6 | 1.6.1.1.3.1 |  |  | Helix Programme Board |  | LDSO Communication and Information Gathering - Phase 1 | 100% | Mon 23/06/25 | Wed 16/07/25 | 18 days | Mon 23/06/25 | Fri 11/07/25 | 0 days | 3 days | 18 days | Helix |  | 6.29 | Yes
6 | 1.6.1.1.3.2 |  |  | Helix Programme Board |  | LDSO Communication and Information Gathering Completed - Phase 1 | 100% | Wed 16/07/25 | Wed 16/07/25 | 0 days | Wed 16/07/25 | Wed 16/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.3.3 |  |  | Helix Programme Board |  | LDSO ServiceNow Configuration - Phase 1/2 | 100% | Thu 10/07/25 | Wed 23/07/25 | 10 days | Thu 10/07/25 | Wed 23/07/25 | 0 days | 0 days | 10 days | Helix |  | 6.29 | Yes
6 | 1.6.1.1.3.4 |  |  | Helix Programme Board |  | LDSO ServiceNow Configuration Completed - Phase 1/2 | 100% | Wed 16/07/25 | Wed 16/07/25 | 0 days | Wed 16/07/25 | Wed 16/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.3.5 |  |  | Helix Programme Board |  | LDSO Testing and Further Communication - Phase 1 | 100% | Wed 23/07/25 | Wed 30/07/25 | 6 days | Wed 23/07/25 | Wed 30/07/25 | 0 days | 0 days | 6 days | Helix |  | 6.29 | Yes
6 | 1.6.1.1.3.6 |  |  | Helix Programme Board |  | LDSO Testing and Further Communication Completed - Phase 1 | 100% | Wed 30/07/25 | Wed 30/07/25 | 0 days | Wed 30/07/25 | Wed 30/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.3.7 |  |  | Helix Programme Board |  | LDSOs Onboarded into Elexon ServiceNow - Phase 1 | 100% | Wed 30/07/25 | Wed 30/07/25 | 0 days | Wed 30/07/25 | Wed 30/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.29 | Yes
5 | 1.6.1.1.4 |  |  | Helix Programme Board |  | LDSO Onboarding - Phase 2 | 100% | Thu 31/07/25 | Fri 05/09/25 | 27 days | NA | NA | 0 days | 0 days | 27 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.4.1 |  |  | Helix Programme Board |  | LDSO Resources Enrolled in Authenticator - Phase 2 | 100% | Thu 31/07/25 | Wed 27/08/25 | 20 days | Thu 31/07/25 | Wed 27/08/25 | 0 days | 0 days | 20 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.4.2 |  |  | Helix Programme Board |  | LDSO Resources Enrolled in Authenticator Completed - Phase 2 | 100% | Wed 27/08/25 | Wed 27/08/25 | 0 days | Wed 27/08/25 | Wed 27/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.4.3 |  |  | Helix Programme Board |  | Elexon Phase 2 Resources Setup in Portal - Phase 2 | 100% | Thu 28/08/25 | Fri 05/09/25 | 7 days | Thu 28/08/25 | Fri 05/09/25 | 0 days | 0 days | 7 days | Helix |  | 6.3 | Yes
6 | 1.6.1.1.4.4 |  |  | Helix Programme Board |  | Elexon Phase 2 Resources Setup in Portal Completed - Phase 2 | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 05/09/25 | Fri 05/09/25 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
4 | 1.6.1.2 |  |  | Helix Programme Board |  | Operational Readiness Testing | 100% | Mon 03/03/25 | Tue 12/08/25 | 116 days | Mon 03/03/25 | Mon 21/07/25 | 0 days | 15 days | 116 days | Helix |  | 6.24 | Yes
5 | 1.6.1.2.1 |  |  | Helix Programme Board |  | ORT Design | 100% | Mon 03/03/25 | Tue 10/06/25 | 72 days | Mon 03/03/25 | Tue 10/06/25 | 0 days | 0 days | 72 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.1 |  |  | Helix Programme Board |  | ORT Test Scope and Approach | 100% | Mon 03/03/25 | Fri 04/04/25 | 25 days | Mon 03/03/25 | Fri 04/04/25 | 0 days | 0 days | 25 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.2 |  |  | Helix Programme Board |  | ORT Test Approach Shared with MHHS (Initial Review) | 100% | Wed 02/04/25 | Wed 02/04/25 | 0 days | Wed 02/04/25 | Wed 02/04/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.3 |  |  | Helix Programme Board |  | ORT Test Scenarios Shared with MHHS (Initial Review) | 100% | Wed 02/04/25 | Wed 02/04/25 | 0 days | Wed 02/04/25 | Wed 02/04/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.4 |  |  | Helix Programme Board |  | ORT Test Scope and Approach Documents Shared with Industry | 100% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.5 |  |  | Helix Programme Board |  | ORT Test Scope and Approach Consultation (Test Scope and Approach & Test Scripts) | 100% | Tue 08/04/25 | Mon 19/05/25 | 29 days | Tue 08/04/25 | Tue 20/05/25 | 0 days | -2 days | 29 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.5.1 |  |  | Helix Programme Board |  | ORT Test Scope and Approach Consultation | 100% | Tue 08/04/25 | Mon 28/04/25 | 15 days | Tue 08/04/25 | Mon 28/04/25 | 0 days | 0 days | 15 days | PP |  | 6.24 | Yes
7 | 1.6.1.2.1.5.2 |  |  | Helix Programme Board |  | ORT Test Scope and Approach Consultation Completed | 100% | Mon 28/04/25 | Mon 28/04/25 | 0 days | Mon 28/04/25 | Mon 28/04/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.5.3 |  |  | Helix Programme Board |  | ORT Test Scope and Approach Updates (Feedback Review) | 100% | Tue 29/04/25 | Thu 08/05/25 | 8 days | Tue 29/04/25 | Thu 08/05/25 | 0 days | 0 days | 8 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.5.4 |  |  | Helix Programme Board |  | Updated ORT Test Scope and Approach Documents Shared with MHHS and Industry | 100% | Thu 08/05/25 | Thu 08/05/25 | 0 days | Thu 08/05/25 | Thu 08/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.5.5 |  |  | Helix Programme Board |  | TORWG Post-Consultation Update (ORT Approach) | 100% | Wed 14/05/25 | Wed 14/05/25 | 0 days | Wed 14/05/25 | Wed 14/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.5.6 |  |  | Helix Programme Board |  | Updated ORT Test Scope and Approach Documents Released to Industry for eSITWG | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.5.7 |  |  | Helix Programme Board |  | ORT Test Scope and Approach Endorsement (eSITWG) | 100% | Mon 19/05/25 | Mon 19/05/25 | 0 days | Tue 20/05/25 | Tue 20/05/25 | -1 day | -2 days | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.6 |  |  | Helix Programme Board |  | ORT Test Script Production and Updates | 100% | Tue 08/04/25 | Thu 08/05/25 | 23 days | Tue 08/04/25 | Thu 08/05/25 | 0 days | 0 days | 23 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.7 |  |  | Helix Programme Board |  | ORT Test Scripts Shared | 100% | Thu 08/05/25 | Thu 08/05/25 | 0 days | Thu 08/05/25 | Thu 08/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.1.8 |  |  | Helix Programme Board |  | ORT Test Scripts Consultation | 100% | Wed 07/05/25 | Tue 10/06/25 | 25 days | Wed 07/05/25 | Tue 10/06/25 | 0 days | 0 days | 25 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.1 |  |  | Helix Programme Board |  | ORT Spotlight (Test Approach) at Elexon Service Management Helix Steering Group | 100% | Wed 07/05/25 | Wed 07/05/25 | 0 days | Wed 07/05/25 | Wed 07/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.2 |  |  | Helix Programme Board |  | ORT Test Scripts Consultation | 100% | Fri 09/05/25 | Fri 16/05/25 | 6 days | Fri 09/05/25 | Thu 15/05/25 | 0 days | 1 day | 6 days | PP |  | 6.24 | Yes
7 | 1.6.1.2.1.8.3 |  |  | Helix Programme Board |  | ORT Test Scripts Consultation Completed | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Thu 15/05/25 | Thu 15/05/25 | 2 days | 1 day | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.4 |  |  | Helix Programme Board |  | ORT Test Scripts Updates (Feedback Review) | 100% | Mon 19/05/25 | Thu 22/05/25 | 4 days | Fri 16/05/25 | Thu 22/05/25 | 1 day | 0 days | 4 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.5 |  |  | Helix Programme Board |  | ORT Test Scipts Updates Shared with MHHS and Industry | 100% | Thu 22/05/25 | Thu 22/05/25 | 0 days | Thu 22/05/25 | Thu 22/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.6 |  |  | Helix Programme Board |  | Industry Assurance Review Session Post-Consultation Update (ORT Test Scripts) | 100% | Fri 30/05/25 | Fri 30/05/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.7 |  |  | Helix Programme Board |  | Updated ORT Test Script Consultation Documents Released to industry for eSITWG | 100% | Tue 03/06/25 | Tue 03/06/25 | 0 days | Tue 03/06/25 | Tue 03/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.8 |  |  | Helix Programme Board |  | ORT Test Scripts and Readiness Spotlight at Elexon Service Management Steering Group | 100% | Wed 04/06/25 | Wed 04/06/25 | 0 days | Wed 04/06/25 | Wed 04/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
7 | 1.6.1.2.1.8.9 |  |  | Helix Programme Board |  | ORT Test Scipt Updates Endorsement (eSITWG) | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | SITWG |  | 6.24 | Yes
5 | 1.6.1.2.2 |  |  | Helix Programme Board |  | ORT Preparation | 100% | Thu 01/05/25 | Fri 13/06/25 | 32 days | Thu 01/05/25 | Tue 03/06/25 | 0 days | 8 days | 32 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.2.1 |  |  | Helix Programme Board |  | ORT Participant/User Scheduling | 100% | Thu 01/05/25 | Tue 03/06/25 | 24 days | Thu 01/05/25 | Fri 16/05/25 | 0 days | 12 days | 24 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.2.2 |  |  | Helix Programme Board |  | ORT Participant/User Scheduling Completed | 100% | Tue 03/06/25 | Tue 03/06/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 13 days | 12 days | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.2.3 |  |  | Helix Programme Board |  | ORT Training and Preparation | 100% | Wed 04/06/25 | Wed 11/06/25 | 6 days | Wed 04/06/25 | Wed 11/06/25 | 0 days | 0 days | 6 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.2.4 |  |  | Helix Programme Board |  | ORT DITL Session | 100% | Thu 12/06/25 | Thu 12/06/25 | 0 days | Thu 12/06/25 | Thu 12/06/25 | 0 days | -1 day | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.2.5 |  |  | Helix Programme Board |  | ORT Orientation (JiT) | 100% | Fri 13/06/25 | Fri 13/06/25 | 0 days | Fri 13/06/25 | Fri 13/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
5 | 1.6.1.2.3 |  |  | Helix Programme Board |  | ORT Execution | 100% | Mon 16/06/25 | Fri 11/07/25 | 20 days | Mon 16/06/25 | Fri 11/07/25 | 0 days | 0 days | 20 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.3.1 |  |  | Helix Programme Board |  | ORT Execution | 100% | Mon 16/06/25 | Fri 11/07/25 | 20 days | Mon 16/06/25 | Fri 11/07/25 | 0 days | 0 days | 20 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.3.2 |  |  | Helix Programme Board |  | ORT Execution Completed | 100% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 11/07/25 | Fri 11/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
5 | 1.6.1.2.4 |  |  | Helix Programme Board |  | ORT Exit | 100% | Mon 14/07/25 | Thu 31/07/25 | 14 days | Mon 14/07/25 | Thu 31/07/25 | 0 days | 0 days | 14 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.4.1 |  |  | Helix Programme Board |  | ORT Wrap Up | 100% | Mon 14/07/25 | Fri 18/07/25 | 5 days | Mon 14/07/25 | Fri 18/07/25 | 0 days | 0 days | 5 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.4.2 |  |  | Helix Programme Board |  | ORT Exit Report | 100% | Mon 14/07/25 | Fri 25/07/25 | 10 days | Mon 14/07/25 | Fri 25/07/25 | 0 days | 0 days | 10 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.4.3 |  |  | Helix Programme Board |  | ORT Exit Report Shared with Participants | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.24 | Yes
6 | 1.6.1.2.4.4 |  |  | Helix Programme Board |  | ORT eSITWG Exit Report Endorsement | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 1 day | 0 days | 0 days | SITWG |  | 6.24 | Yes
5 | 1.6.1.2.5 |  |  | Helix Programme Board |  | Codification of Service | 100% | Fri 09/05/25 | Tue 12/08/25 | 67 days | Fri 09/05/25 | Thu 31/07/25 | 0 days | 7 days | 67 days | Helix |  | 6.26 | Yes
6 | 1.6.1.2.5.1 |  |  | Helix Programme Board |  | OFGEM Review Meeting | 100% | Fri 09/05/25 | Fri 09/05/25 | 0 days | Fri 09/05/25 | Fri 09/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.2.5.2 |  |  | Helix Programme Board |  | Codification Update at TORWG | 100% | Wed 14/05/25 | Wed 14/05/25 | 0 days | Wed 14/05/25 | Wed 14/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.1.2.5.3 |  |  | Helix Programme Board |  | DIP Code Change Presented at DCAB | 100% | Tue 12/08/25 | Tue 12/08/25 | 0 days | NA | NA | 0 days | 0 days | 0 days | Helix |  | 6.32 | Yes
4 | 1.6.1.3 |  |  | Helix Programme Board |  | Service Go-Live | 100% | Thu 31/07/25 | Mon 15/09/25 | 32 days | Wed 02/07/25 | Mon 01/09/25 | 21 days | 9 days | 32 days | Helix |  | 6.24 | Yes
5 | 1.6.1.3.1 |  |  | Helix Programme Board |  | Service Management Ready (inc. Partners) | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | -22 days | -23 days | 0 days | Helix |  | 6.3 | Yes
5 | 1.6.1.3.2 |  |  | Helix Programme Board |  | Helix Service Management Live for LDSO DIP Onboarding | 100% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 04/08/25 | Mon 04/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
5 | 1.6.1.3.3 |  |  | Helix Programme Board |  | Helix Service Management Live for MHHS Enduring Arrangements | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.33 | Yes
4 | 1.6.1.4 |  |  | Helix Programme Board |  | Non-LDSO SIT PPs ServiceNow Onboarding | 100% | Fri 05/09/25 | Wed 24/09/25 | 12 days | Wed 27/08/25 | Wed 24/09/25 | 8 days | -1 day | 12 days | Helix |  | 6.31 | Yes
5 | 1.6.1.4.1 |  |  | Helix Programme Board |  | Pathway 2 | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Wed 27/08/25 | Wed 27/08/25 | 8 days | 7 days | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.1.4.2 |  |  | Helix Programme Board |  | Pathway 3 | 100% | Tue 09/09/25 | Tue 09/09/25 | 0 days | Tue 09/09/25 | Tue 09/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.1.4.3 |  |  | Helix Programme Board |  | Pathway 4 | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
3 | 1.6.2 |  |  | Helix Programme Board |  | Business Readiness (inc DIP) | 100% | Mon 07/04/25 | Fri 17/10/25 | 140 days? | Tue 02/04/24 | Tue 02/12/25 | 264 days | -32 days | 140 days? | Helix |  | 6.26 | Yes
4 | 1.6.2.1 |  |  | Helix Programme Board |  | Knowledge Transfer triage | 100% | Mon 28/04/25 | Fri 13/06/25 | 35 days? | Mon 28/04/25 | Fri 13/06/25 | 0 days | 0 days | 35 days? | Helix |  | 6.26 | Yes
4 | 1.6.2.2 |  |  | Helix Programme Board |  | Elexon Leading Triage | 100% | Mon 16/06/25 | Mon 01/09/25 | 56 days | Mon 16/06/25 | Mon 01/09/25 | 0 days | 0 days | 56 days | Helix |  | 6.26 | Yes
4 | 1.6.2.3 |  |  | Helix Programme Board |  | MHHS Transition (Knowledge Transfer) | 100% | Tue 06/05/25 | Fri 01/08/25 | 64 days | Tue 06/05/25 | Fri 01/08/25 | 0 days | 0 days | 64 days | Helix |  | 6.26 | Yes
4 | 1.6.2.4 |  |  | Helix Programme Board |  | Artefact Handshake with MHHS | 100% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Fri 01/08/25 | Fri 01/08/25 | 22 days | 21 days | 0 days | Helix |  | 6.26 | Yes
4 | 1.6.2.5 |  |  | Helix Programme Board |  | Operational Control Centre (OCC) Development | 100% | Mon 07/04/25 | Fri 01/08/25 | 85 days | Mon 07/04/25 | Fri 01/08/25 | 0 days | 0 days | 85 days | Helix |  | 6.26 | Yes
4 | 1.6.2.6 |  |  | Helix Programme Board |  | Operational Control Centre (OCC) Live (Service and ULT Triage) | 100% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 04/08/25 | Mon 04/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
4 | 1.6.2.7 |  |  | Helix Programme Board |  | Operational Control Centre (OCC) Live | 100% | Fri 29/08/25 | Fri 29/08/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
4 | 1.6.2.8 |  |  | Helix Programme Board |  | DIP Guidance Notes | 100% | Mon 05/05/25 | Fri 18/07/25 | 55 days | Mon 05/05/25 | Fri 18/07/25 | 0 days | 0 days | 55 days | Helix |  | 6.28 | Yes
5 | 1.6.2.8.1 |  |  | Helix Programme Board |  | GN/LWI creation & publication | 100% | Mon 05/05/25 | Fri 18/07/25 | 55 days | Mon 05/05/25 | Fri 18/07/25 | 0 days | 0 days | 55 days | Helix |  | 6.28 | Yes
5 | 1.6.2.8.2 |  |  | Helix Programme Board |  | Tranche 1 GN/LWI created & published (critical for M10) | 100% | Fri 20/06/25 | Fri 20/06/25 | 0 days | Fri 20/06/25 | Fri 20/06/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes
5 | 1.6.2.8.3 |  |  | Helix Programme Board |  | Tranche 2 GN/LWI created & published | 100% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 04/07/25 | Fri 04/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes
5 | 1.6.2.8.4 |  |  | Helix Programme Board |  | Tranche 3 GN/LWI created & published | 100% | Fri 18/07/25 | Fri 18/07/25 | 0 days | Fri 18/07/25 | Fri 18/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes
4 | 1.6.2.9 |  |  | Helix Programme Board |  | DIP Reporting (M11) | 100% | Mon 12/05/25 | Fri 17/10/25 | 115 days | Mon 12/05/25 | Fri 17/10/25 | 0 days | 0 days | 115 days | Helix |  | 6.35 | Yes
4 | 1.6.2.10 |  |  | Helix Programme Board |  | Functional Training Execution | 100% | Mon 05/05/25 | Fri 12/09/25 | 95 days | Mon 05/05/25 | Fri 29/08/25 | 0 days | 10 days | 95 days | Helix |  | 6.32 | Yes
3 | 1.6.3 |  |  | Helix Programme Board |  | DIP UIT Onboarding | 100% | Mon 31/10/22 | Tue 13/01/26 | 837 days? | Mon 31/10/22 | Wed 31/12/25 | 0 days | 9 days | 837 days? | Helix |  | 6.31 | Yes
4 | 1.6.3.1 |  |  | Helix Programme Board |  | LDSOs | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.1.1 |  |  | Helix Programme Board |  | Date to be Onboarded by | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
4 | 1.6.3.2 |  |  | Helix Programme Board |  | Pathway 2 | 100% | Fri 25/07/25 | Wed 27/08/25 | 23 days | Fri 25/07/25 | Wed 27/08/25 | 0 days | -1 day | 23 days | Helix |  | 6.31 | Yes
5 | 1.6.3.2.1 |  |  | Helix Programme Board |  | Proforma Issued | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.2.2 |  |  | Helix Programme Board |  | Invite to Onbaord Issued | 100% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 08/08/25 | Fri 08/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.2.3 |  |  | Helix Programme Board |  | Date to be Onboarded by | 100% | Wed 27/08/25 | Wed 27/08/25 | 0 days | Wed 27/08/25 | Wed 27/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
4 | 1.6.3.3 |  |  | Helix Programme Board |  | Pathway 3 | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.3.1 |  |  | Helix Programme Board |  | Proforma Issued | 100% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 04/08/25 | Mon 04/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.3.2 |  |  | Helix Programme Board |  | Invite to Onbaord Issued | 100% | Mon 18/08/25 | Mon 18/08/25 | 0 days | Mon 18/08/25 | Mon 18/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.3.3 |  |  | Helix Programme Board |  | Date to be Onboarded by | 100% | Tue 09/09/25 | Tue 09/09/25 | 0 days | Tue 09/09/25 | Tue 09/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
4 | 1.6.3.4 |  |  | Helix Programme Board |  | Pathway 4 | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.4.1 |  |  | Helix Programme Board |  | Proforma Issued | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.4.2 |  |  | Helix Programme Board |  | Invite to Onbaord Issued | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 05/09/25 | Fri 05/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
5 | 1.6.3.4.3 |  |  | Helix Programme Board |  | Date to be Onboarded by | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.31 | Yes
4 | 1.6.3.5 |  |  | Helix Programme Board |  | Operational Readiness E2E Testing | 100% | Tue 13/05/25 | Fri 08/08/25 | 64 days | Tue 13/05/25 | Fri 08/08/25 | 0 days | 0 days | 64 days | Helix |  | 6.28 | Yes
5 | 1.6.3.5.1 |  |  | Helix Programme Board |  | Phase 1 Test Execution (Service Activation and Participant Management) | 100% | Wed 14/05/25 | Wed 13/08/25 | 66 days | Tue 13/05/25 | Fri 18/07/25 | 1 day | 18 days | 66 days | Helix |  | 6.32 | Yes
5 | 1.6.3.5.2 |  |  | Helix Programme Board |  | Phase 2 Test Execution (S&I) | 100% | Wed 11/06/25 | Wed 20/08/25 | 45 days | Wed 11/06/25 | Fri 11/07/25 | 0 days | 28 days | 45 days | Helix |  | 6.32 | Yes
5 | 1.6.3.5.3 |  |  | Helix Programme Board |  | Phase 3 Test Execution (Assurance & mop-up) | 100% | Mon 21/07/25 | Fri 22/08/25 | 25 days | Wed 02/07/25 | Fri 18/07/25 | 13 days | 25 days | 25 days | Helix |  | 6.32 | Yes
5 | 1.6.3.5.4 |  |  | Helix Programme Board |  | E2E Operational Testing Completed | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 18/07/25 | Fri 18/07/25 | 36 days | 35 days | 0 days | Helix |  | 6.33 | Yes
4 | 1.6.3.6 |  |  | Helix Programme Board |  | Service Activation Readiness | 100% | Tue 02/04/24 | Tue 13/01/26 | 466 days? | Tue 02/04/24 | Tue 02/12/25 | 0 days | 30 days | 466 days? | Helix |  | 6.26 | Yes
5 | 1.6.3.6.1 |  |  | Helix Programme Board |  | Phase 1 - Preparation | 100% | Tue 02/04/24 | Fri 05/09/25 | 374 days? | Tue 02/04/24 | Fri 26/09/25 | 0 days | -15 days | 374 days? | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.1 |  |  | Helix Programme Board |  | Business Service Activation Governance, Planning & Scope | 100% | Thu 04/04/24 | Mon 30/09/24 | 128 days | Thu 04/04/24 | Mon 30/09/24 | 0 days | 0 days | 128 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.1.1 |  |  | Helix Programme Board |  | Create and Confirm SA Scope | 100% | Mon 03/06/24 | Thu 13/06/24 | 9 days | Mon 03/06/24 | Thu 13/06/24 | 0 days | 0 days | 9 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.1.2 |  |  | Helix Programme Board |  | POAP Service Activation | 100% | Mon 03/06/24 | Wed 19/06/24 | 13 days | Mon 03/06/24 | Wed 19/06/24 | 0 days | 0 days | 13 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.1.3 |  |  | Helix Programme Board |  | Service Activation Working Group | 100% | Thu 04/04/24 | Fri 28/06/24 | 62 days | Thu 04/04/24 | Fri 28/06/24 | 0 days | 0 days | 62 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.1.4 |  |  | Helix Programme Board |  | Business Readiness Governance Framework | 100% | Fri 02/08/24 | Mon 30/09/24 | 42 days | Fri 02/08/24 | Mon 30/09/24 | 0 days | 0 days | 42 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.1.5 |  |  | Helix Programme Board |  | Service Activation Governance Framework Completed | 100% | Mon 30/09/24 | Mon 30/09/24 | 0 days | Mon 30/09/24 | Mon 30/09/24 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.2 |  |  | Helix Programme Board |  | Service Activation High Level Process Models | 100% | Tue 02/04/24 | Sat 31/08/24 | 109 days | Tue 02/04/24 | Sat 31/08/24 | 0 days | 0 days | 109 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.2.1 |  |  | Helix Programme Board |  | Transition Process Model | 100% | Tue 02/04/24 | Mon 08/07/24 | 70 days | Tue 02/04/24 | Mon 08/07/24 | 0 days | 0 days | 70 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.2.2 |  |  | Helix Programme Board |  | Migration Process Model | 100% | Tue 13/08/24 | Fri 30/08/24 | 14 days | Tue 13/08/24 | Fri 30/08/24 | 0 days | 0 days | 14 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.2.3 |  |  | Helix Programme Board |  | Enduring Process Model | 100% | Mon 03/06/24 | Thu 01/08/24 | 44 days | Mon 03/06/24 | Thu 01/08/24 | 0 days | 0 days | 44 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.2.4 |  |  | Helix Programme Board |  | Service Activation High Level Process Models Completed | 100% | Sat 31/08/24 | Sat 31/08/24 | 0 days | Sat 31/08/24 | Sat 31/08/24 | 0 days | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.3 |  |  | Helix Programme Board |  | Target Operating Model for Service Activation | 100% | Fri 21/06/24 | Tue 15/10/24 | 83 days | Fri 21/06/24 | Tue 15/10/24 | 0 days | 0 days | 83 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.3.1 |  |  | Helix Programme Board |  | MHHSP Engagement Team understanding | 100% | Fri 21/06/24 | Thu 25/07/24 | 25 days | Fri 21/06/24 | Thu 25/07/24 | 0 days | 0 days | 25 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.3.2 |  |  | Helix Programme Board |  | Define and produce organisation model for Service Activation in Elexon | 100% | Fri 21/06/24 | Tue 15/10/24 | 83 days | Fri 21/06/24 | Tue 15/10/24 | 0 days | 0 days | 83 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.3.3 |  |  | Helix Programme Board |  | Implement Target Operating model | 100% | Tue 15/10/24 | Tue 15/10/24 | 1 day | Tue 15/10/24 | Tue 15/10/24 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.3.4 |  |  | Helix Programme Board |  | Target Operating Model for Service Activation Completed | 100% | Tue 15/10/24 | Tue 15/10/24 | 0 days | Tue 15/10/24 | Tue 15/10/24 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.4 |  |  | Helix Programme Board |  | SIT Operational Testing for Service Activation | 100% | Mon 12/08/24 | Fri 16/08/24 | 5 days? | Mon 12/08/24 | Fri 16/08/24 | 0 days | 0 days | 5 days? | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.4.1 |  |  | Helix Programme Board |  | Review and validate test cases | 100% | Mon 12/08/24 | Fri 16/08/24 | 5 days | Mon 12/08/24 | Fri 16/08/24 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.4.2 |  |  | Helix Programme Board |  | SIT Operational Testing for Service Activation Completed | 100% | Fri 16/08/24 | Fri 16/08/24 | 1 day? | Fri 16/08/24 | Fri 16/08/24 | 0 days | 0 days | 1 day? | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.5 |  |  | Helix Programme Board |  | Operational Training for Service Activation | 100% | Thu 15/05/25 | Mon 25/08/25 | 73 days | Wed 13/11/24 | Fri 25/07/25 | 131 days | 21 days | 73 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.5.1 |  |  | Helix Programme Board |  | Training Execution [Placeholder] | 100% | Thu 15/05/25 | Mon 25/08/25 | 73 days | Thu 15/05/25 | Fri 29/08/25 | 0 days | -4 days | 73 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.5.2 |  |  | Helix Programme Board |  | Service Activation Training Completed | 100% | Mon 25/08/25 | Mon 25/08/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | -3 days | -4 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.6 |  |  | Helix Programme Board |  | Service Activation Readiness | 100% | Mon 04/08/25 | Tue 12/08/25 | 7 days | Mon 04/08/25 | Tue 12/08/25 | 0 days | 0 days | 7 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.6.1 |  |  | Helix Programme Board |  | Dress Rehearsal 1 | 100% | Mon 04/08/25 | Tue 05/08/25 | 2 days | Mon 04/08/25 | Tue 05/08/25 | 0 days | 0 days | 2 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.6.2 |  |  | Helix Programme Board |  | Dress Rehearsal 1 Complete | 100% | Tue 05/08/25 | Tue 05/08/25 | 0 days | Tue 05/08/25 | Tue 05/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.6.3 |  |  | Helix Programme Board |  | Dress Rehearsal 2 | 100% | Mon 11/08/25 | Tue 12/08/25 | 2 days | Mon 11/08/25 | Tue 12/08/25 | 0 days | 0 days | 2 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.6.4 |  |  | Helix Programme Board |  | Dress Rehearsal 2 Complete | 100% | Tue 12/08/25 | Tue 12/08/25 | 0 days | Tue 12/08/25 | Tue 12/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.7 |  |  | Helix Programme Board |  | Service Activation Go / No Go | 100% | Fri 22/08/25 | Fri 22/08/25 | 1 day | Wed 13/08/25 | Fri 22/08/25 | 7 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.7.1 |  |  | Helix Programme Board |  | Final Service Activation Go/No Go Decision | 100% | Fri 22/08/25 | Fri 22/08/25 | 1 day | Wed 13/08/25 | Fri 22/08/25 | 7 days | 0 days | 1 day | Helix |  | 6.26 | Yes
8 | 1.6.3.6.1.7.1.1 |  |  | Helix Programme Board |  | DIP Team Ready | 100% | Fri 22/08/25 | Fri 22/08/25 | 1 day | Fri 22/08/25 | Fri 22/08/25 | 0 days | 0 days | 1 day | Helix |  | 6.28 | Yes
8 | 1.6.3.6.1.7.1.2 |  |  | Helix Programme Board |  | DIP Technical Onboarding Processes Completed | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.3.6.1.7.1.3 |  |  | Helix Programme Board |  | PM Team Ready | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.3.6.1.7.1.4 |  |  | Helix Programme Board |  | Operational Support Ready (Ops Control Centre, Account Managers) | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.3.6.1.7.1.5 |  |  | Helix Programme Board |  | Service Management Activity Completed (Resolver Groups) | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.3.6.1.7.1.6 |  |  | Helix Programme Board |  | Process 1.1.1 ISD and Related LWIs Completed | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.8 |  |  | Helix Programme Board |  | SOLR Consultation | 100% | Thu 10/04/25 | Fri 05/09/25 | 107 days? | Thu 10/04/25 | Fri 26/09/25 | 0 days | -15 days | 107 days? | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.8.1 |  |  | Helix Programme Board |  | SOLR workshop 1 | 100% | Thu 10/04/25 | Thu 10/04/25 | 1 day | Thu 10/04/25 | Thu 10/04/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.8.2 |  |  | Helix Programme Board |  | SOLR workshop 2 | 100% | Tue 29/04/25 | Tue 29/04/25 | 1 day | Tue 29/04/25 | Tue 29/04/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.8.3 |  |  | Helix Programme Board |  | SOLR consultation | 100% | Thu 10/04/25 | Thu 31/07/25 | 81 days? | Thu 10/04/25 | Thu 31/07/25 | 0 days | 0 days | 81 days? | Helix |  | 6.28 | Yes
8 | 1.6.3.6.1.8.3.1 |  |  | Helix Programme Board |  | SOLR consultation | 100% | Thu 10/04/25 | Thu 31/07/25 | 81 days? | Thu 10/04/25 | Thu 31/07/25 | 0 days | 0 days | 81 days? | PP |  | 6.29 | Yes
8 | 1.6.3.6.1.8.3.2 |  |  | Helix Programme Board |  | LDSO Workshop | 100% | Mon 30/06/25 | Mon 30/06/25 | 0 days | Mon 30/06/25 | Mon 30/06/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.1.8.3.3 |  |  | Helix Programme Board |  | GLIG | 100% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 04/07/25 | Fri 04/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.1.8.3.4 |  |  | Helix Programme Board |  | QWG | 100% | Tue 08/07/25 | Tue 08/07/25 | 0 days | Tue 08/07/25 | Tue 08/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.1.8.3.5 |  |  | Helix Programme Board |  | GLIG (Second presentation) | 100% | Fri 18/07/25 | Fri 18/07/25 | 0 days | Fri 18/07/25 | Fri 18/07/25 | 0 days | -1 day | 0 days | MHHS |  | 6.28 | Yes
8 | 1.6.3.6.1.8.3.6 |  |  | Helix Programme Board |  | Process Refinement | 100% | Tue 17/06/25 | Thu 31/07/25 | 33 days | Tue 17/06/25 | Thu 31/07/25 | 0 days | 0 days | 33 days | Helix |  | 6.3 | Yes
8 | 1.6.3.6.1.8.3.7 |  |  | Helix Programme Board |  | Process Test | 100% | Fri 01/08/25 | Fri 05/09/25 | 26 days | Fri 01/08/25 | Thu 14/08/25 | 0 days | 16 days | 26 days | Helix |  | 6.3 | Yes
7 | 1.6.3.6.1.8.4 |  |  | Helix Programme Board |  | SOLR comms to MHHS for review | 100% | Wed 27/08/25 | Wed 27/08/25 | 1 day | Tue 26/08/25 | Tue 26/08/25 | 1 day | 1 day | 1 day | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.9 |  |  | Helix Programme Board |  | MDR Process | 100% | Wed 16/04/25 | Thu 31/07/25 | 77 days | Wed 16/04/25 | Thu 31/07/25 | 0 days | 0 days | 77 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.9.1 |  |  | Helix Programme Board |  | MDR workshop 1 | 100% | Wed 16/04/25 | Wed 16/04/25 | 1 day | Wed 16/04/25 | Wed 16/04/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.9.2 |  |  | Helix Programme Board |  | MDR workshop 2 | 100% | Wed 30/04/25 | Wed 30/04/25 | 1 day | Wed 30/04/25 | Wed 30/04/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.9.3 |  |  | Helix Programme Board |  | MDR workshop | 100% | Tue 27/05/25 | Tue 27/05/25 | 1 day | Tue 27/05/25 | Tue 27/05/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.1.9.4 |  |  | Helix Programme Board |  | MDR consultation | 100% | Tue 06/05/25 | Wed 21/05/25 | 12 days | Tue 06/05/25 | Wed 21/05/25 | 0 days | 0 days | 12 days | PP |  | 6.26 | Yes
7 | 1.6.3.6.1.9.5 |  |  | Helix Programme Board |  | MDR consultation ongoing actions | 100% | Wed 07/05/25 | Thu 31/07/25 | 62 days | Wed 07/05/25 | Thu 31/07/25 | 0 days | 0 days | 62 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.1.10 |  |  | Helix Programme Board |  | Service Activation Go / No Go | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.27 | Yes
5 | 1.6.3.6.2 |  |  | Helix Programme Board |  | Phase 2 - Implementation | 100% | Fri 07/06/24 | Tue 13/01/26 | 418 days? | Fri 07/06/24 | Tue 02/12/25 | 0 days | 30 days | 418 days? | Helix |  | 6.26 | Yes
6 | 1.6.3.6.2.1 |  |  | Helix Programme Board |  | Non-SIT LDSO & SIT MVC Data Loading (M10 Ready) | 100% | Fri 07/06/24 | Fri 14/06/24 | 6 days | Fri 07/06/24 | Fri 14/06/24 | 0 days | 0 days | 6 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.1.1 |  |  | Helix Programme Board |  | Define Non-SIT LDSO Upfront Activities | 100% | Fri 07/06/24 | Fri 14/06/24 | 6 days | Fri 07/06/24 | Fri 14/06/24 | 0 days | 0 days | 6 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.2.2 |  |  | Helix Programme Board |  | M10-Ready Activation Preparation Tasks | 100% | Mon 25/08/25 | Fri 12/09/25 | 15 days? | Mon 25/08/25 | Mon 08/09/25 | 0 days | 4 days | 15 days? | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.1 |  |  | Helix Programme Board |  | Identify Resources | 100% | Mon 25/08/25 | Mon 25/08/25 | 1 day | Mon 25/08/25 | Mon 25/08/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.2 |  |  | Helix Programme Board |  | Confirmation from Qualification of Wave Participants Complete | 100% | Mon 25/08/25 | Mon 25/08/25 | 0 days | Mon 25/08/25 | Mon 25/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.3 |  |  | Helix Programme Board |  | Agree & Understand Support Model | 100% | Tue 26/08/25 | Tue 26/08/25 | 1 day | Tue 26/08/25 | Tue 26/08/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.4 |  |  | Helix Programme Board |  | Confirm Training complete | 100% | Wed 27/08/25 | Wed 27/08/25 | 0 days | Wed 27/08/25 | Wed 27/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.5 |  |  | Helix Programme Board |  | Confirm IDNOs global sign completed prior to M10 | 100% | Thu 28/08/25 | Fri 05/09/25 | 7 days | Thu 28/08/25 | Thu 28/08/25 | 0 days | 6 days | 7 days | Helix |  | 6.33 | Yes
7 | 1.6.3.6.2.2.6 |  |  | Helix Programme Board |  | Engagement / Communications with Participants | 100% | Fri 29/08/25 | Wed 10/09/25 | 9 days | Fri 29/08/25 | Fri 29/08/25 | 0 days | 8 days | 9 days | Helix |  | 6.33 | Yes
7 | 1.6.3.6.2.2.7 |  |  | Helix Programme Board |  | Internal Communications | 100% | Mon 01/09/25 | Mon 01/09/25 | 1 day | Mon 01/09/25 | Mon 01/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
8 | 1.6.3.6.2.2.7.1 |  |  | Helix Programme Board |  | Agree Content for Livewire | 100% | Mon 01/09/25 | Mon 01/09/25 | 1 day | Mon 01/09/25 | Mon 01/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
8 | 1.6.3.6.2.2.7.2 |  |  | Helix Programme Board |  | Publish Content for Livewire | 100% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.8 |  |  | Helix Programme Board |  | Validate User Access | 100% | Tue 02/09/25 | Tue 02/09/25 | 1 day | Tue 02/09/25 | Tue 02/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.9 |  |  | Helix Programme Board |  | Target Systems and Environments Ready | 100% | Wed 03/09/25 | Wed 03/09/25 | 1 day | Wed 03/09/25 | Wed 03/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.10 |  |  | Helix Programme Board |  | Publish the guidence with Parties | 100% | Fri 12/09/25 | Fri 12/09/25 | 1 day | Thu 04/09/25 | Thu 04/09/25 | 6 days | 6 days | 1 day | Helix |  | 6.33 | Yes
7 | 1.6.3.6.2.2.11 |  |  | Helix Programme Board |  | Provide LWIs | 100% | Fri 12/09/25 | Fri 12/09/25 | 1 day? | Fri 05/09/25 | Fri 05/09/25 | 5 days | 5 days | 1 day? | Helix |  | 6.33 | Yes
7 | 1.6.3.6.2.2.12 |  |  | Helix Programme Board |  | Business Readiness Governance Approval | 100% | Mon 08/09/25 | Mon 08/09/25 | 1 day | Mon 08/09/25 | Mon 08/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.2.13 |  |  | Helix Programme Board |  | M10-Ready Participants Service Activation Preparation Completed | 100% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Mon 08/09/25 | Mon 08/09/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.2.3 |  |  | Helix Programme Board |  | M10-Ready (Inlcuding Non-SIT LDSOs) Service Activation Implementation | 100% | Wed 10/09/25 | Fri 19/09/25 | 6 days | Wed 06/08/25 | Fri 19/09/25 | 26 days | -1 day | 6 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.1 |  |  | Helix Programme Board |  | MHHSP Enabled Confirmation | 100% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Wed 10/09/25 | Wed 10/09/25 | 1 day | 0 days | 0 days | PAB |  | 6.26 | Yes
7 | 1.6.3.6.2.3.2 |  |  | Helix Programme Board |  | Add EFD (ISD Calendar Date) to DIP | 100% | Thu 11/09/25 | Thu 11/09/25 | 1 day | Thu 11/09/25 | Thu 11/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.3 |  |  | Helix Programme Board |  | Non-SIT LDSO PP DIP User Promoted to Production | 100% | Fri 12/09/25 | Fri 12/09/25 | 1 day | Fri 12/09/25 | Fri 12/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.28 | Yes
7 | 1.6.3.6.2.3.4 |  |  | Helix Programme Board |  | Create M16 in Customer Solution Started | 100% | Thu 11/09/25 | Thu 11/09/25 | 0 days | Thu 11/09/25 | Thu 11/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.5 |  |  | Helix Programme Board |  | Create M16 in Customer Solution | 100% | Thu 11/09/25 | Thu 11/09/25 | 1 day | Thu 11/09/25 | Thu 11/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.6 |  |  | Helix Programme Board |  | DIP Production Success Checks | 100% | Fri 12/09/25 | Fri 12/09/25 | 1 day | Fri 12/09/25 | Fri 12/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.7 |  |  | Helix Programme Board |  | 1st ISD Publish Started | 100% | Thu 11/09/25 | Thu 11/09/25 | 0 days | Thu 11/09/25 | Thu 11/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.8 |  |  | Helix Programme Board |  | 1st ISD Publish (7 day window for this activity is consistent with Code requirements) | 100% | Thu 11/09/25 | Thu 18/09/25 | 6 days | Thu 11/09/25 | Thu 18/09/25 | 0 days | 0 days | 6 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.3.9 |  |  | Helix Programme Board |  | Go Live ISD | 100% | Thu 18/09/25 | Thu 18/09/25 | 1 day | Thu 18/09/25 | Thu 18/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.3.10 |  |  | Helix Programme Board |  | M10-Ready Service Activation Implementation Completed | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.2.4 |  |  | Helix Programme Board |  | M10-Ready Service Activation Implementation MDD | 100% | Wed 10/09/25 | Thu 18/09/25 | 6 days | Wed 10/09/25 | Fri 19/09/25 | 1 day | -1 day | 6 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.4.1 |  |  | Helix Programme Board |  | MDD Final Circular Completed | 100% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Wed 10/09/25 | Wed 10/09/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.4.2 |  |  | Helix Programme Board |  | MDD Manual Update | 100% | Thu 11/09/25 | Mon 15/09/25 | 3 days | Thu 11/09/25 | Mon 15/09/25 | 0 days | 0 days | 3 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.4.3 |  |  | Helix Programme Board |  | MDD Publish | 100% | Thu 11/09/25 | Thu 18/09/25 | 6 days | Thu 11/09/25 | Thu 18/09/25 | 0 days | 0 days | 6 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.4.4 |  |  | Helix Programme Board |  | MDD Go Live | 100% | Thu 18/09/25 | Thu 18/09/25 | 0 days | Thu 18/09/25 | Thu 18/09/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.4.5 |  |  | Helix Programme Board |  | Non-SIT LDSO & SIT MVC Service Activation Implementation MDD Completed | 100% | Thu 18/09/25 | Thu 18/09/25 | 0 days | Thu 18/09/25 | Thu 18/09/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.3.6.2.5 |  |  | Helix Programme Board |  | Non-SIT LDSO & SIT Service Activation Hypercare (M10 Ready) | 100% | Thu 18/09/25 | Tue 02/12/25 | 54 days | Thu 18/09/25 | Tue 02/12/25 | 0 days | 0 days | 54 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.5.1 |  |  | Helix Programme Board |  | Monitoring | 100% | Thu 18/09/25 | Tue 02/12/25 | 54 days | Thu 18/09/25 | Tue 02/12/25 | 0 days | 0 days | 54 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.5.2 |  |  | Helix Programme Board |  | Reporting | 100% | Thu 18/09/25 | Tue 02/12/25 | 54 days | Thu 18/09/25 | Tue 02/12/25 | 0 days | 0 days | 54 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.5.3 |  |  | Helix Programme Board |  | Issue Management | 100% | Thu 18/09/25 | Tue 02/12/25 | 54 days | Thu 18/09/25 | Tue 02/12/25 | 0 days | 0 days | 54 days | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.5.4 |  |  | Helix Programme Board |  | Closed Down Activities | 100% | Fri 19/09/25 | Fri 19/09/25 | 1 day | Fri 19/09/25 | Fri 19/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
7 | 1.6.3.6.2.5.5 |  |  | Helix Programme Board |  | Inform MHHSP | 100% | Fri 19/09/25 | Fri 19/09/25 | 1 day | Fri 19/09/25 | Fri 19/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
6 | 1.6.3.6.2.6 |  |  | Helix Programme Board |  | M11-Ready Activation Preparation Tasks | 100% | Thu 09/10/25 | Mon 13/10/25 | 3 days | Thu 18/09/25 | Tue 02/12/25 | 15 days | -36 days | 3 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.6.1 |  |  | Helix Programme Board |  | Engagement / Communications with Participants | 100% | Thu 09/10/25 | Thu 09/10/25 | 1 day | Thu 09/10/25 | Thu 09/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.6.2 |  |  | Helix Programme Board |  | Validate User Access | 100% | Mon 13/10/25 | Mon 13/10/25 | 1 day | Mon 13/10/25 | Mon 13/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.6.3 |  |  | Helix Programme Board |  | M11-Ready Participants Service Activation Preparation Completed | 100% | Mon 13/10/25 | Mon 13/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | -2 days | -3 days | 0 days | Helix |  | 6.27 | Yes
6 | 1.6.3.6.2.7 |  |  | Helix Programme Board |  | M11-Ready Service Activation Implementation | 100% | Thu 25/09/25 | Wed 22/10/25 | 19 days? | Wed 15/10/25 | Wed 22/10/25 | -13 days | 0 days | 19 days? | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.7.1 |  |  | Helix Programme Board |  | Pathway 4 PPs | 100% | Thu 25/09/25 | Fri 03/10/25 | 6 days? | NA | NA | 0 days | 0 days | 6 days? | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.1 |  |  | Helix Programme Board |  | MHHSP Enabled Confirmation | 100% | Thu 25/09/25 | Thu 25/09/25 | 0 days | Wed 15/10/25 | Wed 15/10/25 | -13 days | -14 days | 0 days | PAB |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.2 |  |  | Helix Programme Board |  | Add EFD (ISD Calendar Date) to DIP | 100% | Thu 25/09/25 | Thu 25/09/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | -14 days | -15 days | 0 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.3 |  |  | Helix Programme Board |  | Create M16 in Customer Solution | 100% | Thu 25/09/25 | Thu 25/09/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | -14 days | -15 days | 0 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.4 |  |  | Helix Programme Board |  | DIP Production Success Checks | 100% | Fri 26/09/25 | Fri 26/09/25 | 1 day? | Fri 17/10/25 | Fri 17/10/25 | -15 days | -15 days | 1 day? | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.5 |  |  | Helix Programme Board |  | Publish ISD | 100% | Fri 26/09/25 | Fri 03/10/25 | 6 days | Wed 15/10/25 | Wed 22/10/25 | -13 days | -13 days | 6 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.6 |  |  | Helix Programme Board |  | Go Live ISD | 100% | Fri 03/10/25 | Fri 03/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | -12 days | -13 days | 0 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.7.1.7 |  |  | Helix Programme Board |  | Pathway 4 Service Activation Implementation Completed | 100% | Fri 03/10/25 | Fri 03/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | -12 days | -13 days | 0 days | Helix |  | 6.28 | Yes
7 | 1.6.3.6.2.7.2 |  |  | Helix Programme Board |  | Pathway 5 PPs | 100% | Wed 15/10/25 | Wed 22/10/25 | 5 days? | NA | NA | 0 days | 0 days | 5 days? | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.1 |  |  | Helix Programme Board |  | MHHSP Enabled Confirmation | 100% | Wed 15/10/25 | Wed 15/10/25 | 0 days | Wed 15/10/25 | Wed 15/10/25 | 1 day | 0 days | 0 days | PAB |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.2 |  |  | Helix Programme Board |  | Add EFD (ISD Calendar Date) to DIP | 100% | Wed 15/10/25 | Wed 15/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.3 |  |  | Helix Programme Board |  | Create M16 in Customer Solution | 100% | Thu 16/10/25 | Thu 16/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | 0 days | -1 day | 0 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.4 |  |  | Helix Programme Board |  | DIP Production Success Checks | 100% | Thu 16/10/25 | Thu 16/10/25 | 1 day? | Fri 17/10/25 | Fri 17/10/25 | -1 day | -1 day | 1 day? | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.5 |  |  | Helix Programme Board |  | Publish ISD | 100% | Thu 16/10/25 | Wed 22/10/25 | 5 days | Wed 15/10/25 | Wed 22/10/25 | 1 day | 0 days | 5 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.6 |  |  | Helix Programme Board |  | Go Live ISD | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.7 |  |  | Helix Programme Board |  | Publish MDD | 100% | Thu 16/10/25 | Wed 22/10/25 | 5 days | Thu 16/10/25 | Wed 22/10/25 | 0 days | 0 days | 5 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.8 |  |  | Helix Programme Board |  | MDD Go Live | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
8 | 1.6.3.6.2.7.2.9 |  |  | Helix Programme Board |  | Pathway 5 Service Activation Implementation Completed | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes |  | 06/10/25 - There will be no PPs on Pathway 5
6 | 1.6.3.6.2.8 |  |  | Helix Programme Board |  | M11-Ready Service Activation Hypercare | 100% | Wed 15/10/25 | Wed 05/11/25 | 16 days | Thu 18/09/25 | Tue 02/12/25 | 19 days | -19 days | 16 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.8.1 |  |  | Helix Programme Board |  | Monitoring | 100% | Wed 15/10/25 | Wed 29/10/25 | 11 days | Wed 15/10/25 | Wed 29/10/25 | 0 days | 0 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.8.2 |  |  | Helix Programme Board |  | Reporting | 100% | Wed 15/10/25 | Wed 29/10/25 | 11 days | Tue 18/11/25 | Tue 02/12/25 | -24 days | -24 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.8.3 |  |  | Helix Programme Board |  | Issue Management | 100% | Wed 15/10/25 | Wed 29/10/25 | 11 days | Wed 15/10/25 | Wed 29/10/25 | 0 days | 0 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.8.4 |  |  | Helix Programme Board |  | Closed Down Activities | 100% | Thu 30/10/25 | Mon 03/11/25 | 3 days | Tue 18/11/25 | Thu 20/11/25 | -13 days | -13 days | 3 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.8.5 |  |  | Helix Programme Board |  | Inform MHHSP | 100% | Tue 04/11/25 | Wed 05/11/25 | 2 days | Tue 18/11/25 | Wed 19/11/25 | -10 days | -10 days | 2 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.8.6 |  |  | Helix Programme Board |  | M11-Ready Service Activation Hypercare Completed | 100% | Wed 05/11/25 | Wed 05/11/25 | 0 days | Wed 19/11/25 | Wed 19/11/25 | -9 days | -10 days | 0 days | Helix |  | 6.27 | Yes
6 | 1.6.3.6.2.9 |  |  | Helix Programme Board |  | Not M11-Ready Service Activation Preparation Tasks | 100% | Mon 13/10/25 | Thu 16/10/25 | 4 days | Mon 25/08/25 | Mon 08/09/25 | 35 days | 28 days | 4 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.9.1 |  |  | Helix Programme Board |  | Engagement / Communications with Participants | 100% | Thu 16/10/25 | Thu 16/10/25 | 1 day | Thu 04/12/25 | Thu 04/12/25 | -35 days | -35 days | 1 day | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.9.2 |  |  | Helix Programme Board |  | Validate User Access | 100% | Mon 13/10/25 | Mon 13/10/25 | 1 day | Mon 08/12/25 | Mon 08/12/25 | -40 days | -40 days | 1 day | Helix |  | 6.27 | Yes
6 | 1.6.3.6.2.10 |  |  | Helix Programme Board |  | Not M11-Ready Service Activation Implementation | 100% | Thu 30/10/25 | Tue 13/01/26 | 53 days | Wed 17/12/25 | Wed 31/12/25 | -33 days | 9 days | 53 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.10.1 |  |  | Helix Programme Board |  | First Pathway 6 PAB | 100% | Thu 30/10/25 | Fri 21/11/25 | 16 days | NA | NA | 0 days | 0 days | 16 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.10.1.1 |  |  | Helix Programme Board |  | MHHSP Enabled Confirmation | 100% | Thu 30/10/25 | Thu 30/10/25 | 0 days | Wed 17/12/25 | Wed 17/12/25 | -33 days | -34 days | 0 days | PAB |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.2 |  |  | Helix Programme Board |  | Add EFD (ISD Calendar Date) to DIP | 100% | Thu 30/10/25 | Thu 30/10/25 | 0 days | Thu 18/12/25 | Fri 19/12/25 | -34 days | -36 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.3 |  |  | Helix Programme Board |  | Create M16 in Customer Solution | 100% | Fri 31/10/25 | Fri 31/10/25 | 0 days | Mon 22/12/25 | Mon 22/12/25 | -35 days | -36 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.4 |  |  | Helix Programme Board |  | DIP Production Success Checks | 100% | Fri 31/10/25 | Fri 31/10/25 | 0 days | Tue 23/12/25 | Wed 31/12/25 | -36 days | -43 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.5 |  |  | Helix Programme Board |  | Publish ISD | 100% | Fri 14/11/25 | Fri 21/11/25 | 6 days | Fri 14/11/25 | Fri 21/11/25 | 0 days | 0 days | 6 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.6 |  |  | Helix Programme Board |  | Go Live ISD | 100% | Fri 21/11/25 | Fri 21/11/25 | 0 days | Fri 21/11/25 | Fri 21/11/25 | 1 day | 0 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.7 |  |  | Helix Programme Board |  | Publish MDD | 100% | Fri 14/11/25 | Fri 21/11/25 | 6 days | Fri 14/11/25 | Fri 21/11/25 | 0 days | 0 days | 6 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.8 |  |  | Helix Programme Board |  | MDD Go Live | 100% | Fri 21/11/25 | Fri 21/11/25 | 0 days | Fri 21/11/25 | Fri 21/11/25 | 1 day | 0 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.1.9 |  |  | Helix Programme Board |  | Service Activation Implementation Completed | 100% | Fri 21/11/25 | Fri 21/11/25 | 0 days | Fri 21/11/25 | Fri 21/11/25 | 1 day | 0 days | 0 days | Helix |  | 6.37 | Yes
7 | 1.6.3.6.2.10.2 |  |  | Helix Programme Board |  | Final Pathway 6 PAB | 100% | Thu 18/12/25 | Tue 13/01/26 | 19 days | Wed 17/12/25 | Tue 30/12/25 | 1 day | 10 days | 19 days | Helix |  | 6.28 | Yes
8 | 1.6.3.6.2.10.2.1 |  |  | Helix Programme Board |  | MHHSP Enabled Confirmation | 100% | Thu 18/12/25 | Thu 18/12/25 | 0 days | Thu 18/12/25 | Thu 18/12/25 | 0 days | -1 day | 0 days | PAB |  | 6.4 | Yes |  | 17/12/25 - Updated to align with date of actual PAB.
8 | 1.6.3.6.2.10.2.2 |  |  | Helix Programme Board |  | Add EFD (ISD Calendar Date) to DIP | 100% | Thu 18/12/25 | Thu 18/12/25 | 0 days | Thu 18/12/25 | Thu 18/12/25 | 0 days | -1 day | 0 days | Helix |  | 6.4 | Yes |  | 17/12/25 - Updated to align with date of actual PAB.
8 | 1.6.3.6.2.10.2.3 |  |  | Helix Programme Board |  | Create M16 in Customer Solution | 100% | Thu 18/12/25 | Thu 18/12/25 | 0 days | Mon 22/12/25 | Mon 22/12/25 | -1 day | -2 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.2.4 |  |  | Helix Programme Board |  | DIP Production Success Checks | 100% | Thu 18/12/25 | Thu 18/12/25 | 0 days | Tue 23/12/25 | Tue 23/12/25 | -2 days | -3 days | 0 days | Helix |  | 6.37 | Yes
8 | 1.6.3.6.2.10.2.5 |  |  | Helix Programme Board |  | Publish ISD | 100% | Mon 05/01/26 | Tue 13/01/26 | 7 days | Mon 05/01/26 | Tue 13/01/26 | 0 days | 0 days | 7 days | Helix |  | 6.4 | Yes
8 | 1.6.3.6.2.10.2.6 |  |  | Helix Programme Board |  | Go Live ISD | 100% | Tue 13/01/26 | Tue 13/01/26 | 0 days | Tue 13/01/26 | Tue 13/01/26 | 1 day | 0 days | 0 days | Helix |  | 6.4 | Yes
8 | 1.6.3.6.2.10.2.7 |  |  | Helix Programme Board |  | Publish MDD | 100% | Mon 22/12/25 | Tue 30/12/25 | 7 days | Mon 22/12/25 | Tue 30/12/25 | 0 days | 0 days | 7 days | Helix |  | 6.4 | Yes
8 | 1.6.3.6.2.10.2.8 |  |  | Helix Programme Board |  | MDD Go Live | 100% | Tue 30/12/25 | Tue 30/12/25 | 0 days | Tue 30/12/25 | Tue 30/12/25 | 1 day | 0 days | 0 days | Helix |  | 6.4 | Yes
8 | 1.6.3.6.2.10.2.9 |  |  | Helix Programme Board |  | Service Activation Implementation Completed | 100% | Tue 13/01/26 | Tue 13/01/26 | 0 days | Tue 13/01/26 | Tue 13/01/26 | 1 day | 0 days | 0 days | Helix |  | 6.4 | Yes
6 | 1.6.3.6.2.11 |  |  | Helix Programme Board |  | Not M11-Ready Service Activation Hypercare | 100% | Wed 17/12/25 | Wed 31/12/25 | 11 days | Wed 17/12/25 | Wed 31/12/25 | 0 days | 0 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.11.1 |  |  | Helix Programme Board |  | Monitoring | 100% | Wed 17/12/25 | Wed 31/12/25 | 11 days | Wed 17/12/25 | Wed 31/12/25 | 0 days | 0 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.11.2 |  |  | Helix Programme Board |  | Reporting | 100% | Wed 17/12/25 | Wed 31/12/25 | 11 days | Wed 17/12/25 | Wed 31/12/25 | 0 days | 0 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.11.3 |  |  | Helix Programme Board |  | Issue Management | 100% | Wed 17/12/25 | Wed 31/12/25 | 11 days | Wed 17/12/25 | Wed 31/12/25 | 0 days | 0 days | 11 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.11.4 |  |  | Helix Programme Board |  | Closed Down Activities | 100% | Mon 29/12/25 | Wed 31/12/25 | 3 days | Mon 29/12/25 | Wed 31/12/25 | 0 days | 0 days | 3 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.11.5 |  |  | Helix Programme Board |  | Inform MHHSP | 100% | Tue 30/12/25 | Wed 31/12/25 | 2 days | Tue 30/12/25 | Wed 31/12/25 | 0 days | 0 days | 2 days | Helix |  | 6.27 | Yes
7 | 1.6.3.6.2.11.6 |  |  | Helix Programme Board |  | Not M11-Ready Service Activation Hypercare Completed | 100% | Wed 31/12/25 | Wed 31/12/25 | 0 days | Wed 31/12/25 | Wed 31/12/25 | 1 day | 0 days | 0 days | Helix |  | 6.27 | Yes
3 | 1.6.4 |  |  | Helix Programme Board |  | Helix Solution Build | 100% | Mon 19/08/24 | Thu 18/09/25 | 284 days? | Mon 19/08/24 | Thu 07/08/25 | 0 days | 30 days | 284 days? | Helix |  | 6.26 | Yes
4 | 1.6.4.1 |  |  | Helix Programme Board |  | M10 Build Candidate | 100% | Mon 28/04/25 | Fri 15/08/25 | 80 days | Mon 28/04/25 | Wed 16/07/25 | 0 days | 22 days | 80 days | Helix |  | 6.32 | Yes
4 | 1.6.4.2 |  |  | Helix Programme Board |  | Helix Code Uplifts | 100% | Mon 18/08/25 | Thu 18/09/25 | 24 days | Mon 18/08/25 | Thu 18/09/25 | 0 days | 0 days | 24 days | Helix |  | 6.32 | Yes
4 | 1.6.4.3 |  |  | Helix Programme Board |  | Helix E2E Settlement Assurance Testing (SAT) | 100% | Mon 19/08/24 | Fri 15/08/25 | 260 days? | Mon 06/01/25 | Fri 04/04/25 | -100 days | 95 days | 260 days? | Helix |  | 6 | Yes
5 | 1.6.4.3.1 |  |  | Helix Programme Board |  | Test design | 100% | Mon 02/09/24 | Fri 21/02/25 | 125 days | Mon 02/09/24 | Fri 21/02/25 | 0 days | 0 days | 125 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.1.1 |  |  | Helix Programme Board |  | SAT tests (Review and finalise) | 100% | Mon 02/09/24 | Fri 10/01/25 | 95 days | Mon 02/09/24 | Fri 10/01/25 | 0 days | 0 days | 95 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.1.2 |  |  | Helix Programme Board |  | Test Automation and Supporting Tools | 100% | Mon 04/11/24 | Fri 21/02/25 | 80 days | Mon 04/11/24 | Fri 21/02/25 | 0 days | 0 days | 80 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.1.3 |  |  | Helix Programme Board |  | SAT tests batch 3 | 100% | Mon 16/12/24 | Fri 21/02/25 | 50 days | Mon 16/12/24 | Fri 21/02/25 | 0 days | 0 days | 50 days | Helix |  | 6.18 | Yes
5 | 1.6.4.3.2 |  |  | Helix Programme Board |  | Data and environment | 100% | Mon 19/08/24 | Fri 31/01/25 | 120 days? | Mon 19/08/24 | Fri 31/01/25 | 0 days | 0 days | 120 days? | Helix |  | 6.18 | Yes
6 | 1.6.4.3.2.1 |  |  | Helix Programme Board |  | Data and environment requirements | 100% | Mon 19/08/24 | Fri 01/11/24 | 55 days | Mon 19/08/24 | Fri 01/11/24 | 0 days | 0 days | 55 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.2.2 |  |  | Helix Programme Board |  | Data sourcing | 100% | Mon 02/09/24 | Fri 10/01/25 | 95 days | Mon 02/09/24 | Fri 10/01/25 | 0 days | 0 days | 95 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.2.3 |  |  | Helix Programme Board |  | Environment data check | 100% | Mon 13/01/25 | Fri 31/01/25 | 15 days? | Mon 13/01/25 | Fri 31/01/25 | 0 days | 0 days | 15 days? | Helix |  | 6.18 | Yes
5 | 1.6.4.3.3 |  |  | Helix Programme Board |  | Execution | 100% | Mon 11/11/24 | Fri 15/08/25 | 200 days | Mon 11/11/24 | Thu 03/07/25 | 0 days | 31 days | 200 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.3.1 |  |  | Helix Programme Board |  | Trial test runs | 100% | Mon 11/11/24 | Fri 17/01/25 | 50 days | Mon 11/11/24 | Fri 17/01/25 | 0 days | 0 days | 50 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.3.2 |  |  | Helix Programme Board |  | Test planning prioritisation | 100% | Mon 20/01/25 | Thu 06/02/25 | 14 days | Mon 20/01/25 | Thu 06/02/25 | 0 days | 0 days | 14 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.3.3 |  |  | Helix Programme Board |  | Programme agreement to start SAT testing | 100% | Thu 06/02/25 | Thu 06/02/25 | 0 days | Thu 06/02/25 | Thu 06/02/25 | 1 day | 0 days | 0 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.3.4 |  |  | Helix Programme Board |  | SAT Testing Start | 100% | Thu 06/02/25 | Thu 06/02/25 | 0 days | Thu 06/02/25 | Thu 06/02/25 | 1 day | 0 days | 0 days | Helix |  | 6.18 | Yes
6 | 1.6.4.3.3.5 |  |  | Helix Programme Board |  | SAT Cycle 1 | 100% | Fri 07/02/25 | Wed 16/07/25 | 114 days | Fri 07/02/25 | Wed 02/04/25 | 0 days | 75 days | 114 days | Helix |  | 6.26 | Yes
7 | 1.6.4.3.3.5.1 |  |  | Helix Programme Board |  | Legacy | 100% | Fri 07/02/25 | Wed 25/06/25 | 99 days | Fri 07/02/25 | Wed 25/06/25 | 0 days | 0 days | 99 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.1 |  |  | Helix Programme Board |  | GMT | 100% | Fri 07/02/25 | Wed 11/06/25 | 89 days | Fri 07/02/25 | Wed 11/06/25 | 0 days | 0 days | 89 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.2 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Fri 23/05/25 | Fri 23/05/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.3 |  |  | Helix Programme Board |  | NESO Validation Period (GMT) | 100% | Wed 28/05/25 | Tue 03/06/25 | 5 days | Wed 28/05/25 | Tue 03/06/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.4 |  |  | Helix Programme Board |  | Long | 100% | Wed 28/05/25 | Fri 13/06/25 | 13 days | Wed 28/05/25 | Fri 13/06/25 | 0 days | 0 days | 13 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.5 |  |  | Helix Programme Board |  | Helix SAT Confidence Check 1 | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.6 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Fri 13/06/25 | Fri 13/06/25 | 0 days | Fri 13/06/25 | Fri 13/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.7 |  |  | Helix Programme Board |  | Helix SAT Confidence Check 2 | 100% | Fri 13/06/25 | Fri 13/06/25 | 0 days | Fri 13/06/25 | Fri 13/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.8 |  |  | Helix Programme Board |  | NESO Validation Period (Long) | 100% | Mon 16/06/25 | Fri 20/06/25 | 5 days | Mon 16/06/25 | Fri 20/06/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.9 |  |  | Helix Programme Board |  | BST | 100% | Mon 02/06/25 | Wed 18/06/25 | 13 days | Mon 02/06/25 | Wed 18/06/25 | 0 days | 0 days | 13 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.10 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Wed 18/06/25 | Wed 18/06/25 | 0 days | Wed 18/06/25 | Wed 18/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.11 |  |  | Helix Programme Board |  | NESO Validation Period (BST) | 100% | Thu 19/06/25 | Wed 25/06/25 | 5 days | Thu 19/06/25 | Wed 25/06/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.1.12 |  |  | Helix Programme Board |  | Trading Dispute | 100% | Wed 18/06/25 | Fri 20/06/25 | 3 days | Wed 18/06/25 | Fri 20/06/25 | 0 days | 0 days | 3 days | Helix |  | 6.26 | Yes
7 | 1.6.4.3.3.5.2 |  |  | Helix Programme Board |  | Transition | 100% | Wed 28/05/25 | Wed 16/07/25 | 36 days | Wed 28/05/25 | Wed 16/07/25 | 0 days | 0 days | 36 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.1 |  |  | Helix Programme Board |  | GMT | 100% | Wed 28/05/25 | Mon 23/06/25 | 19 days | Wed 28/05/25 | Mon 23/06/25 | 0 days | 0 days | 19 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.2 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Fri 13/06/25 | Fri 13/06/25 | 0 days | Fri 13/06/25 | Fri 13/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.3 |  |  | Helix Programme Board |  | NESO Validation Period (GMT) | 100% | Tue 17/06/25 | Mon 23/06/25 | 5 days | Tue 17/06/25 | Mon 23/06/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.4 |  |  | Helix Programme Board |  | Long | 100% | Tue 24/06/25 | Fri 27/06/25 | 4 days | Tue 24/06/25 | Fri 27/06/25 | 0 days | 0 days | 4 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.5 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Fri 27/06/25 | Fri 27/06/25 | 0 days | Fri 27/06/25 | Fri 27/06/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.6 |  |  | Helix Programme Board |  | NESO Validation Period (Long) | 100% | Mon 30/06/25 | Fri 04/07/25 | 5 days | Mon 30/06/25 | Fri 04/07/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.7 |  |  | Helix Programme Board |  | BST | 100% | Thu 26/06/25 | Tue 01/07/25 | 4 days | Thu 26/06/25 | Tue 01/07/25 | 0 days | 0 days | 4 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.8 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.9 |  |  | Helix Programme Board |  | NESO Validation Period (BST) | 100% | Thu 03/07/25 | Wed 09/07/25 | 5 days | Thu 03/07/25 | Wed 09/07/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.10 |  |  | Helix Programme Board |  | Short | 100% | Tue 01/07/25 | Wed 09/07/25 | 7 days | Tue 01/07/25 | Thu 03/07/25 | 0 days | 4 days | 7 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.11 |  |  | Helix Programme Board |  | P0210 file shared for NESO Validation | 100% | Thu 03/07/25 | Thu 03/07/25 | 0 days | Thu 03/07/25 | Thu 03/07/25 | 1 day | 0 days | 0 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.12 |  |  | Helix Programme Board |  | NESO Validation Period (Short) | 100% | Tue 08/07/25 | Mon 14/07/25 | 5 days | Fri 04/07/25 | Thu 10/07/25 | 2 days | 2 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.13 |  |  | Helix Programme Board |  | DCP MPAN Mig | 100% | Tue 01/07/25 | Thu 03/07/25 | 3 days | Tue 01/07/25 | Thu 03/07/25 | 0 days | 0 days | 3 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.14 |  |  | Helix Programme Board |  | ISD | 100% | Tue 01/07/25 | Thu 03/07/25 | 3 days | Tue 01/07/25 | Thu 03/07/25 | 0 days | 0 days | 3 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.15 |  |  | Helix Programme Board |  | Data Agg | 100% | Fri 04/07/25 | Fri 11/07/25 | 6 days | Fri 04/07/25 | Fri 11/07/25 | 0 days | 0 days | 6 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.16 |  |  | Helix Programme Board |  | M16 | 100% | Mon 14/07/25 | Wed 16/07/25 | 3 days | Mon 14/07/25 | Wed 16/07/25 | 0 days | 0 days | 3 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.5.2.17 |  |  | Helix Programme Board |  | End of Cycle 1 | 100% | Wed 16/07/25 | Wed 16/07/25 | 0 days | Wed 16/07/25 | Wed 16/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.4.3.3.6 |  |  | Helix Programme Board |  | SAT Cycle 2 | 100% | Thu 17/07/25 | Fri 01/08/25 | 12 days | Thu 17/07/25 | Fri 01/08/25 | 0 days | 0 days | 12 days | Helix |  | 6.26 | Yes
7 | 1.6.4.3.3.6.1 |  |  | Helix Programme Board |  | Legacy | 100% | Thu 17/07/25 | Fri 01/08/25 | 12 days | Thu 17/07/25 | Fri 01/08/25 | 0 days | 0 days | 12 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.6.1.1 |  |  | Helix Programme Board |  | Pre-M10 | 100% | Thu 17/07/25 | Thu 17/07/25 | 1 day | Thu 17/07/25 | Thu 17/07/25 | 0 days | 0 days | 1 day | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.6.1.2 |  |  | Helix Programme Board |  | GMT & BST & Long | 100% | Fri 18/07/25 | Fri 25/07/25 | 6 days | Fri 18/07/25 | Fri 25/07/25 | 0 days | 0 days | 6 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.6.1.3 |  |  | Helix Programme Board |  | NESO Validation Period (GMT & BST & Long) | 100% | Mon 28/07/25 | Fri 01/08/25 | 5 days | Mon 28/07/25 | Fri 01/08/25 | 0 days | 0 days | 5 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.6.1.4 |  |  | Helix Programme Board |  | Trading Dispute | 100% | Mon 28/07/25 | Tue 29/07/25 | 2 days | Mon 28/07/25 | Tue 29/07/25 | 0 days | 0 days | 2 days | Helix |  | 6.26 | Yes
7 | 1.6.4.3.3.6.2 |  |  | Helix Programme Board |  | Transition | 100% | Thu 24/07/25 | Tue 29/07/25 | 4 days | Thu 24/07/25 | Tue 29/07/25 | 0 days | 0 days | 4 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.6.2.1 |  |  | Helix Programme Board |  | ISD | 100% | Thu 24/07/25 | Tue 29/07/25 | 4 days | Thu 24/07/25 | Tue 29/07/25 | 0 days | 0 days | 4 days | Helix |  | 6.26 | Yes
8 | 1.6.4.3.3.6.2.2 |  |  | Helix Programme Board |  | Data Agg | 100% | Thu 24/07/25 | Mon 28/07/25 | 3 days | Thu 24/07/25 | Mon 28/07/25 | 0 days | 0 days | 3 days | Helix |  | 6.26 | Yes
7 | 1.6.4.3.3.6.3 |  |  | Helix Programme Board |  | End of Cycle 2 | 100% | Fri 01/08/25 | Fri 01/08/25 | 0 days | Fri 01/08/25 | Fri 01/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
6 | 1.6.4.3.3.7 |  |  | Helix Programme Board |  | SAT Exit Report | 100% | Fri 01/08/25 | Fri 15/08/25 | 11 days | Fri 01/08/25 | Fri 15/08/25 | 0 days | 0 days | 11 days | Helix |  | 6.31 | Yes
5 | 1.6.4.3.4 |  |  | Helix Programme Board |  | SAT Complete | 100% | Fri 01/08/25 | Fri 01/08/25 | 0 days | Fri 01/08/25 | Fri 01/08/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
4 | 1.6.4.4 |  |  | Helix Programme Board |  | DR Testing | 100% | Mon 28/04/25 | Fri 29/08/25 | 90 days | Mon 28/04/25 | Fri 06/06/25 | 0 days | 60 days | 90 days | Helix |  | 6.3 | Yes
4 | 1.6.4.5 |  |  | Helix Programme Board |  | Pen Testing | 100% | Mon 28/04/25 | Fri 20/06/25 | 40 days? | Mon 28/04/25 | Fri 20/06/25 | 0 days | 0 days | 40 days? | Helix |  | 6.26 | Yes
4 | 1.6.4.6 |  |  | Helix Programme Board |  | Production Environment Build | 100% | Mon 30/06/25 | Fri 15/08/25 | 35 days | Mon 30/06/25 | Thu 31/07/25 | 0 days | 11 days | 35 days | Helix |  | 6.28 | Yes
4 | 1.6.4.7 |  |  | Helix Programme Board |  | Production Environment Base Platform Sign-off | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Fri 08/08/25 | Fri 08/08/25 | 6 days | 5 days | 0 days | Helix |  | 6.28 | Yes
3 | 1.6.5 |  |  | Helix Programme Board |  | Implementation (Helix & DIP) | 100% | Mon 28/04/25 | Mon 06/10/25 | 116 days | Mon 28/04/25 | Mon 06/10/25 | 0 days | 0 days | 116 days | Helix |  | 6.26 | Yes
4 | 1.6.5.1 |  |  | Helix Programme Board |  | Go / No-Go (DIP & SM) | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 0 days | -1 day | 0 days | Helix |  | 6.26 | Yes
4 | 1.6.5.2 |  |  | Helix Programme Board |  | Implementation Readiness (inc Technical Readiness, Approach and Runbook, Walkthrough / Rehearsals | 100% | Mon 28/04/25 | Mon 04/08/25 | 71 days | Mon 28/04/25 | Mon 04/08/25 | 0 days | 0 days | 71 days | Helix |  | 6.28 | Yes
4 | 1.6.5.3 |  |  | Helix Programme Board |  | M10 Implementation Approach & Go-Live Runbook | 100% | Mon 28/04/25 | Mon 30/06/25 | 46 days | Mon 28/04/25 | Fri 06/06/25 | 0 days | 16 days | 46 days | Helix |  | 6.28 | Yes
4 | 1.6.5.4 |  |  | Helix Programme Board |  | DIP Production Build | 100% | Mon 09/06/25 | Fri 27/06/25 | 15 days | Mon 09/06/25 | Fri 27/06/25 | 0 days | 0 days | 15 days | Helix |  | 6.28 | Yes
4 | 1.6.5.5 |  |  | Helix Programme Board |  | Final Production Deployment | 100% | Mon 07/07/25 | Fri 15/08/25 | 30 days | Mon 07/07/25 | Thu 31/07/25 | 0 days | 11 days | 30 days | Helix |  | 6.28 | Yes
4 | 1.6.5.6 |  |  | Helix Programme Board |  | DIP Portal Available | 100% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 04/08/25 | Mon 04/08/25 | 1 day | 0 days | 0 days | Helix |  | 6.28 | Yes
4 | 1.6.5.7 |  |  | Helix Programme Board |  | Go / No-Go (Helix Central Systems) | 100% | Tue 12/08/25 | Tue 12/08/25 | 0 days | Fri 08/08/25 | Fri 08/08/25 | 2 days | 1 day | 0 days | Helix |  | 6.28 | Yes
4 | 1.6.5.8 |  |  | Helix Programme Board |  | ISD Data Migration | 100% | Mon 18/08/25 | Fri 29/08/25 | 10 days | Fri 15/08/25 | Tue 26/08/25 | 1 day | 3 days | 10 days | Helix |  | 6.32 | Yes
4 | 1.6.5.9 |  |  | Helix Programme Board |  | DAH & ISD Dark Mode | 100% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Tue 26/08/25 | Tue 26/08/25 | 4 days | 3 days | 0 days | Helix |  | 6.32 | Yes
4 | 1.6.5.10 |  |  | Helix Programme Board |  | VAS Inspection pre-prod | 100% | Wed 27/08/25 | Wed 17/09/25 | 16 days | Wed 27/08/25 | Wed 17/09/25 | 0 days | 0 days | 16 days | Helix |  | 6.32 | Yes
4 | 1.6.5.11 |  |  | Helix Programme Board |  | M10 Cutover Weekend (20/09 and 21/09) | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Mon 22/09/25 | Mon 22/09/25 | -1 day | 0 days | 2 days | Helix |  | 6.32 | Yes
4 | 1.6.5.12 |  |  | Helix Programme Board |  | Post Implementation Review | 100% | Mon 06/10/25 | Mon 06/10/25 | 1 day | Mon 06/10/25 | Mon 06/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.32 | Yes
2 | 1.7 |  |  | Helix Programme Board |  | ELEXON / HELIX M10 - M16 | 77% | Wed 03/09/25 | Wed 09/12/26 | 331 days | Wed 03/09/25 | Wed 09/12/26 | 0 days | 0 days | 331 days | Helix |  | 6.34 | Yes
3 | 1.7.1 |  |  | Helix Programme Board |  | Solution Build Sprints | 59% | Wed 03/09/25 | Tue 31/03/26 | 150 days | Wed 03/09/25 | Tue 31/03/26 | 0 days | 0 days | 150 days | Helix |  | 6.38 | Yes
4 | 1.7.1.1 |  |  | Helix Programme Board |  | 25.18 | 100% | Wed 03/09/25 | Tue 16/09/25 | 10 days | Wed 03/09/25 | Tue 16/09/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.2 |  |  | Helix Programme Board |  | 25.19 | 100% | Wed 17/09/25 | Tue 30/09/25 | 10 days | Wed 17/09/25 | Tue 30/09/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.3 |  |  | Helix Programme Board |  | 25.2 | 100% | Wed 01/10/25 | Tue 14/10/25 | 10 days | Wed 01/10/25 | Tue 14/10/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.4 |  |  | Helix Programme Board |  | 25.21 | 100% | Wed 15/10/25 | Tue 28/10/25 | 10 days | Wed 15/10/25 | Tue 28/10/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.5 |  |  | Helix Programme Board |  | 25.22 | 100% | Wed 29/10/25 | Tue 11/11/25 | 10 days | Wed 29/10/25 | Tue 11/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.6 |  |  | Helix Programme Board |  | 25.23 | 100% | Wed 12/11/25 | Tue 25/11/25 | 10 days | Wed 12/11/25 | Tue 25/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.7 |  |  | Helix Programme Board |  | 25.24 | 100% | Wed 26/11/25 | Fri 19/12/25 | 18 days | Wed 26/11/25 | Fri 19/12/25 | 0 days | 0 days | 18 days | Helix |  | 6.38 | Yes
4 | 1.7.1.8 |  |  | Helix Programme Board |  | 26.1 | 30% | Wed 07/01/26 | Tue 20/01/26 | 10 days | Wed 07/01/26 | Tue 20/01/26 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes |  | 28/01/26 - Awaiting updates from Helix
4 | 1.7.1.9 |  |  | Helix Programme Board |  | 26.2 | 0% | Wed 21/01/26 | Tue 03/02/26 | 10 days | Wed 21/01/26 | Tue 03/02/26 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.10 |  |  | Helix Programme Board |  | 26.3 | 0% | Wed 04/02/26 | Tue 17/02/26 | 10 days | Wed 04/02/26 | Tue 17/02/26 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.11 |  |  | Helix Programme Board |  | 26.4 | 0% | Wed 18/02/26 | Tue 03/03/26 | 10 days | Wed 18/02/26 | Tue 03/03/26 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.12 |  |  | Helix Programme Board |  | 26.5 | 0% | Wed 04/03/26 | Tue 17/03/26 | 10 days | Wed 04/03/26 | Tue 17/03/26 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
4 | 1.7.1.13 |  |  | Helix Programme Board |  | 26.6 | 0% | Wed 18/03/26 | Tue 31/03/26 | 10 days | Wed 18/03/26 | Tue 31/03/26 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
3 | 1.7.2 |  |  | Helix Programme Board |  | Release management deployment schedule | 84% | Wed 17/09/25 | Wed 09/12/26 | 321 days | Wed 17/09/25 | Wed 09/12/26 | 0 days | 0 days | 321 days | Helix |  | 6.38 | Yes
4 | 1.7.2.1 |  |  | Helix Programme Board |  | 25.14.5 | 100% | Mon 20/10/25 | Mon 20/10/25 | 1 day | Mon 20/10/25 | Mon 20/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.2 |  |  | Helix Programme Board |  | 25.14.6 | 100% | Tue 04/11/25 | Tue 04/11/25 | 1 day | Tue 04/11/25 | Tue 04/11/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.3 |  |  | Helix Programme Board |  | 25.14.7 | 100% | Wed 19/11/25 | Wed 19/11/25 | 1 day | Wed 19/11/25 | Wed 19/11/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.4 |  |  | Helix Programme Board |  | 25.14.8 | 100% | Wed 03/12/25 | Wed 03/12/25 | 1 day | Tue 02/12/25 | Tue 02/12/25 | 1 day | 1 day | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.5 |  |  | Helix Programme Board |  | 25.14.9 | 100% | Thu 11/12/25 | Thu 11/12/25 | 1 day | Thu 11/12/25 | Thu 11/12/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.6 |  |  | Helix Programme Board |  | 26.1.0 | 0% | Thu 22/01/26 | Thu 22/01/26 | 1 day | Thu 22/01/26 | Thu 22/01/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes |  | 28/01/26 - Awaiting updates from Helix
4 | 1.7.2.7 |  |  | Helix Programme Board |  | 26.2.0 | 0% | Thu 05/02/26 | Thu 05/02/26 | 1 day | Thu 05/02/26 | Thu 05/02/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.8 |  |  | Helix Programme Board |  | 26.3.0 | 0% | Thu 19/02/26 | Thu 19/02/26 | 1 day | Thu 19/02/26 | Thu 19/02/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.9 |  |  | Helix Programme Board |  | 26.4.0 | 0% | Thu 05/03/26 | Thu 05/03/26 | 1 day | Thu 05/03/26 | Thu 05/03/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.10 |  |  | Helix Programme Board |  | 26.5.0 | 0% | Thu 19/03/26 | Thu 19/03/26 | 1 day | Thu 19/03/26 | Thu 19/03/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
4 | 1.7.2.11 |  |  | Helix Programme Board |  | Work Package Development | 85% | Wed 17/09/25 | Wed 09/12/26 | 321 days | Wed 17/09/25 | Wed 09/12/26 | 0 days | 0 days | 321 days | Helix |  | 6.38 | Yes
5 | 1.7.2.11.1 |  |  | Helix Programme Board |  | DAH | 88% | Wed 17/09/25 | Tue 31/03/26 | 140 days | Wed 17/09/25 | Tue 31/03/26 | 0 days | 0 days | 140 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.1 |  |  | Helix Programme Board |  | MSID Counts and Missing DA files (Bronze to Silver) | 100% | Wed 17/09/25 | Tue 30/09/25 | 10 days | Wed 17/09/25 | Tue 30/09/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.2 |  |  | Helix Programme Board |  | P0276 & P0277 Reports | 100% | Wed 01/10/25 | Tue 14/10/25 | 10 days | Wed 01/10/25 | Tue 14/10/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.3 |  |  | Helix Programme Board |  | Throughput monitoring for DIP ingestion | 100% | Wed 17/09/25 | Tue 28/10/25 | 30 days | Wed 17/09/25 | Tue 28/10/25 | 0 days | 0 days | 30 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.4 |  |  | Helix Programme Board |  | P0213 Report | 100% | Wed 29/10/25 | Tue 11/11/25 | 10 days | Wed 29/10/25 | Tue 11/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.5 |  |  | Helix Programme Board |  | P0214 Report | 100% | Wed 29/10/25 | Tue 11/11/25 | 10 days | Wed 29/10/25 | Tue 11/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.6 |  |  | Helix Programme Board |  | P0275 Report | 100% | Wed 29/10/25 | Tue 11/11/25 | 10 days | Wed 29/10/25 | Tue 11/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.7 |  |  | Helix Programme Board |  | Errors & warnings in new DAH table | 100% | Wed 15/10/25 | Tue 11/11/25 | 20 days | Wed 15/10/25 | Tue 11/11/25 | 0 days | 0 days | 20 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.8 |  |  | Helix Programme Board |  | Electralink | 72% | Wed 12/11/25 | Tue 03/02/26 | 60 days | Wed 12/11/25 | Tue 03/02/26 | 0 days | 0 days | 60 days | Helix |  | 6.41 | Yes
6 | 1.7.2.11.1.9 |  |  | Helix Programme Board |  | CP1607 IF-51 Data Refresh (CR044) | 100% | Wed 15/10/25 | Tue 31/03/26 | 120 days | Wed 15/10/25 | Tue 31/03/26 | 0 days | 0 days | 120 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.10 |  |  | Helix Programme Board |  | CP1606 Supplier Start Date Correction Tools (CR045) | 100% | Wed 26/11/25 | Tue 31/03/26 | 90 days | Wed 26/11/25 | Tue 31/03/26 | 0 days | 0 days | 90 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.1.11 |  |  | Helix Programme Board |  | MDS Annual Consumption | 30% | Wed 07/01/26 | Tue 20/01/26 | 10 days | Wed 07/01/26 | Tue 20/01/26 | 0 days | 0 days | 10 days | Helix |  | 6.41 | Yes |  | 28/01/26 - Awaiting updates from Helix
6 | 1.7.2.11.1.12 |  |  | Helix Programme Board |  | Missing Parms report | 10% | Wed 07/01/26 | Tue 17/02/26 | 30 days | Wed 07/01/26 | Tue 17/02/26 | 0 days | 0 days | 30 days | Helix |  | 6.41 | Yes
5 | 1.7.2.11.2 |  |  | Helix Programme Board |  | WP2 (LSS/MDS/VAS/OP) | 80% | Wed 17/09/25 | Wed 09/12/26 | 321 days | Wed 17/09/25 | Wed 09/12/26 | 0 days | 0 days | 321 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.2.1 |  |  | Helix Programme Board |  | Implementation of P0275 | 100% | Wed 15/10/25 | Tue 16/12/25 | 45 days | Wed 15/10/25 | Tue 16/12/25 | 0 days | 0 days | 45 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.2.2 |  |  | Helix Programme Board |  | SCCS Technical Work | 100% | Wed 29/10/25 | Tue 11/11/25 | 10 days | Wed 29/10/25 | Tue 11/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.2.3 |  |  | Helix Programme Board |  | SCCS Report | 100% | Wed 12/11/25 | Tue 25/11/25 | 10 days | Wed 12/11/25 | Tue 25/11/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.2.4 |  |  | Helix Programme Board |  | LSS Publishing Load Shapes | 88% | Wed 29/10/25 | Tue 20/01/26 | 60 days | Wed 29/10/25 | Tue 20/01/26 | 0 days | 0 days | 60 days | Helix |  | 6.41 | Yes |  | 28/01/26 - Awaiting updates from Helix
6 | 1.7.2.11.2.5 |  |  | Helix Programme Board |  | Update configuration parameters into Operator Portal for LSS / VAS | 100% | Wed 17/09/25 | Tue 30/09/25 | 10 days | Wed 17/09/25 | Tue 30/09/25 | 0 days | 0 days | 10 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.2.6 |  |  | Helix Programme Board |  | Operator Portal Configuration Parameters (part 1) | 100% | Wed 17/09/25 | Tue 14/10/25 | 20 days | Wed 17/09/25 | Tue 14/10/25 | 0 days | 0 days | 20 days | Helix |  | 6.38 | Yes
6 | 1.7.2.11.2.7 |  |  | Helix Programme Board |  | MDS Annual Consumption | 30% | Wed 07/01/26 | Tue 20/01/26 | 10 days | Wed 07/01/26 | Tue 20/01/26 | 0 days | 0 days | 10 days | Helix |  | 6.41 | Yes |  | 28/01/26 - Awaiting updates from Helix
6 | 1.7.2.11.2.8 |  |  | Helix Programme Board |  | Missing Parms report | 0% | Wed 21/01/26 | Tue 17/02/26 | 20 days | Wed 21/01/26 | Tue 17/02/26 | 0 days | 0 days | 20 days | Helix |  | 6.41 | Yes
6 | 1.7.2.11.2.9 |  |  | Helix Programme Board |  | Settlement Checks | 50% | Mon 22/09/25 | Wed 09/12/26 | 318 days | Mon 22/09/25 | Wed 09/12/26 | 0 days | 0 days | 318 days | Helix |  | 6.38 | Yes
7 | 1.7.2.11.2.9.1 |  |  | Helix Programme Board |  | M10 | 40% | Mon 22/09/25 | Mon 09/11/26 | 296 days | Mon 22/09/25 | Mon 09/11/26 | 0 days | 0 days | 296 days | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.1.1 |  |  | Helix Programme Board |  | M10 Settlement Start Date | 100% | Mon 22/09/25 | Mon 22/09/25 | 1 day | Mon 22/09/25 | Mon 22/09/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.1.2 |  |  | Helix Programme Board |  | R1 | 100% | Mon 06/10/25 | Mon 06/10/25 | 1 day | Mon 06/10/25 | Mon 06/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.1.3 |  |  | Helix Programme Board |  | R2 | 0% | Wed 14/01/26 | Wed 14/01/26 | 1 day | Wed 14/01/26 | Wed 14/01/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes |  | 28/01/26 - Awaiting updates from Helix
8 | 1.7.2.11.2.9.1.4 |  |  | Helix Programme Board |  | R3 | 0% | Fri 24/04/26 | Fri 24/04/26 | 1 day | Fri 24/04/26 | Fri 24/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.1.5 |  |  | Helix Programme Board |  | RF | 0% | Mon 09/11/26 | Mon 09/11/26 | 1 day | Mon 09/11/26 | Mon 09/11/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
7 | 1.7.2.11.2.9.2 |  |  | Helix Programme Board |  | M11 | 57% | Wed 22/10/25 | Wed 09/12/26 | 296 days | Wed 22/10/25 | Wed 09/12/26 | 0 days | 0 days | 296 days | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.1 |  |  | Helix Programme Board |  | M11 Settlement Start Date | 100% | Wed 22/10/25 | Wed 22/10/25 | 1 day | Wed 22/10/25 | Wed 22/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.2 |  |  | Helix Programme Board |  | II | 100% | Tue 28/10/25 | Tue 28/10/25 | 1 day | Tue 28/10/25 | Tue 28/10/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.3 |  |  | Helix Programme Board |  | SF | 100% | Wed 12/11/25 | Wed 12/11/25 | 1 day | Wed 12/11/25 | Wed 12/11/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.4 |  |  | Helix Programme Board |  | R1 | 100% | Tue 09/12/25 | Tue 09/12/25 | 1 day | Tue 09/12/25 | Tue 09/12/25 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.5 |  |  | Helix Programme Board |  | R2 | 0% | Fri 13/02/26 | Fri 13/02/26 | 1 day | Fri 13/02/26 | Fri 13/02/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.6 |  |  | Helix Programme Board |  | R3 | 0% | Thu 28/05/26 | Thu 28/05/26 | 1 day | Thu 28/05/26 | Thu 28/05/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
8 | 1.7.2.11.2.9.2.7 |  |  | Helix Programme Board |  | RF | 0% | Wed 09/12/26 | Wed 09/12/26 | 1 day | Wed 09/12/26 | Wed 09/12/26 | 0 days | 0 days | 1 day | Helix |  | 6.38 | Yes
3 | 1.7.3 |  |  | Helix Programme Board |  | SAT M16 Test Case Execution | 0% | Wed 01/07/26 | Thu 30/07/26 | 22 days | Wed 01/07/26 | Thu 30/07/26 | 0 days | 0 days | 22 days | Helix |  | 6.34 | Yes
3 | 1.7.4 |  |  | Helix Programme Board |  | LSS provides Load Shape data that is publicly accessible - Business Requirement MHHSP-37 | 0% | Wed 08/04/26 | Wed 08/04/26 | 0 days | Wed 08/04/26 | Wed 08/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
2 | 1.8 |  |  |  |  | S & A QUALIFICATION | 88% | Tue 07/11/23 | Thu 28/01/27 | 843 days? | Tue 07/11/23 | Thu 28/01/27 | 0 days | 0 days | 240 days? | N/A |  | 5.24 | Yes
3 | 1.8.1 |  |  |  |  | MHHS Qualification - Qualification Deliverables | 100% | Tue 07/11/23 | Fri 17/10/25 | 509 days | Tue 07/11/23 | Thu 14/08/25 | 0 days | 46 days | 160 days | N/A |  | 5.24 | Yes
4 | 1.8.1.1 |  |  |  |  | BSC & REC Assessment Criteria | 100% | Tue 07/11/23 | Thu 14/08/25 | 463 days | Tue 07/11/23 | Thu 14/08/25 | 0 days | 0 days | 251 days | N/A |  | 5.24 | Yes
5 | 1.8.1.1.1 |  |  |  |  | Draft BSC Assessment Criteria (Functional) | 100% | Tue 07/11/23 | Tue 05/12/23 | 21 days | Tue 07/11/23 | Tue 05/12/23 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.1.2 |  |  |  |  | BSC PAB Review | 100% | Thu 14/12/23 | Thu 14/12/23 | 1 day | Thu 14/12/23 | Thu 14/12/23 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.1.3 |  |  |  |  | Update BSC Assessment Criteria (Functional, Non-Functional, Migration) | 100% | Wed 07/02/24 | Tue 19/03/24 | 30 days | Wed 07/02/24 | Tue 19/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.1.4 |  |  |  |  | REC & BSC PAB Approval | 100% | Tue 26/03/24 | Thu 28/03/24 | 3 days | Tue 26/03/24 | Thu 28/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.1.5 |  |  |  |  | Update BSC Assessment Criteria (Functional, Non-Functional, Migration, Operational) | 100% | Wed 24/07/24 | Tue 20/08/24 | 20 days | Wed 24/07/24 | Tue 20/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.1.6 | T3 | T3-QU-0080 | QAG |  | Assessment Criteria (Functional, Non-Functional, Migration, Operational) Approved by REC PAB and BSC PAB | 100% | Thu 29/08/24 | Thu 14/08/25 | 250 days | Thu 29/08/24 | Thu 14/08/25 | 1 day | 0 days | 250 days | Code Bodies |  | 5.25 | Yes
4 | 1.8.1.2 |  |  |  |  | Qualification Approach and Plan | 100% | Mon 04/12/23 | Thu 29/08/24 | 194 days | Mon 04/12/23 | Thu 29/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.8.1.2.1 |  |  |  |  | Qualification Approach and Plan v2 | 100% | Mon 04/12/23 | Thu 28/03/24 | 84 days | Mon 04/12/23 | Thu 28/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.8.1.2.1.1 |  |  |  |  | Draft Qualification Approach and Plan v2 | 100% | Mon 04/12/23 | Fri 12/01/24 | 30 days | Mon 04/12/23 | Fri 12/01/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.2.1.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) for Qualification Approach and Plan V2 | 100% | Mon 15/01/24 | Fri 26/01/24 | 10 days | Mon 15/01/24 | Fri 26/01/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.8.1.2.1.3 |  |  |  |  | Industry consultation for Qualification Approach and Plan v2 | 100% | Wed 31/01/24 | Wed 14/02/24 | 11 days | Wed 31/01/24 | Wed 14/02/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.1.2.1.4 |  |  |  |  | Update Qualification Approach and Plan v2 post industry consultation | 100% | Thu 15/02/24 | Wed 28/02/24 | 10 days | Thu 15/02/24 | Wed 28/02/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.2.1.5 |  |  |  |  | QWG Endorsement of Qualification Approach and Plan v2 | 100% | Tue 12/03/24 | Tue 12/03/24 | 1 day | Tue 12/03/24 | Tue 12/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.2.1.6 |  |  |  |  | QAG Approval of Qualification Approach and Plan v2 | 100% | Thu 21/03/24 | Thu 21/03/24 | 1 day | Thu 21/03/24 | Thu 21/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.2.1.7 |  |  |  |  | BSC and REC PAB Approval of Qualification Approach and Plan v2 | 100% | Tue 26/03/24 | Thu 28/03/24 | 3 days | Tue 26/03/24 | Thu 28/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.2.1.8 | T3 | T3-QU-0063 | QAG |  | Functional Testing elements of Qualification Approach & Plan v2 approvement by REC PAB and BSC PAB | 100% | Thu 28/03/24 | Thu 28/03/24 | 0 days | Thu 28/03/24 | Thu 28/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.2.1.9 | T3 | T3-QU-0064 | QAG |  | Migration Testing elements of Qualification Approach & Plan v2 appoved by REC PAB and BSC PAB | 100% | Thu 28/03/24 | Thu 28/03/24 | 0 days | Thu 28/03/24 | Thu 28/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.2.2 |  |  |  |  | Qualification Approach and Plan v3 | 100% | Mon 06/05/24 | Thu 29/08/24 | 84 days | Mon 06/05/24 | Thu 29/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.8.1.2.2.1 |  |  |  |  | Draft Qualification Approach and Plan v3 | 100% | Mon 06/05/24 | Fri 21/06/24 | 35 days | Mon 06/05/24 | Fri 21/06/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.1.2.2.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Approach and Plan v3 | 100% | Mon 24/06/24 | Fri 05/07/24 | 10 days | Mon 24/06/24 | Fri 05/07/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.27 | Yes
6 | 1.8.1.2.2.3 |  |  |  |  | Industry consultation for Qualification Approach and Plan v3 | 100% | Mon 08/07/24 | Fri 19/07/24 | 10 days | Mon 08/07/24 | Fri 19/07/24 | 0 days | 0 days | 0 days | Participants |  | 5.27 | Yes
6 | 1.8.1.2.2.4 |  |  |  |  | Update Qualification Approach and Plan v3 Post-Consultation | 100% | Mon 22/07/24 | Fri 02/08/24 | 10 days | Mon 22/07/24 | Fri 02/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.1.2.2.5 |  |  |  |  | QWG Endorsement of Qualification Approach and Plan v3 | 100% | Tue 13/08/24 | Tue 13/08/24 | 1 day | Tue 13/08/24 | Tue 13/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.1.2.2.6 | T3 | T3-QU-0081 | QAG |  | QAG Approval of Qualification Approach and Plan v3 | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.1.2.2.7 |  |  |  |  | BSC and REC PAB Approval of Qualification Approach and Plan v3 | 100% | Tue 27/08/24 | Thu 29/08/24 | 3 days | Tue 27/08/24 | Thu 29/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.1.2.2.8 | T3 | T3-QU-0065 | QAG |  | Non-Functional Testing elements of Qualification Approach and Plan v3 approved by REC PAB and BSC PAB | 100% | Thu 29/08/24 | Thu 29/08/24 | 0 days | Thu 29/08/24 | Thu 29/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
4 | 1.8.1.3 |  |  |  |  | Qualification Assessment Document | 100% | Fri 22/12/23 | Fri 17/10/25 | 476 days | Fri 22/12/23 | Fri 07/03/25 | 0 days | 160 days | 160 days | N/A |  | 5.24 | Yes
5 | 1.8.1.3.1 |  |  |  |  | Qualification Assessment Document v1 | 100% | Fri 22/12/23 | Thu 28/03/24 | 70 days | Fri 22/12/23 | Thu 28/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.8.1.3.1.1 |  |  |  |  | Draft Qualification Assessment Document v1 | 100% | Fri 22/12/23 | Thu 01/02/24 | 30 days | Fri 22/12/23 | Thu 01/02/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.1.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Assessment Document v1 | 100% | Thu 01/02/24 | Wed 14/02/24 | 10 days | Thu 01/02/24 | Wed 14/02/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.8.1.3.1.3 |  |  |  |  | Industry consultation for Qualification Assessment Document v1 | 100% | Fri 16/02/24 | Fri 01/03/24 | 11 days | Fri 16/02/24 | Fri 01/03/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.1.3.1.4 |  |  |  |  | Update Post-Consultation for Qualification Assessment Document v1 | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.1.5 |  |  |  |  | BSC and REC PAB Approval of Qualification Assessment Document v1 | 100% | Tue 26/03/24 | Thu 28/03/24 | 3 days | Tue 26/03/24 | Thu 28/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.1.6 | T3 | T3-QU-0066 | QAG |  | Qualification Assessment Document v1 approved by REC PAB and BSC PAB | 100% | Thu 28/03/24 | Thu 28/03/24 | 0 days | Thu 28/03/24 | Thu 28/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.3.2 |  |  |  |  | Qualification Assessment Document v3 | 100% | Fri 29/03/24 | Thu 29/08/24 | 110 days | Fri 29/03/24 | Thu 29/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.8.1.3.2.1 |  |  |  |  | Draft Qualification Assessment Document V1.1 | 100% | Fri 29/03/24 | Fri 03/05/24 | 26 days | Fri 29/03/24 | Fri 03/05/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.2.2 |  |  |  |  | Industry Consultation for Qualification Assessment Document V1.1 | 100% | Mon 06/05/24 | Tue 21/05/24 | 12 days | Mon 06/05/24 | Tue 21/05/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.1.3.2.3 |  |  |  |  | Draft Qualification Assessment Document v3 | 100% | Fri 14/06/24 | Fri 21/06/24 | 6 days | Fri 14/06/24 | Fri 21/06/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.2.4 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Assessment Document v3 | 100% | Mon 24/06/24 | Fri 05/07/24 | 10 days | Mon 24/06/24 | Fri 05/07/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.8.1.3.2.5 |  |  |  |  | Industry consultation for Qualification Assessment Document v3 | 100% | Mon 08/07/24 | Fri 19/07/24 | 10 days | Mon 08/07/24 | Fri 19/07/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.1.3.2.6 |  |  |  |  | Update Post-Consultation for Qualification Assessment Document v3 | 100% | Mon 22/07/24 | Fri 02/08/24 | 10 days | Mon 22/07/24 | Fri 02/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.2.7 |  |  |  |  | QWG Endorsement of Qualification Assessment Document v3 | 100% | Tue 13/08/24 | Tue 13/08/24 | 1 day | Tue 13/08/24 | Tue 13/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.2.8 | T3 | T3-QU-0083 | QAG |  | QAG Endorsement of Qualification Assessment Document v3 | 100% | Thu 22/08/24 | Thu 22/08/24 | 1 day | Thu 22/08/24 | Thu 22/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.25 | Yes
6 | 1.8.1.3.2.9 |  |  |  |  | BSC and REC PAB Approval of Qualification Assessment Document v3 | 100% | Tue 27/08/24 | Thu 29/08/24 | 3 days | Tue 27/08/24 | Thu 29/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.2.10 | T3 | T3-QU-0067 | QAG |  | Qualification Assessment Document v3 approved by REC PAB and BSC PAB | 100% | Thu 29/08/24 | Thu 29/08/24 | 0 days | Thu 29/08/24 | Thu 29/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.8.1.3.3 |  |  |  |  | Qualification Assessment Document Portal | 100% | Mon 05/02/24 | Fri 17/10/25 | 445 days | Mon 05/02/24 | Fri 07/03/25 | 0 days | 160 days | 160 days | N/A |  | 5.24 | Yes
6 | 1.8.1.3.3.1 |  |  |  |  | Design Completion | 100% | Mon 05/02/24 | Fri 15/03/24 | 30 days | Mon 05/02/24 | Fri 15/03/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.8.1.3.3.2 |  |  |  |  | Qualification Assessment Document Portal Build | 100% | Mon 18/03/24 | Fri 26/04/24 | 30 days | Mon 18/03/24 | Fri 26/04/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.8.1.3.3.3 |  |  |  |  | Qualification Assessment Document Internal Testing | 100% | Mon 29/04/24 | Fri 24/05/24 | 20 days | Mon 29/04/24 | Fri 24/05/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team. Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.3.4 |  |  |  |  | Qualification Assessment Document Portal Training and Onboarding Material Creation | 100% | Mon 27/05/24 | Fri 21/06/24 | 20 days | Mon 27/05/24 | Fri 21/06/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.8.1.3.3.5 |  |  |  |  | Qualification Assessment Document Portal Webinar (Date TBC) | 100% | Tue 18/06/24 | Tue 18/06/24 | 1 day | Tue 18/06/24 | Tue 18/06/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.8.1.3.3.6 |  |  |  |  | SIT Participant QAD Application Creation in Portal | 100% | Mon 09/12/24 | Fri 20/12/24 | 10 days | Mon 09/12/24 | Fri 20/12/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.3.7 |  |  |  |  | Non-SIT LDSO Participant QAD Application Creation in Portal | 100% | Mon 09/12/24 | Fri 20/12/24 | 10 days | Mon 09/12/24 | Fri 20/12/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.1.3.3.8 |  |  |  |  | QT Wave 1 Participant QAD Application Creation in Portal | 100% | Mon 21/04/25 | Fri 02/05/25 | 10 days | Mon 21/04/25 | Fri 02/05/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.8.1.3.3.9 |  |  |  |  | QT Wave 2 Participant QAD Application Creation in Portal | 100% | Mon 26/05/25 | Fri 06/06/25 | 10 days | Mon 26/05/25 | Fri 06/06/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.8.1.3.3.10 |  |  |  |  | QT Wave 3 Participant QAD Application Creation in Portal | 100% | Mon 28/07/25 | Fri 08/08/25 | 10 days | Mon 28/07/25 | Fri 08/08/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.8.1.3.3.11 |  |  |  |  | QT Wave 4 Participant QAD Application Creation in Portal | 100% | Mon 06/10/25 | Fri 17/10/25 | 10 days | Mon 06/10/25 | Fri 17/10/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.8.1.3.3.12 |  |  |  |  | Update to Qualification Assessment Document Portal post QAD V3 | 100% | Fri 30/08/24 | Thu 12/09/24 | 10 days | Fri 30/08/24 | Thu 12/09/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 6.1 | Yes
6 | 1.8.1.3.3.13 | T3 | T3-QU-0084 | QAG |  | Update to Qualification Assessment Document Portal post QAD V3 Complete | 100% | Thu 12/09/24 | Thu 12/09/24 | 0 days | Thu 12/09/24 | Thu 12/09/24 | 1 day | 0 days | 0 days | QAD Portal Dev Team |  | 6.1 | Yes
3 | 1.8.2 |  |  |  |  | MHHS Qualification - SIT Participants | 99% | Mon 06/01/25 | Thu 30/07/26 | 408 days? | Mon 06/01/25 | Mon 22/12/25 | 0 days | 157 days | 214 days? | N/A |  | 6.11 | Yes
4 | 1.8.2.1 |  |  |  |  | Initial QAD Submission Window opens | 100% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Mon 06/01/25 | Mon 06/01/25 | 0 days | -1 day | 0 days | Participants |  | 6.11 | Yes
4 | 1.8.2.2 |  |  |  |  | SIT Participants submit Initial QAD | 100% | Mon 06/01/25 | Fri 14/02/25 | 30 days | Mon 06/01/25 | Fri 14/02/25 | 0 days | 0 days | 1 day | Participants |  | 6.11 | Yes
4 | 1.8.2.3 |  |  |  |  | Code Bodies review Initial QAD | 100% | Fri 14/02/25 | Fri 04/04/25 | 36 days | Fri 14/02/25 | Fri 04/04/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.8.2.4 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 100% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.8.2.5 |  |  |  |  | MHHS Qualification - M10-Ready | 100% | Mon 07/04/25 | Wed 10/09/25 | 113 days | Mon 07/04/25 | Thu 11/09/25 | 0 days | -1 day | 49 days | N/A |  | 6.25 | Yes
5 | 1.8.2.5.1 |  |  |  |  | Final QAD Submission Window opens | 100% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 1 day | 0 days | 0 days | Participants |  | 6.25 | Yes
5 | 1.8.2.5.2 |  |  |  |  | SIT M10-ready Participants submit Final QAD (exc Test Reports) | 100% | Mon 07/04/25 | Fri 09/05/25 | 25 days | Mon 07/04/25 | Fri 09/05/25 | 0 days | 0 days | -1 day | Participants |  | 6.25 | Yes
5 | 1.8.2.5.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (M10-Ready) | 100% | Mon 12/05/25 | Fri 06/06/25 | 20 days | Mon 12/05/25 | Fri 06/06/25 | 0 days | 0 days | 1 day | Code Bodies |  | 6.25 | Yes
5 | 1.8.2.5.4 |  |  |  |  | SIT / LDSO Pathway 2 | 100% | Thu 07/08/25 | Thu 28/08/25 | 16 days | Thu 07/08/25 | Thu 28/08/25 | 0 days | 0 days | 16 days |  |  | 6.25 | Yes
6 | 1.8.2.5.4.1 |  |  |  |  | QAD Sign Off Deadline + Test Reports | 100% | Thu 07/08/25 | Thu 07/08/25 | 0 days | Thu 07/08/25 | Thu 07/08/25 | 0 days | -1 day | 0 days | Participants |  | 6.25 | Yes
6 | 1.8.2.5.4.2 |  |  |  |  | REC Code Manager / BSC PAB Approval of Qualification (M10-Ready) | 100% | Thu 28/08/25 | Thu 28/08/25 | 0 days | Thu 28/08/25 | Thu 28/08/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.25 | Yes
5 | 1.8.2.5.5 |  |  |  |  | SIT / LDSO Pathway 3 | 100% | Fri 22/08/25 | Wed 10/09/25 | 13 days | Fri 22/08/25 | Wed 10/09/25 | 1 day | 0 days | 13 days |  |  | 6.25 | Yes
6 | 1.8.2.5.5.1 |  |  |  |  | QAD Sign Off Deadline + Test Reports | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.25 | Yes
6 | 1.8.2.5.5.2 |  |  |  |  | REC Code Manager / BSC PAB Approval of Qualification (M10-Ready) | 100% | Tue 09/09/25 | Wed 10/09/25 | 2 days | Tue 09/09/25 | Wed 10/09/25 | 0 days | 0 days | 2 days | Code Bodies |  | 6.25 | Yes
6 | 1.8.2.5.5.3 | T3 | T3-QU-0085 | QAG |  | M10-Ready SIT Participants are qualified | 100% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Wed 10/09/25 | Wed 10/09/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.24 | Yes
4 | 1.8.2.6 |  |  |  |  | MHHS Qualification - M11-Ready | 100% | Mon 07/04/25 | Wed 15/10/25 | 137 days? | Mon 07/04/25 | Wed 15/10/25 | 1 day | 0 days | 137 days? |  |  | 6.25 | Yes
5 | 1.8.2.6.1 |  |  |  |  | Final QAD Submission Window opens | 100% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 1 day | 0 days | 0 days | Participants |  | 6.25 | Yes
5 | 1.8.2.6.2 |  |  |  |  | SIT M11-ready Participants submit Final QAD (exc Test Reports) | 100% | Tue 08/04/25 | Fri 06/06/25 | 44 days | Tue 08/04/25 | Fri 06/06/25 | 0 days | 0 days | 44 days | Participants |  | 6.25 | Yes
5 | 1.8.2.6.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (M11-Ready) | 100% | Mon 09/06/25 | Fri 04/07/25 | 20 days? | Mon 09/06/25 | Fri 04/07/25 | 0 days | 0 days | 20 days? | Code Bodies |  | 6.25 | Yes
5 | 1.8.2.6.4 |  |  |  |  | SIT Pathway 4 | 100% | Thu 04/09/25 | Thu 25/09/25 | 16 days | Thu 04/09/25 | Thu 25/09/25 | 0 days | 0 days | 16 days |  |  | 6.25 | Yes
6 | 1.8.2.6.4.1 |  |  |  |  | QAD Sign Off Deadline + Test Reports | 100% | Thu 04/09/25 | Thu 04/09/25 | 0 days | Thu 04/09/25 | Thu 04/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.25 | Yes
6 | 1.8.2.6.4.2 |  |  |  |  | REC Code Manager / BSC PAB Approval of Qualification (M11-Ready) | 100% | Thu 25/09/25 | Thu 25/09/25 | 0 days | Thu 25/09/25 | Thu 25/09/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.25 | Yes
5 | 1.8.2.6.5 |  |  |  |  | SIT Pathway 5 | 100% | Wed 24/09/25 | Wed 15/10/25 | 16 days | Wed 24/09/25 | Wed 15/10/25 | 0 days | 0 days | 16 days |  |  | 6.25 | Yes
6 | 1.8.2.6.5.1 |  |  |  |  | QAD Sign Off Deadline + Test Reports | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.25 | Yes
6 | 1.8.2.6.5.2 |  |  |  |  | REC Code Manager / BSC PAB Approval of Qualification | 100% | Wed 15/10/25 | Wed 15/10/25 | 0 days | Wed 15/10/25 | Wed 15/10/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.25 | Yes
6 | 1.8.2.6.5.3 |  |  |  |  | 'M11-Ready SIT Participants are qualified' | 100% | Wed 15/10/25 | Wed 15/10/25 | 0 days | Wed 15/10/25 | Wed 15/10/25 | 1 day | 0 days | 0 days | Migration |  | 6.25 | Yes
4 | 1.8.2.7 |  |  |  |  | MHHS Qualification - Not M11-Ready | 99% | Mon 19/05/25 | Thu 30/07/26 | 313 days | Mon 19/05/25 | Wed 17/12/25 | 0 days | 160 days | 184 days | N/A |  | 6.25 | Yes
5 | 1.8.2.7.1 |  |  |  |  | Final QAD Submission Window opens | 100% | Mon 19/05/25 | Mon 19/05/25 | 0 days | Mon 19/05/25 | Mon 19/05/25 | 1 day | 0 days | 0 days | Participants |  | 6.25 | Yes
5 | 1.8.2.7.2 |  |  |  |  | SIT Not M11-Ready Participants submit Final QAD | 100% | Mon 19/05/25 | Fri 19/09/25 | 90 days | Mon 19/05/25 | Fri 19/09/25 | 0 days | 0 days | 4 days | Participants |  | 6.25 | Yes
5 | 1.8.2.7.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (Not M11-Ready) | 100% | Mon 22/09/25 | Fri 24/10/25 | 25 days | Mon 22/09/25 | Fri 24/10/25 | 0 days | 0 days | 6 days | Code Bodies |  | 6.25 | Yes
5 | 1.8.2.7.4 |  |  |  |  | SIT Pathway 6 | 100% | Thu 09/10/25 | Thu 18/12/25 | 50 days | Thu 27/11/25 | Wed 17/12/25 | -35 days | 0 days | 50 days |  |  | 6.25 | Yes
6 | 1.8.2.7.4.1 |  |  |  |  | QAD Sign Off Deadline + Test Reports | 100% | Thu 09/10/25 | Thu 09/10/25 | 0 days | Thu 09/10/25 | Thu 09/10/25 | 0 days | -1 day | 0 days | Participants |  | 6.27 | Yes
6 | 1.8.2.7.4.2 |  |  |  |  | REC Code Manager / BSC PAB Approval of Qualification (first Pathway 6 PAB) | 100% | Thu 30/10/25 | Thu 30/10/25 | 0 days | Thu 30/10/25 | Thu 30/10/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.27 | Yes
6 | 1.8.2.7.4.3 |  |  |  |  | QAD Sign Off Deadline + Test Reports | 100% | Wed 26/11/25 | Wed 26/11/25 | 0 days | Thu 27/11/25 | Thu 27/11/25 | -1 day | -2 days | 0 days | Participants |  | 6.27 | Yes
6 | 1.8.2.7.4.4 |  |  |  |  | REC Code Manager / BSC PAB Approval of Qualification (final Pathway 6 PAB) | 100% | Thu 18/12/25 | Thu 18/12/25 | 0 days | Thu 18/12/25 | Thu 18/12/25 | 0 days | -1 day | 0 days | Code Bodies |  | 6.27 | Yes
5 | 1.8.2.7.5 | T3 | T3-QU-0086 | QAG |  | SIT Participants are Qualified | 0% | Thu 30/07/26 | Thu 30/07/26 | 0 days | Thu 30/07/26 | Thu 30/07/26 | 0 days | -1 day | 0 days | Code Bodies |  | 6.4 | Yes
3 | 1.8.3 |  |  |  |  | MHHS Qualification - Non-SIT LDSO (M10-Ready) | 100% | Mon 06/01/25 | Thu 11/09/25 | 179 days | Mon 06/01/25 | Wed 10/09/25 | 0 days | 1 day | 64 days | N/A |  | 6.11 | Yes
4 | 1.8.3.1 |  |  |  |  | Initial QAD Submission window opens | 100% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Mon 06/01/25 | Mon 06/01/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.8.3.2 |  |  |  |  | Non-SIT LDSO Participants submit initial QAD | 100% | Mon 06/01/25 | Fri 14/02/25 | 30 days | Mon 06/01/25 | Fri 14/02/25 | 0 days | 0 days | 1 day | Participants |  | 6.11 | Yes
4 | 1.8.3.3 | T3 | T3-QU-0087 | QAG |  | Non-SIT LDSO QT Participants have submitted their initial QAD | 100% | Fri 14/02/25 | Fri 14/02/25 | 0 days | Fri 14/02/25 | Fri 14/02/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.8.3.4 |  |  |  |  | Code Bodies review of Non-SIT LDSO participants Initial QAD | 100% | Mon 17/02/25 | Fri 04/04/25 | 35 days | Mon 17/02/25 | Fri 04/04/25 | 0 days | 0 days | -1 day | Code Bodies |  | 6.11 | Yes
4 | 1.8.3.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 100% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.8.3.6 |  |  |  |  | Final QAD Submission window opens | 100% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.8.3.7 |  |  |  |  | Non-SIT LDSO Participants submit Final QAD | 100% | Mon 07/04/25 | Fri 23/05/25 | 35 days | Mon 21/04/25 | Fri 23/05/25 | -10 days | 0 days | 9 days | Participants |  | 6.19 | Yes
4 | 1.8.3.8 | T3 | T3-QU-0088 | QAG |  | Non-SIT LDSO QT Participants have submitted their final QAD | 100% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Fri 23/05/25 | Fri 23/05/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.8.3.9 |  |  |  |  | Completion of Code Bodies review of the Final QAD | 100% | Mon 26/05/25 | Fri 20/06/25 | 20 days | Mon 26/05/25 | Fri 20/06/25 | 0 days | 0 days | 1 day | Code Bodies |  | 6.11 | Yes
4 | 1.8.3.10 |  |  |  |  | QAD Finalisation | 100% | Mon 23/06/25 | Tue 19/08/25 | 42 days | Mon 23/06/25 | Tue 19/08/25 | 0 days | 0 days | 42 days | Participants |  | 6.25 | Yes
4 | 1.8.3.11 |  |  |  |  | QAD Sign Off Deadline (Non-SIT LDSOs) | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | -1 day | Participants |  | 6.11 | Yes
4 | 1.8.3.12 | T2 | T2-QU-0500 | QAG (Non-SIT LDSO) |  | BSC PAB & REC Manager approval of Qualification for Non-SIT LDSOs | 100% | Thu 11/09/25 | Thu 11/09/25 | 0 days | Thu 11/09/25 | Thu 11/09/25 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 6.12 | Yes
3 | 1.8.4 |  |  |  |  | MHHS Qualification - Qualification Waves | 84% | Mon 18/12/23 | Thu 28/01/27 | 814 days? | Mon 18/12/23 | Thu 28/01/27 | 0 days | 0 days | 240 days? | N/A |  | 5.24 | Yes
4 | 1.8.4.1 |  |  |  |  | Qualification Wave Prep | 99% | Mon 18/12/23 | Thu 19/02/26 | 569 days? | Mon 18/12/23 | Fri 26/12/25 | 0 days | 39 days | 145 days? | N/A |  | 5.24 | Yes
5 | 1.8.4.1.1 |  |  |  |  | Non-SIT Supplier and Agent Test Approach and Plan | 100% | Mon 18/12/23 | Thu 30/05/24 | 119 days | Mon 18/12/23 | Thu 30/05/24 | 0 days | 0 days | 1 day | N/A |  | 5.24 | Yes
6 | 1.8.4.1.1.1 |  |  |  |  | Draft Non-SIT S&A Test Approach and Plan | 100% | Mon 18/12/23 | Fri 23/02/24 | 50 days | Mon 18/12/23 | Fri 23/02/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.1.2 |  |  |  |  | Internal Review of Non-SIT S&A Test Approach and Plan (Code Bodies and MHHSP) | 100% | Mon 26/02/24 | Fri 08/03/24 | 10 days | Mon 26/02/24 | Fri 08/03/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.8.4.1.1.3 |  |  |  |  | Issue Non-SIT S&A Test Approach and Plan for Consultation | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | Mon 18/03/24 | Fri 05/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.4.1.1.4 |  |  |  |  | Update Non-SIT S&A Test Approach and Plan Post-Consultation | 100% | Mon 08/04/24 | Fri 19/04/24 | 10 days | Mon 08/04/24 | Fri 19/04/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.1.5 |  |  |  |  | QWG Endorsement of Non-SIT S&A Test Approach and Plan | 100% | Tue 14/05/24 | Tue 14/05/24 | 1 day | Tue 14/05/24 | Tue 14/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.1.6 | T3 | T3-QU-0089 | QAG |  | QAG Approval of Non-SIT S&A Test Approach and Plan | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.8.4.1.1.7 | T3 | T3-QU-0090 | QAG |  | BSC & REC PAB Approval of Non-SIT S&A Test Approach and Plan | 100% | Thu 30/05/24 | Thu 30/05/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.25 | Yes
5 | 1.8.4.1.2 |  |  |  |  | QT Test Data Approach and Plan | 100% | Fri 19/04/24 | Thu 18/07/24 | 64 days | Fri 19/04/24 | Thu 18/07/24 | 1 day | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.8.4.1.2.1 |  |  |  |  | QT Test Data Approach agreed as part of the Non-SIT Supplier and Agent Test Approach and Plan | 100% | Fri 19/04/24 | Fri 19/04/24 | 0 days | Fri 19/04/24 | Fri 19/04/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team, Participants |  | 5.24 | Yes
6 | 1.8.4.1.2.2 |  |  |  |  | Draft Test Data Approach and Plan for QT | 100% | Mon 06/05/24 | Fri 17/05/24 | 10 days | Mon 06/05/24 | Fri 17/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.2.3 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of QT Test Data Approach and Plan | 100% | Mon 20/05/24 | Fri 07/06/24 | 15 days | Mon 20/05/24 | Fri 07/06/24 | 0 days | 0 days | 5 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.8.4.1.2.4 |  |  |  |  | Issue QT Test Data Approach and Plan for Industry Consultation | 100% | Mon 10/06/24 | Fri 21/06/24 | 10 days | Mon 10/06/24 | Fri 21/06/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.4.1.2.5 |  |  |  |  | Update QT Test Approach and Plan Post Industry Consultation | 100% | Mon 24/06/24 | Fri 28/06/24 | 5 days | Mon 24/06/24 | Fri 28/06/24 | 0 days | 0 days | -5 days | Non-SIT S&A QT Team |  | 5.24 | Yes
6 | 1.8.4.1.2.6 |  |  |  |  | QWG Endorsement of Test Data Approach and Plan | 100% | Tue 09/07/24 | Tue 09/07/24 | 1 day | Tue 09/07/24 | Tue 09/07/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.2.7 | T3 | T3-QU-0091 | QAG |  | QAG Approval of QT Test Data Approach and Plan | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.29 | Yes
5 | 1.8.4.1.3 |  |  |  |  | QT Functional Test Scenarios and Test Cases | 100% | Mon 04/03/24 | Thu 23/05/24 | 59 days | Mon 04/03/24 | Thu 23/05/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.8.4.1.3.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 1 | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.3.2 |  |  |  |  | Issue Batch 1 for Consultation | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | Mon 18/03/24 | Fri 05/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.4.1.3.3 |  |  |  |  | Gap analysis against QT Requirements | 100% | Mon 18/03/24 | Wed 27/03/24 | 8 days | Mon 18/03/24 | Wed 27/03/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.3.4 |  |  |  |  | Update Test Scenarios and Test Case list - Batch 2 | 100% | Thu 28/03/24 | Thu 04/04/24 | 6 days | Thu 28/03/24 | Thu 04/04/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.3.5 |  |  |  |  | Issue Batch 2 for consultation | 100% | Fri 05/04/24 | Thu 18/04/24 | 10 days | Fri 05/04/24 | Thu 18/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.4.1.3.6 |  |  |  |  | Update Batch 2 post consultation | 100% | Fri 19/04/24 | Thu 02/05/24 | 10 days | Fri 19/04/24 | Thu 02/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.3.7 |  |  |  |  | QWG Endorsement of Batch 1 and 2 | 100% | Tue 14/05/24 | Tue 14/05/24 | 1 day | Tue 14/05/24 | Tue 14/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.8.4.1.3.8 | T3 | T3-QU-0092 | QAG |  | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 1 and 2 | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.8.4.1.4 |  |  |  |  | QT Migration Test Scenarios and Test Cases | 100% | Mon 06/05/24 | Thu 18/07/24 | 54 days | Mon 06/05/24 | Thu 18/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.25 | Yes
6 | 1.8.4.1.4.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 1 | 100% | Mon 06/05/24 | Fri 31/05/24 | 20 days | Mon 06/05/24 | Fri 31/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | Yes
6 | 1.8.4.1.4.2 |  |  |  |  | Issue Batch 1 for Consultation | 100% | Mon 03/06/24 | Fri 14/06/24 | 10 days | Mon 03/06/24 | Fri 14/06/24 | 0 days | 0 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.8.4.1.4.3 |  |  |  |  | Update Batch 1 Post Consultation | 100% | Mon 17/06/24 | Fri 28/06/24 | 10 days | Mon 17/06/24 | Fri 28/06/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.8.4.1.4.4 |  |  |  |  | QWG Endorsement of Batch 1 | 100% | Tue 09/07/24 | Tue 09/07/24 | 0 days | Tue 09/07/24 | Tue 09/07/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.8.4.1.4.5 | T3 | T3-QU-0119 | QAG |  | QAG Approval of QT Migration Test Scenarios and Test Cases Batches 1 | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.29 | Yes
5 | 1.8.4.1.5 |  |  |  |  | QT Functional (inc NF and Operational) Test Scenarios and Test Cases | 100% | Tue 05/11/24 | Thu 20/02/25 | 77 days | Mon 04/11/24 | Fri 27/12/24 | 1 day | 38 days | 77 days | Non-SIT S&A QT Test Team |  |  | Yes
6 | 1.8.4.1.5.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 3 | 100% | Tue 05/11/24 | Mon 02/12/24 | 20 days | Tue 05/11/24 | Mon 02/12/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.11 | Yes
6 | 1.8.4.1.5.2 |  |  |  |  | Issue Batch 3 for Consultation | 100% | Tue 03/12/24 | Mon 16/12/24 | 10 days | Tue 03/12/24 | Mon 16/12/24 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.11 | Yes
6 | 1.8.4.1.5.3 |  |  |  |  | Update Batch 3 Post Consultation | 100% | Tue 17/12/24 | Mon 13/01/25 | 20 days | Tue 17/12/24 | Mon 13/01/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.11 | Yes
6 | 1.8.4.1.5.4 |  |  |  |  | QWG Endorsement of Batch 3 | 100% | Tue 11/02/25 | Tue 11/02/25 | 0 days | Tue 11/02/25 | Tue 11/02/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.11 | Yes
6 | 1.8.4.1.5.5 | T3 | T3-QU-0123 | QAG |  | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 3 | 100% | Thu 20/02/25 | Thu 20/02/25 | 0 days | Thu 20/02/25 | Thu 20/02/25 | 0 days | -1 day | 0 days | Non-SIT S&A QT Test Team |  | 6.11 | Yes
5 | 1.8.4.1.6 |  |  |  |  | Qualification Testing Framework (Test Stubs and Supporting UI) | 99% | Mon 29/01/24 | Thu 19/02/26 | 539 days? | Mon 29/01/24 | Thu 08/01/26 | 0 days | 30 days | 539 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.8.4.1.6.1 |  |  |  |  | Proof of Concept for QTF Completion | 100% | Mon 29/01/24 | Fri 29/03/24 | 45 days | Mon 29/01/24 | Fri 29/03/24 | 0 days | 0 days | 45 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.8.4.1.6.2 |  |  |  |  | Discovery and Mobilisation | 100% | Mon 01/04/24 | Fri 03/05/24 | 25 days | Mon 01/04/24 | Fri 03/05/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.8.4.1.6.3 |  |  |  |  | Agile DBT of Qualification Testing Framework | 100% | Wed 24/04/24 | Fri 16/08/24 | 83 days | Wed 24/04/24 | Fri 16/08/24 | 0 days | 0 days | 83 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.3.1 |  |  |  |  | User Interface (UI) | 100% | Wed 24/04/24 | Fri 28/06/24 | 48 days | Wed 24/04/24 | Fri 28/06/24 | 0 days | 0 days | 48 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.1.1 |  |  |  |  | UI Wireframe | 100% | Wed 24/04/24 | Fri 28/06/24 | 48 days | Wed 24/04/24 | Fri 28/06/24 | 0 days | 0 days | 48 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.1.2 |  |  |  |  | UI Standards | 100% | Mon 13/05/24 | Fri 28/06/24 | 35 days | Mon 13/05/24 | Fri 28/06/24 | 0 days | 0 days | 35 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.1.3 |  |  |  |  | Elexon Branding Sylesheet | 100% | Fri 17/05/24 | Mon 20/05/24 | 2 days | Fri 17/05/24 | Mon 20/05/24 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.1.4 |  |  |  |  | Elexon Branding QTF Logo | 100% | Fri 31/05/24 | Mon 03/06/24 | 2 days | Fri 31/05/24 | Mon 03/06/24 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.3.2 |  |  |  |  | Design, Build, Test | 100% | Mon 13/05/24 | Fri 16/08/24 | 70 days | Mon 13/05/24 | Fri 16/08/24 | 0 days | 0 days | 70 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.2.1 |  |  |  |  | Core UI Screens | 100% | Mon 13/05/24 | Fri 02/08/24 | 60 days | Mon 13/05/24 | Fri 02/08/24 | 0 days | 0 days | 60 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.2.2 |  |  |  |  | Tooling (Trigger Files / Template Generators) | 100% | Mon 13/05/24 | Fri 16/08/24 | 70 days | Mon 13/05/24 | Fri 16/08/24 | 0 days | 0 days | 70 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.2.3 |  |  |  |  | Database Schema | 100% | Mon 13/05/24 | Fri 19/07/24 | 50 days | Mon 13/05/24 | Fri 19/07/24 | 0 days | 0 days | 50 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.3.2.4 |  |  |  |  | Core API's | 100% | Mon 13/05/24 | Fri 02/08/24 | 60 days | Mon 13/05/24 | Fri 02/08/24 | 0 days | 0 days | 60 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.8.4.1.6.4 |  |  |  |  | QTF Test Cases DBT Refinement, Execution and Results Validation, Defect Management, Error Handling | 100% | Tue 05/11/24 | Thu 20/02/25 | 77 days | Tue 05/11/24 | Thu 20/02/25 | 0 days | -1 day | 77 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.8.4.1.6.5 |  |  |  |  | Environments | 100% | Mon 15/04/24 | Thu 31/07/25 | 339 days | Mon 15/04/24 | Thu 31/07/25 | 0 days | 0 days | 339 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.5.1 |  |  |  |  | Azure Devops | 100% | Mon 15/04/24 | Wed 11/12/24 | 173 days | Mon 15/04/24 | Wed 11/12/24 | 0 days | 0 days | 173 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.1.1 |  |  |  |  | QFT ADO Development Instance | 100% | Mon 15/04/24 | Fri 03/05/24 | 15 days | Mon 15/04/24 | Fri 03/05/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.8.4.1.6.5.1.1.1 |  |  |  |  | Elexon Instance Setup for QTF Build | 100% | Mon 15/04/24 | Fri 19/04/24 | 5 days | Mon 15/04/24 | Fri 19/04/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.8.4.1.6.5.1.1.2 |  |  |  |  | Configuration and User Access | 100% | Mon 22/04/24 | Fri 03/05/24 | 10 days | Mon 22/04/24 | Fri 03/05/24 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.1.2 |  |  |  |  | MHHSP ADO Instance | 100% | Tue 23/07/24 | Wed 11/12/24 | 102 days | Tue 23/07/24 | Wed 11/12/24 | 0 days | 0 days | 102 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.8.4.1.6.5.1.2.1 |  |  |  |  | MHHSP Instance Setup for QTF Production | 100% | Tue 23/07/24 | Fri 30/08/24 | 29 days | Tue 23/07/24 | Fri 30/08/24 | 0 days | 0 days | 29 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.8.4.1.6.5.1.2.2 |  |  |  |  | Configuration and User Access | 100% | Mon 02/09/24 | Wed 11/12/24 | 73 days | Mon 02/09/24 | Wed 11/12/24 | 0 days | 0 days | 73 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.5.2 |  |  |  |  | Temporary Development Environment | 100% | Mon 15/04/24 | Fri 31/05/24 | 35 days | Mon 15/04/24 | Fri 31/05/24 | 0 days | 0 days | 35 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.2.1 |  |  |  |  | Design | 100% | Mon 15/04/24 | Fri 03/05/24 | 15 days | Mon 15/04/24 | Fri 03/05/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.2.2 |  |  |  |  | Build and Deployment | 100% | Mon 06/05/24 | Fri 31/05/24 | 20 days | Mon 06/05/24 | Fri 31/05/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.5.3 |  |  |  |  | Dev, Test & Prod Environment Requirements + Design | 100% | Mon 27/05/24 | Fri 29/11/24 | 135 days | Mon 27/05/24 | Fri 29/11/24 | 0 days | 0 days | 135 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.3.1 |  |  |  |  | Design (including Security Review) | 100% | Mon 27/05/24 | Fri 29/11/24 | 135 days | Mon 27/05/24 | Fri 29/11/24 | 0 days | 0 days | 135 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.3.2 |  |  |  |  | Hub Development Dev/Test | 100% | Mon 10/06/24 | Fri 05/07/24 | 20 days | Mon 10/06/24 | Fri 05/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.3.3 |  |  |  |  | Hub Deployment | 100% | Mon 10/06/24 | Fri 05/07/24 | 20 days | Mon 10/06/24 | Fri 05/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.3.4 |  |  |  |  | Development Envn. Deployment | 100% | Mon 08/07/24 | Thu 19/09/24 | 53.8 days | Mon 08/07/24 | Thu 19/09/24 | 0 days | -0.2 days | 53.8 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.3.5 |  |  |  |  | Test Envn. Deployment | 100% | Thu 19/09/24 | Thu 03/10/24 | 10 days | Thu 19/09/24 | Thu 03/10/24 | 0.8 days | -0.2 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.3.6 |  |  |  |  | Production Envn. Deployment | 100% | Thu 03/10/24 | Thu 07/11/24 | 25 days | Thu 03/10/24 | Thu 07/11/24 | 0.8 days | -0.2 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.5.4 |  |  |  |  | QTF Deployment into Production | 100% | Thu 20/02/25 | Tue 18/03/25 | 19 days | Mon 03/02/25 | Fri 25/04/25 | 13 days | -28 days | 19 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.4.1 |  |  |  |  | App Deployment | 100% | Thu 20/02/25 | Wed 26/02/25 | 5 days | Thu 20/02/25 | Wed 26/02/25 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.4.2 |  |  |  |  | Smoke Test | 100% | Thu 27/02/25 | Fri 28/02/25 | 2 days | Thu 27/02/25 | Fri 28/02/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.4.3 |  |  |  |  | PEN Test | 100% | Mon 03/03/25 | Tue 04/03/25 | 2 days | Mon 03/03/25 | Tue 04/03/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.4.4 |  |  |  |  | Regression Test | 100% | Wed 05/03/25 | Tue 18/03/25 | 10 days | Wed 05/03/25 | Tue 18/03/25 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.8.4.1.6.5.5 |  |  |  |  | DIP Onboarding (UIT) | 100% | Fri 26/07/24 | Fri 13/12/24 | 101 days | Fri 26/07/24 | Fri 29/11/24 | 0 days | 10 days | 101 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.1 |  |  |  |  | DIP Simulator | 100% | Fri 26/07/24 | Thu 15/08/24 | 15 days | Fri 26/07/24 | Thu 15/08/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.2 |  |  |  |  | DIP (UIT) Instance available for Onboarding | 100% | Mon 05/08/24 | Mon 05/08/24 | 1 day | Mon 05/08/24 | Mon 05/08/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.3 |  |  |  |  | DIP (UIT) Portal | 100% | Tue 03/09/24 | Tue 03/09/24 | 1 day | Tue 03/09/24 | Tue 03/09/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.4 |  |  |  |  | DIP (UIT) Onboarding for Development (incl. certificates and security compliance) | 100% | Tue 06/08/24 | Fri 27/09/24 | 39 days | Tue 06/08/24 | Fri 27/09/24 | 0 days | 0 days | 39 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.5 |  |  |  |  | DIP (UIT) Onboarding for Development Connection Confirmed | 100% | Mon 30/09/24 | Mon 30/09/24 | 1 day | Mon 30/09/24 | Mon 30/09/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.6 |  |  |  |  | DIP (UIT) Onboarding for Test (incl. certificates and security compliance) | 100% | Tue 01/10/24 | Mon 07/10/24 | 5 days | Tue 01/10/24 | Mon 07/10/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.7 |  |  |  |  | DIP (UIT) Onboarding for Test Connection Confirmed | 100% | Tue 08/10/24 | Tue 08/10/24 | 1 day | Tue 08/10/24 | Tue 08/10/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.8 |  |  |  |  | DIP (UIT) Onboarding for Prod (incl. certificates and security compliance) | 100% | Wed 09/10/24 | Tue 15/10/24 | 5 days | Wed 09/10/24 | Tue 15/10/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.9 |  |  |  |  | DIP (UIT) Onboarding for Prod Connection Confirmed | 100% | Wed 16/10/24 | Wed 16/10/24 | 1 day | Wed 16/10/24 | Wed 16/10/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.5.10 |  |  |  |  | DIP UIT Test Stubs | 100% | Thu 31/10/24 | Fri 13/12/24 | 32 days | Thu 17/10/24 | Fri 29/11/24 | 10 days | 10 days | 32 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.8.4.1.6.5.6 |  |  |  |  | DTN Onboarding | 100% | Mon 20/05/24 | Fri 25/10/24 | 115 days | Mon 20/05/24 | Fri 25/10/24 | 0 days | 0 days | 115 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.6.1 |  |  |  |  | DTN Request Raised for Onboarding | 100% | Mon 20/05/24 | Fri 21/06/24 | 25 days | Mon 20/05/24 | Fri 21/06/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.6.2 |  |  |  |  | Setup, configuration of New Host and Test Flags | 100% | Mon 24/06/24 | Fri 28/06/24 | 5 days | Mon 24/06/24 | Fri 28/06/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.6.3 |  |  |  |  | New VPN Connection (Test) | 100% | Mon 05/08/24 | Fri 13/09/24 | 30 days | Mon 05/08/24 | Fri 13/09/24 | 0 days | 0 days | 30 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.6.4 |  |  |  |  | New VPN Connection (Prod) | 100% | Mon 16/09/24 | Fri 25/10/24 | 30 days | Mon 16/09/24 | Fri 25/10/24 | 0 days | 0 days | 30 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.6.5 |  |  |  |  | DTN Test Stubs | 100% | Mon 16/09/24 | Fri 27/09/24 | 10 days | Mon 16/09/24 | Fri 27/09/24 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.8.4.1.6.5.7 |  |  |  |  | Generate Tooling | 100% | Mon 22/04/24 | Thu 31/07/25 | 334 days | Mon 22/04/24 | Thu 31/07/25 | 0 days | 0 days | 334 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.1 |  |  |  |  | MPAN Core Generator | 100% | Mon 22/04/24 | Fri 24/05/24 | 25 days | Mon 22/04/24 | Fri 24/05/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.2 |  |  |  |  | MPAN File Generator | 100% | Mon 27/05/24 | Fri 09/08/24 | 55 days | Mon 27/05/24 | Fri 09/08/24 | 0 days | 0 days | 55 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.3 |  |  |  |  | MPAN Template Loader | 100% | Mon 12/08/24 | Tue 24/09/24 | 32 days | Mon 12/08/24 | Tue 24/09/24 | 0 days | 0 days | 32 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.4 |  |  |  |  | ADO Extract (QTC) From SIT | 100% | Mon 06/05/24 | Fri 14/06/24 | 30 days | Mon 06/05/24 | Fri 14/06/24 | 0 days | 0 days | 30 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.5 |  |  |  |  | Populate QT ADO | 100% | Mon 17/06/24 | Fri 09/08/24 | 40 days | Mon 17/06/24 | Fri 09/08/24 | 0 days | 0 days | 40 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.6 |  |  |  |  | Create QTC Spreadsheets | 100% | Mon 03/06/24 | Fri 28/06/24 | 20 days | Mon 03/06/24 | Fri 28/06/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.7 |  |  |  |  | Upload QTC Spreadsheets to QTF | 100% | Mon 01/07/24 | Fri 26/07/24 | 20 days | Mon 01/07/24 | Fri 26/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.8.4.1.6.5.7.8 |  |  |  |  | Create QTC Set / Master QTC Loader | 100% | Mon 22/07/24 | Fri 13/09/24 | 40 days | Mon 22/07/24 | Fri 13/09/24 | 0 days | 0 days | 40 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.8.4.1.6.5.8 |  |  |  |  | Test Data | 100% | Mon 10/06/24 | Fri 28/06/24 | 15 days | Mon 10/06/24 | Fri 28/06/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.5.8.1 |  |  |  |  | Sample MPAN Data + Attributes from Suppliers | 100% | Mon 10/06/24 | Fri 28/06/24 | 15 days | Mon 10/06/24 | Fri 28/06/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.8.4.1.6.6 |  |  |  |  | MPANs, DIP Messages, Settlement, Consumption, Reference | 97% | Mon 27/05/24 | Wed 07/01/26 | 423 days? | Mon 27/05/24 | Wed 07/01/26 | 0 days | 0 days | 423 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.1 |  |  |  |  | Create MPAN Data | 100% | Mon 27/05/24 | Fri 09/08/24 | 55 days | Mon 27/05/24 | Fri 09/08/24 | 0 days | 0 days | 55 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.2 |  |  |  |  | Create message templates (DIP, CSS, DTN) | 100% | Mon 03/06/24 | Fri 26/07/24 | 40 days | Mon 03/06/24 | Fri 26/07/24 | 0 days | 0 days | 40 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.3 |  |  |  |  | Create Consumption Data Templates | 100% | Mon 16/09/24 | Fri 11/10/24 | 20 days | Mon 16/09/24 | Fri 11/10/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.4 |  |  |  |  | Load Consumption Data | 100% | Mon 11/11/24 | Fri 13/12/24 | 25 days | Mon 11/11/24 | Fri 06/12/24 | 0 days | 5 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.5 |  |  |  |  | Create Load Shape and Load Shape Total Templates | 100% | Mon 16/09/24 | Fri 11/10/24 | 20 days | Mon 16/09/24 | Fri 11/10/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.6 |  |  |  |  | Load Shape and Load Shape Total Data | 100% | Mon 11/11/24 | Fri 13/12/24 | 25 days | Mon 11/11/24 | Fri 06/12/24 | 0 days | 5 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.7 |  |  |  |  | Create Settlement Report Templates | 100% | Mon 16/09/24 | Fri 11/10/24 | 20 days | Mon 16/09/24 | Fri 11/10/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.8 |  |  |  |  | Load Settlement Report Data | 100% | Mon 11/11/24 | Fri 13/12/24 | 25 days | Mon 11/11/24 | Fri 06/12/24 | 0 days | 5 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.9 |  |  |  |  | Market Domain Data (MDD) For Legacy Systems | 100% | Mon 29/07/24 | Fri 30/08/24 | 25 days | Mon 29/07/24 | Fri 30/08/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.10 |  |  |  |  | Industry Standing Data (ISD) | 100% | Fri 26/07/24 | Fri 01/11/24 | 71 days? | Fri 26/07/24 | Fri 01/11/24 | 0 days | 0 days | 71 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.1 |  |  |  |  | Dependant on Receiving ISD Agreed Source Data from Helix | 100% | Fri 26/07/24 | Fri 26/07/24 | 1 day | Fri 26/07/24 | Fri 26/07/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.2 |  |  |  |  | Helix Dev Environment migration | 100% | Mon 29/07/24 | Mon 05/08/24 | 6 days | Mon 29/07/24 | Mon 05/08/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.3 |  |  |  |  | STGi (UK) migration | 100% | Mon 09/09/24 | Fri 13/09/24 | 5 days | Mon 09/09/24 | Fri 13/09/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.4 |  |  |  |  | Maintenance window between cycle 2 and 3 | 100% | Fri 20/09/24 | Fri 20/09/24 | 1 day | Fri 20/09/24 | Fri 20/09/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.5 |  |  |  |  | First View of Migrated ISD Data | 100% | Mon 23/09/24 | Fri 27/09/24 | 5 days | Mon 23/09/24 | Fri 27/09/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.6 |  |  |  |  | Second View of Migrated ISD Data (HXT1 (SIT B) migration) | 100% | Mon 23/09/24 | Fri 27/09/24 | 5 days | Mon 23/09/24 | Fri 27/09/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.7 |  |  |  |  | Final Cycle 3 Migrated ISD Data | 100% | Mon 07/10/24 | Fri 11/10/24 | 5 days | Mon 07/10/24 | Fri 11/10/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.8 |  |  |  |  | Create ISD Template inc. DIP ID | 100% | Mon 16/09/24 | Fri 01/11/24 | 35 days? | Mon 16/09/24 | Fri 01/11/24 | 0 days | 0 days | 35 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.10.9 |  |  |  |  | Publish Qualification ISD | 100% | Mon 14/10/24 | Fri 25/10/24 | 10 days? | Mon 14/10/24 | Fri 25/10/24 | 0 days | 0 days | 10 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.11 |  |  |  |  | BETA Testing 1 - Test Data | 100% | Fri 01/11/24 | Mon 09/12/24 | 27 days | Fri 01/11/24 | Fri 15/11/24 | 0 days | 16 days | 27 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.1 |  |  |  |  | Provide Example MPAN File | 100% | Fri 01/11/24 | Tue 05/11/24 | 3 days | Fri 01/11/24 | Tue 05/11/24 | 0 days | 0 days | 3 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.2 |  |  |  |  | Load Example MPAN File | 100% | Wed 06/11/24 | Wed 13/11/24 | 6 days | Wed 06/11/24 | Wed 13/11/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.3 |  |  |  |  | Industry Standing Data (ISD) | 100% | Wed 06/11/24 | Wed 13/11/24 | 6 days | Wed 06/11/24 | Wed 13/11/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.4 |  |  |  |  | Market Domain Data (MDD) | 100% | Wed 06/11/24 | Wed 13/11/24 | 6 days | Wed 06/11/24 | Wed 13/11/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.5 |  |  |  |  | Load ISD / MDD Data | 100% | Fri 06/12/24 | Fri 06/12/24 | 1 day | Thu 14/11/24 | Thu 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.6 |  |  |  |  | Create QTC sets and Test MPANs via QTF | 100% | Fri 06/12/24 | Fri 06/12/24 | 1 day | Thu 14/11/24 | Thu 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.7 |  |  |  |  | Create QTC sets in ADO via QTF | 100% | Fri 06/12/24 | Fri 06/12/24 | 1 day | Thu 14/11/24 | Thu 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.8 |  |  |  |  | Provide Test MPANs (Suppliers only) allocated to specfic QTC's | 100% | Fri 06/12/24 | Fri 06/12/24 | 1 day | Thu 14/11/24 | Thu 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.9 |  |  |  |  | Load Test MPANs | 100% | Mon 09/12/24 | Mon 09/12/24 | 1 day | Fri 15/11/24 | Fri 15/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.11.10 |  |  |  |  | BETA Testing 2 - Test Data | 100% | Wed 08/01/25 | Wed 22/01/25 | 11 days | Wed 08/01/25 | Wed 22/01/25 | 0 days | 0 days | 11 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.1 |  |  |  |  | Provide Example MPAN File | 100% | Wed 08/01/25 | Fri 10/01/25 | 3 days | Wed 08/01/25 | Fri 10/01/25 | 0 days | 0 days | 3 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.2 |  |  |  |  | Load Example MPAN File | 100% | Mon 13/01/25 | Mon 20/01/25 | 6 days | Mon 13/01/25 | Mon 20/01/25 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.3 |  |  |  |  | Industry Standing Data (ISD) | 100% | Wed 08/01/25 | Wed 15/01/25 | 6 days | Wed 08/01/25 | Wed 15/01/25 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.4 |  |  |  |  | Market Domain Data (MDD) | 100% | Wed 08/01/25 | Wed 15/01/25 | 6 days | Wed 08/01/25 | Wed 15/01/25 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.5 |  |  |  |  | Load ISD / MDD Data | 100% | Thu 16/01/25 | Thu 16/01/25 | 1 day | Thu 16/01/25 | Thu 16/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.6 |  |  |  |  | Create QTC sets and Test MPANs via QTF | 100% | Tue 21/01/25 | Tue 21/01/25 | 1 day | Tue 21/01/25 | Tue 21/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.7 |  |  |  |  | Create QTC sets in ADO via QTF | 100% | Tue 21/01/25 | Tue 21/01/25 | 1 day | Tue 21/01/25 | Tue 21/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.8 |  |  |  |  | Provide Test MPANs (Suppliers only) allocated to specfic QTC's | 100% | Tue 21/01/25 | Tue 21/01/25 | 1 day | Tue 21/01/25 | Tue 21/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
9 | 1.8.4.1.6.6.11.10.9 |  |  |  |  | Load Test MPANs | 100% | Wed 22/01/25 | Wed 22/01/25 | 1 day | Wed 22/01/25 | Wed 22/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.8.4.1.6.6.12 |  |  |  |  | Wave 1 Test Data | 100% | Mon 12/05/25 | Tue 15/07/25 | 46 days | Mon 12/05/25 | Tue 15/07/25 | 1 day | 0 days | 46 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.12.1 |  |  |  |  | Test Data Request + Templates Completed | 100% | Mon 14/07/25 | Tue 15/07/25 | 2 days | Mon 14/07/25 | Tue 15/07/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.25 | Yes
8 | 1.8.4.1.6.6.12.2 |  |  |  |  | Test Data Generated | 100% | Wed 16/07/25 | Thu 17/07/25 | 2 days | Wed 16/07/25 | Thu 17/07/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.25 | Yes
8 | 1.8.4.1.6.6.12.3 |  |  |  |  | Test Data Loaded into QP Systems | 100% | Fri 18/07/25 | Thu 07/08/25 | 15 days | Fri 18/07/25 | Thu 07/08/25 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.25 | Yes
8 | 1.8.4.1.6.6.12.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 100% | Mon 11/08/25 | Fri 15/08/25 | 5 days | Mon 11/08/25 | Fri 15/08/25 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.25 | Yes
7 | 1.8.4.1.6.6.13 |  |  |  |  | Wave 2 Test Data | 100% | Mon 07/07/25 | Wed 03/09/25 | 42 days | Mon 07/07/25 | Wed 03/09/25 | 1 day | 0 days | 42 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.13.1 |  |  |  |  | Test Data Request + Templates Completed | 100% | Wed 17/09/25 | Thu 18/09/25 | 2 days | Wed 17/09/25 | Thu 18/09/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.13.2 |  |  |  |  | Test Data Generated | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.13.3 |  |  |  |  | Test Data Loaded into QP Systems | 100% | Tue 23/09/25 | Mon 13/10/25 | 15 days | Tue 23/09/25 | Mon 13/10/25 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.13.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 100% | Tue 14/10/25 | Fri 17/10/25 | 4 days | Tue 14/10/25 | Fri 17/10/25 | 0 days | 0 days | 4 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
7 | 1.8.4.1.6.6.14 |  |  |  |  | Wave 3 Test Data | 100% | Mon 08/09/25 | Mon 10/11/25 | 45 days | Mon 08/09/25 | Mon 10/11/25 | 1 day | 0 days | 45 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.14.1 |  |  |  |  | Test Data Request + Templates Completed | 100% | Mon 10/11/25 | Tue 11/11/25 | 2 days | Mon 10/11/25 | Tue 11/11/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.14.2 |  |  |  |  | Test Data Generated | 100% | Wed 12/11/25 | Thu 13/11/25 | 2 days | Wed 12/11/25 | Thu 13/11/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.14.3 |  |  |  |  | Test Data Loaded into QP Systems | 100% | Fri 14/11/25 | Thu 04/12/25 | 15 days | Fri 14/11/25 | Thu 04/12/25 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.14.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 100% | Fri 05/12/25 | Thu 11/12/25 | 5 days | Fri 05/12/25 | Thu 11/12/25 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
7 | 1.8.4.1.6.6.15 |  |  |  |  | Wave 4 Test Data | 0% | Thu 06/11/25 | Thu 08/01/26 | 45 days | Thu 06/11/25 | Thu 08/01/26 | 1 day | 0 days | 45 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.15.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | Mon 19/01/26 | Tue 20/01/26 | 2 days | Mon 19/01/26 | Tue 20/01/26 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.15.2 |  |  |  |  | Test Data Generated | 0% | Wed 21/01/26 | Thu 22/01/26 | 2 days | Wed 21/01/26 | Thu 22/01/26 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.15.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | Fri 23/01/26 | Thu 12/02/26 | 15 days | Fri 23/01/26 | Thu 12/02/26 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
8 | 1.8.4.1.6.6.15.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | Fri 13/02/26 | Thu 19/02/26 | 5 days | Fri 13/02/26 | Thu 19/02/26 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.18 | Yes
7 | 1.8.4.1.6.6.16 |  |  |  |  | Governance | 100% | Mon 01/07/24 | Fri 28/03/25 | 195 days | Mon 01/07/24 | Fri 20/12/24 | 0 days | 70 days | 195 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.16.1 |  |  |  |  | Onboarding Strategy and Develop Training Requirements & Materials Inc. Day in the Life | 100% | Mon 01/07/24 | Fri 13/12/24 | 120 days | Mon 01/07/24 | Fri 29/11/24 | 0 days | 10 days | 120 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.16.2 |  |  |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 100% | Mon 01/07/24 | Fri 26/07/24 | 20 days | Mon 01/07/24 | Fri 26/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.16.3 |  |  |  |  | Knowledge Transfer, Training, Demonstrations, Documentation, Governance | 100% | Fri 30/08/24 | Tue 17/12/24 | 78 days | Fri 30/08/24 | Tue 17/12/24 | 0 days | 0 days | 78 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.16.4 |  |  |  |  | BETA Testing | 100% | Fri 01/11/24 | Tue 17/12/24 | 33 days | Fri 01/11/24 | Fri 20/12/24 | 0 days | -3 days | 33 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.8.4.1.6.6.16.5 |  |  |  |  | BETA Testing 2 | 100% | Wed 08/01/25 | Fri 28/03/25 | 58 days | Wed 08/01/25 | Fri 28/03/25 | 0 days | 0 days | 58 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
7 | 1.8.4.1.6.6.17 |  |  |  |  | Qualification Testing Framework Readiness Confirmed | 100% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.8.4.1.6.6.18 | T2 | T2-QU-1100 | QAG |  | Qualification Testing Wave Readiness Confirmed | 100% | Thu 21/08/25 | Thu 21/08/25 | 0 days | Thu 21/08/25 | Thu 21/08/25 | 0 days | -1 day | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.8.4.1.7 |  |  |  |  | Wave Allocation | 100% | Tue 02/01/24 | Fri 28/06/24 | 129 days | Tue 02/01/24 | Fri 28/06/24 | 0 days | 0 days | 1 day | N/A |  | 5.24 | Yes
6 | 1.8.4.1.7.1 |  |  |  |  | Draft Pre-Qualification Submission (PQS) document | 100% | Tue 02/01/24 | Mon 29/01/24 | 20 days | Tue 02/01/24 | Mon 29/01/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.7.2 |  |  |  |  | Publish PQS document | 100% | Wed 31/01/24 | Wed 31/01/24 | 1 day | Wed 31/01/24 | Wed 31/01/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.7.3 |  |  |  |  | PQS Submission window | 100% | Mon 05/02/24 | Fri 26/04/24 | 60 days | Mon 05/02/24 | Fri 26/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.8.4.1.7.4 | T3 | T3-QU-0118 | QAG |  | Pre-Qualification Submission and PIT Test Plan Deadline for Submission​ | 100% | Fri 26/04/24 | Fri 26/04/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 | 1 day | 0 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.8.4.1.7.5 |  |  |  |  | PQS Review by Code Bodies | 100% | Mon 29/04/24 | Fri 31/05/24 | 25 days | Mon 29/04/24 | Fri 31/05/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.7.6 |  |  |  |  | Draft Wave Allocations | 100% | Mon 03/06/24 | Fri 21/06/24 | 15 days | Mon 03/06/24 | Fri 21/06/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.8.4.1.7.7 | T3 | T3-QU-0012 | QAG |  | Confirmation of participant Qualification Wave allocation | 100% | Fri 28/06/24 | Fri 28/06/24 | 0 days | Fri 28/06/24 | Fri 28/06/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.28 | Yes
4 | 1.8.4.2 |  |  |  |  | Qualification Wave 1 | 95% | Mon 05/05/25 | Wed 15/04/26 | 248 days | Mon 24/03/25 | Fri 10/04/26 | 30 days | 3 days | 19 days | N/A |  | 6.13 | Yes
5 | 1.8.4.2.1 |  |  |  |  | Qualification Wave 1 QAD Prep | 100% | Mon 05/05/25 | Fri 22/08/25 | 80 days | Mon 24/03/25 | Fri 11/07/25 | 30 days | 30 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.8.4.2.1.1 |  |  |  |  | Initial QAD Submission window opens | 100% | Mon 05/05/25 | Mon 05/05/25 | 0 days | Mon 05/05/25 | Mon 05/05/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.1.2 |  |  |  |  | Qualification Wave 1 Participants Submit Initial QAD | 100% | Mon 05/05/25 | Fri 11/07/25 | 50 days | Mon 05/05/25 | Fri 11/07/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.1.3 | T3 | T3-QU-0094 | QAG |  | Minimum threshold of Qualification Wave 1 Participants required for QT start have submitted their initial QAD | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.1.4 |  |  |  |  | All Qualification Wave 1 Participants have submitted their initial QAD | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.1.5 |  |  |  |  | Code Bodies review of Wave 1 Participants Initial QAD | 100% | Mon 14/07/25 | Fri 22/08/25 | 30 days | Mon 14/07/25 | Fri 22/08/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
6 | 1.8.4.2.1.6 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.8.4.2.2 |  |  |  |  | Qualification Wave 1 Test Prep | 100% | Mon 26/05/25 | Fri 15/08/25 | 60 days | Mon 14/04/25 | Fri 04/07/25 | 30 days | 30 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.8.4.2.2.1 | T3 | T3-QU-0017 | QAG |  | Confirmation from Qualification Wave 1 Participants that DIP onboarding has commenced | 100% | Mon 26/05/25 | Mon 26/05/25 | 0 days | Mon 26/05/25 | Mon 26/05/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.2.2 |  |  |  |  | Qualification Wave 1 Participants DIP Onboarding Window | 100% | Mon 26/05/25 | Fri 11/07/25 | 35 days | Mon 26/05/25 | Fri 11/07/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.2.3 | T3 | T3-QU-0133 | QAG |  | Confirmation from Qualification Wave 1 Participants that DIP onboarding has completed | 100% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 11/07/25 | Fri 11/07/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.2.4 | T3 | T3-QU-0095 | QAG |  | Minimum threshold of Qualification Wave 1 Participants' required for QT start to provide status of PIT completion and submit QT Test Plan | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.2.5 |  |  |  |  | All Qualification Wave 1 Participants' to provide status of PIT completion and submit QT Test Plan | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.2.6 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 100% | Mon 16/06/25 | Fri 15/08/25 | 45 days | Mon 16/06/25 | Fri 15/08/25 | 0 days | 0 days | 30 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.27 | Yes
6 | 1.8.4.2.2.7 | T3 | T3-QU-0016 | QAG |  | Minimum threshold of Qualification Test Plans for Wave 1 Participants required for QT start approved | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Fri 15/08/25 | Fri 15/08/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.2.2.8 |  |  |  |  | All Qualification Test Plans for Wave 1 Participants approved | 100% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Fri 15/08/25 | Fri 15/08/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.2.2.9 | T3 | T3-QU-0096 | QAG |  | Minimum threshold of Qualification Wave 1 Participants required for QT start have submitted PIT Test Completion Report and evidence for QT Entry | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.2.10 |  |  |  |  | Qualification Wave 1 Participants have submitted PIT Test Completion Report and evidence for QT Entry | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.2.11 |  |  |  |  | Review of Participants PIT Test Completion Report | 100% | Mon 14/07/25 | Fri 15/08/25 | 25 days | Mon 14/07/25 | Fri 15/08/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.2.2.12 |  |  |  |  | Onboarding to QTF & ADO | 100% | Mon 14/07/25 | Fri 15/08/25 | 25 days | Mon 14/07/25 | Fri 15/08/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.8.4.2.3 |  |  |  |  | Qualification Wave 1 QT Execution | 100% | Mon 18/08/25 | Fri 09/01/26 | 105 days | Mon 18/08/25 | Fri 09/01/26 | 0 days | 0 days | 5 days | N/A |  | 6.13 | Yes
6 | 1.8.4.2.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 1 Participant | 100% | Mon 18/08/25 | Fri 22/08/25 | 5 days | Mon 18/08/25 | Fri 22/08/25 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.2.3.2 | T3 | T3-QU-0027 | QAG |  | Minimum threshold of Qualification Wave 1 Participant Test required for QT start Readiness Confirmed | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.2.3.3 |  |  |  |  | All Qualification Wave 1 Participant Test Readiness Confirmed | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.2.3.4 | T3 | T3-QU-0028 | QAG |  | Qualification Wave 1 QT Execution Start | 100% | Mon 25/08/25 | Mon 25/08/25 | 0 days | Mon 25/08/25 | Mon 25/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.3.5 |  |  |  |  | Qualification Wave 1 QT Execution Window | 100% | Mon 25/08/25 | Fri 09/01/26 | 100 days | Mon 25/08/25 | Fri 09/01/26 | 0 days | 0 days | 5 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.3.6 | T3 | T3-QU-0054 | QAG |  | Qualification Wave 1 QT Projected Execution End | 100% | Fri 09/01/26 | Fri 09/01/26 | 0 days | Fri 09/01/26 | Fri 09/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.8.4.2.4 |  |  |  |  | Qualification Wave 1 Exit | 84% | Mon 25/08/25 | Wed 15/04/26 | 168 days | Mon 25/08/25 | Wed 15/04/26 | 0 days | 0 days | 19 days | N/A |  | 6.13 | Yes
6 | 1.8.4.2.4.1 |  |  |  |  | Final QAD Submission window opens | 100% | Mon 25/08/25 | Mon 25/08/25 | 0 days | Mon 25/08/25 | Mon 25/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.4.2 |  |  |  |  | Qualification Wave 1 Participants submit their Final QAD | 100% | Mon 25/08/25 | Fri 16/01/26 | 105 days | Mon 25/08/25 | Fri 16/01/26 | 0 days | 0 days | 5 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.4.3 | T3 | T3-QU-0097 | QAG |  | 80% of M14 Critical Qualification Wave 1 Participants have submitted their final QAD | 100% | Fri 16/01/26 | Fri 16/01/26 | 0 days | Fri 16/01/26 | Fri 16/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.4.4 |  |  |  |  | All Qualification Wave 1 Participants have submitted their final QAD | 100% | Fri 16/01/26 | Fri 16/01/26 | 0 days | Fri 16/01/26 | Fri 16/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.2.4.5 |  |  |  |  | Completion of Code Bodies review of Final QAD | 40% | Mon 19/01/26 | Fri 06/03/26 | 35 days | Mon 19/01/26 | Fri 06/03/26 | 0 days | 0 days | 15 days | Code Bodies |  | 6.13 | Yes
6 | 1.8.4.2.4.6 |  |  |  |  | QAD Sign Off deadline | 0% | Fri 20/03/26 | Fri 20/03/26 | 1 day | Fri 20/03/26 | Fri 20/03/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.2.4.7 | T3 | T3-QU-0134 | QAG |  | 80% of M14 Critical Wave 1 Participants Qualification approved by BSC PAB and REC Manager | 0% | Wed 15/04/26 | Wed 15/04/26 | 0 days | Wed 15/04/26 | Wed 15/04/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.38 | Yes
6 | 1.8.4.2.4.8 | T2 | T2-QU-0150 | QAG |  | All M14 Critical Wave 1 Participants Qualification approved by BSC PAB and REC Manager | 0% | Wed 15/04/26 | Wed 15/04/26 | 0 days | Wed 15/04/26 | Wed 15/04/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.38 | Yes
4 | 1.8.4.3 |  |  |  |  | Qualification Wave 2 | 75% | Mon 09/06/25 | Thu 28/05/26 | 254 days | Mon 09/06/25 | Thu 28/05/26 | 0 days | 0 days | 5 days | N/A |  | 6.13 | Yes
5 | 1.8.4.3.1 |  |  |  |  | Qualification Wave 2 QAD Prep | 92% | Mon 09/06/25 | Fri 17/10/25 | 95 days | Mon 09/06/25 | Fri 17/10/25 | 0 days | 0 days | -1 day | N/A |  | 6.13 | Yes
6 | 1.8.4.3.1.1 |  |  |  |  | Initial QAD Submission window opens | 100% | Mon 09/06/25 | Mon 09/06/25 | 0 days | Mon 09/06/25 | Mon 09/06/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.1.2 |  |  |  |  | Qualification Wave 2 Participants Submit Initial QAD | 100% | Mon 09/06/25 | Fri 12/09/25 | 70 days | Mon 09/06/25 | Fri 12/09/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.1.3 | T3 | T3-QU-0098 | QAG |  | Minimum threshold of Qualification Wave 2 Participants required for QT start have submitted their initial QAD | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.1.4 |  |  |  |  | All Qualification Wave 2 Participants have submitted their initial QAD | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.1.5 |  |  |  |  | Code Bodies review of Wave 2 Participants' Initial QAD | 70% | Mon 15/09/25 | Fri 17/10/25 | 25 days | Mon 15/09/25 | Fri 17/10/25 | 0 days | 0 days | -1 day | Code Bodies |  | 6.13 | Yes |  | 21/01/26 - 3/20 pending approval....
6 | 1.8.4.3.1.6 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Fri 17/10/25 | Fri 17/10/25 | 0 days | Fri 17/10/25 | Fri 17/10/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes |  | 21/01/26 - 3/20 pending approval.
5 | 1.8.4.3.2 |  |  |  |  | Qualification Wave 2 Test Prep | 100% | Mon 21/07/25 | Fri 10/10/25 | 60 days | Mon 21/07/25 | Fri 10/10/25 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.8.4.3.2.1 | T3 | T3-QU-0021 | QAG |  | Confirmation from Qualification Wave 2 Participants that DIP Onboarding has commenced | 100% | Mon 21/07/25 | Mon 21/07/25 | 0 days | Mon 21/07/25 | Mon 21/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.2.2 |  |  |  |  | Qualification Wave 2 Participants DIP Onboarding Window | 100% | Mon 21/07/25 | Fri 05/09/25 | 35 days | Mon 21/07/25 | Fri 05/09/25 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.2.3 |  |  |  |  | Confirmation from Qualificiation Wave 2 Participants that DIP onboarding has completed | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 05/09/25 | Fri 05/09/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.2.4 | T3 | T3-QU-0099 | QAG |  | Minimum threshold of Qualification Wave 2 Participants' required for QT start to provide status of PIT completion and submit QT Test Plan | 100% | Mon 18/08/25 | Mon 18/08/25 | 0 days | Mon 18/08/25 | Mon 18/08/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.2.5 |  |  |  |  | All Qualification Wave 2 Participants' to provide status of PIT completion and submit QT Test Plan | 100% | Mon 18/08/25 | Mon 18/08/25 | 0 days | Mon 18/08/25 | Mon 18/08/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.2.6 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 100% | Mon 18/08/25 | Fri 05/09/25 | 15 days | Mon 18/08/25 | Fri 05/09/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.3.2.7 | T3 | T3-QU-0020 | QAG |  | Minimum threshold of Qualification Test Plans for Wave 2 Participants required for QT start approved | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 05/09/25 | Fri 05/09/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.3.2.8 |  |  |  |  | All Qualification Test Plans for Wave 2 Participants approved | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 05/09/25 | Fri 05/09/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.3.2.9 | T3 | T3-QU-0100 | QAG |  | Minimum threshold of Qualification Wave 2 Participants required for QT start have submitted PIT Test Completion Report and evidence for QT entry | 100% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Mon 08/09/25 | Mon 08/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.2.10 |  |  |  |  | All Qualification Wave 2 Participants have submitted PIT Test Completion Report and evidence for QT entry | 100% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Mon 08/09/25 | Mon 08/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.2.11 |  |  |  |  | Review of Participants' PIT Test Completion Report | 100% | Mon 08/09/25 | Fri 10/10/25 | 25 days | Mon 08/09/25 | Fri 10/10/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.3.2.12 |  |  |  |  | Onboarding to QTF & ADO | 100% | Mon 08/09/25 | Fri 10/10/25 | 25 days | Mon 08/09/25 | Fri 10/10/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.8.4.3.3 |  |  |  |  | Qualification Wave 2 QT Execution | 99% | Mon 13/10/25 | Fri 27/02/26 | 100 days | Mon 13/10/25 | Fri 27/02/26 | 0 days | 0 days | 1 day | N/A |  | 6.13 | Yes
6 | 1.8.4.3.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 2 Participant | 100% | Mon 13/10/25 | Fri 17/10/25 | 5 days | Mon 13/10/25 | Fri 17/10/25 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.3.3.2 | T3 | T3-QU-0033 | QAG |  | Minimum threshold of Qualification Wave 2 Participant required for QT start Test Readiness Confirmed | 100% | Fri 17/10/25 | Fri 17/10/25 | 0 days | Fri 17/10/25 | Fri 17/10/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.3.3.3 |  |  |  |  | All Qualification Wave 2 Participant Test Readiness Confirmed | 100% | Fri 17/10/25 | Fri 17/10/25 | 0 days | Fri 17/10/25 | Fri 17/10/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.3.3.4 | T3 | T3-QU-0034 | QAG |  | Qualification Wave 2 Execution Start | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.3.5 |  |  |  |  | Qualification Wave 2 QT Execution Window | 99% | Mon 20/10/25 | Fri 27/02/26 | 95 days | Mon 20/10/25 | Fri 27/02/26 | 0 days | 0 days | 1 day | Participants |  | 6.13 | Yes |  | 26/01/26 - Incomplete - completed test execution, pending PIT evidence however
6 | 1.8.4.3.3.6 | T3 | T3-QU-0055 | QAG |  | Qualfication Wave 2 QT Execution End | 0% | Fri 27/02/26 | Fri 27/02/26 | 0 days | Fri 27/02/26 | Fri 27/02/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.8.4.3.4 |  |  |  |  | Qualification Wave 2 Exit | 24% | Mon 20/10/25 | Thu 28/05/26 | 159 days | Mon 20/10/25 | Thu 28/05/26 | 0 days | 0 days | 6 days | N/A |  | 6.13 | Yes
6 | 1.8.4.3.4.1 |  |  |  |  | Final QAD Submission window opens | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.4.2 |  |  |  |  | Qualification Wave 2 Participants submit their Final QAD | 30% | Mon 20/10/25 | Fri 06/03/26 | 100 days | Mon 20/10/25 | Fri 06/03/26 | 0 days | 0 days | 1 day | Participants |  | 6.13 | Yes
6 | 1.8.4.3.4.3 | T3 | T3-QU-0101 | QAG |  | 80% of M14 Critical Qualification Wave 2 Participants have submitted their final QAD | 0% | Fri 06/03/26 | Fri 06/03/26 | 0 days | Fri 06/03/26 | Fri 06/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.4.4 |  |  |  |  | All Qualification Wave 2 Participants have submitted their final QAD | 0% | Fri 06/03/26 | Fri 06/03/26 | 0 days | Fri 06/03/26 | Fri 06/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.3.4.5 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Mon 09/03/26 | Mon 13/04/26 | 26 days | Mon 09/03/26 | Mon 13/04/26 | 0 days | 0 days | -1 day | Code Bodies |  | 6.13 | Yes
6 | 1.8.4.3.4.6 |  |  |  |  | QAD Sign Off deadline | 0% | Mon 20/04/26 | Mon 20/04/26 | 1 day | Mon 20/04/26 | Mon 20/04/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.3.4.7 | T3 | T3-QU-0135 | QAG |  | 80% of M14 Critical Wave 2 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 28/05/26 | Thu 28/05/26 | 0 days | Thu 28/05/26 | Thu 28/05/26 | 0 days | -1 day | 0 days | Code Bodies |  | 6.38 | Yes
6 | 1.8.4.3.4.8 | T2 | T2-QU-0200 | QAG |  | All M14 Critical Wave 2 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 28/05/26 | Thu 28/05/26 | 0 days | Thu 28/05/26 | Thu 28/05/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.38 | Yes
4 | 1.8.4.4 |  |  |  |  | Qualification Wave 3 | 48% | Mon 11/08/25 | Thu 30/07/26 | 254 days? | Mon 11/08/25 | Thu 30/07/26 | 0 days | 0 days | 15 days? | N/A |  | 6.13 | Yes
5 | 1.8.4.4.1 |  |  |  |  | Qualification Wave 3 QAD Prep | 98% | Mon 11/08/25 | Fri 19/12/25 | 95 days | Mon 11/08/25 | Fri 19/12/25 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.8.4.4.1.1 |  |  |  |  | Initial QAD Submission window opens | 100% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Mon 11/08/25 | Mon 11/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.1.2 |  |  |  |  | Qualification Wave 3 Participants Submit Initial QAD | 100% | Mon 11/08/25 | Fri 07/11/25 | 65 days | Mon 11/08/25 | Fri 07/11/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.1.3 | T3 | T3-QU-0102 | QAG |  | Minimum threshold of Qualification Wave 3 Participants required for QT start have submitted their initial QAD | 100% | Fri 07/11/25 | Fri 07/11/25 | 0 days | Fri 07/11/25 | Fri 07/11/25 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.1.4 |  |  |  |  | All Qualification Wave 3 Participants have submitted their initial QAD | 100% | Fri 07/11/25 | Fri 07/11/25 | 0 days | Fri 07/11/25 | Fri 07/11/25 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.1.5 |  |  |  |  | Code Bodies review of Wave 3 Participants' Initial QAD | 93% | Mon 10/11/25 | Fri 19/12/25 | 30 days | Mon 10/11/25 | Fri 19/12/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.13 | Yes |  | 26/01/26 - Code Bodies still working with PPs to close out remaining comments on Final QAD.
6 | 1.8.4.4.1.6 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Fri 19/12/25 | Fri 19/12/25 | 0 days | Fri 19/12/25 | Fri 19/12/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes |  | 26/01/26 - Code Bodies still working with PPs to close out remaining comments on Final QAD.
5 | 1.8.4.4.2 |  |  |  |  | Qualification Wave 3 Test Prep | 82% | Mon 15/09/25 | Fri 12/12/25 | 65 days | Mon 15/09/25 | Fri 12/12/25 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.8.4.4.2.1 | T3 | T3-QU-0025 | QAG |  | Confirmation from Qualification Wave 3 Participants that DIP Onboarding has commenced | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.2.2 |  |  |  |  | Qualification Wave 3 Participants DIP Onboarding window | 100% | Mon 15/09/25 | Fri 31/10/25 | 35 days | Mon 15/09/25 | Fri 31/10/25 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.2.3 |  |  |  |  | Confirmation from Qualification Wave 3 Participants that DIP onboarding has completed | 100% | Fri 31/10/25 | Fri 31/10/25 | 0 days | Fri 31/10/25 | Fri 31/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.2.4 | T3 | T3-QU-0103 | QAG |  | Minimum threshold of Qualification Wave 3 Participants' required for QT start to provide status of PIT completion and submit QT Test Plan | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.2.5 |  |  |  |  | All Qualification Wave 3 Participants' to provide status of PIT completion and submit QT Test Plan | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.2.6 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 100% | Mon 20/10/25 | Fri 07/11/25 | 15 days | Mon 20/10/25 | Fri 07/11/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.4.2.7 | T3 | T3-QU-0024 | QAG |  | Minimum threshold of Qualification Test Plans for Wave 3 Participants required for QT start approved | 100% | Fri 07/11/25 | Fri 07/11/25 | 0 days | Fri 07/11/25 | Fri 07/11/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.4.2.8 |  |  |  |  | All Qualification Test Plans for Wave 3 Participants approved | 100% | Fri 07/11/25 | Fri 07/11/25 | 0 days | Fri 07/11/25 | Fri 07/11/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.4.2.9 | T3 | T3-QU-0104 | QAG |  | Minimum threshold of Qualification Wave 3 Participants required for QT start have submitted PIT Test Completion Report and evidence for QT Entry | 100% | Mon 10/11/25 | Mon 10/11/25 | 0 days | Mon 10/11/25 | Mon 10/11/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.2.10 |  |  |  |  | All Qualification Wave 3 Participants have submitted PIT Test Completion Report and evidence for QT Entry | 0% | Mon 10/11/25 | Mon 10/11/25 | 0 days | Mon 10/11/25 | Mon 10/11/25 | 0 days | -1 day | 0 days | Participants |  | 6.38 | Yes |  | 26/01/26 - 2 reviews outstanding and 1 PP submission outstanding.
6 | 1.8.4.4.2.11 |  |  |  |  | Review of Participants' PIT Test Completion Report | 28% | Mon 10/11/25 | Fri 12/12/25 | 25 days | Mon 10/11/25 | Fri 12/12/25 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes |  | 26/01/26 - 2 reviews outstanding and 1 PP submission outstanding.
6 | 1.8.4.4.2.12 |  |  |  |  | Onboarding to QTF & ADO | 100% | Mon 10/11/25 | Fri 12/12/25 | 25 days | Mon 10/11/25 | Fri 12/12/25 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes |  | 26/01/26 - 2 reviews outstanding and 1 PP submission outstanding.
5 | 1.8.4.4.3 |  |  |  |  | Qualification Wave 3 QT Execution | 19% | Mon 15/12/25 | Fri 15/05/26 | 110 days? | Mon 03/11/25 | Tue 24/03/26 | 30 days | 38 days | 10 days? | N/A |  | 6.13 | Yes
6 | 1.8.4.4.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 3 Participant | 100% | Mon 15/12/25 | Fri 19/12/25 | 5 days | Mon 15/12/25 | Fri 19/12/25 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.4.3.2 | T3 | T3-QU-0038 | QAG |  | Minimum threshold of Qualification Wave 3 Participant required for QT start Test Readiness confirmed | 100% | Fri 19/12/25 | Fri 19/12/25 | 0 days | Fri 19/12/25 | Fri 19/12/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes
6 | 1.8.4.4.3.3 |  |  |  |  | All Qualification Wave 3 Participant Test Readiness confirmed | 100% | Fri 19/12/25 | Fri 19/12/25 | 0 days | Fri 19/12/25 | Fri 19/12/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.38 | Yes |  | 13/01/26 - 2 reviews outstanding and 1 PP submission outstanding.
6 | 1.8.4.4.3.4 | T3 | T3-QU-0039 | QAG |  | Qualification Wave 3 Execution Start | 100% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Mon 12/01/26 | Mon 12/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.3.5 |  |  |  |  | Qualification Wave 3 QT Execution Window | 14% | Mon 12/01/26 | Fri 15/05/26 | 90 days | Mon 12/01/26 | Fri 15/05/26 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes |  | 26/01/26 - Wave 3 test execution completion score standing at 14% - well above 7% target for end of last week
6 | 1.8.4.4.3.6 | T3 | T3-QU-0056 | QAG |  | Qualification Wave 3 Projected Execution End | 0% | Fri 15/05/26 | Fri 15/05/26 | 0 days | Fri 15/05/26 | Fri 15/05/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.8.4.4.4 |  |  |  |  | Qualification Wave 3 Exit | 2% | Mon 12/01/26 | Thu 30/07/26 | 144 days | Mon 12/01/26 | Thu 30/07/26 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.8.4.4.4.1 |  |  |  |  | Final QAD Submission window opens | 100% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Mon 12/01/26 | Mon 12/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.4.2 |  |  |  |  | Qualification Wave 3 Participants submit their Final QAD | 2% | Mon 12/01/26 | Fri 22/05/26 | 95 days | Mon 12/01/26 | Fri 22/05/26 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.4.3 | T3 | T3-QU-0105 | QAG |  | 80% of M14 Critical Qualification Wave 3 Participants have submitted their Final QAD | 0% | Fri 22/05/26 | Fri 22/05/26 | 0 days | Fri 22/05/26 | Fri 22/05/26 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.4.4 |  |  |  |  | All Qualification Wave 3 Participants have submitted their Final QAD | 0% | Fri 22/05/26 | Fri 22/05/26 | 0 days | Fri 22/05/26 | Fri 22/05/26 | 1 day | 0 days | 0 days | Participants |  | 6.38 | Yes
6 | 1.8.4.4.4.5 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Mon 25/05/26 | Fri 19/06/26 | 20 days | Mon 25/05/26 | Fri 19/06/26 | 0 days | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
6 | 1.8.4.4.4.6 |  |  |  |  | QAD Sign Off deadline | 0% | Fri 26/06/26 | Fri 26/06/26 | 1 day | Fri 26/06/26 | Fri 26/06/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.4.4.7 | T3 | T3-QU-0136 | QAG |  | 80% of M14 Critical Wave 3 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 30/07/26 | Thu 30/07/26 | 0 days | Thu 30/07/26 | Thu 30/07/26 | 0 days | -1 day | 0 days | Code Bodies |  | 6.38 | Yes
6 | 1.8.4.4.4.8 | T2 | T2-QU-0250 | QAG |  | All M14 Critical Wave 3 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 30/07/26 | Thu 30/07/26 | 0 days | Thu 30/07/26 | Thu 30/07/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.38 | Yes
4 | 1.8.4.5 |  |  |  |  | Qualification Wave 4 | 26% | Thu 23/01/25 | Thu 28/01/27 | 526 days | Mon 20/10/25 | Thu 28/01/27 | -192 days | 0 days | 277 days | N/A |  | 6.13 | Yes
5 | 1.8.4.5.1 |  |  |  |  | Qualification Wave 4 QAD Prep | 69% | Mon 20/10/25 | Fri 27/02/26 | 95 days | Mon 20/10/25 | Fri 27/02/26 | 0 days | 0 days | -4 days | N/A |  | 6.13 | Yes
6 | 1.8.4.5.1.1 |  |  |  |  | Initial QAD Submission window opens | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.5.1.2 |  |  |  |  | Qualification Wave 4 Participants Submit Initial QAD | 90% | Mon 20/10/25 | Fri 16/01/26 | 65 days | Mon 20/10/25 | Fri 16/01/26 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes |  | 26/01/26 - 42/43 received.
6 | 1.8.4.5.1.3 | T3 | T3-QU-0106 | QAG |  | Qualification Wave 4 Participants have submitted their Initial QAD | 0% | Fri 16/01/26 | Fri 16/01/26 | 0 days | Fri 16/01/26 | Fri 16/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes |  | 26/01/26 - 42/43 received.
6 | 1.8.4.5.1.4 |  |  |  |  | Code Bodies review of Wave 4 Participants' Initial QAD | 25% | Mon 19/01/26 | Fri 27/02/26 | 30 days | Mon 19/01/26 | Fri 27/02/26 | 0 days | 0 days | 1 day | Code Bodies |  | 6.13 | Yes
6 | 1.8.4.5.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Fri 27/02/26 | Fri 27/02/26 | 0 days | Fri 27/02/26 | Fri 27/02/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.8.4.5.2 |  |  |  |  | Qualification Wave 4 Test Prep | 38% | Mon 03/11/25 | Fri 13/02/26 | 75 days | Mon 03/11/25 | Fri 13/02/26 | 0 days | 0 days | 8 days | N/A |  | 6.13 | Yes
6 | 1.8.4.5.2.1 | T3 | T3-QU-0031 | QAG |  | Confirmation from Qualification 4 Participants that DIP Onboarding has commenced | 100% | Mon 03/11/25 | Mon 03/11/25 | 0 days | Mon 03/11/25 | Mon 03/11/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.5.2.2 |  |  |  |  | Qualification Wave 4 Participants DIP Onboarding Window | 83% | Mon 03/11/25 | Fri 19/12/25 | 35 days | Mon 03/11/25 | Fri 19/12/25 | 0 days | 0 days | -7 days | Participants |  | 6.13 | Yes |  | 26/01/26 - 11 / 18 Wave PPs have been onbaorded to DIP. Code Bodies working with those PPs who have not onboarded yet to have them in DIP in time for Wave 4 QT.
6 | 1.8.4.5.2.3 |  |  |  |  | Confirmation from Qualification Wave 4 Participants that DIP onboarding has completed | 0% | Fri 19/12/25 | Fri 19/12/25 | 0 days | Fri 19/12/25 | Fri 19/12/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes |  | 26/01/26 - 11 / 18 Wave PPs have been onbaorded to DIP. Code Bodies working with those PPs who have not onboarded yet to have them in DIP in time for Wave 4 QT.
6 | 1.8.4.5.2.4 | T3 | T3-QU-0107 | QAG |  | Qualification Wave 4 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | Mon 08/12/25 | Mon 08/12/25 | 0 days | Mon 08/12/25 | Mon 08/12/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes |  | 26/01/26 - 8/18 PIT QT Entry Complete (6/18 with participants to address comments, 4/18 under aassurance team review)
6 | 1.8.4.5.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 50% | Mon 08/12/25 | Fri 09/01/26 | 25 days | Mon 08/12/25 | Fri 09/01/26 | 0 days | 0 days | 9 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes |  | 26/01/26 - Per the completion percentage, 50% of reviews completed.
6 | 1.8.4.5.2.6 | T3 | T3-QU-0030 | QAG |  | Qualification Test Plans for Qualification Wave 4 Participants approved | 0% | Fri 09/01/26 | Fri 09/01/26 | 0 days | Fri 09/01/26 | Fri 09/01/26 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes |  | 26/01/26 - Per the completion percentage, 50% of reviews completed.
6 | 1.8.4.5.2.7 | T3 | T3-QU-0108 | QAG |  | Qualification Wave 4 Participants have submitted PIT Test Completion Report and evidence for QT entry | 0% | Fri 09/01/26 | Fri 09/01/26 | 0 days | Fri 09/01/26 | Fri 09/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes |  | 26/01/26 - 8/18 PIT QT Entry Complete (6/18 with participants to address comments, 4/18 under aassurance team review)
6 | 1.8.4.5.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | Mon 12/01/26 | Fri 13/02/26 | 25 days | Mon 12/01/26 | Fri 13/02/26 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.5.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | Mon 12/01/26 | Fri 13/02/26 | 25 days | Mon 12/01/26 | Fri 13/02/26 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.8.4.5.3 |  |  |  |  | Qualification Wave 4 QT Execution | 0% | Mon 02/03/26 | Fri 17/07/26 | 100 days | Mon 02/03/26 | Fri 17/07/26 | 0 days | 0 days | -1 day | N/A |  | 6.13 | Yes
6 | 1.8.4.5.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 4 Participant | 0% | Mon 02/03/26 | Fri 06/03/26 | 5 days | Mon 02/03/26 | Fri 06/03/26 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.5.3.2 | T3 | T3-QU-0043 | QAG |  | Qualification Wave 4 Participant Test Readiness Confirmed | 0% | Fri 06/03/26 | Fri 06/03/26 | 0 days | Fri 06/03/26 | Fri 06/03/26 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.8.4.5.3.3 | T3 | T3-QU-0044 | QAG |  | Qualification Wave 4 QT Execution Start | 0% | Mon 09/03/26 | Mon 09/03/26 | 0 days | Mon 09/03/26 | Mon 09/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.5.3.4 |  |  |  |  | Qualification Wave 4 QT Execution Window | 0% | Mon 09/03/26 | Fri 17/07/26 | 95 days | Mon 09/03/26 | Fri 17/07/26 | 0 days | 0 days | -1 day | Participants |  | 6.13 | Yes
6 | 1.8.4.5.3.5 | T3 | T3-QU-0057 | QAG |  | Qualification Wave 4 Projected Execution End | 0% | Fri 17/07/26 | Fri 17/07/26 | 0 days | Fri 17/07/26 | Fri 17/07/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.8.4.5.4 |  |  |  |  | Qualification Wave 4 Exit | 0% | Mon 09/03/26 | Thu 24/09/26 | 144 days | Mon 09/03/26 | Thu 24/09/26 | 0 days | 0 days | -6 days | N/A |  | 6.13 | Yes
6 | 1.8.4.5.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | Mon 09/03/26 | Mon 09/03/26 | 0 days | Mon 09/03/26 | Mon 09/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.5.4.2 |  |  |  |  | Qualification Wave 4 Participants submit their Final QAD | 0% | Mon 09/03/26 | Fri 24/07/26 | 100 days | Mon 09/03/26 | Fri 24/07/26 | 0 days | 0 days | -1 day | Participants |  | 6.13 | Yes
6 | 1.8.4.5.4.3 | T3 | T3-QU-0109 | QAG |  | Qualification Wave 4 Participants have submitted their Final QAD | 0% | Fri 24/07/26 | Fri 24/07/26 | 0 days | Fri 24/07/26 | Fri 24/07/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.5.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Mon 27/07/26 | Fri 21/08/26 | 20 days | Mon 27/07/26 | Fri 21/08/26 | 0 days | 0 days | -5 days | Code Bodies |  | 6.13 | Yes
6 | 1.8.4.5.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | Fri 28/08/26 | Fri 28/08/26 | 1 day | Fri 28/08/26 | Fri 28/08/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.8.4.5.4.6 | T3 | T2-QU-0300 | QAG |  | Qualification Wave 4 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 24/09/26 | Thu 24/09/26 | 0 days | Thu 24/09/26 | Thu 24/09/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.8.4.5.5 |  |  |  |  | Qualification Tier 1 Milestone | 0% | Wed 28/10/26 | Thu 28/01/27 | 66 days | Wed 28/10/26 | Thu 28/01/27 | 1 day | 0 days | 66 days | CPT |  | 6.13 | Yes
6 | 1.8.4.5.5.1 | T1 | T1-MI-5000 | PSG |  | All suppliers must be able to access MPANs under the new TOM (M14) | 0% | Wed 28/10/26 | Wed 28/10/26 | 0 days | Wed 28/10/26 | Wed 28/10/26 | 1 day | 0 days | 0 days | CPT |  | 6.13 | Yes
6 | 1.8.4.5.5.2 | T1 | T1-MI-5500 | PSG |  | All suppliers must be able to access MPANs under the new TOM (M14*) - Late Exit | 0% | Thu 28/01/27 | Thu 28/01/27 | 0 days | Thu 28/01/27 | Thu 28/01/27 | 1 day | 0 days | 0 days | CPT |  | 6.13 | Yes
5 | 1.8.4.5.6 |  |  |  |  | PAB dates | 99% | Thu 23/01/25 | Wed 09/12/26 | 490 days | Thu 23/01/25 | Thu 18/12/25 | 0 days | 254 days | 490 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.1 |  |  | PAB |  | PAB288 | 100% | Thu 23/01/25 | Thu 23/01/25 | 0 days | Thu 23/01/25 | Thu 23/01/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.2 |  |  | PAB |  | PAB289 | 100% | Wed 26/02/25 | Thu 27/02/25 | 2 days | Wed 26/02/25 | Thu 27/02/25 | 0 days | 0 days | 2 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.3 |  |  | PAB |  | PAB290 | 100% | Wed 12/03/25 | Wed 12/03/25 | 0 days | Wed 12/03/25 | Wed 12/03/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.4 |  |  | PAB |  | PAB291 | 100% | Thu 27/03/25 | Thu 27/03/25 | 0 days | Thu 27/03/25 | Thu 27/03/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.5 |  |  | PAB |  | PAB292 | 100% | Wed 09/04/25 | Wed 09/04/25 | 0 days | Wed 09/04/25 | Wed 09/04/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.6 |  |  | PAB |  | PAB293 | 100% | Thu 24/04/25 | Thu 24/04/25 | 0 days | Thu 24/04/25 | Thu 24/04/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.7 |  |  | PAB |  | PAB294 | 100% | Wed 14/05/25 | Wed 14/05/25 | 0 days | Wed 14/05/25 | Wed 14/05/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.8 |  |  | PAB |  | PAB295 | 100% | Thu 29/05/25 | Thu 29/05/25 | 0 days | Thu 29/05/25 | Thu 29/05/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.9 |  |  | PAB |  | PAB296 | 100% | Wed 11/06/25 | Wed 11/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.10 |  |  | PAB |  | PAB297 | 100% | Thu 26/06/25 | Thu 26/06/25 | 0 days | Thu 26/06/25 | Thu 26/06/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.11 |  |  | PAB |  | PAB298 | 100% | Wed 16/07/25 | Wed 16/07/25 | 0 days | Wed 16/07/25 | Wed 16/07/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.12 |  |  | PAB |  | PAB299 | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.13 |  |  | PAB |  | PAB300 | 100% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Wed 13/08/25 | Wed 13/08/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.14 |  |  | PAB |  | PAB301 | 100% | Wed 27/08/25 | Thu 28/08/25 | 2 days | Thu 28/08/25 | Thu 28/08/25 | -1 day | 0 days | 2 days | S&A Qualification |  | 6.32 | Yes
6 | 1.8.4.5.6.15 |  |  | PAB |  | PAB302 | 100% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Wed 10/09/25 | Wed 10/09/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.16 |  |  | PAB |  | PAB303 | 100% | Thu 25/09/25 | Thu 25/09/25 | 0 days | Thu 25/09/25 | Thu 25/09/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.17 |  |  | PAB |  | PAB304 | 100% | Wed 15/10/25 | Wed 15/10/25 | 0 days | Wed 15/10/25 | Wed 15/10/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.18 |  |  | PAB |  | PAB305 | 100% | Thu 30/10/25 | Thu 30/10/25 | 0 days | Thu 30/10/25 | Thu 30/10/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.19 |  |  | PAB |  | PAB306 | 100% | Wed 12/11/25 | Wed 12/11/25 | 0 days | Wed 12/11/25 | Wed 12/11/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.20 |  |  | PAB |  | PAB307 | 100% | Thu 27/11/25 | Thu 27/11/25 | 0 days | Thu 27/11/25 | Thu 27/11/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.21 |  |  | PAB |  | PAB308 | 100% | Thu 18/12/25 | Thu 18/12/25 | 0 days | Thu 18/12/25 | Thu 18/12/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.18 | Yes
6 | 1.8.4.5.6.22 |  |  | PAB |  | PAB2026/01 | 0% | Thu 29/01/26 | Thu 29/01/26 | 0 days | Thu 29/01/26 | Thu 29/01/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.23 |  |  | PAB |  | PAB2026/02 | 0% | Wed 11/02/26 | Wed 11/02/26 | 0 days | Wed 11/02/26 | Wed 11/02/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.24 |  |  | PAB |  | PAB2026/03 | 0% | Thu 26/02/26 | Thu 26/02/26 | 0 days | Thu 26/02/26 | Thu 26/02/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.25 |  |  | PAB |  | PAB2026/04 | 0% | Wed 11/03/26 | Wed 11/03/26 | 0 days | Wed 11/03/26 | Wed 11/03/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.26 |  |  | PAB |  | PAB2026/05 | 0% | Thu 26/03/26 | Thu 26/03/26 | 0 days | Thu 26/03/26 | Thu 26/03/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.27 |  |  | PAB |  | PAB2026/06 | 0% | Wed 15/04/26 | Wed 15/04/26 | 0 days | Wed 15/04/26 | Wed 15/04/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.28 |  |  | PAB |  | PAB2026/07 | 0% | Thu 30/04/26 | Thu 30/04/26 | 0 days | Thu 30/04/26 | Thu 30/04/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.29 |  |  | PAB |  | PAB2026/08 | 0% | Wed 13/05/26 | Wed 13/05/26 | 0 days | Wed 13/05/26 | Wed 13/05/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.30 |  |  | PAB |  | PAB2026/09 | 0% | Thu 28/05/26 | Thu 28/05/26 | 0 days | Thu 28/05/26 | Thu 28/05/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.31 |  |  | PAB |  | PAB2026/10 | 0% | Wed 10/06/26 | Wed 10/06/26 | 0 days | Wed 10/06/26 | Wed 10/06/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.32 |  |  | PAB |  | PAB2026/11 | 0% | Thu 25/06/26 | Thu 25/06/26 | 0 days | Thu 25/06/26 | Thu 25/06/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.33 |  |  | PAB |  | PAB2026/12 | 0% | Wed 15/07/26 | Wed 15/07/26 | 0 days | Wed 15/07/26 | Wed 15/07/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.34 |  |  | PAB |  | PAB2026/13 | 0% | Thu 30/07/26 | Thu 30/07/26 | 0 days | Thu 30/07/26 | Thu 30/07/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.35 |  |  | PAB |  | PAB2026/14 | 0% | Wed 12/08/26 | Wed 12/08/26 | 0 days | Wed 12/08/26 | Wed 12/08/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.36 |  |  | PAB |  | PAB2026/15 | 0% | Thu 27/08/26 | Thu 27/08/26 | 0 days | Thu 27/08/26 | Thu 27/08/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.37 |  |  | PAB |  | PAB2026/16 | 0% | Wed 09/09/26 | Wed 09/09/26 | 0 days | Wed 09/09/26 | Wed 09/09/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.38 |  |  | PAB |  | PAB2026/17 | 0% | Thu 24/09/26 | Thu 24/09/26 | 0 days | Thu 24/09/26 | Thu 24/09/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.39 |  |  | PAB |  | PAB2026/18 | 0% | Wed 14/10/26 | Wed 14/10/26 | 0 days | Wed 14/10/26 | Wed 14/10/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.40 |  |  | PAB |  | PAB2026/19 | 0% | Thu 29/10/26 | Thu 29/10/26 | 0 days | Thu 29/10/26 | Thu 29/10/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.41 |  |  | PAB |  | PAB2026/20 | 0% | Wed 11/11/26 | Wed 11/11/26 | 0 days | Wed 11/11/26 | Wed 11/11/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.42 |  |  | PAB |  | PAB2026/21 | 0% | Thu 26/11/26 | Thu 26/11/26 | 0 days | Thu 26/11/26 | Thu 26/11/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
6 | 1.8.4.5.6.43 |  |  | PAB |  | PAB2026/22 | 0% | Wed 09/12/26 | Wed 09/12/26 | 0 days | Wed 09/12/26 | Wed 09/12/26 | 1 day | 0 days | 0 days | S&A Qualification |  | 6.39 | Yes
2 | 1.9 |  |  |  |  | REGULATORY | 100% | Mon 31/10/22 | Wed 24/12/25 | 823 days | Mon 31/10/22 | Wed 24/12/25 | 0 days | 0 days | 143 days | N/A |  | 6.18 | Yes
3 | 1.9.1 |  |  |  |  | Baseline MHHS Code Changes | 100% | Mon 31/10/22 | Fri 23/08/24 | 475 days | Mon 31/10/22 | Fri 23/08/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.1.1 |  |  |  |  | Preparation and planning | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.9.1.1.1 |  |  |  |  | Impact assessment of Programme design on codes to determine required changes | 100% | Mon 31/10/22 | Fri 25/11/22 | 20 days | Mon 31/10/22 | Fri 25/11/22 | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
5 | 1.9.1.1.2 |  |  |  |  | Become 'code draft ready' | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
5 | 1.9.1.1.3 |  |  |  |  | Soft start drafting where possible | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
4 | 1.9.1.2 |  |  |  |  | Code drafting | 100% | Mon 12/12/22 | Wed 21/08/24 | 443 days | Mon 12/12/22 | Wed 21/08/24 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
5 | 1.9.1.2.1 |  |  |  |  | Data Services (BSC driven) | 100% | Mon 12/12/22 | Wed 24/05/23 | 118 days | Mon 12/12/22 | Wed 24/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.1.1 |  |  |  |  | Pre Code Drafting activities | 100% | Mon 12/12/22 | Fri 16/12/22 | 5 days | Mon 12/12/22 | Fri 16/12/22 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.1.2 |  |  |  |  | Code and subsidiary document drafting takes place offline | 100% | Tue 03/01/23 | Fri 27/01/23 | 19 days | Tue 03/01/23 | Fri 27/01/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.1.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Mon 30/01/23 | Mon 13/02/23 | 11 days | Mon 30/01/23 | Mon 13/02/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.1.4 |  |  |  |  | External industry review via consultation | 100% | Tue 14/02/23 | Mon 13/03/23 | 20 days | Tue 14/02/23 | Mon 13/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.1.5 |  |  |  |  | Triage and action comments | 100% | Fri 10/03/23 | Wed 05/04/23 | 19 days | Fri 10/03/23 | Wed 05/04/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.1.6 |  |  |  |  | CDWG review | 100% | Thu 06/04/23 | Wed 17/05/23 | 30 days | Thu 06/04/23 | Wed 17/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.1.7 |  |  |  |  | CCAG review | 100% | Thu 18/05/23 | Wed 24/05/23 | 5 days | Thu 18/05/23 | Wed 24/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.1.8 | T2 | T2-RE-0100 | CCAG | MHHS-ART060 | Code drafting for Data Services topic area approved | 100% | Wed 24/05/23 | Wed 24/05/23 | 0 days | Wed 24/05/23 | Wed 24/05/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.9.1.2.2 |  |  |  |  | Metering (REC driven) | 100% | Mon 12/12/22 | Wed 24/05/23 | 118 days | Mon 12/12/22 | Wed 24/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.2.1 |  |  |  |  | Pre Code Drafting activities | 100% | Mon 12/12/22 | Fri 16/12/22 | 5 days | Mon 12/12/22 | Fri 16/12/22 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.2.2 |  |  |  |  | Code and subsidiary document drafting takes place offline | 100% | Tue 03/01/23 | Fri 27/01/23 | 19 days | Tue 03/01/23 | Fri 27/01/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.2.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Mon 30/01/23 | Mon 13/02/23 | 11 days | Mon 30/01/23 | Mon 13/02/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.2.4 |  |  |  |  | External industry review via consultation | 100% | Tue 14/02/23 | Mon 13/03/23 | 20 days | Tue 14/02/23 | Mon 13/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.2.5 |  |  |  |  | Triage and action comments | 100% | Fri 10/03/23 | Wed 05/04/23 | 19 days | Fri 10/03/23 | Wed 05/04/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.2.6 |  |  |  |  | CDWG review | 100% | Thu 06/04/23 | Wed 17/05/23 | 30 days | Thu 06/04/23 | Wed 17/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.2.7 |  |  |  |  | CCAG review | 100% | Thu 18/05/23 | Wed 24/05/23 | 5 days | Thu 18/05/23 | Wed 24/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.2.8 | T2 | T2-RE-0150 | CCAG | MHHS-ART060 | Code drafting for Metering topic area approved | 100% | Wed 24/05/23 | Wed 24/05/23 | 0 days | Wed 24/05/23 | Wed 24/05/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.9.1.2.3 |  |  |  |  | BSC Central Services (BSC driven) | 100% | Wed 22/02/23 | Wed 27/09/23 | 156 days | Wed 22/02/23 | Wed 27/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.3.1 |  |  |  |  | Pre Code Drafting activities | 100% | Wed 22/02/23 | Tue 28/02/23 | 5 days | Wed 22/02/23 | Tue 28/02/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.3.2 |  |  |  |  | Code Drafting (offline) | 100% | Wed 01/03/23 | Tue 20/06/23 | 80 days | Wed 01/03/23 | Tue 20/06/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.3.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Wed 15/03/23 | Tue 20/06/23 | 70 days | Wed 15/03/23 | Tue 20/06/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.3.4 |  |  |  |  | External industry review via consultation | 100% | Wed 21/06/23 | Tue 11/07/23 | 15 days | Wed 21/06/23 | Tue 11/07/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.3.5 |  |  |  |  | Triage and action comments | 100% | Mon 10/07/23 | Thu 03/08/23 | 19 days | Mon 10/07/23 | Thu 03/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.3.6 |  |  |  |  | CDWG review | 100% | Fri 04/08/23 | Tue 12/09/23 | 28 days | Fri 04/08/23 | Tue 12/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.3.7 |  |  |  |  | CCAG review | 100% | Wed 13/09/23 | Wed 27/09/23 | 11 days | Wed 13/09/23 | Wed 27/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.3.8 | T2 | T2-RE-0200 | CCAG | MHHS-ART060 | Code drafting for BSC Central Services topic area approved | 100% | Wed 27/09/23 | Wed 27/09/23 | 0 days | Wed 27/09/23 | Wed 27/09/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.9.1.2.4 |  |  |  |  | Registration (BSC & REC driven) | 100% | Wed 22/02/23 | Wed 23/08/23 | 131 days | Wed 22/02/23 | Wed 23/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.4.1 |  |  |  |  | Pre Code Drafting activities | 100% | Wed 22/02/23 | Tue 28/02/23 | 5 days | Wed 22/02/23 | Tue 28/02/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.4.2 |  |  |  |  | Code Drafting (offline) | 100% | Wed 01/03/23 | Tue 30/05/23 | 65 days | Wed 01/03/23 | Tue 30/05/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.4.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Wed 15/03/23 | Tue 30/05/23 | 55 days | Wed 15/03/23 | Tue 30/05/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.4.4 |  |  |  |  | External industry review via consultation | 100% | Wed 31/05/23 | Tue 20/06/23 | 15 days | Wed 31/05/23 | Tue 20/06/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.4.5 |  |  |  |  | Triage and action comments | 100% | Mon 19/06/23 | Thu 13/07/23 | 19 days | Mon 19/06/23 | Thu 13/07/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.4.6 |  |  |  |  | CDWG review | 100% | Fri 14/07/23 | Tue 08/08/23 | 18 days | Fri 14/07/23 | Tue 08/08/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.4.7 |  |  |  |  | CCAG review | 100% | Wed 09/08/23 | Wed 23/08/23 | 11 days | Wed 09/08/23 | Wed 23/08/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.4.8 | T2 | T2-RE-0250 | CCAG | MHHS-ART060 | Code drafting for Registration topic area approved | 100% | Wed 23/08/23 | Wed 23/08/23 | 0 days | Wed 23/08/23 | Wed 23/08/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.9.1.2.5 |  |  |  |  | Governance and Qualification (BSC & REC driven) | 100% | Thu 25/05/23 | Wed 22/11/23 | 130 days | Thu 25/05/23 | Wed 22/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.5.1 |  |  |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.5.2 |  |  |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Wed 16/08/23 | 55 days | Thu 01/06/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.5.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Wed 16/08/23 | 45 days | Thu 15/06/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.5.4 |  |  |  |  | External industry review via consultation | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.5.5 |  |  |  |  | Triage and action comments | 100% | Wed 06/09/23 | Mon 02/10/23 | 19 days | Wed 06/09/23 | Mon 02/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.5.6 |  |  |  |  | CDWG review | 100% | Tue 03/10/23 | Tue 14/11/23 | 31 days | Tue 03/10/23 | Tue 14/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.5.7 |  |  |  |  | CCAG review | 100% | Wed 15/11/23 | Wed 22/11/23 | 6 days | Wed 15/11/23 | Wed 22/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.5.8 | T2 | T3-RE-0300 | CCAG | MHHS-ART060 | Code drafting for Governance and Qualification topic areas approved | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
5 | 1.9.1.2.6 |  |  |  |  | Interfaces / Data Specification (REC driven) | 100% | Thu 25/05/23 | Tue 23/01/24 | 174 days | Thu 25/05/23 | Tue 23/01/24 | 0 days | 0 days | -1 day | N/A |  | 5.2 | Yes
6 | 1.9.1.2.6.1 |  |  |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.6.2 |  |  |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Tue 10/10/23 | 94 days | Thu 01/06/23 | Tue 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.9.1.2.6.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Tue 10/10/23 | 84 days | Thu 15/06/23 | Tue 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.9.1.2.6.4 |  |  |  |  | External industry review via consultation | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.9.1.2.6.5 |  |  |  |  | Triage and action comments | 100% | Mon 30/10/23 | Fri 24/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.9.1.2.6.6 |  |  |  |  | CDWG review | 100% | Mon 27/11/23 | Tue 16/01/24 | 37 days | Mon 27/11/23 | Tue 16/01/24 | 0 days | 0 days | 5 days | PP |  | 5.2 | Yes
6 | 1.9.1.2.6.7 |  |  |  |  | CCAG review | 100% | Wed 17/01/24 | Tue 23/01/24 | 5 days | Wed 17/01/24 | Tue 23/01/24 | 0 days | 0 days | -6 days | PP |  | 5.2 | Yes
6 | 1.9.1.2.6.8 | T2 | T3-RE-0350 | CCAG | MHHS-ART060 | Code drafting for Interfaces / Data Specification topic areas approved | 100% | Tue 23/01/24 | Tue 23/01/24 | 0 days | Tue 23/01/24 | Tue 23/01/24 | 1 day | 0 days | 0 days | PP |  | 5.16 | Yes
5 | 1.9.1.2.7 |  |  |  |  | Migration (BSC & REC driven) | 100% | Thu 25/05/23 | Wed 22/11/23 | 130 days | Thu 25/05/23 | Wed 22/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.7.1 |  |  |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.7.2 |  |  |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Wed 16/08/23 | 55 days | Thu 01/06/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.7.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Wed 16/08/23 | 45 days | Thu 15/06/23 | Wed 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.7.4 |  |  |  |  | External industry review via consultation | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.7.5 |  |  |  |  | Triage and action comments | 100% | Wed 06/09/23 | Mon 02/10/23 | 19 days | Wed 06/09/23 | Mon 02/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.7.6 |  |  |  |  | CDWG review | 100% | Tue 03/10/23 | Tue 14/11/23 | 31 days | Tue 03/10/23 | Tue 14/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.7.7 |  |  |  |  | CCAG review | 100% | Wed 15/11/23 | Wed 22/11/23 | 6 days | Wed 15/11/23 | Wed 22/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.7.8 | T2 | T3-RE-0400 | CCAG | MHHS-ART060 | Code drafting for Migration topic area approved | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
5 | 1.9.1.2.8 |  |  |  |  | Consequential Code Change | 100% | Wed 11/10/23 | Mon 11/03/24 | 109 days | Wed 11/10/23 | Mon 11/03/24 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
6 | 1.9.1.2.8.1 |  |  |  |  | External industry review via consultation - drop 1 (DCUSA) | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 0 days | 0 days | 0 days | Code Bodies |  | 5.2 | Yes
6 | 1.9.1.2.8.2 |  |  |  |  | External industry review via consultation - drop 2 (Elexon) | 100% | Mon 19/02/24 | Mon 11/03/24 | 16 days | Mon 19/02/24 | Mon 11/03/24 | 0 days | 0 days | 1 day | Code Bodies |  | 5.2 | Yes
5 | 1.9.1.2.9 |  |  |  |  | Transition Text (all codes) | 100% | Fri 11/08/23 | Tue 23/01/24 | 118 days | Fri 11/08/23 | Tue 23/01/24 | 0 days | 0 days | -1 day | N/A |  | 5.2 | Yes
6 | 1.9.1.2.9.1 |  |  |  |  | Pre Code Drafting activities | 100% | Fri 11/08/23 | Tue 22/08/23 | 8 days | Fri 11/08/23 | Tue 22/08/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.9.2 |  |  |  |  | Code Drafting (offline) | 100% | Fri 18/08/23 | Tue 10/10/23 | 38 days | Fri 18/08/23 | Tue 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.9.1.2.9.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Fri 01/09/23 | Tue 10/10/23 | 28 days | Fri 01/09/23 | Tue 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.9.1.2.9.4 |  |  |  |  | External industry review via consultation | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.9.1.2.9.5 |  |  |  |  | Triage and action comments | 100% | Mon 30/10/23 | Fri 24/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.9.1.2.9.6 |  |  |  |  | CDWG review | 100% | Mon 27/11/23 | Tue 16/01/24 | 37 days | Mon 27/11/23 | Tue 16/01/24 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.9.1.2.9.7 |  |  |  |  | CCAG review | 100% | Wed 17/01/24 | Tue 23/01/24 | 5 days | Wed 17/01/24 | Tue 23/01/24 | 0 days | 0 days | -1 day | PP |  | 5.2 | Yes
6 | 1.9.1.2.9.8 | T2 | T3-RE-0450 | CCAG | MHHS-ART060 | Code drafting for Transition Text topic area approved | 100% | Tue 23/01/24 | Tue 23/01/24 | 0 days | Tue 23/01/24 | Tue 23/01/24 | 1 day | 0 days | 0 days | PP |  | 5.16 | Yes
5 | 1.9.1.2.10 |  |  |  |  | Final Code Drafting (mop-up) (all codes) | 100% | Fri 18/08/23 | Wed 22/05/24 | 199 days | Fri 18/08/23 | Wed 22/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.9.1.2.10.1 |  |  |  |  | Forward look and confirm remaining plan | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.9.1.2.10.2 |  |  |  |  | Identify remaining or additional areas of code (e.g. consequential change requirements) to be completed | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.10.3 |  |  |  |  | Code Drafting (offline) Interim Consultation (1) | 100% | Fri 08/09/23 | Thu 30/11/23 | 60 days | Fri 08/09/23 | Thu 30/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.10.4 |  |  |  |  | Internal review and cross-checking of drafting across code drafters Interim Consultation (1) | 100% | Fri 22/09/23 | Thu 30/11/23 | 50 days | Fri 22/09/23 | Thu 30/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.10.5 |  |  |  |  | External industry review via consultation Interim Consultation (1) | 100% | Fri 01/12/23 | Tue 02/01/24 | 23 days | Fri 01/12/23 | Tue 02/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.10.6 |  |  |  |  | Code Drafting (offline) Final Consultation (2) | 100% | Fri 01/12/23 | Thu 15/02/24 | 55 days | Fri 01/12/23 | Thu 15/02/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.10.7 |  |  |  |  | Internal review and cross-checking of drafting across code drafters Final Consultation (2) | 100% | Fri 15/12/23 | Thu 15/02/24 | 45 days | Fri 15/12/23 | Thu 15/02/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.10.8 |  |  |  |  | External industry review via consultation Final Consultation (2) | 100% | Mon 19/02/24 | Mon 11/03/24 | 16 days | Mon 19/02/24 | Mon 11/03/24 | 0 days | 0 days | 1 day | PP |  | 5 | Yes
6 | 1.9.1.2.10.9 |  |  |  |  | Triage and action comments | 100% | Mon 11/03/24 | Wed 03/04/24 | 18 days | Mon 11/03/24 | Wed 03/04/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.10.10 |  |  |  |  | CDWG review | 100% | Thu 04/04/24 | Tue 14/05/24 | 29 days | Thu 04/04/24 | Tue 14/05/24 | 0 days | 0 days | -2 days | PP |  | 5 | Yes
6 | 1.9.1.2.10.11 |  |  |  |  | CCAG review | 100% | Wed 15/05/24 | Wed 22/05/24 | 6 days | Wed 15/05/24 | Wed 22/05/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.9.1.2.10.12 | T2 | T3-RE-0500 | CCAG | MHHS-ART060 | Final code drafting (mop-up) approved | 100% | Wed 22/05/24 | Wed 22/05/24 | 0 days | Wed 22/05/24 | Wed 22/05/24 | 1 day | 0 days | 0 days | PP |  | 5.25 | Yes
5 | 1.9.1.2.11 |  |  |  |  | Final code review, consistency check and approval | 100% | Thu 04/04/24 | Wed 21/08/24 | 100 days | Thu 04/04/24 | Wed 21/08/24 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
6 | 1.9.1.2.11.1 |  |  |  |  | Gap analysis of final code against design artefacts (reverse process to code drafting) | 100% | Thu 04/04/24 | Mon 27/05/24 | 38 days | Thu 04/04/24 | Mon 27/05/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.11.2 |  |  |  |  | Outputs of gap analysis actioned offline | 100% | Tue 28/05/24 | Tue 11/06/24 | 11 days | Tue 28/05/24 | Tue 11/06/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.11.3 |  |  |  |  | Final documentation collated for final consultation | 100% | Wed 12/06/24 | Fri 21/06/24 | 8 days | Wed 12/06/24 | Fri 21/06/24 | 0 days | 0 days | -1 day | Code Drafting PM |  | 5.23 | Yes
6 | 1.9.1.2.11.4 |  |  |  |  | External industry review via consultation | 100% | Mon 24/06/24 | Fri 12/07/24 | 15 days | Mon 24/06/24 | Fri 12/07/24 | 0 days | 0 days | -5 days | PP |  | 5 | Yes
6 | 1.9.1.2.11.5 |  |  |  |  | Triage and action comments | 100% | Mon 15/07/24 | Fri 26/07/24 | 10 days | Mon 15/07/24 | Fri 26/07/24 | 0 days | 0 days | -3 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.9.1.2.11.6 |  |  |  |  | Final CDWG review | 100% | Fri 02/08/24 | Tue 13/08/24 | 8 days | Fri 02/08/24 | Tue 13/08/24 | 0 days | 0 days | 2 days | PP |  | 5 | Yes
6 | 1.9.1.2.11.7 |  |  |  |  | Final CCAG review | 100% | Wed 14/08/24 | Wed 21/08/24 | 6 days | Wed 14/08/24 | Wed 21/08/24 | 0 days | 0 days | -2 days | PP |  | 5 | Yes
6 | 1.9.1.2.11.8 | T2 | T3-RE-0550 | CCAG | MHHS-ART060 | CCAG recommend final code to PSG for baselining | 100% | Wed 21/08/24 | Wed 21/08/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 | 1 day | 0 days | 0 days | PP |  | 5.9 | Yes
4 | 1.9.1.3 | T1 | T1-RE-1000 | PSG | MHHS-ART012 | Code changes baselined (M6) | 100% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.9.2 |  |  |  |  | Ofgem preparation and enactment of SCR powers | 100% | Mon 05/02/24 | Fri 13/12/24 | 225 days | Mon 05/02/24 | Fri 13/12/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.2.1 |  |  |  |  | Preparation and enactment of SCR Powers | 100% | Mon 05/02/24 | Wed 11/12/24 | 223 days | Mon 05/02/24 | Wed 11/12/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.9.2.1.1 |  |  |  |  | Ofgem to keep Ofgem legal informed of process followed and nature of Code drafting to ensure that prepared for SCR go/no go decision | 100% | Mon 05/02/24 | Mon 24/06/24 | 101 days | Mon 05/02/24 | Mon 24/06/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.9.2.1.2 |  |  |  |  | OFGEM Legal to review Code Artefacts deliver policy intent and process followed and confirm that SCR powers are appropriate to use rather than SMAP - SCR go/no go | 100% | Mon 24/06/24 | Thu 11/07/24 | 14 days | Mon 24/06/24 | Thu 11/07/24 | 0 days | 0 days | -1 day | Ofgem |  | 5 | Yes
5 | 1.9.2.1.3 |  |  |  |  | Code Bodies to draft MOD proposal forms | 100% | Fri 12/07/24 | Thu 08/08/24 | 20 days | Fri 12/07/24 | Thu 08/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.4 |  |  |  |  | Ofgem discuss and agree code mod timetable with code bodies (and MHHSP in relation to the dates for expected decisions) | 100% | Fri 12/07/24 | Thu 08/08/24 | 20 days | Fri 12/07/24 | Thu 08/08/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.9.2.1.5 |  |  |  |  | Ofgem to publish each Direction to each code body specifying the timetable for each modification | 100% | Wed 28/08/24 | Wed 28/08/24 | 1 day | Wed 28/08/24 | Wed 28/08/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.9.2.1.6 |  |  |  |  | Formally submit (by separate email) Modification Proposal Forms and legal texts to each code body | 100% | Wed 28/08/24 | Wed 28/08/24 | 1 day | Wed 28/08/24 | Wed 28/08/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.9.2.1.7 |  |  |  |  | Each Code Body publishes and issues Modification Proposal Forms | 100% | Thu 29/08/24 | Mon 02/09/24 | 3 days | Thu 29/08/24 | Mon 02/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.8 |  |  |  |  | Each Code Body sends Modification Proposal Forms to Panel to approve Mod to go to consultation | 100% | Tue 03/09/24 | Mon 16/09/24 | 10 days | Tue 03/09/24 | Mon 16/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.9 |  |  |  |  | Modification Proposal approved by Panel for Consultation | 100% | Tue 17/09/24 | Tue 17/09/24 | 1 day | Tue 17/09/24 | Tue 17/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.10 |  |  |  |  | Draft Modification Report issued for consultation | 100% | Wed 18/09/24 | Wed 18/09/24 | 1 day | Wed 18/09/24 | Wed 18/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.11 |  |  |  |  | Consultation Close-out for representations | 100% | Thu 19/09/24 | Wed 09/10/24 | 15 days | Thu 19/09/24 | Wed 09/10/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.12 |  |  |  |  | Each Code Body reviews consultation response and drafts Modification Report | 100% | Thu 10/10/24 | Wed 23/10/24 | 10 days | Thu 10/10/24 | Wed 23/10/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.9.2.1.13 |  |  |  |  | Final Modification Report sent to Panel for decision with recommendation to approve | 100% | Thu 24/10/24 | Thu 24/10/24 | 1 day | Thu 24/10/24 | Thu 24/10/24 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.9.2.1.14 |  |  |  |  | Modification Panel decision | 100% | Thu 07/11/24 | Thu 07/11/24 | 1 day | Thu 07/11/24 | Thu 07/11/24 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.9.2.1.15 |  |  |  |  | Code Bodies Submit Final Modification/Change Reports | 100% | Fri 08/11/24 | Fri 08/11/24 | 1 day | Fri 08/11/24 | Fri 08/11/24 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.9.2.1.16 |  |  |  |  | Ofgem Reviews Final Modification/Change Reports | 100% | Mon 11/11/24 | Fri 22/11/24 | 10 days | Mon 11/11/24 | Fri 22/11/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
5 | 1.9.2.1.17 |  |  |  |  | Ofgem Drafts Decision/Direction Letters | 100% | Mon 18/11/24 | Tue 10/12/24 | 17 days | Mon 18/11/24 | Tue 10/12/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
5 | 1.9.2.1.18 |  |  |  |  | Ofgem Internally Signs Off the Decision/Direction Letters and Sends Them to the Code Bodies | 100% | Wed 11/12/24 | Wed 11/12/24 | 1 day | Wed 11/12/24 | Wed 11/12/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
4 | 1.9.2.2 | T2 | T2-RE-0600 | CCAG | MHHS-ART012 | Ofgem decisions on M6 baselined code modification proposals (M7) | 100% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 1 day | 0 days | 0 days | CPT |  | 6.11 | Yes
4 | 1.9.2.3 |  |  |  |  | Ofgem Publishes the Decisions/Directions | 100% | Thu 12/12/24 | Fri 13/12/24 | 2 days | Thu 12/12/24 | Fri 13/12/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
3 | 1.9.3 |  |  |  |  | Deliver MHHS Code Changes | 100% | Tue 12/11/24 | Wed 24/12/25 | 292 days | Tue 12/11/24 | Wed 24/12/25 | 0 days | 0 days | 143 days | N/A |  | 6.11 | Yes
4 | 1.9.3.1 |  |  |  |  | Releases | 100% | Tue 12/11/24 | Thu 27/02/25 | 78 days | Tue 12/11/24 | Wed 24/12/25 | 0 days | -214 days | -71 days | N/A |  | 6.11 | Yes
5 | 1.9.3.1.1 |  |  |  |  | Impacted codes make resourcing provisions and prepare to implement new Code via internal code body change processes | 100% | Tue 12/11/24 | Thu 27/02/25 | 78 days | Tue 12/11/24 | Thu 27/02/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.9.3.2 |  |  |  |  | M8 Code Change Preperation | 100% | Fri 31/01/25 | Fri 05/09/25 | 155 days | Fri 31/01/25 | Wed 24/12/25 | 1 day | -78 days | 155 days |  |  | 6.21 | Yes
5 | 1.9.3.2.1 |  | T3-RE-0600 | CCAG |  | Resources confirmed | 100% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1 day | 0 days | 0 days | All |  | 6.21 | Yes
5 | 1.9.3.2.2 |  | T3-RE-0650 | CCAG |  | CDWG Endorsement | 100% | Tue 10/06/25 | Tue 10/06/25 | 0 days | Tue 10/06/25 | Tue 10/06/25 | 1 day | 0 days | 0 days | All |  | 6.21 | Yes
5 | 1.9.3.2.3 |  | T3-RE-0700 | CCAG |  | CCAG Endorsement | 100% | Wed 25/06/25 | Wed 25/06/25 | 0 days | Wed 25/06/25 | Wed 25/06/25 | 1 day | 0 days | 0 days | All |  | 6.21 | Yes
5 | 1.9.3.2.4 |  | T3-RE-0750 | CCAG |  | Send to Ofgem for SCR Direction | 100% | Wed 25/06/25 | Wed 25/06/25 | 0 days | Wed 25/06/25 | Wed 25/06/25 | 1 day | 0 days | 0 days | All |  | 6.21 | Yes
5 | 1.9.3.2.5 |  | T3-RE-0800 | CCAG |  | Freeze M8 Change Control Log 1.0 and create V2.0 | 100% | Wed 02/07/25 | Wed 02/07/25 | 0 days | Wed 02/07/25 | Wed 02/07/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.21 | Yes
5 | 1.9.3.2.6 |  | T3-RE-0850 | CCAG |  | Agree Fast Track Code Change Process | 100% | Wed 02/07/25 | Wed 02/07/25 | 0 days | Wed 02/07/25 | Wed 02/07/25 | 1 day | 0 days | 0 days | MHHSP |  | 6.21 | Yes
5 | 1.9.3.2.7 |  | T3-RE-0900 | CCAG |  | Ofgem direct SCR Code change | 100% | Thu 03/07/25 | Thu 03/07/25 | 0 days | Thu 03/07/25 | Thu 03/07/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.21 | Yes
5 | 1.9.3.2.8 |  | T3-RE-0950 | CCAG |  | Present to Panel | 100% | Thu 10/07/25 | Thu 10/07/25 | 0 days | Thu 10/07/25 | Thu 10/07/25 | 1 day | 0 days | 0 days | Ofgem/Code Bodies |  | 6.21 | Yes
5 | 1.9.3.2.9 |  | T3-RE-1000 | CCAG |  | Code Change Industry Consultation | 100% | Tue 29/07/25 | Tue 29/07/25 | 0 days | Tue 29/07/25 | Tue 29/07/25 | 1 day | 0 days | 0 days | All |  | 6.21 | Yes
5 | 1.9.3.2.10 |  | T3-RE-1050 | CCAG |  | Panel Recommendation | 100% | Thu 14/08/25 | Thu 14/08/25 | 0 days | Thu 14/08/25 | Thu 14/08/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.21 | Yes
5 | 1.9.3.2.11 |  | T3-RE-1100 | CCAG |  | Ofgem Decision | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 05/09/25 | Fri 05/09/25 | 1 day | 0 days | 0 days | Ofgem |  | 6.21 | Yes
4 | 1.9.3.3 |  |  |  |  | Main Code Release | 100% | Mon 15/09/25 | Wed 24/12/25 | 73 days | Wed 17/09/25 | Wed 24/12/25 | -2 days | 0 days | 2 days | N/A |  | 6.11 | Yes
5 | 1.9.3.3.1 |  |  |  |  | Release preparation (e.g. preparing release documentation) | 100% | Mon 15/09/25 | Mon 22/09/25 | 6 days | Wed 17/09/25 | Wed 24/09/25 | -2 days | -2 days | 1 day | Code Bodies |  | 6.11 | Yes
5 | 1.9.3.3.2 |  |  |  |  | Implement new code on day of code release | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | -1 day | -2 days | -1 day | Code Bodies |  | 6.11 | Yes
5 | 1.9.3.3.3 | T2 | T2-RE-0650 | CCAG | MHHS-ART060 | Code changes delivered (M8) | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.21 | Yes
5 | 1.9.3.3.4 | T2 | T2-RE-0700 | CCAG | MHHS-ART060 | Code changes delivered (M8*) late exit | 100% | Wed 24/12/25 | Wed 24/12/25 | 0 days | Wed 24/12/25 | Wed 24/12/25 | 1 day | 0 days | 0 days | CPT |  | 6.11 | Yes
3 | 1.9.4 |  |  |  |  | External Programme Dependency Management | 100% | Fri 01/12/23 | Wed 24/01/24 | 38 days | Fri 01/12/23 | Wed 24/01/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.9.4.1 |  |  |  |  | DCP397 | 100% | Fri 01/12/23 | Wed 24/01/24 | 38 days | Fri 01/12/23 | Wed 24/01/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.9.4.1.1 |  |  |  |  | Ensure DCP397 drafting included in mop-up code drafting activity (link to mop-up) | 100% | Fri 01/12/23 | Thu 28/12/23 | 20 days | Fri 01/12/23 | Thu 28/12/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.9.4.1.2 |  |  |  |  | Implementation of DCP397 | 100% | Wed 24/01/24 | Wed 24/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
2 | 1.1 |  |  | MCAG (Migration) |  | MIGRATION | 91% | Mon 31/10/22 | Mon 09/08/27 | 1246 days? | Mon 31/10/22 | Mon 09/08/27 | 0 days | 0 days | 154 days? | N/A |  |  | Yes
3 | 1.10.1 |  |  | MCAG (Migration) |  | Regulatory Governance | 88% | Mon 01/04/24 | Fri 27/02/26 | 500 days | Mon 01/04/24 | Wed 01/01/25 | 0 days | 302 days | 327 days | N/A |  | 5.28 | Yes
4 | 1.10.1.1 |  |  | MCAG (Migration) |  | Incentive Mods Created | 100% | Mon 01/04/24 | Fri 30/08/24 | 110 days | Mon 01/04/24 | Fri 30/08/24 | 0 days | 0 days | 25 days | SRO Migration |  | 5.28 | Yes
4 | 1.10.1.2 |  |  | MCAG (Migration) |  | BSC Panel Ruling | 100% | Thu 12/06/25 | Thu 12/06/25 | 0 days | Thu 12/06/25 | Thu 12/06/25 | 1 day | 0 days | -88 days | Code Bodies |  | 6.27 | Yes
4 | 1.10.1.3 |  |  | MCAG (Migration) |  | Ofgem Incentives Approval | 81% | Fri 13/06/25 | Fri 27/02/26 | 186 days | Fri 13/06/25 | Fri 27/02/26 | 0 days | 0 days | 186 days | Code Bodies |  | 6.42 | Yes |  | 27/01/26 - modifications still with Ofgem for consideration, therefore finish date has been ammended.
4 | 1.10.1.4 |  |  | MCAG (Migration) |  | Incentives Implementation | 0% | Fri 27/02/26 | Fri 27/02/26 | 0 days | Fri 23/01/26 | Fri 27/02/26 | 26 days | 0 days | 0 days | Code Bodies |  | 6.42 | Yes |  | 27/01/26 - modifications still with Ofgem for consideration, therefore finish date has been ammended.
3 | 1.10.2 |  |  | MCAG (Migration) |  | Migration Framework Agreed and Implemented | 100% | Thu 01/02/24 | Tue 29/04/25 | 324 days? | Thu 01/02/24 | Thu 23/01/25 | 0 days | 68 days | 110 days? | N/A |  | 5.28 | Yes
4 | 1.10.2.1 |  |  | MCAG (Migration) |  | Consultation 1 - Schedule | 100% | Thu 01/02/24 | Wed 08/05/24 | 70 days | Thu 01/02/24 | Wed 08/05/24 | 0 days | 0 days | 0 days | N/A |  | 5.28 | Yes
5 | 1.10.2.1.1 |  |  | MCAG (Migration) |  | Prepare Artefacts for Consultation | 100% | Thu 01/02/24 | Mon 18/03/24 | 33 days | Thu 01/02/24 | Mon 18/03/24 | 0 days | 0 days | 0 days | SI Migration |  | 5.28 | Yes
5 | 1.10.2.1.2 |  |  | MCAG (Migration) |  | Industry Consultation | 100% | Mon 18/03/24 | Mon 08/04/24 | 16 days | Mon 18/03/24 | Mon 08/04/24 | 0 days | 0 days | 0 days | SI Migration |  | 5.28 | Yes
5 | 1.10.2.1.3 |  |  | MCAG (Migration) |  | Triage and Action Comments | 100% | Mon 08/04/24 | Fri 19/04/24 | 10 days | Mon 08/04/24 | Fri 19/04/24 | 0 days | 0 days | 0 days | SI Migration |  | 5.28 | Yes
5 | 1.10.2.1.4 |  |  | MCAG (Migration) |  | Industry Assurance Review | 100% | Fri 19/04/24 | Fri 26/04/24 | 6 days | Fri 19/04/24 | Fri 26/04/24 | 0 days | 0 days | 0 days | SI Migration |  | 5.28 | Yes
5 | 1.10.2.1.5 |  |  | MCAG (Migration) |  | MWG Recommendation | 100% | Fri 26/04/24 | Fri 26/04/24 | 1 day | Fri 26/04/24 | Fri 26/04/24 | 0 days | 0 days | 0 days | SI Migration |  | 5.28 | Yes
5 | 1.10.2.1.6 |  |  | MCAG (Migration) |  | MCAG Interim Approval Artefacts | 100% | Wed 08/05/24 | Wed 08/05/24 | 1 day | Wed 08/05/24 | Wed 08/05/24 | 0 days | 0 days | 0 days | SI Migration |  | 5.28 | Yes
4 | 1.10.2.2 |  |  | MCAG (Migration) |  | Consultation 2 - Control | 100% | Mon 08/04/24 | Thu 25/07/24 | 79 days | Mon 08/04/24 | Thu 25/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.28 | Yes
5 | 1.10.2.2.1 |  |  | MCAG (Migration) |  | Prepare Artefacts for Consultation | 100% | Mon 08/04/24 | Thu 13/06/24 | 49 days | Mon 08/04/24 | Thu 13/06/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
5 | 1.10.2.2.2 |  |  | MCAG (Migration) |  | Industry Consultation | 100% | Fri 14/06/24 | Fri 28/06/24 | 11 days | Fri 14/06/24 | Fri 28/06/24 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.10.2.2.3 |  |  | MCAG (Migration) |  | Triage and Action Comments | 100% | Mon 01/07/24 | Thu 11/07/24 | 9 days | Mon 01/07/24 | Thu 11/07/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
5 | 1.10.2.2.4 |  |  | MCAG (Migration) |  | Industry Assurance Review | 100% | Fri 12/07/24 | Thu 18/07/24 | 5 days | Fri 12/07/24 | Thu 18/07/24 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.10.2.2.5 |  |  | MCAG (Migration) |  | MWG Recommendation | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1 day | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.10.2.2.6 | T3 | T3-MI-0037 | MCAG (Migration) |  | Consultation 2 - Control - MCAG Approval of Interim Artefacts | 100% | Thu 25/07/24 | Thu 25/07/24 | 0 days | Thu 25/07/24 | Thu 25/07/24 | 1 day | 0 days | 0 days | PP |  | 5.3 | Yes
4 | 1.10.2.3 |  |  | MCAG (Migration) |  | Consultation 3 - Parameters | 100% | Mon 18/11/24 | Tue 25/02/25 | 71 days | Mon 18/11/24 | Tue 25/02/25 | 0 days | -1 day | -5 days | N/A |  | 6.14 | Yes
5 | 1.10.2.3.1 |  |  | MCAG (Migration) |  | Prepare Artefacts for Consultation | 100% | Mon 18/11/24 | Thu 19/12/24 | 24 days | Mon 18/11/24 | Thu 19/12/24 | 0 days | 0 days | -12 days | SRO Migration |  | 6.14 | Yes
5 | 1.10.2.3.2 |  |  | MCAG (Migration) |  | Industry Consultation | 100% | Fri 20/12/24 | Fri 17/01/25 | 21 days | Fri 20/12/24 | Fri 17/01/25 | 0 days | 0 days | 11 days | PP |  | 6.14 | Yes
5 | 1.10.2.3.3 |  |  | MCAG (Migration) |  | Triage Response | 100% | Mon 20/01/25 | Fri 31/01/25 | 10 days | Mon 20/01/25 | Fri 31/01/25 | 0 days | 0 days | 0 days | SRO Migration |  | 6.14 | Yes
5 | 1.10.2.3.4 |  |  | MCAG (Migration) |  | MWG paper day | 100% | Thu 06/02/25 | Thu 06/02/25 | 0 days | Thu 06/02/25 | Thu 06/02/25 | 0 days | -1 day | 0 days | SRO Migration |  | 6.18 | Yes
5 | 1.10.2.3.5 |  |  | MCAG (Migration) |  | MWG Recommendation | 100% | Thu 13/02/25 | Thu 13/02/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | -5 days | -6 days | 0 days | PP |  | 6.14 | Yes
5 | 1.10.2.3.6 |  |  | MCAG (Migration) |  | MCAG Paper Day | 100% | Tue 18/02/25 | Tue 18/02/25 | 0 days | Tue 25/02/25 | Tue 25/02/25 | -4 days | -5 days | 0 days | SRO Migration |  | 6.14 | Yes
5 | 1.10.2.3.7 | T3 | T3-MI-0017 | MCAG (Migration) |  | MCAG Approval of Consultation 3 | 100% | Tue 25/02/25 | Tue 25/02/25 | 0 days | Tue 25/02/25 | Tue 25/02/25 | 0 days | -1 day | 0 days | PP |  | 6.17 | Yes
4 | 1.10.2.4 |  |  | MCAG (Migration) |  | Consultation 4 | 100% | Mon 20/01/25 | Tue 29/04/25 | 72 days? | Tue 07/01/25 | Wed 07/05/25 | 9 days | -6 days | 72 days? | SI Migration |  | 6.17 | Yes
5 | 1.10.2.4.1 |  |  | MCAG (Migration) |  | Agree Consultation 4 Plan | 100% | Mon 20/01/25 | Fri 07/02/25 | 15 days | Mon 20/01/25 | Fri 07/02/25 | 0 days | 0 days | 15 days | SI Migration |  | 6.17 | Yes
5 | 1.10.2.4.2 |  |  | MCAG (Migration) |  | Book MWG | 100% | Fri 07/02/25 | Fri 07/02/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.2.4.3 |  |  | MCAG (Migration) |  | Prepare Consultation 4 content | 100% | Mon 10/02/25 | Thu 20/02/25 | 9 days | Mon 10/02/25 | Thu 20/02/25 | 0 days | 0 days | 9 days | SI Migration |  | 6.18 | Yes
5 | 1.10.2.4.4 |  |  | MCAG (Migration) |  | MWG paper day | 100% | Thu 20/02/25 | Thu 20/02/25 | 0 days | Thu 20/02/25 | Thu 20/02/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.2.4.5 |  |  | MCAG (Migration) |  | MWG recommend Consultation 4 content go for industry consultation | 100% | Tue 04/03/25 | Tue 04/03/25 | 0 days | Thu 27/02/25 | Thu 27/02/25 | 4 days | 3 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.2.4.6 |  |  | MCAG (Migration) |  | Industry Consultation | 100% | Mon 03/03/25 | Fri 14/03/25 | 10 days? | Wed 12/03/25 | Tue 25/03/25 | -7 days | -7 days | 10 days? | PP |  | 6.17 | Yes
5 | 1.10.2.4.7 |  |  | MCAG (Migration) |  | Comment responses by PPs | 100% | Mon 17/03/25 | Fri 28/03/25 | 10 days? | Wed 26/03/25 | Tue 08/04/25 | -7 days | -7 days | 10 days? | SI Migration |  | 6.17 | Yes
5 | 1.10.2.4.8 |  |  | MCAG (Migration) |  | Respond to comments and issue artefacts | 100% | Mon 31/03/25 | Fri 11/04/25 | 10 days? | Mon 31/03/25 | Fri 11/04/25 | 0 days | 0 days | 10 days? | SI Migration |  | 6.18 | Yes
5 | 1.10.2.4.9 |  |  | MCAG (Migration) |  | Assurance meeting | 100% | Tue 22/04/25 | Tue 22/04/25 | 0 days | Wed 09/04/25 | Tue 22/04/25 | 10 days | 0 days | 0 days | SI Migration |  | 6.17 | Yes
5 | 1.10.2.4.10 |  |  | MCAG (Migration) |  | MCAG paper day | 100% | Tue 22/04/25 | Tue 22/04/25 | 0 days | Tue 22/04/25 | Tue 22/04/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.2.4.11 | T3 | T3-MI-0041 | MCAG (Migration) |  | MCAG Approval of Consultation 4 | 100% | Tue 29/04/25 | Tue 29/04/25 | 0 days | Tue 29/04/25 | Tue 29/04/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.17 | Yes
4 | 1.10.2.5 | T2 | T2-MI-7000 | MCAG (Migration) |  | Framework Baselined at MCAG | 100% | Tue 29/04/25 | Tue 29/04/25 | 0 days | Tue 29/04/25 | Tue 29/04/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.17 | Yes
3 | 1.10.3 |  |  | MCAG (Migration) |  | Migration Schedule Agreed and Maintained | 100% | Mon 01/07/24 | Fri 20/12/24 | 125 days? | Mon 31/10/22 | Fri 20/12/24 | 435 days | 0 days | -82 days? | SI Migration |  | 6.17 | Yes
4 | 1.10.3.1 | T3 |  | MCAG (Migration) |  | Schedule Production | 100% | Mon 01/07/24 | Fri 20/12/24 | 125 days? | Mon 01/07/24 | Fri 20/12/24 | 0 days | 0 days | 125 days? | SI Migration |  | 6.14 | Yes
4 | 1.10.3.2 | T3 | T3-MI-0042 | MCAG (Migration) |  | Schedule Production Complete | 100% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1 day | 0 days | 0 days | SI Migration |  | 6.14 | Yes
3 | 1.10.4 |  |  | MCAG (Migration) |  | V1.0 of Migration Schedule Baseline | 100% | Tue 01/04/25 | Tue 22/07/25 | 81 days | Tue 01/04/25 | Tue 22/07/25 | 0 days | 0 days | 81 days | SI Migration |  | 6.18 | Yes
4 | 1.10.4.1 |  |  | MCAG (Migration) |  | Confirm Supplier Migration start dates, MPID groups (SIT & NonSIT) | 100% | Tue 01/04/25 | Tue 01/04/25 | 0 days | Tue 01/04/25 | Tue 01/04/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.18 | Yes
4 | 1.10.4.2 | T2 | T2-MI-7500 | MCAG (Migration) |  | V1.0 of Migration Schedule Baseline Approved at MCAG | 100% | Tue 22/07/25 | Tue 22/07/25 | 0 days | Tue 22/07/25 | Tue 22/07/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.17 | Yes
3 | 1.10.5 | T2 |  | MCAG (Migration) |  | Supplier Submission Support | 100% | Fri 25/04/25 | Wed 18/06/25 | 38 days? | Fri 25/04/25 | Wed 04/06/25 | 0 days | 9 days | 38 days? | SI Migration |  | 6.17 | Yes
4 | 1.10.5.1 |  |  | MCAG (Migration) |  | Support guides issued | 100% | Fri 25/04/25 | Fri 25/04/25 | 1 day? | Fri 25/04/25 | Fri 25/04/25 | 0 days | 0 days | 1 day? | SI Migration |  | 6.18 | Yes
4 | 1.10.5.2 |  |  | MCAG (Migration) |  | Envelope webinar | 100% | Fri 02/05/25 | Fri 02/05/25 | 0 days | Fri 02/05/25 | Fri 02/05/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
4 | 1.10.5.3 |  |  | MCAG (Migration) |  | De-minimus webinar | 100% | Fri 02/05/25 | Fri 02/05/25 | 0 days | Fri 02/05/25 | Fri 02/05/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
4 | 1.10.5.4 |  |  | MCAG (Migration) |  | Drop-in session 1 | 100% | Wed 14/05/25 | Wed 14/05/25 | 0 days | Wed 14/05/25 | Wed 14/05/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
4 | 1.10.5.5 |  |  | MCAG (Migration) |  | Drop-in session 2 | 100% | Wed 28/05/25 | Wed 28/05/25 | 0 days | Wed 28/05/25 | Wed 28/05/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
4 | 1.10.5.6 |  |  | MCAG (Migration) |  | Drop-in session 3 | 100% | Wed 11/06/25 | Wed 11/06/25 | 0 days | Wed 11/06/25 | Wed 11/06/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.26 | Yes
4 | 1.10.5.7 |  |  | MCAG (Migration) |  | Drop-in session 4 | 100% | Wed 18/06/25 | Wed 18/06/25 | 0 days | Wed 18/06/25 | Wed 18/06/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.26 | Yes
3 | 1.10.6 |  |  | MCAG (Migration) |  | MCC Stood up | 100% | Mon 18/11/24 | Fri 21/11/25 | 265 days? | Mon 18/11/24 | Fri 21/11/25 | 0 days | 0 days | 265 days? | SI Migration |  | 6.17 | Yes
4 | 1.10.6.1 |  |  | MCAG (Migration) |  | Migration Planning Management Tool Delivery | 100% | Mon 18/11/24 | Fri 21/11/25 | 265 days | Mon 18/11/24 | Fri 21/11/25 | 0 days | 0 days | 265 days | SI Migration |  | 6.17 | Yes
4 | 1.10.6.2 |  |  | MCAG (Migration) |  | MCC Operational | 100% | Wed 23/04/25 | Fri 05/09/25 | 98 days | Fri 18/04/25 | Fri 29/08/25 | 3 days | 5 days | 98 days | SI Migration |  | 6.17 | Yes
5 | 1.10.6.2.1 |  |  | MCAG (Migration) |  | MCC Dress Rehersal 1 - Initialise Schedule (Weekly) Drop 1, 2 | 100% | Wed 23/04/25 | Tue 22/07/25 | 65 days | Fri 18/04/25 | Tue 15/07/25 | 3 days | 5 days | 65 days | SI Migration |  | 6.17 | Yes
6 | 1.10.6.2.1.1 |  |  | MCAG (Migration) |  | Issue Dress Rehearsal support information to all Suppliers (SIT & Non-SIT) | 100% | Wed 23/04/25 | Wed 23/04/25 | 0 days | Wed 23/04/25 | Wed 23/04/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.1.2 |  |  | MCAG (Migration) |  | Kestrel Webinar 1 | 100% | Wed 23/04/25 | Wed 23/04/25 | 0 days | Wed 23/04/25 | Wed 23/04/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.1.3 |  |  | MCAG (Migration) |  | Onboard and connectivity testing - Dress Rehearsal with Suppliers (All SIT and Wave 1 mandatory) | 100% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.1.4 |  |  | MCAG (Migration) |  | Test Scripts shared with Participants | 100% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.26 | Yes
6 | 1.10.6.2.1.5 |  |  | MCAG (Migration) |  | Dress rehearsal 1 start | 100% | Mon 09/06/25 | Mon 09/06/25 | 0 days | Mon 09/06/25 | Mon 09/06/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.26 | Yes
6 | 1.10.6.2.1.6 |  | T3-MI-0043 | MCAG (Migration) |  | Supplier Schedule Submission #2 complete | 100% | Fri 20/06/25 | Fri 20/06/25 | 1 day | Fri 20/06/25 | Fri 20/06/25 | 0 days | 0 days | 1 day | SI Migration |  | 6.26 | Yes
6 | 1.10.6.2.1.7 |  |  | MCAG (Migration) |  | Consolidate baseline schedule | 100% | Mon 23/06/25 | Fri 11/07/25 | 15 days | Mon 23/06/25 | Fri 11/07/25 | 0 days | 0 days | 15 days | SI Migration |  | 6.26 | Yes
6 | 1.10.6.2.1.8 |  |  | MCAG (Migration) |  | Consolidated baseline schedule published to industry | 100% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 11/07/25 | Fri 11/07/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.26 | Yes
6 | 1.10.6.2.1.9 |  |  | MCAG (Migration) |  | Baselined Schedule available for download | 100% | Mon 14/07/25 | Mon 14/07/25 | 1 day | Mon 14/07/25 | Mon 14/07/25 | 0 days | 0 days | 1 day | SI Migration |  | 6.26 | Yes
6 | 1.10.6.2.1.10 |  |  | MCAG (Migration) |  | Test execution report (weekly) | 100% | Tue 15/07/25 | Tue 15/07/25 | 0 days | Tue 15/07/25 | Tue 15/07/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.1.11 |  |  | MCAG (Migration) |  | Dress rehearsal completion report | 100% | Tue 15/07/25 | Tue 15/07/25 | 0 days | Tue 15/07/25 | Tue 15/07/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.1.12 | T3 | T3-MI-0044 | MCAG (Migration) |  | MCC Dress Rehersal 1 - complete | 100% | Tue 15/07/25 | Tue 15/07/25 | 0 days | Tue 15/07/25 | Tue 15/07/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.17 | Yes
6 | 1.10.6.2.1.13 |  |  | MCAG (Migration) |  | MCAG approval of Baseline Migration schedule | 100% | Tue 22/07/25 | Tue 22/07/25 | 0 days | Tue 22/07/25 | Tue 22/07/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.26 | Yes
5 | 1.10.6.2.2 |  |  | MCAG (Migration) |  | MCC Dress Rehersal 2 - complete | 100% | Mon 14/07/25 | Fri 05/09/25 | 40 days | Mon 14/07/25 | Fri 29/08/25 | 0 days | 5 days | 40 days | SI Migration |  | 6.17 | Yes
6 | 1.10.6.2.2.1 |  |  | MCAG (Migration) |  | Issue Dress Rehearsal support information to Participants | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.2.2 |  |  | MCAG (Migration) |  | Kestrel Webinar 1 | 100% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 14/07/25 | Mon 14/07/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.6.2.2.3 |  |  | MCAG (Migration) |  | Kestrel Webinar 2 | 100% | Wed 06/08/25 | Wed 06/08/25 | 0 days | Wed 06/08/25 | Wed 06/08/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.29 | Yes
6 | 1.10.6.2.2.4 |  |  | MCAG (Migration) |  | Onboard and connectivity testing - Dress Rehearsal with Suppliers (remaining suppliers and non-supplier PPs) | 100% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Mon 11/08/25 | Mon 11/08/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.29 | Yes
6 | 1.10.6.2.2.5 |  |  | MCAG (Migration) |  | MCC Dress Rehersal 2 | 100% | Mon 11/08/25 | Fri 05/09/25 | 20 days | Mon 11/08/25 | Mon 11/08/25 | 0 days | 19 days | 20 days | SI Migration |  | 6.29 | Yes
7 | 1.10.6.2.2.5.1 |  |  | MCAG (Migration) |  | MCC Dress Rehersal 2 start | 100% | Mon 11/08/25 | Mon 11/08/25 | 1 day | Mon 11/08/25 | Mon 11/08/25 | 0 days | 0 days | 1 day | SI Migration |  | 6.29 | Yes
7 | 1.10.6.2.2.5.2 |  |  | MCAG (Migration) |  | Test execution report (weekly) | 100% | Mon 11/08/25 | Fri 05/09/25 | 20 days | Fri 29/08/25 | Fri 29/08/25 | -14 days | 5 days | 20 days | SI Migration |  | 6.33 | Yes
7 | 1.10.6.2.2.5.3 |  |  | MCAG (Migration) |  | Dress rehearsal completion report available | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 6 days | 5 days | 0 days | SI Migration |  | 6.33 | Yes
7 | 1.10.6.2.2.5.4 |  |  | MCAG (Migration) |  | PPs return test scripts | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 6 days | 5 days | 0 days | PP |  | 6.33 | Yes
7 | 1.10.6.2.2.5.5 | T3 | T3-MI-0045 | MCAG (Migration) |  | MCC Dress Rehearsal 2 - complete | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 6 days | 5 days | 0 days | SI Migration |  | 6.32 | Yes
4 | 1.10.6.3 | T2 | T2-MI-0500 | MCAG (Migration) |  | MCC Operational Complete | 100% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 6 days | 5 days | 0 days | SI Migration |  | 6.32 | Yes
3 | 1.10.7 |  |  | MCAG (Migration) |  | M11 Readiness Checkpoint | 100% | Fri 29/08/25 | Mon 20/10/25 | 36 days | Mon 28/07/25 | Thu 28/08/25 | 24 days | 36 days | 36 days | SI Migration |  | 6.31 | Yes
4 | 1.10.7.1 |  |  | MCAG (Migration) |  | Supplier Readiness Assessments for Sprint 0 Day 1 | 100% | Fri 29/08/25 | Thu 25/09/25 | 20 days | Fri 29/08/25 | Thu 25/09/25 | 0 days | 0 days | 20 days | SI Migration |  | 6.34 | Yes
4 | 1.10.7.2 |  |  | MCAG (Migration) |  | MCAG Approve Sprint 0 Day 1 Baseline Schedule | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.34 | Yes
4 | 1.10.7.3 |  |  | MCAG (Migration) |  | Legacy Settlement run stability assessment | 100% | Fri 26/09/25 | Fri 17/10/25 | 16 days | Fri 26/09/25 | Fri 17/10/25 | 0 days | 0 days | 16 days | SI Migration |  | 6.31 | Yes
5 | 1.10.7.3.1 |  |  | MCAG (Migration) |  | Legacy Settlement run stability assessment | 100% | Fri 26/09/25 | Fri 17/10/25 | 16 days | Fri 26/09/25 | Fri 17/10/25 | 0 days | 0 days | 16 days | SI Migration |  | 6.31 | Yes
5 | 1.10.7.3.2 |  |  | MCAG (Migration) |  | Checkpoint 1 | 100% | Fri 03/10/25 | Fri 03/10/25 | 0 days | Fri 03/10/25 | Fri 03/10/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.32 | Yes
5 | 1.10.7.3.3 |  |  | MCAG (Migration) |  | Checkpoint 2 | 100% | Fri 10/10/25 | Fri 10/10/25 | 0 days | Fri 10/10/25 | Fri 10/10/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.32 | Yes
5 | 1.10.7.3.4 |  |  | MCAG (Migration) |  | Checkpoint 3 | 100% | Fri 17/10/25 | Fri 17/10/25 | 0 days | Fri 17/10/25 | Fri 17/10/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.32 | Yes
3 | 1.10.8 |  |  | MCAG (Migration) |  | Migration Artefact Development and Publication | 91% | Mon 31/10/22 | Wed 28/10/26 | 1043 days | Mon 31/10/22 | Wed 03/09/25 | 0 days | 300 days | 408 days | N/A |  | 5 | Yes
4 | 1.10.8.1 |  |  | MCAG (Migration) |  | Migration Approach | 100% | Mon 31/10/22 | Wed 07/12/22 | 28 days | Mon 31/10/22 | Wed 07/12/22 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.8.1.1 |  |  |  |  | Option analysis (via MWG and PPIR) and recommendation | 100% | Mon 31/10/22 | Wed 30/11/22 | 23 days | Mon 31/10/22 | Wed 30/11/22 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.10.8.1.2 | T3 | T3-MI-0010 | PSG | MHHS-DEL770 | Migration Approach approved | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.10.8.2 |  |  |  |  | Migration Design | 100% | Mon 14/11/22 | Fri 31/03/23 | 100 days | Mon 14/11/22 | Fri 31/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.8.2.1 |  |  |  |  | Review and update existing design artefacts and socialise with participants ahead of MDSG | 100% | Mon 14/11/22 | Fri 25/11/22 | 10 days | Mon 14/11/22 | Fri 25/11/22 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.2 |  |  |  |  | Develop design artefacts and supporting technical documents in line with MDSG | 100% | Wed 30/11/22 | Fri 10/02/23 | 53 days | Wed 30/11/22 | Fri 10/02/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.3 | T3 | T3-MI-0011 | DAG |  | Migration design artefacts issued for consultation | 100% | Mon 13/02/23 | Mon 13/02/23 | 0 days | Mon 13/02/23 | Mon 13/02/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.4 |  |  |  |  | Industry consultation | 100% | Tue 14/02/23 | Mon 20/02/23 | 5 days | Tue 14/02/23 | Mon 20/02/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.10.8.2.5 |  |  |  |  | Review consultation feedback, address comments and update artefacts | 100% | Tue 21/02/23 | Mon 27/02/23 | 5 days | Tue 21/02/23 | Mon 27/02/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.6 |  |  |  |  | Internal artefact review and comms preparation | 100% | Tue 28/02/23 | Thu 02/03/23 | 3 days | Tue 28/02/23 | Thu 02/03/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.7 | T3 | T3-MI-0013 | DAG |  | Updated Migration Design artefacts issued to PPs for assurance review | 100% | Fri 03/03/23 | Fri 03/03/23 | 0 days | Fri 03/03/23 | Fri 03/03/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.8 |  |  |  |  | Final Migration Design artefacts walkthrough with PPs | 100% | Wed 22/03/23 | Wed 22/03/23 | 0 days | Wed 22/03/23 | Wed 22/03/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.2.9 | T2 | T2-MI-0050 | DAG |  | Migration Design approved | 100% | Fri 31/03/23 | Fri 31/03/23 | 0 days | Fri 31/03/23 | Fri 31/03/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.10.8.3 |  |  |  |  | Transition Design | 100% | Wed 01/03/23 | Wed 15/11/23 | 186 days | Wed 01/03/23 | Wed 15/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.8.3.1 |  |  |  |  | Tranche 1 | 100% | Wed 01/03/23 | Wed 17/05/23 | 56 days | Wed 01/03/23 | Wed 17/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.10.8.3.1.1 |  |  |  |  | Develop design artefacts and supporting technical details with participants | 100% | Wed 01/03/23 | Tue 09/05/23 | 50 days | Wed 01/03/23 | Tue 09/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.10.8.3.1.2 |  |  |  |  | Issue Material for DAG approval | 100% | Wed 10/05/23 | Wed 10/05/23 | 1 day | Wed 10/05/23 | Wed 10/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.10.8.3.1.3 | T2 | T2-DB-0150 | DAG |  | Tranche 1 Transition Design approved | 100% | Wed 17/05/23 | Wed 17/05/23 | 0 days | Wed 17/05/23 | Wed 17/05/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.10.8.3.2 |  |  |  |  | Tranche 2 | 100% | Thu 18/05/23 | Wed 15/11/23 | 130 days | Thu 18/05/23 | Wed 15/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.10.8.3.2.1 |  |  |  |  | Develop Initial design artefacts and supporting technical details | 100% | Thu 18/05/23 | Thu 31/08/23 | 76 days | Thu 18/05/23 | Thu 31/08/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.2 |  |  |  |  | Communicate Initial Design Artefacts with Industry (MTDSG) | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.3 |  |  |  |  | Host MTDSG | 100% | Mon 11/09/23 | Mon 11/09/23 | 1 day | Mon 11/09/23 | Mon 11/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.4 |  |  |  |  | Process MTDSG Feedback and Amend Design Artefacts | 100% | Tue 12/09/23 | Fri 15/09/23 | 4 days | Tue 12/09/23 | Fri 15/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.5 |  |  |  |  | Communicate Amended Design Artefacts with Industry | 100% | Fri 15/09/23 | Fri 15/09/23 | 1 day | Fri 15/09/23 | Fri 15/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.6 |  |  |  |  | Host MTDSG | 100% | Tue 26/09/23 | Tue 26/09/23 | 1 day | Tue 26/09/23 | Tue 26/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.7 |  |  |  |  | Make Final Amendments to Design Artefact | 100% | Wed 27/09/23 | Tue 03/10/23 | 5 days | Wed 27/09/23 | Tue 03/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.8 |  |  |  |  | Request DAG Consultation | 100% | Wed 04/10/23 | Wed 04/10/23 | 1 day | Wed 04/10/23 | Wed 04/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.9 |  |  |  |  | Consultation Period | 100% | Wed 04/10/23 | Wed 18/10/23 | 11 days | Wed 04/10/23 | Wed 18/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.10 |  |  |  |  | Action Consultation Comments | 100% | Thu 19/10/23 | Wed 25/10/23 | 5 days | Thu 19/10/23 | Wed 25/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.11 |  |  |  |  | Post Consultation Industry Assurance | 100% | Thu 26/10/23 | Wed 01/11/23 | 5 days | Thu 26/10/23 | Wed 01/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.12 |  |  |  |  | Request DAG Approval | 100% | Wed 01/11/23 | Wed 01/11/23 | 1 day | Wed 01/11/23 | Wed 01/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.13 |  |  |  |  | DAG Transition Design Approved | 100% | Wed 08/11/23 | Wed 08/11/23 | 1 day | Wed 08/11/23 | Wed 08/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.14 |  |  |  |  | Update Transition Design Admin | 100% | Thu 09/11/23 | Wed 15/11/23 | 5 days | Thu 09/11/23 | Wed 15/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.10.8.3.2.15 | T2 | T2-DB-0250 | DAG |  | Tranche 2 Transition Design Baselined | 100% | Wed 15/11/23 | Wed 15/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 | 1 day | 0 days | 0 days | SRO |  | 5.12 | Yes
4 | 1.10.8.4 |  |  |  |  | Data Assessment Report | 100% | Tue 06/12/22 | Tue 28/02/23 | 61 days | Tue 06/12/22 | Tue 28/02/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.8.4.1 |  |  |  |  | Develop document with MWG | 100% | Tue 06/12/22 | Fri 10/02/23 | 49 days | Tue 06/12/22 | Fri 10/02/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.4.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Wed 18/01/23 | Tue 21/02/23 | 25 days | Wed 18/01/23 | Tue 21/02/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.10.8.4.3 | T3 | T3-MI-0012 | MCAG |  | Data Assessment Report approved | 100% | Tue 28/02/23 | Tue 28/02/23 | 0 days | Tue 28/02/23 | Tue 28/02/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.10.8.5 |  |  |  |  | Migration, Cutover & Data Strategy (incl. Migration Entry Criteria) | 100% | Thu 08/12/22 | Fri 28/04/23 | 102 days | Thu 08/12/22 | Fri 28/04/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.8.5.1 |  |  |  |  | Develop document with MWG | 100% | Thu 08/12/22 | Fri 10/03/23 | 67 days | Thu 08/12/22 | Fri 10/03/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.5.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Wed 15/03/23 | Fri 21/04/23 | 28 days | Wed 15/03/23 | Fri 21/04/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.10.8.5.3 | T3 | T3-MI-0014 | MCAG |  | Migration, Cutover & Data Strategy approved | 100% | Fri 28/04/23 | Fri 28/04/23 | 0 days | Fri 28/04/23 | Fri 28/04/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.10.8.6 |  |  |  |  | Data Cleanse Plan | 100% | Thu 02/03/23 | Wed 24/09/25 | 670 days | Thu 02/03/23 | Wed 03/09/25 | 0 days | 15 days | 123 days | N/A |  | 5 | Yes
5 | 1.10.8.6.1 |  |  |  |  | Develop document with MWG | 100% | Thu 02/03/23 | Wed 10/05/23 | 50 days | Thu 02/03/23 | Wed 10/05/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.6.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Thu 11/05/23 | Wed 07/06/23 | 20 days | Thu 11/05/23 | Wed 07/06/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.10.8.6.3 | T3 | T3-MI-0020 | MCAG |  | Data Cleanse Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.6.4 |  |  |  |  | Monitor Programme Participant adherence to Data Cleanse Plan | 100% | Thu 15/06/23 | Fri 28/03/25 | 467 days | Thu 15/06/23 | Fri 28/03/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.8.6.5 |  |  |  |  | MTDs | 100% | Fri 16/08/24 | Mon 21/07/25 | 241 days | Fri 16/08/24 | Fri 31/01/25 | 1 day | 121 days | 150 days | N/A |  | 5.4 | Yes
6 | 1.10.8.6.5.1 |  |  |  |  | ESME ID | 100% | Fri 16/08/24 | Fri 16/05/25 | 195 days | Fri 16/08/24 | Fri 20/12/24 | 1 day | 105 days | 105 days | N/A |  | 5.4 | Yes
7 | 1.10.8.6.5.1.1 | T3 | T3-MI-0024 | MCAG (Transition) |  | DCC to extract ESME ID and share with LDSO | 100% | Fri 16/08/24 | Fri 16/08/24 | 0 days | Fri 16/08/24 | Fri 16/08/24 | 1 day | 0 days | 0 days | DCC/SI |  | 5.5 | Yes
7 | 1.10.8.6.5.1.2 | T3 | T3-MI-0025 | MCAG (Transition) |  | LDSO ‘full refresh’ between their Registration Service and the EES (ESME ID) | 100% | Mon 21/10/24 | Mon 11/11/24 | 16 days | Mon 21/10/24 | Mon 11/11/24 | 0 days | 0 days | 16 days | LDSO/EES |  | 5.5 | Yes
7 | 1.10.8.6.5.1.3 |  |  |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 100% | Fri 20/12/24 | Fri 20/12/24 | 1 day | Fri 20/12/24 | Fri 20/12/24 | 0 days | 0 days | 0 days | Supplier |  | 5.4 | Yes
7 | 1.10.8.6.5.1.4 |  |  |  |  | Suppliers complete Work Off plans | 100% | Mon 23/12/24 | Fri 16/05/25 | 105 days | Mon 23/12/24 | Fri 16/05/25 | 0 days | 0 days | 105 days | Supplier |  | 6.19 | Yes
7 | 1.10.8.6.5.1.5 |  |  |  |  | ESME ID Complete | 100% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 16/05/25 | Fri 16/05/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.19 | Yes
6 | 1.10.8.6.5.2 |  |  |  |  | Meter Location and Number of Displayed Register Digits | 100% | Fri 13/09/24 | Mon 21/07/25 | 222 days | Fri 13/09/24 | Fri 31/01/25 | 0 days | 121 days | 131 days | N/A |  | 5.4 | Yes
7 | 1.10.8.6.5.2.1 |  |  |  |  | MEM to extract data and share with LDSO | 100% | Fri 13/09/24 | Fri 20/09/24 | 6 days | Fri 13/09/24 | Fri 20/09/24 | 0 days | 0 days | 5 days | MEM/SI |  | 5.4 | Yes
7 | 1.10.8.6.5.2.2 | T3 | T3-MI-0026 | MCAG (Transition) |  | LDSO ‘full refresh’ between their Registration Service and the EES (Meter Location and Number of Displayed Register Digits) | 100% | Mon 21/10/24 | Fri 15/11/24 | 16 days | Mon 28/10/24 | Mon 18/11/24 | -5 days | -1 day | 16 days | LDSO /EES |  | 5.5 | Yes
7 | 1.10.8.6.5.2.3 |  |  |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 100% | Fri 24/01/25 | Fri 24/01/25 | 1 day | Fri 31/01/25 | Fri 31/01/25 | -5 days | -5 days | 0 days | Supplier |  | 5.4 | Yes
7 | 1.10.8.6.5.2.4 |  |  |  |  | Suppliers complete Work Off plans | 100% | Wed 29/01/25 | Fri 18/07/25 | 123 days | Wed 29/01/25 | Fri 18/07/25 | 0 days | 0 days | 123 days | Supplier |  | 6.19 | Yes
7 | 1.10.8.6.5.2.5 |  |  |  |  | Meter Location and Number of Displayed Register Digits Complete | 100% | Mon 21/07/25 | Mon 21/07/25 | 1 day | Fri 18/07/25 | Fri 18/07/25 | 1 day | 1 day | 1 day | SI Transition |  | 6.19 | Yes
5 | 1.10.8.6.6 |  |  |  |  | Registration Data | 100% | Fri 06/09/24 | Wed 24/09/25 | 274 days | Fri 06/09/24 | Wed 03/09/25 | 0 days | 15 days | 127 days | N/A |  | 5.4 | Yes
6 | 1.10.8.6.6.1 |  |  |  |  | Connection Type | 100% | Fri 06/09/24 | Mon 11/11/24 | 47 days | Fri 06/09/24 | Mon 11/11/24 | 0 days | 0 days | 31 days | N/A |  | 5.4 | Yes
7 | 1.10.8.6.6.1.1 | T3 | T3-MI-0027 | MCAG (Transition) |  | Automated Population of Connection Type for Measurement Classes ‘B’, ‘D’, ‘F’ & ‘G’ | 100% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 04/10/24 | Fri 04/10/24 | 1 day | 0 days | 0 days | LDSO |  | 5.5 | Yes
7 | 1.10.8.6.6.1.2 | T3 | T3-MI-0028 | MCAG (Transition) |  | BAU Population of Connection Type for Site Specific LLFCs within Measurement Classes ‘C’ & ‘E’ | 100% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 04/10/24 | Fri 04/10/24 | 1 day | 0 days | 0 days | LDSO |  | 5.5 | Yes
7 | 1.10.8.6.6.1.3 | T3 | T3-MI-0029 | MCAG (Transition) |  | Automated Population of Connection Type for Smart Meters within Measurement Class ‘A’ | 100% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 04/10/24 | Fri 04/10/24 | 1 day | 0 days | 0 days | LDSO |  | 5.5 | Yes
7 | 1.10.8.6.6.1.4 |  |  |  |  | Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’ | 100% | Fri 06/09/24 | Fri 06/09/24 | 1 day | Fri 06/09/24 | Fri 06/09/24 | 0 days | 0 days | 0 days | Suppliers |  | 5.4 | Yes
7 | 1.10.8.6.6.1.5 | T3 | T3-MI-0030 | MCAG (Transition) |  | Automated Population of Null Connection Type | 100% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 04/10/24 | Fri 04/10/24 | 1 day | 0 days | 0 days | LDSO |  | 5.5 | Yes
7 | 1.10.8.6.6.1.6 |  |  |  |  | Full MPAN refresh to ESS | 100% | Mon 21/10/24 | Mon 11/11/24 | 16 days | Mon 21/10/24 | Mon 11/11/24 | 0 days | 0 days | 15 days | LDSO/EES |  | 5.4 | Yes
7 | 1.10.8.6.6.1.7 |  |  |  |  | Connection Type Complete | 100% | Mon 11/11/24 | Mon 11/11/24 | 0 days | Mon 11/11/24 | Mon 11/11/24 | 1 day | 0 days | 0 days | SI Transition |  | 5.4 | Yes
6 | 1.10.8.6.6.2 |  |  |  |  | Domestic Premises Indicator | 100% | Fri 05/09/25 | Wed 24/09/25 | 14 days | Fri 08/08/25 | Wed 03/09/25 | 20 days | 15 days | -3 days | N/A |  | 5.4 | Yes
7 | 1.10.8.6.6.2.1 |  |  | MCAG (Transition) |  | The DCC to extract Domestic Premises Indicator from the CSS and provide a file to each LDSO and EES. | 100% | Fri 05/09/25 | Mon 08/09/25 | 2 days | Fri 05/09/25 | Mon 08/09/25 | 0 days | 0 days | 1 day | DCC |  | 6.22 | Yes
7 | 1.10.8.6.6.2.2 |  |  | MCAG (Transition) |  | Each LDSO notifies the MHHS Programme SI of any exceptions which have occurred because of the data load and the reason for that exception | 100% | Wed 24/09/25 | Wed 24/09/25 | 1 day | Wed 24/09/25 | Wed 24/09/25 | 0 days | 0 days | 0 days | LDSO |  | 6.22 | Yes
7 | 1.10.8.6.6.2.3 |  |  | MCAG (Transition) |  | Domestic Premises Indicator Complete | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
4 | 1.10.8.7 |  |  |  |  | Connection Type and Meter Type Misalignments | 82% | Mon 03/03/25 | Wed 28/10/26 | 433 days | Mon 03/03/25 | Wed 28/10/26 | 0 days | 0 days | 433 days | SI Transition |  | 6.22 | Yes
5 | 1.10.8.7.1 |  |  |  |  | Traditional Meters installed on Current Transformers | 58% | Mon 03/03/25 | Wed 28/10/26 | 433 days | Mon 03/03/25 | Wed 28/10/26 | 0 days | 0 days | 433 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.1.1 |  |  | MCAG (Transition) |  | Suppliers investigate all MPANs with Traditional Meters installed on a Current Transformer Connection Type | 100% | Mon 03/03/25 | Fri 30/05/25 | 65 days | Mon 03/03/25 | Fri 30/05/25 | 0 days | 0 days | 65 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.1.2 |  |  | MCAG (Transition) |  | Suppliers to raise the relevant SDEP cases with LDSOs in pot 3 | 100% | Fri 30/05/25 | Fri 30/05/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.1.3 |  |  | MCAG (Transition) |  | Suppliers to have ensured that Meter Operators have sent the necessary D0312s for MPANs in pot 2 | 100% | Mon 02/06/25 | Mon 30/06/25 | 21 days | Mon 02/06/25 | Mon 30/06/25 | 0 days | 0 days | 21 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.1.4 |  |  | MCAG (Transition) |  | LDSOs will be required to have corrected all of these Connection Types in pot 3 | 100% | Mon 02/06/25 | Fri 25/07/25 | 40 days | Mon 02/06/25 | Fri 25/07/25 | 0 days | 0 days | 40 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.1.5 |  |  | MCAG (Transition) |  | Suppliers to have completed meter exchanges for those MPANs in pot 1 | 44% | Mon 02/06/25 | Wed 28/10/26 | 368 days | Mon 02/06/25 | Wed 28/10/26 | 0 days | 0 days | 368 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.1.6 |  |  | MCAG (Transition) |  | Traditional Meters installed on Current Transformers complete | 0% | Wed 28/10/26 | Wed 28/10/26 | 0 days | Wed 28/10/26 | Wed 28/10/26 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
5 | 1.10.8.7.2 |  |  |  |  | CHECK Meters | 100% | Mon 03/03/25 | Mon 02/06/25 | 66 days | Fri 30/05/25 | Mon 02/06/25 | -64 days | 0 days | 66 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.2.1 |  |  | MCAG (Transition) |  | Suppliers and their appointed Meter Operator investigate MPANs within their portfolio that have incorrectly populated meters with the Meter Type CHECK within MPRS. Meter Operators are required to send a D0312 to remove the CHECK meter from MPRS. | 100% | Mon 03/03/25 | Fri 30/05/25 | 65 days | Mon 03/03/25 | Fri 30/05/25 | 0 days | 0 days | 65 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.2.2 |  |  | MCAG (Transition) |  | Once CHECK meters are either removed from MPRS or the Meter Type is changed to a valid Meter Type, the LDSO should check that the Connection Type assigned to the MPAN is still valid. | 100% | Mon 03/03/25 | Fri 30/05/25 | 65 days | Mon 03/03/25 | Fri 30/05/25 | 0 days | 0 days | 65 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.2.3 |  |  | MCAG (Transition) |  | Suppliers confirm to the Programme that they have completed this activity | 100% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.2.4 |  |  | MCAG (Transition) |  | CHECK Meters complete | 100% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
5 | 1.10.8.7.3 |  |  |  |  | Smart Meter Types installed on CT Connection Types | 100% | Fri 21/03/25 | Fri 25/07/25 | 90 days | Fri 21/03/25 | Fri 25/07/25 | 1 day | 0 days | 90 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.3.1 |  |  | MCAG (Transition) |  | Programme shares data via email with LDSOs and Suppliers on the total number of misalignments to inform work they will have to complete | 100% | Fri 21/03/25 | Fri 21/03/25 | 0 days | Fri 21/03/25 | Fri 21/03/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.3.2 |  |  | MCAG (Transition) |  | LDSOs investigate Connection Type misalignments and correct where appropriate | 100% | Mon 24/03/25 | Fri 30/05/25 | 50 days | Mon 24/03/25 | Fri 30/05/25 | 0 days | 0 days | 50 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.3.3 |  |  | MCAG (Transition) |  | LDSOs raise SDEP queries with Suppliers where they believe there is an issue | 100% | Fri 30/05/25 | Fri 30/05/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.3.4 |  |  | MCAG (Transition) |  | Suppliers resolve all issues | 100% | Mon 02/06/25 | Fri 25/07/25 | 40 days | Mon 02/06/25 | Fri 25/07/25 | 0 days | 0 days | 40 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.3.5 |  |  | MCAG (Transition) |  | Smart Meter Types installed on CT Connection Types complete | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
5 | 1.10.8.7.4 |  |  |  |  | Linked Import / Export MPANs | 100% | Mon 03/03/25 | Fri 25/07/25 | 105 days | Mon 03/03/25 | Fri 25/07/25 | 0 days | 0 days | 105 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.4.1 |  |  | MCAG (Transition) |  | LDSOs review and correct linked Import / Export MPANs with Different Connection Types | 100% | Mon 03/03/25 | Fri 25/07/25 | 105 days | Mon 03/03/25 | Fri 25/07/25 | 0 days | 0 days | 105 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.4.2 |  |  | MCAG (Transition) |  | LDSOs, Import and Export Suppliers review and correct linked Import / Export MPANs with meters in the Advanced and Traditional or Smart Meter Groups | 100% | Mon 03/03/25 | Fri 25/07/25 | 105 days | Mon 03/03/25 | Fri 25/07/25 | 0 days | 0 days | 105 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.4.3 |  |  | MCAG (Transition) |  | Linked Import / Export MPANs complete | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
5 | 1.10.8.7.5 |  |  |  |  | Related MPANs | 100% | Mon 03/03/25 | Fri 25/07/25 | 105 days | Mon 03/03/25 | Fri 25/07/25 | 0 days | 0 days | 105 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.5.1 |  |  | MCAG (Transition) |  | LDSOs review and correct related MPANs with different Connection Types | 100% | Mon 03/03/25 | Fri 20/06/25 | 80 days | Mon 03/03/25 | Fri 20/06/25 | 0 days | 0 days | 80 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.5.2 |  |  | MCAG (Transition) |  | Suppliers unrelate any MPANs required | 100% | Mon 23/06/25 | Fri 25/07/25 | 25 days | Mon 23/06/25 | Fri 25/07/25 | 0 days | 0 days | 25 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.5.3 |  |  | MCAG (Transition) |  | Suppliers should investigate Related MPANs within different meter groups and verify that they are correct or request that their Meter Operators update the Meter Types where they are incorrect | 100% | Mon 03/03/25 | Fri 25/07/25 | 105 days | Mon 03/03/25 | Fri 25/07/25 | 0 days | 0 days | 105 days | SI Transition |  | 6.22 | Yes
6 | 1.10.8.7.5.4 |  |  | MCAG (Transition) |  | Related MPANs complete | 100% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 25/07/25 | Fri 25/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
4 | 1.10.8.8 |  |  |  |  | Export / Import MPANs | 100% | Fri 22/03/24 | Mon 22/09/25 | 392 days | Fri 22/03/24 | Fri 18/10/24 | 0 days | 241 days | 241 days | N/A |  | 5.4 | Yes
5 | 1.10.8.8.1 |  |  |  |  | Linking of Export / Import MPANS | 100% | Fri 22/03/24 | Fri 18/10/24 | 151 days | Fri 22/03/24 | Fri 18/10/24 | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes
6 | 1.10.8.8.1.1 |  |  |  |  | LDSO utilises BAU processing (DB05s) to populate each import/export association | 100% | Fri 22/03/24 | Fri 22/03/24 | 1 day | Fri 22/03/24 | Fri 22/03/24 | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes
6 | 1.10.8.8.1.2 |  |  |  |  | Each LDSO notifies the Registered Supplier of any exceptions | 100% | Fri 19/04/24 | Fri 19/04/24 | 1 day | Fri 19/04/24 | Fri 19/04/24 | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes
6 | 1.10.8.8.1.3 |  |  |  |  | Each Supplier completes investigation and resolution of exceptions | 100% | Fri 23/08/24 | Fri 23/08/24 | 1 day | Fri 23/08/24 | Fri 23/08/24 | 0 days | 0 days | 0 days | Supplier |  | 5.4 | Yes
6 | 1.10.8.8.1.4 | T3 | T3-MI-0031 | MCAG (Transition) |  | Each LDSO has linked al relevant import/export MPANS | 100% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1 day | 0 days | 0 days | LDSO |  | 5.5 | Yes
6 | 1.10.8.8.1.5 |  |  |  |  | Linking of Export / Import MPANS Complete | 100% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1 day | 0 days | 0 days | SI Transition |  | 5.4 | Yes
5 | 1.10.8.8.2 | T2 | T2-MI-0450 | MCAG (Transition) |  | Pre-migration data cleanse complete | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.33 | Yes
3 | 1.10.9 |  |  |  |  | Migration Period Planning | 98% | Mon 03/07/23 | Fri 31/07/26 | 805 days | Mon 03/07/23 | Tue 26/11/24 | 0 days | 438 days | -46 days | N/A |  | 5 | Yes
4 | 1.10.9.1 |  |  |  |  | Migration Implementation Plan (incl. Migration Exit Criteria) | 98% | Mon 03/07/23 | Fri 31/07/26 | 805 days | Mon 03/07/23 | Tue 26/11/24 | 0 days | 438 days | -46 days | N/A |  | 5 | Yes
5 | 1.10.9.1.1 |  |  |  |  | Migration Threshold Volumes | 100% | Mon 03/07/23 | Mon 20/11/23 | 101 days | Mon 03/07/23 | Mon 20/11/23 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
6 | 1.10.9.1.1.1 |  |  |  |  | Threshold volumes reviewed by MWG | 100% | Mon 03/07/23 | Thu 14/09/23 | 54 days | Mon 03/07/23 | Thu 14/09/23 | 0 days | 0 days | 0 days | SI Migration |  | 5.6 | Yes
6 | 1.10.9.1.1.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 15/09/23 | Mon 20/11/23 | 47 days | Fri 15/09/23 | Mon 20/11/23 | 0 days | 0 days | 3 days | PP |  | 5.9 | Yes
6 | 1.10.9.1.1.3 | T3 | T3-MI-0021 | SITAG |  | Threshold volumes approved at TMAG | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Mon 20/11/23 | Mon 20/11/23 | 1 day | 0 days | 0 days | SI Migration |  | 5.12 | Yes
5 | 1.10.9.1.2 |  |  |  |  | Define acceptance criteria for M15 | 100% | Mon 04/09/23 | Wed 20/12/23 | 78 days | Mon 04/09/23 | Wed 20/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.10.9.1.2.1 |  |  |  |  | Review acceptance criteria and reporting requirements with MWG | 100% | Mon 04/09/23 | Thu 09/11/23 | 49 days | Mon 04/09/23 | Thu 09/11/23 | 0 days | 0 days | 9 days | SI Migration |  | 5 | Yes
6 | 1.10.9.1.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 10/11/23 | Wed 20/12/23 | 29 days | Fri 10/11/23 | Wed 20/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.10.9.1.2.3 | T3 | T3-MI-0022 | SITAG |  | Acceptance criteria for M15 agreed at TMAG | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 1 day | 0 days | 0 days | SI Migration |  | 5.14 | Yes
5 | 1.10.9.1.3 |  |  |  |  | M10/M11 cut-over plan | 100% | Thu 21/12/23 | Tue 04/06/24 | 119 days | Thu 21/12/23 | Tue 04/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
6 | 1.10.9.1.3.1 |  |  |  |  | Draft Document | 100% | Thu 21/12/23 | Tue 16/04/24 | 84 days | Thu 21/12/23 | Tue 16/04/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.10.9.1.3.2 |  |  |  |  | Share Document with SRO | 100% | Wed 17/04/24 | Wed 17/04/24 | 1 day | Wed 17/04/24 | Wed 17/04/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.10.9.1.3.3 |  |  |  |  | Industry Consultation | 100% | Tue 23/04/24 | Tue 07/05/24 | 11 days | Tue 23/04/24 | Tue 07/05/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.10.9.1.3.4 |  |  |  |  | Assurance Meeting | 100% | Tue 21/05/24 | Tue 21/05/24 | 1 day | Tue 21/05/24 | Tue 21/05/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.10.9.1.3.5 | T3 | T3-MI-0023 | MCAG |  | MCAG Approval of M10/M11 Cut-over Plan | 100% | Tue 04/06/24 | Tue 04/06/24 | 0 days | Tue 04/06/24 | Tue 04/06/24 | 1 day | 0 days | 0 days | SI Transition |  | 5.26 | Yes
5 | 1.10.9.1.4 |  |  |  |  | M16 Methodology | 96% | Wed 31/07/24 | Fri 31/07/26 | 523 days | Wed 31/07/24 | Tue 26/11/24 | 0 days | 438 days | 438 days | N/A |  | 5 | Yes
6 | 1.10.9.1.4.1 |  |  |  |  | Draft Document | 100% | Wed 31/07/24 | Thu 31/07/25 | 262 days | Wed 31/07/24 | Tue 08/10/24 | 0 days | 212 days | 212 days | SI Transition |  | 6.33 | Yes
6 | 1.10.9.1.4.2 |  |  |  |  | Share Document with SRO | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Wed 09/10/24 | Wed 09/10/24 | 212 days | 211 days | -1 day | SI Transition |  | 6.33 | Yes
6 | 1.10.9.1.4.3 |  |  |  |  | Industry Consultation | 0% | Wed 06/08/25 | Wed 20/08/25 | 11 days | Tue 15/10/24 | Tue 29/10/24 | 211 days | 211 days | 0 days | SI Transition |  | 5.26 | Yes |  | 14/01/26 - Dates under review
6 | 1.10.9.1.4.4 |  |  |  |  | Assurance Meeting | 0% | Wed 03/09/25 | Wed 03/09/25 | 1 day | Tue 12/11/24 | Tue 12/11/24 | 211 days | 211 days | 0 days | SI Transition |  | 5.26 | Yes |  | 14/01/26 - Dates under review
6 | 1.10.9.1.4.5 | T2 | T3-MI-0500 | MCAG (Transition) |  | M16 methodology approved | 0% | Fri 31/07/26 | Fri 31/07/26 | 0 days | Fri 31/07/26 | Fri 31/07/26 | 1 day | 0 days | 0 days | SI Transition |  | 6.33 | Yes |  | 14/01/26 - SRO continue to deveop M16 methodology, which will be presented to industry in due course.
3 | 1.10.10 |  |  |  |  | Preparation for Cutover to Live | 62% | Mon 03/06/24 | Wed 05/05/27 | 763 days? | Fri 28/06/24 | Wed 22/10/25 | -19 days | 400 days | 562 days? | N/A |  | 6.11 | Yes
4 | 1.10.10.1 |  |  |  |  | Central Systems Prepare for Cutover to Live | 100% | Mon 03/06/24 | Wed 22/10/25 | 363 days? | Fri 28/06/24 | Fri 26/09/25 | -19 days | 18 days | 177 days? | N/A |  | 6.11 | Yes
5 | 1.10.10.1.1 |  |  |  |  | DCC (Functionality available June 2024) | 100% | Fri 28/06/24 | Fri 28/06/24 | 0 days | Fri 28/06/24 | Fri 28/06/24 | 0 days | -1 day | 0 days | DCC |  | 6.11 | Yes
5 | 1.10.10.1.2 |  |  |  |  | Development of Comms Approach and Declaration Guidance | 100% | Mon 28/04/25 | Thu 14/08/25 | 79 days | Mon 28/04/25 | Thu 14/08/25 | 0 days | 0 days | 0 days | N/A |  | 6.11 | Yes
6 | 1.10.10.1.2.1 |  |  |  |  | Draft Cutover Comms Approach | 100% | Mon 28/04/25 | Thu 17/07/25 | 59 days | Mon 28/04/25 | Thu 17/07/25 | 0 days | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.10.10.1.2.2 |  |  |  |  | Draft Cutover Comms Approach shared | 100% | Thu 17/07/25 | Thu 17/07/25 | 0 days | Thu 17/07/25 | Thu 17/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.10.10.1.2.3 |  |  |  |  | Finalised Cutover Comms Approach shared | 100% | Thu 14/08/25 | Thu 14/08/25 | 0 days | Thu 14/08/25 | Thu 14/08/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
5 | 1.10.10.1.3 |  |  |  |  | Development of Cutover Plan requirements with Participants | 100% | Fri 11/04/25 | Wed 22/10/25 | 139 days | Mon 03/03/25 | Wed 06/08/25 | 29 days | 55 days | 80 days | N/A |  | 6.11 | Yes
6 | 1.10.10.1.3.1 |  |  |  |  | Development of Central Parties Cutover Plans | 100% | Fri 11/04/25 | Fri 16/05/25 | 26 days | Fri 11/04/25 | Fri 16/05/25 | 0 days | 0 days | -33 days | SI Transition |  | 6.23 | Yes
6 | 1.10.10.1.3.2 |  |  |  |  | Development of Programme Participant Cutover Plans | 100% | Fri 11/04/25 | Fri 11/07/25 | 66 days | Fri 11/04/25 | Fri 11/07/25 | 0 days | 0 days | 66 days | SI Transition |  | 6.28 | Yes
6 | 1.10.10.1.3.3 |  |  |  |  | Central Party Cutover Plan Assurance | 100% | Mon 14/04/25 | Fri 13/06/25 | 45 days | Mon 14/04/25 | Fri 13/06/25 | 0 days | 0 days | 45 days | SI Transition |  | 6.23 | Yes
6 | 1.10.10.1.3.4 |  |  |  |  | Consolidated MHHS Cutover Plan Developed | 100% | Mon 19/05/25 | Fri 27/06/25 | 30 days | Mon 19/05/25 | Fri 27/06/25 | 0 days | 0 days | 30 days | SI Transition |  | 6.23 | Yes
6 | 1.10.10.1.3.5 |  |  |  |  | LDSO Cutover Plan Assurance | 100% | Mon 14/07/25 | Fri 01/08/25 | 15 days | Mon 14/07/25 | Fri 01/08/25 | 0 days | 0 days | 15 days | SI Transition |  | 6.28 | Yes
6 | 1.10.10.1.3.6 |  |  |  |  | SIT Supplier and SIT Agent Cutover Plan Assurance | 100% | Mon 14/07/25 | Fri 22/08/25 | 30 days | Mon 30/06/25 | Fri 22/08/25 | 10 days | 0 days | 30 days | SI Transition |  | 6.28 | Yes
6 | 1.10.10.1.3.7 |  |  |  |  | Monitor Participant Cutover Plan reporting | 100% | Wed 06/08/25 | Wed 22/10/25 | 56 days | Wed 06/08/25 | Wed 22/10/25 | 0 days | 0 days | 56 days | SI Transition |  | 6.34 | Yes
5 | 1.10.10.1.4 |  |  |  |  | M10/M11 Cutover Activities | 100% | Mon 14/04/25 | Fri 26/09/25 | 120 days? | Mon 14/04/25 | Fri 26/09/25 | 0 days | 0 days | 105 days? |  |  | 6.11 | Yes
6 | 1.10.10.1.4.1 |  |  |  |  | Load Shaping Service (LSS) | 100% | Mon 14/07/25 | Fri 25/07/25 | 10 days | Mon 14/07/25 | Fri 25/07/25 | 0 days | 0 days | 10 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.2 |  |  |  |  | Volume Allocation Service (VAS) | 100% | Mon 14/07/25 | Fri 25/07/25 | 10 days | Mon 14/07/25 | Fri 25/07/25 | 0 days | 0 days | 10 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.3 |  |  |  |  | Market-wide Data Service (MDS) | 100% | Mon 14/07/25 | Fri 25/07/25 | 10 days | Mon 14/07/25 | Fri 25/07/25 | 0 days | 0 days | 10 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.4 |  |  |  |  | Deployment of Industry Standing Data (ISD) Work Package (WP3) source code | 100% | Mon 14/07/25 | Fri 25/07/25 | 10 days | Mon 14/07/25 | Fri 25/07/25 | 0 days | 0 days | 10 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.5 |  |  |  |  | ISD Service Activation | 100% | Tue 05/08/25 | Tue 05/08/25 | 0 days | Tue 05/08/25 | Tue 05/08/25 | 0 days | -1 day | 0 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.6 |  |  |  |  | ISD Data Migration (PR-3) | 100% | Tue 05/08/25 | Fri 22/08/25 | 14 days | Tue 05/08/25 | Tue 12/08/25 | 0 days | 8 days | 14 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.7 |  |  |  |  | ISD Data Migration (PR-4) | 100% | Fri 15/08/25 | Fri 29/08/25 | 11 days | Fri 15/08/25 | Fri 22/08/25 | 0 days | 5 days | 11 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.8 |  |  |  |  | ISD Catalogue Published | 100% | Thu 11/09/25 | Thu 11/09/25 | 0 days | Thu 11/09/25 | Thu 11/09/25 | 0 days | -1 day | 0 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.9 |  |  |  |  | DIP Production Environment stood up | 100% | Fri 18/07/25 | Fri 18/07/25 | 0 days | Fri 18/07/25 | Fri 18/07/25 | 0 days | -1 day | 0 days | DIP Manager, Elexon |  | 6.3 | Yes
6 | 1.10.10.1.4.10 |  |  |  |  | Production DIP Portal (DIP Deployment) | 100% | Fri 01/08/25 | Mon 04/08/25 | 2 days | Fri 01/08/25 | Mon 04/08/25 | 0 days | 0 days | 2 days | Elexon,DIP Manager |  | 6.3 | Yes
6 | 1.10.10.1.4.11 |  |  |  |  | Production Certificates (DIP Deployment) | 100% | Fri 01/08/25 | Mon 04/08/25 | 2 days | Fri 01/08/25 | Mon 04/08/25 | 0 days | 0 days | 2 days | Elexon,DIP Manager |  | 6.3 | Yes
6 | 1.10.10.1.4.12 |  |  |  |  | Service Management Go-Live | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 0 days | -1 day | 0 days | Elexon |  | 6.3 | Yes
6 | 1.10.10.1.4.13 |  |  |  |  | DIP Onboarding | 100% | Mon 04/08/25 | Fri 22/08/25 | 15 days | Mon 04/08/25 | Fri 22/08/25 | 0 days | 0 days | 15 days | LDSOs, DIP Manager |  | 6.3 | Yes
6 | 1.10.10.1.4.14 |  |  |  |  | Deployment of MPRS 9 | 100% | Wed 06/08/25 | Mon 01/09/25 | 19 days | Wed 06/08/25 | Fri 12/09/25 | 0 days | -9 days | 19 days | LDSOs, St Clements |  | 6.3 | Yes
6 | 1.10.10.1.4.15 |  |  |  |  | ISD Population | 100% | Thu 11/09/25 | Thu 11/09/25 | 0 days | Thu 11/09/25 | Thu 11/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
6 | 1.10.10.1.4.16 |  |  |  |  | Population of Market Segment (95%) | 100% | Wed 06/08/25 | Fri 12/09/25 | 28 days | Wed 06/08/25 | Fri 12/09/25 | 0 days | 0 days | 28 days | LDSOs, St Clements |  | 6.3 | Yes
6 | 1.10.10.1.4.17 |  |  |  |  | Population of Market Segment (100%) | 100% | Fri 12/09/25 | Mon 22/09/25 | 7 days | Fri 12/09/25 | Mon 22/09/25 | 0 days | 0 days | 7 days | LDSOs, St Clements |  | 6.3 | Yes
6 | 1.10.10.1.4.18 |  |  |  |  | Population of Domestic Premises Indicator (Weekend start) | 100% | Fri 05/09/25 | Mon 08/09/25 | 2 days | Mon 08/09/25 | Tue 09/09/25 | -1 day | -1 day | 2 days | PP,DCC,SI Transition |  | 6.3 | Yes
6 | 1.10.10.1.4.19 |  |  |  |  | Completion of the pre-M10 MHHS Data Cleanse | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | PP,DCC,SI Transition |  | 6.3 | Yes
6 | 1.10.10.1.4.20 |  |  |  |  | Early Life Support Implemented | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 0 days | -1 day | 0 days | SI Transition,Elexon,Central Services |  | 6.3 | Yes
6 | 1.10.10.1.4.21 |  |  |  |  | MCC Tested and Ready to Operate | 100% | Fri 08/08/25 | Fri 19/09/25 | 31 days | Fri 08/08/25 | Fri 19/09/25 | 0 days | 0 days | 31 days | SI Migration |  | 6.3 | Yes
6 | 1.10.10.1.4.22 |  |  |  |  | Market-wide Participant MHHS Supporting Functionality Ready - Confirmation from Code Bodies | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | Code Bodies |  | 6.3 | Yes
6 | 1.10.10.1.4.23 |  |  |  |  | Market-wide Participant MHHS Supporting Functionality Ready | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | PP |  | 6.3 | Yes
6 | 1.10.10.1.4.24 |  |  |  |  | Pre-M10 Service Activation - LDSOs | 100% | Thu 11/09/25 | Thu 18/09/25 | 6 days | Thu 11/09/25 | Thu 18/09/25 | 0 days | 0 days | 6 days | DIP Manager, Service Activation Team, LDSOs |  | 6.3 | Yes
6 | 1.10.10.1.4.25 |  |  |  |  | Pre-M10 Service Activation - Suppliers and Agents | 100% | Thu 11/09/25 | Wed 15/10/25 | 25 days | Thu 11/09/25 | Wed 15/10/25 | 0 days | 0 days | 25 days | DIP Manager, Service Activation Team, Suppliers, Agents |  | 6.34 | Yes
6 | 1.10.10.1.4.26 |  |  |  |  | Load Shaping Service (LSS) | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.27 |  |  |  |  | Volume Allocation Service (VAS) | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.28 |  |  |  |  | Market-wide Data Service (MDS) | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | Elexon and Elexon Service Providers |  | 6.3 | Yes
6 | 1.10.10.1.4.29 |  |  |  |  | DTS | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | Electralink, RECCo |  | 6.3 | Yes
6 | 1.10.10.1.4.30 |  |  |  |  | EES | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | RECCo |  | 6.3 | Yes
6 | 1.10.10.1.4.31 |  |  |  |  | DCC | 100% | Mon 03/06/24 | Fri 28/06/24 | 20 days | Mon 03/06/24 | Fri 28/06/24 | 0 days | 0 days | 20 days | DCC |  | 6.3 | Yes
6 | 1.10.10.1.4.32 |  |  |  |  | MPRS – Registration Services, UMSO Role, LDSO Role | 100% | Fri 19/09/25 | Mon 22/09/25 | 2 days | Fri 19/09/25 | Mon 22/09/25 | 0 days | 0 days | 2 days | LDSOs, St Clements |  | 6.3 | Yes
6 | 1.10.10.1.4.33 |  |  |  |  | Qualification Pathway 4 Service Activation | 100% | Fri 26/09/25 | Fri 03/10/25 | 6 days | Fri 26/09/25 | Fri 03/10/25 | 0 days | 0 days | 6 days | DIP Manager, Service Activation Team, Suppliers, Agents |  | 6.3 | Yes
6 | 1.10.10.1.4.34 |  |  |  |  | Qualification Pathway 5 Service Activation | 100% | Thu 16/10/25 | Wed 22/10/25 | 5 days | Thu 16/10/25 | Wed 22/10/25 | 0 days | 0 days | 5 days | DIP Manager, Service Activation Team, Suppliers, Agents |  | 6.3 | Yes
6 | 1.8.4.1.4 | T3 | T3-MI-0034 | MCAG (Transition) |  | Central Systems live and Codes designated at 00:00 | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.10.10.1.4.36 |  |  |  |  | IF-047 sent at 9am on Monday 22nd September by Elexon via the DIP to all LDSOs and EES | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | Elexon |  | 6.3 | Yes
6 | 1.10.10.1.4.37 |  |  |  |  | All LDSOs and EES to load ISD files via the URL published within the IF-047 via the Elexon data store (note, this should contain the same ISD file as uploaded to the Elexon portal following 11th September, therefore it may not need to be applied by each p | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | LDSOs, EES |  | 6.3 | Yes
6 | 1.10.10.1.4.38 |  |  |  |  | Following successful loading of ISD data LDSOs can process New Connections via their DB01 interface to MPRS | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
6 | 1.10.10.1.4.39 |  |  |  |  | Each LDSO will track successful sending of the IF-050 message to the DIP | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
6 | 1.10.10.1.4.40 |  |  |  |  | EES will track successful receipt and processing of the IF-050 | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | EES |  | 6.3 | Yes
6 | 1.10.10.1.4.41 |  |  |  |  | IF-047 sent at 9am on Wednesday 22nd October by Elexon via the DIP | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 0 days | -1 day | 0 days | Elexon |  | 6.3 | Yes
4 | 1.10.10.2 |  |  |  |  | Cutover Governance M10 | 100% | Fri 22/08/25 | Wed 24/09/25 | 23 days | Wed 30/07/25 | Wed 24/09/25 | 17 days | -1 day | -4 days | N/A |  | 6.11 | Yes
5 | 1.10.10.2.1 |  |  |  |  | Confirmation from all LDSOs that DIP onboarding has taken place | 100% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Fri 22/08/25 | Fri 22/08/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.2 |  |  |  |  | Confirmation that all LDSOs have deployed MPRS 9 to production | 100% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.3 |  |  |  |  | Confirmation that population of Domestic Premises Indicator is complete | 100% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Mon 08/09/25 | Mon 08/09/25 | 0 days | -1 day | 0 days | LDSOs, RECCo |  | 6.3 | Yes
5 | 1.10.10.2.4 |  |  |  |  | Confirmation that Market Segment has been populated for 95% of LDSO portfolios | 100% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 12/09/25 | Fri 12/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.5 |  |  |  |  | Confirmation of all pre-M10 parties | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | Code Bodies |  | 6.3 | Yes
5 | 1.10.10.2.6 |  |  |  |  | Confirmation that all LDSOs have populated the ISD | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.7 |  |  |  |  | Declaration from all Central Services and LDSOs that they are in a position to move forwards | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | DIP Manager, Elexon (ECS, ISD, Service Management), Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) |  | 6.3 | Yes
5 | 1.10.10.2.8 |  |  |  |  | Market-wide Participant MHHS Migration Supporting Functionality is ready to be deployed | 100% | Mon 15/09/25 | Mon 15/09/25 | 0 days | Mon 15/09/25 | Mon 15/09/25 | 0 days | -1 day | 0 days | Code Bodies |  | 6.3 | Yes
5 | 1.10.10.2.9 |  |  |  |  | Recommendation from TORWG that the Programme should enter M10 | 100% | Wed 17/09/25 | Wed 17/09/25 | 0 days | Wed 17/09/25 | Wed 17/09/25 | 0 days | -1 day | 0 days | TORWG Members, MHHS Transition Team |  | 6.3 | Yes
5 | 1.10.10.2.10 |  |  |  |  | Production Service Activation Activities have taken place for all pre-M10 qualified parties | 100% | Thu 18/09/25 | Thu 18/09/25 | 0 days | Thu 18/09/25 | Thu 18/09/25 | 0 days | -1 day | 0 days | Service Activation Team |  | 6.3 | Yes
5 | 1.10.10.2.11 |  |  |  |  | Early Life Support model is in place | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 0 days | -1 day | 0 days | MHHS Programme |  | 6.3 | Yes
5 | 1.10.10.2.12 |  |  |  |  | MCC Operational | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 0 days | -1 day | 0 days | MHHS Programme |  | 6.3 | Yes
5 | 1.10.10.2.13 |  | T3-MI-0035 |  |  | MCAG (Confirm that the Programme can Enter M10) | 100% | Fri 19/09/25 | Fri 19/09/25 | 0 days | Fri 19/09/25 | Fri 19/09/25 | 0 days | -1 day | 0 days | MCAG Members, MHHS Transition Team |  | 6.3 | Yes
5 | 1.10.10.2.14 |  |  |  |  | Self-Declaration from all Central Services and LDSOs that Cutover activities have been successfully carried out | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) |  | 6.3 | Yes
5 | 1.10.10.2.15 |  |  |  |  | Confirmation that DIP and ECS have been deployed, Service management is active, ISD has been populated | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | Elexon (ECS, ISD, Service Management), DIP Manager |  | 6.3 | Yes
5 | 1.10.10.2.16 |  |  |  |  | Confirmation that Market Segment has been populated for 100% of LDSO portfolios | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.17 |  |  |  |  | IF-047 message has been sent | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | Elexon |  | 6.3 | Yes
5 | 1.10.10.2.18 |  |  |  |  | LDSOs have received the IF-047 message | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.19 |  |  |  |  | EES has received the IF-047 message and loaded the ISD file | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | EES |  | 6.3 | Yes
5 | 1.10.10.2.20 |  |  |  |  | Confirmation that the IF-050 has been sent and the number sent | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | LDSOs |  | 6.3 | Yes
5 | 1.10.10.2.21 |  |  |  |  | Confirmation of the number of IF-050s | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 0 days | -1 day | 0 days | EES |  | 6.3 | Yes
5 | 1.10.10.2.22 |  |  |  |  | Recommendation from TORWG that the M10 acceptance criteria have been met | 100% | Tue 23/09/25 | Tue 23/09/25 | 0 days | Tue 23/09/25 | Tue 23/09/25 | 0 days | -1 day | 0 days | TORWG Members, MHHS Transition Team, PSG |  | 6.3 | Yes
5 | 1.10.10.2.23 |  | T3-MI-0048 |  |  | PSG (OFGEM and PSG to Approve That Conditions of M10 and M13 Have Been Met) | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Wed 24/09/25 | Wed 24/09/25 | 0 days | -1 day | 0 days | PSG, Ofgem |  | 6.3 | Yes
4 | 1.10.10.3 |  |  |  |  | Cutover Governance M11 | 100% | Tue 14/10/25 | Wed 22/10/25 | 6 days | Fri 26/09/25 | Wed 22/10/25 | 12 days | -1 day | 6 days |  |  | 6.11 | Yes
5 | 1.10.10.3.1 |  |  |  |  | Self-Declaration that MHHS Functionality will be deployed to Production by Qualified parties | 100% | Tue 14/10/25 | Tue 14/10/25 | 0 days | Tue 14/10/25 | Tue 14/10/25 | 0 days | -1 day | 0 days | All Qualified Parties |  | 6.3 | Yes
5 | 1.10.10.3.2 |  |  |  |  | Qualification of all pre-M11 parties | 100% | Thu 16/10/25 | Thu 16/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | 0 days | -1 day | 0 days | Code Bodies |  | 6.3 | Yes
5 | 1.10.10.3.3 |  |  |  |  | Self-Declaration that ISD file has been manually accessed and applied by all qualified Suppliers and Agents | 100% | Thu 16/10/25 | Thu 16/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | 0 days | -1 day | 0 days | All Qualified Parties |  | 6.3 | Yes
5 | 1.10.10.3.4 |  |  |  |  | Confirmation of Qualified Parties from TORWG and their readiness | 100% | Fri 17/10/25 | Fri 17/10/25 | 0 days | Fri 17/10/25 | Fri 17/10/25 | 0 days | -1 day | 0 days | TORWG Members, MHHS Transition Team |  | 6.3 | Yes
5 | 1.10.10.3.5 |  | T3-MI-0036 |  |  | Recommendation from MCAG that the Programme can approve M11 / M12 | 100% | Mon 20/10/25 | Mon 20/10/25 | 0 days | Mon 20/10/25 | Mon 20/10/25 | 0 days | -1 day | 0 days | MCAG Members, MHHS Transition Team |  | 6.3 | Yes
5 | 1.10.10.3.6 |  |  |  |  | PSG (OFGEM and PSG Decision to Confirm M11 and M12) | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 0 days | -1 day | 0 days | PSG, Ofgem |  | 6.3 | Yes
4 | 1.10.10.4 |  |  |  |  | Migration Exclusion PPIR | 0% | Mon 16/02/26 | Fri 13/03/26 | 20 days | Mon 16/02/26 | Fri 13/03/26 | 0 days | 0 days | 20 days | SI Migration |  | 6.42 | Yes
5 | 1.10.10.4.1 |  |  |  |  | Publication of migration exclusion PPIR | 0% | Mon 16/02/26 | Mon 16/02/26 | 0 days | Mon 16/02/26 | Mon 16/02/26 | 0 days | -1 day | 0 days | SI Migration |  | 6.42 | Yes
5 | 1.10.10.4.2 |  |  |  |  | Participant response window for PPIR | 0% | Mon 16/02/26 | Fri 13/03/26 | 20 days | Mon 16/02/26 | Fri 13/03/26 | 0 days | 0 days | 20 days | SI Migration |  | 6.42 | Yes
5 | 1.10.10.4.3 |  |  |  |  | PPIR consultation window closed | 0% | Fri 13/03/26 | Fri 13/03/26 | 0 days | Fri 13/03/26 | Fri 13/03/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.42 | Yes
4 | 1.10.10.5 |  |  |  |  | Migration Sprints | 18% | Wed 24/09/25 | Wed 05/05/27 | 421 days | Wed 24/09/25 | Wed 05/05/27 | 0 days | 0 days | 421 days | SI Migration |  | 6.19 | Yes
5 | 1.10.10.5.1 |  |  |  |  | Migration Sprint 0 | 93% | Wed 24/09/25 | Tue 03/02/26 | 95 days | Thu 25/09/25 | Tue 03/02/26 | -1 day | 0 days | 95 days | SI Migration |  | 6.18 | Yes |  | 04/11/25 - For further details on Migration Sprint progress, please refer to the latest TORWG and MCAG papers.
6 | 1.10.10.5.1.1 |  |  |  |  | Sprint 0 Planning start date | 100% | Wed 24/09/25 | Wed 01/10/25 | 6 days | Thu 25/09/25 | Thu 02/10/25 | -1 day | -1 day | 6 days | SI Migration |  | 6.32 | Yes
6 | 1.10.10.5.1.2 |  |  |  |  | Issue Envelope | 100% | Wed 01/10/25 | Wed 01/10/25 | 0 days | Thu 02/10/25 | Thu 02/10/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.32 | Yes
6 | 1.10.10.5.1.3 |  |  |  |  | Supplier Submission Deadline | 100% | Wed 08/10/25 | Wed 08/10/25 | 0 days | Thu 09/10/25 | Thu 09/10/25 | 0 days | -1 day | 0 days | SI Migration, SIT PP |  | 6.32 | Yes
6 | 1.10.10.5.1.4 |  |  |  |  | Baseline Schedule Publication | 100% | Wed 15/10/25 | Wed 15/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.32 | Yes
6 | 1.10.10.5.1.5 | T2 | T2-MI-8000 | MCAG (Migration) |  | Migration Sprint 0 Schedule Baselined | 100% | Thu 16/10/25 | Thu 16/10/25 | 0 days | Thu 16/10/25 | Thu 16/10/25 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.1.6 |  |  |  |  | Sprint Execution Start | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Thu 23/10/25 | Thu 23/10/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.32 | Yes
6 | 1.10.10.5.1.7 |  |  |  |  | Sprint Execution | 92% | Wed 22/10/25 | Tue 03/02/26 | 75 days | Fri 24/10/25 | Tue 03/02/26 | -2 days | 0 days | 75 days | SI Migration, SIT PP |  | 6.32 | Yes
6 | 1.10.10.5.1.8 |  |  |  |  | Sprint Execution End | 0% | Tue 03/02/26 | Tue 03/02/26 | 0 days | Tue 03/02/26 | Tue 03/02/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.2 |  |  |  |  | Migration Sprint 1 | 13% | Wed 07/01/26 | Tue 31/03/26 | 60 days | Wed 07/01/26 | Tue 31/03/26 | 0 days | 0 days | 60 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.2.1 |  |  |  |  | Sprint 1 Planning start date | 100% | Wed 07/01/26 | Wed 14/01/26 | 6 days | Wed 07/01/26 | Wed 14/01/26 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.2.2 |  |  |  |  | Issue Envelope | 100% | Wed 14/01/26 | Wed 14/01/26 | 0 days | Wed 14/01/26 | Wed 14/01/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.2.3 |  |  |  |  | Supplier Submission Deadline | 100% | Wed 21/01/26 | Wed 21/01/26 | 0 days | Wed 21/01/26 | Wed 21/01/26 | 1 day | 0 days | 0 days | SI Migration, SIT PP |  | 6.18 | Yes
6 | 1.10.10.5.2.4 |  |  |  |  | Baseline Schedule Publication | 100% | Wed 28/01/26 | Wed 28/01/26 | 0 days | Wed 28/01/26 | Wed 28/01/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.2.5 |  |  |  |  | Migration Sprint 1 Schedule Baselined | 100% | Wed 28/01/26 | Wed 28/01/26 | 0 days | Wed 28/01/26 | Wed 28/01/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.2.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 04/02/26 | Wed 04/02/26 | 0 days | Wed 04/02/26 | Wed 04/02/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.2.7 |  |  |  |  | Sprint Execution | 0% | Thu 05/02/26 | Tue 31/03/26 | 39 days | Thu 05/02/26 | Tue 31/03/26 | 0 days | 0 days | 39 days | SI Migration, SIT PP |  | 6.18 | Yes
6 | 1.10.10.5.2.8 |  |  |  |  | Sprint Execution End | 0% | Tue 31/03/26 | Tue 31/03/26 | 0 days | Tue 31/03/26 | Tue 31/03/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.3 |  |  |  |  | Migration Sprint 2 | 0% | Wed 04/03/26 | Tue 02/06/26 | 65 days | Wed 04/03/26 | Tue 02/06/26 | 0 days | 0 days | 65 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.1 |  |  |  |  | Sprint 2 Planning start date | 0% | Wed 04/03/26 | Wed 11/03/26 | 6 days | Wed 04/03/26 | Wed 11/03/26 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.2 |  |  |  |  | Issue Envelope | 0% | Wed 11/03/26 | Wed 11/03/26 | 0 days | Wed 11/03/26 | Wed 11/03/26 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.3.3 |  |  |  |  | Supplier Submission Deadline | 0% | Wed 18/03/26 | Wed 18/03/26 | 0 days | Wed 18/03/26 | Wed 18/03/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.4 |  |  |  |  | Baseline Schedule Publication | 0% | Wed 25/03/26 | Wed 25/03/26 | 0 days | Wed 25/03/26 | Wed 25/03/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.5 |  |  |  |  | Migration Sprint 2 Schedule Baselined | 0% | Wed 25/03/26 | Wed 25/03/26 | 0 days | Wed 25/03/26 | Wed 25/03/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 01/04/26 | Wed 01/04/26 | 0 days | Wed 01/04/26 | Wed 01/04/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.7 |  |  |  |  | Sprint Execution | 0% | Thu 02/04/26 | Tue 02/06/26 | 44 days | Thu 02/04/26 | Tue 02/06/26 | 0 days | 0 days | 44 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.3.8 | T2 | T2-MI-8500 | MCAG (Migration) |  | Non-SIT Participants Migration Start | 0% | Fri 15/05/26 | Fri 15/05/26 | 0 days | Fri 15/05/26 | Fri 15/05/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.3.9 |  |  |  |  | Sprint Execution End | 0% | Tue 02/06/26 | Tue 02/06/26 | 0 days | Tue 02/06/26 | Tue 02/06/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.4 |  |  |  |  | Migration Sprint 3 | 0% | Wed 06/05/26 | Tue 04/08/26 | 65 days | Wed 06/05/26 | Tue 04/08/26 | 0 days | 0 days | 65 days | SI Migration |  | 6.2 | Yes
6 | 1.10.10.5.4.1 |  |  |  |  | Sprint 3 Planning start date | 0% | Wed 06/05/26 | Wed 13/05/26 | 6 days | Wed 06/05/26 | Wed 13/05/26 | 0 days | 0 days | 6 days | SI Migration |  | 6.2 | Yes
6 | 1.10.10.5.4.2 |  |  |  |  | Issue Envelope | 0% | Wed 13/05/26 | Wed 13/05/26 | 0 days | Wed 13/05/26 | Wed 13/05/26 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.2 | Yes
6 | 1.10.10.5.4.3 |  |  |  |  | Supplier Submission Deadline | 0% | Wed 20/05/26 | Wed 20/05/26 | 0 days | Wed 20/05/26 | Wed 20/05/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.2 | Yes
6 | 1.10.10.5.4.4 |  |  |  |  | Baseline Schedule Publication | 0% | Wed 27/05/26 | Wed 27/05/26 | 0 days | Wed 27/05/26 | Wed 27/05/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.2 | Yes
6 | 1.10.10.5.4.5 |  |  |  |  | Migration Sprint 3 Schedule Baselined | 0% | Wed 27/05/26 | Wed 27/05/26 | 0 days | Wed 27/05/26 | Wed 27/05/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.2 | Yes
6 | 1.10.10.5.4.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 03/06/26 | Wed 03/06/26 | 0 days | Wed 03/06/26 | Wed 03/06/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.2 | Yes
6 | 1.10.10.5.4.7 |  |  |  |  | Sprint Execution | 0% | Thu 04/06/26 | Tue 04/08/26 | 44 days | Thu 04/06/26 | Tue 04/08/26 | 0 days | 0 days | 44 days | SI Migration, PP |  | 6.2 | Yes
6 | 1.10.10.5.4.8 |  |  |  |  | Sprint Execution End | 0% | Tue 04/08/26 | Tue 04/08/26 | 0 days | Tue 04/08/26 | Tue 04/08/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.2 | Yes
5 | 1.10.10.5.5 |  |  |  |  | Migration Sprint 4 | 0% | Wed 08/07/26 | Tue 06/10/26 | 65 days | Wed 08/07/26 | Tue 06/10/26 | 0 days | 0 days | 65 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.5.1 |  |  |  |  | Sprint 4 Planning start date | 0% | Wed 08/07/26 | Wed 15/07/26 | 6 days | Wed 08/07/26 | Wed 15/07/26 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.5.2 |  |  |  |  | Issue Envelope | 0% | Wed 15/07/26 | Wed 15/07/26 | 0 days | Wed 15/07/26 | Wed 15/07/26 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.5.3 |  |  |  |  | Supplier Submission Deadline | 0% | Wed 22/07/26 | Wed 22/07/26 | 0 days | Wed 22/07/26 | Wed 22/07/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.5.4 |  |  |  |  | Baseline Schedule Publication | 0% | Wed 29/07/26 | Wed 29/07/26 | 0 days | Wed 29/07/26 | Wed 29/07/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.5.5 |  |  |  |  | Migration Sprint 4 Schedule Baselined | 0% | Wed 29/07/26 | Wed 29/07/26 | 0 days | Wed 29/07/26 | Wed 29/07/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.5.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 05/08/26 | Wed 05/08/26 | 0 days | Wed 05/08/26 | Wed 05/08/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.5.7 |  |  |  |  | Sprint Execution | 0% | Thu 06/08/26 | Tue 06/10/26 | 44 days | Thu 06/08/26 | Tue 06/10/26 | 0 days | 0 days | 44 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.5.8 |  |  |  |  | Sprint Execution End | 0% | Tue 06/10/26 | Tue 06/10/26 | 0 days | Tue 06/10/26 | Tue 06/10/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.6 |  |  |  |  | Migration Sprint 5 | 0% | Wed 09/09/26 | Tue 01/12/26 | 60 days | Wed 09/09/26 | Tue 01/12/26 | 0 days | 0 days | 60 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.6.1 |  |  |  |  | Sprint 5 Planning start date | 0% | Wed 09/09/26 | Wed 16/09/26 | 6 days | Wed 09/09/26 | Wed 16/09/26 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.6.2 |  |  |  |  | Issue Envelope | 0% | Wed 16/09/26 | Wed 16/09/26 | 0 days | Wed 16/09/26 | Wed 16/09/26 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.6.3 |  |  |  |  | Supplier Submission Deadline | 0% | Wed 23/09/26 | Wed 23/09/26 | 0 days | Wed 23/09/26 | Wed 23/09/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.6.4 |  |  |  |  | Baseline Schedule Publication | 0% | Wed 30/09/26 | Wed 30/09/26 | 0 days | Wed 30/09/26 | Wed 30/09/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.6.5 |  |  |  |  | Migration Sprint 5 Schedule Baselined | 0% | Wed 30/09/26 | Wed 30/09/26 | 0 days | Wed 30/09/26 | Wed 30/09/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.6.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 07/10/26 | Wed 07/10/26 | 0 days | Wed 07/10/26 | Wed 07/10/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.6.7 |  |  |  |  | Sprint Execution | 0% | Thu 08/10/26 | Tue 01/12/26 | 39 days | Thu 08/10/26 | Tue 01/12/26 | 0 days | 0 days | 39 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.6.8 |  |  |  |  | Sprint Execution End | 0% | Tue 01/12/26 | Tue 01/12/26 | 0 days | Tue 01/12/26 | Tue 01/12/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.7 |  |  |  |  | Migration Sprint 6 | 0% | Wed 04/11/26 | Tue 02/02/27 | 65 days | Wed 04/11/26 | Tue 02/02/27 | 0 days | 0 days | 65 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.7.1 |  |  |  |  | Sprint 6 Planning start date | 0% | Wed 04/11/26 | Wed 11/11/26 | 6 days | Wed 04/11/26 | Wed 11/11/26 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.7.2 |  |  |  |  | Issue Envelope | 0% | Wed 11/11/26 | Wed 11/11/26 | 0 days | Wed 11/11/26 | Wed 11/11/26 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.7.3 |  |  |  |  | Supplier Submission Deadline | 0% | Wed 18/11/26 | Wed 18/11/26 | 0 days | Wed 18/11/26 | Wed 18/11/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.7.4 |  |  |  |  | Baseline Schedule Publication | 0% | Wed 25/11/26 | Wed 25/11/26 | 0 days | Wed 25/11/26 | Wed 25/11/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.7.5 |  |  |  |  | Migration Sprint 6 Schedule Baselined | 0% | Wed 25/11/26 | Wed 25/11/26 | 0 days | Wed 25/11/26 | Wed 25/11/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.7.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 02/12/26 | Wed 02/12/26 | 0 days | Wed 02/12/26 | Wed 02/12/26 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.7.7 |  |  |  |  | Sprint Execution | 0% | Thu 03/12/26 | Tue 02/02/27 | 44 days | Thu 03/12/26 | Tue 02/02/27 | 0 days | 0 days | 44 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.7.8 |  |  |  |  | Sprint Execution End | 0% | Tue 02/02/27 | Tue 02/02/27 | 0 days | Tue 02/02/27 | Tue 02/02/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.8 |  |  |  |  | Migration Sprint 7 | 0% | Wed 06/01/27 | Tue 06/04/27 | 65 days | Wed 06/01/27 | Tue 06/04/27 | 0 days | 0 days | 65 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.8.1 |  |  |  |  | Sprint 6 Planning start date | 0% | Wed 06/01/27 | Wed 13/01/27 | 6 days | Wed 06/01/27 | Wed 13/01/27 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.8.2 |  |  |  |  | Issue Envelope | 0% | Wed 13/01/27 | Wed 13/01/27 | 0 days | Wed 13/01/27 | Wed 13/01/27 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.8.3 |  |  |  |  | Supplier Submission Deadline | 0% | Wed 20/01/27 | Wed 20/01/27 | 0 days | Wed 20/01/27 | Wed 20/01/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.8.4 |  |  |  |  | Baseline Schedule Publication | 0% | Wed 27/01/27 | Wed 27/01/27 | 0 days | Wed 27/01/27 | Wed 27/01/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.8.5 |  |  |  |  | Migration Sprint 7 Schedule Baselined | 0% | Wed 27/01/27 | Wed 27/01/27 | 0 days | Wed 27/01/27 | Wed 27/01/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.8.6 |  |  |  |  | Sprint Execution Start | 0% | Wed 03/02/27 | Wed 03/02/27 | 0 days | Wed 03/02/27 | Wed 03/02/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.8.7 |  |  |  |  | Sprint Execution | 0% | Thu 04/02/27 | Tue 06/04/27 | 44 days | Thu 04/02/27 | Tue 06/04/27 | 0 days | 0 days | 44 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.8.8 |  |  |  |  | Sprint Execution End | 0% | Tue 06/04/27 | Tue 06/04/27 | 0 days | Tue 06/04/27 | Tue 06/04/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
5 | 1.10.10.5.9 |  |  |  |  | Migration Sprint 8 | 0% | Mon 01/03/27 | Wed 05/05/27 | 48 days | Mon 01/03/27 | Wed 05/05/27 | 0 days | 0 days | 48 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.9.1 |  |  |  |  | Sprint 8 Planning start date | 0% | Mon 01/03/27 | Mon 08/03/27 | 6 days | Mon 01/03/27 | Mon 08/03/27 | 0 days | 0 days | 6 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.9.2 |  |  |  |  | Issue Envelope | 0% | Mon 08/03/27 | Mon 08/03/27 | 0 days | Mon 08/03/27 | Mon 08/03/27 | 1 day | 0 days | 0 days | SI Migration, PP |  | 6.18 | Yes
6 | 1.10.10.5.9.3 |  |  |  |  | Supplier Submission Deadline | 0% | Mon 15/03/27 | Mon 15/03/27 | 0 days | Mon 15/03/27 | Mon 15/03/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.9.4 |  |  |  |  | Baseline Schedule Publication | 0% | Mon 22/03/27 | Mon 22/03/27 | 0 days | Mon 22/03/27 | Mon 22/03/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.9.5 |  |  |  |  | Migration Sprint 8 Schedule Baselined | 0% | Mon 22/03/27 | Mon 22/03/27 | 0 days | Mon 22/03/27 | Mon 22/03/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.9.6 |  |  |  |  | Sprint Execution Start | 0% | Mon 29/03/27 | Mon 29/03/27 | 0 days | Mon 29/03/27 | Mon 29/03/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
6 | 1.10.10.5.9.7 |  |  |  |  | Sprint Execution | 0% | Tue 30/03/27 | Wed 05/05/27 | 27 days | Tue 30/03/27 | Wed 05/05/27 | 0 days | 0 days | 27 days | SI Migration, PP |  | 6.18 | Yes
5 | 1.10.10.5.10 | T2 | T2-MI-9000 | MCAG (Migration) |  | Sprint Execution End | 0% | Wed 05/05/27 | Wed 05/05/27 | 0 days | Wed 05/05/27 | Wed 05/05/27 | 1 day | 0 days | 0 days | SI Migration |  | 6.18 | Yes
3 | 1.10.11 |  |  |  |  | External Programme Dependency Management | 100% | Mon 31/10/22 | Fri 29/08/25 | 740 days | Mon 31/10/22 | Fri 29/08/25 | 0 days | 0 days | -87 days | N/A |  | 5 | Yes
4 | 1.10.11.1 |  |  |  |  | BSC Mod P432 & REC CP R0015 | 100% | Mon 31/10/22 | Tue 30/04/24 | 392 days | Mon 31/10/22 | Tue 30/04/24 | 0 days | 0 days | -435 days | N/A |  | 5 | Yes
5 | 1.10.11.1.1 |  |  |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | Mon 31/10/22 | Mon 15/01/24 | 316 days | Mon 31/10/22 | Mon 15/01/24 | 0 days | 0 days | -84 days | CPT,SRO Function |  | 5 | Yes
5 | 1.10.11.1.2 |  |  |  |  | Monitor progress and await implementation date | 100% | Tue 16/01/24 | Tue 30/04/24 | 76 days | Tue 16/01/24 | Tue 30/04/24 | 0 days | 0 days | -576 days | CPT,SRO Function |  | 5 | Yes
4 | 1.10.11.2 |  |  |  |  | BSC Mod P434 | 100% | Mon 31/10/22 | Wed 23/07/25 | 713 days | Mon 31/10/22 | Wed 23/07/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.11.2.1 |  |  |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | Mon 31/10/22 | Mon 23/01/23 | 61 days | Mon 31/10/22 | Mon 23/01/23 | 0 days | 0 days | 0 days | CPT,SRO Function |  | 5 | Yes
5 | 1.10.11.2.2 |  |  |  |  | Monitor progress and await implementation date | 100% | Tue 24/01/23 | Wed 23/07/25 | 652 days | Tue 24/01/23 | Wed 23/07/25 | 0 days | 0 days | 0 days | CPT,SRO Function |  | 5 | Yes
4 | 1.10.11.3 |  |  |  |  | Elexon System Capacity Upgrade | 100% | Mon 31/10/22 | Tue 01/07/25 | 697 days | Mon 31/10/22 | Tue 01/07/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.11.3.1 |  |  |  |  | Monitor progress to implementation | 100% | Mon 31/10/22 | Tue 01/07/25 | 697 days | Mon 31/10/22 | Tue 01/07/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.11.3.2 |  |  |  |  | Implementation date | 100% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.10.11.4 |  |  |  |  | DCC System Capacity Upgrade | 100% | Mon 28/07/25 | Fri 29/08/25 | 25 days | Mon 28/07/25 | Fri 29/08/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.10.11.4.1 |  |  |  |  | Assurance of DCC capacity upgrade to ensure suitability to support migration | 100% | Mon 28/07/25 | Fri 22/08/25 | 20 days | Mon 28/07/25 | Fri 22/08/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.10.11.4.2 | T2 | T2-MI-0350 | MCAG |  | DCC Capacity Upgrade Operational | 100% | Fri 29/08/25 | Fri 29/08/25 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.10.12 |  |  |  |  | Migration - Tier 1 Milestones | 0% | Mon 22/09/25 | Mon 09/08/27 | 490 days | Wed 24/09/25 | Mon 09/08/27 | -1 day | 0 days | 13 days | N/A |  | 5 | Yes
4 | 1.10.12.1 | T1 | T1-MI-2000 | PSG |  | Load Shaping Service switched on (M13) | 100% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Mon 22/09/25 | Mon 22/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.26 | Yes
4 | 1.10.12.2 | T1 | T2-MI-2500 | PSG |  | Load Shaping Service switched on (M13*) - Late Exit | 100% | Wed 24/12/25 | Wed 24/12/25 | 0 days | Wed 24/12/25 | Wed 24/12/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes |  | 06/01/26 - Not required as M13 was met
4 | 1.10.12.3 | T1 | T1-MI-3000 | PSG |  | Start of 18-month migration for UMS / Advanced (M11) | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.10.12.4 | T1 | T2-MI-3500 | PSG |  | Start of 18-month migration for UMS / Advanced (M11*) - Late Exit | 100% | Wed 21/01/26 | Wed 21/01/26 | 0 days | Wed 21/01/26 | Wed 21/01/26 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes |  | 06/01/26 - Not required as M11 was met
4 | 1.10.12.5 | T1 | T1-MI-4000 | PSG |  | Start of 18-month migration for Smart / Non-smart (M12) | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.10.12.6 | T1 | T2-MI-4500 | PSG |  | Start of 18-month migration for Smart / Non-smart (M12*) - Late Exit | 100% | Wed 21/01/26 | Wed 21/01/26 | 0 days | Wed 21/01/26 | Wed 21/01/26 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes |  | 06/01/26 - Not required as M12 was met
4 | 1.10.12.7 | T1 | T1-MI-6000 | PSG |  | Full transition complete (M15) | 0% | Fri 07/05/27 | Fri 07/05/27 | 0 days | Fri 07/05/27 | Fri 07/05/27 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.10.12.8 | T1 | T2-MI-6500 | PSG |  | Full transition complete (M15*) - Late Exit | 0% | Mon 09/08/27 | Mon 09/08/27 | 0 days | Mon 09/08/27 | Mon 09/08/27 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
2 | 1.11 |  |  |  |  | BUSINESS & OPERATIONAL READINESS | 70% | Mon 31/10/22 | Thu 23/12/27 | 1344 days? | Mon 31/10/22 | Thu 23/12/27 | 0 days | 0 days | 380 days? | N/A |  |  | Yes
3 | 1.11.1 |  |  |  |  | Service Management | 76% | Mon 31/10/22 | Sat 14/11/26 | 1055 days? | Tue 19/09/23 | Thu 24/06/27 | -231 days | -159 days | 215 days? | N/A |  | 5 | Yes
4 | 1.11.1.1 |  |  |  |  | Service Management Strategy | 100% | Tue 19/09/23 | Tue 27/02/24 | 116 days | Tue 19/09/23 | Tue 27/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.11.1.1.1 |  |  |  |  | Develop document with relevant participants (incl. review of the design baseline to ensure service management arrangements are in place across the solution architecture) | 100% | Tue 19/09/23 | Fri 12/01/24 | 84 days | Tue 19/09/23 | Fri 12/01/24 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.11.1.1.2 |  |  |  |  | Artefact review (via relevant Advisory Group) and updates | 100% | Mon 15/01/24 | Mon 26/02/24 | 31 days | Mon 15/01/24 | Mon 26/02/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.11.1.1.3 | T3 | T3-BC-0010 | MCAG |  | Service Management Strategy approved | 100% | Tue 27/02/24 | Tue 27/02/24 | 0 days | Tue 27/02/24 | Tue 27/02/24 | 1 day | 0 days | 0 days | SI Design |  | 5.16 | Yes
4 | 1.11.1.2 |  |  |  |  | Early Life Support Model | 100% | Wed 28/02/24 | Tue 29/04/25 | 305 days | Wed 28/02/24 | Tue 30/07/24 | 0 days | 195 days | 195 days | N/A |  | 5.16 | Yes
5 | 1.11.1.2.1 |  |  |  |  | Draft Document | 100% | Wed 28/02/24 | Thu 13/02/25 | 252 days | Wed 28/02/24 | Mon 10/06/24 | 0 days | 178 days | 178 days | SI Transition |  | 6.19 | Yes
5 | 1.11.1.2.2 |  |  |  |  | Share Document with SRO | 100% | Fri 14/02/25 | Fri 14/02/25 | 1 day | Tue 11/06/24 | Tue 11/06/24 | 178 days | 178 days | 0 days | SI Transition |  | 6.19 | Yes
5 | 1.11.1.2.3 |  |  |  |  | Industry Consultation | 100% | Fri 21/02/25 | Fri 07/03/25 | 11 days | Tue 18/06/24 | Tue 02/07/24 | 178 days | 178 days | 0 days | SI Transition |  | 6.19 | Yes
5 | 1.11.1.2.4 |  |  |  |  | Assurance Meeting | 100% | Thu 03/04/25 | Thu 03/04/25 | 1 day | Thu 03/04/25 | Thu 03/04/25 | 0 days | 0 days | 0 days | SI Transition |  | 6.19 | Yes
5 | 1.11.1.2.5 | T3 | T3-MI-0033 | MCAG (Transition) |  | MCAG Approval of Early Life Support Model | 100% | Tue 29/04/25 | Tue 29/04/25 | 0 days | Tue 29/04/25 | Tue 29/04/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.22 | Yes
4 | 1.11.1.3 |  |  |  |  | Service Management Arrangements Implementation | 100% | Mon 31/10/22 | Wed 14/01/26 | 838 days | Thu 25/09/25 | Thu 24/06/27 | -758 days | -376 days | 385 days | N/A |  | 5 | Yes
5 | 1.11.1.3.1 |  |  |  |  | Hypercare post M10 | 100% | Tue 23/09/25 | Wed 14/01/26 | 82 days | Thu 25/09/25 | Wed 14/01/26 | -2 days | 0 days | 2 days | SI Design |  | 6.26 | Yes
5 | 1.11.1.3.2 |  |  |  |  | Monitor Elexon implementation of Service Management arrangements | 100% | Mon 31/10/22 | Mon 01/07/24 | 436 days | Thu 23/10/25 | Thu 24/06/27 | -778 days | -778 days | 0 days | PP |  | 5 | Yes
4 | 1.11.1.4 |  |  |  |  | Wave 1 | 0% | Tue 31/03/26 | Fri 22/05/26 | 39 days? | Mon 31/10/22 | Tue 12/05/26 | 891 days | 8 days | 39 days? | Helix |  | 5.31 | Yes
5 | 1.11.1.4.1 |  |  |  |  | Wave 1 - Service Activation Preparation Tasks | 0% | Tue 31/03/26 | Fri 10/04/26 | 9 days | Tue 31/03/26 | Fri 10/04/26 | 0 days | 0 days | 9 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.4.1.1 |  |  |  |  | Review Entry/Exit Criteria & Lessons Learned | 0% | Tue 31/03/26 | Tue 31/03/26 | 0 days | Tue 31/03/26 | Tue 31/03/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.2 |  |  |  |  | Identify Resources | 0% | Tue 31/03/26 | Tue 31/03/26 | 1 day | Tue 31/03/26 | Tue 31/03/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.3 |  |  |  |  | Confirmation from Qualification of Wave Participants Complete | 0% | Tue 31/03/26 | Tue 31/03/26 | 0 days | Tue 31/03/26 | Tue 31/03/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.4 |  |  |  |  | Agree & Understand Support Model | 0% | Wed 01/04/26 | Wed 01/04/26 | 1 day | Wed 01/04/26 | Wed 01/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.5 |  |  |  |  | Training Confirmation | 0% | Thu 02/04/26 | Thu 02/04/26 | 1 day | Thu 02/04/26 | Thu 02/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.6 |  |  |  |  | Training Confirmation Completed | 0% | Thu 02/04/26 | Thu 02/04/26 | 0 days | Thu 02/04/26 | Thu 02/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.7 |  |  |  |  | Engagement / Communications with Participants Completed | 0% | Fri 03/04/26 | Fri 03/04/26 | 0 days | Fri 03/04/26 | Fri 03/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.8 |  |  |  |  | Internal Communications | 0% | Mon 06/04/26 | Mon 06/04/26 | 1 day | Mon 06/04/26 | Mon 06/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
7 | 1.11.1.4.1.8.1 |  |  |  |  | Agree Content for Livewire | 0% | Mon 06/04/26 | Mon 06/04/26 | 1 day | Mon 06/04/26 | Mon 06/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
7 | 1.11.1.4.1.8.2 |  |  |  |  | Publish Content for Livewire | 0% | Mon 06/04/26 | Mon 06/04/26 | 0 days | Mon 06/04/26 | Mon 06/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.9 |  |  |  |  | Validate User Access | 0% | Tue 07/04/26 | Tue 07/04/26 | 1 day | Tue 07/04/26 | Tue 07/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.10 |  |  |  |  | Target Systems and Environments Ready | 0% | Wed 08/04/26 | Wed 08/04/26 | 1 day | Wed 08/04/26 | Wed 08/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.11 |  |  |  |  | Provide LWIs | 0% | Thu 09/04/26 | Thu 09/04/26 | 1 day | Thu 09/04/26 | Thu 09/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.12 |  |  |  |  | Business Readiness Governance Approval | 0% | Fri 10/04/26 | Fri 10/04/26 | 1 day | Fri 10/04/26 | Fri 10/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.4.1.13 |  |  |  |  | Wave 1 - Service Activation Preparation Tasks (M) | 0% | Fri 10/04/26 | Fri 10/04/26 | 0 days | Fri 10/04/26 | Fri 10/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
5 | 1.11.1.4.2 |  |  |  |  | Wave 1 - Service Activation Implementation | 0% | Thu 02/04/26 | Fri 08/05/26 | 27 days? | Tue 14/04/26 | Fri 24/04/26 | -8 days | 10 days | 27 days? | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.4.2.1 |  |  |  |  | Market Entry to obtain Effective from Date from PP | 0% | Thu 02/04/26 | Thu 02/04/26 | 1 day | Thu 02/04/26 | Thu 02/04/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.2 |  |  |  |  | PP is Qualified by Code Bodies | 0% | Wed 15/04/26 | Wed 15/04/26 | 0 days | Wed 15/04/26 | Wed 15/04/26 | 1 day | 0 days | 0 days | PAB |  | 6.35 | Yes
6 | 1.11.1.4.2.3 |  |  |  |  | DIP Promoted to Production | 0% | Thu 16/04/26 | Wed 22/04/26 | 5 days | Mon 20/04/26 | Fri 24/04/26 | -2 days | -2 days | 5 days | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.4 |  |  |  |  | Create M16 in Customer Solution | 0% | Thu 16/04/26 | Thu 16/04/26 | 1 day | Fri 17/04/26 | Fri 17/04/26 | -1 day | -1 day | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.5 |  |  |  |  | MDD & ISD Publish | 0% | Fri 17/04/26 | Fri 17/04/26 | 1 day | Fri 17/04/26 | Fri 24/04/26 | 0 days | -5 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.6 |  |  |  |  | MDD & ISD Go-Live | 0% | Fri 24/04/26 | Fri 24/04/26 | 0 days | Fri 24/04/26 | Fri 24/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.7 |  |  |  |  | Wave 1 - Service Activation Implementation Complete (M) | 0% | Fri 24/04/26 | Fri 24/04/26 | 0 days | Fri 24/04/26 | Fri 24/04/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.8 |  |  |  |  | Seondary Publish ISD | 0% | Fri 01/05/26 | Fri 01/05/26 | 1 day? | Fri 01/05/26 | Fri 01/05/26 | 0 days | 0 days | 1 day? | Helix |  | 6.35 | Yes
6 | 1.11.1.4.2.9 |  |  |  |  | Secondary Go Live ISD | 0% | Fri 08/05/26 | Fri 08/05/26 | 0 days | Fri 08/05/26 | Fri 08/05/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
5 | 1.11.1.4.3 |  |  |  |  | Wave 1 - Service Activation Implementation MDD | 0% | Wed 15/04/26 | Thu 16/04/26 | 2 days | Fri 17/04/26 | Mon 11/05/26 | -2 days | -17 days | 2 days | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.4.3.1 |  |  |  |  | MDD Final Circular Completed | 0% | Wed 15/04/26 | Wed 15/04/26 | 0 days | Wed 15/04/26 | Wed 15/04/26 | 0 days | -1 day | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.4.3.2 |  |  |  |  | MDD Manual Update | 0% | Wed 15/04/26 | Thu 16/04/26 | 2 days | Wed 15/04/26 | Thu 16/04/26 | 0 days | 0 days | 2 days | Helix |  | 6.35 | Yes
5 | 1.11.1.4.4 |  |  |  |  | Wave 1 - Service Activation Hypercare | 0% | Thu 16/04/26 | Tue 12/05/26 | 19 days | Thu 16/04/26 | Tue 12/05/26 | 0 days | 0 days | 19 days | Helix |  | 6.29 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.4.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Thu 16/04/26 | Tue 12/05/26 | 19 days | Thu 16/04/26 | Tue 12/05/26 | 0 days | 0 days | 19 days | Helix |  | 6.29 | Yes
6 | 1.11.1.4.4.2 |  |  |  |  | Daily Reporting | 0% | Thu 16/04/26 | Tue 12/05/26 | 19 days | Thu 16/04/26 | Tue 12/05/26 | 0 days | 0 days | 19 days | Helix |  | 6.29 | Yes
6 | 1.11.1.4.4.3 |  |  |  |  | Issue Management | 0% | Thu 16/04/26 | Tue 12/05/26 | 19 days | Thu 16/04/26 | Tue 12/05/26 | 0 days | 0 days | 19 days | Helix |  | 6.29 | Yes
6 | 1.11.1.4.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 11/05/26 | Tue 12/05/26 | 2 days | Mon 11/05/26 | Tue 12/05/26 | 0 days | 0 days | 2 days | Helix |  | 6.29 | Yes
6 | 1.11.1.4.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 11/05/26 | Tue 12/05/26 | 2 days | Mon 11/05/26 | Tue 12/05/26 | 0 days | 0 days | 2 days | Helix |  | 6.29 | Yes
6 | 1.11.1.4.4.6 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Complete (M) | 0% | Tue 12/05/26 | Tue 12/05/26 | 0 days | Tue 12/05/26 | Tue 12/05/26 | 1 day | 0 days | 0 days | Helix |  | 6.29 | Yes
5 | 1.11.1.4.5 |  |  |  |  | Wave 1 - Service Activation Retro & Go/No Go | 0% | Tue 12/05/26 | Fri 22/05/26 | 9 days | Tue 12/05/26 | Fri 22/05/26 | 0 days | 0 days | 9 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.4.5.1 |  |  |  |  | Review | 0% | Tue 12/05/26 | Tue 12/05/26 | 0 days | Tue 12/05/26 | Tue 12/05/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.5.2 |  |  |  |  | Lessons Learned | 0% | Tue 12/05/26 | Mon 18/05/26 | 5 days | Tue 12/05/26 | Mon 18/05/26 | 0 days | 0 days | 5 days | Helix |  | 6.3 | Yes
6 | 1.11.1.4.5.3 |  |  |  |  | Wave 2 - Service Activation Readiness Review Against Entry/Exit Criteria | 0% | Mon 18/05/26 | Fri 22/05/26 | 5 days | Mon 18/05/26 | Fri 22/05/26 | 0 days | 0 days | 5 days | Helix |  | 6.3 | Yes
4 | 1.11.1.5 |  |  |  |  | Wave 2 | 0% | Mon 31/10/22 | Fri 19/06/26 | 950 days | Mon 31/10/22 | Mon 08/06/26 | 0 days | 9 days | 950 days | Helix |  | 5.31 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
5 | 1.11.1.5.1 |  |  |  |  | Wave 2 - Service Activation Implementation | 0% | Fri 15/05/26 | Mon 08/06/26 | 16 days | Fri 15/05/26 | Mon 08/06/26 | 0 days | -1 day | 16 days | Helix |  | 6.29 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.5.1.1 |  |  |  |  | Market Entry to obtain Effective from Date from PP | 0% | Fri 15/05/26 | Fri 15/05/26 | 1 day | Fri 15/05/26 | Fri 15/05/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.5.1.2 |  |  |  |  | PP is Qualified by Code Bodies | 0% | Thu 28/05/26 | Thu 28/05/26 | 0 days | Thu 28/05/26 | Thu 28/05/26 | 1 day | 0 days | 0 days | PAB |  | 6.35 | Yes
6 | 1.11.1.5.1.3 |  |  |  |  | DIP Promoted to Production | 0% | Fri 29/05/26 | Thu 04/06/26 | 5 days | Fri 29/05/26 | Thu 04/06/26 | 0 days | 0 days | 5 days | Helix |  | 6.35 | Yes
6 | 1.11.1.5.1.4 |  |  |  |  | Create M16 in Customer Solution | 0% | Fri 29/05/26 | Fri 29/05/26 | 1 day | Fri 29/05/26 | Fri 29/05/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.5.1.5 |  |  |  |  | MDD & ISD Publish | 0% | Fri 29/05/26 | Fri 29/05/26 | 1 day | Fri 29/05/26 | Fri 29/05/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.5.1.6 |  |  |  |  | MDD & ISD Go-Live | 0% | Fri 05/06/26 | Fri 05/06/26 | 0 days | Fri 05/06/26 | Fri 05/06/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.5.1.7 |  |  |  |  | Wave 2 - Service Activation Implementation Complete (M) | 0% | Mon 08/06/26 | Mon 08/06/26 | 0 days | Mon 08/06/26 | Mon 08/06/26 | 0 days | -1 day | 0 days | Helix |  | 6.35 | Yes
5 | 1.11.1.5.2 |  |  |  |  | Wave 2 - Service Activation Implementation MDD | 0% | Mon 31/10/22 | Thu 24/11/22 | 19 days | Mon 31/10/22 | Thu 24/11/22 | 0 days | 0 days | 19 days | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.5.2.1 |  |  |  |  | MDD Final Circular Completed | 0% | Thu 28/05/26 | Thu 28/05/26 | 0 days | Thu 28/05/26 | Thu 28/05/26 | 0 days | -1 day | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.5.2.2 |  |  |  |  | MDD Manual Update | 0% | Fri 12/06/26 | Mon 15/06/26 | 2 days | Fri 12/06/26 | Mon 15/06/26 | 0 days | 0 days | 2 days | Helix |  | 6.35 | Yes
5 | 1.11.1.5.3 |  |  |  |  | Wave 2 - Service Activation Hypercare | 0% | Wed 27/05/26 | Mon 08/06/26 | 9 days | Wed 27/05/26 | Mon 08/06/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.5.3.1 |  |  |  |  | Service& Process Monitoring | 0% | Wed 27/05/26 | Mon 08/06/26 | 9 days | Wed 27/05/26 | Mon 08/06/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.5.3.2 |  |  |  |  | Daily Reporting | 0% | Wed 27/05/26 | Mon 08/06/26 | 9 days | Wed 27/05/26 | Mon 08/06/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.5.3.3 |  |  |  |  | Issue Management | 0% | Wed 27/05/26 | Mon 08/06/26 | 9 days | Wed 27/05/26 | Mon 08/06/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.5.3.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Thu 04/06/26 | Mon 08/06/26 | 3 days | Thu 04/06/26 | Mon 08/06/26 | 0 days | 0 days | 3 days | Helix |  | 6.29 | Yes
6 | 1.11.1.5.3.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 08/06/26 | Mon 08/06/26 | 1 day | Mon 08/06/26 | Mon 08/06/26 | 0 days | 0 days | 1 day | Helix |  | 6.29 | Yes
6 | 1.11.1.5.3.6 |  |  |  |  | Wave 2 - Service Activation Hypercare Complete (M) | 0% | Mon 08/06/26 | Mon 08/06/26 | 0 days | Mon 08/06/26 | Mon 08/06/26 | 0 days | -1 day | 0 days | Helix |  | 6.29 | Yes
5 | 1.11.1.5.4 |  |  |  |  | Wave 2 - Service Activation Retro & Go/No Go | 0% | Mon 08/06/26 | Fri 19/06/26 | 10 days | Mon 08/06/26 | Fri 19/06/26 | 0 days | 0 days | 10 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.5.4.1 |  |  |  |  | Review | 0% | Mon 08/06/26 | Mon 08/06/26 | 0 days | Mon 08/06/26 | Mon 08/06/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.5.4.2 |  |  |  |  | Lessons Learned | 0% | Mon 08/06/26 | Fri 12/06/26 | 5 days | Mon 08/06/26 | Fri 12/06/26 | 0 days | 0 days | 5 days | Helix |  | 6.3 | Yes
6 | 1.11.1.5.4.3 |  |  |  |  | Wave 3 - Service Activation Readiness Review Against Entry/Exit Criteria | 0% | Mon 15/06/26 | Fri 19/06/26 | 5 days | Mon 15/06/26 | Fri 19/06/26 | 0 days | 0 days | 5 days | Helix |  | 6.3 | Yes
4 | 1.11.1.6 |  |  |  |  | Wave 3 | 0% | Mon 31/10/22 | Fri 14/08/26 | 990 days? | Mon 31/10/22 | Fri 21/08/26 | 0 days | -5 days | 990 days? | Helix |  | 5.31 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
5 | 1.11.1.6.1 |  |  |  |  | Wave 3 - Service Activation Preparation Tasks | 0% | Mon 13/07/26 | Fri 24/07/26 | 10 days | Mon 13/07/26 | Fri 24/07/26 | 0 days | 0 days | 10 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.6.1.1 |  |  |  |  | Review Entry/Exit Criteria & Lessons Learned | 0% | Mon 13/07/26 | Mon 13/07/26 | 0 days | Mon 13/07/26 | Mon 13/07/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.2 |  |  |  |  | Identify Resources | 0% | Mon 13/07/26 | Mon 13/07/26 | 1 day | Mon 13/07/26 | Mon 13/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.3 |  |  |  |  | Confirmation from Qualification of Wave Participants Complete | 0% | Mon 13/07/26 | Mon 13/07/26 | 0 days | Mon 13/07/26 | Mon 13/07/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.4 |  |  |  |  | Review Handover from Wave 2 | 0% | Tue 14/07/26 | Tue 14/07/26 | 1 day | Tue 14/07/26 | Tue 14/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.5 |  |  |  |  | Agree & Understand Support Model | 0% | Wed 15/07/26 | Wed 15/07/26 | 1 day | Wed 15/07/26 | Wed 15/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.6 |  |  |  |  | Confirm Training complete | 0% | Thu 16/07/26 | Thu 16/07/26 | 1 day | Thu 16/07/26 | Thu 16/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.7 |  |  |  |  | Engagement / Communications with Participants | 0% | Fri 17/07/26 | Fri 17/07/26 | 1 day | Fri 17/07/26 | Fri 17/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.8 |  |  |  |  | Internal Communications | 0% | Mon 20/07/26 | Mon 20/07/26 | 1 day | Mon 20/07/26 | Mon 20/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
7 | 1.11.1.6.1.8.1 |  |  |  |  | Agree Content for Livewire | 0% | Mon 20/07/26 | Mon 20/07/26 | 1 day | Mon 20/07/26 | Mon 20/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
7 | 1.11.1.6.1.8.2 |  |  |  |  | Publish Content for Livewire | 0% | Mon 20/07/26 | Mon 20/07/26 | 0 days | Mon 20/07/26 | Mon 20/07/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.9 |  |  |  |  | Validate User Access | 0% | Tue 21/07/26 | Tue 21/07/26 | 1 day | Tue 21/07/26 | Tue 21/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.10 |  |  |  |  | Target Systems and Environments Ready | 0% | Wed 22/07/26 | Wed 22/07/26 | 1 day | Wed 22/07/26 | Wed 22/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.11 |  |  |  |  | Provide LWIs | 0% | Thu 23/07/26 | Thu 23/07/26 | 1 day | Thu 23/07/26 | Thu 23/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.12 |  |  |  |  | Business Readiness Governance Approval | 0% | Fri 24/07/26 | Fri 24/07/26 | 1 day | Fri 24/07/26 | Fri 24/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.6.1.13 |  |  |  |  | Wave 3 - Service Activation Preparation Tasks Completed | 0% | Fri 24/07/26 | Fri 24/07/26 | 0 days | Fri 24/07/26 | Fri 24/07/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
5 | 1.11.1.6.2 |  |  |  |  | Wave 3 - Service Activation Implementation | 0% | Mon 31/10/22 | Mon 21/11/22 | 16 days | Mon 31/10/22 | Mon 21/11/22 | 0 days | 0 days | 16 days | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.6.2.1 |  |  |  |  | Market Entry to obtain Effective from Date from PP | 0% | Fri 17/07/26 | Fri 17/07/26 | 1 day | Fri 17/07/26 | Fri 17/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.6.2.2 |  |  |  |  | PP Qualified by Code Bodies | 0% | Thu 30/07/26 | Thu 30/07/26 | 0 days | Thu 30/07/26 | Thu 30/07/26 | 1 day | 0 days | 0 days | PAB |  | 6.35 | Yes
6 | 1.11.1.6.2.3 |  |  |  |  | DIP Promoted to Production | 0% | Fri 31/07/26 | Thu 06/08/26 | 5 days | Fri 31/07/26 | Thu 06/08/26 | 0 days | 0 days | 5 days | Helix |  | 6.35 | Yes
6 | 1.11.1.6.2.4 |  |  |  |  | Create M16 in Customer Solution | 0% | Fri 31/07/26 | Fri 31/07/26 | 1 day | Fri 31/07/26 | Fri 31/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.6.2.5 |  |  |  |  | MDD & ISD Publish | 0% | Fri 31/07/26 | Fri 31/07/26 | 1 day | Fri 31/07/26 | Fri 31/07/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.6.2.6 |  |  |  |  | MDD & ISD Go-Live | 0% | Fri 07/08/26 | Fri 07/08/26 | 0 days | Fri 07/08/26 | Fri 07/08/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
5 | 1.11.1.6.3 |  |  |  |  | Wave 3 - Service Activation Implementation MDD | 0% | Thu 30/07/26 | Fri 14/08/26 | 12 days? | Thu 30/07/26 | Fri 21/08/26 | 0 days | -5 days | 12 days? | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.6.3.1 |  |  |  |  | MDD Final Circular Completed | 0% | Thu 30/07/26 | Thu 30/07/26 | 1 day? | Thu 30/07/26 | Thu 30/07/26 | 0 days | 0 days | 1 day? | Helix |  | 6.35 | Yes
6 | 1.11.1.6.3.2 |  |  |  |  | MDD Manual Update | 0% | Fri 14/08/26 | Fri 14/08/26 | 1 day? | Fri 14/08/26 | Fri 14/08/26 | 0 days | 0 days | 1 day? | Helix |  | 6.35 | Yes
5 | 1.11.1.6.4 |  |  |  |  | Wave 3 - Service Activation Hypercare | 0% | Wed 29/07/26 | Mon 10/08/26 | 9 days | Wed 29/07/26 | Mon 10/08/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.6.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Wed 29/07/26 | Mon 10/08/26 | 9 days | Wed 29/07/26 | Mon 10/08/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.6.4.2 |  |  |  |  | Daily Reporting | 0% | Wed 29/07/26 | Mon 10/08/26 | 9 days | Wed 29/07/26 | Mon 10/08/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.6.4.3 |  |  |  |  | Issue Management | 0% | Wed 29/07/26 | Mon 10/08/26 | 9 days | Wed 29/07/26 | Mon 10/08/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.6.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Thu 06/08/26 | Mon 10/08/26 | 3 days | Thu 06/08/26 | Mon 10/08/26 | 0 days | 0 days | 3 days | Helix |  | 6.29 | Yes
6 | 1.11.1.6.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 10/08/26 | Mon 10/08/26 | 1 day | Mon 10/08/26 | Mon 10/08/26 | 0 days | 0 days | 1 day | Helix |  | 6.29 | Yes
6 | 1.11.1.6.4.6 |  |  |  |  | Wave 3 Service Activation Hypercare Complete (M) | 0% | Mon 10/08/26 | Mon 10/08/26 | 0 days | Mon 10/08/26 | Mon 10/08/26 | 1 day | 0 days | 0 days | Helix |  | 6.29 | Yes
5 | 1.11.1.6.5 |  |  |  |  | Wave 3 - Service Activation Retro & Go/No Go | 0% | Wed 17/06/26 | Fri 14/08/26 | 43 days | Wed 17/06/26 | Fri 14/08/26 | 0 days | 0 days | 43 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.6.5.1 |  |  |  |  | Review | 0% | Mon 10/08/26 | Mon 10/08/26 | 0 days | Mon 10/08/26 | Mon 10/08/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.6.5.2 |  |  |  |  | Lessons Learned | 0% | Mon 10/08/26 | Fri 14/08/26 | 5 days | Mon 10/08/26 | Fri 14/08/26 | 0 days | 0 days | 5 days | Helix |  | 6.3 | Yes
6 | 1.11.1.6.5.3 |  |  |  |  | Wave 4 - Service Activation Readiness Review Against Entry/Exit Criteria | 0% | Wed 17/06/26 | Tue 23/06/26 | 5 days | Wed 17/06/26 | Tue 23/06/26 | 0 days | 0 days | 5 days | Helix |  | 6.3 | Yes
4 | 1.11.1.7 |  |  |  |  | Wave 4 | 0% | Mon 31/10/22 | Sat 14/11/26 | 1055 days? | Mon 31/10/22 | Fri 23/10/26 | 0 days | 15 days | 1055 days? | Helix |  | 5.31 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
5 | 1.11.1.7.1 |  |  |  |  | Wave 4 - Service Activation Preparation Tasks | 0% | Mon 07/09/26 | Fri 18/09/26 | 10 days | Mon 07/09/26 | Fri 18/09/26 | 0 days | 0 days | 10 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.7.1.1 |  |  |  |  | Review Entry/Exit Criteria & Lessons Learned | 0% | Mon 07/09/26 | Mon 07/09/26 | 0 days | Mon 07/09/26 | Mon 07/09/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.2 |  |  |  |  | Identify Resources | 0% | Mon 07/09/26 | Mon 07/09/26 | 1 day | Mon 07/09/26 | Mon 07/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.3 |  |  |  |  | Confirmation from Qualification of Wave Participants Complete | 0% | Mon 07/09/26 | Mon 07/09/26 | 0 days | Mon 07/09/26 | Mon 07/09/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.4 |  |  |  |  | Review Handover from Wave 3 | 0% | Tue 08/09/26 | Tue 08/09/26 | 1 day | Tue 08/09/26 | Tue 08/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.5 |  |  |  |  | Agree & Understand Support Model | 0% | Wed 09/09/26 | Wed 09/09/26 | 1 day | Wed 09/09/26 | Wed 09/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.6 |  |  |  |  | Confirm Training complete | 0% | Thu 10/09/26 | Thu 10/09/26 | 1 day | Thu 10/09/26 | Thu 10/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.7 |  |  |  |  | Engagement / Communications with Participants | 0% | Fri 11/09/26 | Fri 11/09/26 | 1 day | Fri 11/09/26 | Fri 11/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.8 |  |  |  |  | Internal Communications | 0% | Mon 14/09/26 | Mon 14/09/26 | 1 day | Mon 14/09/26 | Mon 14/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
7 | 1.11.1.7.1.8.1 |  |  |  |  | Agree Content for Livewire | 0% | Mon 14/09/26 | Mon 14/09/26 | 1 day | Mon 14/09/26 | Mon 14/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
7 | 1.11.1.7.1.8.2 |  |  |  |  | Publish Content for Livewire | 0% | Mon 14/09/26 | Mon 14/09/26 | 0 days | Mon 14/09/26 | Mon 14/09/26 | 0 days | -1 day | 0 days | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.9 |  |  |  |  | Validate User Access | 0% | Tue 15/09/26 | Tue 15/09/26 | 1 day | Tue 15/09/26 | Tue 15/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.10 |  |  |  |  | Target Systems and Environments Ready | 0% | Wed 16/09/26 | Wed 16/09/26 | 1 day | Wed 16/09/26 | Wed 16/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.11 |  |  |  |  | Provide LWIs | 0% | Thu 17/09/26 | Thu 17/09/26 | 1 day | Thu 17/09/26 | Thu 17/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.12 |  |  |  |  | Business Readiness Governance Approval | 0% | Fri 18/09/26 | Fri 18/09/26 | 1 day | Fri 18/09/26 | Fri 18/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.3 | Yes
6 | 1.11.1.7.1.13 |  |  |  |  | Wave 4 - Service Activation Preparation Tasks Completed | 0% | Fri 18/09/26 | Fri 18/09/26 | 0 days | Fri 18/09/26 | Fri 18/09/26 | 1 day | 0 days | 0 days | Helix |  | 6.3 | Yes
5 | 1.11.1.7.2 |  |  |  |  | Wave 4 - Service Activation Implementation | 0% | Mon 31/10/22 | Mon 21/11/22 | 16 days | Mon 31/10/22 | Mon 21/11/22 | 0 days | 0 days | 16 days | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.7.2.1 |  |  |  |  | Market Entry to obtain Effective from Date from PP | 0% | Fri 11/09/26 | Fri 11/09/26 | 1 day | Fri 11/09/26 | Fri 11/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.7.2.2 |  |  |  |  | MHHSP Enabled Confirmation | 0% | Thu 24/09/26 | Thu 24/09/26 | 0 days | Thu 24/09/26 | Thu 24/09/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.7.2.3 |  |  |  |  | DIP Promoted to Production | 0% | Fri 25/09/26 | Thu 01/10/26 | 5 days | Fri 25/09/26 | Thu 01/10/26 | 0 days | 0 days | 5 days | Helix |  | 6.35 | Yes
6 | 1.11.1.7.2.4 |  |  |  |  | Create M16 in Customer Solution | 0% | Fri 25/09/26 | Fri 25/09/26 | 1 day | Fri 25/09/26 | Fri 25/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.7.2.5 |  |  |  |  | MDD & ISD Publish | 0% | Fri 25/09/26 | Fri 25/09/26 | 1 day | Fri 25/09/26 | Fri 25/09/26 | 0 days | 0 days | 1 day | Helix |  | 6.35 | Yes
6 | 1.11.1.7.2.6 |  |  |  |  | MDD & ISD Go-Live | 0% | Fri 02/10/26 | Fri 02/10/26 | 0 days | Fri 02/10/26 | Fri 02/10/26 | 1 day | 0 days | 0 days | Helix |  | 6.35 | Yes
6 | 1.11.1.7.2.7 |  |  |  |  | Wave 4 - Service Activation Implementation Complete (M) | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 0 days | -1 day | 0 days | Helix |  | 6.35 | Yes
5 | 1.11.1.7.3 |  |  |  |  | Wave 4 - Service Activation Implementation MDD | 0% | Thu 24/09/26 | Fri 16/10/26 | 17 days? | Thu 24/09/26 | Fri 23/10/26 | 0 days | -5 days | 17 days? | Helix |  | 6.35 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.7.3.1 |  |  |  |  | MDD Final Circular Completed | 0% | Thu 24/09/26 | Thu 24/09/26 | 1 day? | Thu 24/09/26 | Thu 24/09/26 | 0 days | 0 days | 1 day? | Helix |  | 6.35 | Yes
6 | 1.11.1.7.3.2 |  |  |  |  | MDD Manual Update | 0% | Fri 16/10/26 | Fri 16/10/26 | 1 day? | Fri 16/10/26 | Fri 16/10/26 | 0 days | 0 days | 1 day? | Helix |  | 6.35 | Yes
5 | 1.11.1.7.4 |  |  |  |  | Wave 4 - Service Activation Hypercare | 0% | Wed 23/09/26 | Sat 14/11/26 | 38 days | Wed 23/09/26 | Mon 05/10/26 | 0 days | 29 days | 38 days | Helix |  | 6.29 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
6 | 1.11.1.7.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Wed 23/09/26 | Mon 05/10/26 | 9 days | Wed 23/09/26 | Mon 05/10/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.7.4.2 |  |  |  |  | Daily Reporting | 0% | Wed 23/09/26 | Mon 05/10/26 | 9 days | Wed 23/09/26 | Mon 05/10/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.7.4.3 |  |  |  |  | Issue Management | 0% | Wed 23/09/26 | Mon 05/10/26 | 9 days | Wed 23/09/26 | Mon 05/10/26 | 0 days | 0 days | 9 days | Helix |  | 6.29 | Yes
6 | 1.11.1.7.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Fri 02/10/26 | Mon 05/10/26 | 2 days | Fri 02/10/26 | Mon 05/10/26 | 0 days | 0 days | 2 days | Helix |  | 6.29 | Yes
6 | 1.11.1.7.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 05/10/26 | Mon 05/10/26 | 1 day | Mon 05/10/26 | Mon 05/10/26 | 0 days | 0 days | 1 day | Helix |  | 6.29 | Yes
6 | 1.11.1.7.4.6 |  |  |  |  | Wave 4 - Service Activation Hypercare Complete (M) | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 1 day | 0 days | 0 days | Helix |  | 6.29 | Yes
6 | 1.11.1.7.4.7 |  |  |  |  | Service Activation Transition Completion | 0% | Mon 12/10/26 | Sat 14/11/26 | 25 days | Mon 12/10/26 | Fri 16/10/26 | 0 days | 20 days | 25 days | Helix |  | 6.3 | Yes |  | 03/12/25 - Programme and Elexon are working to update the Service Activation plan for Non-SIT PPs to reflect the ISD / MDD Calendar which was published on 28/11/25.
7 | 1.11.1.7.4.7.1 |  |  |  |  | Lessons Learnt Review | 0% | Mon 12/10/26 | Fri 16/10/26 | 5 days | Mon 19/10/26 | Fri 06/11/26 | -5 days | -15 days | 5 days | Helix |  | 6.3 | Yes
7 | 1.11.1.7.4.7.2 |  |  |  |  | Document and circulate Lessons Learnt | 0% | Mon 19/10/26 | Fri 06/11/26 | 15 days | Mon 09/11/26 | Sat 14/11/26 | -15 days | -5 days | 15 days | Helix |  | 6.3 | Yes
7 | 1.11.1.7.4.7.3 |  |  |  |  | Handover to Elexon | 0% | Mon 09/11/26 | Sat 14/11/26 | 5 days | Sat 14/11/26 | Sat 14/11/26 | -5 days | 0 days | 5 days | Helix |  | 6.3 | Yes
7 | 1.11.1.7.4.7.4 |  |  |  |  | Service Activation Transition Completed | 0% | Sat 14/11/26 | Sat 14/11/26 | 0 days | Sat 14/11/26 | Sat 14/11/26 | 0 days | 0 days | 0 days | Helix |  | 6.3 | Yes
3 | 1.11.2 |  |  |  |  | Implement Early Life Support Plan | 100% | Mon 07/07/25 | Fri 19/09/25 | 55 days | Mon 07/07/25 | Fri 19/09/25 | 0 days | 0 days | 10 days | N/A |  | 5 | Yes
4 | 1.11.2.1 |  |  |  | MHHS-ART095 | Implement Early Life Support Plan | 100% | Mon 07/07/25 | Fri 19/09/25 | 55 days | Mon 07/07/25 | Fri 19/09/25 | 0 days | 0 days | 10 days | SI Transition |  | 5.23 | Yes
3 | 1.11.3 |  |  |  |  | Early Life Support Phase | 80% | Thu 23/10/25 | Tue 27/01/26 | 69 days | Thu 23/10/25 | Thu 22/01/26 | 0 days | 3 days | 69 days | SI Transition |  | 6.37 | Yes
4 | 1.11.3.1 |  |  |  |  | Phase 1 End | 100% | Thu 23/10/25 | Thu 27/11/25 | 26 days | Thu 23/10/25 | Thu 20/11/25 | 0 days | 5 days | 26 days | SI Transition |  | 6.38 | Yes
4 | 1.11.3.2 |  |  |  |  | Phase 2 End | 100% | Fri 21/11/25 | Thu 18/12/25 | 20 days | Fri 21/11/25 | Thu 18/12/25 | 0 days | 0 days | 20 days | SI Transition |  | 6.37 | Yes
4 | 1.11.3.3 |  |  |  |  | Phase 3 End/Early Life Exit | 46% | Fri 19/12/25 | Tue 27/01/26 | 28 days | Fri 19/12/25 | Tue 27/01/26 | 0 days | 0 days | 28 days | SI Transition |  | 6.39 | Yes
3 | 1.11.4 |  |  |  |  | Business Continuity and Disaster Recovery Plan | 100% | Thu 31/07/25 | Wed 24/09/25 | 40 days | Thu 31/07/25 | Wed 24/09/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.4.1 |  |  |  |  | Central Parties BCDRs in Place | 100% | Thu 31/07/25 | Wed 27/08/25 | 20 days | Thu 31/07/25 | Wed 27/08/25 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.11.4.2 |  |  |  |  | Risk Based Assurance of Cental Party BCDRs | 100% | Thu 28/08/25 | Wed 24/09/25 | 20 days | Thu 28/08/25 | Wed 24/09/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.11.5 |  |  |  |  | PP Business Change | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.5.1 |  |  |  |  | Plan stakeholder management | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.2 |  |  |  |  | Manage stakeholders | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.3 |  |  |  |  | Develop & implement changes to KPIs, organisation & people management | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.4 |  |  |  |  | Develop & test changes to business processes | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.5 |  |  |  |  | Develop and deliver training | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.6 |  |  |  |  | Programme support for PP Business Change activities | 100% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
3 | 1.11.6 |  |  |  |  | Transition to New Settlement Timetable (M16) | 7% | Wed 22/10/25 | Thu 23/12/27 | 566 days | Wed 22/10/25 | Thu 23/12/27 | 1 day | 0 days | 6 days | N/A |  | 6.34 | Yes
4 | 1.11.6.1 |  |  |  |  | Elexon to produce Settlement Calendar for Settlement Year 2025/2026 | 100% | Wed 22/10/25 | Wed 22/10/25 | 0 days | Wed 22/10/25 | Wed 22/10/25 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes
4 | 1.11.6.2 |  |  |  |  | Elexon monitor settlement data of migrated MPANs | 9% | Thu 23/10/25 | Thu 24/06/27 | 436 days | Thu 23/10/25 | Thu 24/06/27 | 0 days | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.3 |  | T2-MR-0400 |  |  | M16 Checkpoint 1 | 0% | Thu 25/06/26 | Thu 25/06/26 | 0 days | Thu 25/06/26 | Thu 25/06/26 | 1 day | 0 days | 0 days | SRO |  | 6.42 | Yes |  | 28/01/26 - The milestone ID T2-MR-0400 has been added to reflect the 'Requirements for the Transition to the new MHHS Settlement Timetable - MHHS Programme' document, which was published in 2025
4 | 1.11.6.4 |  |  |  |  | Confirm if M16 date retained as 07/12/2026 | 0% | Thu 23/07/26 | Thu 23/07/26 | 0 days | Thu 23/07/26 | Thu 23/07/26 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.5 |  |  |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | Thu 20/08/26 | Thu 20/08/26 | 0 days | Thu 20/08/26 | Thu 20/08/26 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.6 |  |  |  |  | Elexon to produce Settlement Calendar for Settlement Year 2026 up until day before M16 cutover | 0% | Mon 19/10/26 | Mon 19/10/26 | 0 days | Mon 19/10/26 | Mon 19/10/26 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.7 |  |  |  |  | M16 Checkpoint 2 | 0% | Fri 02/04/27 | Fri 02/04/27 | 0 days | Fri 02/04/27 | Fri 02/04/27 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.8 |  |  |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | Mon 19/04/27 | Mon 19/04/27 | 0 days | Mon 19/04/27 | Mon 19/04/27 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.9 | T2 | T2-EL-0100 | PSG/BSC PAB |  | Confirm M16 Date | 0% | Fri 30/04/27 | Fri 30/04/27 | 0 days | Fri 30/04/27 | Fri 30/04/27 | 1 day | 0 days | -1 day | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.10 |  |  |  |  | Raise fast track change to ISD (November publish) | 0% | Fri 30/04/27 | Fri 30/04/27 | 0 days | Fri 30/04/27 | Fri 30/04/27 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes |  | 14/01/26 - This activity is the responsibility of SRO, updated to reflect this.
4 | 1.11.6.11 |  |  |  |  | M16 Approval Window | 0% | Fri 25/06/27 | Thu 23/12/27 | 129 days | Fri 25/06/27 | Thu 23/12/27 | 1 day | 0 days | 5 days | SRO |  | 6.34 | Yes
5 | 1.11.6.11.1 |  |  |  |  | Panel approval that M16 criteria met | 0% | Fri 25/06/27 | Fri 25/06/27 | 0 days | Fri 25/06/27 | Fri 25/06/27 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes
5 | 1.11.6.11.2 | T1 | T1-EL-1000 | PSG |  | Cut over to new settlement timetable (M16) | 0% | Fri 02/07/27 | Fri 02/07/27 | 0 days | Fri 02/07/27 | Fri 02/07/27 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes
5 | 1.11.6.11.3 |  |  |  |  | Maximum 6-month window for approval of M16 | 0% | Mon 05/07/27 | Thu 23/12/27 | 124 days | Mon 05/07/27 | Thu 23/12/27 | 0 days | 0 days | 0 days | SRO |  | 6.34 | Yes
5 | 1.11.6.11.4 | T1 | T1-EL-2000 | PSG |  | Cut over to new settlement timetable (M16*) - Late Exit | 0% | Thu 23/12/27 | Thu 23/12/27 | 0 days | Thu 23/12/27 | Thu 23/12/27 | 1 day | 0 days | 0 days | SRO |  | 6.34 | Yes
2 | 1.12 |  |  |  |  | EARLY LIVE RUNNING | 0% | Mon 10/05/27 | Fri 09/07/27 | 45 days | Mon 10/05/27 | Fri 09/07/27 | 0 days | 0 days | -844 days | N/A |  |  | Yes
3 | 1.12.1 |  |  |  |  | Early Live Running Stabilisation Period | 0% | Mon 10/05/27 | Fri 09/07/27 | 45 days | Mon 10/05/27 | Fri 09/07/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.1.1 |  |  |  |  | Manage Early Live Running stabilisation period | 0% | Mon 10/05/27 | Fri 09/07/27 | 45 days | Mon 10/05/27 | Fri 09/07/27 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.12.1.2 |  |  |  |  | Monitor Early Live Running stabilisation period | 0% | Mon 10/05/27 | Fri 09/07/27 | 45 days | Mon 10/05/27 | Fri 09/07/27 | 0 days | 0 days | 0 days | Migration |  | 5 | Yes
2 | 1.13 |  |  |  |  | PROGRAMME CLOSURE | 0% | Mon 08/03/27 | Fri 25/06/27 | 80 days | Mon 08/03/27 | Fri 25/06/27 | 0 days | 0 days | -5 days | N/A |  |  | Yes
3 | 1.13.1 |  |  |  |  | Handover Pack | 0% | Mon 08/03/27 | Fri 25/06/27 | 80 days | Mon 08/03/27 | Fri 25/06/27 | 0 days | 0 days | -5 days | N/A |  | 5 | Yes
4 | 1.13.1.1 |  |  |  |  | Draft Handover Pack (for M15) | 0% | Mon 08/03/27 | Fri 30/04/27 | 40 days | Mon 08/03/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.13.1.1.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
5 | 1.13.1.1.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.13.1.1.3 |  |  |  | MHHS-ART126 | Draft Handover Pack approved | 0% | Fri 30/04/27 | Fri 30/04/27 | 0 days | Fri 30/04/27 | Fri 30/04/27 | 1 day | 0 days | 0 days | SRO |  | 5 | Yes
4 | 1.13.1.2 |  |  |  |  | Master Handover Pack (for M16) | 0% | Mon 03/05/27 | Fri 25/06/27 | 40 days | Mon 03/05/27 | Fri 25/06/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.13.1.2.1 |  |  |  |  | Update document | 0% | Mon 03/05/27 | Fri 28/05/27 | 20 days | Mon 03/05/27 | Fri 28/05/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
5 | 1.13.1.2.2 |  |  |  |  | Document review and update | 0% | Mon 31/05/27 | Fri 25/06/27 | 20 days | Mon 31/05/27 | Fri 25/06/27 | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.13.1.2.3 |  |  |  | MHHS-ART126 | Master Handover Pack approved | 0% | Fri 25/06/27 | Fri 25/06/27 | 0 days | Fri 25/06/27 | Fri 25/06/27 | 1 day | 0 days | 0 days | SRO |  | 5 | Yes
3 | 1.13.2 |  |  |  |  | Programme Lessons Learned | 0% | Mon 08/03/27 | Fri 30/04/27 | 40 days | Mon 08/03/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.2.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.13.2.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
4 | 1.13.2.3 |  |  |  | MHHS-ART131 | Programme Lessons Learned document approved | 0% | Fri 30/04/27 | Fri 30/04/27 | 0 days | Fri 30/04/27 | Fri 30/04/27 | 1 day | 0 days | 0 days | SRO |  | 5 | Yes
3 | 1.13.3 |  |  |  |  | Programme Closure Report | 0% | Mon 08/03/27 | Fri 30/04/27 | 40 days | Mon 08/03/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.3.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.13.3.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
4 | 1.13.3.3 |  |  |  | MHHS-ART130 | Programme Closure Report approved | 0% | Fri 30/04/27 | Fri 30/04/27 | 0 days | Fri 30/04/27 | Fri 30/04/27 | 1 day | 0 days | 0 days | Ofgem |  | 5 | Yes
3 | 1.13.4 |  |  |  |  | Benefit Realisation Report | 0% | Mon 08/03/27 | Fri 07/05/27 | 45 days | Mon 08/03/27 | Fri 07/05/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.4.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.13.4.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.13.4.3 | T3 | T3-PC-0010 | PSG | MHHS-ART124 | Benefit Realisation Report approved | 0% | Fri 07/05/27 | Fri 07/05/27 | 0 days | Fri 07/05/27 | Fri 07/05/27 | 1 day | 0 days | 0 days | PMO |  | 5 | Yes
3 | 1.13.5 |  |  |  |  | Operating Model Gap Review with recommendations | 0% | Mon 08/03/27 | Fri 07/05/27 | 45 days | Mon 08/03/27 | Fri 07/05/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.5.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.13.5.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.13.5.3 | T3 | T3-PC-0020 | DAG | MHHS-ART128 | Operating Model Gap Review with recommendations approved | 0% | Fri 07/05/27 | Fri 07/05/27 | 0 days | Fri 07/05/27 | Fri 07/05/27 | 1 day | 0 days | 0 days | Paul Pettitt |  | 5 | Yes
3 | 1.13.6 |  |  |  |  | Post-Implementation Review | 0% | Mon 08/03/27 | Fri 07/05/27 | 45 days | Mon 08/03/27 | Fri 07/05/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.6.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.13.6.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.13.6.3 | T3 | T3-PC-0030 | PSG | MHHS-ART129 | Post-Implementation Review approved | 0% | Fri 07/05/27 | Fri 07/05/27 | 0 days | Fri 07/05/27 | Fri 07/05/27 | 1 day | 0 days | 0 days | PMO |  | 5 | Yes
3 | 1.13.7 |  |  |  |  | Reinforcement Guide | 0% | Mon 08/03/27 | Fri 07/05/27 | 45 days | Mon 08/03/27 | Fri 07/05/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.7.1 |  |  |  |  | Develop document | 0% | Mon 08/03/27 | Fri 02/04/27 | 20 days | Mon 08/03/27 | Fri 02/04/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.13.7.2 |  |  |  |  | Document review and update | 0% | Mon 05/04/27 | Fri 30/04/27 | 20 days | Mon 05/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.13.7.3 | T3 | T3-PC-0040 | PSG | MHHS-ART133 | Reinforcement Guide approved | 0% | Fri 07/05/27 | Fri 07/05/27 | 0 days | Fri 07/05/27 | Fri 07/05/27 | 1 day | 0 days | 0 days | PMO |  | 5 | Yes
3 | 1.13.8 |  |  |  |  | Material and Licenses Transfer | 0% | Mon 05/04/27 | Fri 25/06/27 | 60 days | Mon 05/04/27 | Fri 25/06/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.8.1 |  |  |  | MHHS-ART139 | Transfer of Programme material to Elexon and perpetual licenses as appropriate | 0% | Mon 05/04/27 | Fri 25/06/27 | 60 days | Mon 05/04/27 | Fri 25/06/27 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
2 | 1.14 |  |  |  |  | READINESS ASSESSMENTS | 47% | Tue 05/09/23 | Thu 17/06/27 | 988 days | Tue 05/09/23 | Thu 17/06/27 | 0 days | 0 days | 139 days | N/A |  |  | Yes
3 | 1.14.1 |  |  |  |  | Readiness Assessment 3 - Design and Build Progress Check and CP2 Check | 100% | Tue 05/09/23 | Mon 27/11/23 | 60 days | Tue 05/09/23 | Mon 27/11/23 | 0 days | 0 days | 10 days | N/A |  | 5.5 | Yes
4 | 1.14.1.1 |  |  |  |  | Launch Readiness Assessment survey | 100% | Tue 05/09/23 | Tue 05/09/23 | 0 days | Tue 05/09/23 | Tue 05/09/23 | 0 days | -1 day | 0 days | PPC |  | 5.5 | Yes
4 | 1.14.1.2 |  |  |  |  | PPs submit survey responses | 100% | Tue 05/09/23 | Mon 25/09/23 | 15 days | Tue 05/09/23 | Mon 25/09/23 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
4 | 1.14.1.3 |  |  |  |  | Analyse survey responses | 100% | Tue 26/09/23 | Mon 16/10/23 | 15 days | Tue 26/09/23 | Mon 16/10/23 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes
4 | 1.14.1.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 100% | Tue 26/09/23 | Mon 16/10/23 | 15 days | Tue 26/09/23 | Mon 16/10/23 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes
4 | 1.14.1.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 100% | Tue 17/10/23 | Mon 20/11/23 | 25 days | Tue 17/10/23 | Mon 20/11/23 | 0 days | 0 days | 10 days | PPC |  | 5.5 | Yes
4 | 1.14.1.6 | T2 | T2-RA-0200 | PSG |  | Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | 100% | Mon 27/11/23 | Mon 27/11/23 | 0 days | Mon 27/11/23 | Mon 27/11/23 | 1 day | 0 days | 0 days | CPT |  | 5.13 | Yes
3 | 1.14.2 |  |  |  |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check | 100% | Mon 28/04/25 | Tue 01/07/25 | 47 days | Mon 21/04/25 | Tue 24/06/25 | 5 days | 5 days | -2 days | N/A |  | 6.18 | Yes
4 | 1.14.2.1 |  |  |  |  | Launch Readiness Assessment survey | 100% | Mon 28/04/25 | Mon 28/04/25 | 0 days | Mon 28/04/25 | Mon 28/04/25 | 0 days | -1 day | 0 days | PPC |  | 6.18 | Yes
4 | 1.14.2.2 |  |  |  |  | PPs submit survey responses | 100% | Mon 28/04/25 | Fri 16/05/25 | 15 days | Mon 28/04/25 | Fri 16/05/25 | 0 days | 0 days | 0 days | PP |  | 6.18 | Yes
4 | 1.14.2.3 |  |  |  |  | Analyse survey responses | 100% | Mon 19/05/25 | Fri 27/06/25 | 30 days | Mon 19/05/25 | Fri 27/06/25 | 0 days | 0 days | 15 days | PPC |  | 6.18 | Yes
4 | 1.14.2.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 100% | Mon 19/05/25 | Fri 27/06/25 | 30 days | Mon 19/05/25 | Fri 27/06/25 | 0 days | 0 days | 15 days | PPC |  | 6.18 | Yes
4 | 1.14.2.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 100% | Mon 09/06/25 | Fri 27/06/25 | 15 days | Mon 09/06/25 | Fri 27/06/25 | 0 days | 0 days | 0 days | PPC |  | 6.18 | Yes
4 | 1.14.2.6 | T2 | T2-RA-0400 | PSG |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check (incl. Readiness Assessment Report approval) Completed | 100% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
3 | 1.14.3 |  |  |  |  | Readiness Assessment 7 - Migration Checkpoint | 0% | Mon 12/01/26 | Thu 19/03/26 | 49 days | Mon 12/01/26 | Thu 19/03/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.3.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Mon 12/01/26 | Mon 12/01/26 | 0 days | -1 day | 0 days | PPC |  | 5 | Yes
4 | 1.14.3.2 |  |  |  |  | PPs submit survey responses | 0% | Mon 12/01/26 | Fri 30/01/26 | 15 days | Mon 12/01/26 | Fri 30/01/26 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.14.3.3 |  |  |  |  | Analyse survey responses | 0% | Mon 02/02/26 | Fri 20/02/26 | 15 days | Mon 02/02/26 | Fri 20/02/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.3.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Mon 02/02/26 | Fri 20/02/26 | 15 days | Mon 02/02/26 | Fri 20/02/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.3.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Mon 23/02/26 | Fri 13/03/26 | 15 days | Mon 23/02/26 | Fri 13/03/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.3.6 | T2 | T2-RA-0600 | PSG |  | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 19/03/26 | Thu 19/03/26 | 0 days | Thu 19/03/26 | Thu 19/03/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.4 |  |  |  |  | Readiness Assessment 8 - Ready to Accept New MPANs | 0% | Thu 06/08/26 | Tue 13/10/26 | 49 days | Thu 06/08/26 | Tue 13/10/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.4.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Thu 06/08/26 | Thu 06/08/26 | 0 days | Thu 06/08/26 | Thu 06/08/26 | 0 days | -1 day | 0 days | PPC |  | 5 | Yes
4 | 1.14.4.2 |  |  |  |  | PPs submit survey responses | 0% | Thu 06/08/26 | Wed 26/08/26 | 15 days | Thu 06/08/26 | Wed 26/08/26 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.14.4.3 |  |  |  |  | Analyse survey responses | 0% | Thu 27/08/26 | Wed 16/09/26 | 15 days | Thu 27/08/26 | Wed 16/09/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.4.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Thu 27/08/26 | Wed 16/09/26 | 15 days | Thu 27/08/26 | Wed 16/09/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.4.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Thu 17/09/26 | Wed 07/10/26 | 15 days | Thu 17/09/26 | Wed 07/10/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.4.6 | T2 | T2-RA-0700 | PSG |  | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | Tue 13/10/26 | Tue 13/10/26 | 0 days | Tue 13/10/26 | Tue 13/10/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.5 |  |  |  |  | Readiness Assessment 9 - Ready for New Settlement Timetable and CP5 Check | 0% | Mon 12/04/27 | Thu 17/06/27 | 49 days | Mon 12/04/27 | Thu 17/06/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.5.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Mon 12/04/27 | Mon 12/04/27 | 0 days | Mon 12/04/27 | Mon 12/04/27 | 0 days | -1 day | 0 days | PPC |  | 5 | Yes
4 | 1.14.5.2 |  |  |  |  | PPs submit survey responses | 0% | Mon 12/04/27 | Fri 30/04/27 | 15 days | Mon 12/04/27 | Fri 30/04/27 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.14.5.3 |  |  |  |  | Analyse survey responses | 0% | Mon 03/05/27 | Fri 21/05/27 | 15 days | Mon 03/05/27 | Fri 21/05/27 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.5.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Mon 03/05/27 | Fri 21/05/27 | 15 days | Mon 03/05/27 | Fri 21/05/27 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.5.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Mon 24/05/27 | Fri 11/06/27 | 15 days | Mon 24/05/27 | Fri 11/06/27 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.14.5.6 | T2 | T2-RA-0800 | PSG |  | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 17/06/27 | Thu 17/06/27 | 0 days | Thu 17/06/27 | Thu 17/06/27 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.6 |  |  |  |  | Readiness Assessments - Tier 1 Milestones | 0% | Tue 01/07/25 | Thu 17/06/27 | 512 days | Tue 24/06/25 | Thu 17/06/27 | 6 days | 0 days | -287 days | N/A |  | 5 | Yes
4 | 1.14.6.1 | T2 | T2-RA-0500 | PSG |  | Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | 100% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 | 1 day | 0 days | 0 days | CPT |  | 6.18 | Yes
4 | 1.14.6.2 | T2 | T2-RA-0600 | PSG |  | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 19/03/26 | Thu 19/03/26 | 0 days | Thu 19/03/26 | Thu 19/03/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.14.6.3 | T2 | T2-RA-0700 | PSG |  | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | Tue 13/10/26 | Tue 13/10/26 | 0 days | Tue 13/10/26 | Tue 13/10/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.14.6.4 | T2 | T2-RA-0800 | PSG |  | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 17/06/27 | Thu 17/06/27 | 0 days | Thu 17/06/27 | Thu 17/06/27 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
2 | 1.15 |  |  |  |  | CONTROL POINTS | 79% | Thu 10/11/22 | Wed 23/06/27 | 1204 days | Thu 10/11/22 | Wed 23/06/27 | 0 days | -1 day | 141 days | N/A |  |  | Yes
3 | 1.15.1 |  |  |  |  | Control Point 1 - Start of System Design, Build & Test | 100% | Thu 10/11/22 | Wed 07/12/22 | 20 days | Thu 10/11/22 | Wed 07/12/22 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.15.1.1 |  |  |  |  | Control Point 1 Preparation (incl. Control Point Report development and review) | 100% | Thu 10/11/22 | Wed 30/11/22 | 15 days | Thu 10/11/22 | Wed 30/11/22 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.15.1.2 | T1 | T1-CP-1000 | PSG |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.15.2 |  |  |  |  | Control Point 2 - Start of Integration & Test | 100% | Mon 02/10/23 | Mon 30/10/23 | 20 days | Mon 02/10/23 | Mon 30/10/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.15.2.1 |  |  |  |  | Control Point 2 Preparation (incl. Control Point Report development and review) | 100% | Mon 02/10/23 | Fri 20/10/23 | 15 days | Mon 02/10/23 | Fri 20/10/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.15.2.2 | T1 | T1-CP-2000 | PSG |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 0 days | -1 day | 0 days | CPT |  | 5.11 | Yes
3 | 1.15.3 |  |  |  |  | Control Point 3/4 - Readiness for Migration | 100% | Thu 21/08/25 | Wed 24/09/25 | 25 days | Thu 21/08/25 | Thu 18/09/25 | 0 days | 4 days | 5 days | N/A |  | 5 | Yes
4 | 1.15.3.1 |  |  |  |  | Control Point 3/4 Preparation (incl. Control Point Report development and review) | 100% | Thu 21/08/25 | Wed 24/09/25 | 25 days | Thu 21/08/25 | Tue 09/09/25 | 0 days | 11 days | 11 days | CPT |  | 5 | Yes
4 | 1.15.3.2 | T1 | T1-CP-3000 | PSG |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Thu 18/09/25 | Thu 18/09/25 | 5 days | 4 days | 0 days | CPT |  | 5 | Yes
3 | 1.15.4 |  |  |  |  | Control Point 5 - Cut Over to New Settlement Timetable | 0% | Wed 26/05/27 | Wed 23/06/27 | 20 days | Wed 26/05/27 | Wed 23/06/27 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.15.4.1 |  |  |  |  | Control Point 5 Preparation (incl. Control Point Report development and review) | 0% | Wed 26/05/27 | Tue 15/06/27 | 15 days | Wed 26/05/27 | Tue 15/06/27 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.15.4.2 | T1 | T1-CP-4000 | PSG |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | Wed 23/06/27 | Wed 23/06/27 | 0 days | Wed 23/06/27 | Wed 23/06/27 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.15.5 |  |  |  |  | Control Points - Tier 1 Milestones | 0% | Wed 07/12/22 | Wed 23/06/27 | 1184 days | Wed 07/12/22 | Wed 23/06/27 | 1 day | -1 day | 141 days | N/A |  | 5 | Yes
4 | 1.15.5.1 | T1 | T1-CP-1000 | PSG |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.15.5.2 | T1 | T1-CP-2000 | PSG |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 0 days | -1 day | 0 days | CPT |  | 5.11 | Yes
4 | 1.15.5.3 | T1 | T1-CP-3000 | PSG |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 100% | Wed 24/09/25 | Wed 24/09/25 | 0 days | Thu 18/09/25 | Thu 18/09/25 | 5 days | 4 days | 0 days | CPT |  | 5 | Yes
4 | 1.15.5.4 | T1 | T1-CP-4000 | PSG |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | Wed 23/06/27 | Wed 23/06/27 | 0 days | Wed 23/06/27 | Wed 23/06/27 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
2 | 1.16 |  |  |  |  | MILESTONE RANGE CHECKPOINTS | 0% | Mon 31/10/22 | Mon 12/04/27 | 1160 days? | Mon 31/10/22 | Mon 12/04/27 | 0 days | -1 day | 724 days? | N/A |  |  | Yes
3 | 1.16.1 |  |  |  |  | M10, M11, M12 and M13 milestone checkpoint | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.16.1.1 | T2 | T2-MR-0100 | PSG |  | M10, M11, M12, and M13 milestone checkpoint - date approval | 100% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.16.2 |  |  |  |  | M14 milestone checkpoint | 0% | Thu 06/08/26 | Thu 06/08/26 | 0 days | Thu 06/08/26 | Thu 06/08/26 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.16.2.1 | T2 | T2-MR-0200 | PSG |  | M14 milestone checkpoint - date approval | 0% | Thu 06/08/26 | Thu 06/08/26 | 0 days | Thu 06/08/26 | Thu 06/08/26 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.16.3 |  |  |  |  | M15 milestone checkpoint | 0% | Mon 15/02/27 | Mon 15/02/27 | 0 days | Mon 15/02/27 | Mon 15/02/27 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.16.3.1 | T2 | T2-MR-0300 | PSG |  | M15 milestone checkpoint - date approval | 0% | Mon 15/02/27 | Mon 15/02/27 | 0 days | Mon 15/02/27 | Mon 15/02/27 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.16.4 |  |  |  |  | M16 milestone checkpoint | 0% | Mon 31/10/22 | Mon 12/04/27 | 1160 days? | Mon 31/10/22 | Mon 12/04/27 | 0 days | -1 day | 1160 days? | N/A |  | 5 | Yes
4 | 1.16.4.1 | T2 | T2-MR-0400 | PSG |  | M16 milestone checkpoint - date approval | 0% | Mon 12/04/27 | Mon 12/04/27 | 0 days | Mon 12/04/27 | Mon 12/04/27 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes