## Coversheet
MHHS-DEL3434 - Facilitating Engagement between Suppliers and Agents Central Register
Document owner: |  | Programme Qualification workstream
Version: |  | 17
Status: |  | Published
Date: |  | 13-Oct-2026
Classification: |  | Public
Useful Context / background:
At the Qualification Working Group (QWG) in June 2024, the Programme took an action to explore how it can support engagement between Suppliers and Customer Appointed Agents so they can better understand Qualification and Migration plans.
The Programme proposed publishing a central register for participants who opt in and consent to information they have provided being shared on the MHHS communications channels (the MHHS website and Collaboration Base), including:
- Qualification Wave allocation (for non-SIT Suppliers & Agents)
- Qualification key contacts (for non-SIT Suppliers & Agents)
- Anticipated Migration start date (for Suppliers)
- Migration key contacts (for Suppliers)
Following participant feedback, at December's QWG, participants were given the opportunity to share their views as to whether this information should be made available to all participants or only those who opt in and consent to their information being shared.
The consensus was that the information should be made available to all participants rather than a restricted audience.
Therefore, at December's Qualification Advisory Group (QAG), the Programme proposed that the Senior Responsible Officer (SRO) approve that published Qualification and Migration information from Suppliers and Agents is made available to all participants.
This decision was approved by the SRO.
Guidance note:
This central register contains Qualification and Migration information for those parties who have opted in and provided consent for their information to be shared.
The Programme intends to regularly update the information held in this register to ensure it is accurate and up to date. Updates will be made in alignment with Migration Planning cycles to reflect changes to participant's anticipated Migration start dates submitted to the Migration Control Centre (MCC).
Participants who wish to opt in and consent to their information being shared in future iterations of the central register should provide the information requested in the 'Consent Form' tab and submit this to the PPC team at PPC@mmhsprogramme.co.uk.
Please note that providing information for publication as part of the central register remains optional and information will only be published for parties who have opted in and provided their consent.
In light of this, if for whatever reason you decide you no longer wish for your information to be published in the central register, please notify the PPC team by emailing PPC@mhhsprogramme.co.uk. In this instance the information will be removed and the central register updated and republished within 3 working days.
Participant's Qualification Wave allocation information will be based on Code Body inputs, whereas participant's anticipated Migration start date information will be based on MCC inputs provided by participants through the Migration Planning cycles
Please navigate to the 'Central Register' tab to access participant Qualification and Migration information.
Please navigate to the 'Coverage' tab to understand the coverage of participant Qualification and Migration information provided in the central register at the date of publishing.
Please note the information in this register provides a snapshot view of participant's Qualification and Migration information and is subject to change. This register has been published to help facilitate engagement between Suppliers and Agents in response to participant feedback, but the Programme will not be held accountable regarding the use of this information by participants to inform commercial decisions and arrangements
If you have any questions regarding the central register, please direct these to the PPC team at PPC@mhhsprogramme.co.uk.

## Coverage
MHHS-DEL3434 - Facilitating Engagement between Suppliers and Agents Central Register

## Central Register
MHHS-DEL3434 - Facilitating Engagement between Suppliers and Agents Central Register
Organisation | Supplier or Agent |  | Type of Agent | Qualification Wave allocation | Qualification Key Contacts | Contact Details | Proposed Migration Start Date | Migration Key Contacts | Contact Details
F&S Energy Limited | Supplier |  | N/A - Supplier | Wave 4 | Imtiaaz Sali Ralph Azagoh-Kouadio Rachel Sullivan | imtiaaz.sali@fs-energy.co.uk ralph.azagoh-kouadio@fs-energy.co.uk rachel.sullivan@fs-energy.co.uk | 2027-01-04 | Imtiaaz Sali Ralph Azagoh-Kouadio Rachel Sullivan | imtiaaz.sali@fs-energy.co.uk ralph.azagoh-kouadio@fs-energy.co.uk rachel.sullivan@fs-energy.co.uk
Tym Huckin Limited | Agent |  | Unmetered Supplies Data Service | N/A - SIT participant | Tym Huckin | thuckin@stark.co.uk | N/A - Agent | N/A - Agent | N/A - Agent
Vattenfall Energy Trading GmbH | Supplier |  | N/A - Supplier | Wave 4 | Dipedndra Singh Janne Niklas Breyer Katrin Willuhn | dipendra.singh@vattenfall.de janneniklas.breyer@vattenfall.de katrin.willuhn@vattenfall.com | 2026-10-19 | Dipedndra Singh Janne Niklas Breyer Katrin Willuhn | dipendra.singh@vattenfall.de janneniklas.breyer@vattenfall.de katrin.willuhn@vattenfall.com
Yorkshire Gas and Power / EE Solutions | Supplier |  | N/A - Supplier | Wave 4 | Robert Johnston | robert.johnson@ygp.co.uk | 2026-10-28 | Jake Walker Ally Brown Robert Johnson | jake.w@ygp.co.uk ally.brown@ygp.co.uk robert.johnson@ygp.co.uk
Noriker / Equinicity | Supplier |  | N/A - Supplier | Wave 4 | Henry Choong Matthew Stell | henryc@noriker.co.uk matts@noriker.co.uk | 2026-09-19 | Henry Choong Matthew Stell | henryc@noriker.co.uk matts@noriker.co.uk
SmartestEnergy Business Limited | Supplier |  | N/A - Supplier | Wave 4 | Nicola Butcher Sophie Enes James Rippon | nicola-butcher@smartestenergy.com sophie-enes@smartestenergy.com james-ripon@smartestenergy.com | 2026-10-26 | Nicola Butcher Sophie Enes James Rippon | nicola-butcher@smartestenergy.com sophie-enes@smartestenergy.com james-ripon@smartestenergy.com
Itron Metering Solutions UK Limited | Agent |  | Advanced Data Services | N/A - SIT participant | Lewis Paine Darren Meek | lewis.paine@itron.com Darren.meek@itron.com | N/A - Agent | N/A - Agent | N/A - Agent
Octopus Energy Limited | Supplier |  | N/A - Supplier | N/A - SIT participant | Lijo Louis Carl Bourn | lijo.louis@octoenergy.com carl.bourn@octoenergy.com | 2025-10-22 | Lijo Louis Carl Bourn | lijo.louis@octoenergy.com carl.bourn@octoenergy.com
Crown Gas and Power | Supplier |  | N/A - Supplier | Wave 3 | Peter Powell Jonathan Matthews Zaahir Ismael | peter.powell@crowngas.co.uk jonathan.matthews@crowngas.co.uk zaahir.ismael@crowngas.co.uk | 2026-08-10 | Peter Powell Jonathan Matthews Zaahir Ismael | peter.powell@crowngas.co.uk jonathan.matthews@crowngas.co.uk zaahir.ismael@crowngas.co.uk
SSE Energy Supply Limited | Supplier |  | N/A - Supplier | Wave 1 | Elaine Green Mark Jones | elaine.green@sse.com mark.jones@sse.com | 2026-09-07 | Emily Luke Alex Persse Vinay Jaiswal | emily.luke@sse.com alex.persse@sse.com vinay.jaiswal@sse.com
Jellyfish Energy / Switch Business Gas and Power | Supplier |  | N/A - Supplier | Wave 4 | Jordan Armstrong Aidon Hudson | Jordan.armstrong@jellyfish.energy Aidon.hudson@jellyfish.energy | 2026-11-02 | Jordan Armstrong Aidon Hudson | Jordan.armstrong@jellyfish.energy Aidon.hudson@jellyfish.energy
Evolve Energy Supply Limited | Supplier |  | N/A - Supplier | Wave 3 | Harrison Clark Lyndsey Antrobus | harrison.clark@bpgenergy.com lyndsey.antrobus@bpgenergy.com | 2026-08-01 | Harrison Clark Lyndsey Antrobus | harrison.clark@bpgenergy.com lyndsey.antrobus@bpgenergy.com
Unify Energy Limited | Supplier |  | N/A - Supplier | N/A - SIT participant | - | - | 2026-02-04 | - | -
E.ON Next | Supplier |  | N/A - Supplier | N/A - SIT participant | Cathy Mulliss Naomi Walker | cathy.mulliss@eonnext.com naomi.walker@eonnext.com | 2025-10-22 | Richard Gwatkin Lucy Marshall Molly O'Driscoll | Richard.Gwatkin@eon-uk.com lucy.marshall@eonnext.com molly.odriscoll@eonnext.com
M Group Energy Data Insight (preiously known as Callisto) | Agent |  | Advanced Data Services Smart Data Services Metering Services Advanced Metering Services Smart | N/A - SIT participant | Simon Harrison | simon.harrison@callisto.co.uk | N/A - Agent | Katie Barber Kristina Evering | katie.barber@callisto.co.uk kristina.evering@callisto.co.uk
Energy Assets | Agent |  | Advanced Data Services Smart Data Services Metering Services Advanced Metering Services Smart | Wave 1 | Martin Thomasson Greg Neil | martinthomasson@energyassets.co.uk gregneil@energyassets.co.uk | N/A - Agent | N/A - Agent | N/A - Agent
Flexitricity | Supplier |  | N/A - Supplier | Wave 3 | - | - | 2026-09-01 | - | -
IMServ Europe Ltd | Agent |  | Advanced Data Services Smart Data Services Metering Services Advanced Metering Services Smart | N/A - SIT participant | Central mailbox Clare Hannah | MHHS@imserv.com clare.hannah@imserv.com | N/A - Agent | N/A - Agent | N/A - Agent
Power Data Associates Limited | Agent |  | Unmetered Supplies Data Service | N/A - SIT participant | Central mailbox Clare Hannah | MHHS@imserv.com clare.hannah@imserv.com | N/A - Agent | N/A - Agent | N/A - Agent
Bryt Energy Limited | Supplier |  | N/A - Supplier | Wave 3 | Heidi Wilbor Simon Moore | Heidi.Wilbor@brytenergy.co.uk Simon.Moore@brytenergy.co.uk | 2026-08-18 | Heidi Wilbor Simon Moore | Heidi.Wilbor@brytenergy.co.uk Simon.Moore@brytenergy.co.uk
British Gas Trading Limited (BIZZ) | Supplier |  | N/A - Supplier | Wave 3 | Adam Iles Catherine Chapman (Non-SIT Qual) Shazia Toqeer (SIT Qual) | adam.iles@centrica.com catherine.chapman@britishgas.co.uk shazia.toqeer@britishgas.co.uk | 2026-09-04 | Neil Strange Adam Iles | neil.strange@britishgas.co.uk adam.iles@centrica.com
Good Energy Limited | Supplier |  | N/A - Supplier | Wave 4 | Kerry Clarke-Smith Kai Preston Liz Kelf | kerry.clarkesmith@goodenergy.co.uk kai.preston@goodenergy.co.uk liz.kelf@goodenergy.co.uk | 2026-10-27 | Kerry Clarke-Smith Kai Preston Liz Kelf | kerry.clarkesmith@goodenergy.co.uk kai.preston@goodenergy.co.uk liz.kelf@goodenergy.co.uk
OVO Energy | Supplier |  | N/A - Supplier | Wave 2 | Chris Butterfield Katie Arcari | chris.butterfield@ovo.com katie.m.odonnell@ovo.com | 2026-05-20 | Steph Keenan Lucy Miles Dom Bradbury | steph.keenan@ovo.com lucy.miles@ovo.com dom.bradbury@ovo.com
OVO Energy | Agent |  | Metering Services Smart | N/A - SIT participant | Chris Butterfield Katie Arcari | chris.butterfield@ovo.com katie.m.odonnell@ovo.com | 2026-06-09 | Lucy Miles Dom Bradbury | lucy.miles@ovo.com dom.bradbury@ovo.com
Eneco Energy Trade / Eneco UK | Supplier |  | N/A - Supplier | Wave 4 | Henry Goossens Finlay Parsons Nigel McManus | henry.goossens@eneco.com finlay.parsons@eneco.com Nigel.McManus@eneco.com | 2026-10-26 | Henry Goossens Finlay Parsons Nigel McManus | henry.goossens@eneco.com finlay.parsons@eneco.com Nigel.McManus@eneco.com
Ecotricity | Supplier |  | N/A - Supplier | Wave 4 | Ben Free | ben.free@ecotricity.co.uk | 2026-10-26 | Ben Free | ben.free@ecotricity.co.uk
Home Energy Trading | Supplier |  | N/A - Supplier | Wave 3 | Simon Dowse Neha Minocha James Doyle | Simon.Dowse@outfox.energy PMO@redfish.com James.Doyle@redfishuk.com | 2026-08-14 | Simon Dowse Neha Minocha James Doyle | Simon.Dowse@outfox.energy PMO@redfish.com James.Doyle@redfishuk.com
United Gas and Power | Supplier |  | N/A - Supplier | Wave 3 | Ben Wetherill Marta Kalanowksi Caroline Gundu | b.wetherill@ugp.co.uk m.kalinowska@ugp.co.uk c.gundu@ugp.co.uk | 2026-09-14 | Ben Wetherill Marta Kalanowksi Caroline Gundu | b.wetherill@ugp.co.uk m.kalinowska@ugp.co.uk c.gundu@ugp.co.uk
ENGIE | Supplier |  | N/A - Supplier | Wave 2 | Andrea Urbano Alex Parker | andrea.urbano@cgi.com alexander.parker@engie.com | 2026-10-19 | Andrea Urbano Alex Parker | andrea.urbano@cgi.com alexander.parker@engie.com
SMS Energy Services | Agent |  | Advanced Data Services Smart Data Services Metering Services Advanced Metering Services Smart | N/A - SIT participant | Kristina Leary Robert Langdon Helen Cloud | Kristina.Leary@smsenergy.com Robert.Langdon@smsenergy.com Helen.Cloud@smsenergyservices.com | N/A - Agent | N/A - Agent | N/A - Agent
SSE Digital Services Limited | Agent |  | Advanced Data Services Smart Data Services | Wave 1 | Owen Smith Tom Ching | Owen.Smith@sse.com Thomas.Ching@sse.com | N/A - Agent | N/A - Agent | N/A - Agent
Coulomb Energy Supply Limited | Supplier |  | N/A - Supplier | Wave 2 | Jo Winspur John Cook Charlotte Murray | jo.winspur@pxlimited.com john.cook@pxlimited.com charlotte.murray@pxlimited.com | 2026-07-01 | Jo Winspur John Cook Charlotte Murray | jo.winspur@pxlimited.com john.cook@pxlimited.com charlotte.murray@pxlimited.com
Callisto | Agent |  | Advanced Data Services Smart Data Services Metering Services Advanced Metering Services Smart | N/A - SIT participant | Simon Harrison John Macmillan | simonjohn.harrison@callisto.co.uk john.macmillan@callisto.co.uk | N/A - Agent | N/A - Agent | N/A - Agent
Stark | Agent |  | Advanced Data Services Smart Data Services Metering Services Advanced Metering Services Smart | N/A - SIT participant | James Murphy Jack Brewer | jmurphy@stark.co.uk jbrewer@stark.co.uk | N/A - Agent | N/A - Agent | N/A - Agent
npower Business Solutions | Supplier |  | N/A - Supplier | Wave 1 | Sarah Lewis | sarah.lewis@eonenergy.com | 2026-05-18 | Mark Pollard Chris Beasley | mark.pollard@eonenergy.com Christopher.Beasley@npower.com
EDF | Agent |  | Metering Services Advanced Data Services | N/A - SIT participant | Lee Northall Christian Hunter Julie Middleton | Lee.Northall@edfenergy.com Christian.Hunter@edfenergy.com Julie.Middleton@edfenergy.com | N/A - Agent | Rae Duke James Raven | Rachel.Duke@edfenergy.com James.Raven@edfenergy.com
EDF | Supplier |  | N/A - Supplier | Wave 2 | Lee Northall Christian Hunter Julie Middleton | Lee.Northall@edfenergy.com Christian.Hunter@edfenergy.com Julie.Middleton@edfenergy.com | 2026-05-18 | Rae Duke James Raven | Rachel.Duke@edfenergy.com James.Raven@edfenergy.com
EDF | Agent |  | Advanced Data Services Smart Data Services Metering Services Smart | Wave 2 | Lee Northall Christian Hunter Julie Middleton | Lee.Northall@edfenergy.com Christian.Hunter@edfenergy.com Julie.Middleton@edfenergy.com | N/A - Agent | N/A - Agent | N/A - Agent
TMA Data Management Ltd | Agent |  | Advanced Data Services Smart Data Services | N/A - SIT participant | Claire Henderson Clare Graham Neil Lamb Steve Wathen Vedat Agolli Keith Donaldson Pamela McInnes | Claire.Henderson@tma.co.uk Clare.Graham@tma.co.uk Neil.lamb@tma.co.uk Steven.wathen@tma.co.uk Vedat.agolli@tma.co.uk Keith.Donaldson@tma.co.uk Pamela.McInnes@tma.co.uk | N/A - Agent | N/A - Agent | N/A - Agent
Outfox the Market | Supplier |  | N/A - Supplier |  | Simon Dowse Neha Minocha James Doyle | Simon.Dowse@outfox.energy PMO@redfish.com James.Doyle@redfishuk.com | 2026-10-26 | Simon Dowse Neha Minocha James Doyle | Simon.Dowse@outfox.energy PMO@redfish.com James.Doyle@redfishuk.com
Smartest Energy Limited | Supplier |  | N/A - Supplier | Wave 3 | Paul Hastings Jono Liddell | paul-hastings@smartestenergy.com jono-liddell@smartestenergy.com MHHS-SEL@smartestenergy.com | 2026-10-20 | George Thomas Jono Liddell | George-Thomas@smartestenergy.com jono-liddell@smartestenergy.com MHHS-SEL@smartestenergy.com
So Energy | Supplier |  | N/A - Supplier | Wave 2 | Barry Obeng Craig Dickson | Barry.Obeng@so.energy Craig.Dickson@so.energy | 2026-07-01 | Barry Obeng Craig Dickson | Barry.Obeng@so.energy Craig.Dickson@so.energy
UC Energy | Supplier |  | N/A - Supplier | Wave 4 | Andrea McCutcheon Jonathan Grayson | A.McCutcheon@urbanchain.co.uk j.grayson@urbanchain.co.uk | 2026-10-12 | Andrea McCutcheon Jonathan Grayson | A.McCutcheon@urbanchain.co.uk j.grayson@urbanchain.co.uk

## Migration Lead Contacts
Name of your organisation | Your full name | Your email address
Axpo UK Limited | Brennon Lobo | brennon.lobo@axpo.com
BP GAS Marketing Limited | Robert Hutcherson | robert.hutcherson@bp.com
British Gas | Neil Strange | neil.strange@britishgas.co.uk
Bryt energy Ltd | Simon Moore | simon.moore@brytenergy.co.uk
NEAS Energy Limited | Rasmus Hyldgaard Hansen | rasmus.hansen@centrica.com
Conrad Energy Trading Limited | Jorgia Dexter | jorgia.dexter@conradenergy.co.uk
Corona Energy | Hannah Kharin | hannah.kharin@coronaenergy.co.uk
Coulomb Energy Supply Limited | Jo Winspur | Jo.winspur@pxlimited.com
Crown Gas and Power | Jonathan Matthews | jonathan.matthews@crowngasandpower.co.uk
Dgp Energy Ltd | Jaykesh Patel | j.patel@dgpenergy.com
Dyce Energy Limited | Matthew Cooke | matthew.cooke@dyce-energy.co.uk
E (Gas and Electricity) ltd. | Mark Treanor | mark.treanor@e.org
E E Solutions Limited T/A Yorkshire Gas and Power | MHHS INBOX | MHHS@ygp.co.uk
Ecotricity | Ben Free | ben.free@ecotricity.co.uk
EDF Energy | James Raven | james.raven@edfenergy.com
| Rachel Duke | rachel.duke@edfenergy.com
Edgware Energy Limited | Meriel Griffiths | meriel.griffiths@rwe.com
Engie | Phillip Thornton | phil.thornton@external.engie.com
E.on | Cathy Mulliss | Cathy.Mulliss@eonnext.com
Equinicity | Abigail Penny | abigailp@noriker.co.uk
Evolve Energy Supply Limited | Graham Templeton | Graham.templeton@evolve-energy.com
F&S Energy Limited | Ralph AZAGOH-KOUADIO | ralph.azagoh-kouadio@fs-energy.co.uk
Farringdon Energy | Joseph Beasley | joe.beasley@champion-energy.co.uk
Flextricity | Catriona Lindsay | catriona.lindsay@flexitricity.com
Good Energy Limited | Kerry Clarke-Smith | kerry.clarkesmith@goodenergy.co.uk
Green Energy (UK) trading as 100Green | Antonis Lamaj | Antonis.L@100green.com
Highland Electricity Limited | Gavin O'Neill | goneill@highlandelectricity.co.uk
Marble Power Limited | Sam Davies | sam.davies@marble-power.com
Maxen Power Supply Limited | Umair Mahmood | umair@maxenpower.com
MVV Environment Services Limited | Johannes Nowak | johannes.nowak@mvv.de
| Axel Gergel | axel.gergel@mvv.de
National Grid Electricity Distribution | Rachael Prosser | rprosser@nationalgrid.co.uk
Northern Powergrid | Catherine Carr | catherine.carr@northernpowergrid.com
Npower Commercial Gas Limited (npower Business Solutions – E.ON I&C) | Chris Beasley | Christopher.beasley@npower.com
Octopus Energy Limited | Carl Bourn | carl.bourn@octoenergy.com
OVO Energy | Chris Butterfield | chris.butterfield@ovo.com
| Dom Bradbury | dom.bradbury@ovo.com
| Ben Palmer | ben.palmer@ovo.com
| Lucy Miles | lucy.miles@ovo.com
Ruby Energy & Smart Choice Metering | Samuel Dynes | samuel.dynes@rubyenergy.uk
ScottishPower Energy Retail Ltd. | Stephen McLaughlin | s-mclaughlin@scottishpower.com
Smartest Energy Limited | George Thomas | George-Thomas@smartestenergy.com
Shell Energy | Sam Wilcock | S.Wilcock@shell.com
SmartestEnergy Business Limited | Nicola Butcher | nicola-butcher@smartestenergy.com
So Energy | Zoe Dickenson | zoe.dickenson@so.energy
SQE Energy (previously known as Squeaky Clean Energy) | Abeda Patel | abedapatel@sqe.energy
| Alessandro Caianiello | alessandrocaianiello@sqe.energy
SSE Energy Supply Limited | Alex Persse | alex.persse@sse.com
UC Energy Ltd | Andrea McCutcheon | a.mccutcheon@urbanchain.co.uk
UK Power Reserve Limited | Terence Freer | terence.freer@sembcorp.com
Unify Energy | Katie Thompson | katie.thompson@unifyenergy.co.uk
United Gas and Power Ltd | Ben Wetherill | b.wetherill@ugp.co.uk
Utility Warehouse | Bhavesh Patel | bpatel@uw.co.uk
Vattenfall Energy Trading GmbH | Katrin Willuhn | ppamanagement_uk@vattenfall.com
Yorkshire Gas & Power (E E Solutions Limited) | Colin Hollins | colin.hollins@ygp.co.uk
| Carl Lang | Carl.Lang@ygp.co.uk
| Mandy Meehan | mandy.meehan@ygp.co.uk

## Consent Form
MHHS-DEL3434 - Facilitating Engagement between Suppliers and Agents Central Register
Question |  | Response - participant to complete
Organisation name
Are you a Supplier or Agent Programme participant?
What type of Agent is your organisation?
Does your organisation consent to the publishing of your Migration start date via the MCC on the Programme comms channels (website and Collaboration Base)?
Does your organisation consent to your Qualification Wave allocation being published on the Programme comms channels?
Are your organisation's Migration key contacts the same as your Qualification key contacts?
If no or you are an Agent, please provide details of your Qualification key contacts (primary and secondary), including their full name, role and email address
Do you consent to your organisation's Qualification and Migration key contacts being published on the Programme comms channels?