## Outline Plan
Outline Level | WBS | Milestone Tier | Milestone ID | Approving Governance Forum | Artefact ID | Task Name | % Complete | Start | Finish | Duration | Baseline Start | Baseline Finish | Predecessors | Successors | Start Variance | Finish Variance | Duration Variance | Responsible | M/S Change Status | Update Version | Active | Resource Names | Notes
1 | 1 |  |  |  |  | PROGRAMME PLAN. | 51% | Mon 31/10/22 | Tue 26/08/49 | 33087 days? | Mon 31/10/22 | Fri 28/05/27 |  |  | 0 days | 31892 days | 31892 days? | N/A |  | 5 | Yes
2 | 1.1 |  |  |  |  | MHHS Programme Start | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 |  | 175 | 0 days | 0 days | 0 days | N/A |  | 5.7 | Yes
2 | 1.2 |  |  |  |  | PROGRAMME MANAGEMENT | 44% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
3 | 1.2.1 |  |  |  |  | Programme Management | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.1.1 |  |  |  |  | Sprint-based prioritisation planning and execution | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.2 |  |  |  |  | Programme governance secretariat | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.3 |  |  |  |  | RAID management and reporting | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.4 |  |  |  |  | Tracking against Programme outcomes and KPIs | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.5 |  |  |  |  | Change control and reporting | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.6 |  |  |  |  | Ongoing identification of lessons learned relating to the PMO and implementation of improvements | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
3 | 1.2.2 |  |  |  |  | Programme Internal Assurance Reviews | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.2.1 |  |  |  |  | Programme Internal Assurance Reviews | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.2.3 |  |  |  |  | Engagement with PPs | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.3.1 |  |  |  |  | Ongoing PP liaison activities | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.2 |  |  |  |  | Milestone and Control Point objective setting | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.3 |  |  |  |  | Reporting | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.4 |  |  |  |  | PP Engagement Events | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.2.3.4.1 |  |  |  |  | Bilateral meetings | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.4.2 |  |  |  |  | Monthly webinars | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.4.3 |  |  |  |  | Open days | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.5 |  |  |  |  | PP Communications | 43% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.2.3.5.1 |  |  |  |  | The Clock updates (weekly) | 43% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.5.2 |  |  |  |  | Maintain and update content on public-facing Portal (and ongoing feedback reviews to identify and implement Portal improvements) | 43% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
3 | 1.2.4 |  |  |  |  | Code Change Support / Other Programme Alignment | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.4.1 |  |  |  |  | Support DCC/BEIS on SEC change | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.2 |  |  |  |  | Support on Smart Meters Act changes | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.3 |  |  |  |  | Support DCC/RECCo on CSS change | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.4 |  |  |  |  | Support Elexon on BSC change | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.5 |  |  |  |  | Support code change inside & outside CCIAG | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.6 |  |  |  |  | Support code change inside & outside CCAG | 43% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.2.5 |  |  |  |  | Programme Replan Baseline | 100% | Mon 31/10/22 | Wed 14/06/23 | 163 days | Mon 31/10/22 | Wed 14/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.5.1 |  |  |  |  | Round 3 consultation preparation | 100% | Mon 31/10/22 | Tue 13/12/22 | 32 days | Mon 31/10/22 | Tue 13/12/22 |  | 33FS-5 days | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.2 |  |  |  |  | PSG decision to launch Round 3 consultation | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 32FS-5 days | 34FS+5 days | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.3 |  |  |  |  | Round 3 consultation (incl. walkthroughs and Q&A) | 100% | Wed 14/12/22 | Tue 31/01/23 | 35 days | Wed 14/12/22 | Tue 31/01/23 | 33FS+5 days | 36,541FF,542,35SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.2.5.4 |  |  |  |  | Review and uplift of foundational testing documents to align with replan approach | 100% | Wed 14/12/22 | Thu 20/04/23 | 92 days | Wed 14/12/22 | Thu 20/04/23 | 34SS |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.2.5.5 |  |  |  |  | Round 3 consultation responses analysis (incl. identification of SIT volunteers) | 100% | Wed 01/02/23 | Tue 14/02/23 | 10 days | Wed 01/02/23 | Tue 14/02/23 | 34 | 37,38 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.6 |  |  |  |  | Replan re-drafting and supporting artefact updates (incl. engagement with Ofgem) | 100% | Wed 15/02/23 | Wed 22/03/23 | 26 days | Wed 15/02/23 | Wed 22/03/23 | 36 |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.7 |  |  |  |  | Draft Replan Change Request | 100% | Wed 15/02/23 | Wed 29/03/23 | 31 days | Wed 15/02/23 | Wed 29/03/23 | 36 | 39FS+5 days | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.8 |  |  |  |  | PSG decision to issue CR for industry impact assessment | 100% | Wed 05/04/23 | Wed 05/04/23 | 0 days | Wed 05/04/23 | Wed 05/04/23 | 38FS+5 days | 40 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.9 |  |  |  |  | Industry impact assessment | 100% | Thu 06/04/23 | Wed 19/04/23 | 10 days | Thu 06/04/23 | Wed 19/04/23 | 39 | 42,41SS+3 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.2.5.10 |  |  |  |  | Replan playbacks (to assist PPs in impact assessment) | 100% | Tue 11/04/23 | Mon 17/04/23 | 5 days | Tue 11/04/23 | Mon 17/04/23 | 40SS+3 days |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.11 |  |  |  |  | Industry impact assessment responses analysis | 100% | Thu 20/04/23 | Wed 26/04/23 | 5 days | Thu 20/04/23 | Wed 26/04/23 | 40 | 43FS+5 days | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.12 |  |  |  |  | Extraordinary PSG decision to agree baseline recommendation | 100% | Wed 03/05/23 | Wed 03/05/23 | 0 days | Wed 03/05/23 | Wed 03/05/23 | 42FS+5 days | 44FS+25 days | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.13 | T1 | T1-PM-1000 | PSG |  | Plan Rebaselined (subject to Ofgem decision) | 100% | Thu 08/06/23 | Thu 08/06/23 | 0 days | Thu 08/06/23 | Thu 08/06/23 | 43FS+25 days | 45 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.14 |  |  |  |  | Programme Replan playbacks and drop-in sessions | 100% | Thu 08/06/23 | Wed 14/06/23 | 5 days | Thu 08/06/23 | Wed 14/06/23 | 44 |  | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
2 | 1.3 |  |  |  |  | DESIGN, BUILD & TEST (PIT) | 80% | Mon 31/10/22 | Mon 18/01/27 | 1101 days? | Mon 31/10/22 | Mon 18/01/27 |  |  | 0 days | 0 days | 0 days? | N/A |  |  | Yes
3 | 1.3.1 |  |  |  |  | Design Baseline & Enduring PP Support | 71% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.1.1 | T1 | T1-DB-1000 | PSG | MHHS-ART001 | Physical design baselined (M5) | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 |  | 53,163,164,170,433FS+10 days,479,76,166,167,168,1802,54,50 | 0 days | 0 days | 0 days | SRO Design |  | 5 | Yes
4 | 1.3.1.2 |  |  |  |  | M5 Design Work-Off Plan Implementation & Approval | 100% | Mon 31/10/22 | Thu 16/02/23 | 79 days | Mon 31/10/22 | Thu 16/02/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.2.1 |  |  |  |  | Implementation of M5 design Work-Off Plan | 100% | Mon 31/10/22 | Thu 09/02/23 | 74 days | Mon 31/10/22 | Thu 09/02/23 | 48 | 51FS+5 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.2.2 | T3 | T3-DB-0014 | DAG |  | M5 design Work-Off Plan completion approved | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 50FS+5 days | 56,61FF | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.3 |  |  |  |  | Enduring PP Design Support | 100% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.3.1 |  |  |  |  | Design playbacks and drop-in sessions | 100% | Mon 31/10/22 | Fri 30/12/22 | 45 days | Mon 31/10/22 | Fri 30/12/22 | 48 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.2 |  |  |  |  | Support participants on E2E MHHS Design | 100% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 48 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.3 |  |  |  |  | DIP Onboarding Support | 100% | Mon 14/11/22 | Fri 17/02/23 | 70 days | Mon 14/11/22 | Fri 17/02/23 |  |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.4 |  |  |  |  | iServer Launch | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 51 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.4 |  |  |  |  | Establish Design Change Management Processes | 36% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.4.1 |  |  |  |  | Internal review of internal change management processes | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  | 59FF | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.3.1.4.2 |  |  |  |  | SRO approval of internal change management processes | 100% | Fri 16/12/22 | Fri 16/12/22 | 0 days | Fri 16/12/22 | Fri 16/12/22 | 58FF |  | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.3.1.4.3 |  |  |  |  | Change Process Webinar | 100% | Mon 16/01/23 | Mon 16/01/23 | 0 days | Mon 16/01/23 | Mon 16/01/23 |  |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.4.4 | T3 | T3-DB-0016 | DAG |  | Enduring change management process approved | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 51FF | 62 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.4.5 |  |  |  |  | Maintain E2E MHHS Design (post-M5 design change management processes operational) | 34% | Fri 17/02/23 | Mon 18/01/27 | 1022 days | Fri 17/02/23 | Mon 18/01/27 | 61 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.5 |  |  |  |  | Design Authority Mobilisation | 100% | Wed 14/12/22 | Mon 23/01/23 | 29 days | Wed 14/12/22 | Mon 23/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.5.1 | T3 | T3-DB-0010 | DAG |  | Design Authority ToR approved | 100% | Wed 14/12/22 | Wed 14/12/22 | 0 days | Wed 14/12/22 | Wed 14/12/22 |  | 65FS+29 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.5.2 |  |  |  |  | Inaugural Design Authority | 100% | Mon 23/01/23 | Mon 23/01/23 | 0 days | Mon 23/01/23 | Mon 23/01/23 | 64FS+29 days |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.6 |  |  |  |  | Network Operation Services Adaptor Procurement | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.6.1 | T3 | T3-DB-0020 | DAG |  | All SIT LDSOs have procured their adapter providers | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 545SS |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
3 | 1.3.2 |  |  |  |  | PP Mobilisation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.2.1 |  |  |  |  | Set up governance | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.2 |  |  |  |  | Set up reporting | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.3 |  |  |  |  | Obtain funding | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.4 |  |  |  |  | Earmark resources | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.5 |  |  |  |  | Mobilise initial team | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.3.3 |  |  |  |  | PIT Stub Specification and Delivery | 100% | Mon 31/10/22 | Fri 28/06/24 | 435 days | Mon 31/10/22 | Fri 21/06/24 |  |  | 0 days | 5 days | 5 days | N/A |  | 5 | Yes
4 | 1.3.3.1 |  |  |  |  | DIP Simulator | 100% | Mon 31/10/22 | Wed 29/03/23 | 108 days | Mon 31/10/22 | Wed 29/03/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.3.1.1 |  |  |  |  | Build & Test | 100% | Mon 31/10/22 | Fri 10/03/23 | 95 days | Mon 31/10/22 | Fri 10/03/23 | 48 | 77SS+10 days,78SS | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.1.2 |  |  |  |  | UAT | 100% | Mon 14/11/22 | Fri 10/03/23 | 85 days | Mon 14/11/22 | Fri 10/03/23 | 76SS+10 days |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.3.1.3 |  |  |  |  | Beta test | 100% | Mon 31/10/22 | Fri 10/03/23 | 95 days | Mon 31/10/22 | Fri 10/03/23 | 76SS | 79FS-5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.3.1.4 |  |  |  |  | Prepare for release | 100% | Mon 06/03/23 | Wed 29/03/23 | 18 days | Mon 06/03/23 | Wed 29/03/23 | 78FS-5 days | 80FF | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.1.5 | T3 | T3-DB-0018 | SITAG |  | DIP Simulator released | 100% | Wed 29/03/23 | Wed 29/03/23 | 0 days | Wed 29/03/23 | Wed 29/03/23 | 79FF | 663695727759 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
4 | 1.3.3.2 |  |  |  |  | DIP Simulator Uplifts | 100% | Thu 06/07/23 | Fri 28/06/24 | 257 days | Thu 06/07/23 | Fri 21/06/24 |  |  | 0 days | 5 days | 5 days | N/A |  | 5.1 | Yes
5 | 1.3.3.2.1 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 06/07/23 | Fri 11/08/23 | 27 days | Thu 06/07/23 | Fri 11/08/23 | 118 | 83 | 0 days | 0 days | 0 days | SI DevOps |  | 5.1 | Yes
5 | 1.3.3.2.2 | T3 | T3-DB-0035 | SITAG |  | DIP Simulator uplifted to align with Interim Release 2 | 100% | Fri 11/08/23 | Fri 11/08/23 | 0 days | Fri 11/08/23 | Fri 11/08/23 | 82 |  | 0 days | 0 days | 0 days | SI DevOps |  | 5.1 | Yes
5 | 1.3.3.2.3 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Mon 09/10/23 | Fri 03/11/23 | 20 days | Mon 09/10/23 | Fri 03/11/23 | 127FS+2 days | 85 | 0 days | 0 days | 0 days | SI DevOps |  | 5.3 | Yes
5 | 1.3.3.2.4 | T3 | T3-DB-0039 | SITAG |  | DIP Simulator uplifted to align with Interim Release 5 | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 84 |  | 0 days | 0 days | 0 days | SI DevOps |  | 5.11 | Yes |  | Amber as S&E couldn't view design docs, & assess scope changes. Required workload likely more than 2 sprints (original estimate). Additional MS work & CIT testing support has stretched capacity further. Delivery could be delayed.
5 | 1.3.3.2.5 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 01/02/24 | Fri 22/03/24 | 37 days | Thu 01/02/24 | Fri 22/03/24 | 135 | 87 | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.6 | T3 | T3-DB-0182 | SITAG |  | DIP Simulator uplifted to align with Interim Release 7 | 100% | Fri 22/03/24 | Fri 22/03/24 | 0 days | Fri 22/03/24 | Fri 22/03/24 | 86 |  | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes |  | 11/12- Add new milestone to reflect confirmation of Interim Release Delivery dates. 20/12 - Approved at TMAG on 20/12
5 | 1.3.3.2.7 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 04/04/24 | Fri 21/06/24 | 57 days | Thu 04/04/24 | Fri 21/06/24 | 139 | 89FS+5 days | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.8 | T3 | T3-DB-0183 | SITAG |  | DIP Simulator uplifted to align with Interim Release 8 | 100% | Fri 28/06/24 | Fri 28/06/24 | 0 days | Fri 21/06/24 | Fri 21/06/24 | 88FS+5 days |  | 5 days | 5 days | 0 days | SI DevOps |  | 5.28 | Yes |  | 20/6: Date missed because a decision was taken and agreed with SRO to bundle IR8 and IR8.1, meaning a later combined release date of 28/6. No PP impact as PIT for SIT Cycle 3 will be baselined against IR8.1
4 | 1.3.3.3 |  |  |  |  | Data Generator | 100% | Thu 01/12/22 | Wed 31/05/23 | 130 days | Thu 01/12/22 | Wed 31/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.3.3.1 |  |  |  |  | Design | 100% | Thu 01/12/22 | Wed 21/12/22 | 15 days | Thu 01/12/22 | Wed 21/12/22 |  | 92FS+40 days | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.2 |  |  |  |  | Build & Test | 100% | Thu 16/02/23 | Wed 26/04/23 | 50 days | Thu 16/02/23 | Wed 26/04/23 | 91FS+40 days | 93,94FS-20 days | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.3 |  |  |  |  | UAT | 100% | Thu 27/04/23 | Wed 10/05/23 | 10 days | Thu 27/04/23 | Wed 10/05/23 | 92 | 95SS | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.3.3.4 |  |  |  |  | Beta test | 100% | Thu 30/03/23 | Wed 31/05/23 | 45 days | Thu 30/03/23 | Wed 31/05/23 | 92FS-20 days,96FF |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.3.3.5 |  |  |  |  | Prepare for release | 100% | Thu 27/04/23 | Tue 30/05/23 | 24 days | Thu 27/04/23 | Tue 30/05/23 | 93SS | 96FS+1 day | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.6 | T3 | T3-DB-0022 | SITAG |  | Data Generator released | 100% | Wed 31/05/23 | Wed 31/05/23 | 0 days | Wed 31/05/23 | Wed 31/05/23 | 95FS+1 day | 94FF,663,695,727,759 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
3 | 1.3.4 |  |  |  |  | Design Artefact Releases | 92% | Wed 22/02/23 | Fri 18/10/24 | 433 days? | Wed 22/02/23 | Fri 30/08/24 |  |  | 0 days | 35 days | 35 days? | N/A |  | 5 | Yes
4 | 1.3.4.1 |  |  |  |  | Interim release 1 | 100% | Wed 22/02/23 | Mon 12/06/23 | 79 days | Wed 22/02/23 | Mon 12/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.1.1 |  |  |  |  | Prioritise DINs and CR | 100% | Wed 22/02/23 | Wed 22/02/23 | 1 day | Wed 22/02/23 | Wed 22/02/23 |  | 101 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.2 |  |  |  |  | Industry input session | 100% | Thu 23/02/23 | Fri 03/03/23 | 7 days | Thu 23/02/23 | Fri 03/03/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.2.1 |  |  |  |  | Raise a CR covering prioritized assessment cluster | 100% | Thu 23/02/23 | Thu 23/02/23 | 1 day | Thu 23/02/23 | Thu 23/02/23 | 99 | 102SS | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.2.2 |  |  |  |  | Organize Industry Input session to go through significant items to reach consensus | 100% | Thu 23/02/23 | Thu 23/02/23 | 1 day | Thu 23/02/23 | Thu 23/02/23 | 101SS | 103FS+5 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.2.3 |  |  |  |  | Conduct Meeting | 100% | Fri 03/03/23 | Fri 03/03/23 | 1 day | Fri 03/03/23 | Fri 03/03/23 | 102FS+5 days |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.3 |  |  |  |  | Update baselined artefacts | 100% | Fri 24/03/23 | Thu 06/04/23 | 10 days | Fri 24/03/23 | Thu 06/04/23 |  | 106FS+5 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.4 |  |  |  |  | Participant review and impact assess changes | 100% | Fri 14/04/23 | Tue 09/05/23 | 18 days | Fri 14/04/23 | Tue 09/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.4.1 |  |  |  |  | Issue Redline Version of documents | 100% | Fri 14/04/23 | Fri 14/04/23 | 1 day | Fri 14/04/23 | Fri 14/04/23 | 104FS+5 days | 107 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.4.2 |  |  |  |  | Participants provide review comments to common log | 100% | Mon 17/04/23 | Tue 09/05/23 | 17 days | Mon 17/04/23 | Tue 09/05/23 | 106 | 109 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.4.1.5 |  |  |  |  | Assurance review | 100% | Wed 10/05/23 | Mon 05/06/23 | 19 days | Wed 10/05/23 | Mon 05/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.5.1 |  |  |  |  | SI Design Review and Respond to Comments | 100% | Wed 10/05/23 | Tue 16/05/23 | 5 days | Wed 10/05/23 | Tue 16/05/23 | 107 | 110 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.2 |  |  |  |  | Prep for Assurance Review Meeting | 100% | Wed 17/05/23 | Thu 25/05/23 | 7 days | Wed 17/05/23 | Thu 25/05/23 | 109 | 111 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.3 |  |  |  |  | Conduct Assurance Review Meeting | 100% | Fri 26/05/23 | Fri 26/05/23 | 1 day | Fri 26/05/23 | Fri 26/05/23 | 110 | 112 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.4 |  |  |  |  | Update Artefacts following Assurance Review | 100% | Mon 29/05/23 | Mon 05/06/23 | 6 days | Mon 29/05/23 | Mon 05/06/23 | 111 | 114 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.6 |  |  |  |  | PSG Approval of interim release plan | 100% | Thu 08/06/23 | Thu 08/06/23 | 1 day | Thu 08/06/23 | Thu 08/06/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
5 | 1.3.4.1.7 |  |  |  |  | Publish updated baselined artefacts | 100% | Tue 06/06/23 | Mon 12/06/23 | 0 days | Tue 06/06/23 | Mon 12/06/23 | 112 | 115 | 0 days | 0 days | -5 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.8 | T3 | T3-DB-0095 | DAG |  | Interim release 1 Go live | 100% | Mon 12/06/23 | Mon 12/06/23 | 0 days | Mon 12/06/23 | Mon 12/06/23 | 114 | 1.0731e+23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.2 |  |  |  |  | Interim release 2 | 100% | Tue 30/05/23 | Wed 05/07/23 | 27 days | Tue 30/05/23 | Wed 05/07/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.2.1 |  |  |  |  | Update baselined artefacts | 100% | Tue 30/05/23 | Wed 05/07/23 | 27 days | Tue 30/05/23 | Wed 05/07/23 |  | 118 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.2.2 | T3 | T3-DB-0096 | DAG |  | Interim release 2 Go live | 100% | Wed 05/07/23 | Wed 05/07/23 | 0 days | Wed 05/07/23 | Wed 05/07/23 | 117 | 82 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.3 |  |  |  |  | Interim release 3 | 100% | Thu 15/06/23 | Wed 02/08/23 | 35 days | Thu 15/06/23 | Wed 02/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.3.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 15/06/23 | Wed 02/08/23 | 35 days | Thu 15/06/23 | Wed 02/08/23 |  | 121 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.3.2 | T3 | T3-DB-0097 | DAG |  | Interim release 3 Go live | 100% | Wed 02/08/23 | Wed 02/08/23 | 0 days | Wed 02/08/23 | Wed 02/08/23 | 120 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.4 |  |  |  |  | Interim release 4 | 100% | Wed 12/07/23 | Wed 30/08/23 | 36 days | Wed 12/07/23 | Wed 30/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.4.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 12/07/23 | Wed 30/08/23 | 36 days | Wed 12/07/23 | Wed 30/08/23 |  | 124 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.4.2 | T3 | T3-DB-0081 | DAG |  | Interim release 4 Go live | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 123 |  | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
4 | 1.3.4.5 |  |  |  |  | Interim release 5 | 100% | Thu 17/08/23 | Fri 08/03/24 | 147 days | Thu 17/08/23 | Fri 08/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.5.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 17/08/23 | Wed 04/10/23 | 35 days | Thu 17/08/23 | Wed 04/10/23 |  | 127 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.5.2 | T3 | T3-DB-0083 | DAG |  | Interim release 5 Go live | 100% | Wed 04/10/23 | Wed 04/10/23 | 0 days | Wed 04/10/23 | Wed 04/10/23 | 126 | 84FS+2 days,128FS+102 days | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.5.3 |  |  |  |  | Interim Release 5 Deployed to SIT | 100% | Mon 26/02/24 | Fri 08/03/24 | 10 days | Mon 26/02/24 | Fri 08/03/24 | 127FS+102 days |  | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.6 |  |  |  |  | Interim release 6 | 100% | Thu 14/09/23 | Fri 07/06/24 | 192 days | Thu 14/09/23 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.6.1 |  |  |  |  | Update baselined artefacts | 100% | Thu 14/09/23 | Wed 01/11/23 | 35 days | Thu 14/09/23 | Fri 27/10/23 |  | 131 | 0 days | 3 days | 3 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.6.2 | T3 | T3-DB-0085 | DAG |  | Interim release 6 Go live | 100% | Wed 01/11/23 | Wed 01/11/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 130 | 132FS+147 days | 3 days | 3 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.4.6.3 |  |  |  |  | Interim Release 6 Deployed to SIT | 100% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 27/05/24 | Fri 07/06/24 | 131FS+147 days |  | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.7 |  |  |  |  | Interim release 7 | 100% | Wed 18/10/23 | Fri 07/06/24 | 168 days | Wed 18/10/23 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
5 | 1.3.4.7.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 18/10/23 | Wed 31/01/24 | 76 days | Wed 18/10/23 | Wed 31/01/24 |  | 135 | 0 days | 0 days | 0 days | SI Design |  | 5.5 | Yes |  | 4/8 - Added in as per PPs advice
5 | 1.3.4.7.2 | T3 | T3-DB-0098 | DAG |  | Interim release 7 Go live | 100% | Wed 31/01/24 | Wed 31/01/24 | 0 days | Wed 31/01/24 | Wed 31/01/24 | 134 | 86,136FS+82 days | 0 days | 0 days | 0 days | SI Design |  | 5.14 | Yes |  | 27/11- Red because forecast date has changed to align with Testing Release Management. Discussed with no objections at FTIG on 23/11. To be taken to Dec DAG for noting
5 | 1.3.4.7.3 |  |  |  |  | Interim Release 7 Deployed to SIT | 100% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 27/05/24 | Fri 07/06/24 | 135FS+82 days |  | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.8 |  |  |  |  | Interim release 8 | 55% | Wed 14/02/24 | Fri 18/10/24 | 178 days? | Wed 14/02/24 | Fri 30/08/24 |  |  | 0 days | 35 days | 35 days? | N/A |  | 5.5 | Yes
5 | 1.3.4.8.1 |  |  |  |  | Update baselined artefacts | 100% | Wed 14/02/24 | Wed 03/04/24 | 36 days | Wed 14/02/24 | Wed 03/04/24 |  | 139 | 0 days | 0 days | 0 days | SI Design |  | 5.5 | Yes |  | 4/8 - Added in as per PPs advice
5 | 1.3.4.8.2 | T3 | T3-DB-0099 | DAG |  | Interim release 8 Go live | 100% | Wed 03/04/24 | Wed 03/04/24 | 0 days | Wed 03/04/24 | Wed 03/04/24 | 138 | 88,141FS+122 days | 0 days | 0 days | 0 days | SI Design |  | 5.14 | Yes |  | 27/11- Amber because forecast date has changed to align with Testing Release Management. Discussed with no objections at FTIG on 23/11. To be taken to Dec DAG for noting
5 | 1.3.4.8.3 |  |  |  |  | Interim Release 8.3 - Maintenance Window | 0% | Mon 23/09/24 | Fri 18/10/24 | 20 days? | NA | NA |  |  | 0 days | 0 days | 20 days? |  |  | 6 | Yes
6 | 1.3.4.8.3.1 |  |  |  |  | Interim Release 8 Deployed to SIT A | 0% | Mon 23/09/24 | Fri 18/10/24 | 20 days | Mon 19/08/24 | Fri 30/08/24 | 139FS+122 days | 1100,1144,142SS | 25 days | 35 days | 10 days | SI Testing |  | 5.16 | Yes
6 | 1.3.4.8.3.2 |  |  |  |  | Interim Release 8 Deployed to SIT B | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days? | NA | NA | 141SS | 1041 | 0 days | 0 days | 10 days? |  |  |  | Yes
3 | 1.3.5 |  |  |  |  | Queries Support / Knowledgebase & Tool Roll-Out (Systems) | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.5.1 |  |  |  |  | Query Management | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.1.1 |  |  |  |  | Respond to Participant Queries | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 |  | 146SS | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.1.2 |  |  |  |  | Respond to Programme Queries | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 | 145SS |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.5.2 |  |  |  |  | Query Support tooling (FreshDesk) | 100% | Thu 01/06/23 | Mon 03/07/23 | 23 days | Thu 01/06/23 | Mon 03/07/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.2.1 |  |  |  |  | Migrate to Standalone Freshdesk | 100% | Thu 01/06/23 | Wed 14/06/23 | 10 days | Thu 01/06/23 | Wed 14/06/23 |  | 154SS,149 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.2 |  |  |  |  | Develop reporting dashboard | 100% | Thu 15/06/23 | Wed 21/06/23 | 5 days | Thu 15/06/23 | Wed 21/06/23 | 148 | 150 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.3 |  |  |  |  | Issue to SRO for Review | 100% | Thu 22/06/23 | Wed 28/06/23 | 5 days | Thu 22/06/23 | Wed 28/06/23 | 149 | 151 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.4 |  |  |  |  | Update following review | 100% | Thu 29/06/23 | Fri 30/06/23 | 2 days | Thu 29/06/23 | Fri 30/06/23 | 150 | 152 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.5 |  |  |  |  | Sign off | 100% | Mon 03/07/23 | Mon 03/07/23 | 1 day | Mon 03/07/23 | Mon 03/07/23 | 151 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.5.3 |  |  |  |  | KnowledgeBase Development | 100% | Thu 01/06/23 | Fri 08/09/23 | 72 days | Thu 01/06/23 | Fri 08/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.3.1 |  |  |  |  | Define Scope of KB | 100% | Thu 01/06/23 | Thu 01/06/23 | 1 day | Thu 01/06/23 | Thu 01/06/23 | 148SS | 155 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.2 |  |  |  |  | Capture Existing KB artefacts | 100% | Fri 02/06/23 | Thu 29/06/23 | 20 days | Fri 02/06/23 | Thu 29/06/23 | 154 | 156 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.3 |  |  |  |  | Tag artefacts | 100% | Fri 30/06/23 | Thu 06/07/23 | 5 days | Fri 30/06/23 | Thu 06/07/23 | 155 | 157 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.4 |  |  |  |  | Develop Participant Interfaces | 100% | Fri 07/07/23 | Thu 03/08/23 | 20 days | Fri 07/07/23 | Thu 03/08/23 | 156 | 158 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.5 |  |  |  |  | Promote to Collaboration Portal | 100% | Fri 04/08/23 | Fri 01/09/23 | 21 days | Fri 04/08/23 | Fri 01/09/23 | 157 | 159 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.6 |  |  |  |  | Link into FreshDesk | 100% | Mon 04/09/23 | Fri 08/09/23 | 5 days | Mon 04/09/23 | Fri 08/09/23 | 158 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
3 | 1.3.6 |  |  |  |  | PP Design, Build & Test (DBT) | 96% | Mon 31/10/22 | Fri 20/12/24 | 560 days | Mon 31/10/22 | Fri 20/09/24 |  |  | 0 days | 65 days | 65 days | N/A |  | 5 | Yes
4 | 1.3.6.1 |  |  |  |  | PP Impact Assessment, Planning & Procurement | 100% | Mon 31/10/22 | Fri 31/03/23 | 110 days | Mon 31/10/22 | Fri 31/03/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.6.1.1 |  |  |  |  | PP Impact Assessment | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.1.1 |  |  |  |  | Develop heatmap for impact of MHHS | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.1.2 |  |  |  |  | Develop detailed impact assessment | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.6.1.2 |  |  |  |  | PP Planning | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.2.1 |  |  |  |  | Develop detailed short-term plan | 100% | Mon 31/10/22 | Wed 30/11/22 | 23 days | Mon 31/10/22 | Wed 30/11/22 | 48 | 420SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.2.2 |  |  |  |  | Develop overall project plan for implementation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.2.3 |  |  |  |  | Develop procurement plan | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.6.1.3 |  |  |  |  | PP Software/Service Procurement | 100% | Mon 31/10/22 | Fri 31/03/23 | 110 days | Mon 31/10/22 | Fri 31/03/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.3.1 |  |  |  |  | Run tender process | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 | 171 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.3.2 |  |  |  |  | Select provider & sign commercials | 100% | Wed 01/02/23 | Fri 31/03/23 | 43 days | Wed 01/02/23 | Fri 31/03/23 | 170 |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.6.2 |  |  |  |  | Central Systems DBT | 100% | Mon 31/10/22 | Fri 26/01/24 | 325 days | Mon 31/10/22 | Fri 23/02/24 |  |  | 0 days | -20 days | -20 days | N/A |  | 5 | Yes
5 | 1.3.6.2.1 |  |  |  |  | Elexon Central Systems DBT CIT (Entering at Interval 1) | 100% | Mon 31/10/22 | Wed 11/10/23 | 248 days | Mon 31/10/22 | Thu 12/10/23 |  |  | 0 days | -1 day | -1 day | N/A |  | 5 | Yes
6 | 1.3.6.2.1.1 |  |  |  |  | Design and Build | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 29/09/23 |  |  | 0 days | -5 days | -5 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.1.1 |  |  |  |  | Helix Design and Build | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 29/09/23 | 2 |  | 0 days | -5 days | -5 days | PP |  | 5 | Yes
6 | 1.3.6.2.1.2 |  |  |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.2.1 |  |  |  |  | Develop Test Approach & Plan | 100% | Mon 31/10/22 | Fri 07/07/23 | 180 days | Mon 31/10/22 | Fri 07/07/23 |  | 178FF+4 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.2.2 | T3 | T3-DB-0029 | SITAG |  | Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Thu 13/07/23 | Thu 13/07/23 | 0 days | Thu 13/07/23 | Thu 13/07/23 | 177FF+4 days | 179FS+9 days,185,188,183FS+10 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.2.3 |  |  |  |  | Elexon Central Systems Test Approach & Plan (PIT) V2 resubmitted to Programme for assurance | 100% | Thu 27/07/23 | Thu 27/07/23 | 0 days | Thu 27/07/23 | Thu 27/07/23 | 178FS+9 days | 180FS+17 days | 0 days | 0 days | 0 days | PP |  | 5.4 | Yes
7 | 1.3.6.2.1.2.4 |  |  |  |  | Elexon Central Systems Test Approach & Plan (PIT) V3 resubmitted to Programme for assurance | 100% | Fri 18/08/23 | Fri 18/08/23 | 0 days | Fri 18/08/23 | Fri 18/08/23 | 179FS+17 days | 181FS+25 days | 0 days | 0 days | 0 days | PP |  | 5.4 | Yes
7 | 1.3.6.2.1.2.5 | T3 | T3-DB-0106 | SITAG |  | Elexon Central Systems Test approach and plan MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 180FS+25 days | 194 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
6 | 1.3.6.2.1.3 |  |  |  |  | Test Readiness Report | 100% | Fri 28/07/23 | Fri 18/08/23 | 16 days | Thu 03/08/23 | Thu 12/10/23 |  |  | -4 days | -39 days | -35 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.3.1 |  |  |  |  | Test readiness reporting | 100% | Fri 28/07/23 | Fri 18/08/23 | 16 days | Thu 03/08/23 | Thu 12/10/23 | 178FS+10 days | 191FS+10 days,192 | -4 days | -39 days | -35 days | PP |  | 5 | Yes
6 | 1.3.6.2.1.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 04/08/23 | Fri 22/09/23 | 35 days | Fri 04/08/23 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.4.1 | T3 | T3-DB-0030 | SITAG | MHHS-ART009 | Elexon Central Systems RTTM submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 178 | 186FS+35 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.4.2 | T3 | T3-DB-0107 | SITAG |  | Elexon Central Systems RTTM MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 185FS+35 days | 194 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
6 | 1.3.6.2.1.5 |  |  |  |  | Test Scenarios | 100% | Fri 04/08/23 | Fri 22/09/23 | 35 days | Fri 04/08/23 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.5.1 | T3 | T3-DB-0032 | SITAG |  | Elexon Central Systems test scenarios submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 178 | 189FS+35 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.1.5.2 | T3 | T3-DB-0108 | SITAG |  | Elexon Central Systems Test scenarios MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 188FS+35 days | 194 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
6 | 1.3.6.2.1.6 |  |  |  |  | PIT Execution | 100% | Mon 21/08/23 | Wed 11/10/23 | 38 days | Mon 31/10/22 | Wed 11/10/23 |  |  | 210 days | 0 days | -210 days | N/A |  | 5 | Yes
7 | 1.3.6.2.1.6.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 04/09/23 | Wed 27/09/23 | 18 days | Mon 31/10/22 | Fri 22/09/23 | 183FS+10 days | 194 | 220 days | 3 days | -217 days | PP |  | 5.1 | Yes
7 | 1.3.6.2.1.6.2 |  |  |  |  | Elexon Central Systems PIT Execution | 100% | Mon 21/08/23 | Wed 27/09/23 | 28 days | Tue 08/11/22 | Mon 09/10/23 | 183 | 193 | 204 days | -8 days | -212 days | PP |  | 5.1 | Yes
7 | 1.3.6.2.1.6.3 | T3 | T3-DB-0109 | SITAG |  | Elexon Central Systems PIT Completion Report submitted to Programme for assurance | 100% | Wed 27/09/23 | Wed 27/09/23 | 0 days | Wed 27/09/23 | Wed 27/09/23 | 192 | 194FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
7 | 1.3.6.2.1.6.4 | T3 | T3-DB-0110 | SITAG |  | Elexon Central Systems PIT Completion Report MHHS Review Completed | 100% | Wed 11/10/23 | Wed 11/10/23 | 0 days | Wed 11/10/23 | Wed 11/10/23 | 186,189,191,193FS+10 days,181 | 631 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
5 | 1.3.6.2.2 |  |  |  |  | DIP DBT CIT (Entering at Interval 1) | 100% | Mon 02/01/23 | Mon 06/11/23 | 221 days | Mon 31/10/22 | Mon 06/11/23 |  |  | 45 days | 0 days | -45 days | N/A |  | 5 | Yes
6 | 1.3.6.2.2.1 |  |  |  |  | Design | 100% | Mon 02/01/23 | Fri 21/04/23 | 80 days | Mon 02/01/23 | Fri 21/04/23 |  | 197SS+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.2.2.2 |  |  |  |  | Build | 100% | Mon 09/01/23 | Fri 11/08/23 | 155 days | Mon 09/01/23 | Fri 11/08/23 | 196SS+5 days |  | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
6 | 1.3.6.2.2.3 |  |  |  |  | Test Approach & Plan | 100% | Fri 07/07/23 | Thu 20/07/23 | 9 days | Mon 31/10/22 | Fri 21/07/23 |  |  | 180 days | -1 day | -181 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.3.1 | T3 | T3-DB-0026 | SITAG | MHHS-ART073 | DIP Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 07/07/23 | Fri 07/07/23 | 0 days | Fri 07/07/23 | Fri 07/07/23 |  | 200FS+9 days,202FS+9 days,204FS+15 days,207FS+15 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.2.3.2 |  |  |  |  | DIP Test Approach & Plan (PIT) MHHS Review Completed | 100% | Thu 20/07/23 | Thu 20/07/23 | 0 days | Mon 10/07/23 | Fri 21/07/23 | 199FS+9 days | 631 | 9 days | -1 day | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.4 |  |  |  |  | PIT Test Readiness Report | 100% | Fri 21/07/23 | Fri 01/09/23 | 31 days | Fri 21/07/23 | Fri 29/09/23 |  |  | 0 days | -20 days | -20 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.4.1 |  |  |  |  | Test readiness reporting | 100% | Fri 21/07/23 | Fri 01/09/23 | 31 days | Fri 21/07/23 | Fri 29/09/23 | 199FS+9 days | 210 | 0 days | -20 days | -20 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.5 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 04/08/23 | Wed 30/08/23 | 18 days | Mon 31/10/22 | Fri 18/08/23 |  |  | 200 days | 8 days | -192 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.5.1 | T3 | T3-DB-0034 | SITAG | MHHS-ART009 | DIP RTTM submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 199FS+15 days | 205FS+18 days | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes |  | RG confirmed Submitted on 10/8/23
7 | 1.3.6.2.2.5.2 |  |  |  |  | DIP RTTM MHHS Review Completed | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Mon 07/08/23 | Fri 18/08/23 | 204FS+18 days | 631 | 18 days | 8 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.6 |  |  |  |  | Test Scenarios | 100% | Mon 31/07/23 | Wed 30/08/23 | 22 days | Mon 31/10/22 | Mon 14/08/23 |  |  | 196 days | 12 days | -184 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.6.1 | T3 | T3-DB-0036 | SITAG |  | DIP PIT test scenarios submitted to Programme for assurance | 100% | Mon 31/07/23 | Mon 31/07/23 | 0 days | Mon 31/07/23 | Mon 31/07/23 | 199FS+15 days | 208FS+22 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.2.6.2 |  |  |  |  | DIP Test scenarios MHHS Review Completed | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Tue 01/08/23 | Mon 14/08/23 | 207FS+22 days |  | 22 days | 12 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.2.2.7 |  |  |  |  | PIT execution | 100% | Tue 29/08/23 | Mon 06/11/23 | 50 days | Fri 01/09/23 | Mon 06/11/23 |  |  | -3 days | 0 days | 3 days | N/A |  | 5 | Yes
7 | 1.3.6.2.2.7.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Fri 01/09/23 | Mon 23/10/23 | 37 days | Fri 01/09/23 | Mon 23/10/23 | 211FF,202 | 215 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes |  | 21/8 - due to complete 9/10 - advised by RG
7 | 1.3.6.2.2.7.2 |  |  |  |  | PIT Execution (Interim Release 1) | 100% | Tue 29/08/23 | Mon 09/10/23 | 30 days | Wed 06/09/23 | Mon 09/10/23 |  | 210FF,212,213 | -6 days | 0 days | 6 days | PP |  | 5.6 | Yes |  | 21/8 - due to complete 9/10 - advised by RG
7 | 1.3.6.2.2.7.3 |  |  |  |  | PIT Execution (Interim Release 2) | 100% | Tue 10/10/23 | Mon 23/10/23 | 10 days | Tue 10/10/23 | Mon 23/10/23 | 211 | 215 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes |  | 21/8 - new line added date are 9/10 - 23/10 - advised by RG.
7 | 1.3.6.2.2.7.4 | T3 | T3-DB-0111 | SITAG |  | DIP PIT Completion Report (Interim Release 1) submitted to Programme for assurance | 100% | Mon 09/10/23 | Mon 09/10/23 | 0 days | Mon 09/10/23 | Mon 09/10/23 | 211 | 214FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 9/10 - RG - After discussions with DM it was decided a completion report for IR1 wasn't required as we are entering IR2 ahead of schedule & draft completion report already submitted & assured
7 | 1.3.6.2.2.7.5 | T3 | T3-DB-0112 | SITAG |  | DIP PIT Completion Report (Interim Release 1) MHHS Review Completed | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 213FS+10 days | 631 | 0 days | 0 days | 0 days | SI Test |  | 5.1 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
7 | 1.3.6.2.2.7.6 | T3 | T3-DB-0113 | SITAG |  | DIP PIT Completion Report (Interim Release 2) submitted to Programme for assurance | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 212210 | 216FS+10 days,631 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
7 | 1.3.6.2.2.7.7 | T3 | T3-DB-0114 | SITAG |  | DIP PIT Completion Report (Interim Release 2) MHHS Review Completed | 100% | Mon 06/11/23 | Mon 06/11/23 | 0 days | Mon 06/11/23 | Mon 06/11/23 | 215FS+10 days |  | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 7/11- Red because further clarity around remaining open low severity defect work off plan requested. No impact. Completed on 8/12
5 | 1.3.6.2.3 |  |  |  |  | DCC (DSP) DBT SIT Functional (Entering at SIT Functional) | 100% | Mon 31/10/22 | Fri 26/01/24 | 325 days | Mon 31/10/22 | Fri 23/02/24 |  |  | 0 days | -20 days | -20 days | N/A |  | 5.18 | Yes
6 | 1.3.6.2.3.1 |  |  |  |  | Design | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  | 220FS+208 days | 0 days | 0 days | 0 days | PP |  | 5.18 | Yes
6 | 1.3.6.2.3.2 |  |  |  |  | Test Approach & Plan | 100% | Fri 17/11/23 | Fri 15/12/23 | 20 days | Fri 17/11/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.2.1 | T3 | T3-DB-0068 | SITAG |  | DCC Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 218FS+208 days | 221FS+20 days,223FS+10 days,759,225FS+20 days,228FS+20 days | 0 days | 0 days | 0 days | PP |  | 5.18 | Yes |  | 21/11- Red because not received. Currently no impact. 30/1 - Completed on 26/1
7 | 1.3.6.2.3.2.2 | T3 | T3-DB-0115 | SITAG |  | DCC Test Approach & Plan (PIT) MHHS Review Completed | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 220FS+20 days |  | 0 days | 0 days | 0 days | SI Test |  | 5.18 | Yes |  | 1/9 - to be raised as new T3 at TMAG DCC no longer in CIT, new dates relate to SIT Functional. Approved at TMAG on 20/9. 19/12 - Red because not received
6 | 1.3.6.2.3.3 |  |  |  |  | Test Readiness Report | 100% | Mon 04/12/23 | Tue 02/01/24 | 22 days | Fri 27/10/23 | Fri 05/01/24 |  |  | 26 days | -3 days | -29 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.3.1 |  |  |  |  | Test readiness reporting | 100% | Mon 04/12/23 | Tue 02/01/24 | 22 days | Fri 27/10/23 | Fri 05/01/24 | 220FS+10 days |  | 26 days | -3 days | -29 days | PP |  | 5.18 | Yes
6 | 1.3.6.2.3.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 15/12/23 | Fri 26/01/24 | 30 days | Fri 15/12/23 | Fri 26/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.4.1 | T3 | T3-DB-0074 | SITAG |  | DCC RTTM submitted to Programme for assurance | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 220FS+20 days | 226FS+30 days,759 | 0 days | 0 days | 0 days | PP |  | 5.18 | Yes |  | 19/12- Red because not received. 30/1 - Completed on 26/1
7 | 1.3.6.2.3.4.2 | T3 | T3-DB-0116 | SITAG |  | DCC RTTM MHHS Review Completed | 100% | Fri 26/01/24 | Fri 26/01/24 | 0 days | Fri 26/01/24 | Fri 26/01/24 | 225FS+30 days |  | 0 days | 0 days | 0 days | SI Test |  | 5.18 | Yes |  | 23/1- Amber because of potential late delivery of RTTM. No impact. No action. 30/1 - Completed on 26/1
6 | 1.3.6.2.3.5 |  |  |  |  | Test Scenarios | 100% | Fri 15/12/23 | Fri 26/01/24 | 30 days | Fri 15/12/23 | Fri 26/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.2.3.5.1 | T3 | T3-DB-0078 | SITAG |  | DCC test scenarios submitted to Programme for assurance | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 220FS+20 days | 229FS+30 days,759 | 0 days | 0 days | 0 days | PP |  | 5.18 | Yes |  | 5/12- Red because of late delivery of PIT approach and plan. No impact. No action. 30/1 - Completed on 26/1
7 | 1.3.6.2.3.5.2 | T3 | T3-DB-0117 | SITAG |  | DCC Test Scenarios MHHS Review Completed | 100% | Fri 26/01/24 | Fri 26/01/24 | 0 days | Fri 26/01/24 | Fri 26/01/24 | 228FS+30 days |  | 0 days | 0 days | 0 days | SI Test |  | 5.18 | Yes |  | 23/1- Amber because of potential late delivery of test scenarios. No impact. No action. 30/1 - Completed on 26/1
5 | 1.3.6.2.4 |  |  |  |  | RECCo (EES) DBT CIT (Entering at Interval 6) | 100% | Fri 13/10/23 | Fri 19/01/24 | 71 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 249 days | 0 days | -249 days | N/A |  | 5 | Yes |  | Assumption that Migration/Reverse Migration DBT is not applicable to RECCo....
6 | 1.3.6.2.4.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 13/10/23 | Thu 09/11/23 | 20 days | Fri 13/10/23 | Thu 09/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.1.1 | T3 | T3-DB-0066 | SITAG |  | EES Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 |  | 233FS+20 days,235FS+10 days,237FS+15 days,240FS+15 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name change. Approved at TMAG on 20/9. 17/10 - Red because document not yet received. No impact currently. Issuance from RECCo requested
7 | 1.3.6.2.4.1.2 | T3 | T3-DB-0119 | SITAG |  | EES Test approach and plan (PIT) MHHS Review Completed | 100% | Thu 09/11/23 | Thu 09/11/23 | 0 days | Thu 09/11/23 | Thu 09/11/23 | 232FS+20 days | 246 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 17/10 - Amber because Late delivery of document plus earlier intervals backlog. Currently no impact
6 | 1.3.6.2.4.2 |  |  |  |  | Test Readiness Report | 100% | Fri 27/10/23 | Thu 09/11/23 | 10 days | Fri 27/10/23 | Fri 05/01/24 |  |  | 0 days | -41 days | -41 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 27/10/23 | Thu 09/11/23 | 10 days | Fri 27/10/23 | Fri 05/01/24 | 232FS+10 days | 243 | 0 days | -41 days | -41 days | PP |  | 5 | Yes
6 | 1.3.6.2.4.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 02/11/23 | Thu 30/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.3.1 | T3 | T3-DB-0072 | SITAG | MHHS-ART009 | EES RTTM submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 232FS+15 days | 238FS+20 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 7/11 - Red because not submitted. No impact. No action
7 | 1.3.6.2.4.3.2 | T3 | T3-DB-0120 | SITAG |  | EES RTTM MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 237FS+20 days | 246 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 5/12- Red because Assurance conducted. Comments issued and awaiting response. No impact. No action. Completed on 15/12
6 | 1.3.6.2.4.4 |  |  |  |  | Test Scenarios | 100% | Thu 02/11/23 | Thu 30/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.4.1 | T3 | T3-DB-0031 | SITAG |  | EES test scenarios submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 232FS+15 days | 241FS+20 days,244FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 7/11 - Red because not submitted. No impact. No action
7 | 1.3.6.2.4.4.2 | T3 | T3-DB-0121 | SITAG |  | EES Test scenarios MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 240FS+20 days | 246 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 5/12- Red because Assurance conducted. Comments issued and awaiting response. No impact. No action. Completed on 15/12
6 | 1.3.6.2.4.5 |  |  |  |  | PIT execution | 100% | Fri 10/11/23 | Fri 19/01/24 | 51 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 269 days | 0 days | -269 days | N/A |  | 5 | Yes
7 | 1.3.6.2.4.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Fri 10/11/23 | Fri 05/01/24 | 41 days | Fri 10/11/23 | Fri 05/01/24 | 235 | 245 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.4.5.2 |  |  |  |  | PIT Execution | 100% | Fri 10/11/23 | Fri 05/01/24 | 41 days | Mon 31/10/22 | Fri 05/01/24 | 240FS+5 days | 245 | 269 days | 0 days | -269 days | PP |  | 5 | Yes
7 | 1.3.6.2.4.5.3 | T3 | T3-DB-0122 | SITAG |  | EES PIT Completion Report submitted to Programme for assurance | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 243244 | 246FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 19/12 - Completed on 15/12
7 | 1.3.6.2.4.5.4 | T3 | T3-DB-0123 | SITAG |  | EES PIT Completion Report MHHS Review Completed | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 233,238,241,245FS+10 days | 786 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 19/12 - Completed on 15/12
5 | 1.3.6.2.5 |  |  |  |  | Registration Services DBT CIT (Entering at Interval 2) | 100% | Fri 28/07/23 | Fri 03/11/23 | 70 days | Fri 28/07/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.2.5.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 28/07/23 | Fri 22/09/23 | 40 days | Fri 28/07/23 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.1.1 | T3 | T3-DB-0028 | SITAG | MHHS-ART073 | Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 28/07/23 | Fri 28/07/23 | 0 days | Fri 28/07/23 | Fri 28/07/23 |  | 250FS+40 days,252FS+10 days,254FS+15 days,257FS+15 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.2.5.1.2 | T3 | T3-DB-0124 | SITAG |  | Registration Services Test approach and plan MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 249FS+40 days | 263 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
6 | 1.3.6.2.5.2 |  |  |  |  | Test Readiness Report | 100% | Mon 14/08/23 | Fri 08/09/23 | 20 days | Fri 11/08/23 | Fri 20/10/23 |  |  | 1 day | -30 days | -31 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.2.1 |  |  |  |  | Test readiness reporting | 100% | Mon 14/08/23 | Fri 08/09/23 | 20 days | Fri 11/08/23 | Fri 20/10/23 | 249FS+10 days | 260 | 1 day | -30 days | -31 days | PP |  | 5 | Yes
6 | 1.3.6.2.5.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 01/09/23 | Fri 29/09/23 | 20 days | Fri 01/09/23 | Fri 29/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.3.1 | T3 | T3-DB-0042 | SITAG | MHHS-ART009 | Registration Services RTTM submitted to Programme for assurance | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 249FS+15 days | 255FS+20 days | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.5.3.2 | T3 | T3-DB-0125 | SITAG |  | Registration Services RTTM MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 254FS+20 days | 263 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 4/10 - Red because small number of comments still to be resolved, will be completed no later than 3/11 ahead of Interval 2 Readiness Assessment
6 | 1.3.6.2.5.4 |  |  |  |  | Test Scenarios | 100% | Fri 01/09/23 | Fri 29/09/23 | 20 days | Fri 01/09/23 | Fri 29/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.4.1 | T3 | T3-DB-0044 | SITAG |  | Registration Services test scenarios submitted to Programme for assurance | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 249FS+15 days | 258FS+20 days,261FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.2.5.4.2 | T3 | T3-DB-0126 | SITAG |  | Registration Services Test scenarios MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 257FS+20 days | 263 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG
6 | 1.3.6.2.5.5 |  |  |  |  | PIT execution | 100% | Mon 11/09/23 | Fri 03/11/23 | 40 days | Mon 11/09/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.2.5.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 11/09/23 | Wed 25/10/23 | 33 days | Mon 11/09/23 | Fri 20/10/23 | 252 | 262 | 0 days | 3 days | 3 days | PP |  | 5 | Yes
7 | 1.3.6.2.5.5.2 |  |  |  |  | PIT Execution | 100% | Mon 11/09/23 | Fri 20/10/23 | 30 days | Mon 11/09/23 | Fri 20/10/23 | 257FS+5 days | 262 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 17/10 - Amber because St Clements assessment. No impact. Being monitored
7 | 1.3.6.2.5.5.3 | T3 | T3-DB-0127 | SITAG |  | Registration Services PIT (CIT interval 2) Completion Report submitted to Programme for assurance | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 260261 | 263FS+7 days | 3 days | 3 days | 0 days | PP |  | 5.1 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 24/10 - Red because 3 day delay to SCS PIT completion. No impact to CIT Interval 2.
7 | 1.3.6.2.5.5.4 | T3 | T3-DB-0128 | SITAG |  | Registration Services PIT (CIT interval 2) Completion Report MHHS Review Completed | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 250,255,258,262FS+7 days | 658 | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 17/10 - Amber because St Clements assessment. No impact. Being monitored
4 | 1.3.6.3 |  |  |  |  | SIT Participants DBT | 89% | Fri 11/08/23 | Fri 20/12/24 | 356 days | Mon 31/10/22 | Fri 20/09/24 |  |  | 204 days | 65 days | -139 days | N/A |  | 5 | Yes
5 | 1.3.6.3.1 |  |  |  |  | All Data Services DBT CIT (Entering at Interval 3) | 100% | Fri 11/08/23 | Fri 17/11/23 | 71 days | Mon 31/10/22 | Fri 17/11/23 |  |  | 204 days | 0 days | -204 days | N/A |  | 5 | Yes
6 | 1.3.6.3.1.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 11/08/23 | Thu 21/09/23 | 30 days | Fri 11/08/23 | Thu 21/09/23 |  |  | -1 day | 0 days | 1 day | N/A |  | 5 | Yes
7 | 1.3.6.3.1.1.1 | T3 | T3-DB-0038 | SITAG |  | All Data Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 11/08/23 | Fri 11/08/23 | 0 days | Fri 11/08/23 | Fri 11/08/23 |  | 268FS+30 days,270FS+10 days,272FS+29 days,275FS+29 days | -1 day | -1 day | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.1.2 | T3 | T3-DB-0129 | SITAG |  | All Data Services Test approach and plans MHHS Review Completed | 100% | Thu 21/09/23 | Thu 21/09/23 | 0 days | Thu 21/09/23 | Thu 21/09/23 | 267FS+30 days | 281 | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. Red due to high volume to be reviewed. Date change under consideration. Review will be completed no later than 17/11 ahead of Interval 3 Readiness Assessment
6 | 1.3.6.3.1.2 |  |  |  |  | Test Readiness Report | 100% | Fri 25/08/23 | Fri 08/09/23 | 11 days | Fri 25/08/23 | Fri 08/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 25/08/23 | Fri 08/09/23 | 11 days | Fri 25/08/23 | Fri 08/09/23 | 267FS+10 days | 278 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.3.1.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Wed 20/09/23 | Fri 29/09/23 | 7 days | Fri 22/09/23 | Fri 29/09/23 |  |  | -2 days | 0 days | 2 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.3.1 | T3 | T3-DB-0058 | SITAG |  | All Data Services RTTMs submitted to Programme for assurance | 100% | Wed 20/09/23 | Wed 20/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 267FS+29 days | 273FS+7 days | -2 days | -2 days | 0 days | PP |  | 5.7 | Yes
7 | 1.3.6.3.1.3.2 | T3 | T3-DB-0130 | SITAG |  | All Data Services RTTMs MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 272FS+7 days | 281 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG Approved at TMAG on 20/9. Red due to high volume to be reviewed. Date change under consideration. Review will be completed no later than 17/11 ahead of Interval 3 Readiness Assessment
6 | 1.3.6.3.1.4 |  |  |  |  | Test Scenarios | 100% | Wed 20/09/23 | Thu 28/09/23 | 6 days | Fri 22/09/23 | Thu 28/09/23 |  |  | -2 days | 0 days | 2 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.4.1 | T3 | T3-DB-0056 | SITAG |  | All Data Services test scenarios' submitted to Programme for assurance | 100% | Wed 20/09/23 | Wed 20/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 267FS+29 days | 276FS+6 days,279FS+5 days | -2 days | -2 days | 0 days | PP |  | 5.7 | Yes
7 | 1.3.6.3.1.4.2 | T3 | T3-DB-0131 | SITAG |  | All Data Services Test scenarios' MHHS Review Completed | 100% | Thu 28/09/23 | Thu 28/09/23 | 0 days | Thu 28/09/23 | Thu 28/09/23 | 275FS+6 days | 281 | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. Red due to high volume to be reviewed. Date change under consideration. Review will be completed no later than 17/11 ahead of Interval 3 Readiness Assessment
6 | 1.3.6.3.1.5 |  |  |  |  | PIT execution | 100% | Mon 11/09/23 | Fri 17/11/23 | 50 days | Mon 31/10/22 | Fri 17/11/23 |  |  | 225 days | 0 days | -225 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 11/09/23 | Fri 03/11/23 | 40 days | Mon 31/10/22 | Fri 27/10/23 | 270 | 280 | 225 days | 5 days | -220 days | PP |  | 5 | Yes |  | 10/10 - LC - red because date in the past, not all participants have provided reports. No impact. No action
7 | 1.3.6.3.1.5.2 |  |  |  |  | PIT Execution | 100% | Thu 28/09/23 | Fri 03/11/23 | 27 days | Mon 31/10/22 | Fri 03/11/23 | 275FS+5 days | 280 | 238 days | 0 days | -238 days | PP |  | 5 | Yes |  | 10/10 - LC - red because date in the past, acceptable for some participants to have not started PIT yet
7 | 1.3.6.3.1.5.3 | T3 | T3-DB-0132 | SITAG |  | All Data Services PIT Completion Reports submitted to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 278279 | 281FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.11 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9
7 | 1.3.6.3.1.5.4 | T3 | T3-DB-0133 | SITAG |  | All Data Services PIT Completion Reports MHHS Review Completed | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 268,273,276,280FS+10 days | 690 | 0 days | 0 days | 0 days | SI Test |  | 5.13 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 21/11-Red because 1 report remains outstanding due to close 22/11. Completed on 22/11
5 | 1.3.6.3.2 |  |  |  |  | All Metering Services DBT CIT (Entering at Interval 4) | 100% | Fri 25/08/23 | Fri 01/12/23 | 70 days | Mon 31/10/22 | Fri 01/12/23 |  |  | 215 days | 0 days | -215 days | N/A |  | 5 | Yes
6 | 1.3.6.3.2.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 25/08/23 | Fri 20/10/23 | 40 days | Fri 25/08/23 | Fri 20/10/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.1.1 | T3 | T3-DB-0040 | SITAG |  | All Metering Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 25/08/23 | Fri 25/08/23 | 0 days | Fri 25/08/23 | Fri 25/08/23 |  | 285FS+40 days,287FS+10 days,289FS+15 days,292FS+15 days | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.2.1.2 | T3 | T3-DB-0134 | SITAG |  | All Metering Services Test approach and plans MHHS Review Completed | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 284FS+40 days | 298 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 7/10 - Red due to high volume to be reviewed. Date change under consideration. Review will be completed no later than 04/12 ahead of Interval 4 Readiness Assessment
6 | 1.3.6.3.2.2 |  |  |  |  | Test Readiness Report | 100% | Mon 11/09/23 | Mon 25/09/23 | 11 days | Fri 08/09/23 | Fri 17/11/23 |  |  | 1 day | -39 days | -40 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.2.1 |  |  |  |  | Test readiness reporting | 100% | Mon 11/09/23 | Mon 25/09/23 | 11 days | Fri 08/09/23 | Fri 17/11/23 | 284FS+10 days | 295 | 1 day | -39 days | -40 days | PP |  | 5 | Yes
6 | 1.3.6.3.2.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 15/09/23 | Fri 27/10/23 | 30 days | Fri 15/09/23 | Fri 27/10/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.3.1 | T3 | T3-DB-0048 | SITAG | MHHS-ART009 | All Metering Services RTTMs submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 284FS+15 days | 290FS+30 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 13/9 - name change at TMAG. Red because 9/10 received. Approved at TMAG on 20/9
7 | 1.3.6.3.2.3.2 | T3 | T3-DB-0135 | SITAG |  | All Metering Services MHHS Reviews Completed | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 289FS+30 days | 298 | 0 days | 0 days | 0 days | SI Test |  | 5.13 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 17/10 - Red because assurance reviews open comments remain outstanding. Final reviews will be completed no later than 4/12 ahead of Interval 4 Readiness Report
6 | 1.3.6.3.2.4 |  |  |  |  | Test Scenarios | 100% | Fri 15/09/23 | Fri 27/10/23 | 30 days | Fri 15/09/23 | Fri 27/10/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.4.1 | T3 | T3-DB-0050 | SITAG |  | All Metering Services test scenarios' submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 284FS+15 days | 293FS+30 days,296FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 13/9 - name change at TMAG Red because 9/10 . Approved at TMAG on 20/9
7 | 1.3.6.3.2.4.2 | T3 | T3-DB-0136 | SITAG |  | All Metering Services Test scenarios' MHHS Review Completed | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 292FS+30 days | 298 | 0 days | 0 days | 0 days | SI Test |  | 5.13 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 17/10 - Red because assurance reviews open comments remain outstanding. Final reviews will be completed no later than 4/12 ahead of Interval 4 Readiness Report
6 | 1.3.6.3.2.5 |  |  |  |  | PIT execution | 100% | Mon 25/09/23 | Fri 01/12/23 | 50 days | Mon 31/10/22 | Fri 01/12/23 |  |  | 235 days | 0 days | -235 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Tue 26/09/23 | Fri 17/11/23 | 39 days | Tue 26/09/23 | Fri 17/11/23 | 287 | 297 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.2.5.2 |  |  |  |  | PIT Execution | 100% | Mon 25/09/23 | Fri 17/11/23 | 40 days | Mon 31/10/22 | Fri 17/11/23 | 292FS+5 days | 297 | 235 days | 0 days | -235 days | PP |  | 5 | Yes
7 | 1.3.6.3.2.5.3 | T3 | T3-DB-0137 | SITAG |  | All Metering Services PIT Completion Reports submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 295296 | 298FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.13 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 21/11-Red because not all test completion reports received. No impact. No action
7 | 1.3.6.3.2.5.4 | T3 | T3-DB-0138 | SITAG |  | All Metering Services PIT Completion Reports MHHS Review Completed | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 285,290,293,297FS+10 days | 722FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5.13 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9.28/11 - Amber because late delivery of some completion reports impairing ability to conclude on time. Expediting reviews ahead of RA 4
5 | 1.3.6.3.3 |  |  |  |  | All SIT Programme Participants PIT (SIT Functional) | 77% | Fri 17/11/23 | Fri 20/12/24 | 286 days | Fri 30/12/22 | Fri 20/09/24 |  |  | 230 days | 65 days | -165 days | N/A |  | 5 | Yes
6 | 1.3.6.3.3.1 |  |  |  |  | Test Approach & Plans | 100% | Fri 17/11/23 | Thu 11/01/24 | 40 days | Fri 17/11/23 | Thu 11/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.1.1 | T3 | T3-DB-0093 | SITAG |  | SIT Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 |  | 302FS+40 days,304FS+10 days,306FS+15 days,309FS+15 days | 0 days | 0 days | 0 days | PP |  | 5.16 | Yes |  | 12/9 - name change to TMAG. Approved at TMAG on 20/9. 5/12-Red because not all test approach and plans received. Escalated at FTIG and PSG. Completed 4/1/24
7 | 1.3.6.3.3.1.2 | T3 | T3-DB-0139 | SITAG |  | All SIT Functional Test approach and plans MHHS Reviews Completed | 100% | Thu 11/01/24 | Thu 11/01/24 | 0 days | Thu 11/01/24 | Thu 11/01/24 | 301FS+40 days | 315 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 16/1- All remaining / late artefacts now received and reviewed by Programme with feedback provided to PPs. Awaiting PPs’ final feedback. Approved complete at SITAG on 21/2/24
6 | 1.3.6.3.3.2 |  |  |  |  | Test Readiness Reports | 100% | Fri 01/12/23 | Fri 15/12/23 | 11 days | Fri 01/12/23 | Fri 09/02/24 |  |  | 0 days | -40 days | -40 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 01/12/23 | Fri 15/12/23 | 11 days | Fri 01/12/23 | Fri 15/12/23 | 301FS+10 days | 312 | 0 days | 0 days | -40 days | PP |  | 5.2 | Yes
6 | 1.3.6.3.3.3 |  |  |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | Thu 07/12/23 | Thu 18/01/24 | 30 days | Thu 07/12/23 | Thu 18/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.3.1 | T3 | T3-DB-0091 | SITAG |  | SIT Functional PIT RTTM submitted to Programme for assurance | 100% | Thu 07/12/23 | Thu 07/12/23 | 0 days | Thu 07/12/23 | Thu 07/12/23 | 301FS+15 days | 307FS+30 days | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes |  | 12/9 - name and date change to TMAG. Approved at TMAG on 20/9. 20/02 - 1 PP artefact not yet received. Escalated at FTIG
7 | 1.3.6.3.3.3.2 | T3 | T3-DB-0140 | SITAG |  | All SIT Functional RTTMs MHHS Reviews Completed | 100% | Thu 18/01/24 | Thu 18/01/24 | 0 days | Thu 18/01/24 | Thu 18/01/24 | 306FS+30 days | 315 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 23/01 - Late due to late delivery of PP artefacts for review
6 | 1.3.6.3.3.4 |  |  |  |  | Test Scenarios | 100% | Thu 07/12/23 | Thu 18/01/24 | 30 days | Thu 07/12/23 | Thu 18/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.3.3.4.1 | T3 | T3-DB-0089 | SITAG |  | SIT Functional PIT test scenarios submitted to Programme for assurance | 100% | Thu 07/12/23 | Thu 07/12/23 | 0 days | Thu 07/12/23 | Thu 07/12/23 | 301FS+15 days | 310FS+30 days,313FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes |  | 12/9 - name and date change to TMAG. Approved at TMAG on 20/9. 20/02 - 2 PP artefacts not yet received. Escalated at FTIG
7 | 1.3.6.3.3.4.2 | T3 | T3-DB-0141 | SITAG |  | All SIT Functional Test scenarios' MHHS Reviews Completed | 100% | Thu 18/01/24 | Thu 18/01/24 | 0 days | Thu 18/01/24 | Thu 18/01/24 | 309FS+30 days | 315 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 12/12 - Late due to late delivery of PP artefacts for review
6 | 1.3.6.3.3.5 |  |  |  |  | PIT execution | 100% | Fri 15/12/23 | Fri 23/02/24 | 51 days | Fri 30/12/22 | Fri 23/02/24 |  |  | 250 days | 0 days | -250 days | N/A |  | 5 | Yes
7 | 1.3.6.3.3.5.1 |  |  |  |  | PIT Test Execution Progress Reports | 100% | Mon 18/12/23 | Fri 09/02/24 | 40 days | Mon 18/12/23 | Fri 09/02/24 | 304 | 314 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 16/4: completed 12/4
7 | 1.3.6.3.3.5.2 |  |  |  |  | PIT Execution | 100% | Fri 15/12/23 | Fri 09/02/24 | 41 days | Fri 30/12/22 | Fri 09/02/24 | 309FS+5 days | 314 | 250 days | 1 day | -249 days | PP |  | 5 | Yes |  | 16/4: completed 12/4
7 | 1.3.6.3.3.5.3 | T3 | T3-DB-0087 | SITAG |  | All SIT Functional PIT Completion Reports submitted to Programme for Assurance | 100% | Fri 09/02/24 | Fri 09/02/24 | 0 days | Fri 09/02/24 | Fri 09/02/24 | 312313 | 315FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.19 | Yes |  | 1/9 - name change at TMAG. Approved at TMAG on 20/9. 20/2 - 23 reports received. The majority of late deliveries have been discussed and agreed with the Programme.5/3 - Approved 1/3 SITAG with work off
7 | 1.3.6.3.3.5.4 | T3 | T3-DB-0142 | SITAG |  | All SIT Functional PIT Completion Reports MHHS Review Completed | 100% | Fri 23/02/24 | Fri 23/02/24 | 0 days | Fri 23/02/24 | Fri 23/02/24 | 302,307,310,314FS+10 days | 863 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 27/2 - Target date missed due to late delivery of some reports. 5/3 - Approved 1/3 SITAG with work off
6 | 1.3.6.3.3.6 |  |  |  |  | All SIT Programme Participants PIT (SIT Migration) | 100% | Fri 16/02/24 | Fri 24/05/24 | 71 days | Fri 31/03/23 | Fri 24/05/24 |  |  | 230 days | 0 days | -230 days | N/A |  | 5.1 | Yes
7 | 1.3.6.3.3.6.1 |  |  |  |  | Test Approach & Plans | 100% | Fri 16/02/24 | Thu 11/04/24 | 40 days | Fri 16/02/24 | Thu 11/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.1.1 | T3 | T3-DB-0143 | SITAG |  | All SIT Migration PIT Test Approach & Plans submitted to Programme for assurance | 100% | Fri 16/02/24 | Fri 16/02/24 | 0 days | Fri 16/02/24 | Fri 16/02/24 |  | 319FS+40 days,321FS+10 days,323FS+15 days,326FS+15 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9.. 19/3 - 33/35 received
8 | 1.3.6.3.3.6.1.2 | T3 | T3-DB-0144 | SITAG |  | All SIT Migration PIT Test approach and plans MHHS Reviews Completed | 100% | Thu 11/04/24 | Thu 11/04/24 | 0 days | Thu 11/04/24 | Thu 11/04/24 | 318FS+40 days | 332 | 0 days | 0 days | 0 days | SI Test |  | 5.23 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 26/3: At risk because of late delivery of PIT test approach and plans by PPs. 16/4: All received. All but 1 reviewed
7 | 1.3.6.3.3.6.2 |  |  |  |  | Test Readiness Reports | 100% | Fri 01/03/24 | Fri 15/03/24 | 11 days | Fri 01/03/24 | Fri 10/05/24 |  |  | 0 days | -40 days | -40 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 01/03/24 | Fri 15/03/24 | 11 days | Fri 01/03/24 | Fri 10/05/24 | 318FS+10 days | 329 | 0 days | -40 days | -40 days | PP |  | 5.2 | Yes
7 | 1.3.6.3.3.6.3 |  |  |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | Thu 07/03/24 | Thu 18/04/24 | 30 days | Thu 07/03/24 | Thu 18/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.3.1 | T3 | T3-DB-0145 | SITAG |  | All SIT Migration PIT RTTMs submitted to Programme for assurance | 100% | Thu 07/03/24 | Thu 07/03/24 | 0 days | Thu 07/03/24 | Thu 07/03/24 | 318FS+15 days | 324FS+30 days | 0 days | 0 days | 0 days | PP |  | 5.23 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 22/04: 33/34 received. Remainder to be chased
8 | 1.3.6.3.3.6.3.2 | T3 | T3-DB-0146 | SITAG |  | All SIT Migration RTTMs MHHS Reviews Completed | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 323FS+30 days | 332 | 0 days | 0 days | 0 days | SI Test |  | 5.25 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 26/3: At risk because of late delivery of RTTMs by PPs 30/4: Late because of late delivery or RTTMS 33/34 reviewed
7 | 1.3.6.3.3.6.4 |  |  |  |  | Test Scenarios | 100% | Thu 07/03/24 | Thu 18/04/24 | 30 days | Thu 07/03/24 | Thu 18/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.6.4.1 | T3 | T3-DB-0147 | SITAG |  | All SIT Migration PIT test scenarios submitted to Programme for assurance | 100% | Thu 07/03/24 | Thu 07/03/24 | 0 days | Thu 07/03/24 | Thu 07/03/24 | 318FS+15 days | 327FS+30 days,330FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.23 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 22/04: 31/34 received. Remainder to be chased
8 | 1.3.6.3.3.6.4.2 | T3 | T3-DB-0148 | SITAG |  | All SIT Migration Test scenarios MHHS Reviews Completed | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 326FS+30 days | 332 | 0 days | 0 days | 0 days | SI Test |  | 5.25 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 26/3: At risk because of late delivery of PIT test scenarios by PPs. 30/4: Late because of late delivery or Test scenarios. 33/34 reviewed
7 | 1.3.6.3.3.6.5 |  |  |  |  | PIT execution | 100% | Fri 15/03/24 | Fri 24/05/24 | 51 days | Fri 31/03/23 | Fri 24/05/24 |  |  | 250 days | 0 days | -250 days | N/A |  | 5.1 | Yes
8 | 1.3.6.3.3.6.5.1 |  |  |  |  | PIT Test Execution Progress Reports | 100% | Mon 18/03/24 | Fri 10/05/24 | 40 days | Mon 18/03/24 | Fri 10/05/24 | 321 | 331 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.6.5.2 |  |  |  |  | PIT Execution | 100% | Fri 15/03/24 | Fri 10/05/24 | 41 days | Fri 31/03/23 | Fri 10/05/24 | 326FS+5 days | 331 | 250 days | 1 day | -249 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.6.5.3 | T3 | T3-DB-0149 | SITAG |  | All SIT Migration PIT Completion Reports submitted to Programme for assurance | 100% | Fri 10/05/24 | Fri 10/05/24 | 0 days | Fri 10/05/24 | Fri 10/05/24 | 329330 | 332FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | Sufficient PIT completion reports on track, some are known to be late. 11/6: 29/33 received. Small number of PPs will be PIT complete late, but before SIT migration. 1 PP will be post SIT Migration start. 11/6: eSITAG approved on 3/6 subject to Work-off
8 | 1.3.6.3.3.6.5.4 | T3 | T3-DB-0150 | SITAG |  | All SIT Migration PIT Completion Reports MHHS Review Completed | 100% | Fri 24/05/24 | Fri 24/05/24 | 0 days | Fri 24/05/24 | Fri 24/05/24 | 319,324,327,331FS+10 days | 920 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 14/5: Won't deliver to forecast because of late delivery of by some PPs of PIT completion report. 11/6: eSITAG approved on 3/6 subject to Work-off
6 | 1.3.6.3.3.7 |  |  |  |  | All SIT Programme Participants PIT (SIT Non Functional) | 64% | Fri 12/07/24 | Fri 20/12/24 | 116 days | Fri 23/06/23 | Fri 16/08/24 |  |  | 275 days | 90 days | -185 days | N/A |  | 5.1 | Yes
7 | 1.3.6.3.3.7.1 |  |  |  |  | Test Approach & Plan | 0% | Fri 27/09/24 | Thu 21/11/24 | 39 days | Fri 10/05/24 | Thu 04/07/24 |  |  | 100 days | 99 days | -1 day | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.7.1.1 | T3 | T3-DB-0151 | SITAG |  | SIT Non-Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 75% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 10/05/24 | Fri 10/05/24 |  | 338FS+10 days,340FS+26 days,343FS+26 days,336FS+40 days | 100 days | 100 days | 0 days | PP |  | 5.3 | Yes |  | 34/34 plans have been submitted to the Programme. Because of the delay to all plans being submitted there is an increased risk to completion of SIT Non-Functional PIT. Re-forecasting the completion date isn’t possible as delivery is dependent on the PPs
8 | 1.3.6.3.3.7.1.2 | T3 | T3-DB-0152 | SITAG |  | SIT Non-Functional Test approach and plan MHHS Review Completed | 100% | Thu 21/11/24 | Thu 21/11/24 | 0 days | Thu 04/07/24 | Thu 04/07/24 | 335FS+40 days | 349 | 99 days | 99 days | 0 days | SI Test |  | 5.3 | Yes |  | 14/34 test approaches completed. Late because the completion of the review is dependant on the delivery of all of the SIT Non-Functional Test Approach and Plans from the PPs. This increases the risk to SIT Non-Functional PIT completion
7 | 1.3.6.3.3.7.2 |  |  |  |  | Test Readiness Report | 85% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 24/05/24 | Fri 02/08/24 |  |  | 95 days | 57 days | -38 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.7.2.1 |  |  |  |  | Test readiness reporting | 85% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 24/05/24 | Fri 02/08/24 | 335FS+10 days | 346 | 95 days | 57 days | -38 days | PP |  | 5.2 | Yes
7 | 1.3.6.3.3.7.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 0% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Thu 30/05/24 | Thu 11/07/24 |  |  | 111 days | 101 days | -10 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.7.3.1 | T3 | T3-DB-0153 | SITAG |  | SIT Non-Functional PIT RTTM submitted to Programme for assurance | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 335FS+26 days | 341FS+20 days | 111 days | 111 days | 0 days | PP |  | 5.8 | Yes |  | 33/34 RTTMs have been submitted to the Programme. Because of the delay to all RTTMs being submitted there is an increased risk to completion of SIT Non-Functional PIT. Re-forecasting the completion date isn’t possible as delivery is dependent on the PPs.
8 | 1.3.6.3.3.7.3.2 | T3 | T3-DB-0154 | SITAG |  | SIT Non-Functional RTTM MHHS Review Completed | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Thu 11/07/24 | Thu 11/07/24 | 340FS+20 days | 349 | 101 days | 101 days | 0 days | SI Test |  | 5.8 | Yes |  | 18/34 reviewed. As per T3-DB-0153, Status red until remaining RTTMs submitted and reviewed....
7 | 1.3.6.3.3.7.4 |  |  |  |  | Test Scenarios | 0% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Thu 30/05/24 | Thu 11/07/24 |  |  | 111 days | 101 days | -10 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.7.4.1 | T3 | T3-DB-0155 | SITAG |  | SIT Non-Functional PIT test scenarios submitted to Programme for assurance | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 335FS+26 days | 344FS+20 days,347FS+5 days | 111 days | 111 days | 0 days | PP |  | 5.8 | Yes |  | 29/34 test scenarios have been submitted to the Programme. Because of the delay to all test scenarios being submitted there is an increased risk to completion of SIT Non-Functional PIT. Re-forecasting the completion date isn’t possible as delivery is depe
8 | 1.3.6.3.3.7.4.2 | T3 | T3-DB-0156 | SITAG |  | SIT Non-Functional Test scenarios MHHS Review Completed | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Thu 11/07/24 | Thu 11/07/24 | 343FS+20 days | 349 | 101 days | 101 days | 0 days | SI Test |  | 5.8 | Yes |  | 16/34 scenarios have been completed. Date missed because the completion of the review is dependent on the delivery of all of the SIT Non-Functional Test Scenarios from the PPs. This increases the risk to SIT Non-Functional PIT completion
7 | 1.3.6.3.3.7.5 |  |  |  |  | PIT execution | 61% | Fri 12/07/24 | Fri 20/12/24 | 116 days | Fri 23/06/23 | Fri 16/08/24 |  |  | 275 days | 90 days | -185 days | N/A |  | 5.1 | Yes
8 | 1.3.6.3.3.7.5.1 |  |  |  |  | PIT Test Execution Progress Report | 56% | Mon 15/07/24 | Thu 21/11/24 | 50 days | Mon 10/06/24 | Thu 01/08/24 | 338 | 348 | 25 days | 80 days | 11 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.7.5.2 |  |  |  |  | PIT Execution | 66% | Fri 12/07/24 | Fri 29/11/24 | 44 days | Fri 23/06/23 | Fri 02/08/24 | 343FS+5 days | 348 | 275 days | 86 days | -246 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.7.5.3 | T3 | T3-DB-0157 | SITAG |  | SIT Non-Functional PIT Completion Report submitted to Programme for assurance | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 02/08/24 | Fri 02/08/24 | 346347 | 349FS+15 days | 85 days | 85 days | 0 days | PP |  | 5.1 | Yes |  | 18/34 SIT Non-Functional PIT RTTMs have been submitted to the Programme. Because of the delay to all RTTMs being submitted there is an increased risk to completion of SIT Operational PIT. Re-forecasting the completion date isn’t possible as delivery is de
8 | 1.3.6.3.3.7.5.4 | T3 | T3-DB-0158 | SITAG |  | SIT Non-Functional PIT Completion Report MHHS Review Completed | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 16/08/24 | Fri 16/08/24 | 336,341,344,348FS+15 days | 981 | 90 days | 90 days | 0 days | SI Test |  | 5.8 | Yes |  | 3/34 reviewed. As per T3-DB-0157. Status red until remaining PIT Test Approach and Plans submitted and reviewed....
6 | 1.3.6.3.3.8 |  |  |  |  | All SIT Programme Participants PIT (SIT Operational) | 46% | Fri 12/07/24 | Fri 20/12/24 | 116 days | Fri 14/06/24 | Fri 20/09/24 |  |  | 20 days | 65 days | 45 days | N/A |  | 5.1 | Yes
7 | 1.3.6.3.3.8.1 |  |  |  |  | Test Approach & Plan | 0% | Fri 27/09/24 | Thu 21/11/24 | 40 days | Fri 14/06/24 | Thu 08/08/24 |  |  | 75 days | 75 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.8.1.1 | T3 | T3-DB-0159 | SITAG |  | SIT Operational PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 14/06/24 | Fri 14/06/24 |  | 353FS+40 days,355FS+10 days,357FS+26 days,360FS+26 days | 75 days | 75 days | 0 days | PP |  | 5.8 | Yes |  | 32/34 test approach and plans have been submitted to the Programme. Because of the delay to all Test Approach and plans being submitted there is an increased risk to completion of SIT Operational PIT. Re-forecasting the completion date isn’t possible as d
8 | 1.3.6.3.3.8.1.2 | T3 | T3-DB-0160 | SITAG |  | SIT Operational Test approach and plan MHHS Review Completed | 0% | Thu 21/11/24 | Thu 21/11/24 | 0 days | Thu 08/08/24 | Thu 08/08/24 | 352FS+40 days | 366 | 75 days | 75 days | 0 days | SI Test |  | 5.8 | Yes |  | 19/34 reviewed. As per T3-DB-0159, Status red until remaining PIT Test Approach and Plans submitted and reviewed....
7 | 1.3.6.3.3.8.2 |  |  |  |  | Test Readiness Report | 42% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 28/06/24 | Fri 06/09/24 |  |  | 70 days | 32 days | -38 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.8.2.1 |  |  |  |  | Test readiness reporting | 42% | Fri 04/10/24 | Tue 22/10/24 | 13 days | Fri 28/06/24 | Fri 06/09/24 | 352FS+10 days | 363 | 70 days | 32 days | -38 days | PP |  | 5.2 | Yes
7 | 1.3.6.3.3.8.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 0% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Thu 04/07/24 | Thu 15/08/24 |  |  | 86 days | 76 days | -10 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.8.3.1 | T3 | T3-DB-0161 | SITAG |  | SIT Operational PIT RTTM submitted to Programme for assurance | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Thu 04/07/24 | Thu 04/07/24 | 352FS+26 days | 358FS+20 days | 86 days | 86 days | 0 days | PP |  | 5.8 | Yes |  | 23/34 SIT Operational PIT RTTMs have been submitted to the Programme. Because of the delay to all RTTMs being submitted there is an increased risk to completion of SIT Operational PIT. Re-forecasting the completion date isn’t possible as delivery is depen
8 | 1.3.6.3.3.8.3.2 | T3 | T3-DB-0162 | SITAG |  | SIT Operational RTTM MHHS Review Completed | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Thu 15/08/24 | Thu 15/08/24 | 357FS+20 days | 366 | 76 days | 76 days | 0 days | SI Test |  | 5.8 | Yes |  | 13/34 reviewed. As per T3-DB-0161. Status red until remaining PIT Test Approach and Plans submitted and reviewed....
7 | 1.3.6.3.3.8.4 |  |  |  |  | Test Scenarios | 0% | Fri 01/11/24 | Fri 29/11/24 | 20 days | Thu 04/07/24 | Thu 15/08/24 |  |  | 86 days | 76 days | -10 days | N/A |  | 5.2 | Yes
8 | 1.3.6.3.3.8.4.1 | T3 | T3-DB-0163 | SITAG |  | SIT Operational PIT test scenarios submitted to Programme for assurance | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Thu 04/07/24 | Thu 04/07/24 | 352FS+26 days | 361FS+20 days,364 | 86 days | 86 days | 0 days | PP |  | 5.8 | Yes |  | 22/34 SIT Operational PIT test scenarios have been submitted to the Programme. Because of the delay to all SIT Operational PIT test scenarios being submitted there is increased risk to the completion of SIT Operational PIT. Re-forecasting the completion d
8 | 1.3.6.3.3.8.4.2 | T3 | T3-DB-0164 | SITAG |  | SIT Operational Test scenarios MHHS Review Completed | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Thu 15/08/24 | Thu 15/08/24 | 360FS+20 days | 366 | 76 days | 76 days | 0 days | SI Test |  | 5.8 | Yes |  | 13/34 reviewed. As per T3-DB-0163. Status red until remaining PIT Test Approach and Plans submitted and reviewed....
7 | 1.3.6.3.3.8.5 |  |  |  |  | PIT execution | 47% | Fri 12/07/24 | Fri 20/12/24 | 116 days | Fri 12/07/24 | Fri 20/09/24 |  |  | 0 days | 65 days | 65 days | N/A |  | 5.1 | Yes
8 | 1.3.6.3.3.8.5.1 |  |  |  |  | PIT Test Execution Progress Report | 45% | Mon 15/07/24 | Thu 21/11/24 | 40 days | Mon 15/07/24 | Fri 06/09/24 | 355 | 365 | 0 days | 54 days | 0 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.8.5.2 |  |  |  |  | PIT Execution | 49% | Fri 12/07/24 | Fri 29/11/24 | 39 days | Fri 12/07/24 | Fri 06/09/24 | 360 | 365 | 0 days | 60 days | -2 days | PP |  | 5.1 | Yes
8 | 1.3.6.3.3.8.5.3 | T3 | T3-DB-0165 | SITAG |  | SIT Operational PIT Completion Report submitted to Programme for assurance | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Fri 06/09/24 | Fri 06/09/24 | 363364 | 366FS+15 days | 60 days | 60 days | 0 days | PP |  | 5.1 | Yes |  | 19/08/24 - Date at risk because of potential delay to submissions for SIT Operational PIT completion reports. Impact may be a delay to the start of SIT Operational Testing. Bilateral’s scheduled for week commencing 19/8....
8 | 1.3.6.3.3.8.5.4 | T3 | T3-DB-0166 | SITAG |  | SIT Operational PIT Completion Report MHHS Review Completed | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 20/09/24 | Fri 20/09/24 | 353,358,361,365FS+15 days | 1051 | 65 days | 65 days | 0 days | SI Test |  | 5.8 | Yes |  | Date at risk because of potential delay to submissions for SIT Operational PIT completion reports. Impact may be a delay to the start of SIT Operational Testing. Continue engagement with PPs...
5 | 1.3.6.3.4 |  |  |  |  | All Suppliers DBT CIT (Entering at Interval 5) | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Mon 31/10/22 | Fri 22/12/23 |  |  | 229 days | 0 days | -229 days | N/A |  | 5 | Yes
6 | 1.3.6.3.4.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 15/09/23 | Thu 12/10/23 | 20 days | Fri 15/09/23 | Thu 12/10/23 |  |  | -1 day | 0 days | 1 day | N/A |  | 5 | Yes
7 | 1.3.6.3.4.1.1 | T3 | T3-DB-0046 | SITAG |  | All SIT Suppliers Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 |  | 370FS+20 days,372FS+10 days,374FS+16 days,377FS+15 days | -1 day | -1 day | 0 days | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name change Red because 7/9 received. Approved at TMAG on 20/9
7 | 1.3.6.3.4.1.2 | T3 | T3-DB-0167 | SITAG |  | All SIT Suppliers Test Approach & Plans MHHS Review Completed | 100% | Thu 12/10/23 | Thu 12/10/23 | 0 days | Thu 12/10/23 | Thu 12/10/23 | 369FS+20 days | 383 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 7/11 - Red due to high volume to be reviewed. Date change under consideration. Initial reviews complete. Final review will be completed no later than 08/01/24 ahead of Interval 5 Readiness Assessment
6 | 1.3.6.3.4.2 |  |  |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 08/12/23 |  |  | 0 days | -40 days | -40 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 08/12/23 | 369FS+10 days | 380 | 0 days | -40 days | -40 days | PP |  | 5 | Yes
6 | 1.3.6.3.4.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 06/10/23 | Fri 03/11/23 | 20 days | Fri 06/10/23 | Fri 03/11/23 |  |  | 1 day | 0 days | -1 day | N/A |  | 5 | Yes
7 | 1.3.6.3.4.3.1 | T3 | T3-DB-0064 | SITAG | MHHS-ART009 | All SIT Suppliers RTTMs submitted to Programme for assurance | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 369FS+16 days | 375FS+20 days | 1 day | 0 days | -1 day | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name change. Approved at TMAG on 20/9. 10/10 - Red because small number of RTTMs still outstanding
7 | 1.3.6.3.4.3.2 | T3 | T3-DB-0168 | SITAG |  | All SIT Suppliers RTTMs MHHS Review Completed | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 374FS+20 days | 383 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 17/10 - Red because open comments still outstanding. Assurance reviews complete. Review will be completed no later than 08/01/24 ahead of Interval 5 Readiness Report . Completed on 14/12
6 | 1.3.6.3.4.4 |  |  |  |  | Test Scenarios | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.4.1 | T3 | T3-DB-0037 | SITAG |  | All SIT Suppliers test scenarios' submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 369FS+15 days | 378FS+20 days,380FS+5 days,381FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name change. Approved at TMAG on 20/9. 10/10 - Red because small number of Test Scenarios still outstanding
7 | 1.3.6.3.4.4.2 | T3 | T3-DB-0169 | SITAG |  | All SIT Suppliers Test scenarios' MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 377FS+20 days | 383 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 17/10 - Red due to high volume and backlog to be reviewed. Review will be completed no later than 08/01/24 ahead of Interval 5 Readiness Report. Completed 14/12
6 | 1.3.6.3.4.5 |  |  |  |  | PIT execution | 100% | Fri 13/10/23 | Fri 22/12/23 | 51 days | Mon 31/10/22 | Fri 22/12/23 |  |  | 249 days | 0 days | -249 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 16/10/23 | Fri 08/12/23 | 40 days | Mon 16/10/23 | Fri 08/12/23 | 377FS+5 days,372 | 382 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.4.5.2 |  |  |  |  | PIT Execution | 100% | Fri 13/10/23 | Fri 08/12/23 | 41 days | Mon 31/10/22 | Fri 08/12/23 | 377FS+5 days | 382 | 249 days | 0 days | -249 days | PP |  | 5 | Yes
7 | 1.3.6.3.4.5.3 | T3 | T3-DB-0170 | SITAG |  | All SIT Suppliers PIT Completion Reports submitted to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 381380 | 383FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 12/12 - Red because not all received. No impact as of yet. No action. Completed 12/12
7 | 1.3.6.3.4.5.4 | T3 | T3-DB-0171 | SITAG |  | All SIT Suppliers PIT Completion Reports MHHS Review Completed | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 382FS+10 days,370,375,378 | 754 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 12/12 - Amber because not all artefacts received. No impact. No action. Completed 15/12
5 | 1.3.6.3.5 |  |  |  |  | All LDSO Network Operations DBT CIT (Entering at Interval 5) | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Mon 31/10/22 | Fri 05/01/24 |  |  | 229 days | -10 days | -239 days | N/A |  | 5 | Yes
6 | 1.3.6.3.5.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Mon 31/10/22 | Fri 05/01/24 |  |  | 229 days | -10 days | -239 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.1.1 | T3 | T3-DB-0054 | SITAG |  | All Network Operation Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 |  | 387FS+20 days,389FS+10 days,391FS+15 days,394FS+15 days | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name and date change Red because only received 1/2 test approach and plans. Approved at TMAG on 20/9
7 | 1.3.6.3.5.1.2 | T3 | T3-DB-0172 | SITAG |  | All Network Operation Test Approach & Plans MHHS Review Completed | 100% | Thu 12/10/23 | Thu 12/10/23 | 0 days | Thu 12/10/23 | Thu 12/10/23 | 386FS+20 days | 400 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes |  | 11/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. Red due to high volume to be reviewed. Date change under consideration. Review will be completed no later than 08/01/24 ahead of Interval 5 Readiness Assessment
7 | 1.3.6.3.5.1.3 |  |  |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 11/08/23 | Fri 20/10/23 |  |  | 35 days | -5 days | -40 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.3.1 |  |  |  |  | Test readiness reporting | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 11/08/23 | Fri 20/10/23 | 386FS+10 days | 397 | 35 days | -5 days | -40 days | PP |  | 5 | Yes
7 | 1.3.6.3.5.1.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.4.1 | T3 | T3-DB-0062 | SITAG | MHHS-ART009 | All Network Operation RTTMs submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 386FS+15 days | 392FS+20 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name and date change Approved at TMAG on 20/9. 10/10 - Red because 50% of RTTMs outstanding
8 | 1.3.6.3.5.1.4.2 | T3 | T3-DB-0173 | SITAG |  | All Network Operation RTTMs MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 391FS+20 days | 400 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 17/10 - Red because open comments still outstanding. Assurance reviews complete. Review will be completed no later than 08/01/24 ahead of Interval 5 Readiness Report . 19/12 - completed 14/12
7 | 1.3.6.3.5.1.5 |  |  |  |  | Test Scenarios | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.5.1 | T3 | T3-DB-0011 | SITAG |  | All Network Operation test scenarios' submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 386FS+15 days | 395FS+20 days,397FS+5 days,398FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.8 | Yes |  | 12/9 - TMAG for name and date change. Approved at TMAG on 20/9. 17/10 - Red because currently 50% have been received. Date change under consideration.
8 | 1.3.6.3.5.1.5.2 | T3 | T3-DB-0174 | SITAG |  | All Network Operation test scenarios' MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 394FS+20 days | 400 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 17/10 - Red because open comments still outstanding. Assurance reviews complete. Review will be completed no later than 08/01/24 ahead of Interval 5 Readiness Assessment . 19/12 - completed 14/12
7 | 1.3.6.3.5.1.6 |  |  |  |  | PIT execution | 100% | Fri 13/10/23 | Fri 22/12/23 | 51 days | Mon 31/10/22 | Fri 05/01/24 |  |  | 249 days | -10 days | -259 days | N/A |  | 5 | Yes
8 | 1.3.6.3.5.1.6.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 16/10/23 | Fri 08/12/23 | 40 days | Mon 31/10/22 | Fri 29/12/23 | 394FS+5 days,389 | 399 | 250 days | -15 days | -265 days | PP |  | 5 | Yes
8 | 1.3.6.3.5.1.6.2 |  |  |  |  | PIT Execution | 100% | Fri 13/10/23 | Fri 08/12/23 | 41 days | Mon 31/10/22 | Fri 05/01/24 | 394FS+5 days | 399 | 249 days | -20 days | -269 days | PP |  | 5 | Yes
8 | 1.3.6.3.5.1.6.3 | T3 | T3-DB-0175 | SITAG |  | All Network Operation PIT (CIT interval 5) Completion Reports submitted to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 398397 | 400FS+10 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 11/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 19/12 - completed 14/12
8 | 1.3.6.3.5.1.6.4 | T3 | T3-DB-0176 | SITAG |  | All Network Operation PIT (CIT interval 5) Completion Reports MHHS Review Completed | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 399FS+10 days,387,392,395 | 754 | 0 days | 0 days | 0 days | SI Test |  | 5.15 | Yes |  | 11/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 12/12 - Amber because all reviews complete, clarifications are requested
5 | 1.3.6.3.6 |  |  |  |  | All UMSO DBT CIT (Entering at Interval 6) | 100% | Fri 29/09/23 | Fri 19/01/24 | 81 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 239 days | 0 days | -239 days | N/A |  | 5 | Yes
6 | 1.3.6.3.6.1 |  |  |  |  | Test Approach & Plan | 100% | Fri 13/10/23 | Thu 09/11/23 | 20 days | Fri 15/09/23 | Thu 09/11/23 |  |  | 20 days | 0 days | -20 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.1.1 | T3 | T3-DB-0052 | SITAG |  | All UMSO Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 |  | 404FS+20 days,406FS+10 days,408FS+15 days,411FS+15 days | 20 days | 19 days | 0 days | PP |  | 5.11 | Yes |  | 12/9 - TMAG for name and date change. Approved at TMAG on 20/9. 17/10 - Red because not all received. Currently no impact. Issuance request sent. Complete 1/11
7 | 1.3.6.3.6.1.2 | T3 | T3-DB-0177 | SITAG |  | All UMSO Test Approach & Plans MHHS Review Completed | 100% | Thu 09/11/23 | Thu 09/11/23 | 0 days | Thu 09/11/23 | Thu 09/11/23 | 403FS+20 days | 417 | 0 days | 0 days | 0 days | SI Test |  | 5.1 | Yes |  | To go to TMAG for date change. Approved for date change at TMAG on 23/10/23. 7/11-Amber because of high volume and backlog to be reviewed. Review will be completed no later than 22/01/24 ahead of Interval 6 Readiness Assessment
6 | 1.3.6.3.6.2 |  |  |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 27/10/23 | Fri 10/11/23 |  |  | -20 days | -20 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.2.1 |  |  |  |  | Test readiness reporting | 100% | Fri 27/10/23 | Fri 10/11/23 | 11 days | Fri 27/10/23 | Fri 10/11/23 | 403FS+10 days | 414 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.3.6.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 05/10/23 | Wed 01/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | -21 days | -21 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.3.1 | T3 | T3-DB-0060 | SITAG | MHHS-ART009 | All UMSO RTTMs submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 403FS+15 days | 409FS+20 days | 0 days | 0 days | 0 days | PP |  | 5.12 | Yes |  | 4/10 - Red because baseline date incorrect. To go to TMAG for date change. Approved for date change at TMAG on 23/10/23. 14/11-Red because up to 50% not received. No impact. No action
7 | 1.3.6.3.6.3.2 | T3 | T3-DB-0178 | SITAG |  | All UMSO RTTMs MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 408FS+20 days | 417 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 4/10 - Red because baseline date incorrect. To go to TMAG for date change. Approved for date change at TMAG on 23/10/23
6 | 1.3.6.3.6.4 |  |  |  |  | Test Scenarios | 100% | Thu 05/10/23 | Wed 01/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | -21 days | -21 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.4.1 | T3 | T3-DB-0025 | SITAG |  | All UMSO test scenarios' submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 403FS+15 days | 412FS+20 days,414FS+5 days,415FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.12 | Yes |  | Approved at TMAG on 20/9. 4/10 - Red because baseline date incorrect. To go to TMAG for date change. Approved for date change at TMAG on 23/10/23. 7/11-Red because not received. Expected 10/11. No impact No action
7 | 1.3.6.3.6.4.2 | T3 | T3-DB-0179 | SITAG |  | All UMSO Test scenarios' MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 411FS+20 days | 417 | 0 days | 0 days | 0 days | SI Test |  | 5.1 | Yes |  | 1/9 - to be raised as new T3 at TMAG. Approved at TMAG on 20/9. 5/12 - Assurance review conducted, but outstanding comments to be addressed
6 | 1.3.6.3.6.5 |  |  |  |  | PIT execution | 100% | Fri 10/11/23 | Fri 19/01/24 | 51 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 269 days | 0 days | -269 days | N/A |  | 5 | Yes
7 | 1.3.6.3.6.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | Mon 13/11/23 | Fri 05/01/24 | 40 days | Mon 13/11/23 | Fri 05/01/24 | 411FS+5 days,406 | 416 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.6.5.2 |  |  |  |  | PIT Execution | 100% | Fri 10/11/23 | Thu 04/01/24 | 40 days | Mon 31/10/22 | Fri 05/01/24 | 411FS+5 days | 416 | 269 days | -1 day | -250 days | PP |  | 5 | Yes
7 | 1.3.6.3.6.5.3 | T3 | T3-DB-0180 | SITAG |  | All UMSO PIT (CIT interval 6) Completion Reports submitted to Programme for assurance | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 415414 | 417FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes |  | . 4/10 - Red because baseline date incorrect. To go to TMAG for date change. Approved for date change at TMAG on 23/10/23. 16/1 - Not all completion reports yet received. Completed on 21/2
7 | 1.3.6.3.6.5.4 | T3 | T3-DB-0181 | SITAG |  | All UMSO PIT (CIT interval 6) Completion Reports MHHS Review Completed | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 404,409,412,416FS+10 days | 786 | 0 days | 0 days | 0 days | SI Test |  | 5.1 | Yes |  | Red because baseline date incorrect. To go to TMAG for date change. Approved for date change at TMAG on 23/10/23. 16/01 - Late due to late delivery of PP artefacts for review. Completed on 21/2
3 | 1.3.7 |  |  |  |  | DBT Monitoring and Assurance | 64% | Mon 31/10/22 | Tue 20/01/26 | 842 days | Mon 31/10/22 | Tue 20/01/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.7.1 |  |  |  |  | Planning and DBT Progress Monitoring of PPs | 67% | Mon 31/10/22 | Mon 30/06/25 | 696 days | Mon 31/10/22 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.1.1 |  |  |  |  | Monitor Non-SIT PPs Planning and DBT1 progress (to inform confirmation of Qualification Testing Tranche participants milestones) | 67% | Mon 31/10/22 | Mon 30/06/25 | 696 days | Mon 31/10/22 | Mon 30/06/25 | 166SS |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes |  | 15/9 - hold in plan until qualification sections updated
4 | 1.3.7.2 |  |  |  |  | DBT Progress Monitoring of Consequential Change | 51% | Thu 02/02/23 | Tue 20/01/26 | 774 days | Thu 02/02/23 | Tue 20/01/26 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.2.1 |  |  |  |  | Monitor & report data cleanse progress | 51% | Thu 02/02/23 | Tue 20/01/26 | 774 days | Thu 02/02/23 | Tue 20/01/26 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 15/9 - query with John Wiggins where this sits
4 | 1.3.7.3 |  |  |  |  | Design Assurance | 71% | Mon 14/11/22 | Wed 06/08/25 | 713 days | Mon 14/11/22 | Wed 06/08/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.3.1 |  |  |  |  | Design Assurance Readiness Assessment Preparation | 100% | Tue 28/02/23 | Fri 21/04/23 | 39 days | Tue 28/02/23 | Fri 21/04/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.1.1 |  |  |  |  | Set up FTIG | 100% | Mon 03/04/23 | Fri 21/04/23 | 15 days | Mon 03/04/23 | Fri 21/04/23 |  |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.2 |  |  |  |  | Produce Draft Questions | 100% | Tue 28/02/23 | Mon 13/03/23 | 10 days | Tue 28/02/23 | Mon 13/03/23 |  | 427,430FS+4 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.3 |  |  |  |  | Pilot with SRO | 100% | Tue 14/03/23 | Tue 14/03/23 | 1 day | Tue 14/03/23 | Tue 14/03/23 | 426 | 428 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.4 |  |  |  |  | Finalise questions | 100% | Wed 15/03/23 | Tue 28/03/23 | 10 days | Wed 15/03/23 | Tue 28/03/23 | 427 | 429 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.5 |  |  |  |  | Prepare on-line RA tooling | 100% | Wed 29/03/23 | Tue 11/04/23 | 10 days | Wed 29/03/23 | Tue 11/04/23 | 428 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.6 |  |  |  |  | Prepare webinar content | 100% | Mon 20/03/23 | Fri 24/03/23 | 5 days | Mon 20/03/23 | Fri 24/03/23 | 426FS+4 days | 431FS+3 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.7 |  |  |  |  | Conduct webinar | 100% | Thu 30/03/23 | Thu 30/03/23 | 1 day | Thu 30/03/23 | Thu 30/03/23 | 430FS+3 days |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.7.3.2 |  |  |  |  | Participant Design Assurance Approach | 100% | Mon 14/11/22 | Wed 11/01/23 | 43 days | Mon 14/11/22 | Wed 11/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.2.1 |  |  |  |  | Develop document | 100% | Mon 14/11/22 | Fri 09/12/22 | 20 days | Mon 14/11/22 | Fri 09/12/22 | 48FS+10 days | 434 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.2.2 |  |  |  |  | Review document | 100% | Mon 12/12/22 | Wed 04/01/23 | 18 days | Mon 12/12/22 | Wed 04/01/23 | 433 | 435FF+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.2.3 | T3 | T3-DB-0012 | DAG |  | Participant Design Assurance Approach approved | 100% | Wed 11/01/23 | Wed 11/01/23 | 0 days | Wed 11/01/23 | Wed 11/01/23 | 434FF+5 days |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.7.3.3 |  |  |  |  | Phase 1 - SIT Volunteers (Core Providers) | 100% | Mon 10/04/23 | Fri 27/10/23 | 145 days | Mon 10/04/23 | Fri 27/10/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.3.1 |  |  |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | Mon 10/04/23 | Mon 10/04/23 | 1 day | Mon 10/04/23 | Mon 10/04/23 |  | 438 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.2 |  |  |  |  | Participants Provide Responses to questionnaires | 100% | Tue 11/04/23 | Mon 01/05/23 | 15 days | Tue 11/04/23 | Mon 01/05/23 | 437 | 439 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.3.3 |  |  |  |  | Assess on-line responses and provided evidence | 100% | Tue 02/05/23 | Mon 08/05/23 | 5 days | Tue 02/05/23 | Mon 08/05/23 | 438 | 440 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.4 |  |  |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | Tue 09/05/23 | Tue 20/06/23 | 31 days | Tue 09/05/23 | Tue 20/06/23 | 439 | 441FS-10 days | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.5 |  |  |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | Wed 07/06/23 | Thu 31/08/23 | 62 days | Wed 07/06/23 | Thu 31/08/23 | 440FS-10 days | 442FS-22 days | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.6 |  |  |  |  | SI endorsement of participants’ design – assurance reports | 100% | Wed 02/08/23 | Fri 29/09/23 | 43 days | Wed 02/08/23 | Fri 29/09/23 | 441FS-22 days | 443SS+19 days | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.7 |  |  |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | Tue 29/08/23 | Fri 27/10/23 | 44 days | Mon 02/10/23 | Fri 27/10/23 | 442SS+19 days | 444 | -24 days | 0 days | 24 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.8 | T2 | T2-DB-0100 | DAG | MHHS-ART002 | Phase 1 - SIT Volunteers (Core Providers) complete | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 443 |  | 0 days | 0 days | 0 days | SI Design |  | 5.11 | Yes |  | 16/10 Awaiting the issuing of backlog reports. But no significant design impacts identified. No impact to commencing SIT
5 | 1.3.7.3.4 |  |  |  |  | Phase 2 - SIT all other participants | 100% | Mon 08/05/23 | Wed 22/11/23 | 143 days | Mon 08/05/23 | Wed 22/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.4.1 |  |  |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | Mon 08/05/23 | Mon 08/05/23 | 1 day | Mon 08/05/23 | Mon 08/05/23 |  | 447 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.4.2 |  |  |  |  | Participants Provide Responses to questionnaires | 100% | Tue 09/05/23 | Mon 29/05/23 | 15 days | Tue 09/05/23 | Mon 29/05/23 | 446 | 448 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.4.3 |  |  |  |  | Assess on-line responses and provided evidence | 100% | Tue 30/05/23 | Mon 05/06/23 | 5 days | Tue 30/05/23 | Mon 05/06/23 | 447 | 449 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.4.4 |  |  |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | Tue 06/06/23 | Fri 29/09/23 | 84 days | Tue 06/06/23 | Fri 29/09/23 | 448 | 450SS+15 days | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.5 |  |  |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | Tue 27/06/23 | Fri 29/09/23 | 69 days | Tue 27/06/23 | Fri 29/09/23 | 449SS+15 days | 451SS+15 days | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.6 |  |  |  |  | SI endorsement of participants’ design – assurance reports | 100% | Tue 18/07/23 | Fri 29/09/23 | 54 days | Tue 18/07/23 | Fri 29/09/23 | 450SS+15 days | 452SS+19 days | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.7 |  |  |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | Mon 14/08/23 | Wed 22/11/23 | 73 days | Mon 02/10/23 | Wed 22/11/23 | 451SS+19 days | 453 | -35 days | 0 days | 35 days | SI Design |  | 5.2 | Yes |  | 6/11 - last report sent out 27/10
6 | 1.3.7.3.4.8 | T2 | T2-DB-0200 | DAG | MHHS-ART002 | SIT PPs design assurance (excl Migration/Reverse Migration) complete | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 452 | 455 | 0 days | 0 days | 0 days | SI Design |  | 5.11 | Yes |  | 6/11 - last report sent out 27/10
5 | 1.3.7.3.5 |  |  |  |  | Non-SIT PPs design assurance | 33% | Thu 23/11/23 | Wed 06/08/25 | 445 days | Thu 23/11/23 | Wed 06/08/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.5.1 |  |  |  |  | Non-SIT PPs design assurance (risk-based sample) | 33% | Thu 23/11/23 | Wed 06/08/25 | 445 days | Thu 23/11/23 | Wed 06/08/25 | 453 |  | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.7.4 |  |  |  |  | Test Assurance | 63% | Wed 01/02/23 | Mon 30/06/25 | 629 days | Mon 31/10/22 | Mon 30/06/25 |  |  | 67 days | 0 days | -67 days | N/A |  | 5 | Yes
5 | 1.3.7.4.1 |  |  |  |  | Non-SIT PPs test assurance | 63% | Wed 01/02/23 | Mon 30/06/25 | 629 days | Wed 01/02/23 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes |  | 15/9 - keep in plan until qualification reviewed
4 | 1.3.7.5 |  |  |  |  | Pre-Qualification Guidance (PIT Guidance) | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.5.1 |  |  |  |  | Develop document (incl. collaboration with code bodies, as required) | 100% | Mon 31/10/22 | Mon 16/01/23 | 56 days | Mon 31/10/22 | Mon 16/01/23 |  | 460 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.7.5.2 |  |  |  |  | Review, update and agree Pre-Qualification Guidance internally | 100% | Tue 17/01/23 | Tue 31/01/23 | 11 days | Tue 17/01/23 | Tue 31/01/23 | 459 |  | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
4 | 1.3.7.6 |  |  |  |  | External Programme Dependency Management | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.6.1 |  |  |  |  | SLC47 | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.6.1.1 |  |  |  |  | SLC47 implementation date | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 |  |  | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
2 | 1.4 |  |  |  |  | SYSTEMS INTEGRATION TESTING (SIT) | 60% | Mon 31/10/22 | Fri 19/02/27 | 1125 days? | Mon 31/10/22 | Mon 19/01/26 |  |  | 0 days | 284 days | 284 days? | N/A |  |  | Yes
3 | 1.4.1 |  |  |  |  | SIT Preparation | 80% | Mon 31/10/22 | Fri 25/04/25 | 650 days? | Mon 31/10/22 | Mon 03/03/25 |  |  | 0 days | 39 days | 39 days? | N/A |  | 5 | Yes
4 | 1.4.1.1 |  |  |  |  | Test Artefact Development | 99% | Mon 31/10/22 | Wed 21/08/24 | 472 days | Mon 31/10/22 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.1.1.1 |  |  |  |  | Environment Approach & Plan | 100% | Wed 16/11/22 | Wed 21/08/24 | 460 days | Wed 16/11/22 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.1.1 | T3 | T3-TE-0010 | SITAG | MHHS-ART139 | Environment Approach & Plan approved | 100% | Wed 16/11/22 | Wed 16/11/22 | 0 days | Wed 16/11/22 | Wed 16/11/22 |  | 901,1239,469FS+1 day,579 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.2 |  |  |  |  | Environment Approach & Plan - Work Off | 100% | Thu 17/11/22 | Fri 23/06/23 | 157 days | Thu 17/11/22 | Fri 23/06/23 | 468FS+1 day | 470FS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.3 | T3 | T3-TE-0068 | SITAG | MHHS-ART139 | Environment Approach & Plan - Work Off Approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 469FS+5 days |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.4 | T3 | T3-TE-0090 | SITAG | MHHS-DEL 618 | Environment Approach and Plan - SIT Functional | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 |  |  | 3 days | 3 days | 0 days | SI Test |  | 5.12 | Yes |  | The LDSO element is on hold whilst discussions are being held between Programme and Code Bodies re: LDSO testing. When concluded, that update will be re-planned by agreement with TMAG. 20/11- Approved at TMAG
6 | 1.4.1.1.1.5 |  |  |  |  | Define Approach to Simulator for Non-SIT LDSO | 100% | Wed 15/11/23 | Wed 15/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 |  | 1233FS+13 days | 0 days | -1 day | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.1.1.6 | T3 | T3-TE-0091 | SITAG/QAG | MHHS-DEL 619 | Environment Approach and Plan - Non SIT LDSO Testing | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 |  | 14091408 | 0 days | 0 days | 0 days | SI Test |  | 5.22 | Yes |  | 25/03: To go to Apr QAG for name change as Non-SIT LDSO and S and A will deliver on different timelines so '& S and A' will be removed. 17/4: Approved for name change at SITAG on 17/4/24.
6 | 1.4.1.1.1.7 | T3 | T3-TE-0120 | SITAG/QAG | MHHS-DEL 619 | Environment Approach and Plan - S and A Testing | 100% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5.27 | Yes |  | . 25/03: New milestone to go to Apr QAG as Non-SIT LDSO and S and A will deliver on different timelines so need to create a new milestone for S and A. 17/4: Approved as new milestone at SITAG on 17/4/24. 19/6: Approved at SITAG on 19/6
6 | 1.4.1.1.1.8 | T3 | T3-TE-0092 | SITAG | MHHS-DEL 620 | Environment Approach and Plan - SIT Non Functional | 100% | Wed 19/06/24 | Wed 19/06/24 | 0 days | Wed 19/06/24 | Wed 19/06/24 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5.27 | Yes |  | 26/3/24: To go to April SITAG for date change approval. Because of dependency on NF test approach and plan. Currently under PP review 17/4: Approved date change at SITAG on 17/4/24. 19/6: Approved at SITAG on 19/6
6 | 1.4.1.1.1.9 | T3 | T3-TE-0093 | SITAG/QAG | MHHS-DEL 621 | Environment Approach and Plan - Sandbox | 100% | Wed 21/08/24 | Wed 21/08/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5.27 | Yes |  | Name change to remove 'qualification and' to reflect sandbox only scope. Name and date change approved at QAG on 21/3/24. 19/6: Approved at SITAG on 19/6
5 | 1.4.1.1.2 |  |  |  |  | Overarching Test Scope (for all stages) | 100% | Mon 31/10/22 | Fri 27/01/23 | 65 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | -110 days | -110 days | N/A |  | 5 | Yes
6 | 1.4.1.1.2.1 |  |  |  |  | Overarching Test Scope (excl. Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 31/10/22 | Fri 27/01/23 | 65 days | Mon 31/10/22 | Fri 27/01/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.1.2.1.1 |  |  |  |  | Develop document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 31/10/22 | Fri 13/01/23 | 55 days | Mon 31/10/22 | Fri 13/01/23 | 48 | 480 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.1.2.1.2 |  |  |  |  | Review, update & agree document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 16/01/23 | Fri 27/01/23 | 10 days | Mon 16/01/23 | Fri 27/01/23 | 479 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.3 |  |  |  |  | Configuration and Release Management Approach & Plan | 100% | Tue 01/11/22 | Fri 16/06/23 | 164 days | Tue 01/11/22 | Fri 16/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.3.1 |  |  |  |  | Develop document | 100% | Tue 01/11/22 | Fri 16/06/23 | 69 days | Tue 01/11/22 | Fri 16/06/23 |  | 483 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.3.2 |  |  |  |  | Review, update and agree Configuration and Release Management Approach & Plan internally | 100% | Wed 01/02/23 | Fri 28/04/23 | 63 days | Wed 01/02/23 | Fri 28/04/23 | 482 |  | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
5 | 1.4.1.1.4 |  |  |  |  | Test Data Overarching Approach & Plan | 100% | Mon 14/11/22 | Thu 20/07/23 | 179 days | Mon 14/11/22 | Thu 20/07/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.4.1 |  |  |  |  | Develop document | 100% | Mon 14/11/22 | Fri 09/12/22 | 20 days | Mon 14/11/22 | Fri 09/12/22 |  | 486 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.4.2 |  |  |  |  | Document review and update | 100% | Mon 12/12/22 | Fri 14/07/23 | 155 days | Mon 12/12/22 | Fri 14/07/23 | 485 | 487FS+3 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.1.1.4.3 | T3 | T3-TE-0072 | SITAG |  | Test Data Overarching Approach & Plan approved by TMAG | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 486FS+3 days | 488 | 0 days | 0 days | 0 days | SRO Test |  | 5 | Yes
6 | 1.4.1.1.4.4 |  |  |  |  | Document publication final version | 100% | Thu 20/07/23 | Thu 20/07/23 | 1 day | Thu 20/07/23 | Thu 20/07/23 | 487 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.5 |  |  |  |  | Interface Code of Connection (dates subject to DIP Service Provider's plan) | 100% | Wed 01/03/23 | Fri 05/05/23 | 48 days | Wed 01/03/23 | Fri 05/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.5.1 |  |  |  |  | Develop Interface Code of Connection with DIP Service Provider | 100% | Wed 01/03/23 | Fri 28/04/23 | 43 days | Wed 01/03/23 | Fri 28/04/23 |  | 491FS+5 days | 0 days | 0 days | 0 days | DIP Provider |  | 5 | Yes
6 | 1.4.1.1.5.2 |  |  |  |  | Interface Code of Connection approved at SDWG | 100% | Fri 05/05/23 | Fri 05/05/23 | 0 days | Fri 05/05/23 | Fri 05/05/23 | 490FS+5 days |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.6 |  |  |  |  | Test Traceability | 98% | Thu 01/06/23 | Wed 17/01/24 | 165 days | Thu 01/06/23 | Wed 17/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.6.1 |  |  |  |  | RTM containing Method Statement Implied Requirements into Azure DevOps | 100% | Thu 01/06/23 | Fri 30/06/23 | 22 days | Thu 01/06/23 | Fri 30/06/23 |  | 495496 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.2 |  |  |  |  | RTM Containing Interface Catalogue Implied Requirements | 100% | Thu 01/06/23 | Fri 07/07/23 | 27 days | Thu 01/06/23 | Fri 07/07/23 |  | 495496 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.3 |  |  |  |  | SIT CIT Full Traceability & Coverage complete | 100% | Mon 10/07/23 | Wed 20/12/23 | 118 days | Mon 10/07/23 | Fri 08/12/23 | 494493 |  | 0 days | 8 days | 8 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.4 |  |  |  |  | SIT Functional Full Traceability & Coverage complete | 96% | Mon 10/07/23 | Wed 17/01/24 | 138 days | Mon 10/07/23 | Wed 17/01/24 | 494493 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | Stays red till delivery plan agreed at SITAG
4 | 1.4.1.2 |  |  |  |  | Test Tool Development | 95% | Mon 31/10/22 | Mon 23/10/23 | 256 days? | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 81 days | 81 days? | N/A |  | 5 | Yes
5 | 1.4.1.2.1 |  |  |  |  | Test Management Tool | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 81 days | 81 days | N/A |  | 5 | Yes
6 | 1.4.1.2.1.1 |  |  |  |  | Test Management Tool Implementation | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 81 days | 81 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.1.1 |  |  |  |  | Requirements identification | 100% | Mon 31/10/22 | Fri 23/12/22 | 40 days | Mon 31/10/22 | Fri 23/12/22 |  | 501FS+5 days,509 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.2 |  |  |  |  | Development | 100% | Mon 02/01/23 | Fri 23/06/23 | 125 days | Mon 02/01/23 | Fri 23/06/23 | 500FS+5 days | 502FF,506SS | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.3 |  |  |  |  | Testing | 100% | Mon 02/01/23 | Fri 23/06/23 | 125 days | Mon 02/01/23 | Fri 23/06/23 | 501FF | 503FF,506SS | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.4 |  |  |  |  | Accept tool | 100% | Fri 23/06/23 | Fri 23/06/23 | 0 days | Fri 23/06/23 | Fri 23/06/23 | 502FF | 504FS+85 days | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.5 |  |  |  |  | Implementation | 100% | Mon 23/10/23 | Mon 23/10/23 | 1 day | Fri 30/06/23 | Fri 30/06/23 | 503FS+85 days |  | 81 days | 81 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.1.2.1.2 |  |  |  |  | Test Management Tool User Guide | 100% | Mon 02/01/23 | Fri 09/06/23 | 115 days | Mon 02/01/23 | Fri 09/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.2.1 |  |  |  |  | Develop document | 100% | Mon 02/01/23 | Fri 19/05/23 | 100 days | Mon 02/01/23 | Fri 19/05/23 | 501SS,502SS | 507 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.2.2 |  |  |  |  | Review, update and agree Test Management Tool User Guide internally | 100% | Mon 22/05/23 | Fri 09/06/23 | 15 days | Mon 22/05/23 | Fri 09/06/23 | 506 |  | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
6 | 1.4.1.2.1.3 |  |  |  |  | Test Management Tool Configuration Guide | 100% | Mon 02/01/23 | Fri 24/03/23 | 60 days | Mon 02/01/23 | Fri 24/03/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.3.1 |  |  |  |  | Develop document | 100% | Mon 02/01/23 | Fri 03/03/23 | 45 days | Mon 02/01/23 | Fri 03/03/23 | 500 | 510 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.3.2 |  |  |  |  | Review, update and agree Test Management Tool Configuration Guide internally | 100% | Mon 06/03/23 | Fri 24/03/23 | 15 days | Mon 06/03/23 | Fri 24/03/23 | 509 |  | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
5 | 1.4.1.2.2 |  |  |  |  | Secure Volunteer SIT Participants | 0% | Tue 31/01/23 | Thu 14/09/23 | 163 days? | NA | NA |  |  | 0 days | 0 days | 163 days? |  |  | 6 | Yes
6 | 1.4.1.2.2.1 |  |  |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 0% | Tue 31/01/23 | Tue 31/01/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.2 |  |  |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 0% | Tue 14/02/23 | Tue 14/02/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.3 |  |  |  |  | SIT Participant Volunteers Identified | 0% | Tue 14/02/23 | Tue 14/02/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.4 |  |  |  |  | Engagement with SIT volunteers | 0% | Tue 23/05/23 | Tue 23/05/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.5 |  |  |  |  | SIT Participants Agreed | 0% | Tue 23/05/23 | Tue 23/05/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.6 |  |  |  |  | Data Protection Impact Assessment (DPIA) | 0% | Fri 30/06/23 | Fri 14/07/23 | 11 days? | NA | NA |  |  | 0 days | 0 days | 11 days? |  |  | 6 | Yes
7 | 1.4.1.2.2.6.1 |  |  |  |  | Conduct DPIA on Overall Test Data Approach | 0% | Fri 30/06/23 | Fri 30/06/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
7 | 1.4.1.2.2.6.2 |  |  |  |  | Revise Overarching Test Data Approach& plan for DPIA (if required), including engagement with DWG | 0% | Thu 13/07/23 | Thu 13/07/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
7 | 1.4.1.2.2.6.3 |  |  |  |  | Review (internal), update and approve revised Overarching Test Data Approach& Plan (if required) | 0% | Fri 14/07/23 | Fri 14/07/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.7 |  |  |  |  | Data Sharing Agreements | 0% | Fri 04/08/23 | Thu 14/09/23 | 30 days? | NA | NA |  |  | 0 days | 0 days | 30 days? |  |  | 6 | Yes
7 | 1.4.1.2.2.7.1 |  |  |  |  | Produce Data Sharing Agreement for Industry Review | 0% | Fri 04/08/23 | Fri 04/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
7 | 1.4.1.2.2.7.2 |  |  |  |  | Manage Participant Queries and Contract Agreement Execution | 0% | Thu 14/09/23 | Thu 14/09/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
7 | 1.4.1.2.2.7.3 |  |  |  |  | Data Sharing Agreements Complete | 0% | Thu 14/09/23 | Thu 14/09/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.2.2.8 |  |  |  |  | Production Data Cut & Data Obfuscation | 0% | Mon 19/06/23 | Fri 01/09/23 | 55 days? | NA | NA |  |  | 0 days | 0 days | 55 days? |  |  | 6 | Yes
7 | 1.4.1.2.2.8.1 |  |  |  |  | SI Data Cut Preparation& Infrastructure | 0% | Mon 19/06/23 | Fri 18/08/23 | 45 days? | NA | NA |  |  | 0 days | 0 days | 45 days? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.1 |  |  |  |  | SI Data Cut Planning activities (incl. pre-cut and post-cut cleansing and population approach) | 0% | Mon 19/06/23 | Mon 19/06/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.2 |  |  |  |  | Set up SI database and transmission structure | 0% | Thu 17/08/23 | Thu 17/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.3 |  |  |  |  | Mechanism for transfer of data in place | 0% | Fri 18/08/23 | Fri 18/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.4 |  |  |  |  | SI Data Cut Preparation& Infrastructure Complete | 0% | Fri 18/08/23 | Fri 18/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
7 | 1.4.1.2.2.8.2 |  |  |  |  | Production Data Cut | 0% | Mon 19/06/23 | Fri 01/09/23 | 55 days? | NA | NA |  |  | 0 days | 0 days | 55 days? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.1 |  |  |  |  | Notification of Production Data Cut issued to relevant participants | 0% | Mon 19/06/23 | Mon 19/06/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.2 |  |  |  |  | Coordinate relevant participants taking data cut from production systems | 0% | Fri 11/08/23 | Fri 11/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.3 |  |  |  |  | Production data cut GONG decision | 0% | Wed 16/08/23 | Wed 16/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.4 |  |  |  |  | Relevant participants take data cut from production systems (Saturday 19 August) | 0% | Mon 21/08/23 | Mon 21/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.5 |  |  |  |  | EES transmit request data to SI | 0% | Fri 25/08/23 | Fri 25/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.6 |  |  |  |  | Check data alignment and integrity of data cut | 0% | Fri 01/09/23 | Fri 01/09/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.7 |  |  |  |  | Data cut from relevant participants' production systems completed (Saturday 19 August) | 0% | Mon 21/08/23 | Mon 21/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.8 |  |  |  |  | Production Data Cut Complete | 0% | Mon 21/08/23 | Mon 21/08/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
4 | 1.4.1.3 |  |  |  |  | SIT Participation | 100% | Mon 31/10/22 | Tue 23/05/23 | 147 days | Mon 31/10/22 | Tue 23/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.1.3.1 |  |  |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 34FF | 542 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.4.1.3.2 |  |  |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 100% | Wed 01/02/23 | Tue 14/02/23 | 10 days | Wed 01/02/23 | Tue 14/02/23 | 541,34 | 543FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.3 | T2 | T2-TE-0100 | SITAG |  | SIT Participant Volunteers Identified | 100% | Tue 14/02/23 | Tue 14/02/23 | 0 days | Tue 14/02/23 | Tue 14/02/23 | 542FF |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.4 |  |  |  |  | Engagement with SIT volunteers | 100% | Mon 31/10/22 | Tue 23/05/23 | 147 days | Mon 31/10/22 | Tue 23/05/23 |  | 545 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.5 | T2 | T2-TE-0150 | SITAG |  | SIT Participants Agreed | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 544,579FS-74 days | 67SS,1070 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.1.4 |  |  |  |  | SIT Stage-Specific Preparation | 75% | Mon 31/10/22 | Fri 25/04/25 | 650 days? | Mon 31/10/22 | Mon 03/03/25 |  |  | 0 days | 39 days | 39 days? | N/A |  | 5 | Yes
5 | 1.4.1.4.1 |  |  |  |  | SIT Component Integration Preparation | 100% | Mon 31/10/22 | Fri 19/01/24 | 320 days | Mon 31/10/22 | Mon 22/01/24 |  |  | 0 days | -1 day | -1 day | N/A |  | 5 | Yes
6 | 1.4.1.4.1.1 |  |  |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Wed 19/07/23 | 188 days | Mon 31/10/22 | Wed 19/07/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.1.1 |  |  |  |  | Develop document with SITWG | 100% | Mon 31/10/22 | Thu 08/06/23 | 159 days | Mon 31/10/22 | Thu 08/06/23 |  | 558SS+45 days,550 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.1.2 |  |  |  |  | Industry consultation | 100% | Fri 09/06/23 | Thu 22/06/23 | 10 days | Fri 09/06/23 | Thu 22/06/23 | 549 | 551,554SS | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.1.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 23/06/23 | Wed 19/07/23 | 19 days | Fri 23/06/23 | Wed 19/07/23 | 550 | 552 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.1.4 | T3 | T3-TE-0012 | SITAG | MHHS-ART073 | SIT Component Integration Testing Test Approach & Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 551 | 1073,1074,1075,1076,1077,1078,629FS+40 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.1.2 |  |  |  |  | Test Data Approach & Plan | 100% | Fri 09/06/23 | Wed 19/07/23 | 29 days | Fri 09/06/23 | Wed 19/07/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.2.1 |  |  |  |  | Industry consultation | 100% | Fri 09/06/23 | Thu 22/06/23 | 10 days | Fri 09/06/23 | Thu 22/06/23 | 550SS | 555 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 23/06/23 | Wed 19/07/23 | 19 days | Fri 23/06/23 | Wed 19/07/23 | 554 | 556 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.2.3 |  |  |  |  | SIT Component Integration Testing Test Data Approach & Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 555 | 6.1611e+26 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.1.3 |  |  |  |  | Test scenarios | 100% | Mon 02/01/23 | Wed 30/08/23 | 173 days | Mon 02/01/23 | Wed 30/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.3.1 |  |  |  |  | Development of test scenarios | 100% | Mon 02/01/23 | Fri 28/04/23 | 0 days | Mon 02/01/23 | Fri 28/04/23 | 549SS+45 days | 559SS+22 days,564 | 0 days | 0 days | -85 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.3.2 |  |  |  |  | Review test scenarios with SIT Working Group | 100% | Wed 01/02/23 | Wed 09/08/23 | 11 days | Wed 01/02/23 | Wed 09/08/23 | 558SS+22 days | 560FS+15 days | 0 days | 0 days | -125 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.3.3 | T3 | T3-TE-0014 | SITAG | MHHS-ART148 | SIT Component Integration Testing Test scenarios approved | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 559FS+15 days | 1.0731e+23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 17/8 - to go to ETMAG on 30/8
6 | 1.4.1.4.1.4 |  |  |  |  | Test cases | 100% | Mon 01/05/23 | Fri 08/12/23 | 160 days | Mon 01/05/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
7 | 1.4.1.4.1.4.1 |  |  |  |  | SI Test cases | 100% | Mon 01/05/23 | Fri 08/12/23 | 160 days | Mon 01/05/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
8 | 1.4.1.4.1.4.1.1 |  |  |  |  | Batch 1 (CIT Intervals 1 and 2) | 100% | Mon 01/05/23 | Fri 29/09/23 | 110 days | Mon 01/05/23 | Fri 29/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.1.1 |  |  |  |  | Develop Test cases | 100% | Mon 01/05/23 | Fri 15/09/23 | 100 days | Mon 01/05/23 | Fri 15/09/23 | 558 | 565 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.1.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 18/09/23 | Thu 28/09/23 | 9 days | Mon 18/09/23 | Thu 28/09/23 | 564 | 566FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.1.3 | T3 | T3-TE-0069 | SITAG | MHHS-ART073 | SIT Component Integration Testing Test cases Batch 1 (CIT Intervals 1 and 2) approved at ETMAG | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 565FS+1 day | 568,627,654FS+18 days | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
8 | 1.4.1.4.1.4.1.2 |  |  |  |  | Batch 2 (CIT Intervals 3 and 4) | 100% | Mon 02/10/23 | Fri 03/11/23 | 25 days | Mon 02/10/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.2.1 |  |  |  |  | Develop Test cases | 100% | Mon 02/10/23 | Fri 20/10/23 | 15 days | Mon 02/10/23 | Fri 20/10/23 | 566 | 569 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.2.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 23/10/23 | Thu 02/11/23 | 9 days | Mon 23/10/23 | Thu 02/11/23 | 568 | 570FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.2.3 | T3 | T3-TE-0104 | SITAG |  | SIT Component Integration Testing Test cases Batch 2 (CIT Intervals 3 and 4) approved at ETMAG | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 569FS+1 day | 572686718 | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
8 | 1.4.1.4.1.4.1.3 |  |  |  |  | Batch 3 (CIT Intervals 5 and 6) | 100% | Fri 03/11/23 | Fri 08/12/23 | 25 days | Fri 03/11/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.3.1 |  |  |  |  | Develop Test cases | 100% | Fri 03/11/23 | Fri 24/11/23 | 15 days | Fri 03/11/23 | Fri 24/11/23 | 570 | 573 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.3.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 27/11/23 | Thu 07/12/23 | 9 days | Mon 27/11/23 | Thu 07/12/23 | 572 | 574FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes |  | 18/8 - added in with LC to reflect his ppt slide
9 | 1.4.1.4.1.4.1.3.3 | T3 | T3-TE-0105 | SITAG |  | SIT Component Integration Testing Test cases Batch 3 (CIT Intervals 5 and 6) approved at ETMAG | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 573FS+1 day | 750782 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 18/8 - added in with LC to reflect his ppt slide. 28/11 - Red because TMAG date has moved from 8/12 to 20/12 due to reduction in Dec TMAGs. No impact. No action. 20/12 - Approved at TMAG on 20/12
6 | 1.4.1.4.1.5 |  |  |  |  | CIT Interval 1 Preparation | 100% | Wed 16/11/22 | Fri 15/12/23 | 283 days | Wed 16/11/22 | Fri 08/12/23 |  |  | 0 days | 5 days | 5 days | N/A |  | 5.6 | Yes
7 | 1.4.1.4.1.5.1 |  |  |  |  | Environments (SIT A) | 100% | Wed 16/11/22 | Wed 25/10/23 | 246 days | Wed 16/11/22 | Mon 16/10/23 |  |  | 0 days | 7 days | 7 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.1.1 |  |  |  |  | PPs register PKI Officers and request PKI certificates | 100% | Mon 09/10/23 | Fri 13/10/23 | 5 days | Mon 09/10/23 | Fri 13/10/23 |  | 578FS+8 days | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
8 | 1.4.1.4.1.5.1.2 | T3 | T3-TE-0094 | SITAG |  | PPs register PKI Officers and request PKI certificates Complete - Interval 1 | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 | 577FS+8 days |  | 8 days | 8 days | 0 days | PP |  | 5.1 | Yes |  | 16/8- new milestones added in and date change. Approved at TMAG on 16/8. 18/10 - Red because there is an issue that is preventing the issue of PKI certificates. Avanade are working with GlobalSign to resolve. A fix is in the process of being tested
8 | 1.4.1.4.1.5.1.3 |  |  |  |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 100% | Wed 16/11/22 | Fri 13/10/23 | 238 days | Wed 16/11/22 | Fri 01/09/23 | 468 | 581FF,545FS-74 days,580SS | 0 days | 30 days | 30 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.4 |  |  |  |  | SI coordinate SIT Participants' SIT A environment preparation | 100% | Wed 16/11/22 | Fri 13/10/23 | 238 days | Wed 16/11/22 | Fri 01/09/23 | 579SS |  | 0 days | 30 days | 30 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.5 |  |  |  |  | PP submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 579FF | 582FF+5 days,583SS | 30 days | 30 days | 0 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.6 |  |  |  |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | Mon 16/10/23 | Fri 20/10/23 | 5 days | Mon 04/09/23 | Fri 08/09/23 | 581FF+5 days |  | 30 days | 30 days | 0 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.7 | T3 | T3-TE-0019 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 1 | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 581SS | 584,624SF,625SF,631 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.5.1.8 |  |  |  |  | PP SIT A environment connectivity proving | 100% | Mon 04/09/23 | Fri 15/09/23 | 10 days | Tue 12/09/23 | Mon 09/10/23 | 583 | 585SS,588SS | -6 days | -16 days | -10 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.9 |  |  |  |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 100% | Mon 04/09/23 | Fri 15/09/23 | 10 days | Tue 12/09/23 | Mon 09/10/23 | 584SS |  | -6 days | -16 days | -10 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.10 |  |  |  |  | PP deployment of MHHS solution code to SIT A environments | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Tue 26/09/23 | Mon 09/10/23 | 627FF |  | -1 day | -1 day | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.1.11 |  |  |  |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Tue 26/09/23 | Mon 09/10/23 | 627FF |  | -1 day | -1 day | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.1.12 |  |  |  |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 100% | Mon 04/09/23 | Fri 13/10/23 | 30 days | Tue 12/09/23 | Mon 09/10/23 | 584SS | 589FF+5 days | -6 days | 4 days | 10 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.13 |  |  |  |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 100% | Mon 18/09/23 | Fri 20/10/23 | 25 days | Tue 12/09/23 | Mon 16/10/23 | 588FF+5 days |  | 4 days | 4 days | 0 days | SI Test |  | 5.8 | Yes
7 | 1.4.1.4.1.5.2 |  |  |  |  | Test Data - ISD Creation | 100% | Tue 22/08/23 | Fri 01/09/23 | 9 days | Tue 22/08/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give e more clarity around work being undertaken
8 | 1.4.1.4.1.5.2.1 |  |  |  |  | Set-up Market Participants and DIP ID Data | 100% | Tue 22/08/23 | Thu 31/08/23 | 8 days | Tue 22/08/23 | Thu 31/08/23 |  | 592 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give e more clarity around work being undertaken
8 | 1.4.1.4.1.5.2.2 |  |  |  |  | Distribute ISD Data to Participants | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 591 | 593 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give e more clarity around work being undertaken
8 | 1.4.1.4.1.5.2.3 | T3 | T3-TE-0083 | SITAG |  | Test Data - ISD Creation Complete | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 592 | 616 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
7 | 1.4.1.4.1.5.3 |  |  |  |  | Test Data - SFTP Onboarding | 100% | Mon 21/08/23 | Fri 24/11/23 | 70 days | Mon 21/08/23 | Fri 24/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.3.1 |  |  |  |  | Create Containers and Keys for Participants | 100% | Mon 21/08/23 | Wed 23/08/23 | 3 days | Mon 21/08/23 | Wed 23/08/23 |  | 596 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.3.2 |  |  |  |  | Share SFTP Access with Participants | 100% | Thu 24/08/23 | Wed 30/08/23 | 5 days | Thu 24/08/23 | Wed 30/08/23 | 595 | 597 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.3.3 |  |  |  |  | Test SFTP Connectivity | 100% | Thu 31/08/23 | Wed 06/09/23 | 5 days | Thu 31/08/23 | Wed 06/09/23 | 596 | 598FS+57 days | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.3.4 | T3 | T3-TE-0084 | SITAG |  | Test Data - SFTP Onboarding Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 597FS+57 days | 1078 | 0 days | 0 days | 0 days | SI Test Data |  | 5.13 | Yes |  | Approved at TMAG on 20/9. 26/9 - RP - Red because we have changed the approach to SFTP onboarding to be phased by interval. To go to TMAG for date change approval. Approved for date change at TMAG on 23/10/23
7 | 1.4.1.4.1.5.4 |  |  |  |  | Test Data - Provide Sample Files | 100% | Mon 21/08/23 | Fri 01/09/23 | 10 days | Mon 21/08/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.4.1 |  |  |  |  | Generate Sample Files off IF Messages | 100% | Mon 21/08/23 | Wed 30/08/23 | 8 days | Mon 21/08/23 | Wed 30/08/23 |  | 601 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.4.2 |  |  |  |  | Transmit Sample Files off IF Messages to Participants (More detail needs to be planned for a POC) | 100% | Thu 31/08/23 | Fri 01/09/23 | 2 days | Thu 31/08/23 | Fri 01/09/23 | 600 | 602 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.4.3 | T3 | T3-TE-0085 | SITAG |  | Test Data - Provide Sample Files Complete | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 601 | 619,604FS+3 days | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
7 | 1.4.1.4.1.5.5 |  |  |  |  | Test Data - Detailed SIT Data Load Guidance | 100% | Thu 07/09/23 | Wed 06/12/23 | 65 days | Thu 07/09/23 | Fri 01/12/23 |  |  | 0 days | 3 days | 3 days | N/A |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.5.1 |  |  |  |  | Document Guidance | 100% | Thu 07/09/23 | Thu 05/10/23 | 21 days | Thu 07/09/23 | Thu 28/09/23 | 602FS+3 days | 605 | 0 days | 5 days | 5 days | SI Test Data |  | 5.9 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.5.2 |  |  |  |  | Provide Guidance to PPs | 100% | Fri 06/10/23 | Fri 06/10/23 | 1 day | Fri 29/09/23 | Fri 29/09/23 | 604 | 606FS+43 days | 5 days | 5 days | 0 days | SI Test Data |  | 5.9 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.5.3 | T3 | T3-TE-0095 | SITAG | MHHS-DEL 1545 | Test Data - Detailed SIT Functional Data Load Guidance Complete | 100% | Wed 06/12/23 | Wed 06/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 605FS+43 days | 835 | 3 days | 3 days | 0 days | SI Test Data |  | 5.13 | Yes |  | 28/11- Red because of slow start to CIT Interval 3, doc timelines may need to be extended. Currently no impact on final doc. Aim to update the doc incrementally
7 | 1.4.1.4.1.5.6 |  |  |  |  | Test Data - Population of Data Items for Testing Guidance - Draft | 100% | Thu 17/08/23 | Wed 06/12/23 | 80 days | Thu 17/08/23 | Fri 01/12/23 |  |  | 0 days | 3 days | 3 days | N/A |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.6.1 |  |  |  |  | Document Guidance - Draft | 100% | Thu 17/08/23 | Thu 31/08/23 | 11 days | Thu 17/08/23 | Thu 31/08/23 | 797 | 609,612SS | 0 days | 0 days | 0 days | SI Test Data |  | 5.6 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.6.2 |  |  |  |  | Provide Guidance to PPs - Draft | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 608 | 610FS+68 days | 0 days | 0 days | 0 days | SI Test Data |  | 5.6 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.6.3 | T3 | T3-TE-0096 | SITAG | MHHS-DEL 816 | Test Data - Population of Data Items for Testing Guidance - Draft Complete | 100% | Wed 06/12/23 | Wed 06/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 609FS+68 days |  | 3 days | 3 days | 0 days | SI Test Data |  | 5.13 | Yes |  | 28/11- Red because of slow start to CIT Interval 3, doc timelines may need to be extended. Currently no impact on final doc. Aim to update the doc incrementally
7 | 1.4.1.4.1.5.7 |  |  |  |  | Test Data - Population of Data Items for Testing Guidance - Final | 100% | Thu 17/08/23 | Fri 15/12/23 | 87 days | Mon 09/10/23 | Fri 08/12/23 |  |  | -37 days | 5 days | 42 days | N/A |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.7.1 |  |  |  |  | Update Document Guidance With PPS Feedback | 100% | Thu 17/08/23 | Thu 07/12/23 | 81 days | Mon 09/10/23 | Thu 07/12/23 | 608SS | 613 | -37 days | 0 days | 37 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.7.2 |  |  |  |  | Provide Final Guidance to PPs | 100% | Fri 08/12/23 | Fri 08/12/23 | 1 day | Fri 08/12/23 | Fri 08/12/23 | 612 | 614FS+5 days | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes |  | 3/8 - JW and CL meeting - added in to give more clarity around work being undertaken
8 | 1.4.1.4.1.5.7.3 | T3 | T3-TE-0097 | SITAG | MHHS-DEL 816 | Test Data - Population of Data Items for Testing Guidance - Final Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 613FS+5 days | 835 | 5 days | 5 days | 0 days | SI Test Data |  | 5.14 | Yes |  | 15/8 - JW and CL meeting - added in to give more clarity around work being undertaken. 12/12 - Red because we needed to provide the SRO 5 more working days to review. No impact. No action
7 | 1.4.1.4.1.5.8 |  |  |  |  | Test Data (SIT A) Interval 1 | 100% | Mon 04/09/23 | Fri 27/10/23 | 40 days | Mon 04/09/23 | Fri 29/09/23 |  |  | 0 days | 20 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.8.1 |  |  |  |  | Run data allocation | 100% | Mon 04/09/23 | Thu 07/09/23 | 4 days | Mon 04/09/23 | Thu 07/09/23 | 556593 | 617 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.2 |  |  |  |  | Cleanse, anonymise and populate data post cut | 100% | Fri 08/09/23 | Wed 13/09/23 | 4 days | Fri 08/09/23 | Wed 13/09/23 | 616 | 618 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.3 |  |  |  |  | Transmit data sets to PPs | 100% | Fri 15/09/23 | Tue 19/09/23 | 3 days | Fri 15/09/23 | Fri 15/09/23 | 617 | 619 | 0 days | 2 days | 2 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 20/09/23 | Thu 28/09/23 | 7 days | Mon 18/09/23 | Fri 22/09/23 | 618602 | 620,643SS | 2 days | 4 days | 2 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Fri 29/09/23 | Fri 29/09/23 | 1 day | Mon 25/09/23 | Fri 29/09/23 | 619 | 621FF | 4 days | 0 days | -4 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 620FF | 622FS+20 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.7 | T3 | T3-TE-0073 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 1 Complete | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 621FS+20 days | 631627 | 20 days | 20 days | 0 days | SI Test |  | 5.1 | Yes |  | 28/7: CH: added in to be aT3 milestone. 10/10 - RP - Red because Avanade plan to load Test Data on week commencing 23/10, this is the earliest it can be planned due to latest code being required (M9 dependant)
7 | 1.4.1.4.1.5.9 |  |  |  |  | Other Preparation | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.9.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 583SF |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.9.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 583SF | 627631 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.5.10 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Thu 14/09/23 | Mon 23/10/23 | 28 days | Mon 09/10/23 | Fri 20/10/23 |  |  | -18 days | 1 day | 19 days | N/A |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Mon 09/10/23 | Mon 09/10/23 | 625566622 | 586FF,587FF,631,628SS | 9 days | 9 days | 0 days | PP |  | 5.6 | Yes |  | 18/8 - dates changed to reflect PIT Execution date changes advised by RG
8 | 1.4.1.4.1.5.10.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 23/10/23 | Mon 23/10/23 | 1 day | Tue 10/10/23 | Mon 16/10/23 | 627SS | 631 | 9 days | 5 days | -4 days | SI Test |  | 5.6 | Yes |  | 18/8 - dates changed to reflect PIT Execution date changes advised by RG
8 | 1.4.1.4.1.5.10.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Thu 14/09/23 | Mon 16/10/23 | 23 days | Tue 10/10/23 | Fri 13/10/23 | 552FS+40 days | 630 | -18 days | 1 day | 19 days | SI Test |  | 5.6 | Yes |  | 18/8 - dates changed to reflect PIT Execution date changes advised by RG
8 | 1.4.1.4.1.5.10.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Tue 17/10/23 | Fri 20/10/23 | 4 days | Mon 16/10/23 | Fri 20/10/23 | 629 | 631FS+1 day | 1 day | 0 days | -1 day | SI Test |  | 5.6 | Yes |  | 18/8 - dates changed to reflect PIT Execution date changes advised by RG
7 | 1.4.1.4.1.5.11 | T2 | T2-TE-0250 | SITAG | MHHS-ART071 | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 630FS+1 day,627,583,625,622,200,205,194,214,215,628 | 1070FS+5 days,1073SS+1 day | 4 days | 4 days | 0 days | SI Test |  | 5.11 | Yes |  | Red because prep now dependant on an agreed work-off plan.
6 | 1.4.1.4.1.6 |  |  |  |  | CIT Interval 2 Preparation | 100% | Mon 03/07/23 | Wed 22/11/23 | 103 days | Mon 03/07/23 | Fri 10/11/23 |  |  | 0 days | 8 days | 8 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.6.1 |  |  |  |  | Environments (SIT A) | 100% | Fri 22/09/23 | Wed 22/11/23 | 43 days | Fri 22/09/23 | Fri 10/11/23 |  |  | 0 days | 8 days | 8 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.1.1 | T3 | T3-TE-0020 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 2 | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 |  | 651SF,658 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.6.1.2 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 |  | 636 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Mon 25/09/23 | Fri 06/10/23 | 635 | 637 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 636 | 638FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 16/10/23 | Wed 22/11/23 | 28 days | Mon 16/10/23 | Fri 10/11/23 | 637FS+5 days | 639 | 0 days | 8 days | 8 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.6 |  |  |  |  | DIP Onboarding Complete | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 638 | 640 | 8 days | 8 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.7 | T3 | T3-TE-0098 | SITAG |  | PPs Register PKI Officers and request PKI certificates Complete - Interval 2 | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 639 |  | 23 days | 23 days | 0 days | PP |  | 5.15 | Yes |  | 5/12- Red because only 1 PP has successfully registered their PKI Officers; received their PKI certificates; set-up validation compete; end point creation complete; and completed controlled smoke test. The other PP is currently in Step 4 of E2E onboarding
8 | 1.4.1.4.1.6.1.8 |  |  |  |  | PP Code Deployment | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.6.2 |  |  |  |  | Test Data (SIT A) Interval 2 | 100% | Wed 20/09/23 | Fri 17/11/23 | 43 days | Mon 18/09/23 | Fri 20/10/23 |  |  | 2 days | 20 days | 18 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.2.1 |  |  |  |  | Run data allocation | 100% | Wed 20/09/23 | Thu 28/09/23 | 7 days | Mon 18/09/23 | Fri 22/09/23 | 619SS | 644 | 2 days | 4 days | 2 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Fri 29/09/23 | Mon 02/10/23 | 2 days | Mon 25/09/23 | Fri 29/09/23 | 643 | 645 | 4 days | 1 day | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.3 |  |  |  |  | Transmit data sets to PPs | 100% | Tue 03/10/23 | Tue 03/10/23 | 1 day | Mon 02/10/23 | Tue 03/10/23 | 644 | 646,675SS | 1 day | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 04/10/23 | Fri 17/11/23 | 33 days | Wed 04/10/23 | Fri 13/10/23 | 645 | 647FF | 0 days | 25 days | 25 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 23/10/23 | Fri 17/11/23 | 15 days | Mon 16/10/23 | Fri 20/10/23 | 646FF | 648FF | 5 days | 20 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 647FF | 649 | 20 days | 20 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.7 | T3 | T3-TE-0074 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 2 Complete | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 648 |  | 20 days | 20 days | 0 days | SI Test |  | 5.12 | Yes |  | 28/7: CH: added in to be aT3 milestone. 15/11 - Red because of Data Customisation requirement for St. Clements and additional DIP message requirement. Impact is CIT able to start on selected MPANS remaining MPANS to be fixed by 16/11
7 | 1.4.1.4.1.6.3 |  |  |  |  | Other Preparation | 100% | Mon 03/07/23 | Tue 31/10/23 | 87 days | Mon 03/07/23 | Tue 31/10/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.3.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 03/07/23 | Fri 22/09/23 | 60 days | Mon 03/07/23 | Fri 22/09/23 | 634SF | 652 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.3.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 25/09/23 | Tue 31/10/23 | 27 days | Mon 25/09/23 | Tue 31/10/23 | 651 | 658 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.6.4 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 02/10/23 | Fri 03/11/23 | 25 days | Mon 02/10/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.4.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 566FS+18 days | 655 | 3 days | 3 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.4.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Thu 26/10/23 | Fri 27/10/23 | 2 days | Mon 23/10/23 | Fri 27/10/23 | 654 | 656FF | 3 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.4.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 02/10/23 | Fri 27/10/23 | 20 days | Mon 02/10/23 | Fri 27/10/23 | 655FF | 657 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.4.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 30/10/23 | Fri 03/11/23 | 5 days | Mon 30/10/23 | Fri 03/11/23 | 656 | 658FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.6.5 | T2 | T2-TE-0300 | SITAG | MHHS-ART071 | SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 06/11/23 | Mon 06/11/23 | 0 days | Mon 06/11/23 | Mon 06/11/23 | 652,657FS+1 day,634,263 | 1074SS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes |  | Amber because of dependency on PPs PIT and known reduced window to review and prepare documentation. No impact currently known. No action. 7/11 - Approved at TMAG on 6/11 with work-off
6 | 1.4.1.4.1.7 |  |  |  |  | CIT Interval 3 Preparation | 100% | Tue 03/10/23 | Fri 15/12/23 | 54 days | Mon 17/07/23 | Mon 20/11/23 |  |  | 56 days | 19 days | -37 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.7.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 13/10/23 | Fri 17/11/23 | 26 days | Fri 13/10/23 | Fri 10/11/23 |  |  | 0 days | 5 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 13/10/23 | Fri 27/10/23 | 11 days | Fri 13/10/23 | Fri 13/10/23 |  | 662 | 0 days | 10 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 30/10/23 | Fri 03/11/23 | 5 days | Mon 16/10/23 | Fri 03/11/23 | 661 | 663 | 10 days | 0 days | -10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.1.3 | T3 | T3-DB-0017 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 662,80,96 | 664690 | 0 days | 0 days | 0 days | PP |  | 5.11 | Yes
8 | 1.4.1.4.1.7.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 06/11/23 | Fri 17/11/23 | 10 days | Mon 06/11/23 | Fri 10/11/23 | 663 |  | 0 days | 5 days | 5 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.7.2 |  |  |  |  | Environments (SIT A) | 100% | Fri 06/10/23 | Fri 15/12/23 | 51 days | Fri 06/10/23 | Fri 10/11/23 |  |  | 0 days | 25 days | 25 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 |  | 668FS+1 day,667 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.2 | T3 | T3-TE-0021 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 3 | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 666 | 690 | -1 day | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 09/10/23 | Fri 20/10/23 | 10 days | Mon 09/10/23 | Fri 20/10/23 | 666FS+1 day | 669 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 668 | 670FS+5 days,673FS+15 days | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 30/10/23 | Fri 15/12/23 | 35 days | Mon 30/10/23 | Fri 10/11/23 | 669FS+5 days | 671 | 0 days | 25 days | 25 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 670 | 672FF | 25 days | 25 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.7 | T3 | T3-TE-0099 | SITAG |  | PPs Register PKI Officers and Request PKI certificates Complete - Interval 3 | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 671FF |  | 25 days | 25 days | 0 days | PP |  | 5.13 | Yes |  | 09/01 - 1 participant yet to complete onboarding. Anticipated resolution unknown
8 | 1.4.1.4.1.7.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 669FS+15 days |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.7.3 |  |  |  |  | Test Data (SIT A) Interval 3 | 100% | Tue 03/10/23 | Fri 17/11/23 | 34 days | Mon 02/10/23 | Fri 03/11/23 |  |  | 1 day | 10 days | 9 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.3.1 |  |  |  |  | Run data allocation | 100% | Tue 03/10/23 | Fri 06/10/23 | 4 days | Mon 02/10/23 | Fri 06/10/23 | 645SS | 676 | 1 day | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Mon 09/10/23 | Fri 13/10/23 | 5 days | Mon 09/10/23 | Fri 13/10/23 | 675 | 677,707FS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Mon 16/10/23 | Tue 17/10/23 | 2 days | Mon 16/10/23 | Tue 17/10/23 | 676 | 678 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 18/10/23 | Fri 27/10/23 | 8 days | Wed 18/10/23 | Fri 27/10/23 | 677 | 679 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 30/10/23 | Fri 17/11/23 | 15 days | Mon 30/10/23 | Fri 03/11/23 | 678 | 680FF | 0 days | 10 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 679FF | 681 | 10 days | 10 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.7 | T3 | T3-TE-0075 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 3 Complete | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 680 | 690 | 10 days | 10 days | 0 days | SI Test |  | 5.13 | Yes |  | 28/7: CH: added in to be aT3 milestone. 14/11-Red because 8 out of 9 participants complete. Final data checks from PP to be made this week. No impact to CIT interval 3 start.
7 | 1.4.1.4.1.7.4 |  |  |  |  | Other Preparation | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 17/07/23 | Fri 06/10/23 |  |  | 65 days | 30 days | -35 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 17/07/23 | Fri 06/10/23 |  |  | 65 days | 30 days | -35 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 17/07/23 | Fri 06/10/23 |  | 690 | 65 days | 30 days | -35 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.7.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 16/10/23 | Fri 17/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 570 | 687FF+5 days,690 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 06/11/23 | Fri 10/11/23 | 5 days | Mon 06/11/23 | Fri 10/11/23 | 686FF+5 days | 688FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 10/11/23 | 20 days | Mon 16/10/23 | Fri 10/11/23 | 687FF | 689 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.5.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 13/11/23 | Fri 17/11/23 | 5 days | Mon 13/11/23 | Fri 17/11/23 | 688 | 690FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.7.6 | T2 | T2-TE-0350 | SITAG | MHHS-ART071 | SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Mon 20/11/23 | Mon 20/11/23 | 689FS+1 day,663,667,686,684,681,281 | 1075SS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.4.1.8 |  |  |  |  | CIT Interval 4 Preparation | 100% | Mon 16/10/23 | Mon 04/12/23 | 36 days | Mon 16/10/23 | Mon 04/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.8.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 27/10/23 | Fri 24/11/23 | 21 days | Fri 27/10/23 | Fri 24/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 27/10/23 | Fri 27/10/23 | 1 day | Fri 27/10/23 | Fri 27/10/23 |  | 694 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 30/10/23 | Fri 17/11/23 | 15 days | Mon 30/10/23 | Fri 17/11/23 | 693 | 695 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.1.3 | T3 | T3-DB-0019 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 694,80,96 | 696722 | 0 days | 0 days | 0 days | PP |  | 5.13 | Yes |  | 21/11-Red because not all received. Reminders sent. No impact. No issue
8 | 1.4.1.4.1.8.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 20/11/23 | Fri 24/11/23 | 5 days | Mon 20/11/23 | Fri 24/11/23 | 695 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.8.2 |  |  |  |  | Environments (SIT A) | 100% | Mon 23/10/23 | Fri 24/11/23 | 25 days | Fri 20/10/23 | Fri 24/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 |  | 699 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.2 | T3 | T3-TE-0022 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 4 | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 698 | 722700 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 23/10/23 | Fri 03/11/23 | 10 days | Mon 23/10/23 | Fri 03/11/23 | 699 | 701 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 700 | 702FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 13/11/23 | Fri 24/11/23 | 10 days | Mon 13/11/23 | Fri 24/11/23 | 701FS+5 days | 703 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 702 | 704 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.7 | T3 | T3-TE-0100 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 4 | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 703 |  | 0 days | 0 days | 0 days | PP |  | 5.16 | Yes |  | 16/02 - Red because 2 participants yet to complete onboarding. Completed 19/1/24
8 | 1.4.1.4.1.8.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.8.3 |  |  |  |  | Test Data (SIT A) Interval 4 | 100% | Mon 23/10/23 | Fri 01/12/23 | 30 days | Mon 16/10/23 | Fri 17/11/23 |  |  | 5 days | 10 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.3.1 |  |  |  |  | Run data allocation | 100% | Mon 23/10/23 | Fri 27/10/23 | 5 days | Mon 16/10/23 | Fri 20/10/23 | 676FS+5 days | 708 | 5 days | 5 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Mon 30/10/23 | Tue 31/10/23 | 2 days | Mon 23/10/23 | Fri 27/10/23 | 707 | 709 | 5 days | 2 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Wed 01/11/23 | Tue 07/11/23 | 5 days | Mon 30/10/23 | Tue 31/10/23 | 708 | 710,739SS | 2 days | 5 days | 3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 08/11/23 | Tue 14/11/23 | 5 days | Wed 01/11/23 | Fri 10/11/23 | 709 | 711 | 5 days | 2 days | -3 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Wed 15/11/23 | Fri 01/12/23 | 13 days | Mon 13/11/23 | Fri 17/11/23 | 710 | 712FF | 2 days | 10 days | 8 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 711FF | 713 | 10 days | 10 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.7 | T3 | T3-TE-0076 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 4 Complete | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 712 | 722 | 10 days | 10 days | 0 days | SI Test |  | 5.13 | Yes |  | 28/11 - red because data was delivered 1 week late. This led to an onward impact. We expect data to be loaded and checked by 1/12. No impact on CIT Tests Start date
7 | 1.4.1.4.1.8.4 |  |  |  |  | Other Preparation | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.8.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Tue 21/11/23 | 27 days | Mon 30/10/23 | Fri 01/12/23 |  |  | -10 days | -8 days | 2 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 570 | 719FF+5 days,722 | -10 days | -10 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 06/11/23 | Fri 10/11/23 | 5 days | Mon 20/11/23 | Fri 24/11/23 | 718FF+5 days | 720FF | -10 days | -10 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 10/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 719FF | 721 | -10 days | -10 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.5.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Mon 13/11/23 | Tue 21/11/23 | 7 days | Mon 27/11/23 | Fri 01/12/23 | 720 | 722FS+2 days | -10 days | -8 days | 2 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.8.6 | T2 | T2-TE-0400 | SITAG | MHHS-ART071 | SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 04/12/23 | Mon 04/12/23 | 0 days | Mon 04/12/23 | Mon 04/12/23 | 721FS+2 days,695,699,718,713,298FS+1 day | 1076SS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5.13 | Yes |  | 5/12 - Approved at Etmag on 4/12 with work off plan
6 | 1.4.1.4.1.9 |  |  |  |  | CIT Interval 5 Preparation | 100% | Wed 01/11/23 | Fri 12/01/24 | 53 days | Mon 30/10/23 | Fri 12/01/24 |  |  | 2 days | 0 days | -2 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.9.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 17/11/23 | Fri 15/12/23 | 21 days | Fri 17/11/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 1 day | Fri 17/11/23 | Fri 17/11/23 |  | 726 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 20/11/23 | Fri 08/12/23 | 15 days | Mon 20/11/23 | Fri 08/12/23 | 725 | 727 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.1.3 | T3 | T3-DB-0021 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 726,80,96 | 728754 | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes |  | 4/12- Amber because not all received yet. No impact. No action. 19/12 - complete on 14/12
8 | 1.4.1.4.1.9.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 727 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.9.2 |  |  |  |  | Environments (SIT A) | 100% | Fri 10/11/23 | Fri 08/12/23 | 21 days | Fri 10/11/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 |  | 732FS+1 day,731 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.2 | T3 | T3-TE-0023 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 5 | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 730 | 754 | -1 day | -1 day | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.9.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 13/11/23 | Fri 24/11/23 | 10 days | Mon 13/11/23 | Fri 24/11/23 | 730FS+1 day | 733 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 732 | 734 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 27/11/23 | Fri 08/12/23 | 10 days | Mon 27/11/23 | Fri 08/12/23 | 733 | 735 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 734 | 736 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.7 | T3 | T3-TE-0101 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 5 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 735 | 737 | 0 days | 0 days | 0 days | PP |  | 5.17 | Yes |  | 16/01- Red because 1 has yet to complete onboarding. 30/1 - Completed on 26/1/24
8 | 1.4.1.4.1.9.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 736 |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.9.3 |  |  |  |  | Test Data (SIT A) Interval 5 | 100% | Wed 01/11/23 | Fri 15/12/23 | 33 days | Mon 30/10/23 | Fri 08/12/23 |  |  | 2 days | 5 days | 3 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.3.1 |  |  |  |  | Run data allocation | 100% | Wed 01/11/23 | Tue 07/11/23 | 5 days | Mon 30/10/23 | Fri 10/11/23 | 709SS | 740 | 2 days | -3 days | -5 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Wed 08/11/23 | Fri 17/11/23 | 8 days | Mon 13/11/23 | Fri 17/11/23 | 739 | 741 | -3 days | 0 days | 3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Mon 20/11/23 | Tue 21/11/23 | 2 days | Mon 20/11/23 | Tue 21/11/23 | 740 | 742,771SS | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 22/11/23 | Fri 01/12/23 | 8 days | Wed 22/11/23 | Fri 01/12/23 | 741 | 743 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 08/12/23 | 742 | 744FF | 0 days | 5 days | 5 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 743FF | 745 | 5 days | 5 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.7 | T3 | T3-TE-0077 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 5 Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 744 | 754 | 5 days | 5 days | 0 days | SI Test |  | 5.14 | Yes |  | 28/7: CH: added in to be aT3 milestone. 12/12 - Red because PPs required additional time due to some data changes required. No impact. Action to follow-up with PPs for latest progress
7 | 1.4.1.4.1.9.4 |  |  |  |  | Other Preparation | 100% | Mon 20/11/23 | Fri 12/01/24 | 40 days | Mon 20/11/23 | Fri 12/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 20/11/23 | Fri 12/01/24 | 40 days | Mon 20/11/23 | Fri 12/01/24 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 20/11/23 | Mon 08/01/24 | 36 days | Mon 20/11/23 | Mon 08/01/24 |  | 754 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.9.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 05/01/24 | 35 days | Mon 20/11/23 | Fri 05/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 574 | 751FF+5 days,754 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 750FF+5 days | 752FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 15/12/23 | 20 days | Mon 20/11/23 | Fri 15/12/23 | 751FF | 753 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.5.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Mon 18/12/23 | Fri 05/01/24 | 15 days | Mon 18/12/23 | Fri 05/01/24 | 752 | 754FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.9.6 | T2 | T2-TE-0450 | SITAG | MHHS-ART071 | SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 08/01/24 | Mon 08/01/24 | 0 days | Mon 08/01/24 | Mon 08/01/24 | 753FS+1 day,727,731,748,750,745,400,383 | 1077SS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5.15 | Yes |  | 2/1/24 - Approved at Dec TMAG following change in CIT governance
6 | 1.4.1.4.1.10 |  |  |  |  | CIT Interval 6 Preparation | 100% | Mon 20/11/23 | Fri 19/01/24 | 45 days | Mon 20/11/23 | Mon 22/01/24 |  |  | 0 days | -1 day | -1 day | N/A |  | 5 | Yes
7 | 1.4.1.4.1.10.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 01/12/23 | Fri 12/01/24 | 31 days | Fri 01/12/23 | Fri 12/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 01/12/23 | Fri 01/12/23 | 1 day | Fri 01/12/23 | Fri 01/12/23 |  | 758 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 04/12/23 | Fri 05/01/24 | 25 days | Mon 04/12/23 | Fri 05/01/24 | 757 | 759 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.1.3 | T3 | T3-DB-0023 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 758,80,96,220,225,228 | 760786 | 0 days | 0 days | 0 days | PP |  | 5.19 | Yes |  | 9/1 - Not all completion reports yet received. Completed 22/2/24
8 | 1.4.1.4.1.10.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 08/01/24 | Fri 12/01/24 | 5 days | Mon 08/01/24 | Fri 12/01/24 | 759 |  | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
7 | 1.4.1.4.1.10.2 |  |  |  |  | Environments (SIT A) | 100% | Fri 24/11/23 | Fri 05/01/24 | 30 days | Fri 24/11/23 | Fri 05/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 |  | 763 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.2 | T3 | T3-TE-0024 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 6 | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 762 | 786,764FS+1 day,766FS+6 days | -1 day | -1 day | 0 days | PP |  | 5.6 | Yes |  | 29/11 - Red because forecast date missed. Participants status to be determined by 4th December. No risk to future milestones
8 | 1.4.1.4.1.10.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | Mon 27/11/23 | Fri 08/12/23 | 10 days | Mon 27/11/23 | Fri 08/12/23 | 763FS+1 day | 765 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 764 |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 04/12/23 | Fri 08/12/23 | 5 days | Mon 04/12/23 | Fri 08/12/23 | 763FS+6 days | 767 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes |  | 5/12 -
8 | 1.4.1.4.1.10.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 766 | 768 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.7 | T3 | T3-TE-0102 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 6 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 767 |  | 1 day | 0 days | 0 days | PP |  | 5.17 | Yes |  | 12/12 - Red because 1 Participant still to complete. 30/1 - Completed 29/1/24
8 | 1.4.1.4.1.10.2.8 |  |  |  |  | PP Code Deployment | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 |  |  | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.10.3 |  |  |  |  | Test Data (SIT A) Interval 6 | 100% | Mon 20/11/23 | Fri 22/12/23 | 25 days | Mon 20/11/23 | Fri 22/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.3.1 |  |  |  |  | Run data allocation | 100% | Mon 20/11/23 | Fri 01/12/23 | 10 days | Mon 20/11/23 | Fri 24/11/23 | 741SS | 772 | 0 days | 5 days | 5 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | Mon 04/12/23 | Mon 04/12/23 | 1 day | Mon 27/11/23 | Fri 01/12/23 | 771 | 773 | 5 days | 1 day | -4 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | Tue 05/12/23 | Tue 05/12/23 | 1 day | Mon 04/12/23 | Tue 05/12/23 | 772 | 774 | 1 day | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | Wed 06/12/23 | Fri 15/12/23 | 8 days | Wed 06/12/23 | Fri 15/12/23 | 773 | 775 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | Mon 18/12/23 | Fri 22/12/23 | 5 days | Mon 18/12/23 | Fri 22/12/23 | 774 | 776FF | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 775FF | 777 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.7 | T3 | T3-TE-0078 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 6 Complete | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 776 | 786 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes |  | 28/7: CH: added in to be aT3 milestone
7 | 1.4.1.4.1.10.4 |  |  |  |  | Other Preparation | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 |  |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 |  | 786 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.10.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 22/12/23 | 25 days | Mon 18/12/23 | Fri 19/01/24 |  |  | -20 days | -20 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 574 | 783FF+5 days,786 | -20 days | -20 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 08/01/24 | Fri 12/01/24 | 782FF+5 days | 784FF | -20 days | -20 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 15/12/23 | 20 days | Mon 18/12/23 | Fri 12/01/24 | 783FF | 785 | -20 days | -20 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.5.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 18/12/23 | Fri 22/12/23 | 5 days | Mon 15/01/24 | Fri 19/01/24 | 784 | 786FS+1 day | -20 days | -20 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.10.6 | T2 | T2-TE-0500 | SITAG | MHHS-ART071 | SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Mon 22/01/24 | Mon 22/01/24 | 785FS+1 day,759,763,780,782,777,246,417 | 1078 | -1 day | -1 day | 0 days | SI Test |  | 5.15 | Yes |  | 2/1/24 - Approved at Dec TMAG following change in CIT governance
5 | 1.4.1.4.2 |  |  |  |  | SIT Functional Preparation | 78% | Mon 31/10/22 | Fri 04/04/25 | 635 days? | Mon 31/10/22 | Fri 25/10/24 |  |  | 0 days | 115 days | 115 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.2.1 |  |  |  |  | Environment Approach and Plan - SIT Functional | 100% | Mon 20/11/23 | Mon 20/11/23 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  | 6 | Yes
6 | 1.4.1.4.2.2 |  |  |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Wed 16/08/23 | 208 days | Mon 31/10/22 | Wed 16/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.2.1 |  |  |  |  | Develop document with SITWG | 100% | Mon 31/10/22 | Thu 06/07/23 | 179 days | Mon 31/10/22 | Thu 06/07/23 |  | 799SS+45 days,791 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.2.2 |  |  |  |  | Industry Consultation | 100% | Fri 07/07/23 | Thu 20/07/23 | 10 days | Fri 07/07/23 | Thu 20/07/23 | 790 | 792,795SS | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.2.2.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 21/07/23 | Wed 16/08/23 | 19 days | Fri 21/07/23 | Wed 16/08/23 | 791 |  | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.2.2.4 | T3 | T3-TE-0013 | SITAG | MHHS-ART073 | SIT Functional Testing Test Approach & Plan approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 |  | 8639811088 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.2.3 |  |  |  |  | Test Data Approach & Plan | 100% | Fri 07/07/23 | Wed 16/08/23 | 29 days | Fri 07/07/23 | Wed 16/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.3.1 |  |  |  |  | Industry Consultation | 100% | Fri 07/07/23 | Thu 20/07/23 | 10 days | Fri 07/07/23 | Thu 20/07/23 | 791SS | 796 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.2.3.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 21/07/23 | Wed 16/08/23 | 19 days | Fri 21/07/23 | Wed 16/08/23 | 795 | 797 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.2.3.3 |  |  |  |  | SIT Functional Testing Test Data Approach & Plan approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 796 | 608 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
6 | 1.4.1.4.2.4 |  |  |  |  | Test scenarios | 100% | Mon 02/01/23 | Wed 21/02/24 | 298 days | Mon 02/01/23 | Wed 21/02/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.4.1 |  |  |  |  | Development of test scenarios | 100% | Mon 02/01/23 | Fri 28/04/23 | 85 days | Mon 02/01/23 | Fri 28/04/23 | 790SS+45 days | 800FS+78 days,806 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.4.2 |  |  |  |  | Review test scenarios with SIT Working Group | 100% | Thu 17/08/23 | Wed 15/11/23 | 65 days | Thu 17/08/23 | Wed 15/11/23 | 799FS+78 days | 801FS+17 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.4.3 | T3 | T3-TE-0015 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (themes 1-5) approved | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 800FS+17 days | 863,1088,802FS+28 days | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | Red because 8/12 TMAG moved to 20/12 due to reduction of Dec TMAGS. 5/12 Name change to SIT Functional Testing Test scenarios (themes 1-5) approved 20/12 - Approved at TMAG on 20/12
7 | 1.4.1.4.2.4.4 | T3 | T3-TE-0106 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (themes 6,7,9) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 801FS+28 days | 803FS+25 days,1088 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes |  | 5/12 - New milestone to go to 20/12 TMAG for approval. Added because of new delivery approach for SIT functional artifacts 20/12 - Approved at TMAG on 20/12
7 | 1.4.1.4.2.4.5 | T3 | T3-TE-0107 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (theme 8) approved | 100% | Wed 21/02/24 | Wed 21/02/24 | 0 days | Wed 21/02/24 | Wed 21/02/24 | 802FS+25 days | 1088 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 5/12 - New milestone to go to 20/12 TMAG for approval. Added because of new delivery approach for SIT functional artifacts 20/12 - Approved at TMAG on 20/12
6 | 1.4.1.4.2.5 |  |  |  |  | Test cases | 77% | Mon 01/05/23 | Fri 20/09/24 | 365 days? | Mon 01/05/23 | Wed 21/02/24 |  |  | 0 days | 152 days | 152 days? | N/A |  | 5 | Yes
7 | 1.4.1.4.2.5.1 |  |  |  |  | SI Test cases | 100% | Mon 01/05/23 | Wed 21/02/24 | 213 days | Mon 01/05/23 | Wed 21/02/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.5.1.1 |  |  |  |  | Development of Test cases | 100% | Mon 01/05/23 | Fri 24/11/23 | 150 days | Mon 01/05/23 | Fri 24/11/23 | 799 | 807SS+105 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 15/9 - Potentially add in additional lines to track against progress
8 | 1.4.1.4.2.5.1.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | Mon 25/09/23 | Wed 10/01/24 | 78 days | Mon 25/09/23 | Wed 10/01/24 | 806SS+105 days | 808FS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.5.1.3 | T3 | T3-TE-0070 | SITAG | MHHS-ART140 | SIT Functional Testing Test Cases (themes 1-5) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 807FS+5 days | 863809 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 5/12 Name change to SIT Functional Testing Test Cases (themes 1-5) approved 20/12 - Approved at TMAG on 20/12
8 | 1.4.1.4.2.5.1.4 | T3 | T3-TE-0108 | SITAG | MHHS-ART140 | SIT Functional Testing Test cases (themes 6,7,9) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 808 | 810FS+25 days | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 5/12- New milestone added because revised delivery approach for SIT Functional 20/12 - Approved at TMAG on 20/12
8 | 1.4.1.4.2.5.1.5 | T3 | T3-TE-0109 | SITAG | MHHS-ART140 | SIT Functional Testing Test cases (theme 8) approved | 100% | Wed 21/02/24 | Wed 21/02/24 | 0 days | Wed 21/02/24 | Wed 21/02/24 | 809FS+25 days | 1088 | 0 days | 0 days | 0 days | SI Test |  | 5.14 | Yes |  | 5/12- New milestone added because revised delivery approach for SIT Functional
7 | 1.4.1.4.2.5.2 |  |  |  |  | SIT Functional Programme RTTM | 0% | Mon 29/07/24 | Fri 20/09/24 | 40 days? | NA | NA |  |  | 0 days | 0 days | 40 days? |  |  |  | Yes
8 | 1.4.1.4.2.5.2.1 |  |  |  |  | Development of Manual SIT Functional RTTM | 0% | Mon 29/07/24 | Fri 06/09/24 | 30 days? | NA | NA |  | 813 | 0 days | 0 days | 30 days? |  |  |  | Yes
8 | 1.4.1.4.2.5.2.2 |  |  |  |  | Manual SIT Functional RTTM Complete | 0% | Fri 06/09/24 | Fri 06/09/24 | 0 days? | NA | NA | 812 |  | 0 days | 0 days | 0 days? |  |  |  | Yes
8 | 1.4.1.4.2.5.2.3 |  |  |  |  | Development of Automated SIT Functional RTTM | 0% | Mon 29/07/24 | Fri 20/09/24 | 40 days? | NA | NA |  | 815 | 0 days | 0 days | 40 days? |  |  |  | Yes
8 | 1.4.1.4.2.5.2.4 |  |  |  |  | Automated SIT Functional RTTM Complete | 0% | Fri 20/09/24 | Fri 20/09/24 | 0 days? | NA | NA | 814 |  | 0 days | 0 days | 0 days? |  |  |  | Yes
6 | 1.4.1.4.2.6 |  |  |  |  | Environments (SIT-Staging) | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Wed 16/11/22 | Fri 09/02/24 |  |  | 273 days | -40 days | -313 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.6.1 |  |  |  |  | SIT Functional pre-requisites | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
8 | 1.4.1.4.2.6.1.1 |  |  |  |  | DCC | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
9 | 1.4.1.4.2.6.1.1.1 |  |  |  |  | CSS | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.1.1 |  |  |  |  | SIT participants have requested DCC CSS PKI certificates for access to UIT-B environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  | 821 | 0 days | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.1.2 | T3 | T3-TE-0088 | SITAG |  | SIT participants have received DCC CSS PKI certificates for UIT-B environment | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 820 |  | 0 days | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) |  | 5.5 | Yes |  | To be proposed as a T3 Milestone at next TMAG
9 | 1.4.1.4.2.6.1.1.2 |  |  |  |  | DSP | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.2.1 |  |  |  |  | SIT participants have requested DCC DSP PKI certificates for access to UIT-B environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  | 824 | 0 days | 0 days | 0 days | PPs in SDS Market Role |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.2.2 | T3 | T3-TE-0089 | SITAG |  | SIT participants have received DCC DSP PKI certificates for UIT-B environment | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 823 |  | 0 days | 0 days | 0 days | PPs in SDS Market Role |  | 5.5 | Yes |  | 19/12 - MHHS PPs who require DCC, DSP, PKI certificates will request them in order to participate in DCC UEPT
6 | 1.4.1.4.2.7 |  |  |  |  | Stand up SIT A Environment | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 08/01/24 | Fri 09/02/24 |  |  | 20 days | 20 days | 0 days | N/A |  | 6 | Yes |  | 12/09/24 - Name change in line with SI Plan
7 | 1.4.1.4.2.7.1 |  |  |  |  | SIT Functional Connectivity Proving | 100% | Mon 12/02/24 | Fri 01/03/24 | 15 days | Mon 08/01/24 | Fri 02/02/24 |  |  | 25 days | 20 days | -5 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.2.7.1.1 |  |  |  |  | SIT Functional Connectivity Proving Period | 100% | Mon 12/02/24 | Fri 01/03/24 | 15 days | Mon 12/02/24 | Fri 01/03/24 |  | 828 | 0 days | 0 days | -5 days | SI Test |  | 5.19 | Yes |  | 16/8 - Needs to start 8 weeks before SIT Functional Testing starts
8 | 1.4.1.4.2.7.1.2 | T3 | T3-TE-0103 | SITAG |  | SIT Functional Connectivity Proving Complete | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 827 |  | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes |  | 21/2/24 - Date change approved at SITAG on 21/2/24. 4/3 - PPs in the process of completing the activity, two thirds complete, the remain under in various stages of completeness
7 | 1.4.1.4.2.7.2 |  |  |  |  | PP Environments (SIT A) | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 |  |  | 0 days | 20 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.7.2.1 |  |  |  |  | Deployment of MHHS solution code to SIT A environments | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 |  | 832SS | 0 days | 20 days | 20 days | PP |  | 5 | Yes
7 | 1.4.1.4.2.7.3 |  |  |  |  | SI Environments (SIT A) | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 |  |  | 0 days | 20 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.7.3.1 |  |  |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 | 830SS |  | 0 days | 20 days | 20 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.2.8 |  |  |  |  | Test data (SIT A) | 38% | Mon 18/12/23 | Fri 04/04/25 | 340 days | Mon 18/12/23 | Fri 25/10/24 |  |  | 0 days | 115 days | 115 days | N/A |  | 5.4 | Yes
7 | 1.4.1.4.2.8.1 |  |  |  |  | Cycle 1 Test data (SIT A) | 100% | Mon 18/12/23 | Fri 01/03/24 | 55 days | Mon 18/12/23 | Fri 01/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.1.1 |  |  |  |  | Prepare, Generate and Allocate Test Data | 100% | Mon 18/12/23 | Wed 24/01/24 | 28 days | Mon 18/12/23 | Wed 24/01/24 | 606614 | 836FS+1 day | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.2 |  |  |  |  | Transmit Data Sets to PPs | 100% | Fri 26/01/24 | Wed 31/01/24 | 4 days | Thu 25/01/24 | Fri 26/01/24 | 835FS+1 day | 837 | 1 day | 3 days | 2 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.3 |  |  |  |  | PP's Iterative load and data integrity check | 100% | Thu 01/02/24 | Fri 01/03/24 | 22 days | Mon 29/01/24 | Fri 09/02/24 | 836 | 838 | 3 days | 15 days | 12 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.4 | T3 | T3-TE-0079 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 1 - PP's confirmation that test data is ready for SIT Functional | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 837 | 840FS+18 days,863,1091 | 0 days | 0 days | 0 days | SI Test Data |  | 5.18 | Yes |  | 21/2/24 - Date change approved at SITAG on 21/2/24. 5/3 - Red because 20% of PPs differed the data load to 6/3. These PPs have an action plan to complete this.
7 | 1.4.1.4.2.8.2 |  |  |  |  | Cycle 2 Test data (inc. Settlement Data) (SIT A) | 100% | Thu 28/03/24 | Fri 14/06/24 | 57 days | Thu 28/03/24 | Fri 31/05/24 |  |  | 0 days | 10 days | 10 days | N/A |  | 6 | Yes |  | 12/09/24 - Name change in line with the SI Plan
8 | 1.4.1.4.2.8.2.1 |  |  |  |  | Prepare, Generate and Allocate Test Data | 100% | Thu 28/03/24 | Thu 09/05/24 | 31 days | Thu 28/03/24 | Thu 09/05/24 | 838FS+18 days | 841 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.2 |  |  |  |  | Transmit Data Sets to PPs | 100% | Fri 10/05/24 | Tue 14/05/24 | 3 days | Fri 10/05/24 | Tue 14/05/24 | 840 | 842 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.3 |  |  |  |  | PP's Iterative load and data integrity check | 100% | Wed 15/05/24 | Fri 31/05/24 | 13 days | Wed 15/05/24 | Fri 31/05/24 | 841 | 843FS+10 days | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.4 | T3 | T3-TE-0080 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 2 - PP's confirmation that test data is ready for SIT Functional | 100% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Fri 31/05/24 | Fri 31/05/24 | 842FS+10 days | 845FS+5 days,1094 | 10 days | 10 days | 0 days | SI Test Data |  | 5.27 | Yes |  | 4/6: Date missed because there are 3 separate data loads for each PP to complete. This is proving time consuming but is expected to complete by 14/6
7 | 1.4.1.4.2.8.3 |  |  |  |  | Cycle 3 Test data (SIT A) (2) | 15% | Mon 24/06/24 | Fri 18/10/24 | 85 days | Mon 24/06/24 | Mon 19/08/24 |  |  | 0 days | 44 days | 44 days | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.3.1 |  |  |  |  | Prepare, Generate and Allocate Test Data | 22% | Mon 24/06/24 | Fri 13/09/24 | 60 days | Mon 24/06/24 | Wed 17/07/24 | 843FS+5 days | 846 | 0 days | 42 days | 42 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.3.2 |  |  |  |  | Transmit Data Sets to PPs | 0% | Mon 16/09/24 | Tue 17/09/24 | 2 days | Thu 18/07/24 | Fri 19/07/24 | 845 | 847 | 42 days | 42 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.3.3 |  |  |  |  | PP's Iterative load and data integrity check | 0% | Wed 18/09/24 | Fri 18/10/24 | 23 days | Mon 22/07/24 | Mon 19/08/24 | 846 | 848 | 42 days | 44 days | 2 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.3.4 | T3 | T3-TE-0081 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 3 - PP's confirmation that test data is ready for SIT Functional (end 18/10/24) | 0% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Mon 19/08/24 | Mon 19/08/24 | 847 | 850FS+4 days | 45 days | 44 days | 0 days | SI Test Data |  | 5.14 | Yes |  | Date re-forecast in line with short term scenario planning. Introduction of 5 weeks of additional sprints.
7 | 1.4.1.4.2.8.4 |  |  |  |  | Regression Test data (SIT A) | 0% | Fri 25/10/24 | Fri 04/04/25 | 116 days | Mon 26/08/24 | Fri 25/10/24 |  |  | 44 days | 115 days | 71 days | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.4.1 |  |  |  |  | Prepare, Generate and Allocate Test Data | 0% | Fri 25/10/24 | Wed 05/03/25 | 94 days | Mon 26/08/24 | Wed 25/09/24 | 848FS+4 days | 851 | 44 days | 115 days | 71 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.4.2 |  |  |  |  | Transmit Data Sets to PPs | 0% | Thu 06/03/25 | Fri 07/03/25 | 2 days | Mon 23/09/24 | Fri 04/10/24 | 850 | 852 | 118 days | 110 days | -8 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.4.3 |  |  |  |  | PP's Iterative load and data integrity check | 0% | Mon 10/03/25 | Fri 04/04/25 | 20 days | Mon 21/10/24 | Fri 25/10/24 | 851 | 853 | 100 days | 115 days | 15 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.4.4 | T3 | T3-TE-0082 | SITAG | MHHS-ART140 MHHS-ART169 | Regression - PP's confirmation that test data is ready for SIT Functional | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 25/10/24 | Fri 25/10/24 | 852 | 1115 | 115 days | 115 days | 0 days | SI Test Data |  | 5.14 | Yes |  | 02/09/24: Date at risk due to programme scenario re-planning.
6 | 1.4.1.4.2.9 |  |  |  |  | SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Fri 01/03/24 | 45 days | Mon 01/01/24 | Thu 29/02/24 |  |  | 0 days | 1 day | 1 day | N/A |  | 5 | Yes
7 | 1.4.1.4.2.9.1 |  |  |  |  | PP SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Thu 29/02/24 | 44 days | Mon 01/01/24 | Thu 29/02/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.9.1.1 |  |  |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | Mon 01/01/24 | Mon 29/01/24 | 21 days | Mon 01/01/24 | Mon 29/01/24 |  | 860SS,858,857SS+10 days | 0 days | 1 day | 1 day | PP |  | 5 | Yes
8 | 1.4.1.4.2.9.1.2 |  |  |  |  | Placing Reliance Stage 2 Review | 100% | Mon 15/01/24 | Thu 29/02/24 | 34 days | Mon 15/01/24 | Thu 29/02/24 | 856SS+10 days | 863 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.2.9.1.3 |  |  |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | Tue 30/01/24 | Fri 09/02/24 | 9 days | Mon 29/01/24 | Fri 09/02/24 | 856 | 860FF+5 days | 1 day | 0 days | -1 day | PP |  | 5 | Yes
7 | 1.4.1.4.2.9.2 |  |  |  |  | SI SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Fri 23/02/24 | 40 days | Mon 01/01/24 | Fri 23/02/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.9.2.1 |  |  |  |  | Assure Test Participants' Test Readiness Reports | 100% | Mon 01/01/24 | Fri 16/02/24 | 35 days | Mon 01/01/24 | Fri 16/02/24 | 856SS,858FF+5 days | 861FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.9.2.2 |  |  |  |  | Develop Overarching SIT Functional Test Readiness Report | 100% | Mon 22/01/24 | Fri 16/02/24 | 20 days | Mon 22/01/24 | Fri 16/02/24 | 860FF | 862 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.9.2.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Mon 19/02/24 | Fri 23/02/24 | 5 days | Mon 19/02/24 | Fri 23/02/24 | 861 | 863FF+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.9.3 | T2 | T2-TE-0550 | SITAG |  | SIT Functional Testing Preparation Complete | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 862FF+5 days,793,315,857,801,808,838 | 1088FS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 28/11 - At risk because of challenges with CCP and PP readiness & dependent on successful Secondary Routing Testing. Approved at 1/3 eSITAG
5 | 1.4.1.4.3 |  |  |  |  | SIT Migration Testing Preparation | 97% | Mon 31/10/22 | Fri 27/09/24 | 500 days? | Mon 31/10/22 | Fri 07/06/24 |  |  | 0 days | 80 days | 80 days? | N/A |  | 5.21 | Yes
6 | 1.4.1.4.3.1 |  |  |  |  | Test Approach & Plan | 100% | Thu 07/09/23 | Wed 20/12/23 | 75 days | Thu 07/09/23 | Wed 20/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.1.1 |  |  |  |  | Develop document with SITWG | 100% | Thu 07/09/23 | Fri 20/10/23 | 32 days | Thu 07/09/23 | Wed 11/10/23 | 2006 | 867 | 0 days | 7 days | 7 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.2 |  |  |  |  | Draft document review with Code Bodies | 100% | Mon 23/10/23 | Wed 01/11/23 | 8 days | Thu 12/10/23 | Wed 25/10/23 | 866 | 868 | 7 days | 5 days | -2 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.3 |  |  |  |  | Industry Consultation | 100% | Thu 02/11/23 | Wed 15/11/23 | 10 days | Thu 02/11/23 | Wed 15/11/23 | 867 | 869,872SS | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.3.1.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Thu 16/11/23 | Wed 20/12/23 | 25 days | Thu 09/11/23 | Wed 20/12/23 | 868 | 870 | 5 days | 0 days | -5 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.5 | T3 | T3-TE-0018 | SITAG | MHHS-ART073 | SIT Migration Testing Test Approach & Plan approved | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 869 | 9201158877883880 | 1 day | 0 days | -1 day | SI Test |  | 5.14 | Yes |  | 24/10 - Amber because consultation window delayed by 5 days. 20/12 - Approved to complete at TMAG on 20/12
6 | 1.4.1.4.3.2 |  |  |  |  | Test Data Approach & Plan | 100% | Thu 02/11/23 | Wed 20/12/23 | 35 days | Thu 02/11/23 | Wed 20/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.2.1 |  |  |  |  | Industry Consultation | 100% | Thu 02/11/23 | Wed 15/11/23 | 10 days | Thu 02/11/23 | Wed 15/11/23 | 868SS | 873 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.3.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Thu 16/11/23 | Wed 20/12/23 | 25 days | Thu 09/11/23 | Wed 20/12/23 | 872 | 874 | 5 days | 0 days | -5 days | SI Test Data |  | 5 | Yes
7 | 1.4.1.4.3.2.3 |  |  |  |  | SIT Migration Test Data Test Approach & Plan approved | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 873 | 1158 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes |  | 20/12 - approved at TMAG on 20/12
6 | 1.4.1.4.3.3 |  |  |  |  | Test scenarios & Test Cases | 86% | Thu 21/12/23 | Fri 27/09/24 | 202 days? | Thu 21/12/23 | Wed 20/03/24 |  |  | 0 days | 137 days | 137 days? | N/A |  | 5.16 | Yes
7 | 1.4.1.4.3.3.1 |  |  |  |  | Theme 1 | 100% | Thu 21/12/23 | Wed 20/03/24 | 65 days | Thu 21/12/23 | Wed 20/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 24/01/24 | 25 days | Thu 21/12/23 | Wed 24/01/24 | 870 | 878 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.2 |  |  |  |  | Industry Review Workshop | 100% | Thu 25/01/24 | Thu 25/01/24 | 1 day | Thu 25/01/24 | Thu 25/01/24 | 877 | 879FS+6 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.3 |  |  |  |  | Industry Consultation Review | 100% | Mon 05/02/24 | Mon 12/02/24 | 6 days | Mon 05/02/24 | Mon 12/02/24 | 878FS+6 days | 880FS+12 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.4 |  |  |  |  | Review with SIT Working Group | 100% | Thu 29/02/24 | Wed 06/03/24 | 5 days | Thu 29/02/24 | Wed 06/03/24 | 879FS+12 days | 881FS+10 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.19 | Yes
8 | 1.4.1.4.3.3.1.5 |  | T3-TE-0110 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 1 | 100% | Wed 20/03/24 | Wed 20/03/24 | 0 days | Wed 20/03/24 | Wed 20/03/24 | 880FS+10 days | 9201158 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes |  | 23/1 - New milestones added because of new themed delivery approach. To go to Feb SITAG for approval
7 | 1.4.1.4.3.3.2 |  |  |  |  | Theme 2 | 100% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 17/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 14/02/24 | 40 days | Thu 21/12/23 | Wed 14/02/24 | 870 | 884 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.2 |  |  |  |  | Industry Review Workshop | 100% | Thu 15/02/24 | Thu 15/02/24 | 1 day | Thu 15/02/24 | Thu 15/02/24 | 883 | 885FS+6 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.3 |  |  |  |  | Industry Consultation Review | 100% | Mon 26/02/24 | Mon 04/03/24 | 6 days | Mon 26/02/24 | Mon 04/03/24 | 884FS+6 days | 886FS+17 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.19 | Yes
8 | 1.4.1.4.3.3.2.4 |  |  |  |  | Review with SIT Working Group | 100% | Thu 28/03/24 | Wed 03/04/24 | 5 days | Thu 28/03/24 | Wed 03/04/24 | 885FS+17 days | 887FS+10 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.5 |  | T3-TE-0111 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 2 | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 886FS+10 days | 9201158 | 0 days | 0 days | 0 days | SI Test |  | 5.22 | Yes |  | 23/1 - New milestones added because of new themed delivery approach
7 | 1.4.1.4.3.3.3 |  |  |  |  | Theme 3 | 100% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 17/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 06/03/24 | 55 days | Thu 21/12/23 | Wed 06/03/24 | 870 | 890 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
8 | 1.4.1.4.3.3.3.2 |  |  |  |  | Industry Review Workshop | 100% | Thu 07/03/24 | Thu 07/03/24 | 1 day | Thu 07/03/24 | Thu 07/03/24 | 889 | 891FS+3 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.3 |  |  |  |  | Industry Consultation Review | 100% | Wed 13/03/24 | Wed 20/03/24 | 6 days | Wed 13/03/24 | Wed 20/03/24 | 890FS+3 days | 892FS+5 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.4 |  |  |  |  | Review with SIT Working Group | 100% | Thu 28/03/24 | Wed 03/04/24 | 5 days | Thu 28/03/24 | Wed 03/04/24 | 891FS+5 days | 893FS+10 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.5 |  | T3-TE-0112 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 3 | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 892FS+10 days | 920,1158,1558FS+12 days | 0 days | 0 days | 0 days | SI Test |  | 5.22 | Yes |  | 23/1 - New milestones added because of new themed delivery approach
7 | 1.4.1.4.3.3.4 |  |  |  |  | SIT Migration Programme RTTM | 0% | Mon 09/09/24 | Fri 27/09/24 | 15 days? | NA | NA |  |  | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.1.4.3.3.4.1 |  |  |  |  | Develop Manual SIT Migration RTTM | 0% | Mon 09/09/24 | Fri 20/09/24 | 10 days? | NA | NA |  | 896 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.1.4.3.3.4.2 |  |  |  |  | Manual SIT Migration RTTM Complete | 0% | Fri 20/09/24 | Fri 20/09/24 | 0 days | NA | NA | 895 |  | 0 days | 0 days | 0 days |  |  |  | Yes
8 | 1.4.1.4.3.3.4.3 |  |  |  |  | Develop Automated SIT Migration RTTM | 0% | Mon 09/09/24 | Fri 27/09/24 | 15 days? | NA | NA |  | 898 | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.1.4.3.3.4.4 |  |  |  |  | Automated SIT Migration RTTM Complete | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days? | NA | NA | 897 |  | 0 days | 0 days | 0 days? |  |  |  | Yes
6 | 1.4.1.4.3.4 |  |  |  |  | Environments (SIT B) | 100% | Mon 31/10/22 | Fri 28/06/24 | 435 days | Mon 31/10/22 | Fri 07/06/24 |  |  | 0 days | 15 days | 15 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.4.1 |  |  |  |  | PP Environments (SIT B) | 100% | Fri 03/05/24 | Fri 28/06/24 | 41 days | Fri 03/05/24 | Fri 07/06/24 |  |  | 0 days | 15 days | 15 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.4.1.1 |  |  |  |  | PP Environments available | 100% | Fri 03/05/24 | Fri 03/05/24 | 0 days | Fri 03/05/24 | Fri 03/05/24 | 468 | 902FS+6 days,903FS+26 days,908FS+24 days | 0 days | 0 days | 0 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.2 |  |  |  |  | PP Onboarding / Smoke test | 100% | Mon 13/05/24 | Fri 28/06/24 | 35 days | Mon 13/05/24 | Fri 07/06/24 | 901FS+6 days |  | 0 days | 15 days | 15 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.3 |  |  |  |  | DTN Connectivity Proving Complete | 100% | Mon 10/06/24 | Fri 14/06/24 | 5 days | Fri 31/05/24 | Fri 31/05/24 | 901FS+26 days | 904 | 5 days | 10 days | 5 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.4 |  |  |  |  | PP Code Deployment | 100% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Mon 03/06/24 | Mon 03/06/24 | 903 | 910 | 9 days | 9 days | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.3.4.2 |  |  |  |  | SI Environments (SIT B) | 100% | Mon 31/10/22 | Fri 14/06/24 | 425 days | Mon 31/10/22 | Fri 07/06/24 |  |  | 0 days | 5 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.4.2.1 |  |  |  |  | Coordinate SIT Participants' SIT B environment preparation | 100% | Mon 31/10/22 | Fri 07/06/24 | 420 days | Mon 31/10/22 | Fri 07/06/24 |  | 907 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.2 |  |  |  |  | Assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | Fri 07/06/24 | Fri 07/06/24 | 0 days | Fri 07/06/24 | Fri 07/06/24 | 906 |  | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.3 | T3 | T3-TE-0033 | SITAG |  | SIT Participants' SIT B environments ready to start connectivity proving (incl. certificates and security compliance) | 100% | Wed 05/06/24 | Wed 05/06/24 | 0 days | Fri 03/05/24 | Fri 03/05/24 | 901FS+24 days | 909 | 24 days | 24 days | 0 days | SI Test |  | 5.26 | Yes |  | 3/6: SI coordinated smoke test will run from 5th - 7th June
8 | 1.4.1.4.3.4.2.4 |  |  |  |  | Coordinate SIT Participants' SIT B environment connectivity proving | 100% | Thu 06/06/24 | Fri 07/06/24 | 2 days | Tue 14/05/24 | Fri 07/06/24 | 908 |  | 17 days | 0 days | -17 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.5 |  |  |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Tue 04/06/24 | Fri 07/06/24 | 904 |  | 9 days | 5 days | -4 days | SI Test |  | 5.21 | Yes
6 | 1.4.1.4.3.5 |  |  |  |  | SIT Migration Test Readiness Report | 100% | Tue 02/04/24 | Fri 31/05/24 | 44 days | Tue 02/04/24 | Fri 31/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.5.1 |  |  |  |  | PP SIT Migration Test Readiness Report | 100% | Tue 02/04/24 | Fri 31/05/24 | 44 days | Tue 02/04/24 | Fri 31/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.5.1.1 |  |  |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | Tue 02/04/24 | Mon 29/04/24 | 20 days | Tue 02/04/24 | Tue 30/04/24 |  | 917SS,915,914SS+9 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.3.5.1.2 |  |  |  |  | Placing Reliance Stage 2 Review | 100% | Mon 15/04/24 | Fri 31/05/24 | 35 days | Mon 15/04/24 | Fri 31/05/24 | 913SS+9 days | 920 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.3.5.1.3 |  |  |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | Tue 30/04/24 | Mon 13/05/24 | 10 days | Tue 30/04/24 | Mon 13/05/24 | 913 | 917FF+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.3.5.2 |  |  |  |  | SI SIT Migration Test Readiness Report | 100% | Tue 02/04/24 | Mon 27/05/24 | 40 days | Tue 02/04/24 | Mon 27/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.5.2.1 |  |  |  |  | Assure Test Participants' Test Readiness Reports | 100% | Tue 02/04/24 | Mon 20/05/24 | 35 days | Tue 02/04/24 | Mon 20/05/24 | 913SS,915FF+5 days | 918FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.3.5.2.2 |  |  |  |  | Develop Overarching SIT Migration Test Readiness Report | 100% | Tue 23/04/24 | Mon 20/05/24 | 20 days | Tue 23/04/24 | Mon 20/05/24 | 917FF | 919 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.3.5.2.3 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Tue 21/05/24 | Mon 27/05/24 | 5 days | Tue 21/05/24 | Mon 27/05/24 | 918 | 920FF+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.3.6 | T2 | T2-TE-0650 | SITAG |  | SIT Migration Testing Preparation Complete | 100% | Mon 03/06/24 | Mon 03/06/24 | 0 days | Mon 03/06/24 | Mon 03/06/24 | 919FF+5 days,870,332,914,881,887,893 | 1158FS+10 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 28/5: Amber because subject to SITAG agreement on work-off items. 4/6 eSITAG approved milestone completion subject to work-off items
5 | 1.4.1.4.4 |  |  |  |  | SIT Non-Functional Preparation | 50% | Thu 30/11/23 | Fri 25/04/25 | 367 days? | Thu 30/11/23 | Tue 27/08/24 |  |  | 0 days | 174 days | 174 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.4.1 |  |  |  |  | Test Approach & Plan | 100% | Thu 30/11/23 | Wed 15/05/24 | 120 days | Thu 30/11/23 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.1.1 |  |  |  |  | Develop document with SITWG | 100% | Thu 30/11/23 | Fri 01/03/24 | 67 days | Thu 30/11/23 | Fri 01/03/24 |  | 924946940934 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.1.2 |  |  |  |  | Draft document review with Code Bodies | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 | 923 | 9251338 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.1.3 |  |  |  |  | Industry Consultation | 100% | Mon 18/03/24 | Fri 29/03/24 | 10 days | Mon 18/03/24 | Fri 29/03/24 | 924 | 929SS+2 days,926FS+8 days | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.4.1.4 |  |  |  |  | Industry Assurance Review | 100% | Thu 11/04/24 | Wed 17/04/24 | 5 days | Thu 11/04/24 | Wed 17/04/24 | 925FS+8 days | 927FS+20 days | 0 days | 0 days | 0 days |  |  | 5.16 | Yes
7 | 1.4.1.4.4.1.5 | T3 | T3-TE-0026 | SITAG | MHHS-ART073 | SIT Non-Functional Testing Test Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 926FS+20 days | 931FF,1171,1342,1460 | 0 days | 0 days | 0 days | SI Test |  | 5.3 | Yes |  | Deferred from May SITAG approval, pending further confirmation and agreement of DIP-Helix Phase 1 testing. Start of SIT Non-Functional Testing at risk. Phase
6 | 1.4.1.4.4.2 |  |  |  |  | Test Data Approach & Plan | 100% | Wed 20/03/24 | Wed 15/05/24 | 41 days | Wed 20/03/24 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.2.1 |  |  |  |  | Industry Consultation | 100% | Wed 20/03/24 | Mon 08/04/24 | 14 days | Wed 20/03/24 | Mon 08/04/24 | 925SS+2 days | 930 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.4.2.2 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Tue 09/04/24 | Wed 15/05/24 | 27 days | Tue 09/04/24 | Wed 15/05/24 | 929 | 931 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.2.3 |  | T3-TE-0113 | SITAG |  | SIT Non-Functional Testing Test Data Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 927FF,930 | 1171 | 0 days | 0 days | 0 days | SI Test |  | 5.24 | Yes |  | 13/2 - To go to Feb SITAG as a new milestone. 21/2/24 - Approved at SITAG on 21/2/24 as a new milestone. 3/4 At risk because of tight delivery schedule (added as amber to align with Lee's status)
6 | 1.4.1.4.4.3 |  |  |  |  | Test scenarios & Test Cases | 93% | Mon 04/03/24 | Wed 17/07/24 | 98 days? | Mon 04/03/24 | Wed 21/08/24 |  |  | 0 days | -25 days | -25 days? | N/A |  | 5.21 | Yes |  | 12/09/24 - Forecast date changed to reflect the SI Plan
7 | 1.4.1.4.4.3.1 |  |  |  |  | Theme 1 | 100% | Mon 04/03/24 | Wed 19/06/24 | 78 days | Mon 04/03/24 | Wed 19/06/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 17/04/24 | 33 days | Mon 04/03/24 | Wed 17/04/24 | 923 | 935 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.2 |  |  |  |  | Industry Review Workshop | 100% | Thu 18/04/24 | Thu 18/04/24 | 1 day | Thu 18/04/24 | Thu 18/04/24 | 934 | 936FS+9 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.3 |  |  |  |  | Industry Consultation Review | 100% | Thu 02/05/24 | Fri 10/05/24 | 7 days | Thu 02/05/24 | Fri 10/05/24 | 935FS+9 days | 937FS+14 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.4 |  |  |  |  | Review with NFT Working Group | 100% | Fri 31/05/24 | Thu 06/06/24 | 5 days | Fri 31/05/24 | Thu 06/06/24 | 936FS+14 days | 938FS+9 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.5 |  | T3-TE-0114 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 1 | 100% | Wed 19/06/24 | Wed 19/06/24 | 0 days | Wed 19/06/24 | Wed 19/06/24 | 937FS+9 days | 9811171 | 0 days | 0 days | 0 days | SI Test |  | 5.3 | Yes |  | Deferred from June SITAG approval, pending further confirmation and agreement of DIP-Helix Phase 1 testing. Start of SIT Non-Functional Testing at risk. Phase 1 approach to be concluded and re-issued for SITAG approval. Forecast SITAG TBC
7 | 1.4.1.4.4.3.2 |  |  |  |  | Theme 2 | 100% | Mon 04/03/24 | Wed 17/07/24 | 98 days | Mon 04/03/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 15/05/24 | 53 days | Mon 04/03/24 | Wed 15/05/24 | 923 | 941 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.2 |  |  |  |  | Industry Review Workshop | 100% | Thu 16/05/24 | Thu 16/05/24 | 1 day | Thu 16/05/24 | Thu 16/05/24 | 940 | 942FS+1 day | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.3 |  |  |  |  | Industry Consultation Review | 100% | Mon 20/05/24 | Tue 28/05/24 | 7 days | Mon 20/05/24 | Tue 28/05/24 | 941FS+1 day | 943FS+22 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.4 |  |  |  |  | Review with NFT Working Group | 100% | Fri 28/06/24 | Thu 04/07/24 | 5 days | Fri 28/06/24 | Thu 04/07/24 | 942FS+22 days | 944FS+9 days | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.5 |  | T3-TE-0115 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 2 | 100% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 943FS+9 days | 981,1171,1369FF,1374FF,1564FS+2 days | 0 days | 0 days | 0 days | SI Test |  | 5.22 | Yes |  | Date missed because of the deferment of the SIT Non-Functional Test Approach and Plan. This increases the risk to the start of SIT Non-Functional Testing
7 | 1.4.1.4.4.3.3 |  |  |  |  | Theme 3 | 100% | Mon 04/03/24 | Wed 17/07/24 | 98 days? | Mon 04/03/24 | Wed 21/08/24 |  |  | 0 days | -25 days | -25 days? | N/A |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan
8 | 1.4.1.4.4.3.3.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Mon 04/03/24 | Wed 29/05/24 | 63 days | Mon 04/03/24 | Wed 29/05/24 | 923 | 947 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.4.3.3.2 |  |  |  |  | Industry Review Workshop | 100% | Thu 30/05/24 | Thu 30/05/24 | 1 day | Thu 30/05/24 | Thu 30/05/24 | 946 | 948FS+6 days | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.3 |  |  |  |  | Industry Consultation Review | 100% | Mon 10/06/24 | Mon 17/06/24 | 6 days | Mon 10/06/24 | Mon 17/06/24 | 947FS+6 days | 949FS+8 days | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.4 |  |  |  |  | Review with NFT Working Group | 100% | Fri 28/06/24 | Thu 04/07/24 | 5 days | Fri 28/06/24 | Thu 08/08/24 | 948FS+8 days | 950FS+9 days | 0 days | -25 days | -25 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Duration shortened to 5 days to be in line with the SI Plan.
8 | 1.4.1.4.4.3.3.5 |  | T3-TE-0116 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 3 | 100% | Wed 18/09/24 | Wed 18/09/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 | 949FS+9 days | 981,1171,1564FS+2 days,952 | 19 days | 19 days | 0 days | SI Test |  | 5.3 | Yes |  | Date missed because of uncertainty around test scenarios based PPs engagement. Test cases may not be ready in time for the start of SIT Non-Functional testing. Approval forecast at Sep SITAG in prep for testing commencing 7/10....
7 | 1.4.1.4.4.3.4 |  |  |  |  | SIT NFT Programme RTTM | 0% | Wed 18/09/24 | Tue 08/10/24 | 15 days | NA | NA |  |  | 0 days | 0 days | 15 days |  |  |  | Yes
8 | 1.4.1.4.4.3.4.1 |  |  |  |  | Develop Manual SIT NFT RTTM | 0% | Wed 18/09/24 | Tue 01/10/24 | 10 days | NA | NA | 950 | 953 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.1.4.4.3.4.2 |  |  |  |  | Manual SIT NFT RTTM Complete | 0% | Tue 01/10/24 | Tue 01/10/24 | 0 days | NA | NA | 952 | 954 | 0 days | 0 days | 0 days |  |  |  | Yes
8 | 1.4.1.4.4.3.4.3 |  |  |  |  | Develop Automated SIT NFT RTTM | 0% | Wed 02/10/24 | Tue 08/10/24 | 5 days | NA | NA | 953 | 955 | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.4.3.4.4 |  |  |  |  | Automated SIT NFT RTTM Complete | 0% | Tue 08/10/24 | Tue 08/10/24 | 0 days | NA | NA | 954 |  | 0 days | 0 days | 0 days |  |  |  | Yes
6 | 1.4.1.4.4.4 |  |  |  |  | Environments (SIT B) | 0% | Tue 27/08/24 | Fri 03/01/25 | 94 days? | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 94 days | 94 days? | N/A |  | 5 | Yes
7 | 1.4.1.4.4.4.1 |  |  |  |  | PP Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.4.1.1 |  |  |  |  | Deployment of MHHS solution code to SIT B environments | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  | 960SS | 0 days | 0 days | 0 days | PP |  | 5.21 | Yes |  | 25/3: SB - Date aligns to IR8 code delivery for SIT B
7 | 1.4.1.4.4.4.2 |  |  |  |  | SI Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.4.2.1 |  |  |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 958SS |  | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes |  | 25/3: SB - Date aligns to IR8 code delivery for SIT B
7 | 1.4.1.4.4.4.3 |  |  |  |  | Helix and Avanade Environments Upscale | 0% | Mon 23/12/24 | Fri 03/01/25 | 10 days? | NA | NA |  |  | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.1.4.4.4.3.1 |  |  |  |  | Environment Uplift Window | 0% | Mon 23/12/24 | Fri 03/01/25 | 10 days? | NA | NA | 1114 | 965967968 | 0 days | 0 days | 10 days? |  |  |  | Yes
6 | 1.4.1.4.4.5 |  |  |  |  | Test Data - Non-Functional and Operational (SIT B) | 0% | Mon 06/01/25 | Fri 14/03/25 | 50 days? | NA | NA |  |  | 0 days | 0 days | 50 days? |  |  |  | Yes
7 | 1.4.1.4.4.5.1 |  |  |  |  | Data Load | 0% | Mon 06/01/25 | Fri 14/03/25 | 50 days? | NA | NA |  |  | 0 days | 0 days | 50 days? |  |  |  | Yes
8 | 1.4.1.4.4.5.1.1 |  |  |  |  | Non-Functional Theme 1 (Helix & DIP Volume Testing) Data Load | 0% | Mon 06/01/25 | Fri 10/01/25 | 5 days? | NA | NA | 962 | 1169 | 0 days | 0 days | 5 days? |  |  |  | Yes
8 | 1.4.1.4.4.5.1.2 |  |  |  |  | Non-Functional Theme 2 & 3 (Helix and DIP) Data Load | 0% | Mon 03/02/25 | Fri 07/02/25 | 5 days | NA | NA | 1170 | 971 | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.4.5.1.3 |  |  |  |  | Non-Functional Themes 2 & 3 (Central Parties and PPs) Data Load | 0% | Mon 06/01/25 | Fri 31/01/25 | 20 days? | NA | NA | 962 | 11711173 | 0 days | 0 days | 20 days? |  |  |  | Yes
8 | 1.4.1.4.4.5.1.4 |  |  |  |  | Operational Themes 1, 2 & 3 (Batch 2) (Central Parties and PPs) Data Load | 0% | Mon 06/01/25 | Fri 31/01/25 | 20 days? | NA | NA | 962 | 1186 | 0 days | 0 days | 20 days? |  |  |  | Yes
8 | 1.4.1.4.4.5.1.5 |  |  |  |  | Operational Themes 1, 2 & 3 (Batch 2) (Helix & DIP) Data Load | 0% | Mon 03/02/25 | Fri 07/02/25 | 5 days | NA | NA | 1170 | 9701186 | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.4.5.1.6 |  |  |  |  | Non-Functional and Operational Test Data Preparation Complete | 0% | Fri 07/02/25 | Fri 07/02/25 | 0 days | NA | NA | 969 |  | 0 days | 0 days | 0 days |  |  |  | Yes
8 | 1.4.1.4.4.5.1.7 |  |  |  |  | Non-Functional Theme 2 & 3 PP Preparation | 0% | Mon 10/02/25 | Fri 14/03/25 | 25 days? | NA | NA | 966 | 11711173 | 0 days | 0 days | 25 days? |  |  |  | Yes
6 | 1.4.1.4.4.6 |  |  |  |  | SIT Non-Functional Test Readiness Report | 22% | Tue 25/06/24 | Fri 25/04/25 | 219 days | Tue 25/06/24 | Fri 23/08/24 |  |  | 0 days | 175 days | 175 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.6.1 |  |  |  |  | PP SIT Non-Functional Test Readiness Report | 22% | Tue 25/06/24 | Fri 25/04/25 | 219 days | Tue 25/06/24 | Fri 23/08/24 |  |  | 0 days | 175 days | 175 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.6.1.1 |  |  |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | Tue 25/06/24 | Mon 22/07/24 | 20 days | Tue 25/06/24 | Mon 22/07/24 |  | 978SS,976,975SS+4 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.4.6.1.2 |  |  |  |  | Placing Reliance Stage 2 Review | 13% | Mon 01/07/24 | Fri 25/04/25 | 215 days | Mon 01/07/24 | Fri 23/08/24 | 974SS+4 days | 981 | 0 days | 175 days | 175 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.4.6.1.3 |  |  |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 70% | Tue 23/07/24 | Mon 05/08/24 | 10 days | Tue 23/07/24 | Mon 05/08/24 | 974 | 978FF+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.4.6.2 |  |  |  |  | SI SIT Non-Functional Test Readiness Report | 21% | Tue 25/06/24 | Wed 25/12/24 | 132 days | Tue 25/06/24 | Mon 19/08/24 |  |  | 0 days | 92 days | 92 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.6.2.1 |  |  |  |  | Assure Test Participants' Test Readiness Reports | 19% | Tue 25/06/24 | Fri 29/11/24 | 114 days | Tue 25/06/24 | Mon 12/08/24 | 974SS,976FF+5 days | 979 | 0 days | 79 days | 79 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.4.6.2.2 |  |  |  |  | Develop Overarching SIT Non-Functional Test Readiness Report | 35% | Fri 08/11/24 | Wed 18/12/24 | 20 days | Tue 16/07/24 | Mon 12/08/24 | 978 | 980 | 83 days | 92 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.4.6.2.3 |  |  |  |  | Artefact review (via SITAG) and updates | 0% | Thu 19/12/24 | Wed 25/12/24 | 5 days | Tue 13/08/24 | Mon 19/08/24 | 979 | 981FF+5 days | 92 days | 92 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.4.7 | T2 | T2-TE-0700 | SITAG |  | SIT Non-Functional Testing Preparation Complete | 0% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Mon 26/08/24 | Mon 26/08/24 | 980FF+5 days,793,349,975,938,944,950 | 1171FS+5 days | 174 days | 174 days | 0 days | SI Test |  | 5 | Yes |  | Date at risk due to lower than expected SIT functional test velocity. Date re-forecast in line with short term scenario planning. Introduction of 5 weeks additional sprints. ...
5 | 1.4.1.4.5 |  |  |  |  | SIT Operational Preparation | 30% | Thu 01/02/24 | Fri 31/01/25 | 262 days? | Thu 01/02/24 | Mon 03/03/25 |  |  | 0 days | -21 days | -21 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.5.1 |  |  |  |  | Test Approach & Plan | 100% | Thu 01/02/24 | Wed 15/05/24 | 75 days | Thu 01/02/24 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.1.1 |  |  |  |  | Develop document with SITWG | 100% | Thu 01/02/24 | Wed 06/03/24 | 25 days | Thu 01/02/24 | Wed 06/03/24 |  | 985FS+10 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.2 |  |  |  |  | Draft document review with Code Bodies | 100% | Thu 21/03/24 | Tue 26/03/24 | 4 days | Thu 07/03/24 | Wed 20/03/24 | 984FS+10 days | 986 | 10 days | 4 days | -6 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.3 |  |  |  |  | Industry Consultation | 100% | Wed 27/03/24 | Tue 09/04/24 | 10 days | Wed 27/03/24 | Tue 09/04/24 | 985 | 987,990SS,995,1001,1021 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.5.1.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Wed 10/04/24 | Wed 15/05/24 | 26 days | Thu 04/04/24 | Wed 15/05/24 | 986 | 988 | 4 days | 0 days | -4 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.5 | T3 | T3-TE-0029 | SITAG | MHHS-ART073 | SIT Operational Testing Test Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 987 | 1186 | 0 days | 0 days | 0 days | SI Test |  | 5.24 | Yes |  | 26/3 - At risk because of tight delivery schedule
6 | 1.4.1.4.5.2 |  |  |  |  | Test Data Approach & Plan | 100% | Wed 27/03/24 | Wed 15/05/24 | 36 days | Wed 27/03/24 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.2.1 |  |  |  |  | Industry Consultation | 100% | Wed 27/03/24 | Tue 09/04/24 | 10 days | Wed 27/03/24 | Tue 09/04/24 | 986SS | 991 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.5.2.2 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Wed 10/04/24 | Wed 15/05/24 | 26 days | Wed 10/04/24 | Wed 15/05/24 | 990 | 992 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.2.3 |  |  |  |  | SIT Operational Testing Test Data Approach & Plan approved | 100% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 991 | 1186 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.5.3 |  |  |  |  | Test scenarios & Test Cases | 27% | Wed 10/04/24 | Fri 31/01/25 | 213 days? | Wed 10/04/24 | Wed 18/09/24 |  |  | 0 days | 97 days | 97 days? | N/A |  | 5.21 | Yes
7 | 1.4.1.4.5.3.1 |  |  |  |  | Theme 1 | 100% | Wed 10/04/24 | Fri 06/09/24 | 108 days | Wed 10/04/24 | Wed 21/08/24 |  |  | 0 days | 12 days | 12 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.1.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Wed 10/04/24 | Fri 21/06/24 | 53 days | Wed 10/04/24 | Wed 01/05/24 | 986 | 996 | 0 days | 37 days | 37 days | SI Test |  | 6 | Yes |  | 12/09/24 - Duration increased from 16 days to 53 days, in line with the SI Plan
8 | 1.4.1.4.5.3.1.2 |  |  |  |  | Industry Review Workshop | 100% | Mon 24/06/24 | Mon 24/06/24 | 1 day | Thu 02/05/24 | Thu 02/05/24 | 995 | 997FS+17 days | 37 days | 37 days | 0 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.1.3 |  |  |  |  | Industry Consultation Review | 100% | Tue 02/07/24 | Tue 09/07/24 | 6 days | Tue 28/05/24 | Tue 04/06/24 | 996FS+17 days | 998FS+16 days | 25 days | 25 days | 0 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.1.4 |  |  |  |  | Review with SIT Working Group | 100% | Mon 19/08/24 | Fri 23/08/24 | 5 days | Thu 27/06/24 | Wed 03/07/24 | 997FS+16 days | 999FS+10 days | 37 days | 37 days | 0 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.1.5 |  | T3-TE-0117 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 1 | 100% | Fri 06/09/24 | Fri 06/09/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 | 998FS+10 days | 1186,1570FS+2 days,1051 | 12 days | 12 days | 0 days | SI Test |  | 6 | Yes |  | 12/09/24 - Lag reduced from 35 days to 10 days in line with the SI Plan. Confirmed with Roger R that this is complete.
7 | 1.4.1.4.5.3.2 |  |  |  |  | Theme 2 | 100% | Wed 10/04/24 | Fri 06/09/24 | 107 days | Wed 10/04/24 | Wed 17/07/24 |  |  | 0 days | 36 days | 36 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.2.1 |  |  |  |  | Develop Test Scenarios & Test Cases | 100% | Wed 10/04/24 | Fri 21/06/24 | 53 days | Wed 10/04/24 | Wed 22/05/24 | 986 | 1002 | 0 days | 22 days | 22 days | SI Test |  | 6 | Yes |  | 12/09/24 - Duration increased from 31 days to 53 days, in line with the SI Plan
8 | 1.4.1.4.5.3.2.2 |  |  |  |  | Industry Review Workshop | 100% | Mon 24/06/24 | Mon 24/06/24 | 1 day | Thu 23/05/24 | Thu 23/05/24 | 1001 | 1003FS+7 days,1479 | 22 days | 22 days | 0 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.2.3 |  |  |  |  | Industry Consultation Review | 100% | Tue 02/07/24 | Tue 09/07/24 | 6 days | Tue 04/06/24 | Tue 11/06/24 | 1002FS+7 days | 1004FS+11 days | 20 days | 20 days | 0 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.2.4 |  |  |  |  | Review with SIT Working Group | 100% | Mon 19/08/24 | Fri 23/08/24 | 5 days | Thu 27/06/24 | Wed 03/07/24 | 1003FS+11 days | 1005FS+10 days | 37 days | 37 days | 0 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.2.5 |  | T3-TE-0118 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 2 | 100% | Fri 06/09/24 | Fri 06/09/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 1004FS+10 days | 1186,1575FS+2 days,1051 | 36 days | 36 days | 0 days | SI Test |  | 6 | Yes |  | 23/1 - New milestone added because of Operational themed delivery approach. To go to April SITAG for approval. 17/4: Approved as new milestone at SITAG on 17/4/24. Roger R confirmed this is complete.
7 | 1.4.1.4.5.3.3 |  |  |  |  | Elexon / Helix Service Management Test Prep | 0% | Mon 15/07/24 | Fri 31/01/25 | 145 days? | NA | NA |  |  | 0 days | 0 days | 145 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.3.1 |  |  |  |  | Elexon Service Now Build and Implementation | 0% | Mon 15/07/24 | Fri 31/01/25 | 145 days? | NA | NA |  | 1183 | 0 days | 0 days | 145 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.3.2 |  |  |  |  | Helix Engagement and Comms | 0% | Mon 09/09/24 | Fri 31/01/25 | 105 days? | NA | NA |  | 1183 | 0 days | 0 days | 105 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.3.3 |  |  |  |  | Helix Service Management Documentation (Service Design Pack and Service User Op Model) | 0% | Mon 09/09/24 | Fri 31/01/25 | 105 days? | NA | NA |  | 1183 | 0 days | 0 days | 105 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.3.4 |  |  |  |  | Helix Knowledge Articles | 0% | Mon 09/09/24 | Fri 31/01/25 | 105 days? | NA | NA |  | 1183 | 0 days | 0 days | 105 days? |  |  |  | Yes
7 | 1.4.1.4.5.3.4 |  |  |  |  | Theme 3 (Batch 2) | 14% | Thu 19/09/24 | Wed 11/12/24 | 60 days? | Wed 10/04/24 | Wed 18/09/24 |  |  | 116 days | 60 days | -56 days? | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.4.1 |  |  |  |  | Conclude BCDR Scope with SRO, Code Bodies and DIP Manager | 0% | Thu 19/09/24 | Fri 11/10/24 | 17 days | NA | NA |  | 1013 | 0 days | 0 days | 17 days |  |  |  | Yes
8 | 1.4.1.4.5.3.4.2 |  |  |  |  | Develop BDCR Test Scenarios & Test Cases (Batch 2) | 100% | Mon 14/10/24 | Fri 25/10/24 | 10 days | NA | NA | 1012 |  | 0 days | 0 days | 10 days |  |  | 6 | Yes |  | 12/09/24 - Added new milestone for Batch 2
8 | 1.4.1.4.5.3.4.3 |  |  |  |  | Develop DIP Test Scenarios and Test Cases (Batch 2) | 0% | Thu 19/09/24 | Fri 25/10/24 | 27 days | NA | NA |  | 1015 | 0 days | 0 days | 27 days |  |  |  | Yes
8 | 1.4.1.4.5.3.4.4 |  |  |  |  | SRO Review | 0% | Mon 28/10/24 | Fri 01/11/24 | 5 days | NA | NA | 1014 | 1016 | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.5.3.4.5 |  |  |  |  | Industry Review Workshop (Batch 2) | 10% | Mon 04/11/24 | Fri 15/11/24 | 10 days | Thu 13/06/24 | Thu 13/06/24 | 1015 | 1017 | 102 days | 111 days | 9 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.3.4.6 |  |  |  |  | Review Feedback and Update | 0% | Mon 18/11/24 | Fri 22/11/24 | 5 days | NA | NA | 1016 | 1018FS+3 days | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.5.3.4.7 |  |  |  |  | Review with SIT WG (Batch 2) | 0% | Thu 28/11/24 | Thu 05/12/24 | 6 days | NA | NA | 1017FS+3 days | 1019FS+3 days | 0 days | 0 days | 6 days |  |  |  | Yes
8 | 1.4.1.4.5.3.4.8 |  |  |  |  | SITAG Approval (Batch 2) | 0% | Wed 11/12/24 | Wed 11/12/24 | 1 day? | NA | NA | 1018FS+3 days | 10301187 | 0 days | 0 days | 1 day? |  |  |  | Yes
7 | 1.4.1.4.5.3.5 |  |  |  |  | Theme 3 (Batch 1) | 58% | Wed 10/04/24 | Wed 11/12/24 | 176 days? | NA | NA |  |  | 0 days | 0 days | 176 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.5.1 |  |  |  |  | Develop Test Scenarios & Test Cases (Batch 1) | 100% | Wed 10/04/24 | Fri 26/07/24 | 78 days | Wed 10/04/24 | Wed 12/06/24 | 986 |  | 0 days | 32 days | 32 days | SI Test |  | 6 | Yes |  | 12/09/24 - Duration increased from 46 days to 78 days to reflect the SI Plan.
8 | 1.4.1.4.5.3.5.2 |  |  |  |  | Conclude Industry Consultation (Batch 1) | 0% | Thu 05/09/24 | Thu 19/09/24 | 11 days | NA | NA |  | 1023 | 0 days | 0 days | 11 days |  |  |  | Yes
8 | 1.4.1.4.5.3.5.3 |  |  |  |  | Review Feedback and Update | 0% | Fri 20/09/24 | Thu 26/09/24 | 5 days | NA | NA | 1022 | 1024FS+1 day | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.5.3.5.4 |  |  |  |  | Draft Test Cases from Feedback and Approved LLSD | 0% | Mon 30/09/24 | Fri 18/10/24 | 15 days? | NA | NA | 1023FS+1 day,1033 | 1025 | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.5.5 |  |  |  |  | SRO Review | 0% | Mon 21/10/24 | Fri 25/10/24 | 5 days? | NA | NA | 1024 | 1026 | 0 days | 0 days | 5 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.5.6 |  |  |  |  | Industry Consultation | 0% | Mon 28/10/24 | Fri 08/11/24 | 10 days? | NA | NA | 1025 | 1027 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.5.7 |  |  |  |  | Review Feedback and Update | 0% | Mon 11/11/24 | Fri 15/11/24 | 5 days | NA | NA | 1026 | 1028FS+8 days | 0 days | 0 days | 5 days |  |  |  | Yes
8 | 1.4.1.4.5.3.5.8 |  |  |  |  | Review with SITWG (Batch 1) | 0% | Thu 28/11/24 | Wed 04/12/24 | 5 days? | NA | NA | 1027FS+8 days | 1029FS+4 days | 0 days | 0 days | 5 days? |  |  |  | Yes
8 | 1.4.1.4.5.3.5.9 |  |  |  |  | SITAG for approval (Batch 1) | 0% | Wed 11/12/24 | Wed 11/12/24 | 1 day | NA | NA | 1028FS+4 days | 10301183 | 0 days | 0 days | 1 day |  |  |  | Yes
8 | 1.4.1.4.5.3.5.10 |  | T3-TE-0119 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 3 (Batch 1 + 2) | 0% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 18/09/24 | Wed 18/09/24 | 103310191029 | 1186,1580FS+2 days,1051,1035,1183 | 60 days | 60 days | 0 days | SI Test |  | 6 | Yes |  | 12/09/24 - Lag reduced from 35 days to 15 days in line with the SI Plan.
7 | 1.4.1.4.5.3.6 |  |  |  |  | Helix SDD and LLSD Development and Approval | 0% | Fri 27/09/24 | Mon 30/09/24 | 1 day | NA | NA |  |  | 0 days | 0 days | 1 day |  |  |  | Yes
8 | 1.4.1.4.5.3.6.1 |  |  |  |  | Development | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  |  | Yes
8 | 1.4.1.4.5.3.6.2 |  |  |  |  | Approval | 0% | Mon 30/09/24 | Mon 30/09/24 | 0 days | NA | NA |  | 10301024 | 0 days | 0 days | 0 days |  |  |  | Yes
6 | 1.4.1.4.5.4 |  |  |  |  | SIT Operational Programme RTTM | 0% | Thu 12/12/24 | Fri 17/01/25 | 27 days? | NA | NA |  |  | 0 days | 0 days | 27 days? |  |  |  | Yes
7 | 1.4.1.4.5.4.1 |  |  |  |  | Develop Manual SIT Operational RTTM | 0% | Thu 12/12/24 | Fri 10/01/25 | 22 days? | NA | NA | 1030 | 10371036 | 0 days | 0 days | 22 days? |  |  |  | Yes
7 | 1.4.1.4.5.4.2 |  |  |  |  | Manual SIT Operational RTTM Complete | 0% | Fri 10/01/25 | Fri 10/01/25 | 0 days | NA | NA | 1035 |  | 0 days | 0 days | 0 days |  |  |  | Yes
7 | 1.4.1.4.5.4.3 |  |  |  |  | Develop Automated SIT Operational RTTM | 0% | Mon 13/01/25 | Fri 17/01/25 | 5 days | NA | NA | 1035 | 1038 | 0 days | 0 days | 5 days |  |  |  | Yes
7 | 1.4.1.4.5.4.4 |  |  |  |  | Automated SIT Operational RTTM Complete | 0% | Fri 17/01/25 | Fri 17/01/25 | 0 days | NA | NA | 1037 |  | 0 days | 0 days | 0 days |  |  |  | Yes
6 | 1.4.1.4.5.5 |  |  |  |  | Environments (SIT B) | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 29 days | 29 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.5.1 |  |  |  |  | PP Environments (SIT B) | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 29 days | 29 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.5.5.1.1 |  |  |  |  | Deployment of MHHS solution code to SIT B environments | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 142 | 1043SS | 29 days | 29 days | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.5.5.2 |  |  |  |  | SI Environments (SIT B) | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 29 days | 29 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.5.5.2.1 |  |  |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 1041SS | 1114 | 29 days | 29 days | 0 days | SI Test |  | 5.21 | Yes
6 | 1.4.1.4.5.6 |  |  |  |  | SIT Operational Test Readiness Report | 0% | Mon 05/08/24 | Wed 18/09/24 | 33 days | Mon 05/08/24 | Mon 03/03/25 |  |  | 0 days | -118 days | -118 days | N/A |  | 6 | Yes |  | 12/09/24 - Forecast start date brought forward to 05/08/24, duration extended from 19 days to 33 days in line with the SI Plan.
7 | 1.4.1.4.5.6.1 |  |  |  |  | PP SIT Operational Test Readiness Report | 0% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Mon 05/08/24 | Mon 03/02/25 |  |  | 0 days | -131 days | -131 days | N/A |  | 6 | Yes |  | 12/09/24 - Forecast start date brought forward to 05/08/24 in line with the SI Plan.
8 | 1.4.1.4.5.6.1.1 |  |  |  |  | Test Readiness Report submitted to Programme for assurance | 0% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Tue 07/01/25 | Mon 03/02/25 |  | 1048 | -111 days | -131 days | -20 days | PP |  | 6 | Yes |  | 12/09/24 - Forecast start date brought forward to 05/08/24 in line with the SI Plan.
7 | 1.4.1.4.5.6.2 |  |  |  |  | SI SIT Operational Test Readiness Report | 0% | Mon 05/08/24 | Fri 17/01/25 | 120 days | Tue 07/01/25 | Mon 03/03/25 |  |  | -111 days | -31 days | 80 days | N/A |  | 5 | Yes
8 | 1.4.1.4.5.6.2.1 |  |  |  |  | Assure Test Participants' Test Readiness Reports | 0% | Mon 05/08/24 | Fri 10/01/25 | 115 days | Tue 07/01/25 | Mon 24/02/25 | 1046 |  | -111 days | -31 days | 80 days | SI Test |  | 6 | Yes |  | 12/09/24 - Duration increased from 5 days to 25 days in line with the SI Plan.
8 | 1.4.1.4.5.6.2.2 |  |  |  |  | Develop Overarching SIT Operational Test Readiness Report | 0% | Mon 02/12/24 | Fri 10/01/25 | 30 days | Tue 28/01/25 | Mon 24/02/25 |  | 1050 | -41 days | -31 days | 10 days | SI Test |  | 6 | Yes |  | 12/09/24 - Duration increased from 4 days to 18 days in line with the SI Plan.
8 | 1.4.1.4.5.6.2.3 |  |  |  |  | Artefact review (via SITAG) and updates | 0% | Mon 13/01/25 | Fri 17/01/25 | 5 days | Tue 25/02/25 | Mon 03/03/25 | 1049 | 1051 | -31 days | -31 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.5.7 | T2 | T2-TE-0750 | SITAG |  | SIT Operational Testing Preparation Complete | 0% | Fri 17/01/25 | Fri 17/01/25 | 0 days | Wed 25/09/24 | Wed 25/09/24 | 3.67e+17 | 1186FS+8 days | 82 days | 82 days | 0 days | SI Test |  | 6 | Yes |  | 12/09/24 - Date updated in line with the SI Plan.
5 | 1.4.1.4.6 |  |  |  |  | Regression Test Preperation | 0% | Mon 16/09/24 | Fri 04/04/25 | 145 days? | NA | NA |  |  | 0 days | 0 days | 145 days? |  |  |  | Yes
6 | 1.4.1.4.6.1 |  |  |  |  | Regression Test Approach | 0% | Mon 16/09/24 | Fri 25/10/24 | 30 days? | NA | NA |  |  | 0 days | 0 days | 30 days? |  |  |  | Yes
7 | 1.4.1.4.6.1.1 |  |  |  |  | Develop approach doc | 0% | Mon 16/09/24 | Tue 01/10/24 | 12 days | NA | NA |  | 1055 | 0 days | 0 days | 12 days |  |  |  | Yes
7 | 1.4.1.4.6.1.2 |  |  |  |  | SITWG Feedback on approach doc | 0% | Wed 02/10/24 | Tue 08/10/24 | 5 days | NA | NA | 1054 | 1056 | 0 days | 0 days | 5 days |  |  |  | Yes
7 | 1.4.1.4.6.1.3 |  |  |  |  | SRO Review of approach doc | 0% | Wed 09/10/24 | Tue 15/10/24 | 5 days | NA | NA | 1055 | 1057FS+5 days | 0 days | 0 days | 5 days |  |  |  | Yes
7 | 1.4.1.4.6.1.4 |  |  |  |  | Incorporate SRO + SITWG feedback into approach doc | 0% | Wed 23/10/24 | Wed 23/10/24 | 1 day? | NA | NA | 1056FS+5 days | 1058 | 0 days | 0 days | 1 day? |  |  |  | Yes
7 | 1.4.1.4.6.1.5 |  |  |  |  | SRO Approval | 0% | Thu 24/10/24 | Thu 24/10/24 | 1 day | NA | NA | 1057 | 1059 | 0 days | 0 days | 1 day |  |  |  | Yes
7 | 1.4.1.4.6.1.6 |  |  |  |  | SIT Regression Testing Approach and Plan Approval | 0% | Fri 25/10/24 | Fri 25/10/24 | 1 day? | NA | NA | 1058 | 1061 | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.4.1.4.6.2 |  |  |  |  | Regression Test Suite | 0% | Mon 28/10/24 | Thu 05/12/24 | 29 days? | NA | NA |  |  | 0 days | 0 days | 29 days? |  |  |  | Yes
7 | 1.4.1.4.6.2.1 |  |  |  |  | Build Regression Test Suite | 0% | Mon 28/10/24 | Tue 12/11/24 | 12 days | NA | NA | 1059 | 1062 | 0 days | 0 days | 12 days |  |  |  | Yes
7 | 1.4.1.4.6.2.2 |  |  |  |  | SITWG Feedback on regression suite doc | 0% | Wed 13/11/24 | Tue 19/11/24 | 5 days | NA | NA | 1061 | 1063 | 0 days | 0 days | 5 days |  |  |  | Yes
7 | 1.4.1.4.6.2.3 |  |  |  |  | SRO Review of regression suite doc | 0% | Wed 20/11/24 | Tue 03/12/24 | 10 days | NA | NA | 1062 | 1064 | 0 days | 0 days | 10 days |  |  |  | Yes
7 | 1.4.1.4.6.2.4 |  |  |  |  | Incorporate SRO + SITWG feedback into regression suite doc | 0% | Wed 04/12/24 | Wed 04/12/24 | 1 day? | NA | NA | 1063 | 1065 | 0 days | 0 days | 1 day? |  |  |  | Yes
7 | 1.4.1.4.6.2.5 |  |  |  |  | SRO Approval | 0% | Thu 05/12/24 | Thu 05/12/24 | 1 day | NA | NA | 1064 | 1117 | 0 days | 0 days | 1 day |  |  |  | Yes
6 | 1.4.1.4.6.3 |  |  |  |  | Regression Test Data Load Window (SIT Functional and Migration) - SIT A | 0% | Fri 14/03/25 | Mon 17/03/25 | 1 day? | NA | NA |  |  | 0 days | 0 days | 1 day? |  |  |  | Yes
7 | 1.4.1.4.6.3.1 |  |  |  |  | Regression Test Data Load Start | 0% | Fri 14/03/25 | Fri 14/03/25 | 0 days? | NA | NA | 11091152 | 1068 | 0 days | 0 days | 0 days? |  |  |  | Yes
7 | 1.4.1.4.6.3.2 |  |  |  |  | Regression Test Data Load Window | 0% | Mon 17/03/25 | Fri 04/04/25 | 15 days? | NA | NA | 1067 | 1115 | 0 days | 0 days | 15 days? |  |  |  | Yes
3 | 1.4.2 |  |  |  |  | SIT Execution | 16% | Mon 31/10/22 | Fri 19/02/27 | 1125 days? | Mon 30/10/23 | Fri 25/04/25 |  |  | -260 days | 475 days | 735 days? | N/A |  | 5 | Yes
4 | 1.4.2.1 | T1 | T1-TE-1000 | PSG | MHHS-ART071 | System Integration Testing Start (M9) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 631FS+5 days,545 | 1072,2505,2460FS-40 days | 0 days | 0 days | 0 days | CPT |  | 5.11 | Yes |  | On track, however there are a number of associated risks that are being mitigated by the Programme
4 | 1.4.2.2 |  |  |  |  | SIT Component Integration Testing | 100% | Mon 30/10/23 | Mon 11/03/24 | 96 days | Mon 30/10/23 | Fri 08/03/24 |  |  | 0 days | 1 day | 1 day | N/A |  | 5 | Yes
5 | 1.4.2.2.1 |  |  |  |  | SIT Component Integration Testing Start | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 1070 |  | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes
5 | 1.4.2.2.2 | T3 | T3-TE-0060 | SITAG | MHHS-ART071 | Component Integration Testing Interval 1 Start | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 631SS+1 day,552,556,560,115 | 1079SS | 0 days | 0 days | 0 days | SI Test |  | 5.11 | Yes |  | On track, however there are a number of associated risks that are being mitigated by the Programme
5 | 1.4.2.2.3 | T3 | T3-TE-0061 | SITAG |  | Component Integration Testing Interval 2 Start | 100% | Mon 13/11/23 | Mon 13/11/23 | 0 days | Mon 13/11/23 | Mon 13/11/23 | 658SS+5 days,552,560,556,115 |  | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
5 | 1.4.2.2.4 | T3 | T3-TE-0062 | SITAG |  | Component Integration Testing Interval 3 Start | 100% | Mon 27/11/23 | Mon 27/11/23 | 0 days | Mon 27/11/23 | Mon 27/11/23 | 690SS+5 days,552,556,560,115 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.5 | T3 | T3-TE-0063 | SITAG |  | Component Integration Testing Interval 4 Start | 100% | Mon 11/12/23 | Mon 11/12/23 | 0 days | Mon 11/12/23 | Mon 11/12/23 | 722SS+5 days,552,556,560,115 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 13/12 - Complete noting a work-off plan and revised CIT Approach being taken to Dec TMAG
5 | 1.4.2.2.6 | T3 | T3-TE-0064 |  |  | Component Integration Testing Interval 5 Start | 100% | Mon 15/01/24 | Mon 15/01/24 | 0 days | Mon 15/01/24 | Mon 15/01/24 | 754SS+5 days,552,556,560,115 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 2/1//24 - Approved at 20/12 TMAG based on CIT Gov approach change
5 | 1.4.2.2.7 | T3 | T3-TE-0065 | SITAG |  | Component Integration Testing Interval 6 Start | 100% | Mon 29/01/24 | Mon 29/01/24 | 0 days | Mon 29/01/24 | Mon 29/01/24 | 5.5256e+17 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 2/1//24 - Approved at 20/12 TMAG based on CIT Gov approach change
5 | 1.4.2.2.8 |  |  |  |  | SIT Component Integration Testing Execution | 100% | Mon 30/10/23 | Fri 23/02/24 | 85 days | Mon 30/10/23 | Fri 23/02/24 | 1073SS | 1080FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.9 | T3 | T3-TE-0032 | SITAG | MHHS-ART074 | SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 100% | Fri 23/02/24 | Fri 23/02/24 | 0 days | Fri 23/02/24 | Fri 23/02/24 | 1079FF | 1083FF,1081FF+5 days | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes |  | All PPs are expected to complete their CIT by the target date on 09-Feb
5 | 1.4.2.2.10 |  |  |  |  | Assurance of PPs Test Completion Reports | 100% | Mon 22/01/24 | Fri 01/03/24 | 30 days | Mon 22/01/24 | Fri 01/03/24 | 1080FF+5 days | 1084FF | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.11 |  |  |  |  | SIT CI Test Completion Report | 100% | Wed 07/02/24 | Fri 01/03/24 | 18 days | Wed 07/02/24 | Fri 01/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.2.2.11.1 |  |  |  |  | Develop document | 100% | Wed 07/02/24 | Fri 23/02/24 | 13 days | Wed 07/02/24 | Fri 23/02/24 | 1080FF | 1084 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
6 | 1.4.2.2.11.2 |  |  |  |  | Review & agree document | 100% | Mon 26/02/24 | Fri 01/03/24 | 5 days | Mon 26/02/24 | Fri 01/03/24 | 1083,1081FF | 1085FS+6 days | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.12 | T2 | T2-TE-0600 | SITAG | MHHS-ART074 | SIT Component Integration Testing Test Completion Report Approved | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days | Fri 08/03/24 | Fri 08/03/24 | 1084FS+6 days | 11991088 | 1 day | 1 day | 0 days | SI Test |  | 5.18 | Yes |  | 20/2 - Date changed to align with SITAG meeting. On track for approval 11/3
4 | 1.4.2.3 |  |  |  |  | SIT - Minimum Viable Cohort (MVC) | 10% | Mon 31/10/22 | Fri 19/02/27 | 1125 days? | Mon 11/03/24 | Fri 07/02/25 |  |  | -355 days | 530 days | 885 days? | N/A |  | 5 | Yes
5 | 1.4.2.3.1 |  |  |  |  | SIT Functional Testing (MVC) | 21% | Mon 31/10/22 | Fri 19/02/27 | 1125 days? | Mon 11/03/24 | Fri 17/01/25 |  |  | -355 days | 545 days | 900 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.1.1 | T3 | T3-TE-0034 | SITAG | MHHS-ART073 | SIT Functional Testing Start | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days | Mon 11/03/24 | Mon 11/03/24 | 1085,863FS+5 days,793,801,802,803,810 | 1091SS-1 day | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 28/11 - At risk because of challenges with CCP and PP readiness & dependent on successful Secondary Routing Testing
6 | 1.4.2.3.1.2 |  |  |  |  | SIT Functional Testing Execution (Minimum Viable Cohort) | 21% | Mon 31/10/22 | Fri 20/06/25 | 690 days? | Mon 11/03/24 | Fri 17/01/25 |  |  | -355 days | 110 days | 465 days? | N/A |  | 5 | Yes
7 | 1.4.2.3.1.2.1 |  |  |  |  | Cycle 1 (Full Cycle) | 100% | Mon 11/03/24 | Fri 14/06/24 | 70 days | Mon 11/03/24 | Fri 12/07/24 |  |  | 0 days | -20 days | -20 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.1.1 |  |  |  |  | Test Execution | 100% | Mon 11/03/24 | Fri 24/05/24 | 55 days | Mon 11/03/24 | Fri 28/06/24 | 1088SS-1 day,838 | 1092 | 0 days | -25 days | -25 days | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.1.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 100% | Mon 27/05/24 | Fri 14/06/24 | 15 days | Mon 01/07/24 | Fri 12/07/24 | 1091 | 1094 | -25 days | -20 days | 5 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.2 |  |  |  |  | Cycle 2 (Defect retests and targeted regression testing) | 41% | Mon 17/06/24 | Fri 04/10/24 | 80 days | Mon 15/07/24 | Fri 20/09/24 |  |  | -20 days | 10 days | 30 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.2.1 |  |  |  |  | Test Execution | 47% | Mon 17/06/24 | Fri 20/09/24 | 70 days | Mon 15/07/24 | Fri 06/09/24 | 1092843 | 1095,1171FS+5 days | -20 days | 10 days | 30 days | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.2.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 09/09/24 | Fri 20/09/24 | 1094 | 1097 | 10 days | 10 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.3 |  |  |  |  | SIT Functional Testing back-up progress risk-assessment | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 23/09/24 | Fri 18/10/24 |  |  | -495 days | -515 days | -20 days | N/A |  | 5.31 | Yes
8 | 1.4.2.3.1.2.3.1 |  |  |  |  | Back-up risk-assessment of SIT Functional progress to assess whether Qualification Execution can start early | 0% | Mon 07/10/24 | Fri 25/10/24 | 15 days | Mon 23/09/24 | Fri 11/10/24 | 1095 | 1098FS+5 days | 10 days | 10 days | 0 days | SI Test |  | 5.31 | No
8 | 1.4.2.3.1.2.3.2 | T3 | T3-TE-0041 | QAG |  | Back-up SITAG decision on early Qualification Testing Execution start | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1097FS+5 days |  | 10 days | 10 days | 0 days | SI Test | Approved | 5.31 | No |  | 15/8/24: Milestone to be removed as no longer applicable
7 | 1.4.2.3.1.2.4 |  |  |  |  | Cycle 3 (Defect retests and targeted regression testing) | 0% | Mon 21/10/24 | Fri 19/02/27 | 610 days? | Mon 23/09/24 | Fri 01/11/24 |  |  | 20 days | 600 days | 580 days? | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.4.1 |  |  |  |  | Sprint 5 | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days? | NA | NA | 141 | 1101 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.2 |  |  |  |  | Sprint 6 | 0% | Mon 04/11/24 | Fri 15/11/24 | 10 days? | NA | NA | 1100 | 1102 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.3 |  |  |  |  | Sprint 7 | 0% | Mon 18/11/24 | Fri 29/11/24 | 10 days? | NA | NA | 1101 | 1103 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.4 |  |  |  |  | Sprint 8 | 0% | Mon 02/12/24 | Fri 20/12/24 | 15 days? | NA | NA | 1102 | 1104 | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.5 |  |  |  |  | Christmas downtime | 0% | Mon 23/12/24 | Fri 03/01/25 | 10 days? | NA | NA | 1103 | 1105 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.6 |  |  |  |  | Sprint 9 | 0% | Mon 06/01/25 | Fri 17/01/25 | 10 days? | NA | NA | 1104 | 1106 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.7 |  |  |  |  | Sprint 10 | 0% | Mon 20/01/25 | Fri 31/01/25 | 10 days? | NA | NA | 1105 | 1107 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.8 |  |  |  |  | Sprint 11 | 0% | Mon 03/02/25 | Fri 14/02/25 | 10 days? | NA | NA | 1106 | 1108 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.9 |  |  |  |  | Sprint 12 | 0% | Mon 17/02/25 | Fri 28/02/25 | 10 days? | NA | NA | 1107 | 1109 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.10 |  |  |  |  | Sprint 13 (RTTM gap analysis scope) | 0% | Mon 03/03/25 | Fri 14/03/25 | 10 days? | NA | NA | 1108 | 1067 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.4.11 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days | Mon 21/10/24 | Fri 01/11/24 |  | 1111FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.5 | T3 | T3-TE-0045 | SITAG |  | Core Systems Code Freeze | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1110FF | 1314FS+1 day | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of Functional could be delayed. Programme-wide scenario re-planning underway
7 | 1.4.2.3.1.2.6 |  |  |  |  | SIT Functional Settlement Testing | 0% | Mon 17/06/24 | Fri 02/05/25 | 230 days? | NA | NA |  |  | 0 days | 0 days | 230 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.6.1 |  |  |  |  | Settlement Testing Cycle 1 | 0% | Mon 17/06/24 | Fri 20/09/24 | 70 days | NA | NA |  |  | 0 days | 0 days | 70 days |  |  |  | Yes
8 | 1.4.2.3.1.2.6.2 |  |  |  |  | Settlement Testing Cycle 2 | 0% | Mon 07/10/24 | Fri 20/12/24 | 55 days? | NA | NA | 1043 | 962 | 0 days | 0 days | 55 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.6.3 |  |  |  |  | Settlement Testing Cycle 3 (CoS Settlement Testing) | 0% | Mon 07/04/25 | Fri 02/05/25 | 20 days? | NA | NA | 8531068 | 1.1171e+23 | 0 days | 0 days | 20 days? |  |  |  | Yes
7 | 1.4.2.3.1.2.7 |  |  |  |  | SIT Functional MVC Regression Testing (code freeze) | 0% | Mon 05/05/25 | Fri 27/06/25 | 40 days? | Mon 04/11/24 | Fri 03/01/25 |  |  | 130 days | 125 days | -5 days? | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.7.1 |  |  |  |  | Regression Sprint 1 | 0% | Mon 05/05/25 | Fri 16/05/25 | 10 days? | NA | NA | 11151065 | 1118 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.1.2.7.2 |  |  |  |  | Regression Sprint 2 | 0% | Mon 19/05/25 | Fri 30/05/25 | 10 days | NA | NA | 1117 | 1119 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.1.2.7.3 |  |  |  |  | Regression Sprint 3 | 0% | Mon 02/06/25 | Fri 20/06/25 | 15 days | NA | NA | 1118 | 1120 | 0 days | 0 days | 15 days |  |  |  | Yes
8 | 1.4.2.3.1.2.7.4 | T3 | T3-TE-0046 | SITAG | MHHS-ART072 | SIT Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 20/06/25 | Fri 20/06/25 | 0 days | Fri 03/01/25 | Fri 03/01/25 | 1119 | 1123FF,1121FF+5 days | 120 days | 120 days | 0 days | SI Test |  | 6 | Yes |  | 16/09/24 - Date pushed back to 14/03/25, in line with recalibration exercise.
8 | 1.4.2.3.1.2.7.5 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 19/05/25 | Fri 27/06/25 | 30 days | Mon 02/12/24 | Fri 10/01/25 | 1120FF+5 days | 1124FF | 120 days | 120 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.8 |  |  |  |  | SIT Functional Test Completion Report (Minimum Viable Cohort) | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Mon 16/12/24 | Fri 10/01/25 |  |  | 120 days | 125 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.8.1 |  |  |  |  | Develop document | 0% | Mon 02/06/25 | Fri 20/06/25 | 15 days | Mon 16/12/24 | Fri 03/01/25 | 1120FF | 1124,1197FF | 120 days | 120 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.2.3.1.2.8.2 |  |  |  |  | Review & agree document | 0% | Mon 23/06/25 | Fri 27/06/25 | 5 days | Mon 06/01/25 | Fri 10/01/25 | 1123,1121FF | 1125FF+5 days | 120 days | 120 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.2.3.1.2.8.3 | T2 | T2-TE-0850 | SITAG | MHHS-ART072 | SIT Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 1124FF+5 days | 1199FS+5 days,1696 | 120 days | 120 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of Functional could be delayed. Programme-wide scenario re-planning underway
5 | 1.4.2.3.2 |  |  |  |  | Helix E2E Settlement Testing | 0% | Mon 05/05/25 | Fri 01/08/25 | 65 days | NA | NA |  |  | 0 days | 0 days | 65 days |  |  |  | Yes
6 | 1.4.2.3.2.1 |  |  |  |  | Helix E2E Settlement Testing Execution | 0% | Mon 05/05/25 | Fri 01/08/25 | 65 days | NA | NA | 1115 | 1128 | 0 days | 0 days | 65 days |  |  |  | Yes
6 | 1.4.2.3.2.2 |  |  |  |  | Helix E2E Settlement Testing Execution Complete | 0% | Fri 01/08/25 | Fri 01/08/25 | 0 days | NA | NA | 1127 |  | 0 days | 0 days | 0 days |  |  |  | Yes
6 | 1.4.2.3.2.3 |  |  |  |  | MHHSP Helix E2E Testing Assurance | 0% | Mon 05/05/25 | Fri 01/08/25 | 65 days | NA | NA | 1115 | 1130 | 0 days | 0 days | 65 days |  |  |  | Yes
6 | 1.4.2.3.2.4 |  |  |  |  | MHHSP Helix E2E Testing Assurance Complete | 0% | Fri 01/08/25 | Fri 01/08/25 | 0 days | NA | NA | 1129 |  | 0 days | 0 days | 0 days |  |  |  | Yes
5 | 1.4.2.3.3 |  |  |  |  | SIT Migration Testing (MVC) | 7% | Mon 31/10/22 | Fri 04/07/25 | 700 days? | Mon 10/06/24 | Fri 10/01/25 |  |  | -420 days | 125 days | 545 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.3.1 |  |  |  |  | SIT Migration Testing Start | 0% | Mon 11/03/24 | Mon 11/03/24 | 0 days? | NA | NA |  |  | 0 days | 0 days | 0 days? |  |  |  | Yes
6 | 1.4.2.3.3.2 |  |  |  |  | SIT Migration Testing Execution (Minimum Viable Cohort) | 7% | Mon 31/10/22 | Fri 20/06/25 | 690 days? | NA | NA |  |  | 0 days | 0 days | 690 days? |  |  |  | Yes
7 | 1.4.2.3.3.2.1 |  |  |  |  | Cycle 1 (Full Cycle) | 0% | Mon 11/03/24 | Fri 14/06/24 | 70 days? | NA | NA |  |  | 0 days | 0 days | 70 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.1.1 |  |  |  |  | Test Execution | 0% | Mon 11/03/24 | Fri 24/05/24 | 55 days? | NA | NA |  |  | 0 days | 0 days | 55 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.1.2 |  |  |  |  | Defect resolution, assurance, review, data& environments maintenance | 0% | Mon 27/05/24 | Fri 14/06/24 | 15 days? | NA | NA |  | 1138 | 0 days | 0 days | 15 days? |  |  |  | Yes
7 | 1.4.2.3.3.2.2 |  |  |  |  | Cycle 2 (Defect retests and targeted regression testing) | 0% | Mon 11/03/24 | Fri 28/06/24 | 80 days? | NA | NA |  |  | 0 days | 0 days | 80 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.2.1 |  |  |  |  | Test Execution | 0% | Mon 17/06/24 | Fri 20/09/24 | 70 days? | NA | NA | 1136 | 1139 | 0 days | 0 days | 70 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.2.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days? | NA | NA | 1138 | 1141 | 0 days | 0 days | 10 days? |  |  |  | Yes
7 | 1.4.2.3.3.2.3 |  |  |  |  | SIT Functional Testing back-up progress risk-assessment | 0% | Mon 17/06/24 | Fri 20/09/24 | 70 days? | NA | NA |  |  | 0 days | 0 days | 70 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.3.1 |  |  |  |  | Back-up risk-assessment of SIT Migration progress to assess whether Qualification Execution can start early | 0% | Mon 07/10/24 | Fri 25/10/24 | 15 days? | NA | NA | 1139 | 1142FS+5 days | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.3.2 |  |  |  |  | Back-up SITAG decision on early Qualification Testing Execution start | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days? | NA | NA | 1141FS+5 days |  | 0 days | 0 days | 0 days? |  |  |  | Yes
7 | 1.4.2.3.3.2.4 |  |  |  |  | Cycle 3 (Defect retests and targeted regression testing) | 0% | Mon 07/10/24 | Fri 25/10/24 | 15 days? | NA | NA |  |  | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.4.1 |  |  |  |  | Sprint 5 | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days | NA | NA | 141 | 1145 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.2 |  |  |  |  | Sprint 6 | 0% | Mon 04/11/24 | Fri 15/11/24 | 10 days | NA | NA | 1144 | 1146 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.3 |  |  |  |  | Sprint 7 | 0% | Mon 18/11/24 | Fri 29/11/24 | 10 days | NA | NA | 1145 | 1147 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.4 |  |  |  |  | Sprint 8 | 0% | Mon 02/12/24 | Fri 20/12/24 | 15 days | NA | NA | 1146 | 1148 | 0 days | 0 days | 15 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.5 |  |  |  |  | Christmas downtime | 0% | Mon 23/12/24 | Fri 03/01/25 | 10 days | NA | NA | 1147 | 1149 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.6 |  |  |  |  | Sprint 9 | 0% | Mon 06/01/25 | Fri 17/01/25 | 10 days | NA | NA | 1148 | 1150 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.7 |  |  |  |  | Sprint 10 | 0% | Mon 20/01/25 | Fri 31/01/25 | 10 days | NA | NA | 1149 | 1151 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.8 |  |  |  |  | Sprint 11 | 0% | Mon 03/02/25 | Fri 14/02/25 | 10 days | NA | NA | 1150 | 1152 | 0 days | 0 days | 10 days |  |  |  | Yes
8 | 1.4.2.3.3.2.4.9 |  |  |  |  | Sprint 12 | 0% | Mon 17/02/25 | Fri 28/02/25 | 10 days | NA | NA | 1151 | 1067 | 0 days | 0 days | 10 days |  |  |  | Yes
7 | 1.4.2.3.3.2.5 |  |  |  |  | SIT Migration MVC Regression Testing (code freeze) | 0% | Mon 05/05/25 | Fri 20/06/25 | 35 days? | NA | NA |  |  | 0 days | 0 days | 35 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.5.1 |  |  |  |  | Regression Sprint 1 | 0% | Mon 05/05/25 | Fri 16/05/25 | 10 days? | NA | NA | 1115 | 1155 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.5.2 |  |  |  |  | Regression Sprint 2 | 0% | Mon 19/05/25 | Fri 30/05/25 | 10 days? | NA | NA | 1154 | 1156 | 0 days | 0 days | 10 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.5.3 |  |  |  |  | Regression Sprint 3 | 0% | Mon 02/06/25 | Fri 20/06/25 | 15 days? | NA | NA | 1155 |  | 0 days | 0 days | 15 days? |  |  |  | Yes
8 | 1.4.2.3.3.2.5.4 |  |  |  |  | SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 20/06/25 | Fri 20/06/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  |  | Yes
7 | 1.4.2.3.3.2.6 | T3 | T3-TE-0038 | SITAG | MHHS-ART076 | SIT Migration Test Completion Report (Minimum Viable Cohort) | 22% | Tue 18/06/24 | Fri 03/01/25 | 144 days | Mon 10/06/24 | Mon 10/06/24 | 920FS+10 days,870,874,881,887,893 |  | 6 days | 150 days | 144 days | SI Test |  | 5.27 | Yes |  | 21/5: at risk because dependant on prioritised SIT F CoA tests. Subject to approval at eSITAG on 10/6. 11/6: Missed date because MPRS data and code not ready. Decision deferred to 17/6
8 | 1.4.2.3.3.2.6.1 |  |  |  |  | Develop document | 36% | Tue 18/06/24 | Fri 18/10/24 | 89 days | Mon 10/06/24 | Fri 04/10/24 |  | 1162FF,1160 | 6 days | 10 days | 4 days | SI Test |  | 5 | Yes
8 | 1.4.2.3.3.2.6.2 |  |  |  |  | Review& agree document | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days | Mon 21/10/24 | Fri 01/11/24 | 1159 | 1161 | 0 days | 0 days | 0 days | SI Test |  | 5.27 | Yes
8 | 1.4.2.3.3.2.6.3 |  |  |  |  | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Mon 04/11/24 | Fri 03/01/25 | 45 days | Mon 04/11/24 | Fri 03/01/25 | 1160 | 1162 | 0 days | 0 days | 0 days |  |  | 5.27 | Yes
7 | 1.4.2.3.3.2.7 | T3 | T3-TE-0043 | SITAG | MHHS-ART076 | SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 14/03/25 | Fri 14/03/25 | 0 days | Fri 03/01/25 | Fri 03/01/25 | 1159FF,1161 | 1163FF+5 days | 49 days | 49 days | 0 days | SI Test |  | 6 | Yes |  | 16/09/24 - Date pushed back to 14/03/25, in line with recalibration exercise.
7 | 1.4.2.3.3.2.8 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | Fri 07/02/25 | Thu 20/03/25 | 30 days | Mon 02/12/24 | Fri 10/01/25 | 1162FF+5 days |  | 49 days | 49 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.3.2.9 |  |  |  |  | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) | 0% | Mon 02/06/25 | Fri 27/06/25 | 20 days | Mon 16/09/24 | Fri 11/10/24 |  |  | 185 days | 185 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.2.3.3.2.9.1 |  |  |  |  | Develop document | 0% | Mon 02/06/25 | Fri 20/06/25 | 15 days | Mon 16/09/24 | Fri 04/10/24 |  | 1166 | 185 days | 185 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.2.3.3.2.9.2 |  |  |  |  | Review & agree document | 0% | Mon 23/06/25 | Fri 27/06/25 | 5 days | Mon 07/10/24 | Fri 11/10/24 | 1165 | 1167FS+5 days | 185 days | 185 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.3.2.10 | T2 | T2-TE-0800 | SITAG | MHHS-ART076 | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1166FS+5 days |  | 185 days | 185 days | 0 days | SI Test | Proposed | 5.28 | Yes |  | Date change because the plan did not consider SIT Migration regression testing. SIT Migration Test Completion Report date was incorrect. Revise plan to align to Jan 25 SITAG approval. Date change to form part of Programme CR 55....
5 | 1.4.2.3.4 |  |  |  |  | SIT Non-Functional Testing (all SIT PPs) | 0% | Mon 13/01/25 | Fri 11/07/25 | 130 days? | Mon 02/09/24 | Fri 17/01/25 |  |  | 95 days | 125 days | 30 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.4.1 |  | T3-TE-0040 |  |  | Theme 1 (Helix and DIP Volume Testing) Start | 0% | Mon 13/01/25 | Mon 13/01/25 | 0 days? | NA | NA | 965 | 1170 | 0 days | 0 days | 0 days? |  |  |  | Yes
6 | 1.4.2.3.4.2 |  |  |  |  | Theme 1 (Helix and DIP Volume Testing) Execution | 0% | Mon 13/01/25 | Fri 31/01/25 | 15 days? | NA | NA | 1169 | 966969 | 0 days | 0 days | 15 days? |  |  |  | Yes
6 | 1.4.2.3.4.3 | T3 | T3-TE-0040 | SITAG | MHHS-ART079 | Theme 2 SIT Non-Functional Testing Start | 0% | Fri 02/05/25 | Fri 02/05/25 | 0 days | Mon 02/09/24 | Mon 02/09/24 | 981FS+5 days,1094FS+5 days,927,931,938,944,950,967,971 | 1172SS | 175 days | 175 days | 0 days | SI Test |  | 5 | Yes |  | Date will be missed due to low SIT functional test velocity. Start of SIT-Non Functional (MVC) will be delayed. Date re-forecast in line with scenario planning. Introduction of 5 weeks additional sprints ...
6 | 1.4.2.3.4.4 |  |  |  |  | Theme 2 SIT Non-Functional Testing Execution | 0% | Mon 05/05/25 | Fri 27/06/25 | 40 days | Mon 02/09/24 | Fri 03/01/25 | 1171SS | 1175FF | 175 days | 125 days | -50 days | SI Test |  | 5 | Yes
6 | 1.4.2.3.4.5 |  |  |  |  | Theme 3 SIT Non-Functional Testing Start | 0% | Mon 17/03/25 | Mon 17/03/25 | 1 day? | NA | NA | 967971 | 1174SS | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.4.2.3.4.6 |  |  |  |  | Theme 3 SIT Non-Functional Testing Execution | 0% | Mon 17/03/25 | Fri 09/05/25 | 40 days? | NA | NA | 1173SS | 1175FF | 0 days | 0 days | 40 days? |  |  |  | Yes
6 | 1.4.2.3.4.7 | T3 | T3-TE-0047 | SITAG | MHHS-ART079 | SIT Non-Functional Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 27/06/25 | Fri 27/06/25 | 0 days | Fri 03/01/25 | Fri 03/01/25 | 1172FF,1174FF | 1178FF,1176FF+5 days | 125 days | 125 days | 0 days | SI Test |  | 5 | Yes |  | 16/09/24 - Date pushed back to 23/05/25, in line with recalibration exercise.
6 | 1.4.2.3.4.8 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 09/06/25 | Fri 04/07/25 | 20 days | Mon 02/12/24 | Fri 10/01/25 | 1175FF+5 days | 1179FF | 135 days | 125 days | -10 days | SI Test |  | 5 | Yes
6 | 1.4.2.3.4.9 |  |  |  |  | SIT Non-Functional Testing Test Completion Report (all SIT PPs) | 0% | Mon 09/06/25 | Fri 04/07/25 | 20 days | Mon 16/12/24 | Fri 10/01/25 |  |  | 125 days | 125 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.2.3.4.9.1 |  |  |  |  | Develop document | 0% | Mon 09/06/25 | Fri 27/06/25 | 15 days | Mon 16/12/24 | Fri 03/01/25 | 1175FF | 1179 | 125 days | 125 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.4.9.2 |  |  |  |  | Review & agree document | 0% | Mon 30/06/25 | Fri 04/07/25 | 5 days | Mon 06/01/25 | Fri 10/01/25 | 1178,1176FF | 1180FF+5 days | 125 days | 125 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.2.3.4.10 | T2 | T2-TE-0900 | SITAG | MHHS-ART079 | SIT Non-Functional Testing Test Completion Report (all SIT PPs) Approved | 0% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 1179FF+5 days | 1199 | 125 days | 125 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Start of SIT-Non Functional (MVC) could be delayed. Programme-wide scenario re-planning underway
5 | 1.4.2.3.5 |  |  |  |  | SIT Operational Testing (all SIT PPs) | 0% | Mon 03/02/25 | Thu 05/06/25 | 89 days? | Mon 07/10/24 | Fri 07/02/25 |  |  | 85 days | 84 days | -1 day? | N/A |  | 5 | Yes
6 | 1.4.2.3.5.1 |  |  |  |  | Non-SIT B Testing | 0% | Mon 03/02/25 | Fri 07/03/25 | 25 days? | NA | NA |  |  | 0 days | 0 days | 25 days? |  |  |  | Yes
7 | 1.4.2.3.5.1.1 |  | T3-TE-XXXX |  |  | SIT Operational Testing Start (Theme 3 - Batch 1 (Service Management)) | 0% | Mon 03/02/25 | Mon 03/02/25 | 0 days? | NA | NA | 1.0301e+23 | 1184 | 0 days | 0 days | 0 days? |  |  | 6 | Yes |  | 17/09/23 - Added new milestone
7 | 1.4.2.3.5.1.2 |  |  |  |  | SIT Operational Testing Execution Window (Theme 3 - Batch 1 (Service Management)) | 0% | Mon 03/02/25 | Fri 07/03/25 | 25 days? | NA | NA | 1183 | 1190 | 0 days | 0 days | 25 days? |  |  |  | Yes
6 | 1.4.2.3.5.2 |  |  |  |  | SIT B Testing | 0% | Fri 07/02/25 | Fri 16/05/25 | 70 days? | NA | NA |  |  | 0 days | 0 days | 70 days? |  |  |  | Yes
7 | 1.4.2.3.5.2.1 | T3 | T3-TE-0042 | SITAG | MHHS-ART073 MHHS-ART143 | SIT Operational Testing Start (SIT B) | 0% | Fri 07/02/25 | Fri 07/02/25 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 1051FS+8 days,988,992,999,1005,1030,968,969 | 1187 | 90 days | 90 days | 0 days | SI Test |  | 5 | Yes |  | Team has a dependency on Helix documentation that has been submitted late, which has impacted the approval of Theme 3 test scripts and test design. Date expected to move to 04/11. ...
7 | 1.4.2.3.5.2.2 |  |  |  |  | SIT Operational Testing Execution Theme 3 Batch 2 | 0% | Mon 10/02/25 | Fri 14/03/25 | 25 days? | NA | NA | 11861019 | 1188 | 0 days | 0 days | 25 days? |  |  |  | Yes
7 | 1.4.2.3.5.2.3 |  |  |  |  | SIT Operational Testing Execution Theme 1 | 0% | Mon 17/03/25 | Fri 18/04/25 | 25 days? | NA | NA | 1187 | 1189 | 0 days | 0 days | 25 days? |  |  |  | Yes
7 | 1.4.2.3.5.2.4 |  |  |  |  | SIT Operational Testing Execution Theme 2 | 0% | Mon 21/04/25 | Fri 16/05/25 | 20 days? | NA | NA | 1188 | 1190 | 0 days | 0 days | 20 days? |  |  |  | Yes
6 | 1.4.2.3.5.3 | T3 | T3-TE-0050 | SITAG | MHHS-ART081 | SIT Operational Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 11891184 | 1193FF,1191FF+5 days,1509FF | 84 days | 84 days | 0 days | SI Test |  | 6 | Yes |  | 16/09/24 - Date pushed back to 23/05/25, in line with recalibration exercise.
6 | 1.4.2.3.5.4 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | Fri 18/04/25 | Thu 29/05/25 | 30 days | Mon 23/12/24 | Fri 31/01/25 | 1190FF+5 days | 1194FF | 84 days | 84 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.2.3.5.5 |  |  |  |  | SIT Operational Testing Test Completion Report (all SIT PPs) | 0% | Fri 02/05/25 | Thu 29/05/25 | 20 days | Mon 06/01/25 | Fri 31/01/25 |  |  | 84 days | 84 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.2.3.5.5.1 |  |  |  |  | Develop document | 0% | Fri 02/05/25 | Fri 23/05/25 | 15 days | Mon 06/01/25 | Fri 24/01/25 | 1190FF | 1194 | 84 days | 84 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.5.5.2 |  |  |  |  | Review & agree document | 0% | Fri 23/05/25 | Thu 29/05/25 | 5 days | Mon 27/01/25 | Fri 31/01/25 | 1193,1191FF | 1195FF+5 days | 84 days | 84 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.2.3.5.6 | T2 | T2-TE-0950 | SITAG | MHHS-ART081 | SIT Operational Testing Test Completion Report (all SIT PPs) Approved | 0% | Thu 05/06/25 | Thu 05/06/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1194FF+5 days | 1199 | 84 days | 84 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Start of SIT Operational (MVC) could be delayed. Programme-wide scenario re-planning underway
5 | 1.4.2.3.6 |  |  |  |  | SIT MVC Test Exit Report | 0% | Mon 02/06/25 | Fri 27/06/25 | 20 days | Mon 06/01/25 | Fri 31/01/25 |  |  | 105 days | 105 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.2.3.6.1 |  |  |  |  | Develop document | 0% | Mon 02/06/25 | Fri 20/06/25 | 15 days | Mon 06/01/25 | Fri 24/01/25 | 1123FF | 1198 | 105 days | 105 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.2.3.6.2 |  |  |  |  | Review & agree document | 0% | Mon 23/06/25 | Fri 27/06/25 | 5 days | Mon 27/01/25 | Fri 31/01/25 | 1197 |  | 105 days | 105 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.3.7 | T1 | T1-TE-2000 | PSG | MHHS-ART081 | SIT Minimum Viable Cohort Complete (SIT Minimum Viable Cohort Test Exit Report Approved) | 0% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1085,1125FS+5 days,1180,1195 | 1510,2110FS+10 days,2111FS+10 days,2129FS+16 days,2126FS+25 days,1317FS+20 days,1528 | 111 days | 111 days | 0 days | CPT |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Start of SIT Operational (MVC) could be delayed. Programme-wide scenario re-planning underway
4 | 1.4.2.4 |  |  |  |  | SIT (non-MVC) | 10% | Mon 05/05/25 | Thu 16/10/25 | 119 days? | Mon 11/03/24 | Fri 25/04/25 |  |  | 300 days | 124 days | -176 days? | N/A |  | 5 | Yes
5 | 1.4.2.4.1 |  |  |  |  | SIT Functional Testing (non-MVC) | 0% | Mon 05/05/25 | Fri 03/10/25 | 110 days? | Mon 11/03/24 | Fri 25/04/25 |  |  | 300 days | 115 days | -185 days? | N/A |  | 5 | Yes
6 | 1.4.2.4.1.1 |  |  |  |  | SIT Functional Testing Execution (non-MVC) | 0% | Mon 05/05/25 | Fri 12/09/25 | 95 days? | Mon 11/03/24 | Fri 04/04/25 |  |  | 300 days | 115 days | -185 days? | N/A |  | 5 | Yes
7 | 1.4.2.4.1.1.1 |  |  |  |  | Test Execution (Cycle 3 Completion and Regression Testing) | 0% | Mon 05/05/25 | Fri 12/09/25 | 95 days? | NA | NA | 1115 | 1204FF | 0 days | 0 days | 95 days? |  |  |  | Yes
7 | 1.4.2.4.1.1.2 | T3 | T3-TE-0052 | SITAG | MHHS-ART072 | SIT Functional Testing End (non-MVC) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1203FF | 1207FF,1205FS+5 days | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Functional Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
6 | 1.4.2.4.1.2 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 22/09/25 | Fri 26/09/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1204FS+5 days | 1208FF | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Functional Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
6 | 1.4.2.4.1.3 |  |  |  |  | SIT Functional Testing Test Completion Report (non-MVC) | 0% | Mon 25/08/25 | Fri 26/09/25 | 25 days | Mon 17/03/25 | Fri 18/04/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.2.4.1.3.1 |  |  |  |  | Develop document | 0% | Mon 25/08/25 | Fri 12/09/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1204FF | 1208 | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Functional Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
7 | 1.4.2.4.1.3.2 |  |  |  |  | Review & agree document | 0% | Mon 22/09/25 | Fri 26/09/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1207,1205FF | 1209FF+5 days | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Functional Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
6 | 1.4.2.4.1.4 | T3 | T3-TE-0055 | SITAG | MHHS-ART072 | SIT Functional Testing Test Completion Report (non-MVC) Approved | 0% | Fri 03/10/25 | Fri 03/10/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1208FF+5 days | 1221,1219FF | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Functional Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
5 | 1.4.2.4.2 |  |  |  |  | SIT Migration Testing (non-MVC) | 23% | Mon 05/05/25 | Fri 03/10/25 | 110 days | Mon 10/06/24 | Fri 25/04/25 |  |  | 235 days | 115 days | -120 days | N/A |  | 5 | Yes
6 | 1.4.2.4.2.1 |  |  |  |  | Test Execution (Cycle 3 Completion and Regression Testing) | 28% | Mon 05/05/25 | Fri 12/09/25 | 95 days | Mon 10/06/24 | Fri 04/04/25 | 1115 | 1212FF | 235 days | 115 days | -120 days | SI Test |  | 5 | Yes
6 | 1.4.2.4.2.2 | T3 | T3-TE-0051 | SITAG | MHHS-ART076 | SIT Migration Testing End (non-MVC) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 12/09/25 | Fri 12/09/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1211FF | 1215FF,1213FS+5 days | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Migration Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
6 | 1.4.2.4.2.3 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 22/09/25 | Fri 26/09/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1212FS+5 days | 1216FF | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.2.4.2.4 |  |  |  |  | SIT Migration Testing Test Completion Report (non-MVC) | 0% | Mon 25/08/25 | Fri 26/09/25 | 25 days | Mon 17/03/25 | Fri 18/04/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.2.4.2.4.1 |  |  |  |  | Develop document | 0% | Mon 25/08/25 | Fri 12/09/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1212FF | 1216 | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.4.2.4.2 |  |  |  |  | Review & agree document | 0% | Mon 22/09/25 | Fri 26/09/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1215,1213FF | 1217FF+5 days | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.2.4.2.5 | T3 | T3-TE-0056 | SITAG | MHHS-ART076 | SIT Migration Testing Test Completion Report (non-MVC Approved) | 0% | Fri 03/10/25 | Fri 03/10/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1216FF+5 days | 1221,1219FF | 115 days | 115 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT Migration Testing (Other Participants) could be delayed. Programme-wide scenario re-planning underway
5 | 1.4.2.4.3 |  |  |  |  | SIT non-MVC Test Exit Report | 0% | Mon 15/09/25 | Fri 10/10/25 | 20 days | Mon 17/03/25 | Fri 11/04/25 |  |  | 130 days | 130 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.2.4.3.1 |  |  |  |  | Develop document | 0% | Mon 15/09/25 | Fri 03/10/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1209FF,1217FF | 1220 | 130 days | 130 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT- Other Particiapnts Test Exit report could be delayed. Programme-wide scenario re-planning underway
6 | 1.4.2.4.3.2 |  |  |  |  | Review & agree document | 0% | Mon 06/10/25 | Fri 10/10/25 | 5 days | Mon 07/04/25 | Fri 11/04/25 | 1219 | 1221FS+4 days | 130 days | 130 days | 0 days | SI Test |  | 5 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT- Other Particiapnts Test Exit report could be delayed. Programme-wide scenario re-planning underway
5 | 1.4.2.4.4 | T3 | T3-TE-0059 | SITAG | MHHS-ART081 | SIT non-MVC Complete | 0% | Thu 16/10/25 | Thu 16/10/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1220FS+4 days,1209,1217 | 1516 | 124 days | 124 days | 0 days | SI Test |  | 5.27 | Yes |  | 6/8/24: Date at risk due to lower than expected test velocity. Completion of SIT- Other Particiapnts Test Exit report could be delayed. Programme-wide scenario re-planning underway
3 | 1.4.3 |  |  |  |  | UIT Environment Preparation | 46% | Mon 31/10/22 | Fri 04/07/25 | 700 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 20 days | 20 days | N/A |  | 5 | Yes
4 | 1.4.3.1 |  |  |  |  | Test Artefact Development | 54% | Wed 01/03/23 | Thu 18/07/24 | 361 days | Wed 01/03/23 | Thu 18/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.3.1.1 |  |  |  |  | E2E Sandbox Guidance | 100% | Wed 01/03/23 | Thu 18/07/24 | 361 days | Wed 01/03/23 | Thu 18/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.1.1.1 |  |  |  |  | Develop document | 100% | Wed 01/03/23 | Fri 23/06/23 | 83 days | Wed 01/03/23 | Fri 23/06/23 |  | 1226,1229SS+20 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.1.1.2 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | Mon 26/06/23 | Fri 28/07/23 | 25 days | Mon 26/06/23 | Fri 28/07/23 | 1225 | 1227FF+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.1.1.3 | T3 | T3-TE-0067 | QAG | MHHS-ART154 | E2E Sandbox Guidance approved | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1226FF+5 days |  | 0 days | 0 days | 0 days | SI Test |  | 5.29 | Yes |  | 26/6: Baseline date change approved at QAG on 20/6/24. 11/7/24: Date change approved at QAG on 20/6/24 from 4/08/24 to 18/7/24
5 | 1.4.3.1.2 |  |  |  |  | E2E Sandbox Test Data Approach & Plan | 0% | Wed 29/03/23 | Fri 04/08/23 | 93 days | Wed 29/03/23 | Fri 04/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.1.2.1 |  |  |  |  | Develop document | 0% | Wed 29/03/23 | Fri 30/06/23 | 68 days | Wed 29/03/23 | Fri 30/06/23 | 1225SS+20 days | 1230 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.1.2.2 |  |  |  |  | Review, update & agree document internally | 0% | Mon 03/07/23 | Fri 04/08/23 | 25 days | Mon 03/07/23 | Fri 04/08/23 | 1229 |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.3.2 |  |  |  |  | UIT Stub Specification and Delivery | 88% | Mon 04/12/23 | Fri 23/08/24 | 190 days | Mon 04/12/23 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.3.2.1 |  |  |  |  | Qualification Test Stubs | 88% | Mon 04/12/23 | Fri 23/08/24 | 190 days | Mon 04/12/23 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
6 | 1.4.3.2.1.1 |  |  |  |  | Specify | 100% | Mon 04/12/23 | Thu 01/02/24 | 44 days | Mon 04/12/23 | Thu 01/02/24 | 472FS+13 days | 1234 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.3.2.1.2 |  |  |  |  | Build & Test | 88% | Fri 02/02/24 | Fri 16/08/24 | 141 days | Fri 02/02/24 | Fri 16/08/24 | 1233 | 1235 | 0 days | 0 days | 0 days | SI DevOps |  | 5.23 | Yes |  | 30/4: Removed previous testing phases as were no longer relevant and extended task to push out to align with existing dates
6 | 1.4.3.2.1.3 |  |  |  |  | Prepare for release | 0% | Mon 19/08/24 | Fri 23/08/24 | 5 days | Mon 19/08/24 | Fri 23/08/24 | 1234 | 1236 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.3.2.1.4 | T3 | T3-TE-0035 | QAG | MHHS-ART080 | Non-SIT LDSO Test Harness Released | 0% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1235 | 1253 | 0 days | 0 days | 0 days | SI DevOps |  | 5.27 | Yes |  | Date will be missed due to Sims & Ems being blocked from completing connectivity and regression testing activities, since message functionality is disabled in the current UIT environment version (IR7.3), only becoming enabled from 2/9 (release of IR8.1 UI
4 | 1.4.3.3 |  |  |  |  | Environments (UIT) | 44% | Mon 31/10/22 | Fri 04/07/25 | 700 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 20 days | 20 days | N/A |  | 5 | Yes
5 | 1.4.3.3.1 |  |  |  |  | Central Party (Avenade) Environments (UIT) | 97% | Wed 16/11/22 | Fri 27/09/24 | 488 days | Wed 16/11/22 | Fri 04/10/24 |  |  | 0 days | -5 days | -5 days | N/A |  | 5.28 | Yes |  | 8/7/24: Updated to reflect Avende are the only PP
6 | 1.4.3.3.1.1 |  |  |  |  | Central Party (Avendae) environment preparation (incl. security certificates and security compliance) | 100% | Wed 16/11/22 | Thu 01/08/24 | 447 days | Wed 16/11/22 | Fri 23/08/24 | 468 | 1240SS,1251SS,1303SS | 0 days | -16 days | -16 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.2 |  |  |  |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | Wed 16/11/22 | Thu 01/08/24 | 447 days | Wed 16/11/22 | Fri 23/08/24 | 1239SS | 1252SS | 0 days | -16 days | -16 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.3 |  |  |  |  | Central Party (Avenade) UIT environment connectivity proving | 0% | Mon 26/08/24 | Fri 27/09/24 | 25 days | Mon 26/08/24 | Fri 27/09/24 | 1253 | 1254SS | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.4 |  |  |  |  | Deployment of MHHS solution code to UIT environments | 0% | Mon 29/07/24 | Tue 30/07/24 | 2 days | Mon 09/09/24 | Fri 20/09/24 |  | 1243,1255SS | -30 days | -38 days | -8 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.5 |  |  |  |  | Central Party (Avenade) UIT environment Regression Testing | 0% | Wed 31/07/24 | Wed 31/07/24 | 1 day | Mon 23/09/24 | Fri 04/10/24 | 1242 |  | -38 days | -47 days | -9 days | PP |  | 5.28 | Yes
5 | 1.4.3.3.2 |  |  |  |  | E2E Sandbox Participants (UIT) | 0% | Mon 31/10/22 | Fri 06/06/25 | 680 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.3.2.1 |  |  |  |  | E2E Sandbox Participants environment preparation (incl. security certificates and security compliance) | 0% | Mon 31/10/22 | Fri 09/05/25 | 660 days | Mon 31/10/22 | Fri 09/05/25 |  | 1303SS,1249SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.2 |  |  |  |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 0% | Mon 31/10/22 | Fri 09/05/25 | 660 days | Mon 31/10/22 | Fri 09/05/25 |  | 1247 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.3 |  |  |  |  | E2E Sandbox Participants UIT environment connectivity proving | 0% | Mon 12/05/25 | Fri 06/06/25 | 20 days | Mon 12/05/25 | Fri 06/06/25 | 1246 | 1248FF | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.4 |  |  |  |  | Deployment of MHHS solution code to UIT environments | 0% | Mon 26/05/25 | Fri 06/06/25 | 10 days | Mon 26/05/25 | Fri 06/06/25 | 1247FF |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.5 |  |  |  |  | Coordinate E2E Sandbox Participants' UIT environment preparation (for E2E Sandbox Testing Start) | 0% | Mon 31/10/22 | Wed 07/08/24 | 463 days | Mon 31/10/22 | Wed 07/08/24 | 1245SS |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.3.3.3 |  |  |  |  | SI Environments (UIT) | 69% | Wed 16/11/22 | Fri 04/07/25 | 688 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 12 days | 20 days | 8 days | N/A |  | 5 | Yes
6 | 1.4.3.3.3.1 |  |  |  |  | Coordinate Central Parties' UIT environment preparation | 100% | Wed 16/11/22 | Thu 01/08/24 | 447 days | Wed 16/11/22 | Fri 23/08/24 | 1239SS |  | 0 days | -16 days | -16 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.2 |  |  |  |  | Assure Central Parties' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 97% | Wed 16/11/22 | Fri 23/08/24 | 463 days | Wed 16/11/22 | Fri 23/08/24 | 1240SS |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.3 | T3 | T3-TE-0044 | QAG |  | Central Parties' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 100% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1236 | 1241 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.4 |  |  |  |  | Coordinate Central Parties' UIT environment connectivity proving | 0% | Mon 26/08/24 | Mon 30/09/24 | 26 days | Mon 12/05/25 | Thu 05/06/25 | 1241SS |  | -185 days | -178 days | 7 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.5 |  |  |  |  | Coordinate deployment of MHHS solution code to Central Parties' UIT environments | 100% | Mon 29/07/24 | Tue 30/07/24 | 2 days | Mon 26/05/25 | Fri 06/06/25 | 1242SS | 1256 | -215 days | -223 days | -8 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.6 |  |  |  |  | Coordinate Central Parties' UIT environment Regression Testing | 0% | Wed 31/07/24 | Wed 31/07/24 | 1 day | Mon 23/09/24 | Fri 04/10/24 | 1255 |  | -38 days | -47 days | -9 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.7 |  |  |  |  | Environments (Non-SIT LDSO) | 0% | Thu 01/08/24 | Mon 30/09/24 | 43 days | Tue 06/08/24 | Mon 13/01/25 |  |  | -3 days | -75 days | -72 days | N/A |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.7.1 |  |  |  |  | Coordinate Qualification Participants' environment preparation | 0% | Thu 01/08/24 | Fri 23/08/24 | 17 days | Tue 06/08/24 | Mon 28/10/24 |  |  | -3 days | -46 days | -43 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.7.2 |  |  |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Thu 01/08/24 | Fri 23/08/24 | 17 days | Tue 15/10/24 | Mon 28/10/24 |  | 1260FS+1 day | -53 days | -46 days | 7 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.7.3 | T3 | T3-QU-0017 | QAG | MHHS-ART073 | Qualification Testing Tranche 1 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 26/08/24 | Mon 26/08/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1259FS+1 day | 1262 | -50 days | -50 days | 0 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.7.4 |  |  |  |  | Coordinate Qualification Participants' connectivity proving (Non-SIT LDSO) | 0% | Tue 27/08/24 | Mon 30/09/24 | 25 days | Tue 05/11/24 | Mon 13/01/25 |  |  | -50 days | -75 days | -25 days | N/A |  | 5 | Yes
8 | 1.4.3.3.3.7.4.1 |  |  |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 27/08/24 | Mon 30/09/24 | 25 days | Tue 05/11/24 | Mon 13/01/25 | 1260 |  | -50 days | -75 days | -25 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.8 |  |  |  |  | Environments (S&A) Wave 1 | 0% | Thu 01/08/24 | Thu 26/09/24 | 41 days | Tue 06/08/24 | Mon 13/01/25 |  |  | -3 days | -77 days | -74 days | N/A |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.8.1 |  |  |  |  | Coordinate Qualification Participants' environment preparation | 0% | Mon 02/09/24 | Fri 27/09/24 | 20 days | Tue 06/08/24 | Mon 28/10/24 |  |  | 19 days | -21 days | -40 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.8.2 |  |  |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days | Tue 15/10/24 | Mon 28/10/24 |  | 1266FS+1 day | 4 days | 4 days | 0 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.8.3 | T3 | New? | QAG | MHHS-ART073 | Qualification Testing Wave 1 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Tue 05/11/24 | Fri 29/11/24 | 19 days | Mon 04/11/24 | Mon 04/11/24 | 1265FS+1 day | 1268 | 0 days | 19 days | 19 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.8.4 |  |  |  |  | Coordinate Qualification Participants' connectivity proving (S&A) | 0% | Mon 02/12/24 | Fri 03/01/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 |  |  | 19 days | -6 days | -25 days | N/A |  | 5 | Yes
8 | 1.4.3.3.3.8.4.1 |  |  |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Mon 02/12/24 | Fri 03/01/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 | 1266 |  | 19 days | -6 days | -25 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.9 |  |  |  |  | Environments (S&A) Wave 2 | 0% | Tue 27/08/24 | Fri 07/03/25 | 139 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 15 days | 39 days | 24 days | N/A |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.9.1 |  |  |  |  | Coordinate Qualification Participants' environment preparation | 0% | Mon 18/11/24 | Fri 13/12/24 | 20 days | Tue 06/08/24 | Mon 28/10/24 |  |  | 74 days | 34 days | -40 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.9.2 |  |  |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Mon 16/12/24 | Fri 10/01/25 | 20 days | Tue 15/10/24 | Mon 28/10/24 |  | 1272 | 44 days | 54 days | 10 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.9.3 | T3 | New? | QAG | MHHS-ART073 | Qualification Testing Wave 2 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 13/01/25 | Fri 31/01/25 | 15 days | Mon 04/11/24 | Mon 04/11/24 | 1271 | 1274 | 49 days | 64 days | 15 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.9.4 |  |  |  |  | Coordinate Qualification Participants' connectivity proving (S&A) | 0% | Tue 27/08/24 | Mon 30/09/24 | 25 days | Tue 05/11/24 | Mon 13/01/25 |  |  | -50 days | -75 days | -25 days | N/A |  | 5 | Yes
8 | 1.4.3.3.3.9.4.1 |  |  |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Mon 03/02/25 | Fri 07/03/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 | 1272 |  | 64 days | 39 days | -25 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.10 |  |  |  |  | Environments (S&A) Wave 3 | 0% | Mon 17/03/25 | Fri 04/07/25 | 80 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 159 days | 124 days | -35 days | N/A |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.10.1 |  |  |  |  | Coordinate Qualification Participants' environment preparation | 0% | Mon 17/03/25 | Fri 25/04/25 | 30 days | Tue 06/08/24 | Mon 28/10/24 |  |  | 159 days | 129 days | -30 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.10.2 |  |  |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Mon 28/04/25 | Fri 09/05/25 | 10 days | Tue 15/10/24 | Mon 28/10/24 |  | 1278FS+1 day | 139 days | 139 days | 0 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.10.3 | T3 | New? | QAG | MHHS-ART073 | Qualification Testing Wave 3 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Tue 13/05/25 | Fri 30/05/25 | 14 days | Mon 04/11/24 | Mon 04/11/24 | 1277FS+1 day | 1280 | 135 days | 149 days | 14 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.10.4 |  |  |  |  | Coordinate Qualification Participants' connectivity proving (S&A) | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 |  |  | 149 days | 124 days | -25 days | N/A |  | 5 | Yes
8 | 1.4.3.3.3.10.4.1 |  |  |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 | 1278 |  | 149 days | 124 days | -25 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.11 |  |  |  |  | Environments (S&A) Wave 4 | 0% | Mon 17/03/25 | Fri 04/07/25 | 80 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 159 days | 124 days | -35 days | N/A |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.11.1 |  |  |  |  | Coordinate Qualification Participants' environment preparation | 0% | Mon 17/03/25 | Fri 25/04/25 | 30 days | Tue 06/08/24 | Mon 28/10/24 |  |  | 159 days | 129 days | -30 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.11.2 |  |  |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Mon 28/04/25 | Fri 09/05/25 | 10 days | Tue 15/10/24 | Mon 28/10/24 |  | 1284FS+1 day | 139 days | 139 days | 0 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.11.3 | T3 | New? | QAG | MHHS-ART073 | Qualification Testing Wave 4 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Tue 13/05/25 | Fri 30/05/25 | 14 days | Mon 04/11/24 | Mon 04/11/24 | 1283FS+1 day | 1286 | 135 days | 149 days | 14 days | SI Test |  | 5.28 | Yes |  | 8/7/24: Updated to reflect the separation between non-sit and s and a and the 4 waves for s and a
7 | 1.4.3.3.3.11.4 |  |  |  |  | Coordinate Qualification Participants' connectivity proving (S&A) | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 |  |  | 149 days | 124 days | -25 days | N/A |  | 5 | Yes
8 | 1.4.3.3.3.11.4.1 |  |  |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Tue 05/11/24 | Mon 13/01/25 | 1284 |  | 149 days | 124 days | -25 days | SI Test |  | 5 | Yes
4 | 1.4.3.4 |  |  |  |  | Test Data | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.3.4.1 |  |  |  |  | Central Parties (for E2E Sandbox & Qualification) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.4.1.1 |  |  |  |  | Central Parties' UIT environment test data loading & verification (& data cleansing, if required) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  | 1295SS,1290SS,1293FF | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 1/5: changed from Simon berry to richard puddephatt. Link was 1143(5579) doesn’t work now as the date has changed
6 | 1.4.3.4.1.2 |  |  |  |  | Submit self-declaration to Programme to confirm loading & verification of test data | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1289SS | 1296SS,1306FF-10 days,1307FF | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 1/5: changed from Simon berry to richard puddephatt
5 | 1.4.3.4.2 |  |  |  |  | E2E Sandbox Participants | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.4.2.1 |  | T3-QU-0124 | QAG |  | E2E Sandbox Test Data Approach and Plan Approved | 0% | Thu 19/09/24 | Thu 19/09/24 | 0 days | Thu 19/09/24 | Thu 19/09/24 |  |  | 0 days | 0 days | 0 days | Sandbox (Qualification Governance) |  | 5.28 | Yes |  | Delays experienced during E2E Sandbox Test Data Approach and Plan development impacting when they'll be available for internal programme review and industry consultation. Industry consultation now targeted for 16-Sep-24 to 30-Sep-24. Approach and plan wil
6 | 1.4.3.4.2.2 |  |  |  |  | UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1289FF | 1297SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 1/5: changed from Simon berry to richard puddephatt
5 | 1.4.3.4.3 |  |  |  |  | SI Test Data | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.4.3.1 |  |  |  |  | Coordinate Central Parties' UIT environment test data loading and verification (and data cleansing, if required) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1289SS |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.4.3.2 |  |  |  |  | Assure evidence of Central Parties' UIT environment test data load and verification | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1290SS |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.4.3.3 |  |  |  |  | Coordinate E2E Sandbox Participants' UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1293SS |  | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.3.5 |  |  |  |  | Other Preparation | 59% | Mon 31/10/22 | Mon 23/09/24 | 496 days | Wed 16/11/22 | Mon 23/09/24 |  |  | -12 days | 0 days | 12 days | N/A |  | 5 | Yes
5 | 1.4.3.5.1 |  |  |  |  | SI Other Preparation | 0% | Mon 31/10/22 | Mon 30/01/23 | 66 days | Thu 02/05/24 | Thu 01/08/24 |  |  | -393 days | -393 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.5.1.1 |  |  |  |  | Onboarding of UIT E2E Sandbox Participants to Test Management Tool for E2E Sandbox Testing Start (onboarding of participants will be ongoing hereafter) | 0% | Mon 31/10/22 | Mon 30/01/23 | 66 days | Thu 02/05/24 | Thu 01/08/24 |  | 1302SS | -393 days | -393 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.3.5.2 |  |  |  |  | Other Preparation (for Central Parties & E2E Sandbox Participants) | 67% | Wed 16/11/22 | Mon 23/09/24 | 484 days | Wed 16/11/22 | Mon 23/09/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.5.2.1 |  |  |  |  | Test Management Tool onboarding for E2E Sandbox Testing Start (onboarding will be ongoing hereafter) | 0% | Thu 02/05/24 | Thu 01/08/24 | 66 days | Thu 02/05/24 | Thu 01/08/24 | 1300SS |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.5.2.2 |  |  |  |  | Other Preparation (incl. test execution planning) | 76% | Wed 16/11/22 | Mon 23/09/24 | 484 days | Wed 16/11/22 | Mon 23/09/24 | 1239SS,1245SS |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.4.3.6 |  |  |  |  | UIT E2E Sandbox Test Readiness Report | 0% | Mon 26/08/24 | Fri 31/01/25 | 114 days | Mon 26/08/24 | Fri 31/01/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.3.6.1 |  |  |  |  | Central Parties E2E Sandbox Test Readiness Report | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.6.1.1 |  |  |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 0% | Mon 26/08/24 | Fri 20/09/24 | 20 days | Mon 26/08/24 | Fri 20/09/24 | 1290FF-10 days | 1309SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.6.1.2 |  |  |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 23/09/24 | Fri 04/10/24 | 1290FF | 1309FF+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.4.3.6.2 |  |  |  |  | SI E2E Sandbox Test Readiness Report | 0% | Mon 26/08/24 | Fri 18/10/24 | 40 days | Mon 26/08/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.6.2.1 |  |  |  |  | Assure Central Parties' E2E Sandbox Test Readiness Reports | 0% | Mon 26/08/24 | Fri 11/10/24 | 35 days | Mon 26/08/24 | Fri 11/10/24 | 1306SS,1307FF+5 days | 1310FF | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.6.2.2 |  |  |  |  | Develop Overarching E2E Sandbox Test Readiness Report | 0% | Mon 16/09/24 | Fri 11/10/24 | 20 days | Mon 16/09/24 | Fri 11/10/24 | 1309FF | 1311 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.6.2.3 |  |  |  |  | Artefact review (via SITAG) and updates | 0% | Mon 14/10/24 | Fri 18/10/24 | 5 days | Mon 14/10/24 | Fri 18/10/24 | 1310 | 1312FS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.3.6.3 | T3 | T3-TE-0048 | QAG | MHHS-ART154 MHHS-ART147 | UIT E2E Sandbox Preparation Complete | 0% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1311FS+5 days | 1314FS+5 days | 0 days | 0 days | 0 days | SI Test |  | 5.28 | Yes |  | 11/7/24: Date change approved at QAG on 20/6/24 from 25/10/24 to 31/1/25
3 | 1.4.4 |  |  |  |  | SIT PPs E2E Sandbox Testing Execution | 0% | Fri 07/02/25 | Fri 24/04/26 | 316 days | Mon 04/11/24 | Mon 19/01/26 |  |  | 69 days | 69 days | 0 days | N/A |  | 5 | Yes
4 | 1.4.4.1 | T3 | T3-TE-0049 | QAG | MHHS-ART018 MHHS-ART154 MHHS-ART147 | SIT PPs E2E Sandbox Testing Start | 0% | Mon 10/02/25 | Mon 10/02/25 | 0 days | Mon 10/02/25 | Mon 10/02/25 | 1111FS+1 day,1312FS+5 days | 1315SS-1 day | 0 days | 0 days | 0 days | SI Test |  | 5.28 | Yes |  | 11/7/24: Date change approved at QAG on 20/6/24 from 4/11/24 to 10/2/25
4 | 1.4.4.2 |  |  |  |  | SIT PPs E2E Sandbox Testing Execution | 0% | Fri 07/02/25 | Fri 24/04/26 | 316 days | Mon 04/11/24 | Mon 19/01/26 | 1314SS-1 day |  | 69 days | 69 days | 0 days | PP |  | 5 | Yes
3 | 1.4.5 |  |  |  |  | System Integration Testing - Tier 1 Milestones | 0% | Wed 13/08/25 | Wed 12/11/25 | 65 days | NA | NA |  |  | 0 days | 0 days | 65 days |  |  |  | Yes
4 | 1.4.5.1 | T1 | T1-MI-1000 | PSG |  | Central systems ready for migrating MPANs (M10) | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1199FS+20 days,2365,2125FS+2 days,2122,2134,2124,2104,2108 | 2176,2178FS+20 days,2180FS+20 days,1932SS,2173FF-23 days,1318FS+65 days,2519FS-3 mons,2197,2112,2114FS-8 days,2508FS-5 days | 113 days | 113 days | 0 days | CPT |  | 5 | Yes |  | 16/09/24 - Date updated to 13/08/25 in line with recalibration exercise.
4 | 1.4.5.2 | T1 | T2-MI-1500 | PSG |  | Central systems ready for migrating MPANs (M10*) - Late Exit | 0% | Wed 12/11/25 | Wed 12/11/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 1317FS+65 days |  | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
3 | 1.4.6 |  |  |  |  | External Programme Dependency Management | 100% | Mon 31/10/22 | Fri 30/06/23 | 174 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.4.6.1 |  |  |  |  | BSC CP1558 | 100% | Mon 31/10/22 | Thu 29/06/23 | 173 days | Mon 31/10/22 | Thu 29/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.6.1.1 |  |  |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Wed 28/06/23 | 173 days | Mon 31/10/22 | Wed 28/06/23 |  | 1322 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.6.1.2 |  |  |  |  | BSC CP1558 Implementation Date | 100% | Thu 29/06/23 | Thu 29/06/23 | 0 days | Thu 29/06/23 | Thu 29/06/23 | 1321 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.4.6.2 |  |  |  |  | REC CP R0032 | 100% | Mon 31/10/22 | Fri 30/06/23 | 174 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.6.2.1 |  |  |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Thu 29/06/23 | 174 days | Mon 31/10/22 | Thu 29/06/23 |  | 1325 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.6.2.2 |  |  |  |  | REC CP R0032 Implementation Date | 100% | Fri 30/06/23 | Fri 30/06/23 | 0 days | Fri 30/06/23 | Fri 30/06/23 | 1324 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.4.6.3 |  |  |  |  | REC CP R0044 | 100% | Mon 31/10/22 | Thu 29/06/23 | 173 days | Mon 31/10/22 | Thu 29/06/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.6.3.1 |  |  |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Wed 28/06/23 | 173 days | Mon 31/10/22 | Wed 28/06/23 |  | 1328 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.6.3.2 |  |  |  |  | REC CP R0044 Implementation Date | 100% | Thu 29/06/23 | Thu 29/06/23 | 0 days | Thu 29/06/23 | Thu 29/06/23 | 1327 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
2 | 1.5 |  |  |  |  | NON SIT LDSO QUALIFICATION | 74% | Tue 07/11/23 | Thu 31/07/25 | 453 days? | Tue 07/11/23 | Fri 28/02/25 |  |  | 0 days | 110 days | 110 days? | N/A |  |  | Yes
3 | 1.5.1 |  |  |  |  | Approach Planning | 100% | Tue 07/11/23 | Thu 22/08/24 | 208 days | Tue 07/11/23 | Thu 22/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.1.1 |  |  |  |  | Develop Draft Testing Approach & Plan | 100% | Tue 07/11/23 | Tue 30/01/24 | 61 days | Tue 07/11/23 | Tue 30/01/24 |  | 1332,1345SS+60 days,1349SS+75 days,1353SS+96 days,1386,1390FS+3 days,1376,1396 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.2 |  |  |  |  | Draft Testing Approach & Plan Issued to LDSO for Review | 100% | Wed 31/01/24 | Wed 31/01/24 | 1 day | Wed 31/01/24 | Wed 31/01/24 | 1331 | 1333 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.3 |  |  |  |  | LDSO Review Complete | 100% | Thu 01/02/24 | Wed 14/02/24 | 10 days | Thu 01/02/24 | Wed 14/02/24 | 1332 | 1334 | 0 days | 0 days | 0 days | LDSOs |  | 5.24 | Yes
4 | 1.5.1.4 |  |  |  |  | Update Following LDSO Review | 100% | Thu 15/02/24 | Tue 05/03/24 | 14 days | Thu 15/02/24 | Tue 05/03/24 | 1333 | 1335FS+4 days | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.5 |  |  |  |  | QWG Review of Approach & Plan | 100% | Tue 12/03/24 | Tue 12/03/24 | 1 day | Tue 12/03/24 | Tue 12/03/24 | 1334FS+4 days | 1336FS+7 days | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.1.6 |  |  |  |  | QAG Approval for Approach & Plan | 100% | Thu 21/03/24 | Thu 21/03/24 | 0 days | Thu 21/03/24 | Thu 21/03/24 | 1335FS+7 days | 1337,1367,1369,1373FS+51 days,1371 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.1.7 | T3 | T3-QU-0011 | QAG (Non-SIT LDSO) |  | Confirmation of Participants for Non-SIT LDSO Qualification Testing | 100% | Thu 21/03/24 | Thu 21/03/24 | 0 days | Thu 21/03/24 | Thu 21/03/24 | 1336 | 1342 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | Have confirmed LDSOs going through SIT. We should receive notifications on non-SIT through January. Milestone holds to baseline. 13/5: date on cr47 was 18/4 but completed before CR approved
4 | 1.5.1.8 |  |  |  |  | Update to Annex 1 for internal review (NF, Not Operational) | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | Mon 18/03/24 | Fri 05/04/24 | 924 | 1339 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | Includes time to update Approach & Plan with updates
4 | 1.5.1.9 |  |  |  |  | Non-Functional, Operational & Migration Approaches Socialised with Code Bodies & LDSO & Feedback Actioned | 100% | Mon 08/04/24 | Mon 05/08/24 | 86 days | Mon 08/04/24 | Mon 05/08/24 | 1338 | 1340FS+5 days | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.1.10 |  |  |  |  | QWG Review Operational, Non-Functional & Migration Annexes of Approach & Plan | 100% | Tue 13/08/24 | Tue 13/08/24 | 1 day | Tue 13/08/24 | Tue 13/08/24 | 1339FS+5 days | 1341,1401FF-10 days | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.27 | Yes
4 | 1.5.1.11 |  |  |  |  | Update Following QWG Review | 100% | Wed 14/08/24 | Wed 21/08/24 | 6 days | Wed 14/08/24 | Wed 21/08/24 | 1340 | 1342FS+1 day | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.27 | Yes
4 | 1.5.1.12 |  | T3-QU-0110 | QAG (Non-SIT LDSO) |  | QAG Approval for Operational, Non-Functional & Migration Annexes of Approach & Plan | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1341FS+1 day,1337,927 | 1399FF,1365 | 0 days | 0 days | 0 days | Code Bodies |  | 5.29 | Yes |  | Date missed because the Non-Functional Test Materials are not available for the July QAG and therefore to maintain our approach of approving plans in parallel with materials, the date has moved to the August QAG. There is no impact on the deliverability
3 | 1.5.2 |  |  |  |  | Functional Test Cases & Scenarios | 100% | Tue 30/01/24 | Thu 18/04/24 | 58 days | Tue 30/01/24 | Thu 18/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.2.1 |  |  |  |  | Functional Test Cases & Scenarios Batch 1 | 100% | Tue 30/01/24 | Thu 08/02/24 | 8 days | Tue 30/01/24 | Thu 08/02/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.1.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 1 with Code Bodies | 100% | Tue 30/01/24 | Tue 30/01/24 | 1 day | Tue 30/01/24 | Tue 30/01/24 | 1331SS+60 days | 1346 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.1.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 1 with LDSO | 100% | Thu 01/02/24 | Thu 01/02/24 | 1 day | Thu 01/02/24 | Thu 01/02/24 | 1345 | 1347 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.1.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 1 | 100% | Fri 02/02/24 | Thu 08/02/24 | 5 days | Fri 02/02/24 | Thu 08/02/24 | 1346 | 1356 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.2 |  |  |  |  | Functional Test Cases & Scenarios Batch 2 | 100% | Tue 20/02/24 | Fri 08/03/24 | 14 days | Tue 20/02/24 | Fri 08/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.2.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 2 with Code Bodies | 100% | Tue 20/02/24 | Tue 20/02/24 | 1 day | Tue 20/02/24 | Tue 20/02/24 | 1331SS+75 days | 1350FS+7 days | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.2.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 2 with LDSO | 100% | Fri 01/03/24 | Fri 01/03/24 | 1 day | Fri 01/03/24 | Fri 01/03/24 | 1349FS+7 days | 1351 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.2.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 2 | 100% | Mon 04/03/24 | Fri 08/03/24 | 5 days | Mon 04/03/24 | Fri 08/03/24 | 1350 | 1356 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.3 |  |  |  |  | Functional Test Cases & Scenarios Batch 3 | 100% | Wed 20/03/24 | Fri 05/04/24 | 13 days | Wed 20/03/24 | Fri 05/04/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.3.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 3 with Code Bodies | 100% | Wed 20/03/24 | Wed 20/03/24 | 1 day | Wed 20/03/24 | Wed 20/03/24 | 1331SS+96 days | 1354FS+5 days | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.3.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 3 with LDSO | 100% | Thu 28/03/24 | Thu 28/03/24 | 1 day | Thu 28/03/24 | Thu 28/03/24 | 1353FS+5 days | 1355 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.3.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 3 | 100% | Fri 29/03/24 | Fri 05/04/24 | 6 days | Fri 29/03/24 | Fri 05/04/24 | 1354 | 1356FS+1 day | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.4 |  |  |  |  | Test Cases & Scenarios Batch 1-3 Discussion at QWG | 100% | Tue 09/04/24 | Tue 09/04/24 | 1 day | Tue 09/04/24 | Tue 09/04/24 | 1347,1351,1355FS+1 day | 1357 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.2.5 |  |  |  |  | Action QWG Feedback on Test Cases & Scenarios Batch 1-3 | 100% | Wed 10/04/24 | Thu 11/04/24 | 2 days | Wed 10/04/24 | Thu 11/04/24 | 1356 | 1358FS+5 days | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.6 |  | T3-QU-0069 | QAG (Non-SIT LDSO) |  | Batch 1-3 Non-SIT LDSO QT Functional Test Scenarios and Test Cases approved | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1357FS+5 days | 13601405 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes |  | 13/5: New milestone approved as part of cr47.
3 | 1.5.3 |  |  |  |  | Test Execution Schedule | 99% | Fri 19/04/24 | Thu 22/08/24 | 90 days | Fri 19/04/24 | Thu 22/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.3.1 |  |  |  |  | Draft Test Delivery Schedule for Functional and Operational Testing | 100% | Fri 19/04/24 | Thu 16/05/24 | 20 days | Fri 19/04/24 | Thu 16/05/24 | 1358 | 1361 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.3.2 |  |  |  |  | Socialise Test Delivery Schedule with Code Bodies & LDSO for Review & Action Feedback | 100% | Fri 17/05/24 | Mon 08/07/24 | 37 days | Fri 17/05/24 | Mon 08/07/24 | 1360 | 1362 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.3.3 |  |  |  |  | Agree Test Execution Timetable Format at QWG, Including Anonymisation Requirements | 100% | Tue 09/07/24 | Tue 09/07/24 | 1 day | Tue 09/07/24 | Tue 09/07/24 | 1361 | 1363 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.3.4 |  |  |  |  | Action QWG Feedback | 100% | Wed 10/07/24 | Fri 12/07/24 | 3 days | Wed 10/07/24 | Fri 12/07/24 | 1362 | 1364FS+4 days | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.3.5 |  | T3-QU-0111 | QAG (Non-SIT LDSO) |  | Agree Test Execution Timetable Format at QAG, Including Anonymisation Requirements | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1363FS+4 days |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.29 | Yes
4 | 1.5.3.6 | T3 | T3-QU-0008 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Execution Schedule Complete | 0% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1342 |  | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes |  | Date not met because of re-planning activity around SIT Cycle 2 Maintenance window. Maintain dialog with Programme scenario planning from SIT. New forecast date will be defined after programme scenario CR is approved. ...
3 | 1.5.4 |  |  |  |  | Functional, Non-Functional, Operational & Migration Test Scenarios & Cases | 100% | Fri 22/03/24 | Thu 22/08/24 | 110 days | Fri 22/03/24 | Thu 22/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.4.1 |  |  |  |  | Test Scenarios & Cases - Functional - Drafted, Reviewed | 100% | Mon 01/04/24 | Thu 18/04/24 | 14 days | Mon 01/04/24 | Thu 18/04/24 | 1336 | 1368 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.2 |  | T3-QU-0070 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases- Functional - Approved at QAG | 100% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1367 | 14201388 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 13/5: New milestone approved as part of cr47.
4 | 1.5.4.3 |  |  |  |  | Test Scenarios & Cases - Non-Functional - Drafted, Reviewed | 100% | Fri 22/03/24 | Thu 22/08/24 | 110 days | Fri 22/03/24 | Thu 22/08/24 | 1336,944FF | 1370 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.4 |  | T3-QU-0071 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Non-Functional - Approved at QAG | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1369 | 1420 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes |  | Date missed because Non-Functional Test Materials are not available for the July QAG. There is no impact the QT window and it will be approved at the August QAG. To go to July QAG for baseline date change
4 | 1.5.4.5 |  |  |  |  | Test Scenarios & Cases - Migration - Drafted, Reviewed | 100% | Fri 22/03/24 | Thu 23/05/24 | 45 days | Fri 22/03/24 | Thu 23/05/24 | 1336 | 1372 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.6 |  | T3-QU-0072 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Migration - Approved at QAG | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1371 | 14201388 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.7 |  |  |  |  | Test Scenarios & Cases - Operational - Drafted, Reviewed | 100% | Mon 03/06/24 | Thu 22/08/24 | 59 days | Mon 03/06/24 | Thu 22/08/24 | 1336FS+51 days | 1374 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.8 |  | T3-QU-0073 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Operational - Approved at QAG | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1373,944FF | 1388 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes |  | Date missed because Operational Test Materials are not available for the July QAG. There is no impact the QT window and it will be approved at the August QAG. To go to July QAG for baseline date change
3 | 1.5.5 |  |  |  |  | Test Data | 61% | Mon 22/01/24 | Mon 23/12/24 | 241 days | Mon 22/01/24 | Mon 23/12/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.5.1 |  |  |  |  | Test Data Plan Drafted & Reviewed | 100% | Mon 22/01/24 | Thu 23/05/24 | 89 days | Mon 22/01/24 | Thu 23/05/24 | 1331 | 1377 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.5.2 |  | T3-QU-0074 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO QT Test Data Plan Approved by QAG | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 16/05/24 | Thu 16/05/24 | 1376 | 13791378 | 6 days | 5 days | 0 days | Code Bodies |  | 5.24 | Yes |  | 13/5: New milestone approved as part of cr47. 13/5: Date change to line up with QAG
4 | 1.5.5.3 |  |  |  |  | Develop Test Data Matrices | 100% | Fri 24/05/24 | Thu 06/06/24 | 10 days | Fri 24/05/24 | Thu 06/06/24 | 1377 | 1380 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.4 |  |  |  |  | Test Data Cut | 100% | Fri 24/05/24 | Mon 17/06/24 | 17 days | Fri 24/05/24 | Mon 17/06/24 | 1377 | 1380 | 0 days | 0 days | 0 days | PP, Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.5 |  | T3-QU-0112 | QAG (Non-SIT LDSO) |  | Test Data Cut Complete | 100% | Mon 17/06/24 | Mon 17/06/24 | 0 days | Mon 17/06/24 | Mon 17/06/24 | 13791378 | 1381 | 0 days | 0 days | 0 days | PP, Non-SIT LDSO |  | 5.27 | Yes |  | 28/5 LDSO will complete test data cut between 3rd and 17th June
4 | 1.5.5.6 |  |  |  |  | Test Data Reviewed by the Programme | 95% | Tue 18/06/24 | Fri 09/08/24 | 39 days | Tue 18/06/24 | Fri 09/08/24 | 1380 | 1382 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.7 |  |  |  |  | Test Data Loaded | 0% | Mon 12/08/24 | Tue 03/09/24 | 17 days | Mon 12/08/24 | Tue 03/09/24 | 1381 | 1383 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.8 |  | T3-QU-0113 | QAG (Non-SIT LDSO) |  | Test Data Signed Off | 0% | Tue 03/09/24 | Tue 03/09/24 | 0 days | Tue 03/09/24 | Tue 03/09/24 | 1382 | 1384 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.25 | Yes |  | Date will be missed due to QT execution replanning. Additionally, the Test Harness will be loaded with dummy suppliers MHHS (outgoing supplier) and MHHX (incoming supplier) for the Change of Supply Test Cases. For messages to flow between DIP, the LDSO s
4 | 1.5.5.9 |  |  |  |  | Test Execution Data Support | 0% | Wed 04/09/24 | Mon 23/12/24 | 79 days | Wed 04/09/24 | Mon 23/12/24 | 1383 |  | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.6 |  |  |  |  | Tooling | 100% | Wed 31/01/24 | Fri 23/08/24 | 148 days | Wed 31/01/24 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.6.1 |  |  |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 100% | Wed 31/01/24 | Fri 12/04/24 | 53 days | Wed 31/01/24 | Fri 12/04/24 | 1331 | 1387 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.6.2 |  |  |  |  | Develop Training Requirements & Materials Inc. Day in the Life | 100% | Mon 15/04/24 | Tue 13/08/24 | 87 days | Mon 15/04/24 | Tue 13/08/24 | 1386 | 1388 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.6.3 |  |  |  |  | ADO Launch complete | 100% | Fri 23/08/24 | Fri 23/08/24 | 1 day | Fri 23/08/24 | Fri 23/08/24 | 1387136813721370 |  | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.7 |  |  |  |  | Pre-Integration Testing | 90% | Wed 31/01/24 | Fri 29/11/24 | 218 days | Wed 31/01/24 | Mon 30/09/24 |  |  | 0 days | 44 days | 44 days | N/A |  | 5.24 | Yes
4 | 1.5.7.1 |  |  |  |  | PIT Guidance & Templates & Approach & Plans Developed | 100% | Mon 05/02/24 | Mon 01/07/24 | 106 days | Mon 05/02/24 | Mon 01/07/24 | 1331FS+3 days | 1391 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.7.2 |  | T3-QU-0075 | QAG (Non-SIT LDSO) |  | PIT Test Approach & Plan Deadline for Submission for Non-SIT LDSO​ QT | 100% | Mon 01/07/24 | Mon 01/07/24 | 0 days | Mon 01/07/24 | Mon 01/07/24 | 1390 | 13921415 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.28 | Yes |  | 13/5: New milestone approved as part of cr47. 11/6: Missed date because additional time requested by PPs. 24/6: Approved at QAG on 20/6
4 | 1.5.7.3 |  |  |  |  | Develop and agree PIT Test Scenarios | 100% | Tue 02/07/24 | Mon 29/07/24 | 20 days | Mon 17/06/24 | Mon 29/07/24 | 1391 | 1393 | 11 days | 0 days | -11 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.4 |  |  |  |  | PIT Execution | 16% | Mon 30/09/24 | Fri 29/11/24 | 45 days | Tue 30/07/24 | Mon 30/09/24 | 1392 | 1394 | 44 days | 44 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.5 |  | T3-QU-0076 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Participants have submitted PIT Test Completion Report & evidence for QT Entry​ | 0% | Fri 29/11/24 | Fri 29/11/24 | 0 days | Mon 30/09/24 | Mon 30/09/24 | 1393 | 1420 | 44 days | 44 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | Date will be missed due to deferral of QT window. Forecast date to be updated from CR. Expected 16th Sept. ...
4 | 1.5.7.6 |  |  |  |  | Placing Reliance - Code Body & LDSO Functional and Migration | 100% | Wed 31/01/24 | Thu 22/08/24 | 147 days | Wed 31/01/24 | Thu 22/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.7.6.1 |  |  |  |  | Placing Reliance Submitted & Reviewed | 100% | Wed 31/01/24 | Wed 28/02/24 | 21 days | Wed 31/01/24 | Wed 28/02/24 | 1331 | 1397 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.6.2 |  |  |  |  | Define & Agree QT Testing for Each LDSO | 100% | Thu 29/02/24 | Fri 29/03/24 | 22 days | Thu 29/02/24 | Fri 29/03/24 | 1396 | 1398 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.6.3 |  |  |  |  | Develop Test Scope & Reliance Submissions | 100% | Mon 01/04/24 | Fri 26/04/24 | 20 days | Mon 01/04/24 | Fri 26/04/24 | 1397 | 1399 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.6.4 |  |  |  |  | Review and Consultation | 100% | Mon 29/04/24 | Thu 22/08/24 | 84 days | Mon 29/04/24 | Thu 22/08/24 | 1398,1342FF | 1403 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.7.7 |  |  |  |  | Placing Reliance - Code Body & LDSO Non Functional and Operational | 100% | Mon 17/06/24 | Thu 22/08/24 | 49 days | Mon 17/06/24 | Thu 22/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.25 | Yes
5 | 1.5.7.7.1 |  |  |  |  | Placing Reliance Submitted & Reviewed | 100% | Mon 17/06/24 | Tue 30/07/24 | 32 days | Mon 17/06/24 | Tue 30/07/24 | 1340FF-10 days | 1402 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.27 | Yes
5 | 1.5.7.7.2 |  |  |  |  | Review and Consultation | 100% | Wed 31/07/24 | Thu 22/08/24 | 17 days | Wed 31/07/24 | Thu 22/08/24 | 1401 | 1403 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
5 | 1.5.7.7.3 |  | T3-QU-0077 | QAG (Non-SIT LDSO) |  | PP Test Scope Presented at QAG | 100% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 14021399 |  | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes |  | Date missed because of the update to Supplier and Agent Approach and Plan. Finalised Test Scope will be presented for approval as part of the assurance around the update to Annex 1. To go to July QAG for baseline date change
3 | 1.5.8 |  |  |  |  | LDSO Test Readiness Reporting | 100% | Fri 19/04/24 | Fri 26/07/24 | 71 days | Fri 19/04/24 | Tue 01/10/24 |  |  | 0 days | -47 days | -47 days | N/A |  | 5.24 | Yes
4 | 1.5.8.1 |  |  |  |  | Interim Test Readiness Report & Plan Developed & Reviewed | 100% | Fri 19/04/24 | Fri 26/07/24 | 71 days | Fri 19/04/24 | Fri 26/07/24 | 1358 | 1406 | 0 days | 0 days | 0 days | Non-SIT LDSO, LDSO |  | 5.24 | Yes
4 | 1.5.8.2 |  | T3-QU-0114 | QAG (Non-SIT LDSO) |  | Test Plan Submission to MHHS Programme For Review | 100% | Fri 26/07/24 | Fri 26/07/24 | 0 days | Fri 26/07/24 | Fri 26/07/24 | 1405 |  | 0 days | 0 days | 0 days | LDSO |  | 5.3 | Yes |  | 9 of the expected 12 Interim Test Readiness Reports and are following up with those who are outstanding. These are not a direct requirement of onboarding but a gap analysis ahead of test start
3 | 1.5.9 |  |  |  |  | Test Environment | 65% | Wed 17/04/24 | Wed 18/09/24 | 111 days | Wed 17/04/24 | Wed 18/09/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.9.1 |  |  |  |  | Define Test Harness Requirements and Sign-Off with SRO | 100% | Wed 17/04/24 | Fri 03/05/24 | 13 days | Wed 17/04/24 | Fri 03/05/24 | 473 | 1420 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.9.2 |  |  |  |  | Central System (DIP Env & Helix Test Harness) Test Environment DBT | 73% | Wed 17/04/24 | Mon 09/09/24 | 104 days | Wed 17/04/24 | Thu 22/08/24 | 473 | 1410FF | 0 days | 12 days | 12 days | LDSO |  | 5.24 | Yes
4 | 1.5.9.3 |  |  |  |  | Coordinate LDSO Env Preparation | 33% | Fri 12/07/24 | Mon 09/09/24 | 42 days | Fri 12/07/24 | Thu 22/08/24 | 1409FF | 1413 | 0 days | 12 days | 12 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.9.4 |  |  |  |  | DIP available for Onboarding | 100% | Thu 01/08/24 | Thu 01/08/24 | 1 day | Thu 01/08/24 | Thu 01/08/24 |  | 1412FS+2 days | 0 days | 0 days | 0 days | Test Env |  | 5.24 | Yes
4 | 1.5.9.5 | T3 | T3-QU-0009 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs Participants' environments) Ready to start DIP onboarding (incl. certificates and security compliance) | 100% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Mon 05/08/24 | Mon 05/08/24 | 1411FS+2 days | 1413FS+32 days | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.3 | Yes
4 | 1.5.9.6 |  | T3-QU-0078 | QAG (Non-SIT LDSO) |  | LDSO Test Environments Connection Confirmed to UIT Environment | 0% | Wed 18/09/24 | Wed 18/09/24 | 0 days | Wed 18/09/24 | Wed 18/09/24 | 1412FS+32 days,1410 | 1423 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | At risk because of DIP env availability for the test harness. (Issue no: I186). Issue will be avoided if start of QT window is delayed...
3 | 1.5.10 |  |  |  |  | Test Readiness | 22% | Tue 02/07/24 | Fri 20/12/24 | 124 days | Mon 17/06/24 | Mon 30/09/24 |  |  | 11 days | 59 days | 48 days | N/A |  | 5.24 | Yes
4 | 1.5.10.1 |  |  |  |  | Preparation for Interim Test Readiness Report | 100% | Tue 02/07/24 | Fri 26/07/24 | 19 days | Mon 17/06/24 | Fri 26/07/24 | 1391 | 1416 | 11 days | 0 days | -11 days | LDSO |  | 5.24 | Yes
4 | 1.5.10.2 |  | T3-QU-0116 | QAG (Non-SIT LDSO) |  | Interim Test Readiness Report Submission to MHHS Programme for Review | 100% | Fri 26/07/24 | Fri 26/07/24 | 0 days | Fri 26/07/24 | Fri 26/07/24 | 1415 | 1417 | 0 days | 0 days | 0 days | LDSO |  | 5.25 | Yes |  | 9 of the expected 12 Interim Test Readiness Reports have been received and are following up with those who are outstanding. These are not a direct requirement of onboarding but a gap analysis ahead of test start
4 | 1.5.10.3 |  |  |  |  | LDSO Update Readiness Report & Final Assurance by Programme | 8% | Mon 29/07/24 | Thu 12/12/24 | 99 days | Mon 29/07/24 | Fri 30/08/24 | 1416 | 141814211419 | 0 days | 74 days | 74 days | Non-SIT LDSO, LDSO |  | 5.24 | Yes
4 | 1.5.10.4 |  |  |  |  | Final Test Readiness Report Submitted to MHHS Programme | 0% | Fri 13/12/24 | Fri 13/12/24 | 1 day | Mon 02/09/24 | Mon 02/09/24 | 1417 | 1420FS+5 days | 74 days | 74 days | 0 days | LDSO |  | 5.24 | Yes
4 | 1.5.10.5 |  |  |  |  | Final Programme Assurance of LDSO Test Readiness | 0% | Fri 13/12/24 | Fri 20/12/24 | 6 days | Mon 02/09/24 | Mon 30/09/24 | 1417 | 1421 | 74 days | 59 days | -15 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.10.6 | T3 | T3-QU-0007 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Programme Test Readiness confirmed | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Mon 30/09/24 | Mon 30/09/24 | 1418FS+5 days,1394,1368,1370,1372,1408 |  | 59 days | 59 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | Date will be missed due to deferral of QT window. Forecast date to be updated from CR. Expected 16th Sept. ...
4 | 1.5.10.7 |  | T2-QU-0550 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed (Final Test Readiness Review for LDSO) | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Mon 30/09/24 | Mon 30/09/24 | 14171419 | 1424FS+11 days,1423 | 59 days | 59 days | 0 days | LDSO |  | 5.24 | Yes |  | 13/5: New milestone approved as part of cr47.
3 | 1.5.11 |  |  |  |  | Test Window | 0% | Mon 06/01/25 | Fri 16/05/25 | 94 days? | Tue 01/10/24 | Fri 20/12/24 |  |  | 69 days | 104 days | 35 days? | N/A |  | 5.24 | Yes
4 | 1.5.11.1 |  |  |  |  | All Non-SIT LDSOs Qualification Testing | 0% | Mon 06/01/25 | Fri 16/05/25 | 94 days? | Tue 01/10/24 | Fri 20/12/24 | 14211413 | 1434 | 69 days | 104 days | 35 days? | LDSO |  | 5.24 | Yes |  | 17/09/24: New milestones added and date shifted in line with programme recalibration.
5 | 1.5.11.1.1 |  | T3-QU-0115 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO QT Test Execution Starts | 0% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Tue 01/10/24 | Tue 01/10/24 | 1421FS+11 days | 1425FS-1 day | 69 days | 69 days | 0 days | Non-SIT LDSO |  | 5.25 | Yes |  | Date will be no earlier than 1st November. Forecast date to be updated from CR. Expected 16th Sept.
5 | 1.5.11.1.2 |  |  |  |  | Non-SIT LDSO QT - Migration Testing | 0% | Mon 06/01/25 | Fri 31/01/25 | 20 days? | NA | NA | 1424FS-1 day | 1426 | 0 days | 0 days | 20 days? |  |  | 6 | Yes
5 | 1.5.11.1.3 |  |  |  |  | Non-SIT LDSO QT - Functional Testing | 0% | Mon 03/02/25 | Fri 28/03/25 | 40 days? | NA | NA | 1425 | 14271429 | 0 days | 0 days | 40 days? |  |  | 6 | Yes
5 | 1.5.11.1.4 |  |  |  |  | Non-SIT LDSO QT - Operational Testing | 0% | Mon 31/03/25 | Fri 18/04/25 | 15 days? | NA | NA | 1426 | 1428 | 0 days | 0 days | 15 days? |  |  | 6 | Yes
5 | 1.5.11.1.5 |  |  |  |  | Non-SIT LDSO QT - Non-Functional Testing | 0% | Mon 21/04/25 | Fri 09/05/25 | 15 days? | NA | NA | 1427 |  | 0 days | 0 days | 15 days? |  |  | 6 | Yes
5 | 1.5.11.1.6 |  |  |  |  | Non-SIT LDSO QT - Regression Testing | 0% | Mon 31/03/25 | Fri 09/05/25 | 30 days? | NA | NA | 1426 | 1430 | 0 days | 0 days | 30 days? |  |  | 6 | Yes
5 | 1.5.11.1.7 |  | T3-QU-0010 |  |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | 0% | Fri 16/05/25 | Fri 16/05/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 1429 | 1529,1432FF | 80 days | 79 days | 0 days |  |  | 5.24 | Yes |  | 13/5: No change as part of cr47
3 | 1.5.12 |  |  |  |  | Test Result Assurance | 0% | Mon 21/04/25 | Thu 29/05/25 | 29 days | Mon 04/11/24 | Fri 24/01/25 |  |  | 120 days | 89 days | -31 days | N/A |  | 5.24 | Yes
4 | 1.5.12.1 |  |  |  |  | LDSOs Develop & Submit Test Report (QT Test Completion Report) | 0% | Mon 21/04/25 | Fri 16/05/25 | 19 days | Mon 04/11/24 | Thu 28/11/24 | 1430FF | 1433,1525SS | 120 days | 120 days | 0 days | LDSO |  | 5.24 | Yes
4 | 1.5.12.2 |  |  |  |  | Test Reports Reviewed By MHHS & Code Bodies & Finalised | 0% | Fri 16/05/25 | Thu 29/05/25 | 10 days | Fri 29/11/24 | Fri 20/12/24 | 1432 | 1434 | 120 days | 114 days | -6 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.12.3 |  | T3-QU-0079 | QAG (Non-SIT LDSO) |  | Non-SIT LDSOs submission deadline for their QT Test Completion Report to MHHS Programme | 0% | Thu 29/05/25 | Thu 29/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 14331423 | 1436 | 114 days | 114 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 13/5: New milestone approved as part of cr47.
3 | 1.5.13 |  |  |  |  | Non-SIT LDSO Qualification Closure | 0% | Fri 30/05/25 | Thu 31/07/25 | 45 days | Mon 23/12/24 | Fri 28/02/25 |  |  | 114 days | 110 days | -4 days | N/A |  | 5.24 | Yes
4 | 1.5.13.1 |  |  |  |  | Non-SIT LDSO Qualification Learned Captured | 0% | Fri 30/05/25 | Thu 19/06/25 | 15 days | Mon 23/12/24 | Fri 10/01/25 | 1434 | 1437 | 114 days | 114 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.13.2 |  |  |  |  | Non-SIT LDSO Qualification Closure Down | 0% | Fri 20/06/25 | Thu 26/06/25 | 5 days | Mon 13/01/25 | Fri 17/01/25 | 1436 | 1438FS+25 days | 114 days | 114 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.13.3 |  | T2-QU-0500 | QAG (Non-SIT LDSO) |  | BSC PAB & REC Manager approval of Qualification for Non-SIT LDSOs (Start of Migration for Qualification Participants) | 0% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1527,1528,1437FS+25 days | 2365 | 110 days | 110 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 13/5: name changed as part of cr47.
2 | 1.6 |  |  |  |  | S & A QUALIFICATION | 33% | Tue 07/11/23 | Tue 08/12/26 | 806 days | Tue 07/11/23 | Fri 27/02/26 |  |  | 0 days | 203 days | 203 days | N/A |  |  | Yes
3 | 1.6.1 |  |  |  |  | MHHS Qualification - Qualification Deliverables | 85% | Tue 07/11/23 | Fri 07/03/25 | 349 days | Tue 07/11/23 | Fri 07/03/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.6.1.1 |  |  |  |  | BSC & REC Assessment Criteria | 99% | Tue 07/11/23 | Thu 29/08/24 | 213 days | Tue 07/11/23 | Thu 29/08/24 |  |  | 0 days | 1 day | 1 day | N/A |  | 5.24 | Yes
5 | 1.6.1.1.1 |  |  |  |  | Draft BSC Assessment Criteria (Functional) | 100% | Tue 07/11/23 | Tue 05/12/23 | 21 days | Tue 07/11/23 | Tue 05/12/23 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.2 |  |  |  |  | BSC PAB Review | 100% | Thu 14/12/23 | Thu 14/12/23 | 1 day | Thu 14/12/23 | Thu 14/12/23 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.3 |  |  |  |  | Update BSC Assessment Criteria (Functional, Non-Functional, Migration) | 100% | Wed 07/02/24 | Tue 19/03/24 | 30 days | Wed 07/02/24 | Tue 19/03/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.4 |  |  |  |  | REC & BSC PAB Approval | 100% | Tue 26/03/24 | Thu 28/03/24 | 3 days | Tue 26/03/24 | Thu 28/03/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.5 |  |  |  |  | Update BSC Assessment Criteria (Functional, Non-Functional, Migration, Operational) | 100% | Wed 24/07/24 | Tue 20/08/24 | 20 days | Wed 24/07/24 | Tue 20/08/24 |  | 1447FS+7 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.6 |  | T3-QU-0080 | QAG |  | Assessment Criteria (Functional, Non-Functional, Migration, Operational) Approved by REC PAB and BSC PAB | 0% | Thu 29/08/24 | Thu 29/08/24 | 0 days | Thu 29/08/24 | Thu 29/08/24 | 1446FS+7 days | 1581 | 1 day | 1 day | 0 days | Code Bodies |  | 5.25 | Yes |  | Date missed because additional changes were identified during test scope analysis, therefore assessment criteria needs further updates (a version was approved in June). On course to be approved at next PAB....
4 | 1.6.1.2 |  |  |  |  | Qualification Approach and Plan | 97% | Mon 04/12/23 | Thu 29/08/24 | 194 days | Mon 04/12/23 | Thu 29/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.6.1.2.1 |  |  |  |  | Qualification Approach and Plan v2 | 100% | Mon 04/12/23 | Thu 28/03/24 | 84 days | Mon 04/12/23 | Thu 28/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.2.1.1 |  |  |  |  | Draft Qualification Approach and Plan v2 | 100% | Mon 04/12/23 | Fri 12/01/24 | 30 days | Mon 04/12/23 | Fri 12/01/24 |  | 1451 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) for Qualification Approach and Plan V2 | 100% | Mon 15/01/24 | Fri 26/01/24 | 10 days | Mon 15/01/24 | Fri 26/01/24 | 1450 | 1452 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.1.2.1.3 |  |  |  |  | Industry consultation for Qualification Approach and Plan v2 | 100% | Wed 31/01/24 | Wed 14/02/24 | 11 days | Wed 31/01/24 | Wed 14/02/24 | 1451 | 1453 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.1.2.1.4 |  |  |  |  | Update Qualification Approach and Plan v2 post industry consultation | 100% | Thu 15/02/24 | Wed 28/02/24 | 10 days | Thu 15/02/24 | Wed 28/02/24 | 1452 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.5 |  |  |  |  | QWG Endorsement of Qualification Approach and Plan v2 | 100% | Tue 12/03/24 | Tue 12/03/24 | 1 day | Tue 12/03/24 | Tue 12/03/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.6 |  |  |  |  | QAG Approval of Qualification Approach and Plan v2 | 100% | Thu 21/03/24 | Thu 21/03/24 | 1 day | Thu 21/03/24 | Thu 21/03/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.7 |  |  |  |  | BSC and REC PAB Approval of Qualification Approach and Plan v2 | 100% | Tue 26/03/24 | Thu 28/03/24 | 3 days | Tue 26/03/24 | Thu 28/03/24 |  | 14571458 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.8 |  | T3-QU-0063 | QAG |  | Functional Testing elements of Qualification Approach & Plan v2 approvement by REC PAB and BSC PAB | 100% | Thu 28/03/24 | Thu 28/03/24 | 0 days | Thu 28/03/24 | Thu 28/03/24 | 1456 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.9 |  | T3-QU-0064 | QAG |  | Migration Testing elements of Qualification Approach & Plan v2 appoved by REC PAB and BSC PAB | 100% | Thu 28/03/24 | Thu 28/03/24 | 0 days | Thu 28/03/24 | Thu 28/03/24 | 1456 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.2.2 |  |  |  |  | Qualification Approach and Plan v3 | 94% | Mon 06/05/24 | Thu 29/08/24 | 84 days | Mon 06/05/24 | Thu 29/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.2.2.1 |  |  |  |  | Draft Qualification Approach and Plan v3 | 100% | Mon 06/05/24 | Fri 21/06/24 | 35 days | Mon 06/05/24 | Fri 21/06/24 | 927 | 1461 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Approach and Plan v3 | 100% | Mon 24/06/24 | Fri 05/07/24 | 10 days | Mon 24/06/24 | Fri 05/07/24 | 1460 | 1462 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.27 | Yes
6 | 1.6.1.2.2.3 |  |  |  |  | Industry consultation for Qualification Approach and Plan v3 | 100% | Mon 08/07/24 | Fri 19/07/24 | 10 days | Mon 08/07/24 | Fri 19/07/24 | 1461 | 1463 | 0 days | 0 days | 0 days | Participants |  | 5.27 | Yes
6 | 1.6.1.2.2.4 |  |  |  |  | Update Qualification Approach and Plan v3 Post-Consultation | 100% | Mon 22/07/24 | Fri 02/08/24 | 10 days | Mon 22/07/24 | Fri 02/08/24 | 1462 | 1464FS+6 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.5 |  |  |  |  | QWG Endorsement of Qualification Approach and Plan v3 | 0% | Tue 13/08/24 | Tue 13/08/24 | 1 day | Tue 13/08/24 | Tue 13/08/24 | 1463FS+6 days | 1465FS+7 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.6 |  | T3-QU-0081 | QAG |  | QAG Approval of Qualification Approach and Plan v3 | 0% | Thu 22/08/24 | Thu 22/08/24 | 0 days | Thu 22/08/24 | Thu 22/08/24 | 1464FS+7 days | 1466FS+2 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes |  | 28/5: Late because of delay to approval of SIT Non Functional approach. Re-planned to align to v4. To go to June QAG for baseline date change. 24/6: Approved at QAG on 20/6
6 | 1.6.1.2.2.7 |  |  |  |  | BSC and REC PAB Approval of Qualification Approach and Plan v3 | 0% | Tue 27/08/24 | Thu 29/08/24 | 3 days | Tue 27/08/24 | Thu 29/08/24 | 1465FS+2 days | 1467 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.8 |  | T3-QU-0065 | QAG |  | Non-Functional Testing elements of Qualification Approach and Plan v3 approved by REC PAB and BSC PAB | 100% | Thu 29/08/24 | Thu 29/08/24 | 0 days | Thu 29/08/24 | Thu 29/08/24 | 1466 | 1567 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes |  | 28/5: Late because of delay to approval of SIT Non Functional approach. Re-planned to align to v4. 24/6: Approved at QAG on 20/6
4 | 1.6.1.3 |  |  |  |  | Qualification Assessment Document | 76% | Fri 22/12/23 | Fri 07/03/25 | 316 days | Fri 22/12/23 | Fri 07/03/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.6.1.3.1 |  |  |  |  | Qualification Assessment Document v1 | 100% | Fri 22/12/23 | Thu 28/03/24 | 70 days | Fri 22/12/23 | Thu 28/03/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.3.1.1 |  |  |  |  | Draft Qualification Assessment Document v1 | 100% | Fri 22/12/23 | Thu 01/02/24 | 30 days | Fri 22/12/23 | Thu 01/02/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.1.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Assessment Document v1 | 100% | Thu 01/02/24 | Wed 14/02/24 | 10 days | Thu 01/02/24 | Wed 14/02/24 |  |  | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.1.3.1.3 |  |  |  |  | Industry consultation for Qualification Assessment Document v1 | 100% | Fri 16/02/24 | Fri 01/03/24 | 11 days | Fri 16/02/24 | Fri 01/03/24 |  | 1473 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.1.3.1.4 |  |  |  |  | Update Post-Consultation for Qualification Assessment Document v1 | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 | 1472 |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.1.5 |  |  |  |  | BSC and REC PAB Approval of Qualification Assessment Document v1 | 100% | Tue 26/03/24 | Thu 28/03/24 | 3 days | Tue 26/03/24 | Thu 28/03/24 |  | 1475 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.1.6 |  | T3-QU-0066 | QAG |  | Qualification Assessment Document v1 approved by REC PAB and BSC PAB | 100% | Thu 28/03/24 | Thu 28/03/24 | 0 days | Thu 28/03/24 | Thu 28/03/24 | 1474 | 1477 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.3.2 |  |  |  |  | Qualification Assessment Document v3 | 94% | Fri 29/03/24 | Thu 29/08/24 | 110 days | Fri 29/03/24 | Thu 29/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.3.2.1 |  |  |  |  | Draft Qualification Assessment Document V1.1 | 100% | Fri 29/03/24 | Fri 03/05/24 | 26 days | Fri 29/03/24 | Fri 03/05/24 | 1475 | 1478 | 0 days | 0 days | 0 days |  |  | 5.24 | Yes
6 | 1.6.1.3.2.2 |  |  |  |  | Industry Consultation for Qualification Assessment Document V1.1 | 100% | Mon 06/05/24 | Tue 21/05/24 | 12 days | Mon 06/05/24 | Tue 21/05/24 | 1477 | 1479 | 0 days | 0 days | 0 days |  |  | 5.24 | Yes
6 | 1.6.1.3.2.3 |  |  |  |  | Draft Qualification Assessment Document v3 | 100% | Fri 14/06/24 | Fri 21/06/24 | 6 days | Fri 14/06/24 | Fri 21/06/24 | 10021478 | 1480 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.4 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Assessment Document v3 | 100% | Mon 24/06/24 | Fri 05/07/24 | 10 days | Mon 24/06/24 | Fri 05/07/24 | 1479 | 1481 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.1.3.2.5 |  |  |  |  | Industry consultation for Qualification Assessment Document v3 | 100% | Mon 08/07/24 | Fri 19/07/24 | 10 days | Mon 08/07/24 | Fri 19/07/24 | 1480 | 1482 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.1.3.2.6 |  |  |  |  | Update Post-Consultation for Qualification Assessment Document v3 | 100% | Mon 22/07/24 | Fri 02/08/24 | 10 days | Mon 22/07/24 | Fri 02/08/24 | 1481 | 1483FS+6 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.7 |  |  |  |  | QWG Endorsement of Qualification Assessment Document v3 | 0% | Tue 13/08/24 | Tue 13/08/24 | 1 day | Tue 13/08/24 | Tue 13/08/24 | 1482FS+6 days | 1484FS+6 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.8 |  | T3-QU-0083 | QAG |  | QAG Endorsement of Qualification Assessment Document v3 | 0% | Thu 22/08/24 | Thu 22/08/24 | 1 day | Thu 22/08/24 | Thu 22/08/24 | 1483FS+6 days | 1485FS+2 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.25 | Yes
6 | 1.6.1.3.2.9 |  |  |  |  | BSC and REC PAB Approval of Qualification Assessment Document v3 | 0% | Tue 27/08/24 | Thu 29/08/24 | 3 days | Tue 27/08/24 | Thu 29/08/24 | 1484FS+2 days | 1486 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.10 |  | T3-QU-0067 | QAG |  | Qualification Assessment Document v3 approved by REC PAB and BSC PAB | 100% | Thu 29/08/24 | Thu 29/08/24 | 0 days | Thu 29/08/24 | Thu 29/08/24 | 1485 | 1499 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.3.3 |  |  |  |  | Qualification Assessment Document Portal | 59% | Mon 05/02/24 | Fri 07/03/25 | 285 days | Mon 05/02/24 | Fri 07/03/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.3.3.1 |  |  |  |  | Design Completion | 100% | Mon 05/02/24 | Fri 15/03/24 | 30 days | Mon 05/02/24 | Fri 15/03/24 |  | 1489 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.2 |  |  |  |  | Qualification Assessment Document Portal Build | 100% | Mon 18/03/24 | Fri 26/04/24 | 30 days | Mon 18/03/24 | Fri 26/04/24 | 1488 | 1490 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.3 |  |  |  |  | Qualification Assessment Document Internal Testing | 100% | Mon 29/04/24 | Fri 24/05/24 | 20 days | Mon 29/04/24 | Fri 24/05/24 | 1489 | 1491 | 0 days | 0 days | 0 days | QAD Portal Dev Team. Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.4 |  |  |  |  | Qualification Assessment Document Portal Training and Onboarding Material Creation | 100% | Mon 27/05/24 | Fri 21/06/24 | 20 days | Mon 27/05/24 | Fri 21/06/24 | 1490 | 1493FS+35 days,1494FS+35 days,1495FS+65 days,1496FS+90 days,1497FS+135 days,1498FS+175 days | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.5 |  |  |  |  | Qualification Assessment Document Portal Webinar (Date TBC) | 100% | Tue 18/06/24 | Tue 18/06/24 | 1 day | Tue 11/06/24 | Tue 11/06/24 |  |  | 5 days | 5 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.6 |  |  |  |  | SIT Participant QAD Application Creation in Portal | 0% | Mon 12/08/24 | Fri 23/08/24 | 10 days | Mon 12/08/24 | Fri 23/08/24 | 1491FS+35 days | 1502FS+96 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.7 |  |  |  |  | Non-SIT LDSO Participant QAD Application Creation in Portal | 0% | Mon 12/08/24 | Fri 23/08/24 | 10 days | Mon 12/08/24 | Fri 23/08/24 | 1491FS+35 days | 1519FS+96 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.8 |  |  |  |  | QT Wave 1 Participant QAD Application Creation in Portal | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 23/09/24 | Fri 04/10/24 | 1491FS+65 days | 1678FS+120 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.9 |  |  |  |  | QT Wave 2 Participant QAD Application Creation in Portal | 0% | Mon 28/10/24 | Fri 08/11/24 | 10 days | Mon 28/10/24 | Fri 08/11/24 | 1491FS+90 days | 1708FS+120 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.3.3.10 |  |  |  |  | QT Wave 3 Participant QAD Application Creation in Portal | 0% | Mon 30/12/24 | Fri 10/01/25 | 10 days | Mon 30/12/24 | Fri 10/01/25 | 1491FS+135 days | 1738FS+120 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.3.3.11 |  |  |  |  | QT Wave 4 Participant QAD Application Creation in Portal | 0% | Mon 24/02/25 | Fri 07/03/25 | 10 days | Mon 24/02/25 | Fri 07/03/25 | 1491FS+175 days | 1768FS+120 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.3.3.12 |  |  |  |  | Update to Qualification Assessment Document Portal post QAD V3 | 0% | Fri 30/08/24 | Thu 12/09/24 | 10 days | Fri 30/08/24 | Thu 12/09/24 | 1486 | 1500 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.13 |  | T3-QU-0084 | QAG |  | Update to Qualification Assessment Document Portal post QAD V3 Complete | 0% | Thu 12/09/24 | Thu 12/09/24 | 0 days | Thu 12/09/24 | Thu 12/09/24 | 1499 | 1507 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.25 | Yes
3 | 1.6.2 |  |  |  |  | MHHS Qualification - SIT Participants | 0% | Mon 06/01/25 | Fri 14/11/25 | 225 days | Mon 02/09/24 | Fri 30/05/25 |  |  | 90 days | 121 days | 31 days | N/A |  | 5.24 | Yes
4 | 1.6.2.1 |  |  |  |  | Initial QAD Submission Window opens | 0% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Mon 02/09/24 | Mon 02/09/24 | 1493FS+96 days |  | 91 days | 91 days | 0 days | Participants |  | 5.24 | Yes
4 | 1.6.2.2 |  |  |  |  | SIT Participants submit Initial QAD | 0% | Mon 06/01/25 | Thu 13/02/25 | 29 days | Mon 02/09/24 | Thu 10/10/24 |  | 1504 | 90 days | 90 days | 0 days | Participants |  | 5.24 | Yes
4 | 1.6.2.3 |  |  |  |  | Code Bodies review Initial QAD | 0% | Fri 14/02/25 | Fri 04/04/25 | 36 days | Fri 11/10/24 | Fri 29/11/24 | 1503 | 15071505 | 90 days | 90 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.6.2.4 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1504 | 1507,1513FS+1 day | 90 days | 90 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.6.2.5 |  |  |  |  | MHHS Qualification - SIT MVC Participants | 0% | Fri 04/04/25 | Thu 31/07/25 | 84 days | Fri 29/11/24 | Fri 28/02/25 |  |  | 90 days | 110 days | 20 days | N/A |  | 5.24 | Yes
5 | 1.6.2.5.1 |  |  |  |  | Final QAD Submission Window (MVC) opens | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 150415001505 | 1508 | 90 days | 90 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.2.5.2 |  |  |  |  | SIT MVC Participants submit Final QAD | 0% | Mon 07/04/25 | Mon 12/05/25 | 26 days | Mon 02/12/24 | Mon 06/01/25 | 1507 | 1509 | 90 days | 90 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.2.5.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (MVC) | 0% | Tue 13/05/25 | Fri 06/06/25 | 19 days | Tue 07/01/25 | Fri 31/01/25 | 1508,1190FF | 1510 | 90 days | 90 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.2.5.4 |  |  |  |  | QAD Sign Off Deadline (MVC) | 0% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 11991509 | 1511FS+14 days | 111 days | 110 days | -1 day | Participants |  | 5.24 | Yes
5 | 1.6.2.5.5 |  | T3-QU-0085 | QAG |  | REC Code Manager / BSC PAB Approval of Qualification (MVC) | 0% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1510FS+14 days | 2214SS | 110 days | 110 days | 0 days | Code Bodies |  | 5.25 | Yes |  | 6/8/24: Date at risk from scenario planning activity
4 | 1.6.2.6 |  |  |  |  | MHHS Qualification - SIT Non-MVC Participants | 0% | Mon 07/04/25 | Fri 14/11/25 | 159 days | Mon 02/12/24 | Fri 30/05/25 |  |  | 91 days | 121 days | 30 days | N/A |  | 5.24 | Yes
5 | 1.6.2.6.1 |  |  |  |  | Final QAD Submission Window (Non-MVC) opens | 0% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1505FS+1 day | 1514SS | 91 days | 91 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.2.6.2 |  |  |  |  | SIT Non-MVC Participants submit Final QAD | 0% | Tue 08/04/25 | Mon 04/08/25 | 85 days | Mon 02/12/24 | Mon 31/03/25 | 1513SS | 1515 | 91 days | 90 days | -1 day | Participants |  | 5.24 | Yes
5 | 1.6.2.6.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (Non-MVC) | 0% | Tue 05/08/25 | Fri 29/08/25 | 19 days | Tue 01/04/25 | Fri 25/04/25 | 1514 | 1516FS+4 days | 90 days | 90 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.2.6.4 |  |  |  |  | QAD Sign Off Deadline (Non-MVC) | 0% | Fri 17/10/25 | Fri 17/10/25 | 1 day | Fri 02/05/25 | Fri 02/05/25 | 1515FS+4 days,1221 | 1517FS+20 days | 120 days | 120 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.2.6.5 |  | T3-QU-0086 | QAG |  | REC Code Manager / BSC PAB Approval of Qualification (Non-MVC) | 0% | Fri 14/11/25 | Fri 14/11/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1516FS+20 days | 2239SS | 121 days | 121 days | 0 days | Code Bodies |  | 5.25 | Yes |  | 6/8/24: Date at risk from scenario planning activity
3 | 1.6.3 |  |  |  |  | MHHS Qualification - Non-SIT LDSO | 0% | Mon 06/01/25 | Thu 31/07/25 | 149 days | Mon 02/09/24 | Fri 07/02/25 |  |  | 90 days | 124 days | 34 days | N/A |  | 5.24 | Yes
4 | 1.6.3.1 |  |  |  |  | Initial QAD Submission window opens | 0% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Mon 02/09/24 | Mon 02/09/24 | 1494FS+96 days |  | 91 days | 91 days | 0 days | Participants |  | 5.24 | Yes
4 | 1.6.3.2 |  |  |  |  | Non-SIT LDSO Participants submit initial QAD | 0% | Mon 06/01/25 | Thu 13/02/25 | 29 days | Mon 02/09/24 | Thu 10/10/24 |  | 1521 | 90 days | 90 days | 0 days | Participants |  | 5.24 | Yes
4 | 1.6.3.3 |  | T3-QU-0087 | QAG |  | Non-SIT LDSO QT Participants have submitted their initial QAD | 0% | Thu 13/02/25 | Thu 13/02/25 | 0 days | Thu 10/10/24 | Thu 10/10/24 | 1520 | 1522 | 90 days | 90 days | 0 days | Participants | Proposed | 5.25 | Yes |  | 28/08/24 - Date will be missed because the date for the initial QAD submission window has been moved back to reflect the delay to SIT activities and to provide Programme PPs with more time to prepare. Milestone date change was approved at QAG on 22/08/24,
4 | 1.6.3.4 |  |  |  |  | Code Bodies review of Non-SIT LDSO participants Initial QAD | 0% | Fri 14/02/25 | Fri 04/04/25 | 36 days | Fri 11/10/24 | Fri 29/11/24 | 1521 | 1523 | 90 days | 90 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.6.3.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 29/11/24 | Fri 29/11/24 | 1522 | 1524FS+1 day | 90 days | 90 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.6.3.6 |  |  |  |  | Final QAD Submission window opens | 0% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1523FS+1 day | 1525SS | 91 days | 91 days | 0 days | Participants |  | 5.24 | Yes
4 | 1.6.3.7 |  |  |  |  | Non-SIT LDSO Participants submit Final QAD | 0% | Mon 21/04/25 | Fri 23/05/25 | 25 days | Mon 02/12/24 | Mon 06/01/25 | 1432SS,1524SS | 1526 | 100 days | 99 days | -1 day | Participants |  | 5.24 | Yes
4 | 1.6.3.8 |  | T3-QU-0088 | QAG |  | Non-SIT LDSO QT Participants have submitted their final QAD | 0% | Fri 23/05/25 | Fri 23/05/25 | 0 days | Mon 06/01/25 | Mon 06/01/25 | 1525 | 1527 | 99 days | 99 days | 0 days | Participants |  | 5.25 | Yes |  | 6/8/24: Date at risk from scenario planning activity
4 | 1.6.3.9 |  |  |  |  | Completion of Code Bodies review of the Final QAD | 0% | Mon 26/05/25 | Thu 19/06/25 | 19 days | Tue 07/01/25 | Fri 31/01/25 | 1526 | 1438,1528FS+5 days | 99 days | 99 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.6.3.10 |  |  |  |  | QAD Sign Off Deadline (Non-SIT LDSOs) | 0% | Fri 11/07/25 | Fri 11/07/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1527FS+5 days,1199 | 1438,1529FS+14 days | 111 days | 110 days | -1 day | Participants |  | 5.24 | Yes |  | 18/09/24 - Adding dependency so the milestone is dependent on SIT LDSO MVC.
4 | 1.6.3.11 |  | T2-QU-0500 | QAG (Non-SIT LDSO) |  | BSC PAB & REC Manager approval of Qualification for Non-SIT LDSOs (Start of Migration for Qualification Participants) | 0% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1430,1528FS+14 days |  | 110 days | 110 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 13/5: name changed as part of cr47.
3 | 1.6.4 |  |  |  |  | MHHS Qualification - Qualification Waves | 29% | Mon 18/12/23 | Tue 08/12/26 | 777 days | Mon 18/12/23 | Fri 27/02/26 |  |  | 0 days | 203 days | 203 days | N/A |  | 5.24 | Yes
4 | 1.6.4.1 |  |  |  |  | Qualification Wave Prep | 53% | Mon 18/12/23 | Wed 07/01/26 | 538 days | Mon 18/12/23 | Thu 31/07/25 |  |  | 0 days | 114 days | 114 days | N/A |  | 5.24 | Yes
5 | 1.6.4.1.1 |  |  |  |  | Non-SIT Supplier and Agent Test Approach and Plan | 100% | Mon 18/12/23 | Thu 30/05/24 | 119 days | Mon 18/12/23 | Thu 30/05/24 |  |  | 0 days | 1 day | 1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.1.1.1 |  |  |  |  | Draft Non-SIT S&A Test Approach and Plan | 100% | Mon 18/12/23 | Fri 23/02/24 | 50 days | Mon 18/12/23 | Fri 23/02/24 |  | 1534 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.1.2 |  |  |  |  | Internal Review of Non-SIT S&A Test Approach and Plan (Code Bodies and MHHSP) | 100% | Mon 26/02/24 | Fri 08/03/24 | 10 days | Mon 26/02/24 | Fri 08/03/24 | 1533 | 1535 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.4.1.1.3 |  |  |  |  | Issue Non-SIT S&A Test Approach and Plan for Consultation | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | Mon 18/03/24 | Fri 05/04/24 | 1534 | 1536 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.1.4 |  |  |  |  | Update Non-SIT S&A Test Approach and Plan Post-Consultation | 100% | Mon 08/04/24 | Fri 19/04/24 | 10 days | Mon 08/04/24 | Fri 19/04/24 | 1535 | 1541,1590FS+2 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.1.5 |  |  |  |  | QWG Endorsement of Non-SIT S&A Test Approach and Plan | 100% | Tue 14/05/24 | Tue 14/05/24 | 1 day | Tue 14/05/24 | Tue 14/05/24 |  | 1538FS+7 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.1.6 |  | T3-QU-0089 | QAG |  | QAG Approval of Non-SIT S&A Test Approach and Plan | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1537FS+7 days | 1539FS+5 days | 1 day | 1 day | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.1.7 |  | T3-QU-0090 | QAG |  | BSC & REC PAB Approval of Non-SIT S&A Test Approach and Plan | 100% | Thu 30/05/24 | Thu 30/05/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 1538FS+5 days |  | 1 day | 1 day | 0 days | Code Bodies |  | 5.25 | Yes
5 | 1.6.4.1.2 |  |  |  |  | QT Test Data Approach and Plan | 100% | Fri 19/04/24 | Thu 18/07/24 | 64 days | Fri 19/04/24 | Thu 18/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.1.2.1 |  |  |  |  | QT Test Data Approach agreed as part of the Non-SIT Supplier and Agent Test Approach and Plan | 100% | Fri 19/04/24 | Fri 19/04/24 | 0 days | Fri 19/04/24 | Fri 19/04/24 | 1536 | 1542 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Participants |  | 5.24 | Yes
6 | 1.6.4.1.2.2 |  |  |  |  | Draft Test Data Approach and Plan for QT | 100% | Mon 06/05/24 | Fri 17/05/24 | 10 days | Mon 06/05/24 | Fri 17/05/24 | 1541 | 1543 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.2.3 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of QT Test Data Approach and Plan | 100% | Mon 20/05/24 | Fri 07/06/24 | 15 days | Mon 20/05/24 | Fri 31/05/24 | 1542 | 15441635 | 0 days | 5 days | 5 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.4.1.2.4 |  |  |  |  | Issue QT Test Data Approach and Plan for Industry Consultation | 100% | Mon 10/06/24 | Fri 21/06/24 | 10 days | Mon 03/06/24 | Fri 14/06/24 | 1543 | 1545 | 5 days | 5 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.2.5 |  |  |  |  | Update QT Test Approach and Plan Post Industry Consultation | 100% | Mon 24/06/24 | Fri 28/06/24 | 5 days | Mon 17/06/24 | Fri 28/06/24 | 1544 | 1546FS+6 days | 5 days | 0 days | -5 days | Non-SIT S&A QT Team |  | 5.24 | Yes
6 | 1.6.4.1.2.6 |  |  |  |  | QWG Endorsement of Test Data Approach and Plan | 100% | Tue 09/07/24 | Tue 09/07/24 | 1 day | Tue 09/07/24 | Tue 09/07/24 | 1545FS+6 days | 1547FS+7 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.2.7 |  | T3-QU-0091 | QAG |  | QAG Approval of QT Test Data Approach and Plan | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1546FS+7 days | 1570 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.29 | Yes
5 | 1.6.4.1.3 |  |  |  |  | QT Functional Test Scenarios and Test Cases | 100% | Mon 04/03/24 | Thu 23/05/24 | 59 days | Mon 04/03/24 | Thu 23/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.1.3.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 1 | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 |  | 15501551 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.3.2 |  |  |  |  | Issue Batch 1 for Consultation | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | Mon 18/03/24 | Fri 05/04/24 | 1549 |  | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.3.3 |  |  |  |  | Gap analysis against QT Requirements | 100% | Mon 18/03/24 | Wed 27/03/24 | 8 days | Mon 18/03/24 | Wed 27/03/24 | 1549 | 1552 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.3.4 |  |  |  |  | Update Test Scenarios and Test Case list - Batch 2 | 100% | Thu 28/03/24 | Thu 04/04/24 | 6 days | Thu 28/03/24 | Thu 04/04/24 | 1551 | 1553 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.3.5 |  |  |  |  | Issue Batch 2 for consultation | 100% | Fri 05/04/24 | Thu 18/04/24 | 10 days | Fri 05/04/24 | Thu 18/04/24 | 1552 | 1554 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.3.6 |  |  |  |  | Update Batch 2 post consultation | 100% | Fri 19/04/24 | Thu 02/05/24 | 10 days | Fri 19/04/24 | Thu 02/05/24 | 1553 |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.3.7 |  |  |  |  | QWG Endorsement of Batch 1 and 2 | 100% | Tue 14/05/24 | Tue 14/05/24 | 1 day | Tue 14/05/24 | Tue 14/05/24 |  | 1556FS+7 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.3.8 |  | T3-QU-0092 | QAG |  | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 1 and 2 | 100% | Thu 23/05/24 | Thu 23/05/24 | 0 days | Thu 23/05/24 | Thu 23/05/24 | 1555FS+7 days |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.6.4.1.4 |  |  |  |  | QT Migration Test Scenarios and Test Cases | 100% | Mon 06/05/24 | Thu 18/07/24 | 54 days | Mon 06/05/24 | Thu 18/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.25 | Yes
6 | 1.6.4.1.4.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 1 | 100% | Mon 06/05/24 | Fri 31/05/24 | 20 days | Mon 06/05/24 | Fri 31/05/24 | 893FS+12 days | 1559 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | Yes
6 | 1.6.4.1.4.2 |  |  |  |  | Issue Batch 1 for Consultation | 100% | Mon 03/06/24 | Fri 14/06/24 | 10 days | Mon 03/06/24 | Fri 14/06/24 | 1558 | 1560 | 0 days | 0 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.4.3 |  |  |  |  | Update Batch 1 Post Consultation | 100% | Mon 17/06/24 | Fri 28/06/24 | 10 days | Mon 17/06/24 | Fri 28/06/24 | 1559 | 1561FS+7 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.4.4 |  |  |  |  | QWG Endorsement of Batch 1 | 100% | Tue 09/07/24 | Tue 09/07/24 | 0 days | Tue 09/07/24 | Tue 09/07/24 | 1560FS+7 days | 1562FS+7 days | 1 day | 1 day | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.4.5 |  | T3-QU-0119 | QAG |  | QAG Approval of QT Migration Test Scenarios and Test Cases Batches 1 | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1561FS+7 days | 1601FF | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.29 | Yes
5 | 1.6.4.1.5 |  |  |  |  | QT Non-Functional Test Scenarios and Test Cases | 0% | Fri 20/09/24 | Fri 13/12/24 | 61 days | Mon 22/07/24 | Thu 19/09/24 |  |  | 44 days | 62 days | 18 days | N/A |  | 5.25 | Yes
6 | 1.6.4.1.5.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 2 | 0% | Fri 20/09/24 | Mon 28/10/24 | 27 days | Mon 22/07/24 | Fri 02/08/24 | 950FS+2 days,944FS+2 days | 1565 | 44 days | 61 days | 17 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | Yes
6 | 1.6.4.1.5.2 |  |  |  |  | Issue Batch 2 for Consultation | 0% | Tue 29/10/24 | Mon 11/11/24 | 10 days | Mon 05/08/24 | Fri 16/08/24 | 1564 | 1566 | 61 days | 61 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.5.3 |  |  |  |  | Update Batch 2 Post Consultation | 0% | Tue 12/11/24 | Mon 25/11/24 | 10 days | Mon 19/08/24 | Fri 30/08/24 | 1565 | 1567FS+7 days | 61 days | 61 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.5.4 |  |  |  |  | QWG Endorsement of Batch 2 | 0% | Wed 04/12/24 | Wed 04/12/24 | 0 days | Tue 10/09/24 | Tue 10/09/24 | 1566FS+7 days,1467 | 1568FS+7 days | 62 days | 62 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.5.5 |  | T3-QU-0120 | QAG |  | QAG Approval of QT Non-Functional Test Scenarios and Test Cases Batch 2 | 0% | Fri 13/12/24 | Fri 13/12/24 | 0 days | Thu 19/09/24 | Thu 19/09/24 | 1567FS+7 days | 1601FF | 62 days | 62 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes |  | Date will be missed because of SIT Non-Functional/Operational Test Scenario Approval dates. QT Test Scenarios which reuse SIT Scenarios are unable to be approved until SIT Scenarios are approved. Review scope of SIT NF/Operational to understand whether al
5 | 1.6.4.1.6 |  |  |  |  | QT Operational Test Scenarios and Test Cases | 0% | Tue 10/09/24 | Wed 01/01/25 | 82 days | Mon 22/07/24 | Thu 17/10/24 |  |  | 36 days | 55 days | 19 days | N/A |  | 5.25 | Yes |  | Impact: QT Test Scenarios which reuse SIT Scenarios are unable to be approved until SIT Scenarios are approved.
6 | 1.6.4.1.6.1 |  |  |  |  | Draft QT Operational Test Cases - Batch 1 | 0% | Wed 11/09/24 | Thu 14/11/24 | 47 days | Mon 22/07/24 | Fri 02/08/24 | 999FS+2 days,1547 | 1571 | 37 days | 74 days | 37 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | Yes |  | Action: Review scope of SIT NF/Operational to understand whether all themes impact QT, work with SIT team to increase parallelisation of activities where possible.
6 | 1.6.4.1.6.2 |  |  |  |  | Issue Batch 1 for Consultation | 0% | Fri 15/11/24 | Thu 28/11/24 | 10 days | Mon 05/08/24 | Fri 16/08/24 | 1570 | 1572 | 74 days | 74 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.6.3 |  |  |  |  | Update Batch 1 Post Consultation | 0% | Fri 29/11/24 | Thu 12/12/24 | 10 days | Mon 19/08/24 | Fri 30/08/24 | 1571 | 1573FS+7 days | 74 days | 74 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.6.4 |  |  |  |  | QWG Endorsement of Batch 1 | 0% | Mon 23/12/24 | Mon 23/12/24 | 0 days | Tue 10/09/24 | Tue 10/09/24 | 1572FS+7 days | 1574FS+7 days | 75 days | 75 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.6.5 |  | T3-QU-0121 | QAG |  | QAG Approval of QT Operational Test Scenarios and Test Cases Batch 1 | 0% | Wed 01/01/25 | Wed 01/01/25 | 0 days | Thu 19/09/24 | Thu 19/09/24 | 1573FS+7 days | 1601FF | 75 days | 75 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes |  | Date will be missed because of delay to SIT Non-Functional/Operational Test Scenario Approval dates. QT Test Scenarios which reuse SIT Scenarios are unable to be approved until SIT Scenarios are approved. Review scope of SIT NF/Operational to understand w
6 | 1.6.4.1.6.6 |  |  |  |  | Draft QT Operational Test Cases - Batch 2 | 0% | Tue 10/09/24 | Mon 23/09/24 | 10 days | Mon 22/07/24 | Fri 02/08/24 | 1005FS+2 days | 1576 | 36 days | 36 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | Yes
6 | 1.6.4.1.6.7 |  |  |  |  | Issue Batch 2 for Consultation | 0% | Tue 24/09/24 | Mon 07/10/24 | 10 days | Mon 05/08/24 | Fri 16/08/24 | 1575 | 1577 | 36 days | 36 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.6.8 |  |  |  |  | Update Batch 2 Post Consultation | 0% | Tue 08/10/24 | Mon 21/10/24 | 10 days | Mon 19/08/24 | Fri 30/08/24 | 1576 | 1578FS+7 days | 36 days | 36 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.6.9 |  |  |  |  | QWG Endorsement of Batch 2 | 0% | Wed 30/10/24 | Wed 30/10/24 | 0 days | Tue 10/09/24 | Tue 10/09/24 | 1577FS+7 days | 1579FS+7 days | 37 days | 37 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.6.10 |  | T3-QU-0122 | QAG |  | QAG Approval of QT Operational Test Scenarios and Test Cases Batch 2 | 0% | Fri 08/11/24 | Fri 08/11/24 | 0 days | Thu 19/09/24 | Thu 19/09/24 | 1578FS+7 days | 1601FF | 37 days | 37 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes |  | Date will be missed because of delay to SIT Non-Functional/Operational Test Scenario Approval dates. QT Test Scenarios which reuse SIT Scenarios are unable to be approved until SIT Scenarios are approved. Review scope of SIT NF/Operational to understand w
6 | 1.6.4.1.6.11 |  |  |  |  | Draft QT Operational Test Cases - Batch 3 | 0% | Mon 16/12/24 | Fri 27/12/24 | 10 days | Mon 26/08/24 | Fri 06/09/24 | 1030FS+2 days | 1581 | 80 days | 80 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | No
6 | 1.6.4.1.6.12 |  |  |  |  | Issue Batch 3 for Consultation | 0% | Mon 30/12/24 | Fri 10/01/25 | 10 days | Mon 09/09/24 | Fri 20/09/24 | 15801447 | 1582 | 80 days | 80 days | 0 days | Participants |  | 5.25 | No
6 | 1.6.4.1.6.13 |  |  |  |  | Update Batch 3 Post Consultation | 0% | Mon 13/01/25 | Fri 17/01/25 | 5 days | Mon 23/09/24 | Fri 27/09/24 | 1581 | 1583FS+7 days | 80 days | 80 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | No
6 | 1.6.4.1.6.14 |  |  |  |  | QWG Endorsement of Batch 3 | 0% | Tue 28/01/25 | Tue 28/01/25 | 0 days | Tue 08/10/24 | Tue 08/10/24 | 1582FS+7 days | 1584FS+7 days | 81 days | 81 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | No
6 | 1.6.4.1.6.15 |  | T3-QU-0123 | QAG |  | QAG Approval of QT Operational Test Scenarios and Test Cases Batch 3 | 0% | Thu 06/02/25 | Thu 06/02/25 | 0 days | Thu 17/10/24 | Thu 17/10/24 | 1583FS+7 days | 1601FF+10 days | 81 days | 81 days | 0 days | Non-SIT S&A QT Test Team | Approved | 5.31 | No |  | 15/8/24: Milestone to be removed as it has been confirmed by the Code Bodies that it doesn't contain the scope of testing involved in Qualification Testing
5 | 1.6.4.1.7 |  |  |  |  | Qualification Testing Framework (Test Stubs and Supporting UI) | 47% | Mon 29/01/24 | Wed 07/01/26 | 508 days | Mon 29/01/24 | Thu 31/07/25 |  |  | 0 days | 114 days | 114 days | N/A |  | 5.27 | Yes
6 | 1.6.4.1.7.1 |  |  |  |  | Proof of Concept for QTF Completion | 100% | Mon 29/01/24 | Fri 29/03/24 | 45 days | Mon 29/01/24 | Fri 29/03/24 |  | 1587 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
6 | 1.6.4.1.7.2 |  |  |  |  | Discovery and Mobilisation | 100% | Mon 01/04/24 | Fri 03/05/24 | 25 days | Mon 01/04/24 | Fri 03/05/24 | 1586 | 1611SS+10 days,1605SS+10 days,1592FS+10 days,1593FS+20 days,1599FS+49 days,1614FS+15 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
6 | 1.6.4.1.7.3 |  |  |  |  | Agile DBT of Qualification Testing Framework | 96% | Wed 24/04/24 | Fri 16/08/24 | 83 days | Wed 24/04/24 | Fri 16/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
7 | 1.6.4.1.7.3.1 |  |  |  |  | User Interface (UI) | 100% | Wed 24/04/24 | Fri 28/06/24 | 48 days | Wed 24/04/24 | Fri 28/06/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.3.1.1 |  |  |  |  | UI Wireframe | 100% | Wed 24/04/24 | Fri 28/06/24 | 48 days | Wed 24/04/24 | Fri 28/06/24 | 1536FS+2 days | 1591SS+13 days,1596SS+13 days,1597SS+13 days,1598SS+13 days,1664 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.1.2 |  |  |  |  | UI Standards | 100% | Mon 13/05/24 | Fri 28/06/24 | 35 days | Mon 13/05/24 | Fri 28/06/24 | 1590SS+13 days | 1595SS | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.1.3 |  |  |  |  | Elexon Branding Sylesheet | 100% | Fri 17/05/24 | Mon 20/05/24 | 1 day | Fri 17/05/24 | Mon 20/05/24 | 1587FS+10 days |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.1.4 |  |  |  |  | Elexon Branding QTF Logo | 100% | Fri 31/05/24 | Mon 03/06/24 | 1 day | Fri 31/05/24 | Mon 03/06/24 | 1587FS+20 days |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.3.2 |  |  |  |  | Design, Build, Test | 95% | Mon 13/05/24 | Fri 16/08/24 | 70 days | Mon 13/05/24 | Fri 16/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.3.2.1 |  |  |  |  | Core UI Screens | 100% | Mon 13/05/24 | Fri 02/08/24 | 60 days | Mon 13/05/24 | Fri 02/08/24 | 1591SS |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.2.2 |  |  |  |  | Tooling (Trigger Files / Template Generators) | 83% | Mon 13/05/24 | Fri 16/08/24 | 70 days | Mon 13/05/24 | Fri 16/08/24 | 1590SS+13 days | 1636SS+20 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.2.3 |  |  |  |  | Database Schema | 100% | Mon 13/05/24 | Fri 19/07/24 | 50 days | Mon 13/05/24 | Fri 19/07/24 | 1590SS+13 days |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.2.4 |  |  |  |  | Core API's | 100% | Mon 13/05/24 | Fri 02/08/24 | 60 days | Mon 13/05/24 | Fri 02/08/24 | 1590SS+13 days |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.3.2.5 |  |  |  |  | DIP (SIT-A) Onboarding for Development inc. Test Stubs | 100% | Fri 12/07/24 | Fri 12/07/24 | 1 day | Fri 12/07/24 | Fri 12/07/24 | 1587FS+49 days | 1600 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Electralink |  | 5.27 | Yes
8 | 1.6.4.1.7.3.2.6 |  |  |  |  | DTN Onboarding for Development inc. Test Stubs | 100% | Mon 15/07/24 | Mon 15/07/24 | 1 day | Mon 15/07/24 | Mon 15/07/24 | 1599 |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, MHHSP, Avanade |  | 5.27 | Yes
6 | 1.6.4.1.7.4 |  |  |  |  | QTF Test Cases DBT Refinement, Execution and Results Validation, Defect Management, Error Handling | 0% | Wed 03/07/24 | Wed 01/01/25 | 131 days | Mon 15/07/24 | Thu 31/10/24 | 1562FF,1568FF,1574FF,1579FF,1584FF+10 days | 1620 | -8 days | 44 days | 52 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
6 | 1.6.4.1.7.5 |  |  |  |  | Environments | 49% | Mon 15/04/24 | Tue 21/01/25 | 202 days | Mon 15/04/24 | Wed 20/11/24 |  |  | 0 days | 44 days | 44 days | N/A |  | 5.27 | Yes
7 | 1.6.4.1.7.5.1 |  |  |  |  | Azure Devops | 42% | Mon 15/04/24 | Fri 27/09/24 | 120 days | Mon 15/04/24 | Fri 27/09/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.5.1.1 |  |  |  |  | QFT ADO Development Instance | 100% | Mon 15/04/24 | Fri 03/05/24 | 15 days | Mon 15/04/24 | Fri 03/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
9 | 1.6.4.1.7.5.1.1.1 |  |  |  |  | Elexon Instance Setup for QTF Build | 100% | Mon 15/04/24 | Fri 19/04/24 | 5 days | Mon 15/04/24 | Fri 19/04/24 | 1587SS+10 days | 1606 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
9 | 1.6.4.1.7.5.1.1.2 |  |  |  |  | Configuration and User Access | 100% | Mon 22/04/24 | Fri 03/05/24 | 10 days | Mon 22/04/24 | Fri 03/05/24 | 1605 | 1612 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.1.2 |  |  |  |  | MHHSP ADO Instance | 24% | Tue 23/07/24 | Fri 27/09/24 | 49 days | Mon 22/07/24 | Fri 27/09/24 |  |  | 1 day | 0 days | -1 day | N/A |  | 5.27 | Yes
9 | 1.6.4.1.7.5.1.2.1 |  |  |  |  | MHHSP Instance Setup for QTF Production | 41% | Tue 23/07/24 | Fri 30/08/24 | 29 days | Mon 22/07/24 | Fri 30/08/24 | 1614SS+41 days | 1609 | 1 day | 0 days | -1 day | MHHSP |  | 5.27 | Yes
9 | 1.6.4.1.7.5.1.2.2 |  |  |  |  | Configuration and User Access | 0% | Mon 02/09/24 | Fri 27/09/24 | 20 days | Mon 02/09/24 | Fri 27/09/24 | 16081665 | 1692 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.5.2 |  |  |  |  | Temporary Development Environment | 100% | Mon 15/04/24 | Fri 31/05/24 | 35 days | Mon 15/04/24 | Fri 31/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.5.2.1 |  |  |  |  | Design | 100% | Mon 15/04/24 | Fri 03/05/24 | 15 days | Mon 15/04/24 | Fri 03/05/24 | 1587SS+10 days | 1612,1625,1630FS+10 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.2.2 |  |  |  |  | Build and Deployment | 100% | Mon 06/05/24 | Fri 31/05/24 | 20 days | Mon 06/05/24 | Fri 31/05/24 | 16061611 |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.5.3 |  |  |  |  | Dev, Test & Prod Environment Requirements + Design | 58% | Mon 27/05/24 | Fri 18/10/24 | 105 days | Mon 27/05/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.5.3.1 |  |  |  |  | Design (including Security Review) | 76% | Mon 27/05/24 | Fri 30/08/24 | 70 days | Mon 27/05/24 | Fri 30/08/24 | 1587FS+15 days | 1608SS+41 days,1615SS+10 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.3.2 |  |  |  |  | Hub Deployment | 100% | Mon 10/06/24 | Fri 05/07/24 | 20 days | Mon 10/06/24 | Fri 05/07/24 | 1614SS+10 days | 1616 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.3.3 |  |  |  |  | Development Envn. Deployment | 58% | Mon 08/07/24 | Fri 30/08/24 | 40 days | Mon 08/07/24 | Fri 30/08/24 | 1615 | 1617 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.3.4 |  |  |  |  | Test Envn. Deployment | 0% | Mon 02/09/24 | Fri 13/09/24 | 10 days | Mon 02/09/24 | Fri 13/09/24 | 1616 | 1618 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.3.5 |  |  |  |  | Production Envn. Deployment | 0% | Mon 16/09/24 | Fri 18/10/24 | 25 days | Mon 16/09/24 | Fri 18/10/24 | 1617 | 1620 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.5.4 |  |  |  |  | QTF Deployment into Production | 0% | Thu 02/01/25 | Tue 21/01/25 | 14 days | Fri 01/11/24 | Wed 20/11/24 |  |  | 44 days | 44 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.5.4.1 |  |  |  |  | App Deployment | 0% | Thu 02/01/25 | Thu 02/01/25 | 1 day | Fri 01/11/24 | Fri 01/11/24 | 16011618 | 1621SS | 44 days | 44 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.4.2 |  |  |  |  | Smoke Test | 0% | Thu 02/01/25 | Fri 03/01/25 | 2 days | Fri 01/11/24 | Mon 04/11/24 | 1620SS | 1622 | 44 days | 44 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.4.3 |  |  |  |  | PEN Test | 0% | Mon 06/01/25 | Tue 07/01/25 | 2 days | Tue 05/11/24 | Wed 06/11/24 | 1621 | 1623 | 44 days | 44 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.4.4 |  |  |  |  | Regresssion Test | 0% | Wed 08/01/25 | Tue 21/01/25 | 10 days | Thu 07/11/24 | Wed 20/11/24 | 1622 |  | 44 days | 44 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.5.5 |  |  |  |  | DIP Onboarding (UIT) | 0% | Mon 05/08/24 | Tue 24/09/24 | 37 days | Mon 05/08/24 | Tue 24/09/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.5.5.1 |  |  |  |  | DIP available for Onboarding | 0% | Mon 05/08/24 | Mon 05/08/24 | 1 day | Mon 05/08/24 | Mon 05/08/24 | 1611 | 1626 | 0 days | 0 days | 0 days | MHHSP, Avanade |  | 5.27 | Yes
8 | 1.6.4.1.7.5.5.2 |  |  |  |  | Qualification Testing for Non-SIT S&A Participants' environments) Ready to start DIP onboarding (incl. certificates and security compliance) | 0% | Tue 06/08/24 | Mon 26/08/24 | 15 days | Tue 06/08/24 | Mon 26/08/24 | 1625 | 1627 | 0 days | 0 days | 0 days | MHHSP, Avanade |  | 5.27 | Yes
8 | 1.6.4.1.7.5.5.3 |  |  |  |  | Non-SIT S&A QTF Environments Connection Confirmed to UIT Environment | 0% | Tue 27/08/24 | Tue 27/08/24 | 1 day | Tue 27/08/24 | Tue 27/08/24 | 1626 | 1628 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.5.4 |  |  |  |  | DIP UIT Test Stubs | 0% | Wed 28/08/24 | Tue 24/09/24 | 20 days | Wed 28/08/24 | Tue 24/09/24 | 1627 |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.5.6 |  |  |  |  | DTN Onboarding | 47% | Mon 20/05/24 | Fri 27/09/24 | 95 days | Mon 20/05/24 | Fri 27/09/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.5.6.1 |  |  |  |  | DTN Request Raised for Onboarding | 100% | Mon 20/05/24 | Fri 21/06/24 | 25 days | Mon 20/05/24 | Fri 21/06/24 | 1611FS+10 days | 1631 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.5.6.2 |  |  |  |  | Setup, configuration of New Host and Test Flags | 100% | Mon 24/06/24 | Fri 28/06/24 | 5 days | Mon 24/06/24 | Fri 28/06/24 | 1630 | 1632FS+25 days | 0 days | 0 days | 0 days | Electralink |  | 5.27 | Yes
8 | 1.6.4.1.7.5.6.3 |  |  |  |  | New VPN Connection | 10% | Mon 05/08/24 | Fri 13/09/24 | 30 days | Mon 05/08/24 | Fri 13/09/24 | 1631FS+25 days | 1633 | 0 days | 0 days | 0 days | QT Test Team |  | 5.3 | Yes
8 | 1.6.4.1.7.5.6.4 |  |  |  |  | DTN Test Stubs | 0% | Mon 16/09/24 | Fri 27/09/24 | 10 days | Mon 16/09/24 | Fri 27/09/24 | 1632 |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
6 | 1.6.4.1.7.6 |  |  |  |  | Test Data (MPANs, DIP Messages, Settlement, Consumption, Reference) | 14% | Mon 10/06/24 | Wed 07/01/26 | 413 days | Mon 10/06/24 | Thu 31/07/25 |  |  | 0 days | 114 days | 114 days | N/A |  | 5.27 | Yes
7 | 1.6.4.1.7.6.1 |  |  |  |  | Sample MPAN Data + Attributes from Suppliers | 100% | Mon 10/06/24 | Fri 28/06/24 | 15 days | Mon 10/06/24 | Fri 28/06/24 | 1543 | 1636FF+25 days | 0 days | 0 days | 0 days | Participants |  | 5.27 | Yes
7 | 1.6.4.1.7.6.2 |  |  |  |  | Test Data Templates and generator tools ready | 93% | Mon 24/06/24 | Fri 02/08/24 | 30 days | Mon 24/06/24 | Fri 02/08/24 | 1596SS+20 days,1635FF+25 days |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.6.3 |  |  |  |  | Industry Standing Data (ISD) | 6% | Fri 26/07/24 | Tue 10/09/24 | 33 days | Fri 26/07/24 | Tue 10/09/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.6.3.1 |  |  |  |  | Dependant on Receiving ISD Agreed Source Data from Helix | 100% | Fri 26/07/24 | Fri 26/07/24 | 1 day | Fri 26/07/24 | Fri 26/07/24 |  | 1639 | 0 days | 0 days | 0 days | Helix |  | 5.27 | Yes
8 | 1.6.4.1.7.6.3.2 |  |  |  |  | First View of Migrated ISD Data | 0% | Mon 19/08/24 | Mon 19/08/24 | 1 day | Mon 19/08/24 | Mon 19/08/24 | 1638 | 1640 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
8 | 1.6.4.1.7.6.3.3 |  |  |  |  | Final Cycle 3 Migrated ISD Data | 0% | Tue 20/08/24 | Tue 20/08/24 | 1 day | Tue 20/08/24 | Tue 20/08/24 | 1639 | 1641 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
8 | 1.6.4.1.7.6.3.4 |  |  |  |  | Create ISD Template inc. DIP ID | 0% | Wed 21/08/24 | Tue 27/08/24 | 5 days | Wed 21/08/24 | Tue 27/08/24 | 1640 | 1642 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.6.3.5 |  |  |  |  | Publish Qualification ISD | 0% | Wed 28/08/24 | Tue 10/09/24 | 10 days | Wed 28/08/24 | Tue 10/09/24 | 1641 |  | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.6.4 |  |  |  |  | Wave 1 Test Data | 0% | Mon 12/05/25 | Mon 14/07/25 | 46 days | Fri 29/11/24 | Fri 31/01/25 |  |  | 116 days | 116 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.6.4.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | Mon 12/05/25 | Mon 02/06/25 | 16 days | Fri 29/11/24 | Fri 20/12/24 | 1687 | 1645 | 116 days | 116 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.4.2 |  |  |  |  | Test Data Generated | 0% | Tue 03/06/25 | Mon 16/06/25 | 10 days | Mon 23/12/24 | Fri 03/01/25 | 1644 | 16461647 | 116 days | 116 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.6.4.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | Tue 17/06/25 | Mon 14/07/25 | 20 days | Mon 06/01/25 | Fri 31/01/25 | 1645 | 1695 | 116 days | 116 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.4.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | Tue 17/06/25 | Mon 14/07/25 | 20 days | Mon 06/01/25 | Fri 31/01/25 | 1645 | 1695 | 116 days | 116 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.6.5 |  |  |  |  | Wave 2 Test Data | 0% | Mon 07/07/25 | Tue 02/09/25 | 42 days | Fri 31/01/25 | Mon 31/03/25 |  |  | 111 days | 111 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.6.5.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | Mon 07/07/25 | Mon 28/07/25 | 16 days | Fri 31/01/25 | Fri 21/02/25 | 1717 | 1650 | 111 days | 111 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.5.2 |  |  |  |  | Test Data Generated | 0% | Tue 29/07/25 | Mon 11/08/25 | 10 days | Mon 24/02/25 | Fri 07/03/25 | 1649 | 16511652 | 111 days | 111 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.6.5.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | Tue 12/08/25 | Tue 02/09/25 | 16 days | Mon 10/03/25 | Mon 31/03/25 | 1650 | 1725 | 111 days | 111 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.5.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | Tue 12/08/25 | Tue 02/09/25 | 16 days | Mon 10/03/25 | Mon 31/03/25 | 1650 | 1725 | 111 days | 111 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.6.6 |  |  |  |  | Wave 3 Test Data | 0% | Mon 08/09/25 | Fri 07/11/25 | 45 days | Mon 31/03/25 | Fri 30/05/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.6.6.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | Mon 08/09/25 | Fri 26/09/25 | 15 days | Mon 31/03/25 | Fri 18/04/25 | 1747 | 1655 | 115 days | 115 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.6.2 |  |  |  |  | Test Data Generated | 0% | Mon 29/09/25 | Fri 10/10/25 | 10 days | Mon 21/04/25 | Fri 02/05/25 | 1654 | 16561657 | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.6.6.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | Mon 13/10/25 | Fri 07/11/25 | 20 days | Mon 05/05/25 | Fri 30/05/25 | 1655 | 1755 | 115 days | 115 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.6.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | Mon 13/10/25 | Fri 07/11/25 | 20 days | Mon 05/05/25 | Fri 30/05/25 | 1655 | 1755 | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.6.7 |  |  |  |  | Wave 4 Test Data | 0% | Thu 06/11/25 | Wed 07/01/26 | 45 days | Fri 30/05/25 | Thu 31/07/25 |  |  | 114 days | 114 days | 0 days | N/A |  | 5.27 | Yes
8 | 1.6.4.1.7.6.7.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | Thu 06/11/25 | Wed 26/11/25 | 15 days | Fri 30/05/25 | Thu 19/06/25 | 1777 | 1660 | 114 days | 114 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.7.2 |  |  |  |  | Test Data Generated | 0% | Thu 27/11/25 | Wed 10/12/25 | 10 days | Fri 20/06/25 | Thu 03/07/25 | 1659 | 16611662 | 114 days | 114 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
8 | 1.6.4.1.7.6.7.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | Thu 11/12/25 | Wed 07/01/26 | 20 days | Fri 04/07/25 | Thu 31/07/25 | 1660 | 1785 | 114 days | 114 days | 0 days | Participants |  | 5.27 | Yes
8 | 1.6.4.1.7.6.7.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | Thu 11/12/25 | Wed 07/01/26 | 20 days | Fri 04/07/25 | Thu 31/07/25 | 1660 | 1785 | 114 days | 114 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
6 | 1.6.4.1.7.7 |  |  |  |  | Governance | 29% | Mon 01/07/24 | Fri 27/12/24 | 130 days | Mon 01/07/24 | Fri 27/12/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.27 | Yes
7 | 1.6.4.1.7.7.1 |  |  |  |  | Onboarding Strategy and Develop Training Requirements & Materials Inc. Day in the Life | 43% | Mon 01/07/24 | Fri 27/09/24 | 65 days | Mon 01/07/24 | Fri 27/09/24 | 1590 | 1665SS,1666SS+45 days | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.7.2 |  |  |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 62% | Mon 01/07/24 | Fri 30/08/24 | 45 days | Mon 01/07/24 | Fri 30/08/24 | 1664SS | 1609 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
7 | 1.6.4.1.7.7.3 |  |  |  |  | Knowledge Transfer, Training, Demonstrations, Documentation, Governance | 0% | Mon 02/09/24 | Fri 27/12/24 | 85 days | Mon 02/09/24 | Fri 27/12/24 | 1664SS+45 days | 1667 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.27 | Yes
6 | 1.6.4.1.7.8 |  | T3-QU-0117 | QAG |  | Qualification Testing Wave Readiness Confirmed | 0% | Fri 27/12/24 | Fri 27/12/24 | 0 days | Thu 23/01/25 | Thu 23/01/25 | 1666 | 1696 | -19 days | -19 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.6.4.1.8 |  |  |  |  | Wave Allocation | 100% | Tue 02/01/24 | Fri 28/06/24 | 129 days | Tue 02/01/24 | Fri 28/06/24 |  |  | 0 days | 1 day | 1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.1.8.1 |  |  |  |  | Draft Pre-Qualification Submission (PQS) document | 100% | Tue 02/01/24 | Mon 29/01/24 | 20 days | Tue 02/01/24 | Mon 29/01/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.8.2 |  |  |  |  | Publish PQS document | 100% | Wed 31/01/24 | Wed 31/01/24 | 1 day | Wed 31/01/24 | Wed 31/01/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.8.3 |  |  |  |  | PQS Submission window | 100% | Mon 05/02/24 | Fri 26/04/24 | 60 days | Mon 05/02/24 | Fri 26/04/24 |  | 16731672 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.8.4 |  | T3-QU-0118 | QAG |  | Pre-Qualification Submission and PIT Test Plan Deadline for Submission​ | 100% | Fri 26/04/24 | Fri 26/04/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 | 1671 | 1673 | 0 days | 0 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.8.5 |  |  |  |  | PQS Review by Code Bodies | 100% | Mon 29/04/24 | Fri 31/05/24 | 25 days | Mon 29/04/24 | Fri 31/05/24 | 16711672 | 1674 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.8.6 |  |  |  |  | Draft Wave Allocations | 100% | Mon 03/06/24 | Fri 21/06/24 | 15 days | Mon 03/06/24 | Fri 21/06/24 | 1673 | 1675FS+5 days | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.8.7 |  | T3-QU-0012 | QAG |  | Confirmation of participant Qualification Wave allocation | 100% | Fri 28/06/24 | Fri 28/06/24 | 0 days | Fri 28/06/24 | Fri 28/06/24 | 1674FS+5 days | 1678 | 1 day | 1 day | 0 days | Code Bodies |  | 5.28 | Yes
4 | 1.6.4.2 |  |  |  |  | Qualification Wave 1 | 0% | Fri 21/03/25 | Fri 20/02/26 | 240 days | Mon 14/10/24 | Fri 29/08/25 |  |  | 115 days | 126 days | 11 days | N/A |  | 5.24 | Yes
5 | 1.6.4.2.1 |  |  |  |  | Qualification Wave 1 QAD Prep | 0% | Fri 21/03/25 | Thu 10/07/25 | 79 days | Mon 14/10/24 | Fri 31/01/25 |  |  | 115 days | 114 days | -1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.2.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | Fri 21/03/25 | Fri 21/03/25 | 0 days | Mon 14/10/24 | Mon 14/10/24 | 1675,1495FS+120 days | 1679 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.1.2 |  |  |  |  | Qualification Wave 1 Participants Submit Initial QAD | 0% | Mon 24/03/25 | Thu 29/05/25 | 49 days | Mon 14/10/24 | Fri 20/12/24 | 1678 | 16811680 | 115 days | 114 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.2.1.3 |  | T3-QU-0094 | QAG |  | Qualification Wave 1 Participants have submitted their initial QAD | 0% | Thu 29/05/25 | Thu 29/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1679 | 1681 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.2.1.4 |  |  |  |  | Code Bodies review of Wave 1 Participants Initial QAD | 0% | Fri 30/05/25 | Thu 10/07/25 | 30 days | Mon 23/12/24 | Fri 31/01/25 | 16791680 | 16951682 | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.2.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Thu 10/07/25 | Thu 10/07/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1681 | 1695,1694FF | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.4.2.2 |  |  |  |  | Qualification Wave 1 Test Prep | 0% | Mon 14/04/25 | Fri 04/07/25 | 60 days | Fri 01/11/24 | Fri 24/01/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.2.2.1 |  | T3-QU-0017 | QAG |  | Confirmation from Qualification Wave 1 Participants that DIP onboarding has commenced | 0% | Mon 14/04/25 | Mon 14/04/25 | 0 days | Fri 01/11/24 | Fri 01/11/24 |  | 1685 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.2.2 |  |  |  |  | Qualification Wave 1 Participants DIP Onboarding Window | 0% | Mon 14/04/25 | Fri 30/05/25 | 35 days | Mon 04/11/24 | Fri 20/12/24 | 1684 | 1686 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.2.3 |  |  |  |  | Confirmation from Qualification Wave 1 Participants that DIP onboarding has completed | 0% | Fri 30/05/25 | Fri 30/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1685 | 1694 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.2.4 |  | T3-QU-0095 | QAG |  | Qualification Wave 1 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | Mon 12/05/25 | Mon 12/05/25 | 0 days | Fri 29/11/24 | Fri 29/11/24 |  | 16881644 | 116 days | 116 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.2.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | Mon 12/05/25 | Fri 30/05/25 | 15 days | Mon 02/12/24 | Fri 20/12/24 | 1687 | 1689 | 115 days | 115 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.2.2.6 |  | T3-QU-0016 | QAG |  | Qualification Test Plans for Wave 1 Participants approved | 0% | Fri 30/05/25 | Fri 30/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 1688 | 1694 | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.2.2.7 |  | T3-QU-0096 | QAG |  | Qualification Wave 1 Participants have submitted PIT Test Completion Report and evidence for QT Entry | 0% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 |  | 1691 | 115 days | 115 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.2.2.8 |  |  |  |  | Review of Participants PIT Test Completion Report | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Mon 23/12/24 | Fri 24/01/25 | 1690 | 1692SS,1694 | 115 days | 115 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.2.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | Mon 02/06/25 | Fri 04/07/25 | 25 days | Mon 23/12/24 | Fri 24/01/25 | 1691SS,1609 | 1696 | 115 days | 115 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.6.4.2.3 |  |  |  |  | Qualification Wave 1 QT Execution | 0% | Mon 07/07/25 | Mon 24/11/25 | 101 days | Mon 27/01/25 | Fri 13/06/25 |  |  | 115 days | 116 days | 1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.2.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 1 Participant | 0% | Mon 07/07/25 | Fri 11/07/25 | 5 days | Mon 27/01/25 | Fri 31/01/25 | 1682FF,1686,1689,1691 | 1695FF | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.2.3.2 |  | T3-QU-0027 | QAG |  | Qualification Wave 1 Participant Test Readiness Confirmed | 0% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1681,1682,1694FF,1646,1647 | 1696 | 116 days | 116 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.2.3.3 |  | T3-QU-0028 | QAG |  | Qualification Wave 1 QT Execution Start | 0% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 03/02/25 | Mon 03/02/25 | 1695166716921120 | 16971700 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes |  | 16/09/24 - Date updated to 14/07/25, in line with recalibration planning.
6 | 1.6.4.2.3.4 |  |  |  |  | Qualification Wave 1 QT Execution Window | 0% | Mon 14/07/25 | Mon 24/11/25 | 95 days | Mon 03/02/25 | Fri 13/06/25 | 1696 | 1698 | 116 days | 116 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.3.5 |  | T3-QU-0054 | QAG |  | Qualification Wave 1 QT Projected Execution End | 0% | Mon 24/11/25 | Mon 24/11/25 | 0 days | Fri 13/06/25 | Fri 13/06/25 | 1697 | 1702 | 116 days | 116 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.4.2.4 |  |  |  |  | Qualification Wave 1 Exit | 0% | Mon 14/07/25 | Fri 20/02/26 | 159 days | Mon 03/02/25 | Fri 29/08/25 |  |  | 116 days | 126 days | 10 days | N/A |  | 5.24 | Yes
6 | 1.6.4.2.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | Mon 14/07/25 | Mon 14/07/25 | 0 days | Mon 03/02/25 | Mon 03/02/25 | 1696 | 1701 | 116 days | 116 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.4.2 |  |  |  |  | Qualification Wave 1 Participants submit their Final QAD | 0% | Tue 15/07/25 | Fri 28/11/25 | 99 days | Mon 03/02/25 | Fri 20/06/25 | 1700 | 17031702 | 116 days | 115 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.2.4.3 |  | T3-QU-0097 | QAG |  | Qualification Wave 1 Participants have submitted their final QAD | 0% | Fri 28/11/25 | Fri 28/11/25 | 0 days | Fri 20/06/25 | Fri 20/06/25 | 17011698 | 1703 | 115 days | 115 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.2.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Mon 01/12/25 | Fri 09/01/26 | 30 days | Mon 23/06/25 | Fri 18/07/25 | 17011702 | 1704FS+8 days | 115 days | 125 days | 10 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.2.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | Thu 22/01/26 | Thu 22/01/26 | 1 day | Thu 31/07/25 | Thu 31/07/25 | 1703FS+8 days | 1705FS+21 days | 125 days | 125 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.2.4.6 |  | T2-QU-0150 | QAG |  | Qualification Wave 1 Participants Qualification approved by BSC PAB and REC Manager | 0% | Fri 20/02/26 | Fri 20/02/26 | 0 days | Fri 29/08/25 | Fri 29/08/25 | 1704FS+21 days | 2259 | 126 days | 126 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.6.4.3 |  |  |  |  | Qualification Wave 2 | 0% | Fri 25/04/25 | Thu 09/04/26 | 249 days | Mon 18/11/24 | Fri 31/10/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.6.4.3.1 |  |  |  |  | Qualification Wave 2 QAD Prep | 0% | Fri 25/04/25 | Fri 05/09/25 | 95 days | Mon 18/11/24 | Mon 31/03/25 |  |  | 115 days | 114 days | -1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.3.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Mon 18/11/24 | Mon 18/11/24 | 1496FS+120 days | 1709 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.3.1.2 |  |  |  |  | Qualification Wave 2 Participants Submit Initial QAD | 0% | Mon 28/04/25 | Thu 31/07/25 | 69 days | Mon 18/11/24 | Fri 21/02/25 | 1708 | 1710 | 115 days | 114 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.3.1.3 |  | T3-QU-0098 | QAG |  | Qualification Wave 2 Participants have submitted their initial QAD | 0% | Thu 31/07/25 | Thu 31/07/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1709 | 1711 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.3.1.4 |  |  |  |  | Code Bodies review of Wave 2 Participants' Initial QAD | 0% | Fri 01/08/25 | Fri 05/09/25 | 26 days | Mon 24/02/25 | Mon 31/03/25 | 1710 | 1712 | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.3.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 1711 | 1724FF,1725 | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.4.3.2 |  |  |  |  | Qualification Wave 2 Test Prep | 0% | Mon 09/06/25 | Fri 29/08/25 | 60 days | Mon 06/01/25 | Fri 28/03/25 |  |  | 110 days | 110 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.3.2.1 |  | T3-QU-0021 | QAG |  | Confirmation from Qualification Wave 2 Participants that DIP Onboarding has commenced | 0% | Mon 09/06/25 | Mon 09/06/25 | 0 days | Mon 06/01/25 | Mon 06/01/25 |  | 1715 | 110 days | 110 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.3.2.2 |  |  |  |  | Qualification Wave 2 Participants DIP Onboarding Window | 0% | Mon 09/06/25 | Fri 25/07/25 | 35 days | Mon 06/01/25 | Fri 28/02/25 | 1714 | 1716 | 110 days | 105 days | -5 days | Participants |  | 5.24 | Yes
6 | 1.6.4.3.2.3 |  |  |  |  | Confirmation from Qualificiation Wave 2 Participants that DIP onboarding has completed | 0% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 28/02/25 | Fri 28/02/25 | 1715 | 1724 | 105 days | 105 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.3.2.4 |  | T3-QU-0099 | QAG |  | Qualification Wave 2 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | Mon 07/07/25 | Mon 07/07/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 |  | 17181649 | 111 days | 111 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.3.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | Mon 07/07/25 | Fri 25/07/25 | 15 days | Mon 03/02/25 | Fri 21/02/25 | 1717 | 1719 | 110 days | 110 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.3.2.6 |  | T3-QU-0020 | QAG |  | Qualification Test Plans for Wave 2 Participants approved | 0% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1718 | 1724 | 110 days | 110 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.3.2.7 |  | T3-QU-0100 | QAG |  | Qualification Wave 2 Participants have submitted PIT Test Completion Report and evidence for QT entry | 0% | Mon 28/07/25 | Mon 28/07/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 |  | 1721 | 111 days | 111 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.3.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | Mon 28/07/25 | Fri 29/08/25 | 25 days | Mon 24/02/25 | Fri 28/03/25 | 1720 | 1722SS,1724 | 110 days | 110 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.3.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | Mon 28/07/25 | Fri 29/08/25 | 25 days | Mon 24/02/25 | Fri 28/03/25 | 1721SS | 1726 | 110 days | 110 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.6.4.3.3 |  |  |  |  | Qualification Wave 2 QT Execution | 0% | Mon 01/09/25 | Wed 14/01/26 | 98 days | Tue 25/03/25 | Fri 08/08/25 |  |  | 114 days | 113 days | -1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.3.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 2 Participant | 0% | Mon 01/09/25 | Fri 05/09/25 | 5 days | Tue 25/03/25 | Mon 31/03/25 | 1712FF,1716,1719,1721 | 1725FS+1 day | 114 days | 114 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.3.3.2 |  | T3-QU-0033 | QAG |  | Qualification Wave 2 Participant Test Readiness Confirmed | 0% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 1724FS+1 day,1712,1651,1652 | 1726 | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.3.3.3 |  | T3-QU-0034 | QAG |  | Qualification Wave 2 Execution Start | 0% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Tue 01/04/25 | Tue 01/04/25 | 17251722 | 1727SS-1 day,1730 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes |  | 6/8/24: Date at risk from scenario planning activity
6 | 1.6.4.3.3.4 |  |  |  |  | Qualification Wave 2 QT Execution Window | 0% | Mon 08/09/25 | Wed 14/01/26 | 93 days | Tue 01/04/25 | Fri 08/08/25 | 1726SS-1 day | 1728 | 114 days | 113 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.3.3.5 |  | T3-QU-0055 | QAG |  | Qualfication Wave 2 QT Execution End | 0% | Wed 14/01/26 | Wed 14/01/26 | 0 days | Fri 08/08/25 | Fri 08/08/25 | 1727 | 1732 | 113 days | 113 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.4.3.4 |  |  |  |  | Qualification Wave 2 Exit | 0% | Mon 08/09/25 | Thu 09/04/26 | 153 days | Tue 01/04/25 | Fri 31/10/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.3.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Tue 01/04/25 | Tue 01/04/25 | 1726 | 1731 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.3.4.2 |  |  |  |  | Qualification Wave 2 Participants submit their Final QAD | 0% | Tue 09/09/25 | Thu 22/01/26 | 98 days | Tue 01/04/25 | Fri 15/08/25 | 1730 | 1732 | 115 days | 114 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.3.4.3 |  | T3-QU-0101 | QAG |  | Qualification Wave 2 Participants have submitted their final QAD | 0% | Thu 22/01/26 | Thu 22/01/26 | 0 days | Fri 15/08/25 | Fri 15/08/25 | 17311728 | 1733 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.3.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Fri 23/01/26 | Mon 02/03/26 | 27 days | Mon 18/08/25 | Tue 23/09/25 | 1732 | 1734FS+4 days | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.3.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | Mon 09/03/26 | Mon 09/03/26 | 1 day | Tue 30/09/25 | Tue 30/09/25 | 1733FS+4 days | 1735FS+23 days | 114 days | 114 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.3.4.6 |  | T2-QU-0200 | QAG |  | Qualification Wave 2 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 09/04/26 | Thu 09/04/26 | 0 days | Fri 31/10/25 | Fri 31/10/25 | 1734FS+23 days | 2283 | 115 days | 115 days | 0 days | Code Bodies |  | 5.24 | Yes |  | 14/5: Baseline and name updated after cr48 approval at psg on 1/5
4 | 1.6.4.4 |  |  |  |  | Qualification Wave 3 | 0% | Fri 27/06/25 | Thu 28/05/26 | 239 days | Mon 20/01/25 | Fri 19/12/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.6.4.4.1 |  |  |  |  | Qualification Wave 3 QAD Prep | 0% | Fri 27/06/25 | Thu 06/11/25 | 94 days | Mon 20/01/25 | Fri 30/05/25 |  |  | 115 days | 114 days | -1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.4.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | Fri 27/06/25 | Fri 27/06/25 | 0 days | Mon 20/01/25 | Mon 20/01/25 | 1497FS+120 days | 1739 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.4.1.2 |  |  |  |  | Qualification Wave 3 Participants Submit Initial QAD | 0% | Mon 30/06/25 | Thu 25/09/25 | 64 days | Mon 20/01/25 | Fri 18/04/25 | 1738 | 1740 | 115 days | 114 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.4.1.3 |  | T3-QU-0102 | QAG |  | Qualification Wave 3 Participants have submitted their initial QAD | 0% | Thu 25/09/25 | Thu 25/09/25 | 0 days | Fri 18/04/25 | Fri 18/04/25 | 1739 | 1741 | 115 days | 115 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.4.1.4 |  |  |  |  | Code Bodies review of Wave 3 Participants' Initial QAD | 0% | Fri 26/09/25 | Thu 06/11/25 | 30 days | Mon 21/04/25 | Fri 30/05/25 | 1740 | 1742 | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.4.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Thu 06/11/25 | Thu 06/11/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1741 | 1754FF | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.4.4.2 |  |  |  |  | Qualification Wave 3 Test Prep | 0% | Mon 04/08/25 | Fri 31/10/25 | 65 days | Mon 03/03/25 | Fri 30/05/25 |  |  | 110 days | 110 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.4.2.1 |  | T3-QU-0025 | QAG |  | Qualification Wave 3 Participants' have started DIP Onboarding | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 03/03/25 | Mon 03/03/25 |  | 1745 | 110 days | 110 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.4.2.2 |  |  |  |  | Qualification Wave 3 Participants DIP Onboarding window | 0% | Mon 04/08/25 | Fri 19/09/25 | 35 days | Mon 03/03/25 | Fri 25/04/25 | 1744 | 1746 | 110 days | 105 days | -5 days | Participants |  | 5.24 | Yes
6 | 1.6.4.4.2.3 |  |  |  |  | Confirmation from Qualification Wave 3 Participants that DIP onboarding has completed | 0% | Mon 22/09/25 | Mon 22/09/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1745 | 17551754 | 105 days | 105 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.4.2.4 |  | T3-QU-0103 | QAG |  | Qualification Wave 3 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | Mon 08/09/25 | Mon 08/09/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 |  | 17481654 | 115 days | 115 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.4.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | Mon 08/09/25 | Fri 26/09/25 | 15 days | Mon 31/03/25 | Fri 18/04/25 | 1747 | 1749 | 115 days | 115 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.4.2.6 |  | T3-QU-0024 | QAG |  | Qualification Test Plans for Wave 3 Participants approved | 0% | Fri 26/09/25 | Fri 26/09/25 | 0 days | Fri 18/04/25 | Fri 18/04/25 | 1748 |  | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.4.2.7 |  | T3-QU-0104 | QAG |  | Qualification Wave 3 Participants have submitted PIT Test Completion Report and evidence for QT Entry | 0% | Mon 29/09/25 | Mon 29/09/25 | 0 days | Fri 18/04/25 | Fri 18/04/25 |  | 1751 | 116 days | 116 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.4.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | Mon 29/09/25 | Fri 31/10/25 | 25 days | Mon 21/04/25 | Fri 30/05/25 | 1750 | 1752SS | 115 days | 110 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.4.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | Mon 29/09/25 | Fri 31/10/25 | 25 days | Mon 21/04/25 | Fri 30/05/25 | 1751SS | 17561754 | 115 days | 110 days | -5 days |  |  | 5.24 | Yes
5 | 1.6.4.4.3 |  |  |  |  | Qualification Wave 3 QT Execution | 0% | Mon 03/11/25 | Tue 24/03/26 | 102 days | Mon 26/05/25 | Fri 10/10/25 |  |  | 115 days | 117 days | 2 days | N/A |  | 5.24 | Yes
6 | 1.6.4.4.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 3 Participant | 0% | Mon 03/11/25 | Fri 07/11/25 | 5 days | Mon 26/05/25 | Fri 30/05/25 | 1746,1742FF,1752 | 17571755 | 115 days | 115 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.4.3.2 |  | T3-QU-0038 | QAG |  | Qualification Wave 3 Participant Test Readiness confirmed | 0% | Mon 10/11/25 | Mon 10/11/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1746175416561650 | 1756 | 116 days | 116 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.4.3.3 |  | T3-QU-0039 | QAG |  | Qualification Wave 3 Execution Start | 0% | Mon 10/11/25 | Mon 10/11/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 17551752 | 17571760 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes |  | 6/8/24: Date at risk from scenario planning activity
6 | 1.6.4.4.3.4 |  |  |  |  | Qualification Wave 3 QT Execution Window | 0% | Mon 10/11/25 | Mon 23/03/26 | 96 days | Mon 02/06/25 | Fri 10/10/25 | 17541756 | 1758 | 115 days | 116 days | 1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.4.3.5 |  | T3-QU-0056 | QAG |  | Qualification Wave 3 Projected Execution End | 0% | Mon 23/03/26 | Mon 23/03/26 | 0 days | Fri 10/10/25 | Fri 10/10/25 | 1757 | 1762 | 116 days | 116 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.4.4.4 |  |  |  |  | Qualification Wave 3 Exit | 0% | Mon 10/11/25 | Thu 28/05/26 | 144 days | Mon 02/06/25 | Fri 19/12/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.4.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | Mon 10/11/25 | Mon 10/11/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 1756 | 1761 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.4.4.2 |  |  |  |  | Qualification Wave 3 Participants submit their Final QAD | 0% | Mon 10/11/25 | Thu 26/03/26 | 99 days | Mon 02/06/25 | Fri 17/10/25 | 1760 | 1762 | 115 days | 114 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.4.4.3 |  | T3-QU-0105 | QAG |  | Qualification Wave 3 Participants have submitted their Final QAD | 0% | Thu 26/03/26 | Thu 26/03/26 | 0 days | Fri 17/10/25 | Fri 17/10/25 | 17611758 | 1763 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.4.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Fri 27/03/26 | Thu 23/04/26 | 20 days | Mon 20/10/25 | Fri 14/11/25 | 1762 | 1764FS+4 days | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.4.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | Thu 30/04/26 | Thu 30/04/26 | 1 day | Fri 21/11/25 | Fri 21/11/25 | 1763FS+4 days | 1765FS+20 days | 114 days | 114 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.4.4.6 |  | T2-QU-0250 | QAG |  | Qualification Wave 3 Participants Qualification approved by BSC PAB and REC Manager | 0% | Thu 28/05/26 | Thu 28/05/26 | 0 days | Fri 19/12/25 | Fri 19/12/25 | 1764FS+20 days | 2307 | 115 days | 115 days | 0 days | Code Bodies |  | 5.24 | Yes |  | 14/5: Baseline and name updated after cr48 approval at psg on 1/5
4 | 1.6.4.5 |  |  |  |  | Qualification Wave 4 | 0% | Fri 22/08/25 | Tue 08/12/26 | 337 days | Mon 17/03/25 | Fri 27/02/26 |  |  | 115 days | 203 days | 88 days | N/A |  | 5.24 | Yes
5 | 1.6.4.5.1 |  |  |  |  | Qualification Wave 4 QAD Prep | 0% | Fri 22/08/25 | Wed 07/01/26 | 98 days | Mon 17/03/25 | Thu 31/07/25 |  |  | 115 days | 114 days | -1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.5.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | Fri 22/08/25 | Fri 22/08/25 | 0 days | Mon 17/03/25 | Mon 17/03/25 | 1498FS+120 days | 1769 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.5.1.2 |  |  |  |  | Qualification Wave 4 Participants Submit Initial QAD | 0% | Mon 25/08/25 | Thu 27/11/25 | 69 days | Mon 17/03/25 | Fri 20/06/25 | 1768 | 1770 | 115 days | 114 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.5.1.3 |  | T3-QU-0106 | QAG |  | Qualification Wave 4 Participants have submitted their Initial QAD | 0% | Thu 27/11/25 | Thu 27/11/25 | 0 days | Fri 20/06/25 | Fri 20/06/25 | 1769 | 1771 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.5.1.4 |  |  |  |  | Code Bodies review of Wave 4 Participants' Initial QAD | 0% | Fri 28/11/25 | Wed 07/01/26 | 29 days | Mon 23/06/25 | Thu 31/07/25 | 1770 | 1772 | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.5.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | Wed 07/01/26 | Wed 07/01/26 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 1771 | 1784FF | 114 days | 114 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.4.5.2 |  |  |  |  | Qualification Wave 4 Test Prep | 0% | Mon 06/10/25 | Fri 19/12/25 | 55 days | Thu 01/05/25 | Fri 01/08/25 |  |  | 112 days | 100 days | -12 days | N/A |  | 5.24 | Yes
6 | 1.6.4.5.2.1 |  | T3-QU-0031 | QAG |  | Confirmation from Qualification 4 Participants that DIP Onboarding has commenced | 0% | Mon 06/10/25 | Mon 06/10/25 | 0 days | Thu 01/05/25 | Thu 01/05/25 |  | 1775 | 112 days | 112 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.5.2.2 |  |  |  |  | Qualification Wave 4 Participants DIP Onboarding Window | 0% | Mon 06/10/25 | Fri 21/11/25 | 35 days | Thu 01/05/25 | Fri 27/06/25 | 1774 | 1776 | 112 days | 105 days | -7 days | Participants |  | 5.24 | Yes
6 | 1.6.4.5.2.3 |  |  |  |  | Confirmation from Qualification Wave 4 Participants that DIP onboarding has completed | 0% | Fri 21/11/25 | Fri 21/11/25 | 0 days | Fri 27/06/25 | Fri 27/06/25 | 1775 | 17841785 | 105 days | 105 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.5.2.4 |  | T3-QU-0107 | QAG |  | Qualification Wave 4 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | Thu 06/11/25 | Thu 06/11/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 |  | 17781659 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.5.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | Thu 06/11/25 | Wed 26/11/25 | 15 days | Fri 30/05/25 | Fri 20/06/25 | 1777 | 1779 | 114 days | 113 days | -1 day | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.5.2.6 |  | T3-QU-0030 | QAG |  | Qualification Test Plans for Qualification Wave 4 Participants approved | 0% | Wed 26/11/25 | Wed 26/11/25 | 0 days | Fri 20/06/25 | Fri 20/06/25 | 1778 | 1780 | 113 days | 113 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.5.2.7 |  | T3-QU-0108 | QAG |  | Qualification Wave 4 Participants have submitted PIT Test Completion Report and evidence for QT entry | 0% | Thu 27/11/25 | Thu 27/11/25 | 0 days | Fri 20/06/25 | Fri 20/06/25 | 1779 | 1781 | 114 days | 114 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.5.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | Thu 27/11/25 | Fri 19/12/25 | 17 days | Fri 20/06/25 | Thu 31/07/25 | 1780 | 1782SS | 114 days | 101 days | -13 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.5.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | Thu 27/11/25 | Fri 19/12/25 | 17 days | Mon 23/06/25 | Fri 01/08/25 | 1781SS | 1786 | 113 days | 100 days | -13 days | Code Bodies, Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.6.4.5.3 |  |  |  |  | Qualification Wave 4 QT Execution | 0% | Mon 05/01/26 | Fri 22/05/26 | 100 days | Fri 25/07/25 | Fri 12/12/25 |  |  | 116 days | 115 days | -1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.5.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 4 Participant | 0% | Mon 05/01/26 | Fri 09/01/26 | 5 days | Fri 25/07/25 | Thu 31/07/25 | 1772FF,1776 | 17871785 | 116 days | 116 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.5.3.2 |  | T3-QU-0043 | QAG |  | Qualification Wave 4 Participant Test Readiness Confirmed | 0% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Thu 31/07/25 | Thu 31/07/25 | 1776178416611660 | 1786 | 117 days | 117 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.5.3.3 |  | T3-QU-0044 | QAG |  | Qualification Wave 4 QT Execution Start | 0% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Fri 01/08/25 | Fri 01/08/25 | 17851782 | 17871790 | 116 days | 116 days | 0 days | Participants |  | 5.24 | Yes |  | 6/8/24: Date at risk from scenario planning activity
6 | 1.6.4.5.3.4 |  |  |  |  | Qualification Wave 4 QT Execution Window | 0% | Mon 12/01/26 | Fri 22/05/26 | 95 days | Fri 01/08/25 | Fri 12/12/25 | 17861784 | 1788 | 116 days | 115 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.5.3.5 |  | T3-QU-0057 | QAG |  | Qualification Wave 4 Projected Execution End | 0% | Fri 22/05/26 | Fri 22/05/26 | 0 days | Fri 12/12/25 | Fri 12/12/25 | 1787 | 1792 | 115 days | 115 days | 0 days | Participants |  | 5.24 | Yes
5 | 1.6.4.5.4 |  |  |  |  | Qualification Wave 4 Exit | 0% | Mon 12/01/26 | Fri 31/07/26 | 145 days | Fri 01/08/25 | Fri 27/02/26 |  |  | 116 days | 111 days | -5 days | N/A |  | 5.24 | Yes
6 | 1.6.4.5.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Fri 01/08/25 | Fri 01/08/25 | 1786 | 1791 | 116 days | 116 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.5.4.2 |  |  |  |  | Qualification Wave 4 Participants submit their Final QAD | 0% | Mon 12/01/26 | Fri 29/05/26 | 100 days | Fri 01/08/25 | Fri 19/12/25 | 1790 | 1792 | 116 days | 115 days | -1 day | Participants |  | 5.24 | Yes
6 | 1.6.4.5.4.3 |  | T3-QU-0109 | QAG |  | Qualification Wave 4 Participants have submitted their Final QAD | 0% | Fri 29/05/26 | Fri 29/05/26 | 0 days | Fri 19/12/25 | Fri 19/12/25 | 17911788 | 1793 | 115 days | 115 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.5.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | Mon 01/06/26 | Fri 26/06/26 | 20 days | Mon 22/12/25 | Fri 23/01/26 | 1792 | 1794FS+4 days | 115 days | 110 days | -5 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.5.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | Fri 03/07/26 | Fri 03/07/26 | 1 day | Fri 30/01/26 | Fri 30/01/26 | 1793FS+4 days | 1795FS+20 days | 110 days | 110 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.5.4.6 |  | T2-QU-0300 | QAG |  | Qualification Wave 4 Participants Qualification approved by BSC PAB and REC Manager | 0% | Fri 31/07/26 | Fri 31/07/26 | 0 days | Fri 27/02/26 | Fri 27/02/26 | 1794FS+20 days | 2331,1797FS+26 days | 111 days | 111 days | 0 days | Code Bodies |  | 5.24 | Yes |  | 14/5: Baseline and name updated after cr48 approval at psg on 1/5
5 | 1.6.4.5.5 |  |  |  |  | Qualification Tier 1 Milestone | 0% | Mon 07/09/26 | Tue 08/12/26 | 66 days | NA | NA |  |  | 0 days | 0 days | 66 days |  |  |  | Yes
6 | 1.6.4.5.5.1 | T1 | T1-MI-5000 | PSG |  | All suppliers must be able to access MPANs under the new TOM (M14) | 0% | Mon 07/09/26 | Mon 07/09/26 | 0 days | Mon 16/03/26 | Mon 16/03/26 | 1795FS+26 days | 2481FS-60 days,1798FS+66 days,2521FS-3 mons | 125 days | 125 days | 0 days | CPT |  | 5 | Yes
6 | 1.6.4.5.5.2 | T1 | T1-MI-5500 | PSG |  | All suppliers must be able to access MPANs under the new TOM (M14*) - Late Exit | 0% | Tue 08/12/26 | Tue 08/12/26 | 0 days | Tue 16/06/26 | Tue 16/06/26 | 1797FS+66 days |  | 125 days | 125 days | 0 days | CPT |  | 5 | Yes
2 | 1.7 |  |  |  |  | REGULATORY | 93% | Mon 31/10/22 | Wed 12/11/25 | 793 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 113 days | 113 days | N/A |  |  | Yes
3 | 1.7.1 |  |  |  |  | Baseline MHHS Code Changes | 100% | Mon 31/10/22 | Fri 23/08/24 | 475 days | Mon 31/10/22 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.7.1.1 |  |  |  |  | Preparation and planning | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.7.1.1.1 |  |  |  |  | Impact assessment of Programme design on codes to determine required changes | 100% | Mon 31/10/22 | Fri 25/11/22 | 20 days | Mon 31/10/22 | Fri 25/11/22 | 48 |  | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
5 | 1.7.1.1.2 |  |  |  |  | Become 'code draft ready' | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  |  | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
5 | 1.7.1.1.3 |  |  |  |  | Soft start drafting where possible | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  |  | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
4 | 1.7.1.2 |  |  |  |  | Code drafting | 100% | Mon 12/12/22 | Wed 21/08/24 | 443 days | Mon 12/12/22 | Fri 23/08/24 |  |  | 0 days | -2 days | -2 days | N/A |  | 5 | Yes
5 | 1.7.1.2.1 |  |  |  |  | Data Services (BSC driven) | 100% | Mon 12/12/22 | Wed 24/05/23 | 118 days | Mon 12/12/22 | Wed 24/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.1.1 |  |  |  |  | Pre Code Drafting activities | 100% | Mon 12/12/22 | Fri 16/12/22 | 5 days | Mon 12/12/22 | Fri 16/12/22 |  | 1808FS+11 days,1816SS | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.1.2 |  |  |  |  | Code and subsidiary document drafting takes place offline | 100% | Tue 03/01/23 | Fri 27/01/23 | 19 days | Tue 03/01/23 | Fri 27/01/23 | 1807FS+11 days | 1809 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.1.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Mon 30/01/23 | Mon 13/02/23 | 11 days | Mon 30/01/23 | Mon 13/02/23 | 1808 | 18101835 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.1.4 |  |  |  |  | External industry review via consultation | 100% | Tue 14/02/23 | Mon 13/03/23 | 20 days | Tue 14/02/23 | Mon 13/03/23 | 1809 | 1811FS-2 days,1826SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.1.5 |  |  |  |  | Triage and action comments | 100% | Fri 10/03/23 | Wed 05/04/23 | 19 days | Fri 10/03/23 | Wed 05/04/23 | 1810FS-2 days | 1812 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.1.6 |  |  |  |  | CDWG review | 100% | Thu 06/04/23 | Wed 17/05/23 | 30 days | Thu 06/04/23 | Wed 17/05/23 | 1811 | 1813 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.1.7 |  |  |  |  | CCAG review | 100% | Thu 18/05/23 | Wed 24/05/23 | 5 days | Thu 18/05/23 | Wed 24/05/23 | 1812 | 1814 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.1.8 | T2 | T2-RE-0100 | CCAG | MHHS-ART060 | Code drafting for Data Services topic area approved | 100% | Wed 24/05/23 | Wed 24/05/23 | 0 days | Wed 24/05/23 | Wed 24/05/23 | 1813 | 1903 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.2 |  |  |  |  | Metering (REC driven) | 100% | Mon 12/12/22 | Wed 24/05/23 | 118 days | Mon 12/12/22 | Wed 24/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.2.1 |  |  |  |  | Pre Code Drafting activities | 100% | Mon 12/12/22 | Fri 16/12/22 | 5 days | Mon 12/12/22 | Fri 16/12/22 | 1807SS | 1817FS+11 days | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.2.2 |  |  |  |  | Code and subsidiary document drafting takes place offline | 100% | Tue 03/01/23 | Fri 27/01/23 | 19 days | Tue 03/01/23 | Fri 27/01/23 | 1816FS+11 days | 1818 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.2.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Mon 30/01/23 | Mon 13/02/23 | 11 days | Mon 30/01/23 | Mon 13/02/23 | 1817 | 18191835 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.2.4 |  |  |  |  | External industry review via consultation | 100% | Tue 14/02/23 | Mon 13/03/23 | 20 days | Tue 14/02/23 | Mon 13/03/23 | 1818 | 1820FS-2 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.2.5 |  |  |  |  | Triage and action comments | 100% | Fri 10/03/23 | Wed 05/04/23 | 19 days | Fri 10/03/23 | Wed 05/04/23 | 1819FS-2 days | 1821 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.2.6 |  |  |  |  | CDWG review | 100% | Thu 06/04/23 | Wed 17/05/23 | 30 days | Thu 06/04/23 | Wed 17/05/23 | 1820 | 1822 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.2.7 |  |  |  |  | CCAG review | 100% | Thu 18/05/23 | Wed 24/05/23 | 5 days | Thu 18/05/23 | Wed 24/05/23 | 1821 | 1823 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.2.8 | T2 | T2-RE-0150 | CCAG | MHHS-ART060 | Code drafting for Metering topic area approved | 100% | Wed 24/05/23 | Wed 24/05/23 | 0 days | Wed 24/05/23 | Wed 24/05/23 | 1822 | 1903 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.3 |  |  |  |  | BSC Central Services (BSC driven) | 100% | Wed 22/02/23 | Wed 27/09/23 | 156 days | Wed 22/02/23 | Wed 27/09/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.3.1 |  |  |  |  | Pre Code Drafting activities | 100% | Wed 22/02/23 | Tue 28/02/23 | 5 days | Wed 22/02/23 | Tue 28/02/23 | 1826SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.3.2 |  |  |  |  | Code Drafting (offline) | 100% | Wed 01/03/23 | Tue 20/06/23 | 80 days | Wed 01/03/23 | Tue 20/06/23 | 1810SS | 1827SS+10 days,1825SS-5 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.3.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Wed 15/03/23 | Tue 20/06/23 | 70 days | Wed 15/03/23 | Tue 20/06/23 | 1826SS+10 days | 1828 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.3.4 |  |  |  |  | External industry review via consultation | 100% | Wed 21/06/23 | Tue 11/07/23 | 15 days | Wed 21/06/23 | Tue 11/07/23 | 1827 | 1829FS-2 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.3.5 |  |  |  |  | Triage and action comments | 100% | Mon 10/07/23 | Thu 03/08/23 | 19 days | Mon 10/07/23 | Thu 03/08/23 | 1828FS-2 days | 1830 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.3.6 |  |  |  |  | CDWG review | 100% | Fri 04/08/23 | Tue 12/09/23 | 28 days | Fri 04/08/23 | Tue 12/09/23 | 1829 | 1831 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.3.7 |  |  |  |  | CCAG review | 100% | Wed 13/09/23 | Wed 27/09/23 | 11 days | Wed 13/09/23 | Wed 27/09/23 | 1830 | 1832 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.3.8 | T2 | T2-RE-0200 | CCAG | MHHS-ART060 | Code drafting for BSC Central Services topic area approved | 100% | Wed 27/09/23 | Wed 27/09/23 | 0 days | Wed 27/09/23 | Wed 27/09/23 | 1831 | 1903 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.4 |  |  |  |  | Registration (BSC & REC driven) | 100% | Wed 22/02/23 | Wed 23/08/23 | 131 days | Wed 22/02/23 | Wed 23/08/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.4.1 |  |  |  |  | Pre Code Drafting activities | 100% | Wed 22/02/23 | Tue 28/02/23 | 5 days | Wed 22/02/23 | Tue 28/02/23 | 1835SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.4.2 |  |  |  |  | Code Drafting (offline) | 100% | Wed 01/03/23 | Tue 30/05/23 | 65 days | Wed 01/03/23 | Tue 30/05/23 | 18091818 | 1836SS+10 days,1834SS-5 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.4.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Wed 15/03/23 | Tue 30/05/23 | 55 days | Wed 15/03/23 | Tue 30/05/23 | 1835SS+10 days | 1837 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.4.4 |  |  |  |  | External industry review via consultation | 100% | Wed 31/05/23 | Tue 20/06/23 | 15 days | Wed 31/05/23 | Tue 20/06/23 | 1836 | 1838FS-2 days,1844SS+1 day,1853SS+1 day,1862SS+1 day | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.4.5 |  |  |  |  | Triage and action comments | 100% | Mon 19/06/23 | Thu 13/07/23 | 19 days | Mon 19/06/23 | Thu 13/07/23 | 1837FS-2 days | 1839 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.4.6 |  |  |  |  | CDWG review | 100% | Fri 14/07/23 | Tue 08/08/23 | 18 days | Fri 14/07/23 | Tue 08/08/23 | 1838 | 1840 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.4.7 |  |  |  |  | CCAG review | 100% | Wed 09/08/23 | Wed 23/08/23 | 11 days | Wed 09/08/23 | Wed 23/08/23 | 1839 | 1841 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.4.8 | T2 | T2-RE-0250 | CCAG | MHHS-ART060 | Code drafting for Registration topic area approved | 100% | Wed 23/08/23 | Wed 23/08/23 | 0 days | Wed 23/08/23 | Wed 23/08/23 | 1840 | 1903 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.5 |  |  |  |  | Governance and Qualification (BSC & REC driven) | 100% | Thu 25/05/23 | Wed 22/11/23 | 130 days | Thu 25/05/23 | Wed 22/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.5.1 |  |  |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 1844SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.5.2 |  |  |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Wed 16/08/23 | 55 days | Thu 01/06/23 | Wed 16/08/23 | 1837SS+1 day | 1845SS+10 days,1843SS-5 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.5.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Wed 16/08/23 | 45 days | Thu 15/06/23 | Wed 16/08/23 | 1844SS+10 days | 1846FS+1 day | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.5.4 |  |  |  |  | External industry review via consultation | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1845FS+1 day | 1847FS-2 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.5.5 |  |  |  |  | Triage and action comments | 100% | Wed 06/09/23 | Mon 02/10/23 | 19 days | Wed 06/09/23 | Mon 02/10/23 | 1846FS-2 days | 1848 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.5.6 |  |  |  |  | CDWG review | 100% | Tue 03/10/23 | Tue 14/11/23 | 31 days | Tue 03/10/23 | Tue 14/11/23 | 1847 | 1849 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.5.7 |  |  |  |  | CCAG review | 100% | Wed 15/11/23 | Wed 22/11/23 | 6 days | Wed 15/11/23 | Wed 22/11/23 | 1848 | 1850 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.5.8 | T2 | T3-RE-0300 | CCAG | MHHS-ART060 | Code drafting for Governance and Qualification topic areas approved | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1849 | 1903 | 0 days | 0 days | 0 days | PP |  | 5.12 | Yes |  | 10/10 - CH - Agreed at PSG on 4/10 to downgrade from T2 to T3
5 | 1.7.1.2.6 |  |  |  |  | Interfaces / Data Specification (REC driven) | 100% | Thu 25/05/23 | Tue 23/01/24 | 174 days | Thu 25/05/23 | Wed 24/01/24 |  |  | 0 days | -1 day | -1 day | N/A |  | 5.2 | Yes
6 | 1.7.1.2.6.1 |  |  |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 1853SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.6.2 |  |  |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Tue 10/10/23 | 94 days | Thu 01/06/23 | Tue 10/10/23 | 1837SS+1 day | 1852SS-5 days,1854SS+10 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.6.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Tue 10/10/23 | 84 days | Thu 15/06/23 | Tue 10/10/23 | 1853SS+10 days | 1855 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.6.4 |  |  |  |  | External industry review via consultation | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 1854 | 1856FS-2 days | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.6.5 |  |  |  |  | Triage and action comments | 100% | Mon 30/10/23 | Fri 24/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 1855FS-2 days | 1857 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.6.6 |  |  |  |  | CDWG review | 100% | Mon 27/11/23 | Tue 16/01/24 | 37 days | Mon 27/11/23 | Tue 09/01/24 | 1856 | 1858 | 0 days | 5 days | 5 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.6.7 |  |  |  |  | CCAG review | 100% | Wed 17/01/24 | Tue 23/01/24 | 5 days | Wed 10/01/24 | Wed 24/01/24 | 1857 | 1859 | 5 days | -1 day | -6 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.6.8 | T2 | T3-RE-0350 | CCAG | MHHS-ART060 | Code drafting for Interfaces / Data Specification topic areas approved | 100% | Tue 23/01/24 | Tue 23/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 | 1858 | 1903 | -1 day | -1 day | 0 days | PP |  | 5.16 | Yes |  | 10/10 - CH - Agreed at PSG on 4/10 to downgrade from T2 to T3
5 | 1.7.1.2.7 |  |  |  |  | Migration (BSC & REC driven) | 100% | Thu 25/05/23 | Wed 22/11/23 | 130 days | Thu 25/05/23 | Wed 22/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.7.1 |  |  |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 1862SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.7.2 |  |  |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Wed 16/08/23 | 55 days | Thu 01/06/23 | Wed 16/08/23 | 1837SS+1 day | 1861SS-5 days,1863SS+10 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.7.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Wed 16/08/23 | 45 days | Thu 15/06/23 | Wed 16/08/23 | 1862SS+10 days | 1864FS+1 day | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.7.4 |  |  |  |  | External industry review via consultation | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1863FS+1 day | 1865FS-2 days,1874SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.7.5 |  |  |  |  | Triage and action comments | 100% | Wed 06/09/23 | Mon 02/10/23 | 19 days | Wed 06/09/23 | Mon 02/10/23 | 1864FS-2 days | 1866 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.7.6 |  |  |  |  | CDWG review | 100% | Tue 03/10/23 | Tue 14/11/23 | 31 days | Tue 03/10/23 | Tue 14/11/23 | 1865 | 1867 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.7.7 |  |  |  |  | CCAG review | 100% | Wed 15/11/23 | Wed 22/11/23 | 6 days | Wed 15/11/23 | Wed 22/11/23 | 1866 | 1868 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.7.8 | T2 | T3-RE-0400 | CCAG | MHHS-ART060 | Code drafting for Migration topic area approved | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1867 | 1903 | 0 days | 0 days | 0 days | PP |  | 5.12 | Yes |  | 31/07/23 - Changed date to 22/11/23 from 13/11/23 after approval from CCAG on 28/6/23. 10/10 - CH - Agreed at PSG on 4/10 to downgrade from T2 to T3
5 | 1.7.1.2.8 |  |  |  |  | Consequential Code Change | 100% | Wed 11/10/23 | Mon 11/03/24 | 109 days | Wed 11/10/23 | Fri 08/03/24 |  |  | 0 days | 1 day | 1 day | N/A |  | 5 | Yes
6 | 1.7.1.2.8.1 |  |  |  |  | External industry review via consultation - drop 1 (DCUSA) | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 1876SS |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.2 | Yes |  | Review of drop schedule and scope is being undertaken with CCAG.
6 | 1.7.1.2.8.2 |  |  |  |  | External industry review via consultation - drop 2 (Elexon) | 100% | Mon 19/02/24 | Mon 11/03/24 | 16 days | Mon 19/02/24 | Fri 08/03/24 | 1886SS |  | 0 days | 1 day | 1 day | Code Bodies |  | 5.2 | Yes |  | Review of drop schedule and scope is being undertaken with CCAG.
5 | 1.7.1.2.9 |  |  |  |  | Transition Text (all codes) | 100% | Fri 11/08/23 | Tue 23/01/24 | 118 days | Fri 11/08/23 | Wed 24/01/24 |  |  | 0 days | -1 day | -1 day | N/A |  | 5.2 | Yes
6 | 1.7.1.2.9.1 |  |  |  |  | Pre Code Drafting activities | 100% | Fri 11/08/23 | Tue 22/08/23 | 8 days | Fri 11/08/23 | Tue 22/08/23 | 1874SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.9.2 |  |  |  |  | Code Drafting (offline) | 100% | Fri 18/08/23 | Tue 10/10/23 | 38 days | Fri 18/08/23 | Tue 10/10/23 | 1864SS | 1875SS+10 days,1873SS-5 days,1882SS | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.9.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Fri 01/09/23 | Tue 10/10/23 | 28 days | Fri 01/09/23 | Tue 10/10/23 | 1874SS+10 days | 1876 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.9.4 |  |  |  |  | External industry review via consultation | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 1875 | 1877FS-2 days,1870SS | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.9.5 |  |  |  |  | Triage and action comments | 100% | Mon 30/10/23 | Fri 24/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 1876FS-2 days | 1878 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.9.6 |  |  |  |  | CDWG review | 100% | Mon 27/11/23 | Tue 16/01/24 | 37 days | Mon 27/11/23 | Tue 16/01/24 | 1877 | 1879 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.9.7 |  |  |  |  | CCAG review | 100% | Wed 17/01/24 | Tue 23/01/24 | 5 days | Wed 17/01/24 | Wed 24/01/24 | 1878 | 1880 | 0 days | -1 day | -1 day | PP |  | 5.2 | Yes
6 | 1.7.1.2.9.8 | T2 | T3-RE-0450 | CCAG | MHHS-ART060 | Code drafting for Transition Text topic area approved | 100% | Tue 23/01/24 | Tue 23/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 | 1879 | 1903 | -1 day | -1 day | 0 days | PP |  | 5.16 | Yes |  | 10/10 - CH - Agreed at PSG on 4/10 to downgrade from T2 to T3
5 | 1.7.1.2.10 |  |  |  |  | Final Code Drafting (mop-up) (all codes) | 100% | Fri 18/08/23 | Wed 22/05/24 | 199 days | Fri 18/08/23 | Wed 22/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.10.1 |  |  |  |  | Forward look and confirm remaining plan | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1874SS | 1883SS | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.10.2 |  |  |  |  | Identify remaining or additional areas of code (e.g. consequential change requirements) to be completed | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1882SS | 1884 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.3 |  |  |  |  | Code Drafting (offline) Interim Consultation (1) | 100% | Fri 08/09/23 | Thu 30/11/23 | 60 days | Fri 08/09/23 | Thu 30/11/23 | 1883 | 1885SS+10 days,1936SS | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.4 |  |  |  |  | Internal review and cross-checking of drafting across code drafters Interim Consultation (1) | 100% | Fri 22/09/23 | Thu 30/11/23 | 50 days | Fri 22/09/23 | Thu 30/11/23 | 1884SS+10 days | 18861887 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.5 |  |  |  |  | External industry review via consultation Interim Consultation (1) | 100% | Fri 01/12/23 | Tue 02/01/24 | 23 days | Fri 01/12/23 | Tue 02/01/24 | 1885 | 1871SS | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.10.6 |  |  |  |  | Code Drafting (offline) Final Consultation (2) | 100% | Fri 01/12/23 | Thu 15/02/24 | 55 days | Fri 01/12/23 | Thu 15/02/24 | 1885 | 1888SS+10 days,1936SS | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.7 |  |  |  |  | Internal review and cross-checking of drafting across code drafters Final Consultation (2) | 100% | Fri 15/12/23 | Thu 15/02/24 | 45 days | Fri 15/12/23 | Thu 15/02/24 | 1887SS+10 days | 1889FS+1 day | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.8 |  |  |  |  | External industry review via consultation Final Consultation (2) | 100% | Mon 19/02/24 | Mon 11/03/24 | 16 days | Mon 19/02/24 | Fri 08/03/24 | 1888FS+1 day | 1890FS-1 day | 0 days | 1 day | 1 day | PP |  | 5 | Yes
6 | 1.7.1.2.10.9 |  |  |  |  | Triage and action comments | 100% | Mon 11/03/24 | Wed 03/04/24 | 18 days | Thu 07/03/24 | Mon 01/04/24 | 1889FS-1 day | 1891 | 2 days | 2 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.10 |  |  |  |  | CDWG review | 100% | Thu 04/04/24 | Tue 14/05/24 | 29 days | Tue 02/04/24 | Tue 14/05/24 | 1890 | 1895SS,1892 | 2 days | 0 days | -2 days | PP |  | 5 | Yes
6 | 1.7.1.2.10.11 |  |  |  |  | CCAG review | 100% | Wed 15/05/24 | Wed 22/05/24 | 6 days | Wed 15/05/24 | Wed 22/05/24 | 1891 | 1893 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.10.12 | T2 | T3-RE-0500 | CCAG | MHHS-ART060 | Final code drafting (mop-up) approved | 100% | Wed 22/05/24 | Wed 22/05/24 | 0 days | Wed 22/05/24 | Wed 22/05/24 | 1892 | 1903 | 0 days | 0 days | 0 days | PP |  | 5.25 | Yes |  | 10/10 - CH - Agreed at PSG on 4/10 to downgrade from T2 to T3
5 | 1.7.1.2.11 |  |  |  |  | Final code review, consistency check and approval | 100% | Thu 04/04/24 | Wed 21/08/24 | 100 days | Thu 04/04/24 | Fri 23/08/24 |  |  | 0 days | -2 days | -2 days | N/A |  | 5 | Yes
6 | 1.7.1.2.11.1 |  |  |  |  | Gap analysis of final code against design artefacts (reverse process to code drafting) | 100% | Thu 04/04/24 | Mon 27/05/24 | 38 days | Thu 04/04/24 | Mon 27/05/24 | 1891SS | 1896 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.11.2 |  |  |  |  | Outputs of gap analysis actioned offline | 100% | Tue 28/05/24 | Tue 11/06/24 | 11 days | Tue 28/05/24 | Tue 11/06/24 | 1895 | 1897 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.11.3 |  |  |  |  | Final documentation collated for final consultation | 100% | Wed 12/06/24 | Fri 21/06/24 | 8 days | Wed 12/06/24 | Mon 24/06/24 | 1896 | 1898 | 0 days | -1 day | -1 day | Code Drafting PM |  | 5.23 | Yes
6 | 1.7.1.2.11.4 |  |  |  |  | External industry review via consultation | 100% | Mon 24/06/24 | Fri 12/07/24 | 15 days | Mon 24/06/24 | Fri 19/07/24 | 1897 | 1899,1907SS | 0 days | -5 days | -5 days | PP |  | 5 | Yes
6 | 1.7.1.2.11.5 |  |  |  |  | Triage and action comments | 100% | Mon 15/07/24 | Fri 26/07/24 | 10 days | Thu 18/07/24 | Mon 05/08/24 | 1898 | 1900FS+4 days | -3 days | -6 days | -3 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.11.6 |  |  |  |  | Final CDWG review | 100% | Fri 02/08/24 | Tue 13/08/24 | 8 days | Tue 06/08/24 | Tue 13/08/24 | 1899FS+4 days | 1901 | -2 days | 0 days | 2 days | PP |  | 5 | Yes
6 | 1.7.1.2.11.7 |  |  |  |  | Final CCAG review | 100% | Wed 14/08/24 | Wed 21/08/24 | 6 days | Wed 14/08/24 | Fri 23/08/24 | 1900 | 1903FS+2 days,1902 | 0 days | -2 days | -2 days | PP |  | 5 | Yes
6 | 1.7.1.2.11.8 | T2 | T3-RE-0550 | CCAG | MHHS-ART060 | CCAG recommend final code to PSG for baselining | 100% | Wed 21/08/24 | Wed 21/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1901 |  | -2 days | -2 days | 0 days | PP |  | 5.9 | Yes |  | 10/10 - CH - Agreed at PSG on 4/10 to downgrade from T2 to T3
4 | 1.7.1.3 | T1 | T1-RE-1000 | PSG | MHHS-ART012 | Code changes baselined (M6) | 100% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1901FS+2 days,1893,1880,1868,1859,1850,1841,1832,1823,1814 | 19241932 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes |  | CCAG will approve the code text to go to Ofgem on 23/8/24. PSG will then ratify the milestone at PSG on 2/9/24...
3 | 1.7.2 |  |  |  |  | Ofgem preparation and enactment of SCR powers | 71% | Mon 05/02/24 | Fri 13/12/24 | 225 days | Mon 05/02/24 | Fri 13/12/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.7.2.1 |  |  |  |  | Preparation and enactment of SCR Powers | 72% | Mon 05/02/24 | Wed 11/12/24 | 223 days | Mon 05/02/24 | Wed 11/12/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.7.2.1.1 |  |  |  |  | Ofgem to keep Ofgem legal informed of process followed and nature of Code drafting to ensure that prepared for SCR go/no go decision | 100% | Mon 05/02/24 | Mon 24/06/24 | 101 days | Mon 05/02/24 | Tue 25/06/24 | 1907SF |  | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.2 |  |  |  |  | OFGEM Legal to review Code Artefacts deliver policy intent and process followed and confirm that SCR powers are appropriate to use rather than SMAP - SCR go/no go | 100% | Mon 24/06/24 | Thu 11/07/24 | 14 days | Mon 24/06/24 | Fri 12/07/24 | 1898SS | 1906SF,1908,1909 | 0 days | -1 day | -1 day | Ofgem |  | 5 | Yes
5 | 1.7.2.1.3 |  |  |  |  | Code Bodies to draft MOD proposal forms | 100% | Fri 12/07/24 | Thu 08/08/24 | 20 days | Mon 15/07/24 | Fri 09/08/24 | 1907 |  | -1 day | -1 day | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.4 |  |  |  |  | Ofgem discuss and agree code mod timetable with code bodies (and MHHSP in relation to the dates for expected decisions) | 100% | Fri 12/07/24 | Thu 08/08/24 | 20 days | Mon 15/07/24 | Fri 09/08/24 | 1907 | 1910FS+13 days,1911FS+13 days | -1 day | -1 day | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.5 |  |  |  |  | Ofgem to publish each Direction to each code body specifying the timetable for each modification | 100% | Wed 28/08/24 | Wed 28/08/24 | 1 day | Wed 28/08/24 | Wed 28/08/24 | 1909FS+13 days | 1912 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.6 |  |  |  |  | Formally submit (by separate email) Modification Proposal Forms and legal texts to each code body | 100% | Wed 28/08/24 | Wed 28/08/24 | 1 day | Wed 28/08/24 | Wed 28/08/24 | 1909FS+13 days | 1912 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.7 |  |  |  |  | Each Code Body publishes and issues Modification Proposal Forms | 100% | Thu 29/08/24 | Mon 02/09/24 | 3 days | Thu 29/08/24 | Mon 02/09/24 | 19111910 | 1913 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.8 |  |  |  |  | Each Code Body sends Modification Proposal Forms to Panel to approve Mod to go to consultation | 33% | Tue 03/09/24 | Mon 16/09/24 | 10 days | Tue 03/09/24 | Mon 16/09/24 | 1912 | 1914 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes |  | 16/09/24 - Modifications sent to Panel. Individual CB meeting cycle not aligned to the plan, but no concerns or delays expected to Consultation Close-out (6460).
5 | 1.7.2.1.9 |  |  |  |  | Modification Proposal approved by Panel for Consultation | 0% | Tue 17/09/24 | Tue 17/09/24 | 1 day | Tue 17/09/24 | Tue 17/09/24 | 1913 | 1915 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes |  | 16/09/24 - Modifications sent to Panel. Individual CB meeting cycle not aligned to the plan, but no concerns or delays expected to Consultation Close-out (6460).
5 | 1.7.2.1.10 |  |  |  |  | Draft Modification Report issued for consultation | 0% | Wed 18/09/24 | Wed 18/09/24 | 1 day | Wed 18/09/24 | Wed 18/09/24 | 1914 | 1916 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes |  | 16/09/24 - Modifications sent to Panel. Individual CB meeting cycle not aligned to the plan, but no concerns or delays expected to Consultation Close-out (6460).
5 | 1.7.2.1.11 |  |  |  |  | Consultation Close-out for representations | 0% | Thu 19/09/24 | Wed 09/10/24 | 15 days | Thu 19/09/24 | Wed 09/10/24 | 1915 | 1917 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.12 |  |  |  |  | Each Code Body reviews consultation response and drafts Modification Report | 0% | Thu 10/10/24 | Wed 23/10/24 | 10 days | Thu 10/10/24 | Wed 23/10/24 | 1916 | 1918 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.13 |  |  |  |  | Final Modification Report sent to Panel for decision with recommendation to approve | 0% | Thu 24/10/24 | Thu 24/10/24 | 1 day | Thu 24/10/24 | Thu 24/10/24 | 1917 | 1919FS+9 days | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.14 |  |  |  |  | Modification Panel decision | 0% | Thu 07/11/24 | Thu 07/11/24 | 1 day | Thu 07/11/24 | Thu 07/11/24 | 1918FS+9 days | 1920 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.15 |  |  |  |  | Code Bodies Submit Final Modification/Change Reports | 0% | Fri 08/11/24 | Fri 08/11/24 | 1 day | Fri 08/11/24 | Fri 08/11/24 | 1919 | 1921 | 0 days | 0 days | 0 days | Code Bodies |  | 5.31 | Yes
5 | 1.7.2.1.16 |  |  |  |  | Ofgem Reviews Final Modification/Change Reports | 0% | Mon 11/11/24 | Fri 22/11/24 | 10 days | Mon 11/11/24 | Fri 22/11/24 | 1920 | 1922SS+5 days | 0 days | 0 days | 0 days | Ofgem |  | 5.31 | Yes
5 | 1.7.2.1.17 |  |  |  |  | Ofgem Drafts Decision/Direction Letters | 0% | Mon 18/11/24 | Tue 10/12/24 | 17 days | Mon 18/11/24 | Tue 10/12/24 | 1921SS+5 days | 1923 | 0 days | 0 days | 0 days | Ofgem |  | 5.31 | Yes
5 | 1.7.2.1.18 |  |  |  |  | Ofgem Internally Signs Off the Decision/Direction Letters and Sends Them to the Code Bodies | 0% | Wed 11/12/24 | Wed 11/12/24 | 1 day | Wed 11/12/24 | Wed 11/12/24 | 1922 | 1924 | 0 days | 0 days | 0 days | Ofgem |  | 5.31 | Yes
4 | 1.7.2.2 | T2 | T2-RE-0600 | CCAG | MHHS-ART012 | Ofgem decisions on M6 baselined code modification proposals (M7) | 0% | Wed 11/12/24 | Wed 11/12/24 | 0 days | Wed 11/12/24 | Wed 11/12/24 | 19031923 | 19321925 | 0 days | 0 days | 0 days | CPT | Approved | 5.31 | Yes
4 | 1.7.2.3 |  |  |  |  | Ofgem Publishes the Decisions/Directions | 0% | Thu 12/12/24 | Fri 13/12/24 | 2 days | Thu 12/12/24 | Fri 13/12/24 | 1924 |  | 0 days | 0 days | 0 days | Ofgem |  | 5.31 | Yes
3 | 1.7.3 |  |  |  |  | Deliver MHHS Code Changes | 0% | Tue 12/11/24 | Wed 12/11/25 | 262 days | Tue 12/11/24 | Fri 06/06/25 |  |  | 0 days | 113 days | 113 days | N/A |  | 5 | Yes
4 | 1.7.3.1 |  |  |  |  | Releases | 0% | Tue 12/11/24 | Wed 12/11/25 | 262 days | Tue 12/11/24 | Fri 06/06/25 |  |  | 0 days | 113 days | 113 days | N/A |  | 5 | Yes
5 | 1.7.3.1.1 |  |  |  |  | Impacted codes make resourcing provisions and prepare to implement new Code via internal code body change processes | 0% | Tue 12/11/24 | Thu 27/02/25 | 78 days | Tue 12/11/24 | Thu 27/02/25 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.3.1.2 |  |  |  |  | Main Code Release | 0% | Wed 06/08/25 | Wed 12/11/25 | 71 days | Fri 28/02/25 | Fri 06/06/25 |  |  | 113 days | 113 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.3.1.2.1 |  |  |  |  | Release preparation (e.g. preparing release documentation) | 0% | Wed 06/08/25 | Wed 13/08/25 | 6 days | Fri 28/02/25 | Fri 07/03/25 | 1931SF |  | 113 days | 114 days | 1 day | Code Bodies |  | 5 | Yes
6 | 1.7.3.1.2.2 |  |  |  |  | Implement new code on day of code release | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1932SF | 1930SF | 114 days | 113 days | -1 day | Code Bodies |  | 5 | Yes
6 | 1.7.3.1.2.3 | T2 | T2-RE-0650 | CCAG | MHHS-ART060 | Code changes delivered (M8) | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1924,1903,1317SS | 2389FS-40 days,1931SF,1933FS+65 days | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
6 | 1.7.3.1.2.4 | T2 | T2-RE-0700 | CCAG | MHHS-ART060 | Code changes delivered (M8*) late exit | 0% | Wed 12/11/25 | Wed 12/11/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 1932FS+65 days |  | 113 days | 113 days | 0 days | CPT |  | 5.1 | Yes
3 | 1.7.4 |  |  |  |  | External Programme Dependency Management | 100% | Fri 01/12/23 | Wed 24/01/24 | 38 days | Fri 01/12/23 | Wed 24/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.7.4.1 |  |  |  |  | DCP397 | 100% | Fri 01/12/23 | Wed 24/01/24 | 38 days | Fri 01/12/23 | Wed 24/01/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.7.4.1.1 |  |  |  |  | Ensure DCP397 drafting included in mop-up code drafting activity (link to mop-up) | 100% | Fri 01/12/23 | Thu 28/12/23 | 20 days | Fri 01/12/23 | Thu 28/12/23 | 1887SS,1884SS |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.7.4.1.2 |  |  |  |  | Implementation of DCP397 | 100% | Wed 24/01/24 | Wed 24/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
2 | 1.8 |  |  |  |  | MIGRATION | 35% | Mon 31/10/22 | Tue 15/06/27 | 1207 days | Mon 31/10/22 | Tue 05/01/27 |  |  | 0 days | 115 days | 115 days | N/A |  |  | Yes
3 | 1.8.1 | T3 | T3-MI-0016 | MCAG (Migration) |  | Migration Period Plan Review 1 Completed | 0% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 |  |  | 0 days | 0 days | 0 days | SRO |  | 5.28 | No |  | 2/7: To go to July MCAG for removal because milestone no longer reflects the delivery of the migration approach
3 | 1.8.2 |  |  |  |  | Regulatory Governance | 47% | Mon 01/04/24 | Wed 01/01/25 | 198 days | Mon 01/04/24 | Wed 27/11/24 |  |  | 0 days | 25 days | 25 days | N/A |  | 5.28 | Yes
4 | 1.8.2.1 |  |  |  |  | Incentive Mods Created | 85% | Mon 01/04/24 | Fri 30/08/24 | 110 days | Mon 01/04/24 | Fri 26/07/24 |  | 1942 | 0 days | 25 days | 25 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.2.2 |  |  |  |  | Incentives Implemented | 0% | Mon 02/09/24 | Wed 01/01/25 | 88 days | Mon 29/07/24 | Wed 27/11/24 | 1941 |  | 25 days | 25 days | 0 days | Code Bodies |  | 5.28 | Yes
3 | 1.8.3 |  |  |  |  | Migration Framework Agreed and Implemented | 62% | Thu 01/02/24 | Thu 23/01/25 | 256 days | Thu 01/02/24 | Tue 26/11/24 |  |  | 0 days | 42 days | 42 days | N/A |  | 5.28 | Yes
4 | 1.8.3.1 |  |  |  |  | Consultation 1 - Schedule | 100% | Thu 01/02/24 | Wed 08/05/24 | 70 days | Thu 01/02/24 | Wed 08/05/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.28 | Yes
5 | 1.8.3.1.1 |  |  |  |  | Prepare Artefacts for Consultation | 100% | Thu 01/02/24 | Mon 18/03/24 | 33 days | Thu 01/02/24 | Mon 18/03/24 |  |  | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.2 |  |  |  |  | Industry Consultation | 100% | Mon 18/03/24 | Mon 08/04/24 | 16 days | Mon 18/03/24 | Mon 08/04/24 |  |  | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.3 |  |  |  |  | Triage and Action Comments | 100% | Mon 08/04/24 | Fri 19/04/24 | 10 days | Mon 08/04/24 | Fri 19/04/24 |  |  | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.4 |  |  |  |  | Industry Assurance Review | 100% | Fri 19/04/24 | Fri 26/04/24 | 6 days | Fri 19/04/24 | Fri 26/04/24 |  |  | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.5 |  |  |  |  | MWG Recommendation | 100% | Fri 26/04/24 | Fri 26/04/24 | 1 day | Fri 26/04/24 | Fri 26/04/24 |  |  | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.6 |  |  |  |  | MCAG Interim Approval Artefacts | 100% | Wed 08/05/24 | Wed 08/05/24 | 1 day | Wed 08/05/24 | Wed 08/05/24 |  | 1976,1978,1966FS+37 days,1975 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
4 | 1.8.3.2 |  |  |  |  | Consultation 2 - Control | 100% | Mon 08/04/24 | Thu 25/07/24 | 79 days | Mon 08/04/24 | Thu 25/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.28 | Yes
5 | 1.8.3.2.1 |  |  |  |  | Prepare Artefacts for Consultation | 100% | Mon 08/04/24 | Thu 13/06/24 | 49 days | Mon 08/04/24 | Thu 13/06/24 |  | 1953 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.2.2 |  |  |  |  | Industry Consultation | 100% | Fri 14/06/24 | Fri 28/06/24 | 11 days | Fri 14/06/24 | Fri 28/06/24 | 1952 | 1954 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.2.3 |  |  |  |  | Triage and Action Comments | 100% | Mon 01/07/24 | Thu 11/07/24 | 9 days | Mon 01/07/24 | Thu 11/07/24 | 1953 | 1955 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
5 | 1.8.3.2.4 |  |  |  |  | Industry Assurance Review | 100% | Fri 12/07/24 | Thu 18/07/24 | 5 days | Fri 12/07/24 | Thu 18/07/24 | 1954 | 1956 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.2.5 |  |  |  |  | MWG Recommendation | 100% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Thu 18/07/24 | Thu 18/07/24 | 1955 | 1957FS+5 days | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.2.6 |  | T3-MI-0037 | MCAG (Migration) |  | Consultation 2 - Control - MCAG Approval of Interim Artefacts | 100% | Thu 25/07/24 | Thu 25/07/24 | 0 days | Thu 25/07/24 | Thu 25/07/24 | 1956FS+5 days | 1967,1983FS+2 days | 0 days | 0 days | 0 days | PP | Approved | 5.3 | Yes |  | New milestone added to reflect updated delivery approach for migration. To go to July MCAG for approval
4 | 1.8.3.3 |  |  |  |  | Consultation 3 - Parameters | 18% | Tue 09/07/24 | Thu 23/01/25 | 143 days | Tue 09/07/24 | Tue 22/10/24 |  |  | 0 days | 67 days | 67 days | N/A |  | 5.28 | Yes
5 | 1.8.3.3.1 |  |  |  |  | Prepare Artefacts (9) for Consultation | 23% | Tue 09/07/24 | Mon 18/11/24 | 95 days | Tue 09/07/24 | Tue 27/08/24 | 1966SS+6 days | 1960 | 0 days | 59 days | 59 days | SRO Migration |  | 5.28 | Yes
5 | 1.8.3.3.2 |  |  |  |  | Industry Consultation | 0% | Tue 19/11/24 | Mon 02/12/24 | 10 days | Wed 28/08/24 | Tue 10/09/24 | 1959 | 1961 | 59 days | 59 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.3.3 |  |  |  |  | Triage and Action Comments | 0% | Tue 03/12/24 | Mon 16/12/24 | 10 days | Wed 11/09/24 | Tue 24/09/24 | 1960 | 1962 | 59 days | 59 days | 0 days | SRO Migration |  | 5.28 | Yes
5 | 1.8.3.3.4 |  |  |  |  | Industry Assurance Review | 0% | Tue 17/12/24 | Wed 25/12/24 | 7 days | Wed 25/09/24 | Thu 03/10/24 | 1961 | 1963FS+8 days | 59 days | 59 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.3.5 |  |  |  |  | MWG Recommendation | 0% | Mon 06/01/25 | Mon 06/01/25 | 0 days | Thu 03/10/24 | Thu 03/10/24 | 1962FS+8 days | 1964FS+13 days | 67 days | 67 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.3.6 |  | T3-MI-0017 | MCAG (Migration) |  | MCAG Approval of Migration Framework Artefacts (Baselined) | 0% | Thu 23/01/25 | Thu 23/01/25 | 0 days | Tue 22/10/24 | Tue 22/10/24 | 1967,1963FS+13 days | 1991FS+2 days,1992FS+2 days | 67 days | 67 days | 0 days | PP | Approved | 5.3 | Yes |  | It is expected that baseline date will need to be changed. This is due to a combination of the changes coming out of MWG for Consultation 3 being very minimal for the original release date of 28th August and not warranting an industry consultation, couple
3 | 1.8.4 |  |  |  |  | Migration Schedule Agreed and Maintained | 14% | Mon 01/07/24 | Fri 30/01/26 | 415 days | Mon 01/07/24 | Tue 15/04/25 |  |  | 0 days | 208 days | 208 days | N/A |  | 5.28 | Yes
4 | 1.8.4.1 |  |  |  |  | Indicative Envelopes Issued | 100% | Mon 01/07/24 | Wed 31/07/24 | 23 days | Mon 01/07/24 | Wed 31/07/24 | 1950FS+37 days | 1967,1959SS+6 days,1989SS | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.2 |  |  |  |  | Supplier Submissions | 11% | Thu 01/08/24 | Wed 02/10/24 | 45 days | Thu 01/08/24 | Wed 02/10/24 | 19661957 | 19641968 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
4 | 1.8.4.3 |  |  |  |  | Team Assess Responses | 0% | Thu 03/10/24 | Wed 16/10/24 | 10 days | Thu 03/10/24 | Wed 16/10/24 | 1967 | 1969 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.4 |  |  |  |  | Discuss and Agree Approach with Participants where necessary | 0% | Thu 17/10/24 | Tue 22/10/24 | 4 days | Thu 17/10/24 | Tue 22/10/24 | 1968 | 1970 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.5 |  | T3-MI-0039 | MCAG (Migration) |  | V1.0 of Migration Schedule Baseline Approved at MCAG | 0% | Fri 10/01/25 | Fri 10/01/25 | 0 days | Tue 22/10/24 | Tue 22/10/24 | 19791969 | 1971FS+110 days | 58 days | 58 days | 0 days | PP | Approved | 5.3 | Yes |  | On Track.
4 | 1.8.4.6 |  |  |  |  | Sprint Planning (Cycle 1) | 0% | Mon 16/06/25 | Fri 08/08/25 | 40 days | Wed 20/11/24 | Tue 17/12/24 | 1970FS+110 days | 1972FS+25 days | 148 days | 168 days | 20 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.7 |  |  |  |  | Sprint Planning (Cycle 2) | 0% | Mon 15/09/25 | Fri 07/11/25 | 40 days | Wed 22/01/25 | Tue 18/02/25 | 1971FS+25 days | 1973FS+20 days | 168 days | 188 days | 20 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.8 |  |  |  |  | Sprint Planning (Cycle 3) | 0% | Mon 08/12/25 | Fri 30/01/26 | 40 days | Thu 20/03/25 | Tue 15/04/25 | 1972FS+20 days,1987 |  | 187 days | 208 days | 21 days | SRO Migration |  | 5.28 | Yes
3 | 1.8.5 |  |  |  |  | Migration Control Centre Tooling | 30% | Thu 09/05/24 | Fri 11/04/25 | 242 days | Thu 09/05/24 | Fri 17/01/25 |  |  | 0 days | 60 days | 60 days | N/A |  | 5.28 | Yes
4 | 1.8.5.1 |  |  |  |  | Data Source Definition | 46% | Thu 09/05/24 | Wed 23/10/24 | 120 days | Thu 09/05/24 | Wed 31/07/24 | 1950 | 1977 | 0 days | 60 days | 60 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.5.2 |  |  |  |  | Scheduling and Data Requirements | 46% | Thu 09/05/24 | Wed 23/10/24 | 120 days | Thu 09/05/24 | Wed 31/07/24 | 1950 | 1977 | 0 days | 60 days | 60 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.5.3 |  |  |  |  | Tool Phase 1 | 0% | Thu 24/10/24 | Thu 07/11/24 | 11 days | Thu 01/08/24 | Thu 15/08/24 | 19761975 | 1978 | 60 days | 60 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.5.4 |  |  |  |  | Data Requirements | 0% | Fri 08/11/24 | Fri 06/12/24 | 21 days | Fri 16/08/24 | Fri 13/09/24 | 19501977 | 1979 | 60 days | 60 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.5.5 |  |  |  |  | Tool Phase 2 | 0% | Mon 09/12/24 | Fri 10/01/25 | 25 days | Mon 16/09/24 | Fri 18/10/24 | 1978 | 19701980 | 60 days | 60 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.5.6 |  |  |  |  | Data Source Provision | 0% | Mon 13/01/25 | Tue 21/01/25 | 7 days | Mon 21/10/24 | Tue 29/10/24 | 1979 | 1981 | 60 days | 60 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.5.7 |  |  |  |  | Tool - Internal and External Testing | 0% | Wed 22/01/25 | Fri 11/04/25 | 58 days | Wed 30/10/24 | Fri 17/01/25 | 1980 | 1987 | 60 days | 60 days | 0 days | SRO Migration |  | 5.28 | Yes
3 | 1.8.6 |  |  |  |  | Migration Control Centre Mobilised and Ready | 1% | Tue 30/07/24 | Mon 14/04/25 | 185 days | Wed 31/07/24 | Mon 03/02/25 |  |  | -1 day | 50 days | 51 days | N/A |  | 5.28 | Yes
4 | 1.8.6.1 |  |  |  |  | Migration Control Centre TOM Definition | 3% | Tue 30/07/24 | Mon 28/10/24 | 65 days | Wed 31/07/24 | Mon 09/09/24 | 1957FS+2 days | 1984FS+4 days | -1 day | 35 days | 36 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.6.2 |  |  |  |  | Access to Data | 0% | Mon 04/11/24 | Fri 06/12/24 | 25 days | Mon 16/09/24 | Fri 18/10/24 | 1983FS+4 days | 1985FS+11 days | 35 days | 35 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.6.3 |  |  |  |  | Migration Control Centre Delegation of Authority | 0% | Tue 24/12/24 | Wed 08/01/25 | 12 days | Mon 04/11/24 | Tue 19/11/24 | 1984FS+11 days | 1986SS | 36 days | 36 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.6.4 |  |  |  |  | Recruit and Train | 0% | Tue 24/12/24 | Mon 24/03/25 | 65 days | Mon 04/11/24 | Fri 31/01/25 | 1985SS | 1987 | 36 days | 36 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.6.5 |  |  |  |  | Dress Rehearsal | 0% | Mon 14/04/25 | Mon 14/04/25 | 1 day | Mon 03/02/25 | Mon 03/02/25 | 1981198619911990 | 1973 | 50 days | 50 days | 0 days | SRO Migration |  | 5.28 | Yes
3 | 1.8.7 |  |  |  |  | PP's Prepared for Migration | 23% | Mon 01/07/24 | Mon 31/03/25 | 196 days | Mon 01/07/24 | Thu 30/01/25 |  |  | 0 days | 42 days | 42 days | N/A |  | 5.28 | Yes
4 | 1.8.7.1 |  |  |  |  | Prep for Envelope Webinar | 100% | Mon 01/07/24 | Mon 05/08/24 | 26 days | Mon 01/07/24 | Mon 05/08/24 | 1966SS | 1990FF | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.7.2 |  |  |  |  | Envelope/Submission Webinar | 100% | Mon 05/08/24 | Mon 05/08/24 | 1 day | Mon 05/08/24 | Mon 05/08/24 | 1989FF |  | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.7.3 |  |  |  |  | Guides Creation | 0% | Tue 28/01/25 | Mon 31/03/25 | 45 days | Fri 29/11/24 | Thu 30/01/25 | 1964FS+2 days | 1987 | 42 days | 42 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.7.4 |  |  |  |  | Support Channels | 0% | Tue 28/01/25 | Mon 31/03/25 | 45 days | Fri 29/11/24 | Thu 30/01/25 | 1964FS+2 days | 1987 | 42 days | 42 days | 0 days | SRO Migration |  | 5.28 | Yes
3 | 1.8.8 |  |  |  |  | Migration Artefact Development and Publication | 78% | Mon 31/10/22 | Wed 03/09/25 | 743 days | Mon 31/10/22 | Fri 04/04/25 |  |  | 0 days | 108 days | 108 days | N/A |  | 5 | Yes
4 | 1.8.8.1 |  |  |  |  | Migration Approach | 100% | Mon 31/10/22 | Wed 07/12/22 | 28 days | Mon 31/10/22 | Wed 07/12/22 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.8.1.1 |  |  |  |  | Option analysis (via MWG and PPIR) and recommendation | 100% | Mon 31/10/22 | Wed 30/11/22 | 23 days | Mon 31/10/22 | Wed 30/11/22 |  | 1996FS+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.8.1.2 | T3 | T3-MI-0010 | PSG | MHHS-DEL770 | Migration Approach approved | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 1995FS+5 days | 2033 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.8.2 |  |  |  |  | Migration Design | 100% | Mon 14/11/22 | Fri 31/03/23 | 100 days | Mon 14/11/22 | Fri 31/03/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.8.2.1 |  |  |  |  | Review and update existing design artefacts and socialise with participants ahead of MDSG | 100% | Mon 14/11/22 | Fri 25/11/22 | 10 days | Mon 14/11/22 | Fri 25/11/22 |  | 1999FS+2 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.2 |  |  |  |  | Develop design artefacts and supporting technical documents in line with MDSG | 100% | Wed 30/11/22 | Fri 10/02/23 | 53 days | Wed 30/11/22 | Fri 10/02/23 | 1998FS+2 days | 2000FS+1 day | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.3 | T3 | T3-MI-0011 | DAG |  | Migration design artefacts issued for consultation | 100% | Mon 13/02/23 | Mon 13/02/23 | 0 days | Mon 13/02/23 | Mon 13/02/23 | 1999FS+1 day | 2001SS | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.4 |  |  |  |  | Industry consultation | 100% | Tue 14/02/23 | Mon 20/02/23 | 5 days | Tue 14/02/23 | Mon 20/02/23 | 2000SS | 2002 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.8.2.5 |  |  |  |  | Review consultation feedback, address comments and update artefacts | 100% | Tue 21/02/23 | Mon 27/02/23 | 5 days | Tue 21/02/23 | Mon 27/02/23 | 2001 | 2003 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.6 |  |  |  |  | Internal artefact review and comms preparation | 100% | Tue 28/02/23 | Thu 02/03/23 | 3 days | Tue 28/02/23 | Thu 02/03/23 | 2002 | 2004FS+1 day | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.7 | T3 | T3-MI-0013 | DAG |  | Updated Migration Design artefacts issued to PPs for assurance review | 100% | Fri 03/03/23 | Fri 03/03/23 | 0 days | Fri 03/03/23 | Fri 03/03/23 | 2003FS+1 day | 2005FS+13 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.8 |  |  |  |  | Final Migration Design artefacts walkthrough with PPs | 100% | Wed 22/03/23 | Wed 22/03/23 | 0 days | Wed 22/03/23 | Wed 22/03/23 | 2004FS+13 days | 2006FS+7 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.2.9 | T2 | T2-MI-0050 | DAG |  | Migration Design approved | 100% | Fri 31/03/23 | Fri 31/03/23 | 0 days | Fri 31/03/23 | Fri 31/03/23 | 2005FS+7 days | 866,2113FS+501 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.8.3 |  |  |  |  | Transition Design | 100% | Wed 01/03/23 | Wed 15/11/23 | 186 days | Wed 01/03/23 | Wed 15/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.8.3.1 |  |  |  |  | Tranche 1 | 100% | Wed 01/03/23 | Wed 17/05/23 | 56 days | Wed 01/03/23 | Wed 17/05/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.8.3.1.1 |  |  |  |  | Develop design artefacts and supporting technical details with participants | 100% | Wed 01/03/23 | Tue 09/05/23 | 50 days | Wed 01/03/23 | Tue 09/05/23 |  | 2010 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.8.8.3.1.2 |  |  |  |  | Issue Material for DAG approval | 100% | Wed 10/05/23 | Wed 10/05/23 | 1 day | Wed 10/05/23 | Wed 10/05/23 | 2009 | 2011FS+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.8.8.3.1.3 | T2 | T2-DB-0150 | DAG |  | Tranche 1 Transition Design approved | 100% | Wed 17/05/23 | Wed 17/05/23 | 0 days | Wed 17/05/23 | Wed 17/05/23 | 2010FS+5 days | 2013 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.8.8.3.2 |  |  |  |  | Tranche 2 | 100% | Thu 18/05/23 | Wed 15/11/23 | 130 days | Thu 18/05/23 | Wed 15/11/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.8.3.2.1 |  |  |  |  | Develop Initial design artefacts and supporting technical details | 100% | Thu 18/05/23 | Thu 31/08/23 | 76 days | Thu 18/05/23 | Thu 31/08/23 | 2011 | 2014 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.2 |  |  |  |  | Communicate Initial Design Artefacts with Industry (MTDSG) | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 2013 | 2015FS+5 days | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.3 |  |  |  |  | Host MTDSG | 100% | Mon 11/09/23 | Mon 11/09/23 | 1 day | Mon 11/09/23 | Mon 11/09/23 | 2014FS+5 days | 2016 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.4 |  |  |  |  | Process MTDSG Feedback and Amend Design Artefacts | 100% | Tue 12/09/23 | Fri 15/09/23 | 4 days | Tue 12/09/23 | Fri 15/09/23 | 2015 | 2017FF | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.5 |  |  |  |  | Communicate Amended Design Artefacts with Industry | 100% | Fri 15/09/23 | Fri 15/09/23 | 1 day | Fri 15/09/23 | Fri 15/09/23 | 2016FF | 2018FS+6 days | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.6 |  |  |  |  | Host MTDSG | 100% | Tue 26/09/23 | Tue 26/09/23 | 1 day | Tue 26/09/23 | Tue 26/09/23 | 2017FS+6 days | 2019 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.7 |  |  |  |  | Make Final Amendments to Design Artefact | 100% | Wed 27/09/23 | Tue 03/10/23 | 5 days | Wed 27/09/23 | Tue 03/10/23 | 2018 | 2020 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.8 |  |  |  |  | Request DAG Consultation | 100% | Wed 04/10/23 | Wed 04/10/23 | 1 day | Wed 04/10/23 | Wed 04/10/23 | 2019 | 2021SS | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.9 |  |  |  |  | Consultation Period | 100% | Wed 04/10/23 | Wed 18/10/23 | 11 days | Wed 04/10/23 | Wed 18/10/23 | 2020SS | 2022 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.10 |  |  |  |  | Action Consultation Comments | 100% | Thu 19/10/23 | Wed 25/10/23 | 5 days | Thu 19/10/23 | Wed 25/10/23 | 2021 | 2023 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.11 |  |  |  |  | Post Consultation Industry Assurance | 100% | Thu 26/10/23 | Wed 01/11/23 | 5 days | Thu 26/10/23 | Wed 01/11/23 | 2022 | 2024FF | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.12 |  |  |  |  | Request DAG Approval | 100% | Wed 01/11/23 | Wed 01/11/23 | 1 day | Wed 01/11/23 | Wed 01/11/23 | 2023FF | 2025FS+4 days | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.13 |  |  |  |  | DAG Transition Design Approved | 100% | Wed 08/11/23 | Wed 08/11/23 | 1 day | Wed 08/11/23 | Wed 08/11/23 | 2024FS+4 days | 2026 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.14 |  |  |  |  | Update Transition Design Admin | 100% | Thu 09/11/23 | Wed 15/11/23 | 5 days | Thu 09/11/23 | Wed 15/11/23 | 2025 | 2027 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.8.3.2.15 | T2 | T2-DB-0250 | DAG |  | Tranche 2 Transition Design Baselined | 100% | Wed 15/11/23 | Wed 15/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 | 2026 |  | 0 days | 0 days | 0 days | SRO |  | 5.12 | Yes |  | 14/8 - Milestone aligned to 5 days after DAG approval, to update comms and admin on collaboration base. CR number to be added. 15/9 - Rebaseline approved at DAG on 13/9/23
4 | 1.8.8.4 |  |  |  |  | Data Assessment Report | 100% | Tue 06/12/22 | Tue 28/02/23 | 61 days | Tue 06/12/22 | Tue 28/02/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.8.4.1 |  |  |  |  | Develop document with MWG | 100% | Tue 06/12/22 | Fri 10/02/23 | 49 days | Tue 06/12/22 | Fri 10/02/23 |  | 2030FS-18 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.4.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Wed 18/01/23 | Tue 21/02/23 | 25 days | Wed 18/01/23 | Tue 21/02/23 | 2029FS-18 days | 2031FS+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.8.4.3 | T3 | T3-MI-0012 | MCAG |  | Data Assessment Report approved | 100% | Tue 28/02/23 | Tue 28/02/23 | 0 days | Tue 28/02/23 | Tue 28/02/23 | 2030FS+5 days |  | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.8.5 |  |  |  |  | Migration, Cutover & Data Strategy (incl. Migration Entry Criteria) | 100% | Thu 08/12/22 | Fri 28/04/23 | 102 days | Thu 08/12/22 | Fri 28/04/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.8.5.1 |  |  |  |  | Develop document with MWG | 100% | Thu 08/12/22 | Fri 10/03/23 | 67 days | Thu 08/12/22 | Fri 10/03/23 | 1996 | 2034FS+2 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.5.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Wed 15/03/23 | Fri 21/04/23 | 28 days | Wed 15/03/23 | Fri 21/04/23 | 2033FS+2 days | 2035FF+5 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.8.5.3 | T3 | T3-MI-0014 | MCAG |  | Migration, Cutover & Data Strategy approved | 100% | Fri 28/04/23 | Fri 28/04/23 | 0 days | Fri 28/04/23 | Fri 28/04/23 | 2034FF+5 days |  | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.8.6 |  |  |  |  | Data Cleanse Plan | 63% | Thu 02/03/23 | Wed 03/09/25 | 655 days | Thu 02/03/23 | Fri 04/04/25 |  |  | 0 days | 108 days | 108 days | N/A |  | 5 | Yes
5 | 1.8.8.6.1 |  |  |  |  | Develop document with MWG | 100% | Thu 02/03/23 | Wed 10/05/23 | 50 days | Thu 02/03/23 | Wed 10/05/23 |  | 2038 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.6.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Thu 11/05/23 | Wed 07/06/23 | 20 days | Thu 11/05/23 | Wed 07/06/23 | 2037 | 2039FS+30 days | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.8.6.3 | T3 | T3-MI-0020 | MCAG |  | Data Cleanse Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 2038FS+30 days | 2040,2043FS+282 days,2048FS+301 days,2054FS+317 days,2055FS+317 days,2056FS+317 days,2057FS+296 days,2058FS+317 days,2059FS+327 days,2068FS+176 days | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.6.4 |  |  |  |  | Monitor Programme Participant adherence to Data Cleanse Plan | 64% | Thu 15/06/23 | Fri 28/03/25 | 467 days | Thu 15/06/23 | Fri 28/03/25 | 2039 |  | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.8.6.5 |  |  |  |  | MTDs | 8% | Fri 16/08/24 | Fri 31/01/25 | 120 days | Fri 16/08/24 | Mon 23/12/24 |  |  | 1 day | 30 days | 29 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
6 | 1.8.8.6.5.1 |  |  |  |  | ESME ID | 0% | Fri 16/08/24 | Fri 20/12/24 | 90 days | Fri 16/08/24 | Fri 20/12/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.5.1.1 | T3 | T3-MI-0024 | MCAG (Transition) |  | DCC to extract ESME ID and share with LDSO | 100% | Fri 16/08/24 | Fri 16/08/24 | 0 days | Fri 16/08/24 | Fri 16/08/24 | 2039FS+282 days | 2044FS+45 days | 0 days | 0 days | 0 days | DCC/SI |  | 5.5 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.5.1.2 | T3 | T3-MI-0025 | MCAG (Transition) |  | LDSO ‘full refresh’ between their Registration Service and the EES (ESME ID) | 0% | Mon 21/10/24 | Mon 11/11/24 | 16 days | Mon 21/10/24 | Mon 11/11/24 | 2043FS+45 days | 2045FS+28 days | 0 days | 0 days | 16 days | LDSO/EES | Proposed | 5.5 | Yes |  | 2/8/24: Date missed because Meter Location and Number of Displayed Register Digits has been delayed due to additional data validation activities. This will delay some of the data migration activities. To go to August MCAG for date change approval
7 | 1.8.8.6.5.1.3 |  |  |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 0% | Fri 20/12/24 | Fri 20/12/24 | 1 day | Fri 20/12/24 | Fri 20/12/24 | 2044FS+28 days | 2046 | 0 days | 0 days | 0 days | Supplier |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.5.1.4 |  |  |  |  | ESME ID Complete | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 2045 |  | 0 days | 0 days | 0 days |  |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
6 | 1.8.8.6.5.2 |  |  |  |  | Meter Location and Number of Displayed Register Digits | 13% | Fri 13/09/24 | Fri 31/01/25 | 101 days | Fri 16/08/24 | Mon 23/12/24 |  |  | 20 days | 30 days | 10 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.5.2.1 |  |  |  |  | MEM to extract data and share with LDSO | 50% | Fri 13/09/24 | Fri 20/09/24 | 6 days | Fri 16/08/24 | Fri 16/08/24 | 2039FS+301 days | 2049FS+25 days | 20 days | 25 days | 5 days | MEM/SI |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.5.2.2 | T3 | T3-MI-0026 | MCAG (Transition) |  | LDSO ‘full refresh’ between their Registration Service and the EES (Meter Location and Number of Displayed Register Digits) | 0% | Mon 28/10/24 | Mon 18/11/24 | 16 days | Fri 27/09/24 | Fri 27/09/24 | 2048FS+25 days | 2050FS+53 days | 20 days | 36 days | 16 days | LDSO /EES | Proposed | 5.5 | Yes |  | Date missed due to additional data validation activities for Meter Location and Number of Displayed Register Digits. This will cause a delay to some of the other data migration activities. To go to August MCAG for date change approval
7 | 1.8.8.6.5.2.3 |  |  |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 0% | Fri 31/01/25 | Fri 31/01/25 | 1 day | Fri 20/12/24 | Fri 20/12/24 | 2049FS+53 days | 2051 | 30 days | 30 days | 0 days | Supplier |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.5.2.4 |  |  |  |  | Meter Location and Number of Displayed Register Digits Complete | 0% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Mon 23/12/24 | Mon 23/12/24 | 2050 |  | 30 days | 30 days | 0 days |  |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
5 | 1.8.8.6.6 |  |  |  |  | Registration Data | 5% | Fri 06/09/24 | Wed 03/09/25 | 259 days | Fri 06/09/24 | Mon 31/03/25 |  |  | 0 days | 112 days | 112 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
6 | 1.8.8.6.6.1 |  |  |  |  | Connection Type | 6% | Fri 06/09/24 | Mon 11/11/24 | 47 days | Fri 06/09/24 | Fri 27/09/24 |  |  | 0 days | 31 days | 31 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.1.1 | T3 | T3-MI-0027 | MCAG (Transition) |  | Automated Population of Connection Type for Measurement Classes ‘B’, ‘D’, ‘F’ & ‘G’ | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 2039FS+317 days | 2060 | 15 days | 15 days | 0 days | LDSO | Proposed | 5.5 | Yes
7 | 1.8.8.6.6.1.2 | T3 | T3-MI-0028 | MCAG (Transition) |  | BAU Population of Connection Type for Site Specific LLFCs within Measurement Classes ‘C’ & ‘E’ | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 2039FS+317 days | 2060 | 15 days | 15 days | 0 days | LDSO | Approved | 5.5 | Yes
7 | 1.8.8.6.6.1.3 | T3 | T3-MI-0029 | MCAG (Transition) |  | Automated Population of Connection Type for Smart Meters within Measurement Class ‘A’ | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 2039FS+317 days | 2060 | 15 days | 15 days | 0 days | LDSO | Proposed | 5.5 | Yes
7 | 1.8.8.6.6.1.4 |  |  |  |  | Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’ | 100% | Fri 06/09/24 | Fri 06/09/24 | 1 day | Fri 06/09/24 | Fri 06/09/24 | 2039FS+296 days | 2060 | 0 days | 0 days | 0 days | Suppliers |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.1.5 | T3 | T3-MI-0030 | MCAG (Transition) |  | Automated Population of Null Connection Type | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 2039FS+317 days | 2060 | 15 days | 15 days | 0 days | LDSO | Proposed | 5.5 | Yes
7 | 1.8.8.6.6.1.6 |  |  |  |  | Full MPAN refresh to ESS | 0% | Mon 21/10/24 | Mon 11/11/24 | 16 days | Fri 27/09/24 | Fri 27/09/24 | 2039FS+327 days | 2060 | 16 days | 31 days | 15 days | LDSO/EES |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.1.7 |  |  |  |  | Connection Type Complete | 0% | Mon 11/11/24 | Mon 11/11/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 2.0542e+23 |  | 31 days | 31 days | 0 days |  |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
6 | 1.8.8.6.6.2 |  |  |  |  | Domestic Premises Indicator | 0% | Fri 08/08/25 | Wed 03/09/25 | 19 days | Fri 07/03/25 | Mon 31/03/25 |  |  | 110 days | 112 days | 2 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.2.1 |  |  |  |  | The DCC to extract Domestic Premises Indicator from the CSS and provide a file to each LDSO and EES. | 0% | Fri 08/08/25 | Mon 11/08/25 | 2 days | Fri 07/03/25 | Fri 07/03/25 |  | 2064FS+15 days,2063 | 110 days | 111 days | 1 day | DCC |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.2.2 |  |  |  |  | Each LDSO notifies the DCC of any exceptions | 0% | Tue 12/08/25 | Tue 12/08/25 | 1 day | Fri 07/03/25 | Fri 07/03/25 | 2062 | 2064FS+15 days | 112 days | 112 days | 0 days | LDSO |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.2.3 |  |  |  |  | Each LDSO and DCC completes investigation and resolution of exceptions | 0% | Wed 03/09/25 | Wed 03/09/25 | 1 day | Mon 31/03/25 | Mon 31/03/25 | 2062FS+15 days,2063FS+15 days | 2065 | 112 days | 112 days | 0 days | LDSO / DCC |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.6.2.4 |  |  |  |  | Domestic Premises Indicator Complete | 0% | Wed 03/09/25 | Wed 03/09/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 2064 |  | 112 days | 112 days | 0 days |  |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
5 | 1.8.8.6.7 |  |  |  |  | Export / Import MPANs | 67% | Fri 22/03/24 | Fri 18/10/24 | 151 days | Fri 22/03/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
6 | 1.8.8.6.7.1 |  |  |  |  | Linking of Export / Import MPANS | 67% | Fri 22/03/24 | Fri 18/10/24 | 151 days | Fri 22/03/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.7.1.1 |  |  |  |  | LDSO utilises BAU processing (DB05s) to populate each import/export association | 100% | Fri 22/03/24 | Fri 22/03/24 | 1 day | Fri 22/03/24 | Fri 22/03/24 | 2039FS+176 days | 2069FS+19 days | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.7.1.2 |  |  |  |  | Each LDSO notifies the Registered Supplier of any exceptions | 100% | Fri 19/04/24 | Fri 19/04/24 | 1 day | Fri 19/04/24 | Fri 19/04/24 | 2068FS+19 days | 2070FS+89 days | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.7.1.3 |  |  |  |  | Each Supplier completes investigation and resolution of exceptions | 0% | Fri 23/08/24 | Fri 23/08/24 | 1 day | Fri 23/08/24 | Fri 23/08/24 | 2069FS+89 days | 2071FS+40 days | 0 days | 0 days | 0 days | Supplier |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
7 | 1.8.8.6.7.1.4 | T3 | T3-MI-0031 | MCAG (Transition) |  | Each LDSO has linked al relevant import/export MPANS | 0% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 2070FS+40 days | 2072 | 0 days | 0 days | 0 days | LDSO |  | 5.5 | Yes |  | On track...
7 | 1.8.8.6.7.1.5 |  |  |  |  | Linking of Export / Import MPANS Complete | 0% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 2071 |  | 0 days | 0 days | 0 days |  |  | 5.4 | Yes |  | 27/7 - CH added in with Matthew Breen
5 | 1.8.8.6.8 | T2 | T2-MI-0450 | MCAG (Transition) |  | Pre-migration data cleanse complete | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 |  |  | 92 days | 92 days | 0 days | SI Migration |  | 5 | Yes
3 | 1.8.9 |  |  |  |  | Migration Period Planning | 83% | Mon 03/07/23 | Tue 26/11/24 | 367 days | Mon 03/07/23 | Mon 05/10/26 |  |  | 0 days | -484 days | -484 days | N/A |  | 5 | Yes
4 | 1.8.9.1 |  |  |  |  | Migration Implementation Plan (incl. Migration Exit Criteria) | 83% | Mon 03/07/23 | Tue 26/11/24 | 367 days | Mon 03/07/23 | Mon 05/10/26 |  |  | 0 days | -484 days | -484 days | N/A |  | 5 | Yes
5 | 1.8.9.1.1 |  |  |  |  | Migration Threshold Volumes | 100% | Mon 03/07/23 | Mon 20/11/23 | 101 days | Mon 03/07/23 | Wed 15/11/23 |  |  | 0 days | 3 days | 3 days | N/A |  | 5 | Yes
6 | 1.8.9.1.1.1 |  |  |  |  | Threshold volumes reviewed by MWG | 100% | Mon 03/07/23 | Thu 14/09/23 | 54 days | Mon 03/07/23 | Thu 14/09/23 |  | 2078 | 0 days | 0 days | 0 days | SI Migration |  | 5.6 | Yes
6 | 1.8.9.1.1.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 15/09/23 | Mon 20/11/23 | 47 days | Fri 15/09/23 | Wed 15/11/23 | 2077 | 2079 | 0 days | 3 days | 3 days | PP |  | 5.9 | Yes |  | 7/11 - Red because date of TMAG chnaged
6 | 1.8.9.1.1.3 | T3 | T3-MI-0021 | SITAG |  | Threshold volumes approved at TMAG | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 | 2078 |  | 3 days | 3 days | 0 days | SI Migration |  | 5.12 | Yes |  | Red as plan was to approve at extraordinary TMAG on 8/11, however regular TMAG taking place on 15/11 so deferred approval to this date. To go to TMAG for date change. Approved for date change at TMAG on 23/10/23. 7/11 - Red because date of TMAG changed
5 | 1.8.9.1.2 |  |  |  |  | Define acceptance criteria for M15 | 100% | Mon 04/09/23 | Wed 20/12/23 | 78 days | Mon 04/09/23 | Wed 20/12/23 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.9.1.2.1 |  |  |  |  | Review acceptance criteria and reporting requirements with MWG | 100% | Mon 04/09/23 | Thu 09/11/23 | 49 days | Mon 04/09/23 | Fri 27/10/23 |  | 2082 | 0 days | 9 days | 9 days | SI Migration |  | 5 | Yes
6 | 1.8.9.1.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | Fri 10/11/23 | Wed 20/12/23 | 29 days | Fri 10/11/23 | Wed 20/12/23 | 2081 | 2083 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.8.9.1.2.3 | T3 | T3-MI-0022 | SITAG |  | Acceptance criteria for M15 agreed at TMAG | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 2082 | 2085 | 0 days | 0 days | 0 days | SI Migration |  | 5.14 | Yes |  | 17/10 - Red because initial date was not aligned to a TMAG. On track to delivery by 20/12. To go to 20/11/23 TMAG for approval to change date. 20/11 - Date rebaselined. 20/12 - Approved at TMAG on 20/12
5 | 1.8.9.1.3 |  |  |  |  | M10/M11 cut-over plan | 100% | Thu 21/12/23 | Tue 04/06/24 | 119 days | Thu 21/12/23 | Tue 04/06/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
6 | 1.8.9.1.3.1 |  |  |  |  | Draft Document | 100% | Thu 21/12/23 | Tue 16/04/24 | 84 days | Thu 21/12/23 | Tue 16/04/24 | 2083 | 2086 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.9.1.3.2 |  |  |  |  | Share Document with SRO | 100% | Wed 17/04/24 | Wed 17/04/24 | 1 day | Wed 17/04/24 | Wed 17/04/24 | 2085 | 2087FS+3 days | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.9.1.3.3 |  |  |  |  | Industry Consultation | 100% | Tue 23/04/24 | Tue 07/05/24 | 11 days | Tue 23/04/24 | Tue 07/05/24 | 2086FS+3 days | 2088FS+9 days | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.9.1.3.4 |  |  |  |  | Assurance Meeting | 100% | Tue 21/05/24 | Tue 21/05/24 | 1 day | Tue 14/05/24 | Tue 14/05/24 | 2087FS+9 days | 2089FS+10 days | 5 days | 5 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.9.1.3.5 | T3 | T3-MI-0023 | MCAG |  | MCAG Approval of M10/M11 Cut-over Plan | 100% | Tue 04/06/24 | Tue 04/06/24 | 0 days | Tue 04/06/24 | Tue 04/06/24 | 2088FS+10 days |  | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes |  | 27/2 - Approved at MCAG on 27/2/24. 30/4: To go to 8th Red MCAG for rebaselining because MCAG is being rescheduled. 8/5 - Approved date change at MCAG on 8/5/24
5 | 1.8.9.1.4 |  |  |  |  | M16 Methodology | 10% | Wed 31/07/24 | Tue 26/11/24 | 85 days | Wed 31/07/24 | Tue 26/11/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.9.1.4.1 |  |  |  |  | Draft Document | 12% | Wed 31/07/24 | Tue 08/10/24 | 50 days | Wed 31/07/24 | Tue 08/10/24 |  | 2092 | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes
6 | 1.8.9.1.4.2 |  |  |  |  | Share Document with SRO | 0% | Wed 09/10/24 | Wed 09/10/24 | 1 day | Wed 09/10/24 | Wed 09/10/24 | 2091 | 2093FS+3 days | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes
6 | 1.8.9.1.4.3 |  |  |  |  | Industry Consultation | 0% | Tue 15/10/24 | Tue 29/10/24 | 11 days | Tue 15/10/24 | Tue 29/10/24 | 2092FS+3 days | 2094FS+9 days | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes
6 | 1.8.9.1.4.4 |  |  |  |  | Assurance Meeting | 0% | Tue 12/11/24 | Tue 12/11/24 | 1 day | Tue 12/11/24 | Tue 12/11/24 | 2093FS+9 days | 2095FS+10 days | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes
6 | 1.8.9.1.4.5 | T2 | T3-MI-0500 | MCAG (Transition) |  | M16 methodology approved | 0% | Tue 26/11/24 | Tue 26/11/24 | 0 days | Tue 26/11/24 | Tue 26/11/24 | 2094FS+10 days | 2415 | 0 days | 0 days | 0 days | SI Transition | Approved | 5.26 | Yes |  | 27/8/24: Milestone to to to MCAG on 24/9 be renamed because the m15/m16 cutover plan is being combined with the m15/16 cut over plan. Name will change from m16 methodology approved to M15 and M16 Cutover plan and M16 Success Criteria
3 | 1.8.10 |  |  |  |  | Preparation for Cutover to Live | 0% | Mon 31/10/22 | Wed 10/09/25 | 748 days | Fri 28/06/24 | Fri 04/04/25 |  |  | -434 days | 113 days | 547 days | N/A |  | 5.27 | Yes
4 | 1.8.10.1 |  |  |  |  | Central Systems Prepare for Cutover to Live | 0% | Mon 31/10/22 | Fri 15/08/25 | 730 days | Fri 28/06/24 | Fri 14/03/25 |  |  | -434 days | 110 days | 544 days | N/A |  | 5.27 | Yes
5 | 1.8.10.1.1 |  |  |  |  | DCC (Functionality available June 2024) | 100% | Fri 28/06/24 | Fri 28/06/24 | 0 days | Fri 28/06/24 | Fri 28/06/24 |  | 2125FS+1 day | 0 days | 0 days | 0 days | DCC |  | 5.27 | Yes
5 | 1.8.10.1.2 |  |  |  |  | Development of Comms Approach and Declaration Guidance | 0% | Mon 03/03/25 | Thu 19/06/25 | 79 days | Tue 01/10/24 | Fri 17/01/25 |  |  | 109 days | 109 days | 0 days | N/A |  | 5.28 | Yes
6 | 1.8.10.1.2.1 |  |  |  |  | Draft Cutover Comms Approach | 0% | Mon 03/03/25 | Thu 22/05/25 | 59 days | Tue 01/10/24 | Fri 20/12/24 |  | 2101 | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
6 | 1.8.10.1.2.2 |  |  |  |  | Draft Cutover Comms Approach shared | 0% | Thu 22/05/25 | Thu 22/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 2100 | 2104FS+20 days | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
6 | 1.8.10.1.2.3 |  |  |  |  | Development of Implementation Group | 0% | Mon 03/03/25 | Thu 22/05/25 | 59 days | Tue 01/10/24 | Fri 20/12/24 |  | 2103 | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
6 | 1.8.10.1.2.4 |  |  |  |  | Implementation Group Established | 0% | Thu 22/05/25 | Thu 22/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 2102 | 2104FS+20 days | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
6 | 1.8.10.1.2.5 |  |  |  |  | Finalised Cutover Comms Approach shared | 0% | Thu 19/06/25 | Thu 19/06/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 2101FS+20 days,2103FS+20 days | 1317 | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
5 | 1.8.10.1.3 |  |  |  |  | Development of Cutover Plan requirements with Participants | 0% | Mon 03/03/25 | Wed 06/08/25 | 113 days | Tue 01/10/24 | Fri 20/12/24 |  |  | 109 days | 163 days | 54 days | N/A |  | 5.28 | Yes
6 | 1.8.10.1.3.1 |  |  |  |  | Development of SIT Participant Cutover Plans | 0% | Mon 03/03/25 | Thu 22/05/25 | 59 days | Tue 01/10/24 | Fri 20/12/24 |  | 2107 | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
6 | 1.8.10.1.3.2 |  |  |  |  | SIT Participant Cutover Plans Ready | 0% | Thu 22/05/25 | Thu 22/05/25 | 0 days | Fri 20/12/24 | Fri 20/12/24 | 2106 | 2108FS+10 days | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
6 | 1.8.10.1.3.3 |  |  |  |  | Programme SIT Participant Cutover Plan Assurance | 0% | Fri 06/06/25 | Wed 06/08/25 | 44 days | Mon 06/01/25 | Thu 06/03/25 | 2107FS+10 days | 1317 | 109 days | 109 days | 0 days | SI Transition |  | 5.28 | Yes
5 | 1.8.10.1.4 |  |  |  |  | M10/M11 Cutover Activities | 0% | Mon 31/10/22 | Fri 15/08/25 | 730 days | Fri 21/02/25 | Fri 14/03/25 |  |  | -605 days | 110 days | 715 days |  |  | 5.27 | Yes
6 | 1.8.10.1.4.1 |  |  |  |  | Production DIP Portal (DIP Deployment) | 0% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1199FS+10 days | 2133 | 110 days | 110 days | 0 days | Elexon,DIP Manager |  | 5.27 | Yes
6 | 1.8.10.1.4.2 |  |  |  |  | Production Certificates (DIP Deployment) | 0% | Fri 25/07/25 | Fri 25/07/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1199FS+10 days | 2133 | 110 days | 110 days | 0 days | Elexon,DIP Manager |  | 5.27 | Yes
6 | 1.8.10.1.4.3 |  |  |  |  | Completion of the MHHS Data Cleanse | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Wed 26/02/25 | Wed 26/02/25 | 1317 |  | 120 days | 120 days | 0 days | PP,DCC,SI Transition |  | 5.27 | Yes
6 | 1.8.10.1.4.4 |  |  |  |  | Market-wide Participant MHHS Supporting Functionality Ready - Confirmation from Code Bodies | 0% | Mon 03/03/25 | Mon 03/03/25 | 0 days | Mon 03/03/25 | Mon 03/03/25 | 2006FS+501 days |  | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.10.1.4.5 |  |  |  |  | Market-wide Participant MHHS Supporting Functionality Ready | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1317FS-8 days |  | 105 days | 105 days | 0 days | PP |  | 5.27 | Yes
6 | 1.8.10.1.4.6 |  |  |  |  | Elexon Central Services Deployment | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | DIP Manager,Elexon |  | 5.27 | Yes
6 | 1.8.10.1.4.7 |  |  |  |  | Service Management Go-Live | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | Elexon |  | 5.27 | Yes
6 | 1.8.10.1.4.8 |  |  |  |  | Data Transfer Service (DTS) New Functionality Deployment | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | Code Bodies,Electralink |  | 5.27 | Yes
6 | 1.8.10.1.4.9 |  |  |  |  | Electricity Enquiry Service (EES) Deployment | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.8.10.1.4.10 |  |  |  |  | MPRS, UMSO Role, LDSO Role Operational | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | PP |  | 5.27 | Yes
6 | 1.8.10.1.4.11 |  |  |  |  | Population of Domestic Premises Indicator | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | PP,DCC,SI Transition |  | 5.27 | Yes
6 | 1.8.10.1.4.12 |  |  |  |  | Population of Market Segment | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 2125FS+1 day | 110 days | 110 days | 0 days | PP,SI Transition |  | 5.27 | Yes
6 | 1.8.10.1.4.13 |  |  |  |  | Early Life Support Implemented | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2134 | 1317 | 110 days | 110 days | 0 days | SI Transition,Elexon,Central Services |  | 5.27 | Yes
6 | 1.8.10.1.4.14 |  |  |  |  | MCC Tested and Ready to Operate | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Fri 07/03/25 | Fri 07/03/25 |  | 21242212 | -615 days | -615 days | 0 days | SI Migration |  | 5.27 | Yes
6 | 1.8.10.1.4.15 |  |  |  |  | MCC Operational | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2123 | 1317 | -615 days | -615 days | 0 days | SI Migration |  | 5.27 | Yes
6 | 1.8.4.1.4 |  | T3-MI-0034 | MCAG (Transition) |  | Central Systems live and Codes designated at 00:00 | 0% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2115FS+1 day,2116FS+1 day,2117FS+1 day,2118FS+1 day,2119FS+1 day,2120FS+1 day,2121FS+1 day,2098FS+1 day | 1317FS+2 days | 111 days | 111 days | 0 days | SI Transition | Proposed | 5.3 | Yes |  | 6/8/24: Forecast date updated to correctly reflect the cutover plan which was approved in June. To go to August MCAG for date change approval
6 | 1.8.10.1.4.17 |  |  |  |  | SIT Participant Qualification - The final date by which participant qualification status can be confirmed for participants to be ready for the start of Migration at M11. | 0% | Fri 15/08/25 | Fri 15/08/25 | 0 days | Fri 14/03/25 | Fri 14/03/25 | 1199FS+25 days | 2145 | 110 days | 110 days | 0 days | PP,Code Bodies,BSC PAB |  | 5.27 | Yes
4 | 1.8.10.2 |  |  |  |  | Cutover Governance M10 | 0% | Wed 30/07/25 | Wed 13/08/25 | 11 days | Wed 26/02/25 | Fri 04/04/25 |  |  | 109 days | 93 days | -16 days | N/A |  | 5.27 | Yes
5 | 1.8.10.2.1 |  |  |  |  | Confirmation that Pre-migration Data Cleanse Activities have successfully taken place | 0% | Wed 30/07/25 | Wed 30/07/25 | 0 days | Wed 26/02/25 | Wed 26/02/25 |  | 2133 | 109 days | 109 days | 0 days | PP |  | 5.27 | Yes
5 | 1.8.10.2.2 |  |  |  |  | Confirmation of Qualification Status for SIT MVC | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 03/03/25 | Mon 03/03/25 | 1199FS+16 days | 2131,2133FS+2 days | 110 days | 110 days | 0 days | SIT MVC,Code Bodies |  | 5.27 | Yes
5 | 1.8.10.2.3 |  |  |  |  | Confirmation of Qualification Status for Non-SIT LDSOs | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 03/03/25 | Mon 03/03/25 | 2134FS-5 days |  | 109 days | 109 days | 0 days | PP,Code Bodies |  | 5.27 | Yes
5 | 1.8.10.2.4 |  |  |  |  | Confirmation of Qualification Status of at least one Supplier and their contracted Agents | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 03/03/25 | Mon 03/03/25 | 2129 | 2133FS+2 days | 110 days | 110 days | 0 days | S&A Qualification |  | 5.27 | Yes
5 | 1.8.10.2.5 |  |  |  |  | Declaration from all Central Services and LDSOs that they are in a position to move forwards | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 03/03/25 | Mon 03/03/25 | 2134FS-5 days |  | 109 days | 109 days | 0 days | DIP Manager,Elexon,PP,Code Bodies |  | 5.27 | Yes
5 | 1.8.10.2.6 |  |  |  |  | TORWG (Recommendation from TORWG that the Programme should enter M10) | 0% | Wed 06/08/25 | Wed 06/08/25 | 0 days | Wed 05/03/25 | Wed 05/03/25 | 2128,2129FS+2 days,2131FS+2 days,2110,2111,2216 | 2134FS+2 days | 110 days | 110 days | 0 days | SI Transition |  | 5.27 | Yes
5 | 1.8.4.1.4 |  | T3-MI-0035 | MCAG (Transition) |  | MCAG (Confirm that the Programme can Enter M10) | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 2133FS+2 days,2222 | 2115,2116,2117,2118,2119,2120,2121,2135FS+1 day,2136FS+1 day,2137FS+1 day,2138FS+1 day,1317,2122,2130FS-5 days,2132FS-5 days | 110 days | 110 days | 0 days | SI Migration | Approved | 5.3 | Yes |  | 18/6: New T3 milestone agreed at MCAG on 4/6/24
5 | 1.8.10.2.8 |  |  |  |  | Self-Declaration from all Central Services and LDSOs that Cutover activities have been successfully carried out | 0% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Mon 10/03/25 | Mon 10/03/25 | 2134FS+1 day | 2139FS+1 day | 110 days | 110 days | 0 days | PP,DCC,Code Bodies |  | 5.27 | Yes
5 | 1.8.10.2.9 |  |  |  |  | Confirmation that DIP and ECS have been deployed, Service management is active, ISD has been populated | 0% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Mon 10/03/25 | Mon 10/03/25 | 2134FS+1 day | 2139FS+1 day | 110 days | 110 days | 0 days | Elexon,DIP Manager |  | 5.27 | Yes
5 | 1.8.10.2.10 |  |  |  |  | Self-Declarations against all M10 Data Cleanse Activities | 0% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Mon 10/03/25 | Mon 10/03/25 | 2134FS+1 day | 2139FS+1 day | 110 days | 110 days | 0 days | PP |  | 5.27 | Yes
5 | 1.8.10.2.11 |  |  |  |  | IF-047 has been sent | 0% | Mon 11/08/25 | Mon 11/08/25 | 0 days | Mon 10/03/25 | Mon 10/03/25 | 2134FS+1 day | 2139FS+1 day | 110 days | 110 days | 0 days | ECS |  | 5.27 | Yes
5 | 1.8.10.2.12 |  |  |  |  | Recommendation from TORWG that PSG should approve M10 | 0% | Tue 12/08/25 | Tue 12/08/25 | 0 days | Tue 11/03/25 | Tue 11/03/25 | 2135FS+1 day,2136FS+1 day,2137FS+1 day,2138FS+1 day,2220 | 2140FS+1 day | 110 days | 110 days | 0 days | SI Transition |  | 5.27 | Yes
5 | 1.8.10.2.13 |  |  |  |  | PSG (OFGEM and PSG to Approve That Conditions of M10 and M13 Have Been Met) | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Wed 12/03/25 | Wed 12/03/25 | 2139FS+1 day | 2142FS+1 day,2143FS+12 days,2144FS+12 days | 110 days | 110 days | 0 days | SI Transition,Ofgem |  | 5.27 | Yes
4 | 1.8.10.3 |  |  |  |  | Cutover Governance M11 | 0% | Fri 15/08/25 | Wed 10/09/25 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  |  | Yes
5 | 1.8.10.3.1 |  |  |  |  | Confirmation of Qualified Parties from Code Bodies | 0% | Fri 15/08/25 | Fri 29/08/25 | 11 days | Fri 14/03/25 | Fri 28/03/25 | 2140FS+1 day | 2145FS+1 day | 110 days | 110 days | 0 days | Code Bodies,SIT Participants |  | 5.27 | Yes
5 | 1.8.10.3.2 |  |  |  |  | Self-Declaration that MHHS Functionality will be deployed to Production by Qualified parties | 0% | Fri 29/08/25 | Fri 29/08/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 2140FS+12 days | 2145FS+1 day | 110 days | 110 days | 0 days | PP |  | 5.27 | Yes
5 | 1.8.10.3.3 |  |  |  |  | Production Service Activation Activities have taken place | 0% | Fri 29/08/25 | Fri 29/08/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 2140FS+12 days | 2145FS+1 day | 110 days | 110 days | 0 days | PP |  | 5.27 | Yes
5 | 1.8.10.3.4 |  |  |  |  | TORWG (Confirmation of Qualified Parties from TORWG) | 0% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 2142FS+1 day,2143FS+1 day,2144FS+1 day,2126,2217,2221 | 2146FS+4 days | 110 days | 110 days | 0 days | SI Transition |  | 5.27 | Yes
5 | 1.8.10.3.5 |  | T3-MI-0036 | MCAG (Transition) |  | MCAG (Provide recommendation to PSG on M11 decision) | 0% | Fri 05/09/25 | Fri 05/09/25 | 0 days | Wed 02/04/25 | Wed 02/04/25 | 2145FS+4 days | 2178,2147FS+3 days | 112 days | 112 days | 0 days | SI Migration | Approved | 5.3 | Yes |  | 18/6: New T3 milestone agreed at MCAG on 4/6/24
5 | 1.8.10.3.6 |  |  |  |  | PSG (OFGEM and PSG Decision to Confirm M11 and M12) | 0% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 2146FS+3 days | 2178 | 113 days | 113 days | 0 days | SI Transition |  | 5.27 | Yes
3 | 1.8.11 |  |  |  |  | UMS / Advanced Migration | 0% | Thu 11/09/25 | Fri 12/03/27 | 392 days | Fri 04/04/25 | Fri 02/10/26 |  |  | 114 days | 115 days | 1 day | N/A |  | 5.24 | Yes
4 | 1.8.11.1 |  |  |  |  | SIT MVC UMS / Advanced Migration | 0% | Thu 11/09/25 | Thu 11/03/27 | 391 days | Fri 04/04/25 | Fri 02/10/26 | 22222178 | 2182,2198SS | 114 days | 114 days | 0 days |  |  | 5.24 | Yes
4 | 1.8.11.2 |  |  |  |  | SIT Non-MVC UMS / Advanced Migration | 0% | Thu 27/11/25 | Thu 25/02/27 | 326 days | Fri 04/07/25 | Fri 02/10/26 | 2243 | 2182 | 104 days | 104 days | 0 days |  |  | 5.24 | Yes
4 | 1.8.11.3 |  |  |  |  | Wave 1 UMS / Advanced Migration | 0% | Fri 27/03/26 | Fri 12/03/27 | 251 days | Fri 03/10/25 | Fri 02/10/26 | 2259 | 2182 | 125 days | 115 days | -10 days |  |  | 5.24 | Yes
4 | 1.8.11.4 |  |  |  |  | Wave 2 UMS / Advanced Migration | 0% | Thu 14/05/26 | Fri 12/03/27 | 217 days | Fri 05/12/25 | Fri 02/10/26 | 2283 | 2182 | 114 days | 115 days | 1 day |  |  | 5.24 | Yes
4 | 1.8.11.5 |  |  |  |  | Wave 3 UMS / Advanced Migration | 0% | Thu 02/07/26 | Fri 12/03/27 | 182 days | Fri 23/01/26 | Fri 02/10/26 | 2307 | 2182 | 114 days | 115 days | 1 day |  |  | 5.24 | Yes
4 | 1.8.11.6 |  |  |  |  | Wave 4 UMS / Advanced Migration | 0% | Fri 04/09/26 | Fri 12/03/27 | 136 days | Fri 03/04/26 | Fri 02/10/26 | 2331 | 2182 | 110 days | 115 days | 5 days |  |  | 5.24 | Yes
3 | 1.8.12 |  |  |  |  | Smart / Non-Smart Migration | 0% | Thu 11/09/25 | Fri 12/03/27 | 392 days | Fri 04/04/25 | Fri 02/10/26 |  |  | 114 days | 115 days | 1 day | N/A |  | 5.24 | Yes
4 | 1.8.12.1 |  |  |  |  | SIT MVC Smart / Non-Smart Migration | 0% | Thu 11/09/25 | Thu 11/03/27 | 391 days | Fri 04/04/25 | Fri 02/10/26 | 22222178 | 2182,2198SS | 114 days | 114 days | 0 days |  |  | 5.24 | Yes
4 | 1.8.12.2 |  |  |  |  | SIT Non-MVC Smart / Non-Smart Migration | 0% | Thu 27/11/25 | Thu 25/02/27 | 326 days | Fri 04/07/25 | Fri 02/10/26 | 2243 | 2182 | 104 days | 104 days | 0 days |  |  | 5.24 | Yes
4 | 1.8.12.3 |  |  |  |  | Wave 1 Smart / Non-Smart Migration | 0% | Fri 27/03/26 | Fri 12/03/27 | 251 days | Fri 03/10/25 | Fri 02/10/26 | 2259 | 2182 | 125 days | 115 days | -10 days |  |  | 5.24 | Yes
4 | 1.8.12.4 |  |  |  |  | Wave 2 Smart / Non-Smart Migration | 0% | Thu 14/05/26 | Fri 12/03/27 | 217 days | Fri 05/12/25 | Fri 02/10/26 | 2283 | 2182 | 114 days | 115 days | 1 day |  |  | 5.24 | Yes
4 | 1.8.12.5 |  |  |  |  | Wave 3 Smart / Non-Smart Migration | 0% | Thu 02/07/26 | Fri 12/03/27 | 182 days | Fri 23/01/26 | Fri 02/10/26 | 2307 | 2182 | 114 days | 115 days | 1 day |  |  | 5.24 | Yes
4 | 1.8.12.6 |  |  |  |  | Wave 4 Smart / Non-Smart Migration | 0% | Fri 04/09/26 | Fri 12/03/27 | 136 days | Fri 03/04/26 | Fri 02/10/26 | 2331 | 2182FS+1 day | 110 days | 115 days | 5 days |  |  | 5.24 | Yes
3 | 1.8.13 |  |  |  |  | External Programme Dependency Management | 66% | Mon 31/10/22 | Wed 23/07/25 | 713 days | Mon 31/10/22 | Tue 30/12/25 |  |  | 0 days | -114 days | -114 days | N/A |  | 5 | Yes
4 | 1.8.13.1 |  |  |  |  | BSC Mod P432 & REC CP R0015 | 100% | Mon 31/10/22 | Tue 30/04/24 | 392 days | Mon 31/10/22 | Tue 30/12/25 |  |  | 0 days | -435 days | -435 days | N/A |  | 5 | Yes
5 | 1.8.13.1.1 |  |  |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | Mon 31/10/22 | Mon 15/01/24 | 316 days | Mon 31/10/22 | Fri 10/05/24 |  | 2165 | 0 days | -84 days | -84 days | CPT,SRO Function |  | 5 | Yes
5 | 1.8.13.1.2 |  |  |  |  | Monitor progress and await implementation date | 100% | Tue 16/01/24 | Tue 30/04/24 | 76 days | Mon 03/07/23 | Tue 30/12/25 | 2164 |  | 141 days | -435 days | -576 days | CPT,SRO Function |  | 5 | Yes
4 | 1.8.13.2 |  |  |  |  | BSC Mod P434 | 57% | Mon 31/10/22 | Wed 23/07/25 | 713 days | Mon 31/10/22 | Wed 23/07/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.13.2.1 |  |  |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | Mon 31/10/22 | Mon 23/01/23 | 61 days | Mon 31/10/22 | Mon 23/01/23 |  | 2168 | 0 days | 0 days | 0 days | CPT,SRO Function |  | 5 | Yes
5 | 1.8.13.2.2 |  |  |  |  | Monitor progress and await implementation date | 52% | Tue 24/01/23 | Wed 23/07/25 | 652 days | Tue 24/01/23 | Wed 23/07/25 | 2167 |  | 0 days | 0 days | 0 days | CPT,SRO Function |  | 5 | Yes
4 | 1.8.13.3 |  |  |  |  | Elexon System Capacity Upgrade | 58% | Mon 31/10/22 | Tue 01/07/25 | 697 days | Mon 31/10/22 | Tue 01/07/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.13.3.1 |  |  |  |  | Monitor progress to implementation | 58% | Mon 31/10/22 | Tue 01/07/25 | 697 days | Mon 31/10/22 | Tue 01/07/25 |  | 2171 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.13.3.2 |  |  |  |  | Implementation date | 0% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 | 2170 |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.8.13.4 |  |  |  |  | DCC System Capacity Upgrade | 0% | Mon 16/06/25 | Fri 18/07/25 | 25 days | Mon 13/01/25 | Fri 14/02/25 |  |  | 110 days | 110 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.13.4.1 |  |  |  |  | Assurance of DCC capacity upgrade to ensure suitability to support migration | 0% | Mon 16/06/25 | Fri 11/07/25 | 20 days | Mon 13/01/25 | Fri 07/02/25 | 1317FF-23 days | 2174FS+5 days | 110 days | 110 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.13.4.2 | T2 | T2-MI-0350 | MCAG |  | DCC Capacity Upgrade Operational | 0% | Fri 18/07/25 | Fri 18/07/25 | 0 days | Fri 14/02/25 | Fri 14/02/25 | 2173FS+5 days |  | 110 days | 110 days | 0 days | PP |  | 5 | Yes
3 | 1.8.14 |  |  |  |  | Migration - Tier 1 Milestones | 0% | Wed 13/08/25 | Tue 15/06/27 | 479 days | Fri 07/03/25 | Tue 05/01/27 |  |  | 113 days | 115 days | 2 days | N/A |  | 5 | Yes
4 | 1.8.14.1 | T1 | T1-MI-2000 | PSG |  | Load Shaping Service switched on (M13) | 0% | Wed 13/08/25 | Wed 13/08/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1317 | 2177FS+65 days,2178,2180,2519FS-3 mons | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.2 | T1 | T2-MI-2500 | PSG |  | Load Shaping Service switched on (M13*) - Late Exit | 0% | Wed 12/11/25 | Wed 12/11/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 2176FS+65 days |  | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.3 | T1 | T1-MI-3000 | PSG |  | Start of 18-month migration for UMS / Advanced (M11) | 0% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 2176,2146,2147,2222,1317FS+20 days | 2179FS+65 days,2519FS-3 mons,2403,2149,2156 | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.4 | T1 | T2-MI-3500 | PSG |  | Start of 18-month migration for UMS / Advanced (M11*) - Late Exit | 0% | Wed 10/12/25 | Wed 10/12/25 | 0 days | Fri 04/07/25 | Fri 04/07/25 | 2178FS+65 days |  | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.5 | T1 | T1-MI-4000 | PSG |  | Start of 18-month migration for Smart / Non-smart (M12) | 0% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 2176,1317FS+20 days | 2392FS-45 days,2181FS+65 days,2519FS-3 mons | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.6 | T1 | T2-MI-4500 | PSG |  | Start of 18-month migration for Smart / Non-smart (M12*) - Late Exit | 0% | Wed 10/12/25 | Wed 10/12/25 | 0 days | Fri 04/07/25 | Fri 04/07/25 | 2180FS+65 days |  | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.7 | T1 | T1-MI-6000 | PSG |  | Full transition complete (M15) | 0% | Mon 15/03/27 | Mon 15/03/27 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2149,2150,2151,2152,2153,2154,2156,2157,2158,2159,2160,2161FS+1 day | 2420,2425FS-45 days,2433FS-45 days,2437FS-45 days,2441FS-45 days,2445FS-45 days,2449FS-45 days,2453FS-45 days,2183FS+66 days,2523FS-3 mons,2415FS+40 days | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
4 | 1.8.14.8 | T1 | T2-MI-6500 | PSG |  | Full transition complete (M15*) - Late Exit | 0% | Tue 15/06/27 | Tue 15/06/27 | 0 days | Tue 05/01/27 | Tue 05/01/27 | 2182FS+66 days |  | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
2 | 1.9 |  |  |  |  | BUSINESS & OPERATIONAL READINESS | 6% | Mon 31/10/22 | Tue 26/08/49 | 33087 days? | Tue 19/09/23 | Fri 28/05/27 |  |  | -231 days | 31892 days | 32123 days? | N/A |  |  | Yes
3 | 1.9.1 |  |  |  |  | Service Management | 26% | Tue 19/09/23 | Thu 13/05/27 | 953 days | Tue 19/09/23 | Mon 07/12/26 |  |  | 0 days | 113 days | 113 days | N/A |  | 5 | Yes
4 | 1.9.1.1 |  |  |  |  | Service Management Strategy | 100% | Tue 19/09/23 | Tue 27/02/24 | 116 days | Tue 19/09/23 | Tue 27/02/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.9.1.1.1 |  |  |  |  | Develop document with relevant participants (incl. review of the design baseline to ensure service management arrangements are in place across the solution architecture) | 100% | Tue 19/09/23 | Fri 12/01/24 | 84 days | Tue 19/09/23 | Fri 12/01/24 |  | 2188 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.9.1.1.2 |  |  |  |  | Artefact review (via relevant Advisory Group) and updates | 100% | Mon 15/01/24 | Mon 26/02/24 | 31 days | Mon 15/01/24 | Mon 26/02/24 | 2187 | 2189FS+1 day | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.9.1.1.3 | T3 | T3-BC-0010 | MCAG |  | Service Management Strategy approved | 100% | Tue 27/02/24 | Tue 27/02/24 | 0 days | Tue 27/02/24 | Tue 27/02/24 | 2188FS+1 day | 2191 | 0 days | 0 days | 0 days | SI Design |  | 5.16 | Yes |  | 17/1 - Baseline change approved at TMAG to change date from 21/2/24 to 27/2/24. Changed because MCAG has been scheduled for 27/2/24. Approved at TMAG on 7/1/24
4 | 1.9.1.2 |  |  |  |  | Early Life Support Model | 82% | Wed 28/02/24 | Tue 30/07/24 | 110 days | Wed 28/02/24 | Tue 30/07/24 |  |  | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
5 | 1.9.1.2.1 |  |  |  |  | Draft Document | 96% | Wed 28/02/24 | Mon 10/06/24 | 74 days | Wed 28/02/24 | Mon 10/06/24 | 2189 | 2192 | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.2 |  |  |  |  | Share document with SRO | 0% | Tue 11/06/24 | Tue 11/06/24 | 1 day | Tue 11/06/24 | Tue 11/06/24 | 2191 | 2193FS+4 days | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.3 |  |  |  |  | Industry Consultation | 0% | Tue 18/06/24 | Tue 02/07/24 | 11 days | Tue 18/06/24 | Tue 02/07/24 | 2192FS+4 days | 2194FS+9 days | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.4 |  |  |  |  | Assurance Meeting | 0% | Tue 16/07/24 | Tue 16/07/24 | 1 day | Tue 16/07/24 | Tue 16/07/24 | 2193FS+9 days | 2195FS+10 days | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.5 |  | T3-MI-0033 | MCAG (Transition) |  | MCAG Approval of Early Life Support Model | 100% | Tue 30/07/24 | Tue 30/07/24 | 0 days | Tue 30/07/24 | Tue 30/07/24 | 2194FS+10 days | 2387 | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes |  | Date has been missed because of late input from Code-Bodies. This input has now been received and we are looking to finalise the document and schedule the industry consultation and then confirm an updated baseline date. Baseline date to be approved at Sep
4 | 1.9.1.3 |  |  |  |  | Service Management Arrangements Implementation | 0% | Thu 14/08/25 | Thu 13/05/27 | 456 days | Thu 13/03/25 | Mon 07/12/26 |  |  | 110 days | 113 days | 3 days | N/A |  | 5 | Yes
5 | 1.9.1.3.1 |  |  |  |  | Hypercare post M10 | 0% | Thu 14/08/25 | Wed 03/12/25 | 80 days | Thu 13/03/25 | Wed 02/07/25 | 1317 |  | 110 days | 110 days | 0 days | SI Design |  | 5 | Yes |  | 10/5: Detail to be added when available
5 | 1.9.1.3.2 |  |  |  |  | Monitor Elexon implementation of Service Management arrangements | 0% | Thu 11/09/25 | Thu 13/05/27 | 436 days | Mon 07/04/25 | Mon 07/12/26 | 2149SS,2156SS |  | 113 days | 113 days | 0 days | PP |  | 5 | Yes |  | 10/5: Detail to be added when available
3 | 1.9.2 |  |  |  |  | Service Activation | 0% | Mon 31/10/22 | Thu 03/09/26 | 1004 days? | Mon 24/02/25 | Thu 02/04/26 |  |  | -605 days | 110 days | 715 days? | N/A |  | 5.24 | Yes |  | 8/7/24: Likely Servce action will be on a pp by pp basis
4 | 1.9.2.1 |  |  |  |  | SIT MVC | 0% | Mon 31/10/22 | Mon 11/08/25 | 726 days? | NA | NA |  |  | 0 days | 0 days | 726 days? |  |  | 5.31 | Yes
5 | 1.9.2.1.1 |  |  |  |  | SIT MVC Service Activation Preparation Tasks | 0% | Mon 03/02/25 | Fri 28/02/25 | 20 days | NA | NA |  |  | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.1 |  |  |  |  | Identify operational resources | 0% | Mon 03/02/25 | Fri 07/02/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.2 |  |  |  |  | Define and approve operational support model | 0% | Mon 10/02/25 | Fri 14/02/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.3 |  |  |  |  | Confirm SA Training completed | 0% | Mon 10/02/25 | Fri 21/02/25 | 10 days | NA | NA |  |  | 0 days | 0 days | 10 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.4 |  |  |  |  | Participant Engagement / Communications | 0% | Mon 10/02/25 | Fri 28/02/25 | 15 days | NA | NA |  |  | 0 days | 0 days | 15 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.5 |  |  |  |  | Internal Communications | 0% | Mon 10/02/25 | Fri 28/02/25 | 15 days | NA | NA |  |  | 0 days | 0 days | 15 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.6 |  |  |  |  | Validate User Access | 0% | Mon 17/02/25 | Fri 21/02/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.7 |  |  |  |  | Target Systems and Environments Ready | 0% | Thu 20/02/25 | Mon 24/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days | HELIX |  | 5.31 | Yes
6 | 1.9.2.1.1.8 |  |  |  |  | Provide opeartional resources with LWIs | 0% | Mon 17/02/25 | Fri 21/02/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.9 |  |  |  |  | Business Readiness Governance Approval | 0% | Mon 17/02/25 | Wed 19/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.10 |  |  |  |  | SIT MVC Service Activation Preparation Tasks Complete | 0% | Fri 28/02/25 | Fri 28/02/25 | 0 days | NA | NA |  | 2214 | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.1.2 |  |  |  |  | MHHSP Confirms SIT MVC PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA | 2123 | 2214 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: For M11 need mcc enabled - need confirmation suppliers agree to being mhhs enabled
5 | 1.9.2.1.3 |  |  |  |  | SIT MVC Service Activation Implementation | 0% | Fri 01/08/25 | Mon 11/08/25 | 7 days? | NA | NA |  |  | 0 days | 0 days | 7 days? |  |  | 5.31 | Yes
6 | 1.9.2.1.3.1 |  |  |  |  | Add EDF to DIP | 0% | Fri 01/08/25 | Fri 01/08/25 | 1 day | NA | NA | 1511SS,2212,2211 | 2215 | 0 days | 0 days | 1 day |  |  | 5.31 | Yes
6 | 1.9.2.1.3.2 |  |  |  |  | DIP Promoted to Production | 0% | Mon 04/08/25 | Mon 04/08/25 | 1 day? | NA | NA | 2214 | 221822162217 | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.9.2.1.3.3 |  |  |  |  | SIT LDSOs Create Certificates and Test Connectivity | 0% | Tue 05/08/25 | Tue 05/08/25 | 1 day? | NA | NA | 2215 | 2133 | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.9.2.1.3.4 |  |  |  |  | SIT MVC S&As Create Certificates and Test Connectivity | 0% | Tue 05/08/25 | Tue 05/08/25 | 1 day? | NA | NA | 2215 | 2145 | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.9.2.1.3.5 |  |  |  |  | Create M16 in Customer Solution | 0% | Tue 05/08/25 | Wed 06/08/25 | 2 days | NA | NA | 2215 | 2219 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes |  | 18/09/24 - This milestone is consistent with the Service Activation Verison 2.0 Process Map.
6 | 1.9.2.1.3.6 |  |  |  |  | Publish ISD | 0% | Thu 07/08/25 | Fri 08/08/25 | 2 days | NA | NA | 2218 | 222222202221 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.1.3.7 |  |  |  |  | SIT LDSOs to update systems with ISD | 0% | Mon 11/08/25 | Mon 11/08/25 | 1 day? | NA | NA | 2219 | 2139 | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.9.2.1.3.8 |  |  |  |  | SIT MVC S&As to update systems with ISD | 0% | Mon 11/08/25 | Mon 11/08/25 | 1 day? | NA | NA | 2219 | 2145 | 0 days | 0 days | 1 day? |  |  |  | Yes
6 | 1.9.2.1.3.9 |  |  |  |  | SIT MVC Service Activation Implementation Complete | 0% | Fri 08/08/25 | Fri 08/08/25 | 0 days | NA | NA | 2219 | 2178214921562130 | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.1.4 |  |  |  |  | SIT MVC Service Activation Implementation MDD | 0% | Thu 06/03/25 | Tue 25/03/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.1.4.1 |  |  |  |  | MDD Manual Load | 0% | Thu 06/03/25 | Fri 14/03/25 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.1.4.2 |  |  |  |  | MDD Update | 0% | Fri 14/03/25 | Tue 25/03/25 | 8 days | NA | NA |  |  | 0 days | 0 days | 8 days |  |  | 5.31 | Yes
6 | 1.9.2.1.4.3 |  |  |  |  | SIT MVC Service Activation Implementation MDD Complete | 0% | Tue 25/03/25 | Tue 25/03/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.1.5 |  |  |  |  | SIT MVC Service Activation Hypercare | 0% | Mon 03/03/25 | Wed 26/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.1.5.1 |  |  |  |  | Service & Process Monitoring | 0% | Mon 03/03/25 | Wed 26/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.1.5.2 |  |  |  |  | Daily Reporting | 0% | Mon 03/03/25 | Wed 26/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.1.5.3 |  |  |  |  | Issue Management | 0% | Mon 03/03/25 | Wed 26/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.1.5.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 03/03/25 | Wed 26/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.1.5.5 |  |  |  |  | Handover to MHHSP | 0% | Fri 21/03/25 | Tue 25/03/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days |  |  | 5.31 | Yes
6 | 1.9.2.1.5.6 |  |  |  |  | SIT MVC Service Activation Hypercare Complete | 0% | Tue 25/03/25 | Tue 25/03/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.2 |  |  |  |  | SIT Non-MVC | 0% | Mon 31/10/22 | Wed 26/11/25 | 803 days | NA | NA |  |  | 0 days | 0 days | 803 days |  |  | 5.31 | Yes
5 | 1.9.2.2.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  |  | 0 days | 0 days | 1 day |  |  | 5.31 | Yes
6 | 1.9.2.2.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.2.1.2 |  |  |  |  | MHHSP Confirms SIT Non-MVC PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  | 2239 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: Confirm Predecessors
5 | 1.9.2.2.2 |  |  |  |  | SIT Non-MVC Service Activation Implementation | 0% | Mon 17/11/25 | Wed 26/11/25 | 8 days | NA | NA |  |  | 0 days | 0 days | 8 days |  |  | 5.31 | Yes
6 | 1.9.2.2.2.1 |  |  |  |  | Add EDF to DIP | 0% | Mon 17/11/25 | Tue 18/11/25 | 2 days | NA | NA | 1517SS,2237 | 2240 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.2.2.2 |  |  |  |  | DIP Promoted to Production | 0% | Wed 19/11/25 | Thu 20/11/25 | 2 days | NA | NA | 2239 | 2241 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.2.2.3 |  |  |  |  | Create M16 in Customer Solution | 0% | Fri 21/11/25 | Mon 24/11/25 | 2 days | NA | NA | 2240 | 2242 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.2.2.4 |  |  |  |  | Publish ISD | 0% | Tue 25/11/25 | Wed 26/11/25 | 2 days | NA | NA | 2241 | 2243 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.2.2.5 |  |  |  |  | SIT Non-MVC Service Activation Implementation Complete | 0% | Wed 26/11/25 | Wed 26/11/25 | 0 days | NA | NA | 2242 | 21502157 | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.2.3 |  |  |  |  | SIT Non-MVC Service Activation Implementation MDD | 0% | Thu 05/06/25 | Tue 24/06/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.2.3.1 |  |  |  |  | MDD Manual Load | 0% | Thu 05/06/25 | Fri 13/06/25 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.2.3.2 |  |  |  |  | MDD Update | 0% | Fri 13/06/25 | Tue 24/06/25 | 8 days | NA | NA |  |  | 0 days | 0 days | 8 days |  |  | 5.31 | Yes
6 | 1.9.2.2.3.3 |  |  |  |  | SIT Non-MVC Service Activation Implementation MDD Complete | 0% | Tue 24/06/25 | Tue 24/06/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.2.4 |  |  |  |  | Non-SIT MVC Service Activation Hypercare | 0% | Mon 02/06/25 | Thu 26/06/25 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.2.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Mon 02/06/25 | Wed 25/06/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.2.4.2 |  |  |  |  | Daily Reporting | 0% | Mon 02/06/25 | Wed 25/06/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.2.4.3 |  |  |  |  | Issue Management | 0% | Mon 02/06/25 | Wed 25/06/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.2.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 02/06/25 | Wed 25/06/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.2.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 23/06/25 | Thu 26/06/25 | 4 days | NA | NA |  |  | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.2.4.6 |  |  |  |  | Non-SIT MVC Service Activation Hypercare Complete (M) | 0% | Wed 25/06/25 | Wed 25/06/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.3 |  |  |  |  | Wave 1 | 0% | Mon 31/10/22 | Thu 26/03/26 | 889 days | NA | NA |  |  | 0 days | 0 days | 889 days |  |  | 5.31 | Yes
5 | 1.9.2.3.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | Mon 31/10/22 | Thu 26/03/26 | 889 days | NA | NA |  |  | 0 days | 0 days | 889 days |  |  | 5.31 | Yes
6 | 1.9.2.3.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.3.1.2 |  |  |  |  | MHHSP Confirms Wave 1 PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  | 2259 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: Confirm Predecessors
6 | 1.9.2.3.1.3 |  |  |  |  | Wave 1 Service Activation | 0% | Mon 23/02/26 | Thu 26/03/26 | 24 days | Fri 29/08/25 | Thu 02/10/25 | 17052258 | 21512158 | 126 days | 125 days | -1 day |  |  | 5.24 | Yes
5 | 1.9.2.3.2 |  |  |  |  | Wave 1 - Service Activation Implementation | 0% | Mon 01/09/25 | Fri 05/09/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | Mon 01/09/25 | Tue 02/09/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.2 |  |  |  |  | PAB Approval | 0% | Mon 01/09/25 | Tue 02/09/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.3 |  |  |  |  | Add EDF to DIP | 0% | Tue 02/09/25 | Wed 03/09/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.4 |  |  |  |  | DIP Promoted to Production | 0% | Wed 03/09/25 | Thu 04/09/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | Thu 04/09/25 | Fri 05/09/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.6 |  |  |  |  | Publish ISD | 0% | Thu 04/09/25 | Fri 05/09/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.7 |  |  |  |  | Wave 1 - Service Activation Implementation Complete (M) | 0% | Fri 05/09/25 | Fri 05/09/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.3.3 |  |  |  |  | Wave 1 - Service Activation Implementation MDD | 0% | Thu 04/09/25 | Wed 17/09/25 | 10 days | NA | NA |  |  | 0 days | 0 days | 10 days |  |  | 5.31 | Yes
6 | 1.9.2.3.3.1 |  |  |  |  | MDD Manual Load | 0% | Thu 04/09/25 | Wed 10/09/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.3.3.2 |  |  |  |  | MDD Update | 0% | Wed 10/09/25 | Wed 17/09/25 | 6 days | NA | NA |  |  | 0 days | 0 days | 6 days |  |  | 5.31 | Yes
6 | 1.9.2.3.3.3 |  |  |  |  | Wave 1 - Service Activation Implementation MDD Complete (M) | 0% | Wed 17/09/25 | Wed 17/09/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.3.4 |  |  |  |  | Wave 1 - Service Activation Hypercare | 0% | Mon 31/10/22 | Thu 18/09/25 | 754 days | NA | NA |  |  | 0 days | 0 days | 754 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Mon 01/09/25 | Thu 18/09/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.2 |  |  |  |  | Daily Reporting | 0% | Mon 01/09/25 | Thu 18/09/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.3 |  |  |  |  | Issue Management | 0% | Mon 01/09/25 | Thu 18/09/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 01/09/25 | Thu 18/09/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 15/09/25 | Thu 18/09/25 | 4 days | NA | NA |  |  | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.6 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Complete (M) | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.4 |  |  |  |  | Wave 2 | 0% | Mon 31/10/22 | Wed 13/05/26 | 923 days | NA | NA |  |  | 0 days | 0 days | 923 days |  |  | 5.31 | Yes
5 | 1.9.2.4.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | Mon 31/10/22 | Wed 13/05/26 | 923 days | NA | NA |  |  | 0 days | 0 days | 923 days |  |  | 5.31 | Yes
6 | 1.9.2.4.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.4.1.2 |  |  |  |  | MHHSP Confirms Wave 2 PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  | 2283 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: Confirm Predecessors
6 | 1.9.2.4.1.3 |  |  |  |  | Wave 2 Service Activation | 0% | Fri 10/04/26 | Wed 13/05/26 | 24 days | Fri 31/10/25 | Thu 04/12/25 | 17352282 | 21522159 | 115 days | 114 days | -1 day |  |  | 5.24 | Yes
5 | 1.9.2.4.2 |  |  |  |  | Wave 2 - Service Activation Implementation | 0% | Mon 03/11/25 | Fri 07/11/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | Mon 03/11/25 | Tue 04/11/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.2 |  |  |  |  | PAB Approval | 0% | Mon 03/11/25 | Tue 04/11/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.3 |  |  |  |  | Add EDF to DIP | 0% | Tue 04/11/25 | Wed 05/11/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.4 |  |  |  |  | DIP Promoted to Production | 0% | Wed 05/11/25 | Thu 06/11/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | Thu 06/11/25 | Fri 07/11/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.6 |  |  |  |  | Publish ISD | 0% | Thu 06/11/25 | Fri 07/11/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.7 |  |  |  |  | Wave 2 - Service Activation Implementation Complete (M) | 0% | Fri 07/11/25 | Fri 07/11/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.4.3 |  |  |  |  | Wave 2 - Service Activation Implementation MDD | 0% | Thu 06/11/25 | Wed 19/11/25 | 10 days | NA | NA |  |  | 0 days | 0 days | 10 days |  |  | 5.31 | Yes
6 | 1.9.2.4.3.1 |  |  |  |  | MDD Manual Load | 0% | Thu 06/11/25 | Wed 12/11/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.4.3.2 |  |  |  |  | MDD Update | 0% | Wed 12/11/25 | Wed 19/11/25 | 6 days | NA | NA |  |  | 0 days | 0 days | 6 days |  |  | 5.31 | Yes
6 | 1.9.2.4.3.3 |  |  |  |  | Wave 2 - Service Activation Implementation MDD Complete (M) | 0% | Wed 19/11/25 | Wed 19/11/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.4.4 |  |  |  |  | Wave 2 - Service Activation Hypercare | 0% | Mon 03/11/25 | Thu 20/11/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Mon 03/11/25 | Thu 20/11/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.2 |  |  |  |  | Daily Reporting | 0% | Mon 03/11/25 | Thu 20/11/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.3 |  |  |  |  | Issue Management | 0% | Mon 03/11/25 | Thu 20/11/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 03/11/25 | Thu 20/11/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 17/11/25 | Thu 20/11/25 | 4 days | NA | NA |  |  | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.6 |  |  |  |  | Wave 2 - Service Activation Hypercare Complete (M) | 0% | Wed 19/11/25 | Wed 19/11/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.5 |  |  |  |  | Wave 3 | 0% | Mon 31/10/22 | Wed 01/07/26 | 958 days | NA | NA |  |  | 0 days | 0 days | 958 days |  |  | 5.31 | Yes
5 | 1.9.2.5.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | Mon 31/10/22 | Wed 01/07/26 | 958 days | NA | NA |  |  | 0 days | 0 days | 958 days |  |  | 5.31 | Yes
6 | 1.9.2.5.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.5.1.2 |  |  |  |  | MHHSP Confirms Wave 3 PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  | 2307 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: Confirm Predecessors
6 | 1.9.2.5.1.3 |  |  |  |  | Wave 3 Service Activation | 0% | Fri 29/05/26 | Wed 01/07/26 | 24 days | Fri 19/12/25 | Thu 22/01/26 | 17652306 | 21532160 | 115 days | 114 days | -1 day |  |  | 5.24 | Yes
5 | 1.9.2.5.2 |  |  |  |  | Wave 3 - Service Activation Implementation | 0% | Mon 22/12/25 | Tue 30/12/25 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | Mon 22/12/25 | Tue 23/12/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.2 |  |  |  |  | PAB Approval | 0% | Mon 22/12/25 | Tue 23/12/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.3 |  |  |  |  | Add EDF to DIP | 0% | Tue 23/12/25 | Wed 24/12/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.4 |  |  |  |  | DIP Promoted to Production | 0% | Mon 29/12/25 | Tue 30/12/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | Mon 29/12/25 | Tue 30/12/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.6 |  |  |  |  | Publish ISD | 0% | Mon 29/12/25 | Tue 30/12/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.7 |  |  |  |  | Wave 3 - Service Activation Implementation Complete (M) | 0% | Tue 30/12/25 | Tue 30/12/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.5.3 |  |  |  |  | Wave 3 - Service Activation Implementation MDD | 0% | Mon 31/10/22 | Thu 15/01/26 | 839 days | NA | NA |  |  | 0 days | 0 days | 839 days |  |  | 5.31 | Yes
6 | 1.9.2.5.3.1 |  |  |  |  | MDD Manual Load | 0% | Mon 29/12/25 | Tue 06/01/26 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.5.3.2 |  |  |  |  | MDD Update | 0% | Mon 06/01/25 | Thu 15/01/26 | 269 days | NA | NA |  |  | 0 days | 0 days | 269 days |  |  | 5.31 | Yes
6 | 1.9.2.5.3.3 |  |  |  |  | Wave 3 - Service Activation Implementation MDD Complete (M) | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.5.4 |  |  |  |  | Wave 3 - Service Activation Hypercare | 0% | Mon 31/10/22 | Fri 16/01/26 | 840 days | NA | NA |  |  | 0 days | 0 days | 840 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Mon 22/12/25 | Fri 16/01/26 | 20 days | NA | NA |  |  | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.2 |  |  |  |  | Daily Reporting | 0% | Mon 22/12/25 | Fri 16/01/26 | 20 days | NA | NA |  |  | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.3 |  |  |  |  | Issue Management | 0% | Mon 22/12/25 | Fri 16/01/26 | 20 days | NA | NA |  |  | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 22/12/25 | Fri 16/01/26 | 20 days | NA | NA |  |  | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 12/01/26 | Thu 15/01/26 | 4 days | NA | NA |  |  | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.6 |  |  |  |  | Wave 3 Service Activation Hypercare Complete (M) | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.6 |  |  |  |  | Wave 4 | 0% | Mon 31/10/22 | Thu 03/09/26 | 1004 days | NA | NA |  |  | 0 days | 0 days | 1004 days |  |  | 5.31 | Yes
5 | 1.9.2.6.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | Mon 31/10/22 | Thu 03/09/26 | 1004 days | NA | NA |  |  | 0 days | 0 days | 1004 days |  |  | 5.31 | Yes
6 | 1.9.2.6.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.6.1.2 |  |  |  |  | MHHSP Confirms Wave 4 PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  | 2331 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: Confirm Predecessors
6 | 1.9.2.6.1.3 |  |  |  |  | Wave 4 Service Activation | 0% | Mon 03/08/26 | Thu 03/09/26 | 24 days | Fri 27/02/26 | Thu 02/04/26 | 17952330 | 21542161 | 111 days | 110 days | -1 day |  |  | 5.24 | Yes
5 | 1.9.2.6.2 |  |  |  |  | Wave 4 - Service Activation Implementation | 0% | Mon 03/03/25 | Fri 06/03/26 | 265 days | NA | NA |  |  | 0 days | 0 days | 265 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | Mon 02/03/26 | Tue 03/03/26 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.2 |  |  |  |  | PAB Approval | 0% | Mon 03/03/25 | Mon 03/03/25 | 1 day | NA | NA |  |  | 0 days | 0 days | 1 day |  |  | 5.31 | Yes
6 | 1.9.2.6.2.3 |  |  |  |  | Add EDF to DIP | 0% | Tue 03/03/26 | Wed 04/03/26 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.4 |  |  |  |  | DIP Promoted to Production | 0% | Wed 04/03/26 | Thu 05/03/26 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | Thu 05/03/26 | Fri 06/03/26 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.6 |  |  |  |  | Publish ISD | 0% | Thu 05/03/26 | Fri 06/03/26 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.7 |  |  |  |  | Wave 4 - Service Activation Implementation Complete (M) | 0% | Fri 06/03/26 | Fri 06/03/26 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.6.3 |  |  |  |  | Wave 4 - Service Activation Implementation MDD | 0% | Fri 06/03/26 | Thu 26/03/26 | 15 days | NA | NA |  |  | 0 days | 0 days | 15 days |  |  | 5.31 | Yes
6 | 1.9.2.6.3.1 |  |  |  |  | MDD Manual Load | 0% | Fri 06/03/26 | Mon 16/03/26 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.6.3.2 |  |  |  |  | MDD Update | 0% | Mon 16/03/26 | Thu 26/03/26 | 9 days | NA | NA |  |  | 0 days | 0 days | 9 days |  |  | 5.31 | Yes
6 | 1.9.2.6.3.3 |  |  |  |  | Wave 4 - Service Activation Implementation MDD Complete | 0% | Wed 25/03/26 | Wed 25/03/26 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.6.4 |  |  |  |  | Wave 4 - Service Activation Hypercare | 0% | Mon 02/03/26 | Thu 26/03/26 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.1 |  |  |  |  | Service& Process Monitoring | 0% | Mon 02/03/26 | Thu 26/03/26 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.2 |  |  |  |  | Daily Reporting | 0% | Mon 02/03/26 | Thu 26/03/26 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.3 |  |  |  |  | Issue Management | 0% | Mon 02/03/26 | Thu 26/03/26 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 02/03/26 | Thu 26/03/26 | 19 days | NA | NA |  |  | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.5 |  |  |  |  | Handover to MHHSP | 0% | Mon 02/03/26 | Thu 05/03/26 | 4 days | NA | NA |  |  | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.6 |  |  |  |  | Wave 4 - Service Activation Hypercare Complete (M) | 0% | Wed 25/03/26 | Wed 25/03/26 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.7 |  |  |  |  | Non-SIT LDSO | 0% | Mon 31/10/22 | Fri 08/08/25 | 725 days | NA | NA |  |  | 0 days | 0 days | 725 days |  |  | 5.31 | Yes
5 | 1.9.2.7.1 |  |  |  |  | Non-SIT LDSO Service Activation Data Loading | 0% | Fri 07/06/24 | Fri 07/02/25 | 176 days | NA | NA |  |  | 0 days | 0 days | 176 days |  |  | 5.31 | Yes
6 | 1.9.2.7.1.1 |  |  |  |  | Define pre Non-SIT LDSO upfront activities | 0% | Fri 07/06/24 | Mon 17/06/24 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.7.1.2 |  |  |  |  | Execute Non-SIT LDSO Activities | 0% | Mon 03/02/25 | Fri 07/02/25 | 5 days | NA | NA |  |  | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
7 | 1.9.2.7.1.2.1 |  |  |  |  | Create Entity Forms in Customer Solution | 0% | Mon 03/02/25 | Wed 05/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days | PMP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.2 |  |  |  |  | DIP - Promote to Production Environment | 0% | Mon 03/02/25 | Wed 05/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days | DIP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.3 |  |  |  |  | DIP - Enable Technology capabilities for participants | 0% | Mon 03/02/25 | Wed 05/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days | DIP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.4 |  |  |  |  | DIP - Add EFD to DIP | 0% | Mon 03/02/25 | Wed 05/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days | DIP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.5 |  |  |  |  | ISD - Replicate Entity Forms from CS | 0% | Thu 06/02/25 | Fri 07/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days | HELIX |  | 5.31 | Yes
7 | 1.9.2.7.1.2.6 |  |  |  |  | MDD - Load MHHS roles | 0% | Mon 03/02/25 | Wed 05/02/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.1.3 |  |  |  |  | Non-SIT LDSO Service Activation Data Loading Completed (M) | 0% | Fri 07/02/25 | Fri 07/02/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.7.2 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | Mon 31/10/22 | Fri 08/08/25 | 725 days | NA | NA |  |  | 0 days | 0 days | 725 days |  |  | 5.31 | Yes
6 | 1.9.2.7.2.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | Mon 31/10/22 | Mon 31/10/22 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.7.2.2 |  |  |  |  | MHHSP Confirms Non-SIT LDSO PPs MHHS Enabled | 0% | Mon 31/10/22 | Mon 31/10/22 | 1 day | NA | NA |  | 2365 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24: Confirm Predecessors
6 | 1.9.2.7.2.3 |  |  |  |  | Non-SIT LDSO Service Activation | 0% | Fri 01/08/25 | Fri 08/08/25 | 6 days | Mon 24/02/25 | Thu 06/03/25 | 14382364 | 1317 | 114 days | 111 days | -3 days |  |  | 5.24 | Yes
5 | 1.9.2.7.3 |  |  |  |  | Non-SIT LDSO Service Activation Implementation | 0% | Mon 24/02/25 | Thu 27/02/25 | 4 days | NA | NA |  |  | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.7.3.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | Mon 24/02/25 | Tue 25/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days | MHHSP |  | 5.31 | Yes
6 | 1.9.2.7.3.2 |  |  |  |  | PAB Approval | 0% | Mon 24/02/25 | Tue 25/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days | QUALF |  | 5.31 | Yes
6 | 1.9.2.7.3.3 |  |  |  |  | Add EDF to DIP | 0% | Tue 25/02/25 | Wed 26/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days | DIP |  | 5.31 | Yes
6 | 1.9.2.7.3.4 |  |  |  |  | DIP Promoted to Production | 0% | Wed 26/02/25 | Thu 27/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days | DIP |  | 5.31 | Yes
6 | 1.9.2.7.3.5 |  |  |  |  | Create M16 in Customer Solution | 0% | Wed 26/02/25 | Thu 27/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.3.6 |  |  |  |  | Publish ISD | 0% | Wed 26/02/25 | Thu 27/02/25 | 2 days | NA | NA |  |  | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.7.3.7 |  |  |  |  | Non-SIT LDSO Service Activation Implementation Completed (M) | 0% | Thu 27/02/25 | Thu 27/02/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.7.4 |  |  |  |  | Non-SIT LDSO Service Activation Implementation MDD | 0% | Thu 27/02/25 | Tue 18/03/25 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.7.4.1 |  |  |  |  | MDD Manual Load | 0% | Thu 27/02/25 | Fri 07/03/25 | 7 days | NA | NA |  |  | 0 days | 0 days | 7 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.4.2 |  |  |  |  | MDD Update | 0% | Fri 07/03/25 | Tue 18/03/25 | 8 days | NA | NA |  |  | 0 days | 0 days | 8 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.4.3 |  |  |  |  | Non-SIT LDSO Service Activation Implementation MDD Complete (M) | 0% | Tue 18/03/25 | Tue 18/03/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.7.5 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare | 0% | Mon 24/02/25 | Wed 19/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.7.5.1 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Support | 0% | Mon 24/02/25 | Wed 19/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.1 |  |  |  |  | Service& Process Monitoring | 0% | Mon 24/02/25 | Wed 19/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.2 |  |  |  |  | Daily Reporting | 0% | Mon 24/02/25 | Wed 19/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.3 |  |  |  |  | Issue Management | 0% | Mon 24/02/25 | Wed 19/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | Mon 24/02/25 | Wed 19/03/25 | 18 days | NA | NA |  |  | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.5 |  |  |  |  | Handover to MHHSP | 0% | Fri 14/03/25 | Tue 18/03/25 | 3 days | NA | NA |  |  | 0 days | 0 days | 3 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.6 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Complete (M) | 0% | Tue 18/03/25 | Tue 18/03/25 | 0 days | NA | NA |  |  | 0 days | 0 days | 0 days |  |  | 5.31 | Yes
3 | 1.9.3 |  |  |  |  | Implement Early Life Support Plan | 0% | Mon 06/01/25 | Fri 07/03/25 | 45 days | Mon 06/01/25 | Fri 07/03/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.3.1 |  |  |  | MHHS-ART095 | Implement Early Life Support Plan | 0% | Mon 06/01/25 | Fri 07/03/25 | 45 days | Mon 06/01/25 | Fri 07/03/25 | 2195 |  | 0 days | 0 days | 0 days | SI Transition |  | 5.23 | Yes
3 | 1.9.4 |  |  |  |  | Business Continuity and Disaster Recovery Plan | 0% | Thu 19/06/25 | Wed 13/08/25 | 40 days | Mon 13/01/25 | Fri 07/03/25 |  |  | 113 days | 113 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.4.1 |  |  |  |  | Central Parties BCDRs in Place | 0% | Thu 19/06/25 | Wed 16/07/25 | 20 days | Mon 13/01/25 | Fri 07/02/25 | 1932FS-40 days | 2390 | 113 days | 113 days | 0 days | SI Design |  | 5 | Yes
4 | 1.9.4.2 |  |  |  |  | Risk Based Assurance of Cental Party BCDRs | 0% | Thu 17/07/25 | Wed 13/08/25 | 20 days | Mon 10/02/25 | Fri 07/03/25 | 2389 |  | 113 days | 113 days | 0 days | PP |  | 5 | Yes
3 | 1.9.5 |  |  |  |  | Training and Support Materials | 0% | Thu 10/07/25 | Tue 02/09/25 | 39 days | Mon 03/02/25 | Fri 28/03/25 |  |  | 113 days | 112 days | -1 day | N/A |  | 5 | Yes
4 | 1.9.5.1 |  |  |  |  | Develop document | 0% | Thu 10/07/25 | Wed 06/08/25 | 20 days | Mon 03/02/25 | Fri 28/02/25 | 2180FS-45 days | 2393 | 113 days | 113 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.9.5.2 |  |  |  |  | Document review and update | 0% | Thu 07/08/25 | Tue 02/09/25 | 19 days | Mon 03/03/25 | Fri 28/03/25 | 2392 | 2394 | 113 days | 112 days | -1 day | SI Migration |  | 5 | Yes
4 | 1.9.5.3 |  |  |  | MHHS-ART118 | Training and Support Materials approved | 0% | Tue 02/09/25 | Tue 02/09/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 2393 |  | 112 days | 112 days | 0 days | SI Migration |  | 5 | Yes
3 | 1.9.6 |  |  |  |  | PP Business Change | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.6.1 |  |  |  |  | Plan stakeholder management | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.2 |  |  |  |  | Manage stakeholders | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.3 |  |  |  |  | Develop & implement changes to KPIs, organisation & people management | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.4 |  |  |  |  | Develop & test changes to business processes | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.5 |  |  |  |  | Develop and deliver training | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.6 |  |  |  |  | Programme support for PP Business Change activities | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
3 | 1.9.7 |  |  |  |  | Transition to New Settlement Timetable (M16) | 0% | Wed 10/09/25 |  |  | Fri 04/04/25 | Fri 28/05/27 |  |  | 113 days | -446 days | -559 days? | N/A |  | 5.15 | Yes
4 | 1.9.7.1 |  |  |  |  | Elexon to produce Settlement Calendar for Settlement Year 2025/2026 | 0% | Wed 10/09/25 | Wed 10/09/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 2178 | 2404,2405FS+176 days | 113 days | 113 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.2 |  |  |  |  | Elexon monitor settlement data of migrated MPANs | 0% | Thu 11/09/25 | Thu 13/05/27 | 436 days | Mon 07/04/25 | Mon 07/12/26 | 2403 | 2415 | 113 days | 113 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.3 |  |  |  |  | M16 Checkpoint 1 | 0% | Thu 14/05/26 | Thu 14/05/26 | 0 days | Mon 08/12/25 | Mon 08/12/25 | 2403FS+176 days | 2406FS+20 days | 113 days | 113 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.4 |  |  |  |  | Confirm if M16 date retained as 07/12/2026 | 0% | Thu 11/06/26 | Thu 11/06/26 | 0 days | Mon 05/01/26 | Mon 05/01/26 | 2405FS+20 days | 2407FS+20 days | 113 days | 113 days | 0 days | CPT |  | 5.15 | Yes
4 | 1.9.7.5 |  |  |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | Thu 09/07/26 | Thu 09/07/26 | 0 days | Mon 02/02/26 | Mon 02/02/26 | 2406FS+20 days | 2408FS+42 days | 113 days | 113 days | 0 days | CPT |  | 5.15 | Yes
4 | 1.9.7.6 |  |  |  |  | Elexon to produce Settlement Calendar for Settlement Year 2026 up until day before M16 cutover | 0% | Mon 07/09/26 | Mon 07/09/26 | 0 days | Wed 01/04/26 | Wed 01/04/26 | 2407FS+42 days | 2409FS+119 days | 113 days | 113 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.7 |  |  |  |  | M16 Checkpoint 2 | 0% | Fri 19/02/27 | Fri 19/02/27 | 0 days | Tue 15/09/26 | Tue 15/09/26 | 2408FS+119 days | 2410FS+11 days | 113 days | 113 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.8 |  |  |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | Mon 08/03/27 | Mon 08/03/27 | 0 days | Wed 30/09/26 | Wed 30/09/26 | 2409FS+11 days | 2411FS+9 days | 113 days | 113 days | 0 days | CPT |  | 5.15 | Yes
4 | 1.9.7.9 | T2 | T2-EL-0100 | PSG/BSC PAB |  | Confirm M16 Date | 0% | Fri 19/03/27 | Fri 19/03/27 | 0 days | Tue 13/10/26 | Tue 13/10/26 | 2410FS+9 days | 2414FS+40 days,2412 | 114 days | 113 days | -1 day | CPT |  | 5.3 | Yes
4 | 1.9.7.10 |  |  |  |  | Raise fast track change to ISD (November publish) | 0% | Fri 19/03/27 | Fri 19/03/27 | 0 days | Tue 13/10/26 | Tue 13/10/26 | 2411 | 2415 | 113 days | 113 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.11 |  |  |  |  | M16 Approval Window | 0% | Thu 13/05/27 | Tue 26/08/49 | 31903 days? | Mon 07/12/26 | Fri 28/05/27 |  |  | 113 days | 31892 days | 31779 days? | N/A |  | 5 | Yes
5 | 1.9.7.11.1 |  |  |  |  | Panel approval that M16 criteria met | 0% | Fri 14/05/27 | Fri 14/05/27 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 2411FS+40 days | 2415 | 114 days | 114 days | 0 days | Panel |  | 5 | Yes
5 | 1.9.7.11.2 | T1 | T1-EL-1000 | PSG |  | Cut over to new settlement timetable (M16) | 0% | Fri 14/05/27 | Fri 14/05/27 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 2414,2182FS+40 days,2404,2412,2095 | 2416,2511FS-8 days,2488FS-60 days,2429FS-45 days,2525FS-3 mons,2457FF-5 days | 114 days | 114 days | 0 days | CPT |  | 5 | Yes
5 | 1.9.7.11.3 |  |  |  |  | Maximum 6-month window for approval of M16 | 0% | Mon 17/05/27 | Thu 04/11/27 | 124 days | Tue 08/12/26 | Fri 28/05/27 | 2415 | 2417 | 114 days | 114 days | 0 days | CPT |  | 5 | Yes
5 | 1.9.7.11.4 | T1 | T1-EL-2000 | PSG |  | Cut over to new settlement timetable (M16*) - Late Exit | 0% | Thu 04/11/27 | Thu 04/11/27 | 0 days | Fri 28/05/27 | Fri 28/05/27 | 2416 |  | 114 days | 114 days | 0 days | CPT |  | 5 | Yes
2 | 1.1 |  |  |  |  | EARLY LIVE RUNNING | 0% | Tue 16/03/27 | Mon 17/05/27 | 45 days | Tue 02/01/24 | Fri 28/05/27 |  |  | 835 days | -9 days | -844 days | N/A |  |  | Yes
3 | 1.10.1 |  |  |  |  | Early Live Running Stabilisation Period | 0% | Tue 16/03/27 | Mon 17/05/27 | 45 days | Tue 06/10/26 | Mon 07/12/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.10.1.1 |  |  |  |  | Manage Early Live Running stabilisation period | 0% | Tue 16/03/27 | Mon 17/05/27 | 45 days | Tue 06/10/26 | Mon 07/12/26 | 2182 | 2421SS | 115 days | 115 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.10.1.2 |  |  |  |  | Monitor Early Live Running stabilisation period | 0% | Tue 16/03/27 | Mon 17/05/27 | 45 days | Tue 06/10/26 | Mon 07/12/26 | 2420SS |  | 115 days | 115 days | 0 days | SI Migration |  | 5 | Yes
2 | 1.11 |  |  |  |  | PROGRAMME CLOSURE | 0% | Tue 12/01/27 | Fri 07/05/27 | 84 days | Tue 04/08/26 | Mon 30/11/26 |  |  | 115 days | 114 days | -1 day | N/A |  |  | Yes
3 | 1.11.1 |  |  |  |  | Handover Pack | 0% | Tue 12/01/27 | Fri 07/05/27 | 84 days | Tue 04/08/26 | Mon 30/11/26 |  |  | 115 days | 114 days | -1 day | N/A |  | 5 | Yes
4 | 1.11.1.1 |  |  |  |  | Draft Handover Pack (for M15) | 0% | Tue 12/01/27 | Mon 08/03/27 | 40 days | Tue 04/08/26 | Mon 28/09/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
5 | 1.11.1.1.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2426 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
5 | 1.11.1.1.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2425 | 2427 | 115 days | 115 days | 0 days | SRO |  | 5 | Yes
5 | 1.11.1.1.3 |  |  |  | MHHS-ART126 | Draft Handover Pack approved | 0% | Mon 08/03/27 | Mon 08/03/27 | 0 days | Mon 28/09/26 | Mon 28/09/26 | 2426 |  | 115 days | 115 days | 0 days | SRO |  | 5 | Yes
4 | 1.11.1.2 |  |  |  |  | Master Handover Pack (for M16) | 0% | Mon 15/03/27 | Fri 07/05/27 | 40 days | Tue 06/10/26 | Mon 30/11/26 |  |  | 114 days | 114 days | 0 days | N/A |  | 5 | Yes
5 | 1.11.1.2.1 |  |  |  |  | Update document | 0% | Mon 15/03/27 | Fri 09/04/27 | 20 days | Tue 06/10/26 | Mon 02/11/26 | 2415FS-45 days | 2430 | 114 days | 114 days | 0 days | PMO |  | 5 | Yes
5 | 1.11.1.2.2 |  |  |  |  | Document review and update | 0% | Mon 12/04/27 | Fri 07/05/27 | 20 days | Tue 03/11/26 | Mon 30/11/26 | 2429 | 2431 | 114 days | 114 days | 0 days | SRO |  | 5 | Yes
5 | 1.11.1.2.3 |  |  |  | MHHS-ART126 | Master Handover Pack approved | 0% | Fri 07/05/27 | Fri 07/05/27 | 0 days | Mon 30/11/26 | Mon 30/11/26 | 2430 |  | 114 days | 114 days | 0 days | SRO |  | 5 | Yes
3 | 1.11.2 |  |  |  |  | Programme Lessons Learned | 0% | Tue 12/01/27 | Mon 08/03/27 | 40 days | Tue 04/08/26 | Mon 28/09/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.2.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2434 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.2.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2433 | 2435 | 115 days | 115 days | 0 days | SRO |  | 5 | Yes
4 | 1.11.2.3 |  |  |  | MHHS-ART131 | Programme Lessons Learned document approved | 0% | Mon 08/03/27 | Mon 08/03/27 | 0 days | Mon 28/09/26 | Mon 28/09/26 | 2434 |  | 115 days | 115 days | 0 days | SRO |  | 5 | Yes
3 | 1.11.3 |  |  |  |  | Programme Closure Report | 0% | Tue 12/01/27 | Mon 08/03/27 | 40 days | Tue 04/08/26 | Mon 28/09/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.3.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2438 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.3.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2437 | 2439 | 115 days | 115 days | 0 days | Ofgem |  | 5 | Yes
4 | 1.11.3.3 |  |  |  | MHHS-ART130 | Programme Closure Report approved | 0% | Mon 08/03/27 | Mon 08/03/27 | 0 days | Mon 28/09/26 | Mon 28/09/26 | 2438 |  | 115 days | 115 days | 0 days | Ofgem |  | 5 | Yes
3 | 1.11.4 |  |  |  |  | Benefit Realisation Report | 0% | Tue 12/01/27 | Mon 15/03/27 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.4.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2442 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.4.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2441 | 2443FS+5 days | 115 days | 115 days | 0 days | PP |  | 5 | Yes
4 | 1.11.4.3 | T3 | T3-PC-0010 | PSG | MHHS-ART124 | Benefit Realisation Report approved | 0% | Mon 15/03/27 | Mon 15/03/27 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2442FS+5 days |  | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
3 | 1.11.5 |  |  |  |  | Operating Model Gap Review with recommendations | 0% | Tue 12/01/27 | Mon 15/03/27 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.5.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2446 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.5.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2445 | 2447FS+5 days | 115 days | 115 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.3 | T3 | T3-PC-0020 | DAG | MHHS-ART128 | Operating Model Gap Review with recommendations approved | 0% | Mon 15/03/27 | Mon 15/03/27 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2446FS+5 days |  | 115 days | 115 days | 0 days | Paul Pettitt |  | 5 | Yes
3 | 1.11.6 |  |  |  |  | Post-Implementation Review | 0% | Tue 12/01/27 | Mon 15/03/27 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.6.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2450 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.6.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2449 | 2451FS+5 days | 115 days | 115 days | 0 days | PP |  | 5 | Yes
4 | 1.11.6.3 | T3 | T3-PC-0030 | PSG | MHHS-ART129 | Post-Implementation Review approved | 0% | Mon 15/03/27 | Mon 15/03/27 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2450FS+5 days |  | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
3 | 1.11.7 |  |  |  |  | Reinforcement Guide | 0% | Tue 12/01/27 | Mon 15/03/27 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.7.1 |  |  |  |  | Develop document | 0% | Tue 12/01/27 | Mon 08/02/27 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 2182FS-45 days | 2454 | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.7.2 |  |  |  |  | Document review and update | 0% | Tue 09/02/27 | Mon 08/03/27 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2453 | 2455FS+5 days | 115 days | 115 days | 0 days | PP |  | 5 | Yes
4 | 1.11.7.3 | T3 | T3-PC-0040 | PSG | MHHS-ART133 | Reinforcement Guide approved | 0% | Mon 15/03/27 | Mon 15/03/27 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2454FS+5 days |  | 115 days | 115 days | 0 days | PMO |  | 5 | Yes
3 | 1.11.8 |  |  |  |  | Material and Licenses Transfer | 0% | Mon 15/02/27 | Fri 07/05/27 | 60 days | Tue 08/09/26 | Mon 30/11/26 |  |  | 114 days | 114 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.8.1 |  |  |  | MHHS-ART139 | Transfer of Programme material to Elexon and perpetual licenses as appropriate | 0% | Mon 15/02/27 | Fri 07/05/27 | 60 days | Tue 08/09/26 | Mon 30/11/26 | 2415FF-5 days |  | 114 days | 114 days | 0 days | PMO |  | 5 | Yes
2 | 1.12 |  |  |  |  | READINESS ASSESSMENTS | 23% | Tue 05/09/23 | Thu 29/04/27 | 953 days | Tue 05/09/23 | Fri 04/12/26 |  |  | 0 days | 104 days | 104 days | N/A |  |  | Yes
3 | 1.12.1 |  |  |  |  | Readiness Assessment 3 - Design and Build Progress Check and CP2 Check | 100% | Tue 05/09/23 | Mon 27/11/23 | 60 days | Tue 05/09/23 | Mon 13/11/23 |  |  | 0 days | 10 days | 10 days | N/A |  | 5.5 | Yes
4 | 1.12.1.1 |  |  |  |  | Launch Readiness Assessment survey | 100% | Tue 05/09/23 | Tue 05/09/23 | 0 days | Tue 05/09/23 | Tue 05/09/23 | 1070FS-40 days | 2461 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes
4 | 1.12.1.2 |  |  |  |  | PPs submit survey responses | 100% | Tue 05/09/23 | Mon 25/09/23 | 15 days | Tue 05/09/23 | Mon 25/09/23 | 2460 | 24622463 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
4 | 1.12.1.3 |  |  |  |  | Analyse survey responses | 100% | Tue 26/09/23 | Mon 16/10/23 | 15 days | Tue 26/09/23 | Mon 16/10/23 | 2461 | 2464 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes
4 | 1.12.1.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 100% | Tue 26/09/23 | Mon 16/10/23 | 15 days | Tue 26/09/23 | Mon 16/10/23 | 2461 | 2464 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes |  | 16/11- FD confirmed activity didn't take place for RA3 because responses did not warrant follow-up
4 | 1.12.1.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 100% | Tue 17/10/23 | Mon 20/11/23 | 25 days | Tue 17/10/23 | Mon 06/11/23 | 24622463 | 2465FS+5 days | 0 days | 10 days | 10 days | PPC |  | 5.5 | Yes
4 | 1.12.1.6 | T2 | T2-RA-0200 | PSG |  | Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | 100% | Mon 27/11/23 | Mon 27/11/23 | 0 days | Mon 13/11/23 | Mon 13/11/23 | 2464FS+5 days |  | 10 days | 10 days | 0 days | CPT |  | 5.13 | Yes |  | 16/11-RA3 outputs and initial findings shared with PSG to support M9 decision making. Individual reports and final closure report being finalised. No impact to Programme timelines or activities
3 | 1.12.2 |  |  |  |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check | 0% | Mon 21/04/25 | Tue 24/06/25 | 47 days | Tue 12/11/24 | Fri 17/01/25 |  |  | 114 days | 112 days | -2 days | N/A |  | 5 | Yes
4 | 1.12.2.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Tue 12/11/24 | Tue 12/11/24 |  | 2468 | 114 days | 114 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.2 |  |  |  |  | PPs submit survey responses | 0% | Mon 21/04/25 | Fri 09/05/25 | 15 days | Tue 12/11/24 | Mon 02/12/24 | 2467 | 24692470 | 114 days | 114 days | 0 days | PP |  | 5 | Yes
4 | 1.12.2.3 |  |  |  |  | Analyse survey responses | 0% | Mon 12/05/25 | Fri 30/05/25 | 15 days | Tue 03/12/24 | Mon 23/12/24 | 2468 | 2471 | 114 days | 114 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Mon 12/05/25 | Fri 30/05/25 | 15 days | Tue 03/12/24 | Mon 23/12/24 | 2468 | 2471 | 114 days | 114 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Mon 02/06/25 | Fri 20/06/25 | 15 days | Tue 24/12/24 | Mon 13/01/25 | 24692470 | 2472FS+2 days | 114 days | 114 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.6 | T2 | T2-RA-0400 | PSG |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check (incl. Readiness Assessment Report approval) Completed | 0% | Tue 24/06/25 | Tue 24/06/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 2471FS+2 days | 2495 | 112 days | 112 days | 0 days | CPT |  | 5.18 | Yes |  | 08/02/2024 Name change approval at PSG on 07/02/24 from 'Readiness Assessment 5 - Start of Qualification - Completed (incl. Readiness Assessment Report approval)'
3 | 1.12.3 |  |  |  |  | Readiness Assessment 7 - Migration Checkpoint | 0% | Mon 12/01/26 | Thu 19/03/26 | 49 days | Mon 04/08/25 | Thu 09/10/25 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.3.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Mon 12/01/26 | Mon 12/01/26 | 0 days | Mon 04/08/25 | Mon 04/08/25 |  | 2475 | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.2 |  |  |  |  | PPs submit survey responses | 0% | Mon 12/01/26 | Fri 30/01/26 | 15 days | Mon 04/08/25 | Fri 22/08/25 | 2474 | 24762477 | 115 days | 115 days | 0 days | PP |  | 5 | Yes
4 | 1.12.3.3 |  |  |  |  | Analyse survey responses | 0% | Mon 02/02/26 | Fri 20/02/26 | 15 days | Mon 25/08/25 | Fri 12/09/25 | 2475 | 2478 | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Mon 02/02/26 | Fri 20/02/26 | 15 days | Mon 25/08/25 | Fri 12/09/25 | 2475 | 2478 | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Mon 23/02/26 | Fri 13/03/26 | 15 days | Mon 15/09/25 | Fri 03/10/25 | 24762477 | 2479FS+4 days | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.6 | T2 | T2-RA-0600 | PSG |  | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 19/03/26 | Thu 19/03/26 | 0 days | Thu 09/10/25 | Thu 09/10/25 | 2478FS+4 days | 2496 | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
3 | 1.12.4 |  |  |  |  | Readiness Assessment 8 - Ready to Accept New MPANs | 0% | Tue 16/06/26 | Fri 21/08/26 | 49 days | Tue 06/01/26 | Fri 13/03/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.4.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Tue 16/06/26 | Tue 16/06/26 | 0 days | Tue 06/01/26 | Tue 06/01/26 | 1797FS-60 days | 2482 | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.2 |  |  |  |  | PPs submit survey responses | 0% | Tue 16/06/26 | Mon 06/07/26 | 15 days | Tue 06/01/26 | Mon 26/01/26 | 2481 | 24832484 | 115 days | 115 days | 0 days | PP |  | 5 | Yes
4 | 1.12.4.3 |  |  |  |  | Analyse survey responses | 0% | Tue 07/07/26 | Mon 27/07/26 | 15 days | Tue 27/01/26 | Mon 16/02/26 | 2482 | 2485 | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Tue 07/07/26 | Mon 27/07/26 | 15 days | Tue 27/01/26 | Mon 16/02/26 | 2482 | 2485 | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Tue 28/07/26 | Mon 17/08/26 | 15 days | Tue 17/02/26 | Mon 09/03/26 | 24832484 | 2486FS+4 days | 115 days | 115 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.6 | T2 | T2-RA-0700 | PSG |  | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | Fri 21/08/26 | Fri 21/08/26 | 0 days | Fri 13/03/26 | Fri 13/03/26 | 2485FS+4 days | 2497 | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
3 | 1.12.5 |  |  |  |  | Readiness Assessment 9 - Ready for New Settlement Timetable and CP5 Check | 0% | Mon 22/02/27 | Thu 29/04/27 | 49 days | Tue 29/09/26 | Fri 04/12/26 |  |  | 104 days | 104 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.5.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | Mon 22/02/27 | Mon 22/02/27 | 0 days | Tue 29/09/26 | Tue 29/09/26 | 2415FS-60 days | 2489 | 104 days | 104 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.2 |  |  |  |  | PPs submit survey responses | 0% | Mon 22/02/27 | Fri 12/03/27 | 15 days | Tue 29/09/26 | Mon 19/10/26 | 2488 | 24902491 | 104 days | 104 days | 0 days | PP |  | 5 | Yes
4 | 1.12.5.3 |  |  |  |  | Analyse survey responses | 0% | Mon 15/03/27 | Fri 02/04/27 | 15 days | Tue 20/10/26 | Mon 09/11/26 | 2489 | 2492 | 104 days | 104 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Mon 15/03/27 | Fri 02/04/27 | 15 days | Tue 20/10/26 | Mon 09/11/26 | 2489 | 2492 | 104 days | 104 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Mon 05/04/27 | Fri 23/04/27 | 15 days | Tue 10/11/26 | Mon 30/11/26 | 24902491 | 2493FS+4 days | 104 days | 104 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.6 | T2 | T2-RA-0800 | PSG |  | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 29/04/27 | Thu 29/04/27 | 0 days | Fri 04/12/26 | Fri 04/12/26 | 2492FS+4 days | 2498 | 104 days | 104 days | 0 days | CPT |  | 5 | Yes
3 | 1.12.6 |  |  |  |  | Readiness Assessments - Tier 1 Milestones | 0% | Tue 24/06/25 | Thu 29/04/27 | 482 days | Mon 13/11/23 | Fri 04/12/26 |  |  | 421 days | 104 days | -317 days | N/A |  | 5 | Yes
4 | 1.12.6.1 | T2 | T2-RA-0500 | PSG |  | Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | 0% | Tue 24/06/25 | Tue 24/06/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 2472 |  | 57 days | 57 days | 0 days | CPT |  | 5 | Yes
4 | 1.12.6.2 | T2 | T2-RA-0600 | PSG |  | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 19/03/26 | Thu 19/03/26 | 0 days | Thu 09/10/25 | Thu 09/10/25 | 2479 |  | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
4 | 1.12.6.3 | T2 | T2-RA-0700 | PSG |  | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | Fri 21/08/26 | Fri 21/08/26 | 0 days | Fri 13/03/26 | Fri 13/03/26 | 2486 |  | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
4 | 1.12.6.4 | T2 | T2-RA-0800 | PSG |  | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 29/04/27 | Thu 29/04/27 | 0 days | Fri 04/12/26 | Fri 04/12/26 | 2493 |  | 104 days | 104 days | 0 days | CPT |  | 5 | Yes
2 | 1.13 |  |  |  |  | CONTROL POINTS | 51% | Thu 10/11/22 | Wed 05/05/27 | 1169 days | Thu 10/11/22 | Mon 07/12/26 |  |  | 0 days | 106 days | 106 days | N/A |  |  | Yes
3 | 1.13.1 |  |  |  |  | Control Point 1 - Start of System Design, Build & Test | 100% | Thu 10/11/22 | Wed 07/12/22 | 20 days | Thu 10/11/22 | Wed 07/12/22 |  |  | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.1.1 |  |  |  |  | Control Point 1 Preparation (incl. Control Point Report development and review) | 100% | Thu 10/11/22 | Wed 30/11/22 | 15 days | Thu 10/11/22 | Wed 30/11/22 | 2502SS-20 days |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.1.2 | T1 | T1-CP-1000 | PSG |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 |  | 2501SS-20 days,2513SS | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.13.2 |  |  |  |  | Control Point 2 - Start of Integration & Test | 100% | Mon 02/10/23 | Mon 30/10/23 | 20 days | Tue 03/10/23 | Mon 30/10/23 |  |  | -1 day | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.13.2.1 |  |  |  |  | Control Point 2 Preparation (incl. Control Point Report development and review) | 100% | Mon 02/10/23 | Fri 20/10/23 | 15 days | Tue 03/10/23 | Mon 23/10/23 | 2505SS-20 days |  | -1 day | -1 day | 0 days | CPT |  | 5 | Yes
4 | 1.13.2.2 | T1 | T1-CP-2000 | PSG |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 1070 | 2514SS,2504SS-20 days | -1 day | -1 day | 0 days | CPT |  | 5.11 | Yes
3 | 1.13.3 |  |  |  |  | Control Point 3/4 - Readiness for Migration | 0% | Thu 10/07/25 | Thu 07/08/25 | 20 days | Mon 03/03/25 | Fri 28/03/25 |  |  | 93 days | 93 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.3.1 |  |  |  |  | Control Point 3/4 Preparation (incl. Control Point Report development and review) | 0% | Thu 10/07/25 | Tue 29/07/25 | 14 days | Mon 03/03/25 | Thu 20/03/25 | 2508SS-20 days |  | 93 days | 93 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.3.2 | T1 | T1-CP-3000 | PSG |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 0% | Thu 07/08/25 | Thu 07/08/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1317FS-5 days | 2515SS,2507SS-20 days | 93 days | 93 days | 0 days | CPT |  | 5 | Yes
3 | 1.13.4 |  |  |  |  | Control Point 5 - Cut Over to New Settlement Timetable | 0% | Wed 07/04/27 | Wed 05/05/27 | 20 days | Tue 10/11/26 | Mon 07/12/26 |  |  | 106 days | 106 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.4.1 |  |  |  |  | Control Point 5 Preparation (incl. Control Point Report development and review) | 0% | Wed 07/04/27 | Tue 27/04/27 | 15 days | Tue 10/11/26 | Mon 30/11/26 | 2511SS-20 days |  | 106 days | 106 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.4.2 | T1 | T1-CP-4000 | PSG |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | Wed 05/05/27 | Wed 05/05/27 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 2415FS-8 days | 2516SS,2510SS-20 days | 106 days | 106 days | 0 days | CPT |  | 5 | Yes
3 | 1.13.5 |  |  |  |  | Control Points - Tier 1 Milestones | 0% | Wed 07/12/22 | Wed 05/05/27 | 1149 days | Wed 07/12/22 | Mon 07/12/26 |  |  | 0 days | 106 days | 106 days | N/A |  | 5 | Yes
4 | 1.13.5.1 | T1 | T1-CP-1000 | PSG |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 2502SS |  | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.5.2 | T1 | T1-CP-2000 | PSG |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 2505SS |  | -1 day | -1 day | 0 days | CPT |  | 5.11 | Yes
4 | 1.13.5.3 | T1 | T1-CP-3000 | PSG |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 0% | Thu 07/08/25 | Thu 07/08/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 2508SS |  | 93 days | 93 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.5.4 | T1 | T1-CP-4000 | PSG |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | Wed 05/05/27 | Wed 05/05/27 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 2511SS |  | 106 days | 106 days | 0 days | CPT |  | 5 | Yes
2 | 1.14 |  |  |  |  | MILESTONE RANGE CHECKPOINTS | 0% | Thu 19/06/25 | Mon 22/02/27 | 437 days | Mon 13/01/25 | Tue 15/09/26 |  |  | 113 days | 114 days | 1 day | N/A |  |  | Yes
3 | 1.14.1 |  |  |  |  | M10, M11, M12 and M13 milestone checkpoint | 0% | Thu 19/06/25 | Thu 19/06/25 | 0 days | Mon 13/01/25 | Mon 13/01/25 |  |  | 113 days | 113 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.1.1 | T2 | T2-MR-0100 | PSG |  | M10, M11, M12, and M13 milestone checkpoint - date approval | 0% | Thu 19/06/25 | Thu 19/06/25 | 0 days | Mon 13/01/25 | Mon 13/01/25 | 2178FS-3 mons,2180FS-3 mons,2176FS-3 mons,1317FS-3 mons |  | 113 days | 113 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.2 |  |  |  |  | M14 milestone checkpoint | 0% | Tue 16/06/26 | Tue 16/06/26 | 0 days | Tue 23/12/25 | Tue 23/12/25 |  |  | 125 days | 125 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.2.1 | T2 | T2-MR-0200 | PSG |  | M14 milestone checkpoint - date approval | 0% | Tue 16/06/26 | Tue 16/06/26 | 0 days | Tue 23/12/25 | Tue 23/12/25 | 1797FS-3 mons |  | 125 days | 125 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.3 |  |  |  |  | M15 milestone checkpoint | 0% | Tue 22/12/26 | Tue 22/12/26 | 0 days | Tue 14/07/26 | Tue 14/07/26 |  |  | 115 days | 115 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.3.1 | T2 | T2-MR-0300 | PSG |  | M15 milestone checkpoint - date approval | 0% | Tue 22/12/26 | Tue 22/12/26 | 0 days | Tue 14/07/26 | Tue 14/07/26 | 2182FS-3 mons |  | 115 days | 115 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.4 |  |  |  |  | M16 milestone checkpoint | 0% | Mon 22/02/27 | Mon 22/02/27 | 0 days | Tue 15/09/26 | Tue 15/09/26 |  |  | 114 days | 114 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.4.1 | T2 | T2-MR-0400 | PSG |  | M16 milestone checkpoint - date approval | 0% | Mon 22/02/27 | Mon 22/02/27 | 0 days | Tue 15/09/26 | Tue 15/09/26 | 2415FS-3 mons |  | 114 days | 114 days | 0 days | CPT |  | 5 | Yes