## Slide 1: Non-SIT Suppliers & Agents: Qualification > Service Activation > Migration E2E Journey Maps
May 2026
MHHS-DEL4314

## Slide 2
Several Non-SIT participants have shared feedback with the Programme that it would be beneficial for their planning and preparations to see a comprehensive view of the end-to-end participant journey that starts with completing Qualification Testing (QT) and concludes with their Effective from Date (EFD) or in the case of Suppliers, the Migration of their first Meter Point Administration Number (MPAN).
The PMO and PPC teams have worked collaboratively with the Code Bodies, DIP Manager, Elexon (Helix) and Migration Control Centre (MCC) to create a series of maps, which can be found on the following slides and depict these end-to-end journeys.
The journey maps do not give deadlines that participants should complete each step of the journey by, as this will depend on the target Qualification and Migration start dates for each participant. Instead, they outline the time each step is estimated to take to complete and how this links into these dates for participants. The purpose of the map then, is to provide Non-SIT participants with a tool which allows them to plan out their own journey through this process in a greater level of detail than could be achieved by using the Programme Plan alone.
We have embedded links through to key pieces of supporting information within the journeys, such as guidance documents and proforma templates, to further support Qualification participants with their planning and readiness activities.
We have also set out some key assumptions and considerations on slide 6 to support Qualification participants with interpreting and using the journey maps in the right way.
If you have any feedback or questions around the format or layout of the journey maps, please direct these to the PMO and PPC teams at PMO@mhhsprogramme.co.uk and PPC@mhhsprogramme.co.uk, respectively.
If you have any questions regarding any of the processes depicted in the journey maps, please contact the team responsible for delivering these activities as outlined on slide 7.
Context and Background

## Slide 3
Non-SIT Supplier Journey Map
REC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIP Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PP |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Service Activation (ISD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Service Activation (MDD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migration Sprint Planning Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PP is Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Supplier begins migrating from EFD
Supplier has run all Qualification Test Scripts
BSC review Final QAD
(targeted to be 5 WDs, but can be up to 20WDs)
REC review Final QAD
(targeted to be 15 WDs, but can be up to 20WDs)
BSC / REC make Director Sign Off question available to Supplier on QAD Portal
REC Code Manager review, follow-up and Qualification decision
(up to 20 WDs)
REC Code Manager qualifies Supplier
MCC Issues Supplier Readiness Checks Proforma
(20 WD before PP is Qualified by PAB / REC Manager)
MCC recommends Supplier for Service Activation
MCC conducts Readiness Assessment
(Up to 8 WDs)
Supplier completes Supplier Readiness Checks proforma
(10 WDs)
Supplier submits Migration proforma to the MCC
BSC PAB qualifies Supplier
Submit Supplier for BSC PAB Paper Day)
(4WDs before PAB)
DIP Manager Checklist Complete
(10 WDs prior to Qualification)
DIP Manager Completes Checklist
DIP Onboarding start date
DIP Manager Email to invite Supplier to onboard to DIP production
(Target 1WD of Qualification Approval)
Supplier included in next available MDD / ISD Publication
Supplier loads ISD and MDD if relevant (Within 5 WDs)
Complete Final version QAD (add in QT Completion report)
BSC review Supplier qualification
(up to 16 WDs)
Supplier drafts QT Completion Report
Supplier submits Final QAD
Assurance Team review QT Completion Report
(est. 10WD)
Supplier Director Signoff
Intended EFD communicated by Supplier to Elexon’s Customer On/Offboarding Team
(As soon as possible, should be before the fast-track deadline of the intended MDD / ISD Publication PP plans to be included in)
Supplier sends QT Completion Report to Qual mailbox
Ongoing iteration of the QAD following initial submission
QT Completion Report assurance confirmation
Notification of qualification from BSC and / or REC,
(Same day as PAB / REC Manager approval)
Supplier obtains Director Signoff of QAD (at latest 20 WDs prior to qualification)
DIP Onboarding start date
Supplier onboards to DIP
(Must be completed by -1 WD prior to the Supplier’s EFD)
Set Aspirational EFD
(40 WDs before target PAB)
Supplier completes daily Migration granularity plan
(5WD)
Non-Service Active Supplier completes weekly graduality planning for future sprints
This is ongoing activity all PPs complete from Sprint 0, up until they’ve completed migration
Supplier’s Migration Planning transitions from forecast to committed plan
DIP Onboarding Complete (EFD -1WD)
Assurance Team review QT Completion Report
(est. 10WD)
Final QAD Unlocked on QAD Portal
Key planning milestones
We anticipate that after the Code Bodies review of the Final QAD, there will be frequent communication between Code Bodies and the Supplier to close out feedback on the Final QAD.
Sprint Execution Readiness Check proforma
To be completed as part of Sprint planning for the Sprint the PP is migrating in
DIP Manager transfers DIP IDs (and in some instances DCP IDs) from UIT to Production
Address Final QAD comments
(Depends on how quickly comments are addressed)
Address Final QAD comments
(Depends on how quickly comments are addressed)
Address Final QAD comments
(Depends on how quickly comments are addressed)
Existing Supplier: No MDD action
New Supplier / MPID: Raise MDD CRs and send to MDD co-ordinator by CR deadline
MDD CRs
Impact Assessment
Set Aspirational EFD
(40 WDs before target PAB)
MDD CRs approved
by SVG
MDD / ISD Preparation
BSCCo reviews and provides comments to Supplier
MDD / ISD Go-Live
(5WD after MDD /
ISD Published)

## Slide 4
REC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIP Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PP |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Service Activation (ISD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Service Activation (MDD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migration Sprint Planning Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PP is Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Non-SIT MOA / MEM Journey Map
MOA begins operating on DIP from their EFD
MOA has run all Qualification Test Scripts
REC Code Manager review, follow-up and Qualification decision
(up to 20 WDs)
REC Code Manager qualifies MOA
DIP Manager Checklist Complete
(10 WDs prior to Qualification)
DIP Manager Completes Checklist
DIP Onboarding start date
DIP Manager Email to invite MOA to onboard to DIP production
(Target 1WD of Qualification Approval)
MOA loads MDD / ISD (Within 5 WDs)
Complete Final version QAD (add in QT Completion Report)
MOA drafts QT Completion Report
MOA submits Final QAD
MOA Director Signoff
MOA sends QT Completion Report to Qual mailbox
Ongoing iteration of the QAD following initial submission
QT Completion Report assurance confirmation
Notification of qualification from REC
(Same day as REC Manager approval)
MOA obtains Director Signoff of QAD (at latest 20 WDs prior to qualification)
DIP Onboarding start date
MOA onboards to DIP
(Must be completed by -1 WD prior to the Supplier’s EFD)
Set Aspirational EFD
(40 WDs before target PAB)
DIP Onboarding Complete (EFD -1WD)
Assurance Team review QT Completion Report
(est. 10WD)
Final QAD Unlocked on QAD Portal
Key planning milestones
We anticipate that after the REC review of the Final QAD, there will be frequent communication between REC and the MOA to close out feedback on the Final QAD.
DIP Manager transfers DIP IDs (and in some instances DCP IDs) from UIT to Production
REC review Final QAD
(targeted to be 15 WDs, but can be up to 20WDs)
Address Final QAD comments
(Depends on how quickly comments are addressed)
BSC / REC make Director Sign Off question available to Supplier on QAD Portal
Address Final QAD comments
(Depends on how quickly comments are addressed)
Intended EFD communicated by MOA to Elexon’s Customer On/Offboarding Team
(As soon as possible, should be before the fast-track deadline of the intended MDD / ISD Publication PP plans to be included in)
Set Aspirational EFD
(40 WDs before target PAB)
MOA raises MDD CRs and sends to MDD co-ordinator by CR deadline
MDD CRs
Impact Assessment
MDD CRs approved
by SVG
BSCCo reviews and provides comments to MOA
MOA included in next available MDD /
ISD Publication
MDD / ISD Preparation
MDD / ISD Go-Live
(5WD after MDD /
ISD Published)

## Slide 5
REC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIP Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PP |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Service Activation (ISD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Service Activation (MDD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migration Sprint Planning Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PP is Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Non-SIT Data Services Journey Map
Data Service begins operating on DIP from their EFD
Data Service has run all Qualification Test Scripts
BSC review Final QAD
(up to 20 WDs)
BSC make Director Sign Off question available to Data Service on QAD Portal
BSC PAB qualifies Supplier
Submit Data Service for BSC PAB Paper Day)
(4WDs before PAB)
DIP Manager Checklist Complete
DIP Manager Completes Checklist
DIP Onboarding start date
DIP Manager Email to invite Supplier to onboard to DIP production
(Target 1WD of Qualification Approval)
Data Service loads MDD / ISD
(Within 5 WDs)
Complete Final version QAD (add in QT Completion report)
BSC review Data Service qualification
(up to 16 WDs)
Data Service drafts QT Completion Report
Dat Service submits Final QAD
Assurance Team review QT Completion Report
(est. 10WD)
Data Service Director Signoff
MDD / ISD Go-Live
(5WD after MDD /
ISD Published)
Data Service sends QT Completion Report to Qual mailbox
Ongoing iteration of the QAD following initial submission
QT Completion Report assurance confirmation
Notification of qualification from BSC
(Same day as PAB approval)
Data Service obtains Director Signoff of QAD (at latest 20 WDs prior to qualification)
DIP Onboarding start date
Data Service onboards to DIP
(Must be completed by -1 WD prior to the Supplier’s EFD)
Set Aspirational EFD
(40 WDs before target PAB)
DIP Onboarding Complete (EFD -1WD)
Final QAD Unlocked on QAD Portal
Key planning milestones
We anticipate that after the BSC review of the Final QAD, there will be frequent communication between BSC and the Data Service to close out feedback on the Final QAD.
DIP Manager transfers DIP IDs (and in some instances DCP IDs) from UIT to Production
Address Final QAD comments
(Depends on how quickly comments are addressed)
Address Final QAD comments
(Depends on how quickly comments are addressed)
Intended EFD communicated by Data Service to Elexon’s Customer On/Offboarding Team
(As soon as possible, should be before the fast-track deadline of the intended MDD / ISD Publication PP plans to be included in)
Set Aspirational EFD
(40 WDs before target PAB)
Data Service raises MDD CRs and sends to MDD co-ordinator by CR deadline
MDD CRs
Impact Assessment
MDD CRs approved
by SVG
BSCCo reviews and provides comments to Data Service
Data Service included in next available MDD /
ISD Publication
MDD / ISD Preparation

## Slide 6
The red circles denote key planning steps along the process, which participants are advised to identify as soon as is possible. The majority of these are driven by the target Balancing & Settlement Code (BSC) Performance Assurance Board (PAB)/Retail Energy Code (REC) Code Manager Qualification date for participants with the timings driven by lead times to those dates or days required to execute activities following the BSC PAB/REC Code Manager Qualification date.
The start point of the journey depicted in the journey maps is when a participant has successfully run all test scripts and has no outstanding defects or work-off items. At this point, a participant can complete their Qualification Testing (QT) Exit Report. Participants will have also completed all sections of the Initial Qualification Assessment Document (QAD), with the Final QAD available to them.
There is no set SLA for the length of time a participant should take to draft their Test Completion Reports, but they should complete these promptly to not delay the completion and submission of the Final QAD.
There is no specific journey map for those participants who are placing reliance on other participants but note that if you are placing partial or full reliance, the drafting of your Final QAD can’t be completed until the organisation you have placed reliance on has had their QT Completion Report assured by MHHS Test Assurance team.
For participants placing partial or full reliance on QT, your Final QAD will not be unlocked until the MHHS Test Assurance team have reviewed the Qualification Test Completion Report of the participant(s) you are placing reliance on. A reminder that participants placing full reliance on QT will not be required to submit a Qualification Test Completion Report.
Suppliers will be submitting their Migration Plans at a weekly granularity into the Migration Control Centre (MCC) in line with sprint cycle dates irrespective of whether they are actively migrating in the upcoming sprint. Note that Suppliers are required to submit Migration Plans at a daily level in the sprint planning cycle for the sprint they will start migrating in and only for that sprint. In subsequent sprints after they’ve started migrating, Suppliers will be required to provide weekly forecasts.
A participant’s intended go-live Effective From Date (EFD) should be communicated to Elexon in advance of the Fast Track Change Request (CR) Deadline of the Market Domain Data (MDD) / Industry Standard Data (ISD) version they will be included in, to ensure it can be processed in time for that version. Please note that the Fast Track CR deadline is approximately 1 month before the relevant ISD / MDD version’s go-live date. If there are any changes to the EFD after the fast-track deadline but before the publish, they should reach out to Elexon at the earliest opportunity to discuss the feasibility of getting any last-minute updates made before the publish. There is no guarantee of this though, so should be avoided. The MDD/ISD calendar for 2025 – 2026 can be found here.
Assumptions and Considerations

## Slide 7
Key contacts:
Qualification activities (BSC / REC Code Manager) – email MHHSQualification@elexon.co.uk
DIP activities (DIP Manager) – submit a case to Elexon Support
Service Activation (SA) activities (SA team) – submit a case to Elexon Support
Migration activities (MCC team) – email migration@mhhsprogramme.co.uk.
Other useful links:
Collaboration Base
Elexon Balancing and Settlement Code (BSC) website
MHHS website
Retail Energy Code (REC) website.
Additional Supporting Information

## Slide 8
Agreed BSC PAB Meeting Dates for 2026
Meeting Number | Meeting | Agenda Deadline | Paper Day | Meeting Date
PAB2026/01 | January | 19 January 2026 | 23 January 2026 | 29 January 2026
PAB2026/02 | February | 30 January 2026 | 5 February 2026 | 11 February 2026
PAB2026/03 | February | 16 February 2026 | 20 February 2026 | 26 February 2026
PAB2026/04 | March | 27 February 2026 | 5 March 2026 | 11 March 2026
PAB2026/05 | March | 16 March 2026 | 20 March 2026 | 26 March 2026
PAB2026/06 | April | 2 April 2026 | 9 April 2026 | 15 April 2026
PAB2026/07 | April | 20 April 2026 | 24 April 2026 | 30 April 2026
PAB2026/08 | May | 1 May 2026 | 7 May 2026 | 13 May 2026
PAB2026/09 | May | 18 May 2026 | 22 May 2026 | 28 May 2026
PAB2026/10 | June | 29 May 2026 | 4 June 2026 | 10 June 2026
PAB2026/11 | June | 15 June 2026 | 19 June 2026 | 25 June 2026
PAB2026/12 | July | 3 July 2026 | 9 July 2026 | 15 July 2026
PAB2026/13 | July | 20 July 2026 | 24 July 2026 | 30 July 2026
PAB2026/14 | August | 31 July 2026 | 6 August 2026 | 12 August 2026
PAB2026/15 | August | 17 August 2026 | 21 August 2026 | 27 August 2026
PAB2026/16 | September | 28 August 2026 | 3 September 2026 | 9 September 2026
PAB2026/17 | September | 14 September 2026 | 18 September 2026 | 24 September 2026
PAB2026/18 | October | 2 October 2026 | 8 October 2026 | 14 October 2026
PAB2026/19 | October | 19 October 2026 | 23 October 2026 | 29 October 2026
PAB2026/20 | November | 30 October 2026 | 5 November 2026 | 11 November 2026
PAB2026/21 | November | 16 November 2026 | 20 November 2026 | 26 November 2026
PAB2026/22 | December | 27 November 2026 | 3 December 2026 | 09 December 2026