## Introduction
Introduction to SIT Operational Testing Theme 3 Batch 1 - Service Management Test Scenarios and Test Cases
This batch of Test Scenarios and Test Cases will test Service Management in the MHHS arrangements
The Service Management Strategy sets out the high level approach to service management, concluding on the "hybrid model" approach to service management:
MHHS Service Management Strategy - MHHS Programme
BSCCo under the Helix project have developed these arrangements further into a Service Definition Document (SDD): which is being consulted on in parallel with these Scenarios and summary Test cases
BSCCo under the Helix project have then developed the Service Definitions into 5 further Low Level Service Designs (LLSD) for each of their Service Providers (DIP, BJSS, Cognizant, CGI) and for Service Users. The LLSD for Service Users is being consulted on in parallel with the Scenarios and summary Test cases
The Programme has taken each ITIL core function/process of Service Management to define the Test Scenarios and these can be seen in a separate tab for each Test Scenario
In deriving the Test Cases, the Programme has considered how to exercise the core functions/processes defined in the SDD using a set of defined test conditions to trigger those processes and the test steps have been derived from the Low Level Service Designs, particularly the DIP User LLSD which shows the interactions with industry
The Programme are providing further information on how the test cases for Major Incident Management (MIM) have been defined as it is important to consider these in light of core Programme risks (e.g. R829 raised from the REC PAB)
Assumptions
Service Management systems (e.g. the proposed Elexon Helix ServiceNow instance) will be in place and used to execute tests
Pre-conditions will need to be set-up in order to execute tests (e.g. ServiceNow accounts and log-ins for external parties to trigger tests)
Some elements of testing will have to be paper based (e.g. we will not be implementing fixes to systems for issues, we will not be raising actual Change into operational industry Change Management processes)
Resources will be available from all test participants to execute testing
The MHHS Programme will manage the execution of Operational SIT
Any known constraints for SIT Ops Testing have been shared with MHHS Ops Test team – e.g. any missing integration, any modules that will differ from what will be in production, workarounds to be used in SIT Ops
Register Access test case is run for all SIT PPs who will be raising Service Now tickets as part of other tests
DIP will not take ownership of any Choreography required which will require DIP Manager/Elexon SM to take responsibility to orchestrate any choreography required

## MIM TC Derivation
Derivation of Test Cases for Major Incident Management
In deriving the test cases for Major Incident Management, it is important that we exercise the coordination and interactions with affected industry parties and that we take into account key drivers for the seriousness of industry issues, e.g.:
Service outages that impact multiple industry participants (e.g. Central Services - DIP, Registration, CSS, Elexon Helix)
When an incident occurs during a business day (i.e. Secure Active window, etc.) to assess if the central service management function needs to consider choreography of systems/processes
Delays or interruptions to a key business process occurring in a key window
Establish per participant/central service the downtime which would have a Major business impact (e.g. impact of >1 settlement period of missing consumption data or Helix outage)
#MAPNs impact by issue (e.g. market share of participants, #MPANs in LDSO area)
Assumptions
Individual PP’s will be best placed to define who should be informed if their service/platform goes down or if a Major Incident occurs, therefore engagement with PPs is essential within the MIM process (e.g. triage)
Restorative action needs to take into account choreography of messaging, timings and responsibilities
Elexon service management facilities and triage available to support incident triage out of hours (24x7)
Note that DIP is stateful and therefore there are wide-ranging impacts for some incidents
DIP will not take ownership of any Choreography required which will require DIP Manager/Elexon SM to take responsibility to orchestrate any choreography required
Questions
Does the MHHS service management function need to agree thresholds where individual parties need to highlight MIM events to the MHHS Service Management function?
What is the maximum impact - is it impact on switching data? are there circumstances where consumption or registration data will be lost?
What are the support arrangements at Elexon for out of hours?
Proposed MIM Test Cases on the basis of the above:
# | Industry Impacting Outages | Variations (incl. market share impact) | When an incident occurs? | Downtime | Who raises Issue with Service Now | Notes | Category
SC1 | DIP | DIP service failure | In Hours - within Secure Active window | 2 Settlement Period downtime (impacting incoming consumption and registration data) = hour | SDS receiving http error message (e.g. Callisto) | Impact: (1) DIP secondary routing tables are not updated when in the secure active window*. Response: Therefore need to manage the recovery sequence. This is to avoid misrouting of flows. *5-8pm (tbc) - when registration service are sending out the key appointment flows (IF036) | Choreography
SC2 | DIP | DIP service failure | Out of Hours | 3 Settlement Period downtime (impacting incoming consumption and registration data) = 90 mins | DIP monitoring triggers incident report | Impact: As per SC1 Response: Is on call support sufficient or available to deal with a problem like SC1 | Time or Market Share Thresholds
SC3 | DIP | Security Incident | Within Working Hours | Either unauthorised data breach due to a security incident or suspected security incident at DIP. Unauthorised penetration of customer system(s) at DIP | DIP monitoring triggers incident report | Impact: Potential downtime if penetration occurring. Data breach could be actively managed while platform remains up. Response: Engage Security & act according to the security policy of the organisation impacted | Service Provider Definition of Impact
SC4 | Registration | Single LDSO failure (e.g. DNO Adaptor instance) | In Hours - within Secure Active window | 2 hours | multiple Suppliers (propse 3) not receiving PUB responses LDSO or their SP through monitoring | Impact: Any response from the LDSO Registration service would be delayed and that would impact what DIP can send out. So a secondary routing issue appears on a smaller scale to SC1. Response: Therefore need to manage the recovery sequence for a particular DNO licence area (e.g. Yorkshire ). This is to avoid misrouting of flows. Need to ensure correct sequence of processing in the DIP via manual intervention (TBC - functionality not there at moment but in backlog). | Choreography/Time or Market Share Thresholds
SC5 | Registration | Single LDSO failure (e.g. DNO Adaptor instance) | Out of hours | 2 hours | multiple Suppliers (propse 3) service provider (e.g. ESG) not receiving PUB responses LDSO or their SP through monitoring | Impact: Asper SC4 Response: Is on call support sufficient or available to deal with a problem like SC1 We recognise LDSOs do not run Service Desks out of hours, so this test to run through what happens in these circumstances | Time or Market Share Thresholds
SC6 | Registration | MPRS software failure (i.e. impacting all LDSOs) | In hours - within Secure Active window | 24 hours | multiple Suppliers (propse 3) not receiving PUB responses | Impact: Registration service ceases to function. Appointments, Change of supplier etc aren't updated. Response: Once MPRS issue resolved. all files to be processed by MPRS as normal updating all parties (including EES)Manage the recovery of flows Similar to SC1 (sequencing/secondary routing) & SC17 (managing volume) | Choreography
SC7 | Registration | MPRS software failure (i.e. impacting all LDSOs) | Out of hours | 24 hours | multiple Suppliers (propse 3) not receiving PUB responses | Impact: As above Response: As above We recognise LDSOs do not run Service Desks out of hours, so this test to runthrough what happens in these circumstances | Time or Market Share Thresholds
SC8 | CSS | CSS System failure | As per prior operational incident During working hours system failure for 4 hours | As per prior operational incident During working hours system failure for 4 hours | DCC raise from TOC diagnostics | Impact: Large Problem = messages not getting to registration and therefore Registration Service ceases to function. Appointments, Change of supplier etc aren't updated (like SC6). Smaller Problem = Meter Data Retriever (MDR's) not getting updated to DCC and therefore not able to collect data. As attempts to change the MDR and not been concluded successfully. Therefore out of sync. Response: Sequencing & Volume management A CSS outage would be managed by the Switching Operator and we would expect Elexon Service Management to liase with the Switching Operator to understand any knock on impacts on DIP messages and settlement data so these can be resolved.
SC9 | VAS - Helix | VAS System failure | Working Day as per settlement calendar | 48 hour weekdays | Supplier raises no receipt of REP003 reports | Impact: Suppliers & LDSO's not receive reports. Some of these reports support DUoS Billing (distribution use of system - billing supps for using network). Response: Participants flag to Elexon SM, then Elexon would ultimately engage the Helix SD process. Though we'd expect Helix to have noticed this! | Service Provider Definition of Impact
SC10 | MDS - Helix | MDS System failure | Working Day as per settlement calendar | 48 hour weekdays | LDSO raises no receipt of REP002a reports Helix from internal tooling/monitoring | Impact: Suppliers & LDSO's not receive reports. Some of these reports support DUoS Billing (distribution use of system - billing supps for using network). Response: Participants flag to Elexon SM, then Elexon would ultimately engage the Helix SD process. Though we'd expect Helix to have noticed this! | Service Provider Definition of Impact
SC11 | LSS - Helix | LSS System failure | Working Day as per settlement calendar | 48 hour weekdays | ADS raises no receipt of LSS data | Impact: Suppliers forecasting demand, SDS & ADS wouldn’t receive data allowing them to estimate consumption. So the IF021's would be delayed for estimation only. Also a volume allocation impact as shifting bulk of IF021 to later in the day after that normal expected peak time (5am to 8am) Response: Elexon would ultimately engage the Helix SD process. Though we'd expect Helix to have noticed this! | Service Provider Definition of Impact
SC12 | ISD - Helix | Incorrect data sent impacting PPs | In accordance with ISD timetable (monthly or fortnightly updates) | 48 hour weekdays | LDSO St Clements raises processing issue due to ISD mismatches | Impact: Increased validation failures. As everyone is using this data set for many processes we'd expect many unpredictable impacts Response: Get new ISD issued | Choreography
SC13 | ISD - Helix | ISD system failure | In accordance with ISD timetable (monthly or fortnightly updates) | System down during ISD publication window | Newly Qualified Party raises lack of data to start migration | Impact: Similar to above but on a larger scale Response: Return service to working state | Choreography
SC14 | DAH - Helix | Data Acquisition Hub System failure | 5am to 8am weekday = Peak Data Flow as per the Message Model (31.3M messages) | 3 hours | Helix Internal and/or DIP | Impact: MHHS Consumption & Registration messages will be backing up & retrying for 72 hours on the DIP. Helix's Zone redundancy should ensure no data loss internally Response: Elexon would ultimately engage the Helix SD process. Though we'd expect Helix to have noticed this! | Time or Market Share Thresholds
SC15 | SDS | Failure of major SDS (e.g. Callisto) | Working Days | 2 Settlement Days | Supplier raises lack of actual data in REP003 reports | Similar to SC17 DCC but on a smaller scale. Volume allocation displacement. Shifting 2 days of IF21 volume and then having to manage the re-introduction of the backlog To test criteria of whether Major Incident - may expect this would go to Incident Management | Time or Market Share Thresholds
SC16 | EES | EES Service Failure | Working Days | 2 days | Supplier gets REGS failures as result of inconsistent data | EES out of synch with REG To test criteria of whether Major Incident - if not, could go to Incident Management maybe Cr044 (to be approved) - if EES data gets corrupted we would utilise the proposed flow EES can supply to Registration to bring it back in sync | Choreography /Service Provider Definition of Impact
SC17 | DCC Smart DSP | DCC Smart DSP Service Failure | IF-021's cannot be issued DCC Service Failure, results in consumption data not being able to be sent to Suppliers or MDRs which means downstream delays for SDS being able to generate and send IF-021's to MDS | 1/2 day | DIP identify requirement for increased IF-021 volumes (e.g. in the afternoon) Supplier to raise as expecting number reads not received or SDS or DCC (ToC) For the purposes of this TC we will use DCC (ToC) as the most likely trigger for this event | Impact: Ability for DIP & Helix to flex message volume profile. DIP & Helix are expecting high volumes from 5am to 8.30am (tbc). If this peak is moved by a system outage can DIP & Helix manage recovery in such a way that they are not overwhelmed. Response: Might need a staged recovery from all or key participants to manage the volume backlog Consideration: how the backlog of IFs will be managed following the DIP's recovery under different outage scenarios, multiple PPs of not receiving IF-021's e.g. LDSO's for DUoS, Suppliers for billing | Time or Market Share Thresholds
SC18 | DTN | DTN Service Failure | e.g. D0010 (Meter Readings), D0030 (DUOS report) cannot be issued | 1/2 day | Electralink raises call to advising of a significant DTN outage | Impact: One of awareness to participants who may call ELEXON service desk, example during migration that PP will receive Reports for migrated meters but not for Non-half-hourly | Choreography
# | Category | Description
1a | Choreography: | The incident resolution has to consider the implications of when an incident occurs during a business day (i.e. Secure Active window, etc.) to assess if the central service management function needs to consider choreography of systems/processes. The event driven nature of the system may be overruled in favour bringing systems back up intelligently using choreography.
1b |  | The impact is Major because it delays or interrupts a key business process occurring in a key window
2a | Time or Market Share Thresholds: | Establish per participant/central service the downtime which would have a Major business impact. For example 30 minutes of missing consumption data may not actually impact Settlement (as estimation routines would kick in) but 60 minute might?
2b |  | Establish which Participants or Groups of Participants would cause a Major impact by virtue of their market share of data.
2c |  | The MHHS service management function needs to agree thresholds where individual parties need to highlight issues to the MHHS Service Management function.
2d |  | Seek agreement/alignment with PPs/external service providers
3 | Service Provider Definition of Impact | Individual PP’s will be best placed to define who should be informed if their service/platform goes down. Or if a Major incident occurs.

## TCs
Scenario Incident Management - Major | Test Case variations/resolution routes | Test cases
Entry into Incident process - Major 1 - Service User / MP raises in the Portal 2 - Elexon Event Mngt 3 - Service Provider raises directly 4 - Service Provider Event Mngt 5 - Change Mngt MI possible outcomes: 1 - Implement Restorative action no Change 2a - Change Required happy path 2b - Change Required, Imp fails rollback success 2c - Change Required, Imp fails, rollback fails - covered under Change EMER | MI raised – Resolved, no CR required MI raised – CR Required, goes EMER CR route happy path MI raised – CR Required, goes EMER CR route, change implementation fails rollback instigated/completed MI identified, subsequently downgraded to normal incident Cannot dictate the outcomes, the process itself should dictate this. | Please refer to MIM TC Derivation sheet: SC1, SC2, SC3, SC4, SC5, SC6, SC7, SC8, SC9, SC10, SC11, SC12, SS13, SC14, SC17, SC18
Scenario Incident Management - Normal | Test Case variations/resolution routes | Test cases
Entry into Incident process - Normal 1 Service User raises in Portal 2 Elexon Event Mngt 3 Service Provider raises directly 4 Service Provider Event Mngt Incident Normal possible outcomes: 1 - Resolved at 1st Line, 2nd line or 3rd line no Change required 2 - Change Required 3 - Hand off to Non Elexon Managed - 4 - Incident results in Problem being raised | Incident, resolved by 1st Line Incident, resolved by 2nd line Service user requested to support troubleshooting/investigation Incident, resolved by 3rd line Incident to Change process Normal identified, subsequently re-categorised to major incident | Please refer to MIM TC Derivation: SC15, SC16 Single message failure
Scenario Change Mngt Normal | Test Case variations/resolution routes | Test cases
Entry into Change process - Normal 1 Elexon Support Team request Change 2 Service Provider requests Change direct access 3 Service Provider Problem Mngt 4 Service Provider Release Mngt 5 Elexon Problem Mngt 6 Elexon Release Mngt Change Mngt normal possible outcomes 1 - Implement Restorative action no CR 2a - Change Required happy path 2b - Change required Imp fails Roll back fails - Incident Mngt | Routes: Change raised – doesn’t require approval (CAB) change implemented successfully, Change raised – doesn’t require approval (CAB) change implemented unsuccessfully, roll back successful Variations: 1. Internal Change 2. BSC Change 3. BSC and REC Change 4, Post M10 Change process | TC01 Internal Change TC02 BSC Change TC03 BSC and REC Change TC04 Post M10 Change process
Scenario Change Mngt EMERGENCY | Test Case variations/resolution routes | Test cases
Entry into Change Mngt Emergency 1. Elexon Support team raise 2. Major Incident 3. Service Provider Problem Mngt 4. Service Provider Release Mngt 5. Retrospective Change EMER Change possible outcomes 1 - Change Implemented success 2 - Change Implementation fails, rollback success 3 - Change Implementation fails, rollback fails -> Incident Mngt | EMER Change raised (not as a result of an Incident) change approved and implemented successfully EMER Change raised (not as a result of an incident) change implemented unsuccessfully, roll back instigated/completed successfully EMER Change raised (not as a result of an incident) change implemented unsuccessfully, roll back fails -> Incident Mngt Note: Included EMER Change as a result of a Major Incident as part of MI TCs | Examples below - Others WIP TC01 - Emergency Change SP Release Mngt invoked for emergency patch to be applied
Scenario Problem Mngt (recurring incident, root cause) | Test Case variations/resolution routes | Test cases
Entry into Problem Mngt 1 Elexon Support Team 2 Service Provider raises 3 Internal problem Mngt 4 Incident Mngt Problem Mngt possible outcomes 1 Resolved no Change required 2 Change required 3 Incident Mngt 4 Knowledge Mngt update | Problem resulting in Incident Mngt process (workaround identified) Problem resulting in Change Mngt process Problem resolved no change required resulting in known error identified and directed to Knowledge Mngt | Examples below - Others WIP TC01 - Problem identified by Service Provider TC02 - Problem raised via Incident Mngt trend analysis
Scenario Request Fulfilment | Test Case variations/resolution routes | Test cases
Entry into Request Fulfilment 1 Service User raises 2 Service provider raises Request Fulfilment possible outcomes 1 Request fulfilled - No approval 2 Request fulfilled - with approval | Service Request approved and fulfilled Service Request Rejected | Examples below - Others WIP TC01 - Password re-set TC02 - DIP access request
Scenario Knowledge Mngt | Test Case variations/resolution routes | Test cases
Entry into Knowledge Mngt 1. Service User 2. Incident Mngt 3. Problem Mngt 4. Change Mngt 5. Service Desk 6. Service Partner Possible Outcomes Knowledge Mngt 1. KM item added, modified or retired | Search for item Request an item to be added | Examples below - Others WIP TC01 - Service User access and searches for KM item relating to MP not being able see DIP Ids TC02 - Service User requests that a KM item is added for Domain Name Failure error message
Scenario Dashboards / Reporting | Test Case variations/resolution routes | Test cases
| Service User submits a request and receives Report from Service Now Service User submits a request and receives Dashboards from Service Now | TC01 - Service User submits a request and receives Reports TC02 - Service User submits a request and receives Dashboards
Scenario Service user Registers for account | Test Case variations/resolution routes | Test cases
Entry into Registration 1. Service User | SU Registers for and is able to access Elexon SM Portal | TC01 - Service User (MP) registers for Portal Access
Scenario Service Level Management | Test Case variations/resolution routes | Test cases
Entry into Service Level Mngt 1 Service User raises 2 Service provider raises | SLM Request raised and completed | Examples below - Others WIP TC01 - Request to add an SLA TC02 - Request to change SLA
Scenario Service Catalogue | Test Case variations/resolution routes | Test cases
Entry into Service Catalogue 1 Service User raises 2 Service provider raises Possible outcomes Service Catalogue 1. Request fulfilled 2. Change Mngt | Request raised no change required Request raised change required | Examples below - Others WIP TC01 - Request to add item to the Service Catalogue