## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Release | Defect ID | Reason for change
2023-10-26 | Shaun Magee |  |  | Scenario creation
2023-12-08 | Shaun Magee | 5.2.1 v0.1 |  | Tidy DIP Steps and remove columns Message Output and Message Output Event Code Following PP Comments : Add missing IF-041 missing steps Correct CSS Message Numbers to 5 digits Move BP010C steps to after Disconnection Remove any Flows to Proposed Services Correct MS/DS De-Appointments to properly reflect BP007. Note: Design confirmed that as Meter is not removed (AE Register turned off) no IF-005/IF-006/IF-004 (Smart) or MTD Details need to be issued
2024-02-08 | Dan Gee | 5.2.1 v0.2 |  | Moved De Linking of Import Export MPAN process to before disconnection on TC01 & TC02 based on PP feedback that they would be de linked before they are disconnected
2024-05-15 | Suraj Kadam | IR7 v0.3 |  | Replaced DIP response from "http 202 response from DIP" to "http 201 response from DIP" wherever needed
2024-05-16 | Dan Gee | IR7 v0.3 |  | Add MDR [EnergisationStatusChange] as optional recipiants for PUB-008 due to DIN-901 ON TC01
2024-05-17 | Suraj Kadam | IR7 v0.3.1 |  | Added column "Test Case Version" in SITFTS0030 Overview and TC01 to TC02
2024-07-01 | Dan Gee | IR7 v0.3.2 | 35172 | Added Pre Req to test cases overview and as opening steps on TC01 SITFTS-0025 is requred to be ran as a pre condition in order to have a linked Import and Export with different suppliers updated incorrect Meter service refrenced in TC02
2024-11-08 | Ashwin | IR7 v0.3.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC01 for steps 3,5,10,11,14,23,26,28,36,38,40,45,48,50,52,54,60,66
2024-11-08 | Ashwin | IR7 v0.3.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC02 for steps 3,5,10,14,15,18,26,29,31,38,40,42,47,50,52,54,56,62,68
2025-01-22 | Dan Gee | v0.3.4 | 47336 | Amended incorrect acronym for receipt of PUB-050 from SUPC to EES on TC02
2025-02-03 | Dan Gee | v0.3.4 | 47984 | Amended event code for IF-041/PUB-041 after de energisation has taken place to [ReadingEnergisationChg] on TC01 & TC02 also updated recipiant of IF-019/PUB-019 from REGS to LDSO on TC02
2025-02-07 | Dan Gee | v0.3.4 | 48387 | Amended Pre Req on TC01 to refrence the correct test to run SITFTS-0025 TC01 prior to execution
2025-04-29 | Dan Gee | v0.3.4 | Requirements Update | Removed invalid mappings - TC01 MHHS-BR-SU-067, MHHS-BR-SU-068 TC02 MHHS-BR-SU-067, MHHS-BR-SU-068, MHHS-BR-DS-121, MHHS-BR-DS-122
2025-05-27 | Dan Gee | v0.3.5 | Requirements Update | Removed invalid mappings - TC02 MHHS-BR-LD-028 Added valid mapping TC02 MHHS-BR-LD-027
2025-09-17 | Dan Gee | v0.3.6 | General Update | Performed retrospective clean-up to correct grammar, spelling, and clarify ambiguous steps and acronyms on TC01 & TC02

## SITFTS0855 Overview
Scenario ID | SITFTS-0855
Scenario Title | Disconnection of Linked Export MPAN
Theme | Metering Changes
Description | Supplier De-links an Export MPAN and then initiates De-Energisation/Disconnection ending with Metering Service and Data Service De-Appointment.
Functional Category | Metering Changes
Functional Area 1 | Meter Removal/De-Energisation/Disconnection of Export Linked MPAN
Functional Area 2 | De-Energisation/Disconnection successful and Metering and Data Service De-Appointed
Creator | Shaun Magee
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP010C, BP007, BP009, BP008, BP002, BP003
Pre-Requisites | Test Case 1 Supplier executing SITFTS-0855 TC01 should run SITFTS-0025 TC02 (Smart) as a pre-condition to this test case to ensure that the test data associated with the Linked Export MPAN (Smart) is in the correct set up to successfully execute this test case (Import & Export having different suppliers) by the supplier by disconnecting the Linked Export MPAN.
Boundaries | Processing ends when Export Meter Point is disconnected and Services De-Appointed
Test Case Variables | (1) smart, linked Export MPAN disconnection, where Import and Export have different suppliers - Current Day (2) advanced, linked Export MPAN disconnection, where Import and Export are the same supplier - Current Day
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0855 TC01 | SITFTS-0855-Smart | SITFTS-0855 - Smart | 0.3.6 | Smart Linked Export MPAN, same-day De-Link/Disconnection (as per DES138 data specification) where the Import MPAN has a different Supplier | Smart Meter | Linked MPAN (Export) | Current Day
2 | SITFTS-0855 TC02 | SITFTS-0855-Advanced | SITFTS-0855 - Advanced | 0.3.7 | Advanced Linked Export MPAN, same-day De-Link/Disconnection (as per DES138 data specification) where the Import MPAN has the same Supplier | Advanced Meter | Linked MPAN (Export) | Current Day
Back to List of
Test Scenarios

## SITFTS0855-Smart
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0855 TC01 |  |  |  | 0.3.6 |  | SITFTS-0855-Smart | SITFTS-0855 - Smart | Smart Linked Export MPAN, same-day De-Link/Disconnection (as per DES138 data specification) where the Import MPAN has a different Supplier | Smart Meter | Linked MPAN (Export) | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0855-Smart | Pre Req | Pre Req | [7 empty] | Supplier executing SITFTS-0855 TC01 should run SITFTS-0025 TC01 (Smart) as a pre-condition to this test case to ensure that the test data associated with the Linked Export MPAN (Smart) is in the correct set up to successfully execute this test case (Import & Export having different suppliers) |  | N
| Supplier Removal Request | 1 | BP007 | 10 | MHHS-BR-SU-051 | SUPC |  |  |  | Current Supplier Removal Request |  | N
| Meter Works Request | 2 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142/Agreed Method |  | SMSC | Existing Metering Service receives a Request to carry out meter works - (Turn off the AE Register) and De-Energise |  | Y
| Reading captured and Physical Works completed | 3 | BP009 | 35 | MHHS-BR-MS-054 MHHS-BR-MS-055 | SMSC |  |  |  | Capture Cumulative Meter Reading(s)/HH Downloads |  | N
|  | 4 | BP009 | 40 | MHHS-BR-MS-056 | SMSC |  |  |  | Physical Meter Works completes (Turn off the AE Register) |  | N/A
| Issue Cumulative Meter Read(s) | 5 | BP009 | 60 | MHHS-BR-MS-061 | SMSC | IF-041 | [ReadingEnergisationChg] | DIP | SMSC sends IF-041 to the DIP. | http 201 response from DIP | N
|  | 6 | BP009 | 85 |  | DIP | PUB-041 | [ReadingEnergisationChg] | SDSC, LDSO, SUPC | DIP sends Cumulative Meter Read(s) via the PUB-041 to Data Service, LDSO and Supplier |  | N
|  | 7 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingEnergisationChg] | SDSC | SDSC receives PUB-041. | SDSC receives PUB-041 with Cumulative Meter Read(s) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingEnergisationChg] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 with Cumulative Meter Read(s) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 9 | BP009 | 220 | MHHS-BR-SU-072 | DIP | PUB-041 | [ReadingEnergisationChg] | SUPC | SUPC receives PUB-041. | Supplier (Current) receives PUB-041 with Cumulative Meter Read(s) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 10 | BP009 | 215 | MHHS-BR-SU-071 | SUPC |  |  |  | Supplier (Current) reconciles Metering / Reading Information | On receipt of all the metering updates and reading information Supplier can choose to reconcile these are aligned with the data flows received. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | N
| De-Energisation - Start | 11 | BP008 | 80 | MHHS-BR-MS-049 | SMSC | IF-007 | [EnergisationStatusChange] | DIP | As part of the meter remove process de-energisation starts at this point SMSC sends IF-007 to the DIP. | http 201 response from DIP | N
|  | 12 | BP008 | 90 |  | DIP | PUB-007 | [EnergisationStatusChange] | REGS | As part of the meter remove process energisation starts at this point DIP sends PUB-007 to the REGS. |  | N
|  | 13 | BP008 | 105 110 | MHHS-BR-RS-104 MHHS-BR-RS-105 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | REGS receives PUB-007. | REGS receives PUB-007 with details of Energisation Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS Change of Energisation Status Notification | 14 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to the DIP | http 201 response from DIP | N
|  | 15 | BP008 | 125 135 |  | DIP | PUB-008 | [EnergisationStatusChange] | SMSC, SUPC, LDSO, SDSC, MDS EES & MDR (Optional) | DIP sends PUB-008 to SMSC, SUPC, LDSO, SDSC, MDS, EES & MDR (Optional) |  | N
|  | 16 | BP008 | 140 | MHHS-BR-MS-050 | DIP | PUB-008 | [EnergisationStatusChange] | SMSC | Metering Service (Currently Appointed) receives PUB-008 | Metering Service (Current) receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 17 | BP008 | 175 |  | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | SUP (Current) receives PUB-008. | Supplier (Current) receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 18 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | SDSC | SDS (Current) receives PUB-008. | Data Service (Current) receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 19 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 20 | BP008 | 160 | MDS | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008. | MDS receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 21 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 22 | BP009 | N/A | DIN-901 | DIP | PUB-008 | [EnergisationStatusChange] | MDR (Optional) | MDR (Optional) receives PUB-008. | MDR (Optional) receives PUB-008 EnergisationStatusChange, confirms Update for energisation change and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Supplier issues De-Link request | 23 | BP010C | 860 | MHHS-BR-SU-094 | SUPC | IF-019 | [LinkedImportExportRemove] | DIP | Supplier identifies Export MPAN that needs to be De-Linked and issues the De-Link Request via the Manage Meterpoint Relationships issuing IF-019 to the DIP | http 201 response from DIP | N
|  | 24 | BP010C | 870 |  | DIP | PUB-019 | [LinkedImportExportRemove] | LDSO | DIP sends PUB-019 to LDSO |  | N
|  | 25 | BP010C | 880 890 | MHHS-BR-LD-043.1 MHHS-BR-LD-043.2 | DIP | PUB-019 | [LinkedImportExportRemove] | LDSO | LDSO receives the PUB-019 and performs validation checks before updating the Import/Export linkage | LDSO receives MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 26 | BP010C | 900 | MHHS-BR-LD-043.3 | LDSO | DB05 | N/A | REGS | LDSO issues DB05 (Accepted) to the Registration Service |  | N
|  | 27 | BP010C | 905 | MHHS-BR-RS-071.6 | REGS | DB05 | N/A | REGS | The Registration Service receives the DB05 (Accepted) | REGS receives DB05 (Accepted) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 28 | BP010C | 905 | MHHS-BR-RS-071.8 | REGS | IF-020 | [LinkedImportExportRemove] and Response Code = "A" | DIP | The Registration Service issues IF-020 to DIP | http 201 response from DIP | N
|  | 29 | BP010C | 910 |  | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SUPC, SUPL, SDSC, SMSC, LDSO, EES | DIP sends PUB-020 to the Supplier (Current), Supplier (Linked Import), Data Service (Current), Metering Service (Current), LDSO and EES |  | N
|  | 30 | BP010C | 950 | MHHS-BR-SU-096 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SUPC | Supplier (Current) receives the PUB-020 Accepted De-Link Request Response | Supplier (Current) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 31 | BP010C | 950 | MHHS-BR-SU-096 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SUPL | Supplier (Linked Import) receives the PUB-020 Accepted De-Link Request Response | Supplier (Linked Import) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 32 | BP010C | 930 | MHHS-BR-DS-130.5 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SDSC | Data Service (Current) receives the PUB-020 Accepted De-Link Request Response | Data Service (Current) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 33 | BP010C | 920 | MHHS-BR-MS-066.5 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SMSC | Metering Service (Current) receives the PUB-020 Accepted De-Link Request Response | Metering Service (Current) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 34 | BP010C | 940 | MHHS-BR-LD-046 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | LDSO | LDSO receives the PUB-020 Accepted De-Link Request Response | LDSO receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 35 | BP010C | 931 | MHHS-BR-EES-016.3 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | EES | EES receives the PUB-020 Accepted De-Link Request Response | EES receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Request Disconnection | 36 | BP007 | 59 | MHHS-BR-SU-054 | SUPC | D0132 |  | LDSO | Current Supplier sends a D0132 Details of Disconnection of Supply to the LDSO to Request Disconnection |  | N
|  | 37 | BP007 | 60 | MHHS-BR-LD-016 MHHS-BR-LD-017 | SUPC | D0132 |  | LDSO | LDSO receives the D0132 and accepts the request | LDSO receives D0132 with Details of Disconnection of Supply and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Disconnects Meter Point | 38 | BP007 | 65 | MHHS-BR-LD-016 MHHS-BR-LD-017 MHHS-BR-LD-018 | LDSO | Internal DB03 |  | REGS | LDSO disconnects Meter Point and sends an Internal DB03 to the Registration Service |  | N
|  | 39 | BP007 | 70 | MHHS-BR-RS-097 | LDSO | Internal DB03 |  | REGS | REGS receives the Internal DB03 | REGS receives Internal DB03 and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out LDSO Disconnection Notifications | 40 | BP007 | 70 | MHHS-BR-RS-098 | REGS | IF-009 | [MPANDisconnection] | DIP | REGS sends IF-009 to the DIP to confirm the Meter Point has been disconnected | http 201 response from DIP | N
|  | 41 | BP007 | 85 |  | DIP | PUB-009 | [MPANDisconnection] | SUPC, LDSO, EES | DIP sends PUB-009 to SUP (Current), LDSO and EES to confirm the Meter Point has been disconnected |  | N
|  | 42 | BP007 | 95 | MHHS-BR-SU-056 MHHS-BR-SU-057 | DIP | PUB-009 | [MPANDisconnection] | SUPC | SUP (Current) receives PUB-009. | Supplier (Current) receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 43 | BP007 | 86 | MHHS-BR-LD-020 | DIP | PUB-009 | [MPANDisconnection] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 44 | BP007 | 87 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [MPANDisconnection] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out EES MPAN Status Change Update | 45 | BP007 | 70 | MHHS-BR-RS-099 | REGS | IF-050 | [MPStatusChange] | DIP | REGS sends IF-050 to the DIP to confirm the MPAN status change | http 201 response from DIP | N
|  | 46 | BP007 | 126 |  | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES to confirm the MPAN status change |  | N
|  | 47 | BP007 | 127 | MHHS-BR-EES-016.3 | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050. | EES receives PUB-050 with details of the MPAN Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS MPAN Status Change Update | 48 | BP007 | 70 | MHHS-BR-RS-099 | REGS | CSS00700 | N/A | CSS | REGS sends CSS00700 to CSS |  | N
|  | 49 | BP007 | 115 | CSS | REGS | CSS00700 | N/A | CSS | CSS receives CSS00700 and Terminates RMP |  | Y
| Deactivation Formal Request | 50 | BP007 | 96 | MHHS-BR-SU-057 | SUPC | CSS01900 | N/A | CSS | SUP (Current) sends Registration Deactivation Request CSS01900 to CSS |  | N
|  | 51 | BP007 | 120 | CSS | SUPC | CSS01900 | N/A | CSS | CSS receives CSS01900 and performs Registration Deactivation |  | Y
| CSS Registration Deactivation | 52 | BP007 | 121 | CSS | CSS | CSS02860 | N/A | REGS | CSS performs Registration Deactivation and sends CSS02860 to REGS |  | N
|  | 53 | BP007 | 125 | MHHS-BR-RS-100 MHHS-BR-RS-101 | CSS | CSS02860 | N/A | REGS | REGS receives CSS02860 and updates Registration | REGS receives CSS02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS DeRegistration Notification | 54 | BP007 | 125 | MHHS-BR-RS-101 MHHS-BR-RS-102.1 | REGS | IF-009 | [CSSDeRegistration] | DIP | REGS sends IF-009 to the DIP to confirm the CSS De-Registration | http 201 response from DIP | N
|  | 55 | BP007 | 130 |  | DIP | PUB-009 | [CSSDeRegistration] | SUPC, LDSO, MDS and EES | DIP sends PUB-009 to SUPC, LDSO, MDS and EES to confirm the CSS De-Registration |  | N
|  | 56 | BP007 | 137 |  | DIP | PUB-009 | [CSSDeRegistration] | SUPC | SUPC receives PUB-009. | Supplier (Current) receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 57 | BP007 | 136 | MHHS-BR-LD-020.1 | DIP | PUB-009 | [CSSDeRegistration] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 58 | BP007 | 135 | MDS | DIP | PUB-009 | [CSSDeRegistration] | MDS | MDS receives PUB-009. | MDS receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 59 | BP007 | 131 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [CSSDeRegistration] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| De-appoint Current Metering Service | 60 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [MSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 61 | BP007 | 145 |  | DIP | PUB-037 | [MSDeApp] | SMSC, SUPC, LDSO & EES | DIP sends PUB-037 De-Appoints Current Metering Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS) to Metering Service (Current), Supplier(Outgoing), LDSO & EES |  | N
|  | 62 | BP007 | 150 | MHHS-BR-MS-040 | DIP | PUB-037 | [MSDeApp] | SMSC | Metering Service (Current) receives PUB-037 confirming MS De-appointment | Metering Service (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 63 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [MSDeApp] | SUPC | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Supplier (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 64 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 65 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| De-appoint Current Data Service | 66 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 67 | BP007 | 145 |  | DIP | PUB-037 | [DSDeApp] | SDSC, SUPC, LDSO, EES and MDS | DIP sends PUB-037 - De-Appoints Current Data Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS) to SDSC, SUPC, LDSO, EES and MDS |  | N
|  | 68 | BP007 | 140 | MHHS-BR-DS-104 MHHS-BR-DS-105 | DIP | PUB-037 | [DSDeApp] | SDSC | Smart Data Service (Outgoing) receives PUB-037 | Smart Data Services Outgoing receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 69 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier (Outgoing) receives PUB-037 | Supplier (Current) receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 70 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037. | LDSO receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 71 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037. | EES receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 72 | BP007 |  | DES138 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITFTS0855-Advanced
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | SITFTS-0855 TC02 |  |  |  | 0.3.7 |  | SITFTS-0855-Advanced | SITFTS-0855 - Advanced | Advanced Linked Export MPAN, same-day De-Link/Disconnection (as per DES138 data specification) where the Import MPAN has the same Supplier | Advanced Meter | Linked MPAN (Export) | Current Day
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0855-Advanced | Supplier Removal Request | 1 | BP007 | 10 | MHHS-BR-SU-051 | SUPC |  |  |  | Current Supplier Removal Request |  | N/A
| Meter Works Request | 2 | BP009 | 20 | MHHS-BR-SU-066 | SUPC | D0142/Agreed Method |  | AMSC | Existing Metering Service receives a Request to carry out meter works - (Turn off the AE Register) and De-Energise |  | Y
| Reading captured and Physical Works completed | 3 | BP009 | 35 | MHHS-BR-MS-054 MHHS-BR-MS-055 | AMSC |  |  |  | Capture Cumulative Meter Reading(s)/HH Downloads |  | N
|  | 4 | BP009 | 40 | MHHS-BR-MS-056 | AMSC |  |  |  | Physical Meter Works completes (Turn off the AE Register) |  | N/A
| Issue Cumulative Meter Read(s) Note - If Advanced Meter supports Cumulative Reads | 5 | BP009 | 60 | MHHS-BR-MS-061 | AMSC | IF-041 | [ReadingEnergisationChg] | DIP | AMSC sends IF-041 to the DIP. | http 201 response from DIP | N
|  | 6 | BP009 | 85 |  | DIP | PUB-041 | [ReadingEnergisationChg] | ADSC, LDSO, SUPC | DIP sends Cumulative Meter Read(s) via the PUB-041 to Data Service, LDSO and Supplier |  | N
|  | 7 | BP009 | 180 | MHHS-BR-DS-118 | DIP | PUB-041 | [ReadingEnergisationChg] | ADSC | ADSC receives PUB-041. | Advanced Data Service receives PUB-041 with Cumulative Meter Read(s) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP009 | 190 | MHHS-BR-LD-029 | DIP | PUB-041 | [ReadingEnergisationChg] | LDSO | LDSO receives PUB-041. | LDSO receives PUB-041 with Cumulative Meter Read(s) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 9 | BP009 | 220 | MHHS-BR-SU-072 | DIP | PUB-041 | [ReadingEnergisationChg] | SUPC | SUPC receives PUB-041. | Supplier (Current) receives PUB-041 with Cumulative Meter Read(s) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Issue Read(s) Note - D0010 if Advanced Meter does not support Cumulative Reads | 10 | BP009 | 80 | MHHS-BR-MS-062 | AMSC | D0010 | N/A | SUPC, LDSO, ADSC | Currently appointed meter service issues out D0010 to Supplier, LDSO and Data Service |  | N
|  | 11 | BP009 | 115 | MHHS-BR-SU-070 | AMSC | D0010 | N/A | SUPC | Supplier receives D0010 |  | Y
|  | 12 | BP009 | 120 | MHHS-BR-LD-027 | AMSC | D0010 | N/A | LDSO | LDSO receives D0010 |  | Y
|  | 13 | BP009 | 175 | MHHS-BR-DS-119 MHHS-BR-DS-120 | AMSC | D0010 | N/A | ADSC | Data Service receives D0010 |  | Y
|  | 14 | BP009 | 215 | MHHS-BR-SU-071 | SUPC |  |  |  | Supplier (Current) reconciles Metering / Reading Information | On receipt of all the metering updates and reading information Supplier can choose to reconcile these are aligned with the data flows received. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | N
| De-Energisation - Start | 15 | BP008 | 80 | MHHS-BR-MS-049 | AMSC | IF-007 | [EnergisationStatusChange] | DIP | As part of the meter remove process de-energisation starts at this point AMSC sends IF-007 to the DIP. | http 201 response from DIP | N
|  | 16 | BP008 | 90 |  | DIP | PUB-007 | [EnergisationStatusChange] | REGS | As part of the meter remove process energisation starts at this point DIP sends PUB-007 to the REGS. |  | N
|  | 17 | BP008 | 105 110 | MHHS-BR-RS-104 MHHS-BR-RS-105 | DIP | PUB-007 | [EnergisationStatusChange] | REGS | REGS receives PUB-007. | REGS receives PUB-007 with details of Energisation Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS Change of Energisation Status Notification | 18 | BP008 | 115 | MHHS-BR-RS-107 | REGS | IF-008 | [EnergisationStatusChange] | DIP | REGS sends IF-008 to the DIP | http 201 response from DIP | N
|  | 19 | BP008 | 125 135 |  | DIP | PUB-008 | [EnergisationStatusChange] | AMSC, SUPC, LDSO, ADSC, MDS and EES | DIP sends PUB-008 to AMSC, SUPC, LDSO, ADSC, MDS, and EES |  | N
|  | 20 | BP008 | 140 | MHHS-BR-MS-050 | DIP | PUB-008 | [EnergisationStatusChange] | AMSC | Metering Service (Currently Appointed) receives PUB-008 | Metering Service (Current) receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 21 | BP008 | 175 |  | DIP | PUB-008 | [EnergisationStatusChange] | SUPC | SUP (Current) receives PUB-008. | Supplier (Current) receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 22 | BP008 | 155 | MHHS-BR-DS-106 | DIP | PUB-008 | [EnergisationStatusChange] | ADSC | ADS (Current) receives PUB-008. | Data Service (Current) receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 23 | BP008 | 156 | MHHS-BR-EES-016.3 | DIP | PUB-008 | [EnergisationStatusChange] | EES | EES receives PUB-008. | EES receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 24 | BP008 | 160 | MDS | DIP | PUB-008 | [EnergisationStatusChange] | MDS | MDS receives PUB-008. | MDS receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 25 | BP008 | 165 | MHHS-BR-LD-024 | DIP | PUB-008 | [EnergisationStatusChange] | LDSO | LDSO receives PUB-008. | LDSO receives PUB-008 with details of Energisation Status Change acceptance and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Supplier issues De-Link request | 26 | BP010C | 860 | MHHS-BR-SU-094 | SUPC | IF-019 | [LinkedImportExportRemove] | DIP | Supplier identifies Export MPAN that needs to be De-Linked and issues the De-Link Request via the Manage Meterpoint Relationships and issues IF-019 to the DIP |  | N
|  | 27 | BP010C | 870 |  | DIP | PUB-019 | [LinkedImportExportRemove] | LDSO | DIP sends PUB-019 to LDSO
|  | 28 | BP010C | 880 890 | MHHS-BR-LD-043.1 MHHS-BR-LD-043.2 | DIP | PUB-019 | [LinkedImportExportRemove] | LDSO | LDSO receives the PUB-019 and performs validation checks before updating the Import/Export linkage | LDSO receives MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 29 | BP010C | 900 | MHHS-BR-LD-043.3 | LDSO | DB05 | N/A | REGS | LDSO issues DB05 (Accepted) to the Registration Service |  | N
|  | 30 | BP010C | 905 | MHHS-BR-RS-071.6 | REGS | DB05 | N/A | REGS | The Registration Service receives the DB05 (Accepted) | REGS receives DB05 (Accepted) and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 31 | BP010C | 905 | MHHS-BR-RS-071.8 | REGS | IF-020 | [LinkedImportExportRemove] and Response Code = "A" | DIP | The Registration Service issues the IF-020 Response to the DIP | http 201 response from DIP | N
|  | 32 | BP010C | 910 |  | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SUPC, ADSC, AMSC, LDSO, EES | DIP sends PUB-020 Response to the Supplier (Current), Supplier (Linked Import), Data Service (Current), Metering Service (Current), LDSO and EES |  | N
|  | 33 | BP010C | 950 | MHHS-BR-SU-096 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | SUPC | Supplier (Current) receives the PUB-020 Accepted De-Link Request Response | Supplier (Current) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 34 | BP010C | 930 | MHHS-BR-DS-130.5 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | ADSC | Data Service (Current) receives the PUB-020 Accepted De-Link Request Response | Data Service (Current) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 35 | BP010C | 920 | MHHS-BR-MS-066.5 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | AMSC | Metering Service (Current) receives the PUB-020 Accepted De-Link Request Response | Metering Service (Current) receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 36 | BP010C | 940 | MHHS-BR-LD-046 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | LDSO | LDSO receives the PUB-020 Accepted De-Link Request Response | LDSO receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 37 | BP010C | 931 | MHHS-BR-EES-016.3 | DIP | PUB-020 | [LinkedImportExportRemove] and Response Code = "A" | EES | EES receives the PUB-020 Accepted De-Link Request Response | EES receives accepted MPAN De-Link Request and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Request Disconnection | 38 | BP007 | 59 | MHHS-BR-SU-054 | SUPC | D0132 |  | LDSO | Current Supplier sends a D0132 Details of Disconnection of Supply to the LDSO to Request Disconnection |  | N
|  | 39 | BP007 | 60 | MHHS-BR-LD-016 MHHS-BR-LD-017 | SUPC | D0132 |  | LDSO | LDSO receives the D0132 and accepts the request | LDSO receives D0132 with Details of Disconnection of Supply and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| LDSO Disconnects Meter Point | 40 | BP007 | 65 | MHHS-BR-LD-016 MHHS-BR-LD-017 MHHS-BR-LD-018 | LDSO | Internal DB03 |  | REGS | LDSO disconnects Meter Point and sends an Internal DB03 to the Registration Service |  | N
|  | 41 | BP007 | 70 | MHHS-BR-RS-097 | LDSO | Internal DB03 |  | REGS | REGS receives the Internal DB03 | REGS receives Internal DB03 and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out LDSO Disconnection Notifications | 42 | BP007 | 70 | MHHS-BR-RS-098 | REGS | IF-009 | [MPANDisconnection] | DIP | REGS sends IF-009 to the DIP to confirm the Meter Point has been disconnected | http 201 response from DIP | N
|  | 43 | BP007 | 85 |  | DIP | PUB-009 | [MPANDisconnection] | SUPC, LDSO, EES | DIP sends PUB-009 to SUP (Current), LDSO and EES to confirm the Meter Point has been disconnected |  | N
|  | 44 | BP007 | 95 | MHHS-BR-SU-056 MHHS-BR-SU-057 | DIP | PUB-009 | [MPANDisconnection] | SUPC | SUP (Current) receives PUB-009. | Supplier (Current) receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 45 | BP007 | 86 | MHHS-BR-LD-020 | DIP | PUB-009 | [MPANDisconnection] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 46 | BP007 | 87 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [MPANDisconnection] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the Meter Point Disconnection and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out EES MPAN Status Change Update | 47 | BP007 | 70 | MHHS-BR-RS-099 | REGS | IF-050 | [MPStatusChange] | DIP | REGS sends IF-050 to the DIP to confirm the MPAN status change | http 201 response from DIP | N
|  | 48 | BP007 | 126 |  | DIP | PUB-050 | [MPStatusChange] | EES | DIP sends PUB-050 to EES to confirm the MPAN status change |  | N
|  | 49 | BP007 | 127 | MHHS-BR-EES-016.3 | DIP | PUB-050 | [MPStatusChange] | EES | EES receives PUB-050. | EES receives PUB-050 with details of the MPAN Status Change and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS MPAN Status Change Update | 50 | BP007 | 70 | MHHS-BR-RS-099 | REGS | CSS00700 | N/A | CSS | REGS sends CSS00700 to CSS |  | N
|  | 51 | BP007 | 115 | CSS | REGS | CSS00700 | N/A | CSS | CSS receives CSS00700 and Terminates RMP |  | Y
| Deactivation Formal Request | 52 | BP007 | 96 | MHHS-BR-SU-057 | SUPC | CSS01900 | N/A | CSS | SUP (Current) sends Registration Deactivation Request CSS01900 to CSS |  | N
|  | 53 | BP007 | 120 | CSS | SUPC | CSS01900 | N/A | CSS | CSS receives CSS01900 and performs Registration Deactivation |  | Y
| CSS Registration Deactivation | 54 | BP007 | 121 | CSS | CSS | CSS02860 | N/A | REGS | CSS performs Registration Deactivation and sends CSS02860 to REGS |  | N
|  | 55 | BP007 | 125 | MHHS-BR-RS-100 MHHS-BR-RS-101 | CSS | CSS02860 | N/A | REGS | REGS receives CSS02860 and updates Registration | REGS receives CSS02860 Registration Update and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS sends out CSS DeRegistration Notification | 56 | BP007 | 125 | MHHS-BR-RS-101 MHHS-BR-RS-102.1 | REGS | IF-009 | [CSSDeRegistration] | DIP | REGS sends IF-009 to the DIP to confirm the CSS De-Registration | http 201 response from DIP | N
|  | 57 | BP007 | 130 |  | DIP | PUB-009 | [CSSDeRegistration] | SUPC, LDSO, MDS and EES | DIP sends PUB-009 to SUPC, LDSO, MDS and EES to confirm the CSS De-Registration |  | N
|  | 58 | BP007 | 137 |  | DIP | PUB-009 | [CSSDeRegistration] | SUPC | SUPC receives PUB-009. | Supplier (Current) receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 59 | BP007 | 136 | MHHS-BR-LD-020.1 | DIP | PUB-009 | [CSSDeRegistration] | LDSO | LDSO receives PUB-009. | LDSO receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 60 | BP007 | 135 | MDS | DIP | PUB-009 | [CSSDeRegistration] | MDS | MDS receives PUB-009. | MDS receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 61 | BP007 | 131 | MHHS-BR-EES-016.3 | DIP | PUB-009 | [CSSDeRegistration] | EES | EES receives PUB-009. | EES receives PUB-009 with details of the CSS De-Registration and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| De-appoint Current Metering Service | 62 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [MSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 63 | BP007 | 145 |  | DIP | PUB-037 | [MSDeApp] | AMSC, SUPC, LDSO & EES | DIP sends PUB-037 De-Appoints Current Metering Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS) to Metering Service (Current), Supplier(Outgoing), LDSO & EES |  | N
|  | 64 | BP007 | 150 | MHHS-BR-MS-040 | DIP | PUB-037 | [MSDeApp] | AMSC | Metering Service (Current) receives PUB-037 confirming MS De-appointment | Metering Service (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 65 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [MSDeApp] | SUPC | Outgoing Supplier receives PUB-037 confirming MS De-appointment | Supplier (Current) receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 66 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 67 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| De-appoint Current Data Service | 68 | BP007 | 155 | MHHS-BR-RS-102 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 69 | BP007 | 145 |  | DIP | PUB-037 | [DSDeApp] | ADSC, SUPC, LDSO, EES and MDS | DIP sends PUB-037 - De-Appoints Current Data Service with a De-Appointment Reason Code = "DEREG" (RMP Terminated by CSS) to ADSC, SUPC, LDSO, EES and MDS |  | N
|  | 70 | BP007 | 140 | MHHS-BR-DS-104 MHHS-BR-DS-105 | DIP | PUB-037 | [DSDeApp] | ADSC | Smart Data Service (Outgoing) receives PUB-037 | Smart Data Services Outgoing receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 71 | BP007 | 157 | MHHS-BR-SU-059 | DIP | PUB-037 | [DSDeApp] | SUPC | Supplier (Outgoing) receives PUB-037 | Supplier (Current) receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 72 | BP007 | 156 | MHHS-BR-LD-021 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives PUB-037. | LDSO receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 73 | BP007 |  | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives PUB-037. | EES receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 74 | BP007 |  | DES138 | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y