## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Release | Defect ID | Reason for change
2023-11-09 | Shaun Magee |  |  | New draft
2023-11-15 | Shaun Magee | 5.2.1 |  | Release 5.2.1 for Publishing
2023-11-22 | Shaun Magee | 5.2.1 v0.1 |  | Replace embedded links with File Names
2023-11-30 | Shaun Magee | 5.2.1 v0.1 |  | Correct Smart Test Case Step 180 to clarify Data Service is the actor and that the data is expected to match with data from Supplier. Correct DIP Steps and remove Message Output and Message Output Event Code columns Remove commentary in Steps 10 and 15 concerning new MPANs where this is a COS. Advanced and Unmetered tests as well as other commentary steps referring to Initial Registration
2023-12-04 | Shaun Magee | 5.2.1 v0.1 |  | All CSS References with 4 digits corrected by adding leading 0. Columns Message Output and Message Output Event Code removed.
2023-12-05 | Dan Gee | 5.2.1 v0.1 |  | Added in PUB-001 for Linked Supplier
2023-12-05 | Shaun Magee | 5.2.1 v0.1 |  | IF-002 and IF-001 duplicated for secondary MPAN for Related Test Case (Trad COR)
2023-12-06 | Shaun Magee | 5.2.1 v0.1 |  | Advanced Test case amended following PP comments to remove the call to Transfer of Reads as Data Service is unchanged
2023-12-15 | Shaun Magee | 5.2.1 v0.2 |  | Advanced TC03 ID Correction
2023-12-19 | Shaun Magee | 5.2.1 v0.3 |  | Add new TC for Traditional Agreed Reads. Send multiple IF-001 and IF002 for Linked and Related Test cases and tidy up BRs Add EES Step 180 for all test cases
2024-01-09 | Dan Gee | 5.2.1 v0.3 |  | Added requirement MHHS-BR-DS-028.2 covering off agreed read process for opening/closing read
2024-01-15 | Dan Gee | 5.2.1 v0.3 |  | Added steps for incoming supplier agreeing read as part of disputed read process for requirement MHHS-BR-SU-161
2024-01-23 | Shaun Magee | 5.2.1 v0.3 |  | Added TC06 to handle Smart Agreed Reads covering BR MHHS-BR-DS-028.4
2024-02-05 | Shaun Magee | 5.2.1 v0.4 |  | Requirement GAPs:- MHHS-BR-DS-098.1 MHHS-BR-DS-098.2 MHHS-BR-SU-047.1 MHHS-BR-LD-009.1 Add Read Sharing Steps from BP005 previously in the Settlement Tests but now required to be in Consumption Tests. PP DCC 23/01 Ref: 10/27/30/36/38/40/43 Wording changed in Key Validation & Test Evidence as requested (MHHS-BR-SU-047.1 / MHHS-BR-LD-009.1]
2024-02-09 | Shaun Magee | 5.2.1 v0.4 |  | Add new TC07 to cover missing requirements:- MHHS-BR-DS-026.1 MHHS-BR-DS-026.2 MHHS-BR-DS-026.3 MHHS-BR-DS-026.7
2024-03-19 | Shaun Magee | 5.2.1 v0.5 |  | Merge shared steps
2024-05-14 | Izhan Ahsan | IR7 v0.6 |  | IF-37 steps have been adjusted above IF-36. Found an issue with Test step 60-65 where IF/PUB steps seems incorrect
2024-05-24 | Dan Gee | IR7 v0.6 |  | Updated IF-037/PUB-037 Recipiant as Supplier (Outgoing) due to IR7 updates on TC01 to TC07
2024-05-24 | Dan Gee | IR7 v0.6 |  | Added (If opted in) to IF-036/PUB-036 for LDSO based on IR7 updates DIN-743 on TC's 01 to 07
2024-05-24 | Dan Gee | IR7 v0.6 |  | Updated dip response message to http 201 response from DIP on all test cases
2024-05-24 | Dan Gee | IR7 v0.6 |  | Added REGS Sends end date for existing MDR appointment upon setting new MDR on TC01 based on IR7 updates
2024-05-24 | Dan Gee | IR7 v0.6 |  | Added Process update related to IF-015/IF-016 DIN-710 [ActivePower] as event code on TC07 with successful validation rule message - MSG0000 - Request Sucessful returned on IF-015
2024-06-14 | Bhavin Sikotra | IR7 v0.6.1 (Redlined) |  | Amended DCC MS appointment steps removing refrence to MDR and CSS07000 on TC01
2024-06-17 | Girish Ligde | IR7 v0.6.1 (Redlined) |  | Based on DCC MS appointment steps changed version of TC02
2024-06-18 | Dan Gee | IR7 v0.6.2 | 33404 | Updated test description to make clear that the MS and DS (TC01 & TC02) are to be de appointed and appointed to the same Data and Metering service organization and TC 03 to 05 it is the same org for meter service only for de- appointment appointment
2024-06-18 | Dan Gee | IR7 v0.6.2 |  | Removed TC02 & 03 after SRO review these tests are running through the CoS process with no transfer of read which is already covered by SITFTS-0020 TC03 and SITFTS-0010 TC04, Trad Agreed now becomes TC03 and Smart agreed becomes TC04

## SITFTS0012 Overview
Scenario ID | SITFTS-0012
Theme | Consumption
Scenario Title | Consumption on Change of Supplier, no change of MS
Description | Consumption processing with a change of Supplier (Metering Service remains the same organization in all test cases and Data Service in test cases 1 & 2) Tests 1-2 - Change of Supplier only Test 3-5 - Change of Supplier and DS
Functional Category | Consumption on Change of Supplier
Functional Area 1 | Change of Supplier
Functional Area 2 | Transfer of Reads
Creator | Shaun Magee
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP001, BP002, BP003, (+BP003A for Smart meters), BP003C, BP003D
Pre-Requisites
Boundaries | Processing ends once the exchange of reads has been completed between Suppliers and Data Service
Test Case Variables | (1) traditional, related MPANs, forward-dated with Customer Own Read (2) smart, single Daily Consents, forward-dated (3) traditional, single MPAN, forward-dated with Agreed Read (4) smart, single MPAN Daily Consents, forward-dated with Agreed Read (5) advanced Daily Consents, single, forward-dated
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0012 TC01 | SITFTS-0012 - Trad COR | SITFTS-0012 - Trad COR | 0.6.2 | Traditional Related MPANs, forward-dated Change of Supply with no change of Metering Service or Data Service (Metering & data Service remains the same organization to be appointed by new supplier) (as per DES138 data specification) | Traditional Meter | Related | forward-dated
2 | SITFTS-0012 TC02 | SITFTS-0012 - Smart | SITFTS-0012 - Smart | 0.6.3 | Smart Single MPAN Daily Consents, forward-dated Change of Supply with no change of Metering Service Metering & data Service remains the same organization to be appointed by new supplier) (as per DES138 data specification) | Smart Meter | Single | forward-dated
3 | SITFTS-0012 TC03 | SITFTS-0012 - Trad Agreed | SITFTS-0012 - Trad Agreed | 0.6.2 | Traditional Single MPAN, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the Agreed Reads process is triggered | Traditional Meter | Single | forward-dated
4 | SITFTS-0012 TC04 | SITFTS-0012 - Smart Agreed | SITFTS-0012 - Smart Agreed | 0.6.2 | Smart Single MPAN Daily Consents, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the Agreed Reads process is triggered | Smart Meter | Single | forward-dated
5 | SITFTS-0012 TC05 | SITFTS-0012 -Advanced | SITFTS-0012 - Advanced Single | 0.6.2 | Advanced Linked MPANs Daily Consents, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the old DS is unable to contact the meter. Last 3 months IF-021 data available for IF-015 validation | Advanced Meter | Single | forward-dated
Back to List of
Test Scenarios

## SITFTS0012 Overview-ADO
Scenario ID | SITFTS-0012
Theme | Consumption
Scenario Title | Consumption on Change of Supplier, no change of MS
Description | Consumption processing with a change of Supplier (Metering Service remains the same organization in all test cases and Data Service in test cases 1 & 2) Tests 1-2 - Change of Supplier only Test 3-5 - Change of Supplier and DS
Functional Category | Consumption on Change of Supplier
Functional Area 1 | Change of Supplier
Functional Area 2 | Transfer of Reads
Creator | Shaun Magee
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP001, BP002, BP003, (+BP003A for Smart meters), BP003C, BP003D
Pre-Requisites
Boundaries | Processing ends once the exchange of reads has been completed between Suppliers and Data Service
Test Case Variables | (1) traditional, related MPANs, forward-dated with Customer Own Read (2) smart, single Daily Consents, forward-dated (3) traditional, single MPAN, forward-dated with Agreed Read (4) smart, single MPAN Daily Consents, forward-dated with Agreed Read (5) advanced Daily Consents, single, forward-dated
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | ADO Truncated Test Case Title | ADO Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0012 TC01 | SITFTS-0012 - Trad COR | - Trad COR | SITFTS-0012 TC01 - Trad COR | SITFTS-0012 - Trad COR | 0.6.3 | Traditional Related MPANs, forward-dated Change of Supply with no change of Metering Service or Data Service (Metering & data Service remains the same organization to be appointed by new supplier) (as per DES138 data specification) | Traditional Meter | Related | forward-dated
2 | SITFTS-0012 TC02 | SITFTS-0012 - Smart |  |  | SITFTS-0012 - Smart | 0.6.3 | Smart Single MPAN Daily Consents, forward-dated Change of Supply with no change of Metering Service Metering & data Service remains the same organization to be appointed by new supplier) (as per DES138 data specification) | Smart Meter | Single | forward-dated
3 | SITFTS-0012 TC03 | SITFTS-0012 - Trad Agreed |  |  | SITFTS-0012 - Trad Agreed | 0.6.2 | Traditional Single MPAN, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the Agreed Reads process is triggered | Traditional Meter | Single | forward-dated
4 | SITFTS-0012 TC04 | SITFTS-0012 - Smart Agreed |  |  | SITFTS-0012 - Smart Agreed | 0.6.2 | Smart Single MPAN Daily Consents, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the Agreed Reads process is triggered | Smart Meter | Single | forward-dated
5 | SITFTS-0012 TC05 | SITFTS-0012 -Advanced |  |  | SITFTS-0012 - Advanced Single | 0.6.2 | Advanced Linked MPANs Daily Consents, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the old DS is unable to contact the meter. Last 3 months IF-021 data available for IF-015 validation | Advanced Meter | Single | forward-dated
Back to List of
Test Scenarios

## ADO Scneario Sheet
Scenario ID | Theme | ADO Title | Scenario Title | Description | Functional Category | Functional Area 1 | Functional Area 2 | Creator | Priority | Scenario size | Design Document Ref | Business Process | Pre-Requisites | Boundaries | Test Case Variables
SITFTS-0012 | Consumption | SITFTS-0012 Consumption on Change of Supplier, no change of MS | Consumption on Change of Supplier, no change of MS | Consumption processing with a change of Supplier (Metering Service remains the same organization in all test cases and Data Service in test cases 1 & 2) Tests 1-2 - Change of Supplier only Test 3-5 - Change of Supplier and DS | Consumption on Change of Supplier | Change of Supplier | Transfer of Reads | Shaun Magee | High | Large |  | BP001, BP002, BP003, (+BP003A for Smart meters), BP003C, BP003D |  | Processing ends once the exchange of reads has been completed between Suppliers and Data Service | (1) traditional, related MPANs, forward-dated with Customer Own Read (2) smart, single Daily Consents, forward-dated (3) traditional, single MPAN, forward-dated with Agreed Read (4) smart, single MPAN Daily Consents, forward-dated with Agreed Read (5) advanced Daily Consents, single, forward-dated

## SITFTS0012- Trad COR
No. | Test Case Id | [5 empty] | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type |  | MPAN Type | Effective time
1 | SITFTS-0012 TC01 | [5 empty] | 0.6.2 | SITFTS-0012 - Trad COR | SITFTS-0012 - Trad COR | Traditional Related MPANs, forward-dated Change of Supply with no change of Metering Service or Data Service (Metering & data Service remains the same organization to be appointed by new supplier) (as per DES138 data specification) | Traditional Meter |  | Related | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | ADO BP Step Single line | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | ADO Steps Field ( Combined BP, BP Step, Service Producing Trigger, Service Recipient, Envidence, Test step) | Key Validation & Test Evidence | Evidence Required
SITFTS-0012 - Trad COR | Pre Req | Pre Req | [8 empty] | Change of supply to be created as part of testing pre req. Services to be appointed where the same org meter service & data service is de-appointed and appointed Please refer to SITFTS-0020 Worksheet SITFTS0020- Traditional steps to support the change of supplier process if required. All steps are to be executed before consumption processing can commence. The consumption processing in this script is expected to commence on the day after the CoS has been completed. | - Sender - Receiver - Evidence - Change of supply to be created as part of testing pre req. Services to be appointed where the same org meter service & data service is de-appointed and appointed Please refer to SITFTS-0020 Worksheet SITFTS0020- Traditional steps to support the change of supplier process if required. All steps are to be executed before consumption processing can commence. The consumption processing in this script is expected to commence on the day after the CoS has been completed.
| Transfer of Reads triggered | 1 | BP001 | 105 | 105 | N/A | SUPI |  |  |  | Incoming Supplier triggers Transfer of Reads following Change of Suppler based on a Change of Supply (COS) Customer Own Read (COR) | BP001 - 105 Sender - SUPI Receiver - Evidence - N Incoming Supplier triggers Transfer of Reads following Change of Suppler based on a Change of Supply (COS) Customer Own Read (COR) |  | N
| Incoming Supplier issues COR to Outgoing Supplier | 2 | BP003C | 180 190 | 180,190 | MHHS-BR-SU-151 MHHS-BR-SU-152.1 MHHS-BR-SU-152 | Customer | D0010 |  | SUPI | Incoming Supplier receives the Customer Own Read (D0010) and issues the read to the Outgoing Supplier | BP003C - 180,190 Sender - Customer Receiver - SUPI Evidence - Y Incoming Supplier receives the Customer Own Read (D0010) and issues the read to the Outgoing Supplier | Incoming Supplier receives Customer Own Read via the D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 3 | BP003C | 220 | 220 | MHHS-BR-SU-153 | SUPI | D0010 |  | SUPO | Outgoing Supplier receives the Customer Own Read (D0010) from Incoming Supplier | BP003C - 220 Sender - SUPI Receiver - SUPO Evidence - Y Outgoing Supplier receives the Customer Own Read (D0010) from Incoming Supplier | Outgoing Supplier receives Customer Own Read via the D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Outgoing Supplier accepts COR and issues it to the Data Service | 4 | BP003C | 230 | 230 | MHHS-BR-SU-154 | SUPO | D0010 |  | SDSC | Outgoing Supplier accepts the Customer Own Read (D0010) and issues the read to the Unchanged Data Service | BP003C - 230 Sender - SUPO Receiver - SDSC Evidence - Y Outgoing Supplier accepts the Customer Own Read (D0010) and issues the read to the Unchanged Data Service |  | Y
| Data Service receives COR | 5 | BP003C | 260 270 | 260,270 | MHHS-BR-DS-024.0 | SUPO | D0010 | Read-Flag = T | SDSC | Data Service receives the Customer Own Read (D0010) and manages the read | BP003C - 260,270 Sender - SUPO Receiver - SDSC Evidence - Y Data Service receives the Customer Own Read (D0010) and manages the read | Data Service receives Customer Own Read via the D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 6 | BP003C | 190 | 190 | MHHS-BR-SU-152.1 MHHS-BR-SU-152 | SUPO | D0010 | Read-Flag = T | SUPI | Incoming Supplier receives accepted Customer Own Read (D0010) from Outgoing Supplier | BP003C - 190 Sender - SUPO Receiver - SUPI Evidence - Y Incoming Supplier receives accepted Customer Own Read (D0010) from Outgoing Supplier | Incoming Supplier receives accepted Customer Own Read via the D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 7 | BP003C |  |  | DTN | SUPO | D0010 | Read-Flag = T | LDSO | LDSO receives accepted Customer Own Read (D0010) from Outgoing Supplier | BP003C - Sender - SUPO Receiver - LDSO Evidence - Y LDSO receives accepted Customer Own Read (D0010) from Outgoing Supplier | LDSO receives accepted Customer Own Read via the D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Incoming Supplier receives accepted COR and issues it to the Data Service | 8 | BP003C | 195 | 195 | MHHS-BR-SU-152.2 | SUPI | D0010 | Read-Flag = T | SDSC | Incoming Supplier issues the accepted Customer Own Read (D0010) to the Unchanged Data Service | BP003C - 195 Sender - SUPI Receiver - SDSC Evidence - Y Incoming Supplier issues the accepted Customer Own Read (D0010) to the Unchanged Data Service |  | Y
|  | 9 | BP003C | 250 | 250 | MHHS-BR-DS-024.0 | SUPI | D0010 | Read-Flag = T | SDSC | Data Service receives the accepted Customer Own Read (D0010) from the Incoming Supplier and manages the read | BP003C - 250 Sender - SUPI Receiver - SDSC Evidence - Y Data Service receives the accepted Customer Own Read (D0010) from the Incoming Supplier and manages the read | Data Service receives accepted Customer Own Read via the D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Data Service handles Settlement for Adjustment to Historic Estimations based on COR | 10 | BP005 | 60 | 60 | N/A | SDSC | D0010 |  | Settlement | Unchanged Data Service - Settlement Historic Adjustment invoked following receipt of the Customer Own Read (D0010) . Adjustments to previously estimated UTC Settlement Period Consumption Data [where the calendar is not locked (RF Completed)] are processed. Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” | BP005 - 60 Sender - SDSC Receiver - Settlement Evidence - N Unchanged Data Service - Settlement Historic Adjustment invoked following receipt of the Customer Own Read (D0010) . Adjustments to previously estimated UTC Settlement Period Consumption Data [where the calendar is not locked (RF Completed)] are processed. Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N
| Data Service handles Settlement for use in future estimations | 11 | BP005 | 60 | 60 | N/A | SDSC | D0010 |  | Settlement | Unchanged Data Service - Settlement Future Estimations available following receipt of the Customer Own Read (D0010) . Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” | BP005 - 60 Sender - SDSC Receiver - Settlement Evidence - N Unchanged Data Service - Settlement Future Estimations available following receipt of the Customer Own Read (D0010) . Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N

## SITFTS0012- Smart
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | SITFTS-0012 TC02 | [5 empty] | SITFTS-0012 - Smart | SITFTS-0012 - Smart | Smart Single MPAN Daily Consents, forward-dated Change of Supply with no change of Metering Service Metering & data Service remains the same organization to be appointed by new supplier) (as per DES138 data specification) | Smart Meter | Single | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0012 - Smart | Pre Req | Pre Req | [7 empty] | Change of supply to be created as part of testing pre req. Services to be appointed where the same org meter service is de-appointed and appointed Please refer to SITFTS-0020 Worksheet SITFTS0020- Smart steps to support the change of supplier process if required. All steps are to be executed before consumption processing can commence. The consumption processing in this script is expected to commence on the day after the CoS has been completed.
| Transfer of Reads | 1 | BP001 | 105 | N/A | SUPI |  |  |  | Incoming Supplier triggers Transfer of Reads following Change of Suppler | This step is reflect that read/history transfer and any calculations for readings have been performed within BP003C. These are transferred to Suppliers. | N
| Incoming Supplier Recovers Actual Smart Data Opening Position | 2 | BP003C | 35 | MHHS-BR-SU-141 | SUPI |  |  |  | New Supplier Recovers opening position Smart Actual Data and awaits Register Level Readings from Old Supplier |  | Y
| Data Service on De-Appointment/Re-Appointment recovers Actual Smart Data Opening Position | 3 | BP003C | 55 45 | MHHS-BR-DS-023.1 | SDSC |  |  |  | Data Service recovers smart reads for the opening/closing position As Data Service unchanged this needs to be actioned only once. |  | Y
|  | 4 | BP003C | 100 | MHHS-BR-DS-024.2 MHHS-BR-DS-028.2 | SDSC | IF-041 | [ReadingCOS] | DIP | SDSC issues Cumulative and Register Reads Handshake to DIP Where Data services have obtained actual smart data they will issue these via IF-041 and proceed to BP05 | http 201 response from DIP | Y
|  | 5 | BP003C | 120 |  | DIP | PUB-041 | [ReadingCOS] | SUPI, SUPO, LDSO | DIP issues Cumulative and Register Reads Handshake to Old Supplier, Incoming Supplier and LDSO |  | N
|  | 6 | BP003C | 70 | MHHS-BR-SU-142 | DIP | PUB-041 | [ReadingCOS] | SUPO | Old Supplier receives PUB-041 | Old Supplier receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 7 | BP003C | 140 | MHHS-BR-SU-146 | DIP | PUB-041 | [ReadingCOS] | SUPI | Incoming Supplier receives PUB-041 | Incoming Supplier receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP003C |  | DES138-Interface Catalogue | DIP | PUB-041 | [ReadingCOS] | LDSO | LDSO receives PUB-041 | LDSO receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Old Supplier Recovers Actual Smart Data Closing Position | 9 | BP003C | 60 | MHHS-BR-SU-141 | SUPO |  |  |  | Old Supplier can recover Closing Position Smart Actual Data |  | Y
| Old Supplier validates and runs Final Billing | 10 | BP003C | 65 | MHHS-BR-SU-142 | SUPO |  |  |  | Old Supplier compares & validates Actuals and runs Final Billing | Where the Supplier has been able to obtain smart reads they can compare and validate these against previously obtained data. They can also compare the cumulative reading received. Where a supplier is satisfied with Readings they can progress to final bill. | Y
| Old Supplier issues Register Level Reading(s) to Incoming Supplier | 11 | BP003C | 80 | MHHS-BR-SU-145 | SUPO | D0010 | D0010 | SUPI | Old supplier issues Register Level Consumption (Act) to Incoming Supplier | Suppliers will issue the register level consumption either estimated or actual to the Incoming Supplier | Y
|  | 12 | BP003C | 150 | MHHS-BR-SU-148 | SUPO | D0010 | D0010 | SUPI | Incoming Supplier receives Register Level Readings from Old Supplier | Incoming Supplier receives D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| New Supplier evaluates and runs Final Billing | 13 | BP003C | 160 | MHHS-BR-SU-149 | SUPI |  |  |  | Incoming Supplier Evaluates Reading Data & Types Available and finds no Data Issue | The Incoming Supplier will use all of the data received form the meter, old DS, New DS and the Incoming Supplier and assess whether there are any data issues. | Y
|  | 14 | BP003C | 170 | MHHS-BR-SU-150 | SUPI |  |  |  | Incoming Supplier reconfigures Meter (if required) and starts the Billing Process. | Where supply are satisfied and have chosen which data to use they may at this point decide to reconfigure the Smart meter. | Y
| Data Service assesses all readings and starts the Settlement process | 15 | BP003C | 130 | MHHS-BR-DS-025.1 | SDSC |  |  |  | Compare & Validate where the Data Service has received actual data which matches they obtained | Where the Data Service was able to obtain actual data they can use the data received in PUB-041 to compare and validate against the data they obtained. If no actual was obtained the Data Service will use the data received in PUB-041 as a starting point. | Y
| Data Service handles Settlement for Adjustment to Historic Estimations based on Closing Position | 16 | BP005 | 60 | N/A | SDSC | PUB-041 | [ReadingCOS] | Settlement | Unchanged Data Service - Settlement Historic Adjustment invoked following receipt of the closing PUB-041 Adjustments to previously estimated UTC Settlement Period Consumption Data [where the calendar is not locked (RF Completed)] are processed. Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N
| Data Service handles Settlement for use in future settlement runs | 17 | BP005 | 60 | N/A | SDSC | PUB-041 | [ReadingCOS] | Settlement | Unchanged Data Service - Settlement Future Estimations available following receipt of the closing PUB-041. Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N

## SITFTS0012- Trad Agreed
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 | SITFTS-0012 TC03 |  |  |  |  | 0.6.2 | SITFTS-0012 - Trad Agreed | SITFTS-0012 - Trad Agreed | Traditional Single MPAN, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the Agreed Reads process is triggered | Traditional Meter | Single | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0012 - Trad COR | Pre Req | Pre Req | [7 empty] | Change of supply to be created as part of testing pre req. Services to be appointed where the same org meter service is de-appointed and appointed and different org data service is appointed Please refer to SITFTS-0020 Worksheet SITFTS0020- Traditional steps to support the change of supplier process if required. All steps are to be executed before consumption processing can commence. The consumption processing in this script is expected to commence on the day after the CoS has been completed. |  | N
| Transfer of Reads triggered | 1 | BP001 | 105 | N/A | SUPI |  |  |  | Incoming Supplier and Outgoing Supplier trigger Transfer of Reads following Change of Suppler based on Estimated Reading(s) |  | N
| Outgoing DS generate Estimates (D0010) | 2 | BP003C | 270 | MHHS-BR-DS-024 MHHS-BR-DS-024.0 | SDSO | D0010 |  | SUPC, SDSI | Outgoing Data Service generates Estimates for Traditional Meter and issues the estimates to Old Supplier, Incoming Data Service and New Supplier | Outgoing SDS must, on de-appointment, in the absence of an actual valid read for a Traditional meter, send an estimated read for midnight on the day following the de-appointment ( i.e. if effective de-appointment is 23:59:59 on 1st Jan then read point should be 00:00:00 on 2nd Jan) to the new SDS, LDSO and old Supplier via the appropriate interface. Estimates will be required for each settlement register and should be determined using the Smart Validation & Estimation Method statement. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 3 | BP003C | 280 | MHHS-BR-SU-155 | SDSO | D0010 |  | SUPO | Outgoing Supplier receives the Estimate(s) (D0010) from the Outgoing Data Service. This estimate causes an issue with the consumption/read history as it is over the agreed threshold and within RF. | The old Supplier will receive a D0010 from the old Data service with an estimated read for the COS date. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 4 | BP003C | 290 | MHHS-BR-DS-025 | SDSI | D0010 |  | SUPO | Incoming Data Service receives the Estimate(s) (D0010) from the Outgoing Data Service. | The Incoming Data Service r will receive a D0010 from the old Data service with an estimated read for the COS date. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 5 | BP003C | 290 | MHHS-BR-DS-025 | SDSO | D0010 |  | SDSI | Incoming Data Service receives the Estimate(s) (D0010) from the Outgoing Data Service. | The Incoming Data Service will receive a D0010 from the old Data service with an estimated read for the COS date. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 6 | BP003C | 300 | MHHS-BR-SU-155 | SDSO | D0010 |  | SUPI | Incoming Supplier receives the Estimate(s) (D0010) from the Outgoing Data Service. This estimate causes an issue with consumption/read history the old supplier can raise a D0300 if it is over the agreed threshold and within RF | The Incoming Supplier will receive a D0010 from the old Data service with an estimated read for the COS date. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Outgoing Supplier issues suggested reads (D0300) | 7 | BP003D | 50 | MHHS-BR-SU-158 | SUPC | D0300 |  | SUPI | Outgoing Supplier issues the D0300 Flow to the Incoming Supplier containing new suggested Reading(s) | Where the Old Supplier has identified the COS reads received are inconsistent or missing they will need suggest a new reading in the D0300 and issue this to the New supplier. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP003D | 60 | MHHS-BR-SU-159 | SUPC | D0300 |  | SUPI | Incoming Supplier receives and manages the D0300 Flow which is accepted | The new supplier will also need to manage a D0300 request from the old supplier. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Incoming Supplier issues suggested reads (D0300) | 9 | BP003D | 10 | MHHS-BR-SU-158 MHHS-BR-SU-160 | SUPC | D0300 |  | SUPI | Incoming Supplier issues the D0300 Flow to the Outgoing Supplier containing new suggested Reading(s) | Where the Incoming Supplier has identified the COS reads received are inconsistent or missing they will need suggest a new reading in the D0300 and issue this to the Outgoing Supplier. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 10 | BP003D | 15 | MHHS-BR-SU-158 MHHS-BR-SU-160 | SUPI | D0300 |  | SUPC | Outgoing Supplier receives the D0300 Flow and finds the proposed reads acceptable | When the old Supplier receives the D0300 they will need to assess if the new read provided is acceptable based on their own historic data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Incoming Supplier issues Agreed reads (D0010) | 11 | BP003D | 65 70 | MHHS-BR-SU-161 | SUPC | D0010 |  | SDSI | Incoming Supplier accepts the D0300 and sends Agreed Reading(s) via the D0010 Flow to the Incoming Data Service | Where it is the register read that has been agreed, Supply will issue a D0010 to their Data Service. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 12 | BP003D | 75 | MHHS-BR-DS-028.1 | SUPC | D0010 |  | SDSI | Incoming Data Service receives Agreed Reading(s) | Data Services will receive a re-agreed read via a D0010 and proceed to Settlement Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 13 | BP003D | 60 | MHHS-BR-SU-159 | SUPC | D0300 |  | SUPI | Incoming Supplier receives the D0300 Flow and finds the proposed reads acceptable | When the new Supplier receives the D0300 they will need to assess if the new read provided is acceptable based on their own historic data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Read Sharing - Incoming Data Service | 14 | BP005 | 175 | MHHS-BR-DS-098.1 | SDSI | Data Collection |  |  | Reading Validation | Incoming Data Service will need to follow Validation and Estimation Method Statements | Y
|  | 15 | BP005 | 190 | MHHS-BR-DS-098 | SDSI | D0010 | N/A | SUPC, LDSO | Issue validated Reading Data to Supplier and LDSO |  | Y
|  | 16 | BP005 | 310 | MHHS-BR-SU-047 | SDSI | D0010 | N/A | SUPC | Supplier receives D0010 | Supplier receives D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 17 | BP005 | 300 | MHHS-BR-LD-009 | SDSI | D0010 | N/A | LDSO | LDSO receives D0010 | LDSO receives D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Outgoing Supplier issues Agreed reads (D0010) | 18 | BP003D | 20 25 | MHHS-BR-SU-162 | SUPC | D0010 |  | SDSO | Outgoing Supplier accepts the D0300 and sends agreed reading(s) to the outgoing data Service via the D0010 Flow | Where it is the register read that has been agreed, Supply will issue a D0010 to their Data Service Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 19 | BP003D | 30 | MHHS-BR-DS-028.3 | SUPC | D0010 |  | SDSO | Outgoing Data Service receives Agreed Reading(s) | Data Services will receive a re-agreed read via a D0010 and proceed to Settlement Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Read Sharing - Outgoing Data Service | 20 | BP005 | 175 | MHHS-BR-DS-098.1 | SUPC | Data Collection |  | SDSO | Reading Validation | Outgoing Data Service will need to follow Validation and Estimation Method Statements | Y
|  | 21 | BP005 | 190 | MHHS-BR-DS-098 | SDSO | D0010 | N/A | SUPC, LDSO | Issue validated Reading Data to Supplier and LDSO |  | Y
|  | 22 | BP005 | 310 | MHHS-BR-SU-047 | SDSO | D0010 | N/A | SUPC | Supplier receives D0010 | Supplier receives D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 23 | BP005 | 300 | MHHS-BR-LD-009 | SDSO | D0010 | N/A | LDSO | LDSO receives D0010 | LDSO receives D0010. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Old Data Service handles Historic Settlement for based on the Agreed Read | 24 | BP005 | 60 | N/A | SDSO | D0010 |  | Settlement | Outgoing Data Service - Settlement Historic Adjustment invoked following receipt of the Agreed Read (IF-010) . Adjustments to previously estimated UTC Settlement Period Consumption Data [where the calendar is not locked (RF Completed)] are processed. Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N
| Incoming Data Service handles Settlement for use in future estimations | 25 | BP005 | 60 | N/A | SDSI | D0010 |  | Settlement | Incoming Data Service - Settlement Future Estimations available following receipt of the Customer Own Read (D0010) . Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N

## SITFTS0012- Smart Agreed
No. | Test Case Id |  |  |  |  | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 | SITFTS-0012 TC04 |  |  |  |  | 0.6.2 | SITFTS-0012 - Smart Agreed | SITFTS-0012 - Smart Agreed | Smart Single MPAN Daily Consents, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the Agreed Reads process is triggered | Smart Meter | Single | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0012 - Smart Agreed | Pre Req | Pre Req | [7 empty] | Change of supply to be created as part of testing pre req. Services to be appointed where the same org meter service is de-appointed and appointed and different org data service is appointed Please refer to SITFTS-0020 Worksheet SITFTS0020- Smart steps to support the change of supplier process if required. All steps are to be executed before consumption processing can commence. The consumption processing in this script is expected to commence on the day after the CoS has been completed. |  | N
| Transfer of Reads | 1 | BP001 | 105 | N/A | SUPI |  |  |  | Incoming Supplier triggers Transfer of Reads following Change of Suppler | This step is reflect that read/history transfer and any calculations for readings have been performed within BP003C. These are transferred to Suppliers. | N
| Incoming Supplier fails to recovers Actual Smart Data Opening Position | 2 | BP003C | 35 | MHHS-BR-SU-141 | SUPI |  |  |  | New Supplier attempts to recovers opening position Smart Actual Data and awaits Register Level Readings from Old Supplier No Data Recovered |  | Y
| Outgoing Data Service on De-Appointment fails to recovers Actual Smart Data Closing Position | 3 | BP003C | 55 | MHHS-BR-DS-023.1 | SDSO |  |  |  | Data Service attempts to recovers smart reads for the closing position No Data Recovered. |  | Y
|  | 4 | BP003C | 105 | MHHS-BR-DS-024.1 | SDSO |  |  |  | Where outgoing Data Service unable to obtain actual smart data within 5 Working days they will generate an estimated cumulative read. |  | Y
|  | 5 | BP003C | 110 | MHHS-BR-DS-024.1 | SDSO | IF-041 | [ReadingCOS] | DIP | Issue Estimated Cumulative Read for Handshake | http 201 response from DIP | Y
|  | 6 | BP003C | 120 |  | DIP | PUB-041 | [ReadingCOS] | SUPI, SUPO, SDSI, LDSO | DIP issues Cumulative and Register Reads Handshake to Old Supplier, Incoming Supplier, Incoming Data Service and LDSO |  | N
|  | 7 | BP003C | 70 | MHHS-BR-SU-142 | DIP | PUB-041 | [ReadingCOS] | SUPO | Old Supplier receives PUB-041 | Old Supplier receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 8 | BP003C | 140 | MHHS-BR-SU-146 | DIP | PUB-041 | [ReadingCOS] | SUPI | Incoming Supplier receives PUB-041 | Incoming Supplier receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 9 | BP003C | 125 | MHHS-BR-DS-025.1 | DIP | PUB-041 | [ReadingCOS] | SDSI | Incoming Data Service receives PUB-041 | Incoming Data Service receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 10 | BP003C |  | DES138-Interface Catalogue | DIP | PUB-041 | [ReadingCOS] | LDSO | LDSO receives PUB-041 | LDSO receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Incoming Data Service on Appointment fails to recovers Actual Smart Data Opening Position | 11 | BP003C | 45 | MHHS-BR-DS-023.1 | SDSI |  |  |  | Incoming Data Service attempts to recover smart reads for the opening position No Data Recovered. |  | Y
|  | 12 | BP003C | 130 | MHHS-BR-DS-025.1 | SDSI |  |  |  | Compare & Validate |  | Y
|  | 13 | BP003C | 131 | MHHS-BR-DS-025.2 | SDSI | IF-041 | [ReadingCOS] | DIP | Publish Available Reading(s) / consumption Log | http 201 response from DIP | Y
|  | 14 | BP003C | 135 |  | DIP | PUB-041 | [ReadingCOS] | SUPI | DIP issues Cumulative and Register Reads Handshake to New Supplier |  | N
|  | 15 | BP003C | 145 | MHHS-BR-SU-147 | DIP | PUB-041 | [ReadingCOS] | SUPI | New Supplier receives PUB-041 | New Supplier receives PUB-041 ReadingCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Old Supplier fails to recovers Actual Smart Data Closing Position | 16 | BP003C | 60 | MHHS-BR-SU-141 | SUPO |  |  |  | Old Supplier attempts to recover Closing Position Smart Actual Data No Data Recovered. |  | Y
|  | 17 | BP003C | 75 | MHHS-BR-SU-143 | SUPO |  |  |  | Old Supplier generates Supplier Estimate (BAU Mechanism) |  | Y
|  | 18 | BP003C | 76 | MHHS-BR-SU-144 | SUPO |  |  |  | Old Supplier compares & Validates Estimates and runs Final Billing |  | Y
| New Supplier evaluates and runs Final Billing | 19 | BP003C | 160 | MHHS-BR-SU-149 | SUPI |  |  |  | Incoming Supplier Evaluates Reading Data & Types Available and finds there is a Data Issue | The Incoming Supplier will use all of the data received form the meter, old DS, New DS and the Incoming Supplier and assess whether there are any data issues. | Y
| Outgoing Supplier issues suggested reads (D0300) | 20 | BP003D | 50 | MHHS-BR-SU-158 | SUPO | D0300 |  | SUPI | Outgoing Supplier issues the D0300 Flow to the Incoming Supplier containing new suggested Reading(s) | Where the Incoming Supplier has identified the COS reads received are inconsistent or missing they will need suggest a new reading in the D0300 and issue this to the Outgoing Supplier. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 21 | BP003D | 60 | MHHS-BR-SU-159 | SUPO | D0300 |  | SUPI | Incoming Supplier receives the D0300 Flow and manages the D0300 Flow | When the new Supplier receives the D0300 they will need to assess if the new read provided is acceptable based on their own historic data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Incoming Supplier issues suggested reads (D0300) | 22 | BP003D | 10 | MHHS-BR-SU-158 MHHS-BR-SU-160 | SUPI | D0300 |  | SUPO | Incoming Supplier issues the D0300 Flow to the Outgoing Supplier containing new suggested Reading(s) | Where the Incoming Supplier has identified the COS reads received are inconsistent or missing they will need suggest a new reading in the D0300 and issue this to the Outgoing Supplier. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 23 | BP003D | 15 | MHHS-BR-SU-158 MHHS-BR-SU-160 | SUPO | D0300 |  | SUPI | Outgoing Supplier receives the D0300 Flow and finds the proposed reads acceptable | When the old Supplier receives the D0300 they will need to assess if the new read provided is acceptable based on their own historic data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Incoming Supplier issues Agreed reads (IF-041) | 24 | BP003D | 65 80 | MHHS-BR-SU-161 | SUPI | IF-041 | [SupplierAgreedCOS] | DIP | Incoming Supplier accepts the D0300 and sends agreed reading(s) to the DIP via the IF-041 | http 201 response from DIP | Y
|  | 25 | BP003D | 90 |  | DIP | PUB-041 | [SupplierAgreedCOS] | SDSI | DIP issues PUB-041 to the new Data Service |  | N
|  | 26 | BP003C | 100 | MHHS-BR-DS-028.2 | DIP | PUB-041 | [SupplierAgreedCOS] | SDSI | Incoming Data Service receives PUB-041 | Incoming Data Service receives PUB-041 SupplierAgreedCOS. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Read Sharing - Incoming Data Service | 27 | BP005 | 175 | MHHS-BR-DS-098.1 | SDSI | Data Collection |  |  | Reading Validation | Incoming Data Service will need to follow Validation and Estimation Method Statements | Y
|  | 28 | BP005 | 315 | MHHS-BR-DS-098.2 | SDSI | IF-041 | [ReadingRemote] | DIP | Issue Reading Data to the DIP via the IF-041 | http 201 response from DIP | Y
|  | 29 | BP005 | 320 330 |  | DIP | PUB-041 | [ReadingRemote] | SUPI, LDSO | DIP issues PUB-041 to New Supplier and LDSO |  | N
|  | 30 | BP005 | 340 | MHHS-BR-SU-047.1 | DIP | PUB-041 | [ReadingRemote] | SUPI | New Supplier receives PUB-041 | New Supplier receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 31 | BP005 | 350 | MHHS-BR-LD-009.1 | DIP | PUB-041 | [ReadingRemote] | LDSO | LDSO receives PUB-041 | LDSO receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Outgoing Supplier issues Agreed reads (IF-041) | 32 | BP003D | 20 35 | MHHS-BR-SU-162 | SUPO | IF-041 | [SupplierAgreedCOS] | DIP | Outgoing Supplier accepts the D0300 and sends agreed reading(s) to the outgoing data Service via the IF-041 Flow | http 201 response from DIP | Y
|  | 33 | BP003D | 40 |  | DIP | PUB-041 | [SupplierAgreedCOS] | SDSO | DIP issues PUB-041 to the Outgoing Data Service |  | N
|  | 34 | BP003D | 45 | MHHS-BR-DS-028.4 | DIP | PUB-041 | [SupplierAgreedCOS] | SDSO | Outgoing Data Service receives Agreed Reading(s) | Data Services will receive a re-agreed read via an IF-041 and proceed to Settlement Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Read Sharing - Outgoing Data Service | 35 | BP005 | 175 | MHHS-BR-DS-098.1 | SDSO | Data Collection |  |  | Reading Validation | Outgoing Data Service will need to follow Validation and Estimation Method Statements | Y
|  | 36 | BP005 | 315 | MHHS-BR-DS-098.2 | SDSO | IF-041 | [ReadingRemote] | DIP | Issue Reading Data to the DIP via the IF-041 | http 201 response from DIP | Y
|  | 37 | BP005 | 320 330 |  | DIP | PUB-041 | [ReadingRemote] | SUPO, LDSO | DIP issues PUB-041 to Supplier and LDSO |  | N
|  | 38 | BP005 | 340 | MHHS-BR-SU-047.1 | DIP | PUB-041 | [ReadingRemote] | SUPO | Old Supplier receives PUB-041 | Old Supplier receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 39 | BP005 | 350 | MHHS-BR-LD009.1 | DIP | PUB-041 | [ReadingRemote] | LDSO | LDSO receives PUB-041 | LDSO receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Old Data Service handles Historic Settlement for based on the Agreed Read | 40 | BP005 | 60 | N/A | SDSO | D0010 |  | Settlement | Outgoing Data Service - Settlement Historic Adjustment invoked following receipt of the Agreed Read (IF-041) . Adjustments to previously estimated UTC Settlement Period Consumption Data [where the calendar is not locked (RF Completed)] are processed. Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N
| New Data Service handles Future Settlement based on the Agreed Read | 41 | BP005 | 60 | N/A | SDSI | D0010 |  | Settlement | Incoming Data Service - handles Settlement from Appointment Date following receipt of the Agreed Read (IF-041) . Detailed Requirements are documented in Segment Specific “Validation & Estimation Method Statement” |  | N

## SITFTS0012- Advanced Single
No. | Test Case Id | [5 empty] | Test Case Version | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
5 | SITFTS-0012 TC05 | [5 empty] | 0.6.2 | SITFTS-0012 - Advanced Single | SITFTS-0012 - Advanced Single | Advanced Linked MPANs Daily Consents, forward-dated Change of Supply and Data Service with no change of Metering Service (Metering Service remains the same organization to be appointed) (as per DES138 data specification) where the old DS is unable to contact the meter. Last 3 months IF-021 data available for IF-015 validation | Advanced | Single | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0012 - Advanced Single | Pre Req | Pre Req | [7 empty] | Change of supply to be created as part of testing pre req. Services to be appointed where the same org meter service is de-appointed and appointed and different org data service is appointed Please refer to SITFTS-0020 Worksheet SITFTS0020- Advanced steps to support the change of supplier process if required. All steps are to be executed before consumption processing can commence. The consumption processing in this script is expected to commence on the day after the CoS has been completed. |  | N
| Transfer of Reads - De-Appointment | 1 | BP003 | 301 | MHHS-BR-DS-022 | ADSO |  |  |  | Outgoing Data Service triggers Transfer of Reads following Change of Supplier |  | N
| Outgoing Data Service recovers closing position | 2 | BP003C | 855 | MHHS-BR-DS-026.6 | ADSO |  |  |  | Outgoing Data Service recovers Closing position by accessing the meter - Remote or Local access is not possible |  | Y
| Outgoing Data Service estimates closing position | 3 | BP003C | 860 | MHHS-BR-DS-026.7 | ADSO |  |  |  | Attempt to Read Meter Fails causing Outgoing Data Service to Estimate | Estimate closing UTC period level data ADS must, where remote or local access is not possible, estimate closing UTC period level data for an Advanced meter in line with the Advanced Method Statement. | Y
| Transfer of Reads - Appointment | 4 | BP003 | 347 | N/A | ADSI |  |  |  | Incoming Data Service triggers Transfer of Reads following Change of Supplier based on a Change of Supply (COS) Read for COS Effective Date (midnight start of day) |  | N
| Incoming Data Service recovers opening position | 5 | BP003C | 800 | MHHS-BR-DS-026.3 | ADSI |  |  |  | Incoming Data Service recovers Opening position by accessing the meter - Advanced Actual Data |  | Y
| Incoming Data Service recovers consumption history | 6 | BP003C | 805 | MHHS-BR-DS-026.1 | ADSI | IF-015 | [ConsumptionReplay] | DIP | Incoming Data Service requests Consumption History from the DIP | http 201 response from DIP. All consumption records (IF-021/IF-013) submitted/received by previous Advanced Data Services for a period of four months prior to SSD will be replayed | Y
|  | 7 | BP003C | 810 815 |  | ADSI | IF-015 | [ConsumptionReplay] | DIP | DIP processes Consumption Replay - MSG0000 - Request Successful | The DIP will receive MHHS-IF-015 from the Advanced Data Service for the consumption history | N
|  | 8 | BP003C | 815 |  | DIP | PUB-016 | [ActivePower] | ADSC | DIP sends PUB-016 to ADSI | The DIP will issue PUB-016 to the Advanced Data Service with the consumption history | Y
|  | 9 | BP003C | 820 | MHHS-BR-DS-026.2 | DIP | PUB-016 | [ActivePower] | ADSI | ADSI receives PUB-016 - [ActivePower] | The new Advanced Data Service will receive consumption history from the DIP and progress to Settlement Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Read Sharing - Outgoing Data Service | 10 | BP005 | 175 | MHHS-BR-DS-098.1 | ADSO | Data Collection |  |  | Reading Validation | Outgoing Data Service will need to follow Validation and Estimation Method Statements | Y
|  | 11 | BP005 | 315 | MHHS-BR-DS-098.2 | ADSO | IF-041 | [ReadingRemote] | DIP | Issue Reading Data to the DIP via the IF-041 | http 201 response from DIP | Y
|  | 12 | BP005 | 320 330 |  | DIP | PUB-041 | [ReadingRemote] | SUPO, LDSO | DIP issues PUB-041 to Supplier and LDSO |  | N
|  | 13 | BP005 | 340 | MHHS-BR-SU-047.1 | DIP | PUB-041 | [ReadingRemote] | SUPO | Old Supplier receives PUB-041 | Old Supplier receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 14 | BP005 | 350 | MHHS-BR-LD009.1 | DIP | PUB-041 | [ReadingRemote] | LDSO | LDSO receives PUB-041 | LDSO receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Read Sharing - Incoming Data Service | 15 | BP005 | 175 | MHHS-BR-DS-098.1 | ADSI | Data Collection |  |  | Reading Validation | Incoming Data Service will need to follow Validation and Estimation Method Statements | Y
|  | 16 | BP005 | 315 | MHHS-BR-DS-098.2 | ADSI | IF-041 | [ReadingRemote] | DIP | Issue Reading Data to the DIP via the IF-041 | http 201 response from DIP | Y
|  | 17 | BP005 | 320 330 |  | DIP | PUB-041 | [ReadingRemote] | SUPI, LDSO | DIP issues PUB-041 to New Supplier and LDSO |  | N
|  | 18 | BP005 | 340 | MHHS-BR-SU-047.1 | DIP | PUB-041 | [ReadingRemote] | SUPI | New Supplier receives PUB-041 | New Supplier receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 19 | BP005 | 350 | MHHS-BR-LD-009.1 | DIP | PUB-041 | [ReadingRemote] | LDSO | LDSO receives PUB-041 | LDSO receives Cumulative and/or Smart Register Readings. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA