## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Change Log
Date | Author | Release | Reason for change
2024-05-16 | Iain Smith |  | Scenario created - removed IF-064 from listing as NFT could find no evidence of this being testing in integrated SIT-F
`15/08/2024 | MHHS NFT | 0.2 | Updates to message content flags

## SITNFT-T2-020-010-SMART
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 |  | SITNFT-T2-020-010-SMART |  |  |  |  | SITNFT-T1-020-020 - Smart | Single MPAN | Smart Meter | Single | Calendar
2 |  | SITFTS-0050 TC02 |  |  |  |  | SITFTS-0050 - Unmetered | SITFTS-0050 - Unmetered |  | No Meter | Single | forward-dated
3 |  | SITFTS-0050 TC03 |  |  |  |  | SITFTS-0050 - Traditional | SITFTS-0050 - Traditional |  | Traditional Meter | Single | retro-dated
4 |  | SITFTS-0050 TC04 |  |  |  |  | SITFTS-0050 - Advanced | SITFTS-0050 - Advanced |  | Advanced | Related | forward-dated
5
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Message Output | Message Output Event Code | Key Validation & Test Evidence | Evidence Required
SITNFT-T2-020-010 - Smart | Calendar Check | 10 Pre-Req 1 | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day [D] For the purposes of this test the following is assumed: II Run is UTC Settlement Day [D] - 1 |  |  |  | Y
IF-021 Interface between Data Service Participant and DIP is disable/configured to return error
| Submit UTC Data | 20 | BP005 | 150 | E2E0011 E2E0105 E2E0106 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | SDS | IF-021 | [ActivePower] & [DI-015] = W | DIP | Data Service sends UTC Period Level Consumption Data to the DIP |  | N/A | http error response from DIP (Likely a HTTP 503) | Y
Evidence of IF-021 Queuing/Buffering
IF-021 Interface between Data Service Participant and DIP is enabled/configured to return process as normal
|  | 25 | BP005 | 160 |  | DIP | PUB-021 | [ActivePower] & [DI-015] = W | SUPC, LDSO | DIP sends PUB-021 to Supplier and LDSO | PUB-021 |  |  | N
|  | 30 | BP005 | 280 | E2E0201 E2E0202 E2E0203 E2E0204 E2E0205 E2E0207 E2E0211 E2E1003 E2E1009 | DIP | PUB-021 | [ActivePower] & [DI-015] = W | SUPC | Supplier receives the PUB-021 | PUB-021 | [ActivePower] & [DI-015] = W | Supplier receives PUB-021 [ActivePower] & [DI-015] = W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 35 | BP005 | 270 | E2E0201 E2E0202 E2E0203 E2E0204 E2E0205 E2E0207 E2E0211 E2E1003 E2E1009 | DIP | PUB-021 | [ActivePower] & [DI-015] = W | LDSO | LDSO receives the PUB-021 | PUB-021 | [ActivePower] & [DI-015] = W | LDSO receives PUB-021 [ActivePower] & [DI-015] = W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITNFT-T2-020-040-ADV
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 |  | SITNFT-T2-020-040-ADV |  |  |  |  | SITFTS-0530 - Advanced | Single MPAN | Advanced Meter | Single | Calendar
2 |  | SITFTS-0050 TC02 |  |  |  |  | SITFTS-0050 - Unmetered | SITFTS-0050 - Unmetered |  | No Meter | Single | forward-dated
3 |  | SITFTS-0050 TC03 |  |  |  |  | SITFTS-0050 - Traditional | SITFTS-0050 - Traditional |  | Traditional Meter | Single | retro-dated
4 |  | SITFTS-0050 TC04 |  |  |  |  | SITFTS-0050 - Advanced | SITFTS-0050 - Advanced |  | Advanced | Related | forward-dated
5
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Message Output | Message Output Event Code | Key Validation & Test Evidence | Evidence Required
SITFTS-0530 - Advanced | Calendar Check | 10 Pre-Req 1 | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day [D] For the purposes of this test the following is assumed: II Run is UTC Settlement Day [D] - 1 |  |  |  | Y
IF-021 Interface between Data Service Participant and DIP is disable/configured to return error
| Submit UTC Data | 20 | BP005 | 150 | E2E0011 E2E0105 E2E0106 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | ADS | IF-021 | [ActivePower] & [DI-015] <> W | DIP | Data Service sends UTC Period Level Consumption Data to the DIP |  | N/A | http error response from DIP (Likely a HTTP 503) | Y
Evidence of IF-021 Queuing/Buffering
IF-021 Interface between Data Service Participant and DIP is enabled/configured to return process as normal
|  | 25 | BP005 | 160 |  | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC, LDSO | DIP sends PUB-021 to Supplier and LDSO | PUB-021 |  |  | N
|  | 30 | BP005 | 280 | E2E0201 E2E0202 E2E0203 E2E0204 E2E0205 E2E0207 E2E0211 E2E1003 E2E1009 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC | Supplier receives the PUB-021 | PUB-021 | [ActivePower] & [DI-015] <> W | Supplier receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 35 | BP005 | 270 | E2E0201 E2E0202 E2E0203 E2E0204 E2E0205 E2E0207 E2E0211 E2E1003 E2E1009 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LDSO | LDSO receives the PUB-021 | PUB-021 | [ActivePower] & [DI-015] <> W | LDSO receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITNFT-T2-020-050-UM
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
5 |  | SITNFT-T2-020-050-UM |  |  |  |  | SITFTS-0530 - Advanced | Single MPAN | Advanced Meter | Single | Calendar
2 |  | SITFTS-0050 TC02 |  |  |  |  | SITFTS-0050 - Unmetered | SITFTS-0050 - Unmetered |  | No Meter | Single | forward-dated
3 |  | SITFTS-0050 TC03 |  |  |  |  | SITFTS-0050 - Traditional | SITFTS-0050 - Traditional |  | Traditional Meter | Single | retro-dated
4 |  | SITFTS-0050 TC04 |  |  |  |  | SITFTS-0050 - Advanced | SITFTS-0050 - Advanced |  | Advanced | Related | forward-dated
5
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Message Output | Message Output Event Code | Key Validation & Test Evidence | Evidence Required
SITFTS-0530 - Advanced | Calendar Check | 10 Pre-Req 1 | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day [D] For the purposes of this test the following is assumed: II Run is UTC Settlement Day [D] - 1 |  |  |  | Y
IF-021 Interface between Data Service Participant and DIP is disable/configured to return error
| Submit UTC Data | 20 | BP005 | 150 | E2E0011 E2E0105 E2E0106 E2E0102 E2E0103 E2E0104 E2E0107 E2E0108 E2E0109 | UMSC | IF-021 | [ActivePower] & [DI-015] <> W | DIP | Data Service sends UTC Period Level Consumption Data to the DIP |  | N/A | http error response from DIP (Likely a HTTP 503) | Y
Evidence of IF-021 Queuing/Buffering
IF-021 Interface between Data Service Participant and DIP is enabled/configured to return process as normal
|  | 25 | BP005 | 160 |  | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC, LDSO | DIP sends PUB-021 to Supplier and LDSO | PUB-021 |  |  | N
|  | 30 | BP005 | 280 | E2E0201 E2E0202 E2E0203 E2E0204 E2E0205 E2E0207 E2E0211 E2E1003 E2E1009 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | SUPC | Supplier receives the PUB-021 | PUB-021 | [ActivePower] & [DI-015] <> W | Supplier receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 35 | BP005 | 270 | E2E0201 E2E0202 E2E0203 E2E0204 E2E0205 E2E0207 E2E0211 E2E1003 E2E1009 | DIP | PUB-021 | [ActivePower] & [DI-015] <> W | LDSO | LDSO receives the PUB-021 | PUB-021 | [ActivePower] & [DI-015] <> W | LDSO receives PUB-021 [ActivePower] & [DI-015] <> W containing UTC Settlement Period Consumption Data. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y