## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Change Log
Date | Author | Release | Reason for change
2024-05-16 | Iain Smith |  | Scenario created

## SITNFT-T2-040 Overview
Scenario ID | SITNFT-T2-040
Theme | Change Of Supplier
Scenario Title | Change of Supplier Notifications
Description | TC01 - Smart TC02 - Advanced TC03 - Unmetered TC04 - Traditional
Functional Category | Registration
Functional Area 1 | Registration
Functional Area 2 | Helix systems processing
Creator | Iain Smith
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP001
Pre-Requisites
Boundaries
Test Case Variables | Meter Type
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITNFT-T2-040-010-Smart | SITNFT-T2-040-010-Smart | Appointment date today + 1 | Smart Meter | Single MPAN | Calendar
2 | SITNFT-T2-040-020-Adv | SITNFT-T2-040-020-Adv | Appointment date today + 1 | Advanced Meter | Single MPAN | Calendar
3 | SITNFT-T2-040-030-UM | SITNFT-T2-040-030-UM | Appointment date today + 1 | Unmetered | Single MPAN | Calendar
4 | SITNFT-T2-040-040-Trad | SITNFT-T2-040-040-Trad | Appointment date today + 1 | Traditional Meter | Single MPAN | Calendar
Back to List of
Test Scenarios

## SITNFT-T2-040-010-Smart
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 |  | SITNFT-T2-040-010-Smart |  |  |  |  | SITNFT-T2-040-010-Smart | Appointment date today + 1 | Smart Meter | Single | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0010 - Smart Single MPAN | Change of Supply - Start | 1 | BP001 | 60 | N/A | SUPI | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | SUPI sends Switch Request to CSS Simulated/Data Fix |  | Y
|  | 2 | BP001 | 65 | N/A | SUPI | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | CSS Simulated/Data Fix receives Switch Request from Incoming Supplier and responds to REGS |  | Y
|  | 3 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | CSS Simulated/Data Fix sends CSS Simulated/Data Fix02800 (pending Supplier request via CSS Simulated/Data Fix flow) to the REGS. |  | Y
|  | 4 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS Simulated/Data Fix flow. |  | Y
|  | 5 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to the DIP | http 202 response from DIP | Y
|  | 6 | BP001 | 85 |  | DIP | PUB-002 | [GainMPANInfo] | SUPI | DIP sends PUB-002 to the SUPI | IF-002 Sent to new Supplier in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 7 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPI | SUPI receives PUB-002 from DIP. | Supplier receives PUB-002 GainMPANInfo with all relevant information to set up the site. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 8 | BP002 | 10 20 | MHHS-BR-SU-002 MHHS-BR-SU-005 MHHS-BR-SU-006 MHHS-BR-SU-007 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to the DIP for a MS Appointment. | http 202 response from DIP | Y
|  | 9 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
|  | 10 | BP002 | 40 | MHHS-BR-RS-010 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 11 | BP002 | 45 | MHHS-BR-RS-011 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 12 | BP002 | 50 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 to the Supplier. |  | N
|  | 13 | BP002 | 55 | MHHS-BR-SU-008 MHHS-BR-SU-009 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 14 | BP002 | 60 | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP. | http 202 response from DIP | Y
|  | 15 | BP002 | 65 |  | DIP | PUB-033 | [MSAppSPRequest] | SMSI | DIP sends PUB-033 to the SMS (Incoming). |  | N
|  | 16 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | SMS (Incoming) receives PUB-033. | SMS incoming receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 17 | BP002 | 75 | MHHS-BR-MS-002 MHHS-BR-MS-003 | SMSI | IF-034 | [MSAppSPResponse] | DIP | SMS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 18 | BP002 | 80 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 19 | BP002 | 85 | MHHS-BR-RS-016 MHHS-BR-RS-017 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 20 | BP002 | 87 | MHHS-BR-RS-018 | REGS | IF-035 | [MSAppAccepted] | DIP | REGS sends IF-035 to the DIP. | http 202 response from DIP | Y
|  | 21 | BP002 | 91 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, SMSI | DIP sends PUB-035 to the Supplier and SMS (Incoming) |  | N
|  | 22 | BP002 | 95 | MHHS-BR-SU-010 MHHS-BR-SU-011 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 23 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | SMSI | SMSI receives PUB-035. | SMSI receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Change of Data Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 24 | BP003 | 10 20 | MHHS-BR-SU-002 MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP for a DS Appointment. | http 202 response from DIP | Y
|  | 25 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment |  | N
|  | 26 | BP003 | 40 | MHHS-BR-RS-043 MHHS-BR-RS-044 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier. | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 27 | BP003 | 45 | MHHS-BR-RS-045 MHHS-BR-RS-046 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 28 | BP003 | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the DIP. |  | N
|  | 29 | BP003 | 55 | MHHS-BR-SU-022 MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 30 | BP003 | 60 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 202 response from DIP | Y
|  | 31 | BP003 | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | SDSI | DIP sends PUB-033 to the SDS (Incoming). |  | N
|  | 32 | BP003 | 220 | MHHS-BR-DS-007 MHHS-BR-DS-011 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | SDS (Incoming) receives PUB-033 from the DIP. | SDS receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 33 | BP003 | 221 | MHHS-BR-DS-008 MHHS-BR-DS-011 | SDSI | IF-034 | [DSAppSPResponse] | DIP | SDS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 34 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 35 | BP003 | 85 100 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to determine processing treatment Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS Appointment Accepted | 36 | BP003 | 85 87 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to the DIP | http 202 response from DIP | Y
|  | 37 | BP003 | 215 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC, SDSI | DIP sends PUB-035 to the Supplier and Data Service (Incoming) |  | N
|  | 38 | BP003 | 95 | MHHS-BR-SU-024 MHHS-BR-SU-025 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 39 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | SDSI | SDSI receives PUB-035. | SDSI receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2-040-020-Adv
No. |  | Test Case Id | [5 empty] | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 |  | SITNFT-T2-040-020-Adv | [5 empty] | SITNFT-T2-040-020-Adv | Appointment date today + 1 | Advanced | Import+Export | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0010 - Advanced Linked MPANs (Same Supplier) | Change of Supply - Start | 1 | BP001 | 60 | N/A | SUPC | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | CSS Simulated/Data Fix receives Switch Request from Supplier for Import MPAN and responds to REGS |  | Y
|  | 2 | BP001 | 60 | N/A | SUPC | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | CSS Simulated/Data Fix receives Switch Request from Supplier for Export MPAN and responds to REGS |  | Y
|  | 3 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS Simulated/Data Fix flow for Import MPAN. | The Registration Service will send IF-002 to the prospective Supplier. This will contain all of the current data held within the Registration Service | Y
|  | 4 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS Simulated/Data Fix flow for Export MPAN. | The Registration Service will send IF-002 to the prospective Supplier. This will contain all of the current data held within the Registration Service | Y
| New Supplier Site Info (IF-002) - Import MPAN | 5 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 sent to DIP for Import MPAN | http 202 response from DIP | Y
|  | 6 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPC | DIP sends PUB--002 to SUPC | IF-002 for Import MPAN Sent to new Supplier in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 7 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPC | PUB-002 received by new supplier | Supplier receives PUB-002 for Import MPAN with all relevant information to set up the site. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| New Supplier Site Info (IF-002) - Export MPAN | 8 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 sent to DIP for Export MPAN | http 202 response from DIP | Y
|  | 9 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPC | DIP sends PUB--002 to SUPC | IF-002 for Export MPAN Sent to new Supplier in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 10 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPC | PUB-002 received by new supplier | Supplier receives PUB-002 for Export MPAN with all relevant information to set up the site. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 11 | BP002 | 10 20 | MHHS-BR-SU-005 MHHS-BR-SU-006 MHHS-BR-SU-007 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to the DIP for a MS Appointment. | http 202 response from DIP | Y
|  | 12 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
|  | 13 | BP002 | 40 | MHHS-BR-RS-010 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 14 | BP002 | 45 | MHHS-BR-RS-011 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 15 | BP002 | 50 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 to the Supplier. |  | N
|  | 16 | BP002 | 55 | MHHS-BR-SU-008 MHHS-BR-SU-009 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 17 | BP002 | 60 | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP. | http 202 response from DIP | Y
|  | 18 | BP002 | 65 |  | DIP | PUB-033 | [MSAppSPRequest] | AMSI | DIP sends PUB-033 to the AMS (Incoming). |  | N
|  | 19 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | AMSI | AMS (Incoming) receives PUB-033. | AMS incoming receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 20 | BP002 | 75 | MHHS-BR-MS-002 MHHS-BR-MS-003 | AMSI | IF-034 | [MSAppSPResponse] | DIP | AMS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 21 | BP002 | 80 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 22 | BP002 | 85 | MHHS-BR-RS-016 MHHS-BR-RS-017 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 23 | BP002 | 87 | MHHS-BR-RS-018 MHHS-BR-RS-021 | REGS | IF-035 | [MSAppAccepted] | DIP | REGS sends IF-035 to the DIP. | http 202 response from DIP | Y
|  | 24 | BP002 | 91 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, AMSI | DIP sends PUB-035 to the Supplier and AMS (Incoming) |  | N
|  | 25 | BP002 | 95 | MHHS-BR-SU-010 MHHS-BR-SU-011 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 26 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | AMSI | AMSI receives PUB-035. | AMSI receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 27 | BP002 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 [Prospective Appt] to the DIP. | http 202 response from DIP | Y
|  | 28 | BP002 | 90 |  | DIP | PUB-035 | [IMS-SendMTD] | AMSO | DIP sends PUB-035 [Prospective Appt] to the AMS (Outgoing). |  | N
|  | 29 | BP002 | 160 | MHHS-BR-MS-006 | DIP | PUB-035 | [IMS-SendMTD] | AMSO | AMS (Outgoing) receives PUB-035. | AMS outgoing receives PUB-035 with details of IMS send MTD which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Adv MTD Exchange Notification (If Metering Service is changing) | 30 | BP002 | 165 | MHHS-BR-MS-017 | AMSO | D0383/D0384 | N/A | AMSI | AMSO sends D0383/D0384 to AMSI Note: Only required if Metering Service is changing | Metering Service should issue the MTDs for ALL Linked Export and/or Related MPANs | Y
|  | 31 | BP002 | 170 | MHHS-BR-MS-019 | AMSO | D0383/D0384 | N/A | AMSI | AMSI receives D0383/D0384 from AMSO |  | Y
|  | 32 | BP002 | 170 | MHHS-BR-MS-017 | AMSO | D268 HH Adv MTD | N/A | AMSI | AMSO sends D268 HH Adv MTD to AMSI |  | Y
|  | 33 | BP002 | 175 | MHHS-BR-MS-020 MHHS-BR-MS-019 | AMSO | D268 HH Adv MTD | N/A | AMSI | AMSI receives D268 HH Adv MTD from AMSO |  | Y
| Change of Data Service - Raise Appointment Change Supplier only - Data Service unchanged | [9 empty] | Change Supplier only - Data Service unchanged | N
| Supplier Appointment Request | 34 | BP003 | 10 20 | MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP | http 202 response from DIP | Y
|  | 35 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment. |  | N
|  | 36 | BP003 | 40 | MHHS-BR-RS-043 MHHS-BR-RS-044 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 37 | BP003 | 45 | MHHS-BR-RS-045 MHHS-BR-RS-046 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 to DIP | http 202 response from DIP | Y
|  | 38 | BP003 | 50 | MHHS-BR-RS-045 MHHS-BR-RS-046 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the Supplier. |  | N
|  | 39 | BP003 | 55 | MHHS-BR-SU-022 MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 40 | BP003 | 60 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 202 response from DIP | Y
|  | 41 | BP003 | 65 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | DIP | PUB-033 | [DSAppSPRequest] | ADSI | DIP sends PUB-033 to the ADS (Incoming). |  | N
|  | 42 | BP003 | 220 | MHHS-BR-DS-007 MHHS-BR-DS-011 | DIP | PUB-033 | [DSAppSPRequest] | ADSI | ADS (Incoming) receives PUB-033 from the DIP. | ADS receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 43 | BP003 | 221 | MHHS-BR-DS-008 MHHS-BR-DS-011 | ADSI | IF-034 | [DSAppSPResponse] | DIP | ADSI sends IF-034 to DIP | http 202 response from DIP | Y
|  | 44 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 45 | BP003 | 85 100 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with details of Data Services Appointment PR Response and confirms/determines processing treatment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 46 | BP003 | 86 87 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to DIP | http 202 response from DIP | Y
|  | 47 | BP003 | 215 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | DIP | PUB-035 | [DSAppAccepted] | SUPC, ADSI | DIP sends PUB-035 to the Supplier and Data Service (Incoming) |  | N
|  | 48 | BP003 | 95 | MHHS-BR-SU-024 MHHS-BR-SU-025 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 49 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | ADSI | ADSI receives PUB-035. | ADSI receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 50 | BP003 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 to DIP | http 202 response from DIP | Y
|  | 51 | BP003 | 88 | MHHS-BR-RS-019 | DIP | PUB-035 | [IMS-SendMTD] | AMSO | DIP sends PUB-035 [Prospective Appt] to the AMS (Outgoing). |  | N
|  | 52 | BP003 | 160 | MHHS-BR-MS-006 | DIP | PUB-035 | [IMS-SendMTD] | AMSO | AMS (Outgoing) receives PUB-035 from the DIP. | AMS Outgoing receives PUB-035 with details of IMS-SendMTD and confirm REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2-040-030-UM
No. |  | Test Case Id | [5 empty] | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 |  | SITNFT-T2-040-030-UM | [5 empty] | SITNFT-T2-040-030-UM | Appointment date today + 1 | No Meter | Single | forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0010 - Unmetered | Change of Supply - Start | 1 | BP001 | 60 | N/A | SUPC | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | CSS Simulated/Data Fix receives Switch Request from Supplier and responds to REGS |  | Y
|  | 2 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS Simulated/Data Fix flow. | The Registration Service will send IF-002 to the prospective Supplier. This will contain all of the current data held within the Registration Service | Y
|  | 3 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to DIP | http 202 response from DIP | Y
|  | 4 | BP001 | 75 |  | DIP | PUB-002 | [GainMPANInfo] | SUPC | DIP sends PUB-002 to update new supplier | IF-002 Sent to new Supplier in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 5 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPC | New Supplier receives PUB-002 from DIP |  | Y
| Change of Metering Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 6 | BP002 | 10 20 | MHHS-BR-SU-005 MHHS-BR-SU-006 MHHS-BR-SU-007 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to the DIP for a MS Appointment. | http 202 response from DIP | Y
|  | 7 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
|  | 8 | BP002 | 40 | MHHS-BR-RS-010 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 9 | BP002 | 45 | MHHS-BR-RS-011 | REGS | IF-032 | [MSAppSPResponse] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 10 | BP002 | 50 |  | DIP | PUB-032 | [MSAppSPResponse] | SUPC | DIP sends PUB-032 to the Supplier. |  | N
|  | 11 | BP002 | 55 | MHHS-BR-SU-008 MHHS-BR-SU-009 | DIP | PUB-032 | [MSAppSPResponse] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 12 | BP002 | 60 | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP. | http 202 response from DIP | Y
|  | 13 | BP002 | 65 |  | DIP | PUB-033 | [MSAppSPRequest] | UMSO | DIP sends PUB-033 to the UMSO. |  | N
|  | 14 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | UMSO | UMSO receives PUB-033. | UMSO receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 15 | BP002 | 75 | MHHS-BR-MS-002 MHHS-BR-MS-003 | UMSO | IF-034 | [MSAppSPResponse] | DIP | UMSO sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 16 | BP002 | 80 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 17 | BP002 | 85 | MHHS-BR-RS-016 MHHS-BR-RS-017 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 18 | BP002 | 87 | MHHS-BR-RS-018 | REGS | IF-035 | [MSAppAccepted] | DIP | REGS sends IF-035 to the DIP. | http 202 response from DIP | Y
|  | 19 | BP002 | 91 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, UMSO | DIP sends PUB-035 to the Supplier and UMS (Incoming) |  | N
|  | 20 | BP002 | 95 | MHHS-BR-SU-010 MHHS-BR-SU-011 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | UMSO | UMSO receives PUB-035. | UMSO receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Change of Data Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 22 | BP003 | 10 20 | MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP - for a DS Appointment | http 202 response from DIP | Y
|  | 23 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment |  | N
|  | 24 | BP003 | 40 | MHHS-BR-RS-043 MHHS-BR-RS-044 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier. | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 25 | BP003 | 45 | MHHS-BR-RS-045 MHHS-BR-RS-046 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 26 | BP003 | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the DIP. |  | N
|  | 27 | BP003 | 55 | MHHS-BR-SU-022 MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 28 | BP003 | 60 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 202 response from DIP | Y
|  | 29 | BP003 | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | UMSDSI | DIP sends PUB-033 to the UMSDS (Incoming). |  | N
|  | 30 | BP003 | 220 | MHHS-BR-DS-007 MHHS-BR-DS-011 | DIP | PUB-033 | [DSAppSPRequest] | UMSDSI | UMSDS (Incoming) receives PUB-033 from the DIP. | UMSDS (Incoming) receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 31 | BP003 | 221 | MHHS-BR-DS-008 MHHS-BR-DS-011 | UMSDSI | IF-034 | [DSAppSPResponse] | DIP | UMSDS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 32 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 33 | BP003 | 85 100 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to determine processing treatment Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS Appointment Accepted | 34 | BP003 | 86 87 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to the DIP | http 202 response from DIP | Y
|  | 35 | BP003 | 215 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC, UMSDSI | DIP sends PUB-035 to the Supplier and UMSDS (Incoming) |  | N
|  | 36 | BP003 | 95 | MHHS-BR-SU-024 MHHS-BR-SU-025 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 37 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | UMSDSI | UMSDS (Incoming) receives PUB-035. | UMSDS (Incoming) receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y

## SITNFT-T2-040-040-Trad
No. |  | Test Case Id |  |  |  |  | Test Case Title | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 |  | SITNFT-T2-040-040-Trad |  |  |  |  | SITNFT-T2-040-040-Trad | Appointment date today + 1 | Traditional Meter | Related | forward-dated
2 |  | SITFTS-0050 TC02 |  |  |  |  | SITFTS-0050 - Unmetered | SITFTS-0050 - Unmetered |  | No Meter
3 |  | SITFTS-0050 TC03 |  |  |  |  | SITFTS-0050 - Traditional | SITFTS-0050 - Traditional |  | Traditional Meter
4 |  | SITFTS-0050 TC04 |  |  |  |  | SITFTS-0050 - Advanced | SITFTS-0050 - Advanced |  | Advanced
5
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0010 - Traditional Related MPANs | Change of Supply - Start | 1 | BP001 | 60 | N/A | SUPI | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | SUPI sends Switch Request to CSS Simulated/Data Fix |  | Y
|  | 2 | BP001 | 65 | N/A | SUPI | CSS Simulated/Data Fix01700 | N/A | CSS Simulated/Data Fix | CSS Simulated/Data Fix receives Switch Request from Incoming Supplier and responds to REGS |  | Y
|  | 3 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | CSS Simulated/Data Fix sends CSS Simulated/Data Fix2800 (pending Supplier request via CSS Simulated/Data Fix flow) for primary MPAN to the REGS. |  | Y
|  | 4 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | CSS Simulated/Data Fix sends CSS Simulated/Data Fix2800 (pending Supplier request via CSS Simulated/Data Fix flow) for Secondary MPAN to the REGS. |  | Y
|  | 5 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS Simulated/Data Fix flow for primary MPAN. |  | Y
|  | 6 | BP001 | 70 | MHHS-BR-RS-005 | CSS Simulated/Data Fix | CSS Simulated/Data Fix02800 | N/A | REGS | Registration Service receives pending Supplier request via CSS Simulated/Data Fix flow for Secondary MPAN. |  | Y
| New Supplier of Site Notification - Primary MPAN | 7 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to the DIP for Primary MPAN | http 202 response from DIP | Y
|  | 8 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPI | DIP sends PUB-002 to the SUPI | PUB-002 Sent to new Supplier for Primary MPAN in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 9 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPI | SUPI receives PUB-002 from DIP. | Supplier receives PUB-002 GainMPANInfo with all relevant information to set up the site. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| New Supplier of Site Notification - Secondary MPAN | 10 | BP001 | 75 | MHHS-BR-RS-006 | REGS | IF-002 | [GainMPANInfo] | DIP | REGS sends IF-002 to the DIP for Secondary MPAN | http 202 response from DIP | Y
|  | 11 | BP001 | 80 |  | DIP | PUB-002 | [GainMPANInfo] | SUPI | DIP sends PUB-002 to the SUPI | PUB-002 Sent to new Supplier for Secondary MPAN in order to obtain all relevant information to successfully set up the site in all systems and determine correct Service provider | N
|  | 12 | BP001 | 85 | MHHS-BR-SU-001 | DIP | PUB-002 | [GainMPANInfo] | SUPI | SUPI receives PUB-002 from DIP. | Supplier receives PUB-002 GainMPANInfo with all relevant information to set up the site. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Change of Metering Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 13 | BP002 | 10 20 | MHHS-BR-SU-005 MHHS-BR-SU-006 MHHS-BR-SU-007 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to the DIP for a MS Appointment. | http 202 response from DIP | Y
|  | 14 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
|  | 15 | BP002 | 40 | MHHS-BR-RS-010 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 16 | BP002 | 45 | MHHS-BR-RS-011 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 17 | BP002 | 50 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 to the Supplier. |  | N
|  | 18 | BP002 | 55 | MHHS-BR-SU-008 MHHS-BR-SU-009 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 19 | BP002 | 60 | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP. | http 202 response from DIP | Y
|  | 20 | BP002 | 65 |  | DIP | PUB-033 | [MSAppSPRequest] | SMSI | DIP sends PUB-033 to the SMS (Incoming). |  | N
|  | 21 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | SMS (Incoming) receives PUB-033. | SMS incoming receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 22 | BP002 | 75 | MHHS-BR-MS-002 MHHS-BR-MS-003 | SMSI | IF-034 | [MSAppSPResponse] | DIP | SMS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 23 | BP002 | 80 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 24 | BP002 | 85 | MHHS-BR-RS-016 MHHS-BR-RS-017 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 25 | BP002 | 87 | MHHS-BR-RS-018 | REGS | IF-035 | [MSAppAccepted] | DIP | REGS sends IF-035 to the DIP. | http 202 response from DIP | Y
|  | 26 | BP002 | 91 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, SMSI | DIP sends PUB-035 to the Supplier and SMS (Incoming) |  | N
|  | 27 | BP002 | 95 | MHHS-BR-SU-010 MHHS-BR-SU-011 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | SMSI | SMSI receives PUB-035. | SMSI receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 29 | BP002 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 [Prospective Appt] to the DIP. | http 202 response from DIP | Y
|  | 30 | BP002 | 90 |  | DIP | PUB-035 | [IMS-SendMTD] | SMSO | DIP sends PUB-035 [Prospective Appt] to the SMS (Outgoing). |  | N
|  | 31 | BP002 | 160 | MHHS-BR-MS-006 | DIP | PUB-035 | [IMS-SendMTD] | SMSO | SMS (Outgoing) receives PUB-035. | SMS outgoing receives PUB-035 with details of IMS Send MTD from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Trad MTD Exchange Notification (If Metering Service is changing) | 32 | BP002 | 165 | MHHS-BR-MS-018 | SMSO | D149/D150 Trad MTD | N/A | SMSI | SMSO sends D149/D150 Trad MTD to SMSI Note: Only required if Metering Service is changing | Metering Service should issue the MTDs for ALL Linked Export and/or Related MPANs | Y
|  | 33 | BP002 | 175 | MHHS-BR-MS-020 MHHS-BR-MS-019 | SMSO | D149/D150 Trad MTD | N/A | SMSI | SMSI receives D149/D150 Trad MTD from SMSO. |  | Y
| Change of Data Service - Raise Appointment | [10 empty] | N
| Supplier Appointment Request | 34 | BP003 | 10 20 | MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP - for a DS Appointment | http 202 response from DIP | Y
|  | 35 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment |  | N
|  | 36 | BP003 | 40 | MHHS-BR-RS-043 MHHS-BR-RS-044 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier. | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 37 | BP003 | 45 | MHHS-BR-RS-045 MHHS-BR-RS-046 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 202 response from DIP | Y
|  | 38 | BP003 | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the DIP. |  | N
|  | 39 | BP003 | 55 | MHHS-BR-SU-022 MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 40 | BP003 | 60 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 202 response from DIP | Y
|  | 41 | BP003 | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | SDSI | DIP sends PUB-033 to the SDS (Incoming). |  | N
|  | 42 | BP003 | 220 | MHHS-BR-DS-007 MHHS-BR-DS-011 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | SDS (Incoming) receives PUB-033 from the DIP. | SDS receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 43 | BP003 | 221 | MHHS-BR-DS-008 MHHS-BR-DS-011 | SDSI | IF-034 | [DSAppSPResponse] | DIP | SDS (Incoming) sends IF-034 to the DIP. | http 202 response from DIP | Y
|  | 44 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 45 | BP003 | 85 100 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to determine processing treatment Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS Appointment Accepted | 46 | BP003 | 85 87 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to the DIP | http 202 response from DIP | Y
|  | 47 | BP003 | 91 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC, SDSI | DIP sends PUB-035 to the Supplier and Data Service (Incoming) |  | N
|  | 48 | BP003 | 95 | MHHS-BR-SU-024 MHHS-BR-SU-025 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 49 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | SDSI | SDSI receives PUB-035. | SDSI receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 50 | BP003 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 to DIP | http 202 response from DIP | Y
|  | 51 | BP003 | 88 |  | DIP | PUB-035 | [IMS-SendMTD] | SMSO | DIP sends PUB-035 [Prospective Appt] to the SMS (Outgoing). |  | N
|  | 52 | BP003 | 160 | MHHS-BR-MS-026 | DIP | PUB-035 | [IMS-SendMTD] | SMSO | SMS (Outgoing) receives PUB-035 from the DIP | SMS Outgoing receives PUB-035 with details of IMS-SendMTD and confirm REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y