## Version History
Date | Author | Ver | Comment
2025-03-18 | Steve Evans | 0.2 | Published and sent to Ind for review
2025-03-20 | Steve Evans | 0.3 | Amended Pairings for OPC04 - 09 as icorrect based on PP feedback.

## Schedule
SIT Operations Theme 2 OPC & Sec | Test Case ID | Role Supporting | Cohort | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | Comments
MHHS-DEL2706 SITOPS_OPC001_Manual Process when Incorrect IF-031 received from Supplier | TC01 | Supplier REGS | Cohort F + SSEN | [28 empty] | 10 steps - Specific Data Requirement - Supplier Send IF-031 to DIP with Incorrect CSS Registration ID (DU-849) belonging to a different Supplier. | bar: 2025-05-06
MHHS-DEL2707 SITOPS_OPC002_Manual Process when Incorrect IF-033 received from REGS | TC01 -DS | Supplier REGS Data Service LDSO | Cohort B + SSEN | [28 empty] | 20 steps - Specific Data Requirement - - Requested Agent has no Contract with the Requesting Supplier' | bar: 2025-05-06 to 2025-05-07
| TC02 - MS | Supplier REGS Metering Service LDSO | Cohort B + SSEN | bar: 2025-05-06 to 2025-05-07
MHHS-DEL2708 SITOPS_OPC003_OC_Customer Direct Contract Advisory | TC01-MS | REGS Metering Service | Cohort C + BUUK | [28 empty] | 8 Steps - May req some elapsed time between actions? | bar: 2025-05-07; 2025-05-09
| TC02 - DS | REGS Data Service | Cohort C + BUUK | bar: 2025-05-07; 2025-05-09
| TC03 -MS | REGS Metering Service | Cohort C + BUUK | bar: 2025-05-07; 2025-05-09
| TC04 - DS | REGS Data Service | Cohort C + BUUK | bar: 2025-05-07; 2025-05-09
MHHS-DEL2709 SITOPS_OPC004_OC_Change of Supplier & Change of Segment Determination | TC01 | Supplier LDSO REGS SMS SDS AMS | Cohort E + SSEN PAIRED with Cohort C | [28 empty] | Complex - Test - Approx 60 steps Need executing over out of hours (weekend). Will Probably req multiple runs. | bar: 2025-05-09; 2025-05-12 to 2025-05-13; 2025-05-16; 2025-05-19 to 2025-05-20; 2025-05-22 to 2025-05-23; 2025-05-27
| TC02 | Supplier LDSO REGS SMS SDS AMS | Cohort E + SSEN PAIRED with Cohort C | bar: 2025-05-07 to 2025-05-09
| TC03 | Supplier LDSO REGS SMS SDS ADS AMS EES | Cohort E + SSEN PAIRED with Cohort C | bar: 2025-05-07 to 2025-05-09
| TC04 | Supplier LDSO MSS REGS SMS AMS CSS EES | Cohort E + SSEN PAIRED with Cohort C | bar: 2025-05-09; 2025-05-12 to 2025-05-13; 2025-05-16; 2025-05-19 to 2025-05-20; 2025-05-22 to 2025-05-23; 2025-05-27
MHHS-DEL3313-SITOPS_OP007_COA_MTD | TC01 | Supplier Metering Service Data Service REGS ESS | Cohort F +SSEN PAIRED with Cohort B | [28 empty] | 80+ Steps- Potentially this may be descoped- Awaiting confirmation from Code Bodies. | bar: 2025-05-19 to 2025-05-22; 2025-05-27 to 2025-05-30
MHHS-DEL3319_SITOPS_OPC08_COS_MTD | TC01 | Supplier Metering Service Data Service LDSO REGS CSS | Cohort G +SSEN PAIRED with Cohort H | bar: 2025-05-19 to 2025-05-22; 2025-05-27 to 2025-05-30
MHHS-DEL3320_SITOPS_OPC09_RM_MTD | TC01 | Supplier Metering Service Data Service LDSO REGS CSS ESS DCC | Cohort H +SSEN PAIRED with Cohort G | bar: 2025-05-19 to 2025-05-22; 2025-05-27 to 2025-05-30
MHHS-DEL2715 SITOPS_SEC02 Sending IF with Invalid/revoked/expired certificate | TC01 - Invalid | Any Supplier | Cohort F | [28 empty] | 10 steps - Certs will need prepping before the test. | bar: 2025-05-12
| TC08 - Revoked | Any Data Service | Cohort F | bar: 2025-05-12
| TC15 - Expired | REGS | BUUK | bar: 2025-05-12
MHHS-DEL2716 SITOPS_SEC03 Interface resulting in Message/Event Replay Response | TC01 | Supplier LDSO | Cohort J + SSEN | [28 empty] | 8 Steps. | bar: 2025-05-06
| TC02 | Supplier LDSO | Cohort J + SSEN | bar: 2025-05-06
| TC03 | Supplier REGS | Cohort J + SSEN | bar: 2025-05-06
| TC04 | Supplier REGS | Cohort J + SSEN | bar: 2025-05-06
| TC05 | Supplier LDSO REGS Data Service Metering Service | Cohort J + SSEN | bar: 2025-05-06
| TC06 | Supplier LDSO REGS Data Service Metering Service | Cohort J + SSEN | bar: 2025-05-06
| TC07 | Supplier REGS LDSO Data Service | Cohort J + SSEN | bar: 2025-05-06
| TC08 | Supplier REGS LDSO Data Service | Cohort J + SSEN | bar: 2025-05-06
| TC09 | Supplier LDSO REGS Data Service Metering Service EES | Cohort J + SSEN | bar: 2025-05-06
| TC10 | Supplier LDSO REGS Data Service Metering Service EES | Cohort J + SSEN | bar: 2025-05-06
| TC11 | Supplier LDSO REGS Data Service Metering Service EES | Cohort J + SSEN | bar: 2025-05-06
| TC12 | Supplier LDSO REGS Data Service Metering Service EES | Cohort J + SSEN | bar: 2025-05-06
| TC13 | Supplier LDSO REGS Data Service Metering Service EES | Cohort J + SSEN | bar: 2025-05-06
| TC14 | Supplier LDSO REGS Data Service Metering Service EES | Cohort J + SSEN | bar: 2025-05-06
MHHS-DEL2718 SITOPS_SEC05 Message/Event Obfusication single message with multiple recipients | TC01 | Supplier REGS Metering Service | Cohort A | [28 empty] | 25 steps - but with some Effective date planning? [Prospective Appts only] | bar: 2025-05-15; 2025-05-19
| TC02 | Supplier REGS LDSO Metering Service | Cohort A +BUUK | bar: 2025-05-15; 2025-05-19
| TC03 | Supplier REGS Metering Service EES | Cohort A | bar: 2025-05-15; 2025-05-19
| TC04 | Supplier REGS Metering Service | Cohort A | bar: 2025-05-15; 2025-05-19
| TC05 | Supplier REGS Metering Srrvice Data Service | Cohort A | bar: 2025-05-15; 2025-05-19
| TC06 | Supplier REGS Metering Srrvice MDS | Cohort A | bar: 2025-05-15; 2025-05-19
| TC07 | Supplier REGS Data Service MDS | Cohort A | bar: 2025-05-15; 2025-05-19
| TC08 | Supplier REGS Data Service LDSO | Cohort A +SSEN | bar: 2025-05-15; 2025-05-19
| TC09 | REGS Supplier Data Service EES | Cohort A | bar: 2025-05-15; 2025-05-19
| TC10 | REGS Supplier Data Service Metering Service | Cohort A | bar: 2025-05-15; 2025-05-19
| TC11 | REGS Supplier Data Service MDS Metering Service | Cohort A | bar: 2025-05-15; 2025-05-19
| TC12 | REGS Supplier Data Service MDS | Cohort A | bar: 2025-05-15; 2025-05-19