## Schedule
SIT Operations Theme 3 Batch 2 | Description of Test Case | Test Support Roles | Cohort | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | Comments
MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successfully | TC01_Onboard | Any Service User - Expleo Only | Expleo Only | [28 empty] | Recommend starting this earlier - Does not need to wait for Theme 3 B1 window to open. | Assumptions/Dependncies/Est Notes Scheduled these test towards end of SIT OPS to allow additional time for any incomplete Dev Work. Where possible tried to keep Domain/Certs testing seperate from the more functional test cases, so these are mostly in week 2. DIP09 /DIP10 - These are quick fire tests that are only a few steps to complete, though there are a lot of variants. | bar: 2025-06-09 to 2025-06-13; 2025-06-16 to 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04
MHHS-DEL2701 SITOPS_DIP03_DIP participant in-life Certificate Renewal | TC01_DIP in-life Certificate Success | DIP Manager Any Service User (Kraken) | Cohort A | [28 empty] | Will need a service User approaching end of there cert life or editing existing one - Very Lenghty script TC01 - (140 Steps) | bar: 2025-06-16 to 2025-06-20; 2025-06-23 to 2025-06-27
| TC02_DIP in-life Certificate Fail | DIP Manager Any Service User (PDA) | Cohort A | bar: 2025-06-09 to 2025-06-13
MHHS-DEL2702 SITOPS_DIP04_DIP in-life Certificate Re-Issue | TC01_DIP in-life certificate re-issue | Any Service User Wheatley | Cohort B | bar: 2025-06-17 to 2025-06-18
MHHS-DEL2703 SITOPS_DIP05_DIP In-life changes to DIP User Privileges | TC01_DIP Participant User Admin role assigns privileges to a new user | Any Service User Callisto | Cohort C | bar: 2025-06-09
| TC02 - DIP Participant user Admin adds privileges to an existing user | Any Service User Ensek | Cohort C | bar: 2025-06-09
| TC03 - DIP Participant User Admin removes privileges from an existing user | Any Service User Ensek | Cohort C | bar: 2025-06-09
MHHS-DEL2704 SITOPS_DIP06_DIP Offboard of a Participant | TC01_Ofboard (Techniical) | Any Service User - Expleo Grp Ltd | Expleo Only | [28 empty] | Tech Solution only | bar: 2025-07-03
| TC02 Reverse Offboarding (Teechnical) | Any Service User | Expleo Only | bar: 2025-07-04
MHHS-DEL3236 SITOPS_DIP07_DIP In-Life qualification | TC01 Participant | Any Service User (IMSERV) REGS ISD | Cohort E | bar: 2025-06-16 to 2025-06-17
| TC02 Future Dated | Any Service User (Utiltia) REGS ESS | Cohort E | bar: 2025-06-16 to 2025-06-17
MHHS-DEL3237 SITOPS DIP08 - DIP Reporting/Audit | TC01_SUP | Any Supplier - (Sea Glass) | Cohort F | [28 empty] | Review in DITL Session - More than one partcipant may want to test this functionality in the DIP. | bar: 2025-06-10
| TC02_REGS | REGS | SSEN | bar: 2025-06-10
| TC03_DATA | Any Data Services (ADS/SDS) (TMA) | Cohort F | bar: 2025-06-10
| TC04_MET | Any Metering Service (IMSERV) | Cohort F | bar: 2025-06-10
| TC05_MDS | MDS | Helix | bar: 2025-06-10
| TC06_LDSO | LDSO | BUUK | bar: 2025-06-10
| TC07_DIP | DIP (Not Scripted Added as per Ind Review) | Cohort F | bar: 2025-06-10
MHHS-DEL3044 SITOPS DIP09 - Participant backoff and retry in the event of comms failure | TC01_Supp Success | Any Supplier ESG REGS | Cohort G | bar: 2025-06-11
| TC02_REGS Success | Any Supplier ESG REGS | Cohort G | bar: 2025-06-11
| TC03_DATA Success | Any Data Services (ADS/SDS) - (Energy Assets) Any Supplier - ESG | Cohort G | bar: 2025-06-11
| TC04_MET Success | Any Metering Service - ESG REGS | Cohort G | bar: 2025-06-11
| TC05_MDS | MDS Supplier ESG | Cohort G & Helix | bar: 2025-06-11
| TC06_LDSO | LDSO Supplier ESG | Cohort G + BUUK | bar: 2025-06-11
| TC07_SUP Fail | Any Supplier ESG | Cohort G | bar: 2025-06-11
| TC08_REGS Fail | REGS | Cohort G | bar: 2025-06-11
| TC09_Data Fail | Any Data Services (ADS/SDS) TMA | Cohort G | bar: 2025-06-11
| TC10_MET Fail | Any Metering Service ESG | Cohort G | bar: 2025-06-11
| TC11_MDS Fail | MDS | Helix | bar: 2025-06-11
| TC12_LDSO Fail | LDSO | SSEN | bar: 2025-06-11
MHHS-DEL3045 SITOPS DIP10 - Communication failure send IF messages | TC01_Data Services sends IF-021 where there is an outage with the Supplier's system | Supplier ESG Any Data Services (ADS/SDS) SMS | Cohort H | bar: 2025-06-12
| TC02_Metering Services sends IF-007 where there is an outage with the REG's system | REGS Any Metering Service ESG | Cohort H | bar: 2025-06-12
| TC03_REGS sends IF-001 where there is an outage with the Supplier's system | Supplier ESG REGS | Cohort H | bar: 2025-06-12
| TC04_Supplier sends IF-031 where there is an outage with the REG's system | Supplier ESG REGS | Cohort H | bar: 2025-06-12
| TC05_MDS sends IF-040 where there is an outage with the REG's system | REGS MDS | Cohort H & Helix | bar: 2025-06-12
| TC06_LDSO sends IF-020 where there is an outage with the Supplier's system | Any Supplier Kraken Any LDSO | Cohort B + BUUK | bar: 2025-06-12
| TC07_Data Services sends IF-021 where there is an outage with the DIP | Ant Data Service- SMS Supplier Kraken | Cohort B | bar: 2025-06-12
| TC08_Metering Services sends IF-007 where there is an outage with the DIP | REGS Any Metering Service Wheatley | Cohort B | bar: 2025-06-12
| TC09_REGS sends IF-001 where there is an outage with the DIP | Any Supplier Kraken REGS | Cohort B | bar: 2025-06-12
| TC10_Supplier sends IF-031 where there is an outage with the DIP | Any Supplier Kraken REGS | Cohort B | bar: 2025-06-12
| TC11_MDS sends IF-040 where there is an outage with the DIP | MDS REGS | Cohort B & Helix | bar: 2025-06-12
| TC12_LDSO sends IF-020 where there is an outage with the DIP | Any LDSO Any Supplier Kraken | Cohort B + SSEN | bar: 2025-06-12
MHHS-DEL3257 SITOPS_DIP11_DIP DNS_Domain Re-verification successful. | TC01_Success | Any Service User | Avanade | [28 empty] | Suggest Avanade do this - Only 1 step in script but Avandade have a guide to repeat te solution implememted OCT/Nov last year? | bar: 2025-06-18 to 2025-06-20
MHHS-DEL3234- SITOPS_BCDR01 Business Continuity and Disaster Recovery | TC01 | All Participants | Cohort - A-H | bar: 2025-06-16 to 2025-06-20; 2025-06-23 to 2025-06-27; 2025-06-30 to 2025-07-04