## Version History
Date | Author | Ver | Commentary
2025-03-18 | Steve Evans | 0.2 | Published foto Industry
2025-03-20 | Steve Evans | 0.3 | Corrections made to mapping for BR02 and BR06 to accounts for UMSDS only work with Cohort A,G and J.
2025-03-26 | Steve Evans | 0.4 | Amendments made to Allocation of TC due to Qualification statement

## Schedule
SIT Operations Theme 1 | Test Case ID | Role Supporting | Cohort | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | Comments
MHHS-DEL2624 SITOPS_BR01_Investigate and Resolve Issues | TC01 - SDS | SDS MDS LDSO SUP | All Cohorts + SSEN | [28 empty] | 10 Steps | bar: 2025-03-31; 2025-04-05 to 2025-04-06; 2025-04-12 to 2025-04-13; 2025-04-18 to 2025-04-21; 2025-04-26 to 2025-04-27
| TC02 - ADS | ADS MDS LDSO SUP | All Cohorts + SSEN | bar: 2025-03-31; 2025-04-05 to 2025-04-06; 2025-04-12 to 2025-04-13; 2025-04-18 to 2025-04-21; 2025-04-26 to 2025-04-27
| TC03 - UMSDS | UMSDS MDS LDSO SUP | Cohorts A,J and G + SSEN | bar: 2025-03-31; 2025-04-05 to 2025-04-06; 2025-04-12 to 2025-04-13; 2025-04-18 to 2025-04-21; 2025-04-26 to 2025-04-27
MHHS-DEL2165 SIT_OPS_BR02 - Manage Data on Receipt of Interfaces | TC01_ SDS | SDS LSS | All Cohorts + Helix | [28 empty] | 7 Steps | bar: 2025-04-01; 2025-04-05 to 2025-04-06; 2025-04-12 to 2025-04-13; 2025-04-19 to 2025-04-20; 2025-04-26 to 2025-04-27
| TC02 - ADS | ADS LSS | All Cohorts + Helix | bar: 2025-04-01
| TC03 - UMSDS | UMSDS LSS | Cohorts A,J and G + SSEN | bar: 2025-04-01
| TC04 - UMSO | UMSO REGS LDSO | Cohorts A,J and G + BUUK | bar: 2025-04-01
| TC05 - SMS | SMS REGS LSS | All Cohorts | bar: 2025-04-01
| TC06 - AMS | AMS LDSO REGS | All Cohorts BUUK | bar: 2025-04-01
| TC07 - Supplier | Supplier LSS | All Cohorts + Helix | bar: 2025-04-01
| TC08 - REGS | REGS LDSO MSS | All Cohorts & BUUK | bar: 2025-04-01
MHHS-DEL2616 SIT_OPS_BR03 - Manage previous customer deails | TC01 - ADS | ADS Supplier | All Cohorts | [28 empty] | 2 Steps | bar: 2025-04-02
| TC02 - SDS | SDS Supplier | All Cohorts | bar: 2025-04-02
| TC03 - SMS | SMS Supplier | All Cohorts | bar: 2025-04-02
| TC04 - AMS | AMS Supplier | All Cohorts | bar: 2025-04-02
MHHS-DEL2619 SITOPS_BR04 - Delete any active DSP schedule | TC01 | SUP REGS LDSO EES SDS MDS | All Cohorts +SSEN+Helix+ESS | [28 empty] | Potentially may be descoped - Wait confirmation from Code Bodies. Moved schedule to end of Theme 1 to allow more time for Code Bodies. | bar: 2025-04-16
MHHS-DEL2618 SITOPS_BR05 - Attempted Meter Read fail | TC01 | SDS MDR DCC Supplier | All Cohorts | [28 empty] | Potentially may be descoped - Wait confirmation from Code Bodies. Moved schedule to end of Theme 1 to allow more time for Code Bodies. | bar: 2025-04-16
MHHS-DEL2628 SIT_OPS_BR06 - Escalate where there is consuotion on De Energised MPAN | TC01 UMSDS | MDS UMSDS LSS | Cohorts A,J and G + Helix | [28 empty] | Simple Tests 10 Steps - But does req access to Service Management (Raise incident). | bar: 2025-04-02
| TC02 SDS | MDS SDS LSS | All Cohorts + Helix | bar: 2025-04-02
| TC03 ADS | MDS ADS LSS | All Cohorts + Helix | bar: 2025-04-02
MHHS-DEL2626 SITOPS_BR08 - Investigate Faulty Equipment | TC01 (5wd) | Supplier SMS | All Cohorts | [28 empty] | 5 Steps - There is 5WD and 15WD reference - Is this configurable? or is this real time wait step? | bar: 2025-04-04; 2025-04-07
| TC02 (15wd) | Supplier SMS | All Cohorts | bar: 2025-04-04; 2025-04-11
| TC03 (15wd) | Supplier SMS | All Cohorts | bar: 2025-04-04; 2025-04-11
| TC04 (5wd) | Supplier ADS | All Cohorts | bar: 2025-04-07; 2025-04-09
| TC05 (15wd) | Supplier ADS | All Cohorts | bar: 2025-04-07; 2025-04-14
| TC06 ((15wd) | Supplier ADS | All Cohorts | bar: 2025-04-07; 2025-04-14
| TC07 (New) (5wd) | Supplier SDS | All Cohorts | bar: 2025-04-07; 2025-04-11
MHHS-DEL2629 SIT_OPS_BR11 - Investigate MTD Issue | TC01 MSA | Supllier REGS AMS | All Cohorts +SSEN | [28 empty] | 20 steps. | bar: 2025-04-08 to 2025-04-09
| TC02 MSS | Supllier REGS SMS | All Cohorts +SSEN | bar: 2025-04-08 to 2025-04-09
MHHS-DEL2622 SITOPS_BR12 - Monitoring and Tracking | TC01 | SMS DIP REGS | All Cohorts | [28 empty] | Only 10 steps But requires switching off various channels to track SLA. Will require DIP support to switch off the channels. | bar: 2025-04-03 to 2025-04-04
| TC02 | Supplier DIP REGS | All Cohorts | bar: 2025-04-03 to 2025-04-04
| TC03 | LDSO DIP REGS Supplier | All Cohorts + BUUK | bar: 2025-04-03 to 2025-04-04
| TC04 | REGS DIP Data Service (Any) | All Cohorts | bar: 2025-04-03 to 2025-04-04
| TC05 | SDS DIP LSS | All Cohorts | bar: 2025-04-03 to 2025-04-04
| TC06 | AMS DIP REGS | All Cohorts | bar: 2025-04-03 to 2025-04-04
| TC07 | ADS DIP REGS | All Cohorts | bar: 2025-04-07 to 2025-04-08
| TC08 | USMDS LSS | Cohorts A,J and G + Helix | bar: 2025-04-07 to 2025-04-08
| TC09 | UMSO DIP REGS | UMSO | bar: 2025-04-07 to 2025-04-08
MHHS-DEL2617 SITOPS_BR15 - Maintain OffPeak Declaration | TC01 | Supplier SDS | All Cohorts | [28 empty] | Only 10 steps but Pre Req may be complicated - Supplier, for switched load tariff sites, with a smart meter. May need some useage history? | bar: 2025-04-14 to 2025-04-15
MHHS-DEL2623 SITOPS_BR16 - DIP Platform Error Messge | TC01 | Supplier | All Cohorts | [28 empty] | 5 steps. | bar: 2025-04-14 to 2025-04-15
| TC02 | Data Service (ADS) | All Cohorts | bar: 2025-04-14 to 2025-04-15
| TC03 | Metering Service (MSA) | All Cohorts | bar: 2025-04-14 to 2025-04-15
| TC04 | REGS | REGS Only | bar: 2025-04-14 to 2025-04-15
| TC05 | LDSO | SSEN Only | bar: 2025-04-10
| TC06 | Supplier MDS | All Cohorts | bar: 2025-04-10
| TC07 | Data Service (SDS) MDS | All Cohorts + Helix | bar: 2025-04-10
| TC08 | Metering Service (MSS) REGS | All Cohorts | bar: 2025-04-10
| TC09 | REGS Supplier | All Cohorts | bar: 2025-04-10
| TC10 | LDSO REGS | SSEN Only | bar: 2025-04-10
MHHS-DEL2620 SITOPS_BR17 - Load Shape run information | TC01 | LSS | Helix Only | [28 empty] | 3 Steps | bar: 2025-04-11
MHHS-DEL2621 SITOPS_BR18 - VAS run number setting and date and time storage | TC01 | VAS | Helix Only | [28 empty] | 3 Steps | bar: 2025-04-11
MHHS-DEL2637 SITOPS_BR21 - MPRS in SSEN in target infrastructure | TC01 | SSEN Supplier | All Cohorts +SSEN | [28 empty] | 3 Steps | bar: 2025-03-31
MHHS-DEL2634 SITOPS_BR23 - LSS provides data on request | TC01 | MDS LSS | Helix Only | [28 empty] | 3 Steps | bar: 2025-04-11
MHHS-DEL2635 SITOPS_BR24 - LSS Validation Failure investigation | TC01 | LSS | Helix Only | [28 empty] | 3 Steps | bar: 2025-04-11
MHHS-DEL2639 SITOPS_BR26 - VAS Capture and Store Data | TC01 | VAS | Helix Only | [28 empty] | 3 Steps | bar: 2025-04-11