## Consolidated Tab
Organisation: | Various
Constituency:
Date: | May 2023 Consultation Review | DEL1169 - Systems Integration Testing (SIT) Component Integration Testing (CIT) Test Scenarios Consolidated Comments Log
Anonymised:
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | St Clements |  | 16 & 23 & 30 & 31 (IF-006 < SUPC.SSD) | B033 DI-057 & B039 DI-058 < SUPC.SSD is an invalid scenario for meter install, meter exchange and meter removal, so the message would reject as it is not within the supplier period of ownership (period of registration). DI-979 = 'R' REG1019 - "should be within Metering Service Period of Ownership" | Reject | Reviewer accepted that this was raised in error; the scenarios are valid against the Interface Catalogue | Recommend close
2 | OVO |  | 2 | Initial registration data are new entry into supplier, do suppliers are aware of these data what's coming in (allocated well in advance) | Acknowledged | The Test Data Approach and Plan will be the channel for addressing this | Recommend close
3 | OVO |  | 1 and 3 | The data requirements for this test are going to require participants to make up the data or do additional data prep for these tests outside of the data cut | Acknowledged | The Test Data Approach and Plan will be the channel for addressing this | Recommend close
4 | OVO |  | General | Assume that these are not actual CIT scenarios, CIT expect all IF & PUB transactions to be sent and receive, will there be additional test set will be published for CIT | Reject | The document elaborates the sending scenarios (event codes, data conditions) which also correspond to the receiving context, which is why they receiving scenarios are represented in the summary format. Note that the test cases will be detailed for both the sending and the receiving scenarios. | Recommend close
5 | OVO |  | General | Are the scenarios mandatory, regarding Supplier functionality, e.g. if supplier does not have Smart segment are these tests needed in CIT. or do supplier as a participant to follow any process to define tests are not in scope | Acknowledged | Will need to validate with the code bodies the requirements for qualification and ratify any scope exclusions related to a participant's context | Recommend close
6 | OVO |  | Notes on Scenarios | Suggests full business orchestration needs to be in place for certain scenarios (e.g. IF-05, IF-06), can we have a list of these scenarios for all parties. Clarify this comment as contradictory notes have been stated in SITWG/bi-laterals with the programme, that no business orchestration is required in CIT | Reject | The Notes on Scenarios reflect the current wording in the SIT Test Approach and Plan. There should be no inference that full business orchestration is required for CIT. | Recommend close
7 | OVO |  | 4 and 5 | Just like comment 4 above - This flow states its optional and is a bi-lateral agreement for Comms Hub information, as per DES-138, what happens if the test participant is not developing this interface, can this test be omitted | Acknowledged | We need to establish the context for each participant and ratify any exclusions with the code bodies | Recommend close
8 | OVO |  | General | If all scenarios are mandatory regarding comment 4, or there is a lack of data for participants to complete CIT, are we being granted time and a route to amend MPxNs and inform central parties of these changes? | Acknowledged | Yes. During allocation of MPANs for tests, the SI will switch MPANs from large participants. The PPs will have time to load the changes to the system before test commencing. The Programme is currently considering the option of using manufactured data instead of live data for CIT tests. The Programme will come back with a position on this shortly. | Recommend close
9 | OVO |  | General | Data prep and data usage is not being taken into consideration for SIT Functional, due to the specific of each test case could cause participants to use all data for a certain test in CIT | Acknowledged | The Programme is currently considering the option of using manufactured data instead of live data for CIT tests. This should be followed up in the Test Data Approach & Plan discussions. | Recommend close
10 | OVO |  | General | Is CIT required back end systems(CRM…etc) to be involved or just an initial integration to prove connection with industry | Acknowledged | Participants are expected to be ready to send and receive messages to and from DIP via interfaces for CIT | Recommend close
11 | OVO |  | 6 to 10 | Can you confirm if these tests doesn’t required supplier to play any role in the testing? I believe supplier roles covered in 16 to 44? | Accept | That is correct | Recommend close
12 | Avanade |  | 104103 | Event Code [SSC],[ProfileClass] strike out from the MHHSP-138Interface Catalogue but its mention in the SIT CIT Test Scenarios - IF025 | Reject | This is up to date with the Interim Release 2 baseline of the Interface Catalogue | Recommend close
13 | Avanade |  | 109110 | Event Code [SSC],[ProfileClass] strike out from the MHHSP-138Interface Catalogue but its mention in the SIT CIT Test Scenarios - IF0026 | Reject | This is up to date with the Interim Release 2 baseline of the Interface Catalogue | Recommend close
14 | St Clements |  | Notes on Scenarios | Within the SIT Scoping Document it states:- " the routing exercised will depend not only on the IF message but also on its Event Code and where appropriate on data within the message" From this, we understand that where the event code and data on message change the routing, they would be tested to prove the routing. We believe the intention of CIT is to prove end points and that messages can be sent and received by parties and routed correct as per Always / Primary / Secondary, but not every combination especially the testing of each event code where the routing is the same to the same parties - e.g. IF-001 [ChangeofSupply] & [InitialRegistration] & IF-005 & IF-006 [MeterInstall],[MeterExchange] or IF-050 etc? The CIT testing is to test the sending and receiving and routing of each message. The data and event codes would be tested as part of SIT Functional. | Reject | In CIT we also want to verify the messages can be generated by participant systems. If this functionality is not fully complete and tested for related and import/export MPANs, we can accept the data being place on the MPRS queue. We would need to see rigour applied in PIT, and in the work-off plan for deferred scope, in the run up to SIT Functional. | Recommend close
15 | St Clements |  | Notes on Scenarios | "However a Sender which has passed all of its own tests will also be required to send additional messages to test the DIP routing". The DIP routing configuration functionality should be fully tested as part of DIP PIT and should not wait until CIT to test the functionality. The routing functionality will then be tested end to end within in SIT Functional testing. To test it to this extent in CIT is excessive, especially with the restricted timescales. | Acknowledged | As long as we can demonstrate successful coverage of all the event codes prior to SIT functional (e.g. in PIT) we would be happy with enough coverage in CIT that assures DIP IF handling and message routing. | Recommend close
16 | St Clements |  | REGS scenarios | St Clements have agreed to test the following scenarios as this covers the interaction with each participant: IF-025 [ConsentGranularity] & IF-026 to test Supplier Interaction IF-034 [SDS-MDRUpdate] & IF-035 to test Data Service interaction IF-007 [EnergisationStatusChange] & IF008 to test Metering Service Interaction | Reject | All messages related to your role are critical and in-scope for CIT; as this functionality is central to the design. | Recommend close
17 | St Clements |  | REGS scenarios | The MPRS code for all messages will not be fully developed until the start of SIT - and is being delivered in 2 sprints. Therefore the schedule for this testing will have to be developed with regards to the code availability as the Registration Service is core to the large majority of these tests. | Acknowledged | As per previous discussions, the CIT interface test schedule will be aligned with your incremental code drops. We will need to manage this as a risk. | Recommend close
18 | St Clements |  | Test schedule | As the registration service is core to most scenarios, will there be duplication of effort and repeating of tests as parties become involved in later intervals, or would the routing of outbound messages triggered be held until they are involved? | Reject | for CIT we will be establishing mechanisms to support point to point DIP integration testing, on an individual participant basis, independent of other parties | Recommend close
19 | St Clements |  | Test schedule | Will defects be fixed throughout CIT? and will there be retesting time? If DIP is delayed/blocked, will the timelines of all others be moved, as DIP is the core of all CIT processing? This is a large number of tests, this full set is not feasible within the timescales available, if there are issues/defects/blocked tests. | Reject | Each phase of testing is designed to progressively reduce the risk of blocking issues emerging in subsequent phases; PIT is designed to de-risk CIT and we will be seeking to assure that PIT is conducted so as to be fit for purpose and effective, to minimise blocking defects in CIT that have cross-party impact. The risk cannot be eliminated, the Test Strategy and approach provides quality gates for governing upstream quality; the defect management approach and cross-capability mobilisation are designed to deal with in-phase defects. | Recommend close
20 | St Clements |  | all | How will the secondary routing data be set up in CIT in DIP - for appointments and linked MPANs? | Acknowledged | We are indeed looking at approaches to this and will provide further clarity in the Test Cases and the Test Data Approach | Recommend close
21 | St Clements |  | Receiving Summary by Role | There is no REGS set within Receiving Summary tab | Actioned | Agreed, incorporated as part of 5.2 uplift. | Recommend close
22 | St Clements |  | 17 (IF-006 Meter Install) | ADSO secondary routing is included twice in list | Actioned | Duplicate ADSO removed as part of 5.2 uplift. | Recommend close
23 | St Clements |  | 43 (IF-006 Meter install) | This scenario is covered by the multitude of IF-006 meter install tests between 16 to 22 | Reject | Not a duplicate. This is a happy path with no data condition | Recommend close
24 | St Clements |  | 48 (IF-006) | There are 2 x scenario 48s | Actioned | Resolved as part of 5.2 uplift. | Recommend close
25 | St Clements |  | 75 to 77 (IF-019) | Related IF-019 are now routed to REGS, not LDSO | Actioned | Resolved as part of 5.2 uplift. | Recommend close
26 | St Clements |  | 100, 103 & 104 (IF-025) | An IF-026 is triggered from the receipt of an IF-025, so to trigger IF-026 for different segments (where routing is different), it is necessary to receive IF-025 for the same segments | Acknowledged | Correct, as we are seeking to enable autonomous point to point integration testing, we will want to decouple any "round trip" dependencies. So we will manually trigger messages as required. | Recommend close
27 | St Clements |  | 109 / 110 & 103/104 (IF-025 & IF-026) | SSC & PC has been replaced by 'SSC and PC' so these tests are unnecessary | Actioned | Resolved as part of 5.2 uplift. | Recommend close
28 | St Clements |  | 111 (IF-026 - SSC and PC) | SMART segments would have null SSC and PC | Actioned | Resolved as part of 5.2 uplift. | Recommend close
29 | St Clements |  | 112 to 117 (IF-026 =R) | Testing of Rejection scenarios should not be routed to secondary routing - only SUPS as primary routing | Actioned | Resolved as part of 5.2 uplift. | Recommend close
30 | St Clements |  | 129 to 145 (IF-034) | An IF-035 is triggered from the receipt of an IF-034, so if the intention is to trigger IF-035, it is necessary to test IF-034 and IF-035 for the same segments | Acknowledged | Correct, as we are seeking to enable autonomous point to point integration testing, we will want to decouple any "round trip" dependencies. So we will manually trigger messages as required. | Recommend close
31 | St Clements |  | 142 / 143 (IF-035 - SDS-MDR Outcome) | What is the difference between 142 & 143? Should 142 be [DCC-MDROutcome] - with primary routing SDSS only? | Reject | The distinction is in the data condition applicable to 143 | Recommend close
32 | St Clements |  | 193 (IF-047 ISD) | Initial load of ISD would have to be loaded prior to CIT tests | Acknowledged | This is correct. We will need to carefully manage test execution dependencies. | Recommend close
33 | St Clements |  | 194 (IF-050 - MPAN creation) | MPANs cannot be related at creation, or import/export linked | Acknowledged | Column Q in V5.2.1 CIT Scenarios details 'Include one linked Export MPAN and at least 2 Related MPANs.' Interface cat states - Related/Linked MPANs cannot be grouped together at the point of MPAN creation. Grouping will always occur as a separate action after MPAN creation which will be notified on PUB-020. We will update the notes field accordingly. | Recommend close
34 | IPA |  | General | The Test Data is not present across all the scenarios. Does this mean there are no data requirements to test these scenarios? | Acknowledged | The Test Cases will be more explicit about the test data applicable to the test conditions. | Recommend close
35 | IPA |  | General | Expected Output is missing for the Test Scenarios | Acknowledged | For CIT we are testing send and receive integration via DIP; more details of granular validation outcomes will be included in the forthcoming test cases | Recommend close
36 | IPA |  | General | For the scenarios where the participants expect a response back from the DIP or the central systems, that is not clearly stated in the scenarios | Reject | The existing E2E001 End-to-End Solution Architecture, combined to with test data defined in the forthcoming test cases, specifies the relevant details. | Recommend close
37 | IPA |  | General | For certain Scenarios (e.g. - MHHSP-IF-019, MHHSP-IF-021,MHHSP-IF-022, etc.) can we have the details noted under the Data Conditions and provide a sample message that is expected from the participants? | Reject | Please refer to DES138; includes sample JSON files, including mandatory fields. | Recommend close
38 | IPA |  | General | Do we have a RTTM in place to ensure the coverage is 100% and no scenarios are missed? | Acknowledged | Yes, we are developing a comprehensive RTTM for SIT functional and non-functional to track and assure coverage | Recommend close
39 | Engie |  | N/A | Test scenarios are not referenced to business processes. | Acknowledged | The SIT Functional scenarios will provide full traceability to the business processes, interfaces and method statements | Recommend close
40 | Engie |  | IF-004 message | The IF-004 is an optional flow. | Reject | We are looking to mitigate any risks going into SIT Functional and beyond | Recommend close
41 | BU-UK |  | 149 | We are currently in discussion with the program regarding Design Issue DIN-258. There a number of Market Messages which we would not wish to receive as we believe this is a flaw in the design as this data is easily extractable from our MPRS database. As a result should this change it will affect this CIT scenario making is superfluous. If the purpose of CIT is to check that we can receive these messages we can test that and potentially on behalf of other IDNO's however should the DIN change this will have an impact on this scenario. | Acknowledged | If the DIN resolution results in a design change we will update the test assets, as per the standard process of maintaining consistency with the design baseline. | Recommend close
42 | Morrisonds |  | #169 through #173 | These CIT references are specific to Sender = ADSS, however they appear to be tagged in both the Smart Segment and the Advanced Segment. Is this simply to reflect the fact that the equivalent test is also to be executed for Sender = SDSS (i.e. refs #174 through #178)? | Acknowledged | The two variants will be expressed as distinct test cases in the forthcoming CIT test cases documentation. | Recommend close
43 | Morrisonds |  | #174 through #178 | These CIT references are specific to Sender = SDSS, however they appear to be tagged in both the Smart Segment and the Advanced Segment. Is this simply to reflect the fact that the equivalent test is also to be executed for Sender = ADSS (i.e. refs #169 through #173)? | Acknowledged | The two variants will be expressed as distinct test cases in the forthcoming CIT test cases documentation. | Recommend close
44 | Morrisonds |  | #86 and #89 | Scenarios are around Reactive Power event code for ADS and SDS - understood that Reactive Power only applied to Advanced Sites? | Accept | This has been corrected in the latest update to the scenarios | Recommend close
45 | Participant #1 |  | 1 and 3 | The data requirements for this test are going to require participants to make up the data or do additional data prep for these tests outside of the data cut | Acknowledged | The additional data prep for these tests should not be significant. The functional processing of the messages will be covered in SIT Functional. For CIT, the objective is to guarantee the messages are complete and accurate. | Recommend close
46 | Participant #1 |  | General | Are the scenarios mandatory, regarding Supplier functionality, e.g. if supplier does not have Smart segment are these tests needed in CIT | Acknowledged | Will need to validate with the code bodies the requirements for qualification and ratify any scope exclusions related to a participant's context | Recommend close
47 | Participant #1 |  | Notes on Scenarios | Suggests full business orchestration needs to be in place for certain scenarios (e.g. IF-05, IF-06), can we have a list of these scenarios for all parties. Clarify this comment as contradictory notes have been stated in SITWG/bi-laterals with the programme, that no business orchestration is required in CIT | Reject | The Notes on Scenarios reflect the current wording in the SIT Test Approach and Plan. There should be no inference that full business orchestration is required for CIT. | Recommend close
48 | Participant #1 |  | 4 and 5 | This flow states its optional and is a bi-lateral agreement for Comms Hub information, as per DES-138, what happens if the test participant is not developing this interface, can this test be omitted | Acknowledged | Will need to validate with the code bodies the requirements for qualification and ratify any scope exclusions related to a participant's context. | Recommend close
49 | Participant #1 |  | General | If all scenarios are mandatory regarding comment 2, or there is a lack of data for participants to complete CIT, are we being granted time and a route to amend MPxNs and inform central parties of these changes? | Acknowledged | Yes. During allocation of MPANs for tests, the SI will switch MPANs from large participants. The PPs will have time to load the changes to the system before test commencing. The Programme is currently considering the option of using manufactured data instead of live data for CIT tests. The Programme will come back with a position on this shortly. | Recommend close
50 | Participant #1 |  | General | Data prep and data usage is not being taken into consideration for SIT Functional, due to the specific of each test case could cause participants to use all data for a certain test in CIT | Reject | The Programme is currently considering the option of using manufactured data instead of live data for CIT tests. The Test Data Approach & Plan channel will be the forum for addressing challenges in this area. | Recommend close
51 | Participant #1 |  | General | Document needed to be issued sooner to allow participants view to enter CIT and SIT earlier than current timescales. We have been asking for this documentation since R2 consultation. | Acknowledged | If the documentation issued conflicts with earlier working assumptions or conclusions, we will work collaboratively with parties to make adjustments where possible. | Recommend close
52 | Opus Energy |  | Multiple sending scenarios for Supplier | The sheet generated for Supplier as sender has primary routing to SDSS, ADSS, UDSS. Shouldn’t they be SDSC, ADSC as they are receiving the flow not sending them as the supplier is sending these? | Actioned | Resolved as part of 5.2 uplift. | Recommend close
53 | Opus Energy |  | Receiving Summary by Role | For SUP, IF-004 is mentioned under Primary routing but in the latest Interface Catalogue document v5.1.1 SUPS is mentioned under 'Secondary Routing' in IF-004 sheet | Actioned | Resolved as part of 5.2 uplift. | Recommend close
54 | Opus Energy |  | Receiving Summary by Role | FOR SUP, IF-008 is missing. In the latest Interface catalogue 5.1.1 SUPC,SUPI is mentioned under 'Secondary Routing' for IF-008. | Actioned | Resolved as part of 5.2 uplift. | Recommend close
55 | Opus Energy |  | SUP sending scenario IF-025 | The sheet generated for Supplier as sender has IF -025 scenarios for SCC and Profile class but these two scenarios are removed (strikedthrough) in the latest Interface Catalogue v 5.1.1 | Actioned | Resolved as part of 5.2 uplift. | Recommend close
56 | Opus Energy |  | Receiving Summary by Role | FOR SUP, IF-036 is missing. In the latest Interface catalogue 5.1.1 SUPC is mentioned under 'Secondary Routing' for IF-036. | Actioned | Resolved as part of 5.2 uplift. | Recommend close
57 | Opus Energy |  | Receiving Summary by Role | FOR SUP, IF-047 is missing. In the latest Interface catalogue 5.1.1 'All Roles' is mentioned under 'Always routing' for IF-036. | Actioned | Resolved as part of 5.2 uplift. | Recommend close
58 | Drax |  | Sending Scenarios > MHHSP-IF-001 > Change of Supplier | The notes cover import, export and related. Will there not be a single MPAN or multi un-related/linked CoS? I see it for initial regi (which cannot gained as related), but would suggest unrelated/linked CoS as well. | Acknowledged | From a risk-based perspective we believe these are sufficient for CIT, however there will be additional variants covered in SIT functional | Recommend close
59 | Drax |  | Sending Scenarios > General Comment | It would be easier to read if the scenarios were grouped by type and IF. | Acknowledged | Scenarios can be filtered by type and IF. | Recommend close
60 | Drax |  | General Overall comment | It will be easier to review in conjunction with the test cases. It is a bit hard to read through, and might make sense to split it up by role. So for example as a supplier I see the scenarios specific to our role. Whether we are sending or receiving. | Acknowledged | Acknowledged. We look forward to your feedback on the test cases when they are issued and whether they provide a clearer view of how each role can conduct the tests. | Recommend close
61 | Drax |  | General Overall comment | For CIT, assuming messages are just being sent and received without any other system/data involvement. e.g. does the data changed in CIT need to impact the databases moving into SIT? Because if so, then there needs to be more of a link up here, because currently it is just a scenario per message, rather than a scenario that might cover multiple messages. And worksheet 'Notes on Scenarios' seems to imply they are E2E scenarios (example noted with IF 5 and 6), but the scenarios are they currently are don't make that clear. | Acknowledged | CIT will be conducted between the SI Test Team and the organisation responsible for each component being integrated, with messages being exchanged between special end-points set up by the SI Test Team and the service being integrated. Each role/service will be expected to receive and to send one example of each IF/PUB message relevant to it in order for that service to pass SIT CIT. This means that where the test is that a service receives a PUB message, the SI Test Team will initiate that test by sending in the relevant message from a specially created end-point. For service message receipt, the service is expected to pass the test when it has successfully received a single IF message. Where the test involves a service generating an IF then it is up to that service to generate a message appropriately, triggering it from the same point in their service as would be the case in the E2E business process (i.e. not just from their adaptor layer), this is important as it will build confidence prior to the E2E business process testing in the subsequent SIT Functional Test stage, note that as full E2E testing won't be possible at the CIT stage it is expected that the participant will use the same method/mechanism to generate the IF message in isolation that was used within their PIT testing. Where a service responds to a PUB with the generation of an IF (for example IF-005 being sent by a Metering Service then coming to the Registration Service as PUB-005 and the Registration Service responding by producing a corresponding IF-006), in this case, the test would be triggered by the SI Test Team sending an IF-005. | Recommend close
62 | UK Power Networks |  | 29 & 25 | IF-006,Same scenario/Duplication | Actioned | Resolved as part of 5.2 uplift. | Recommend close
63 | UK Power Networks |  | 22 | IF-006,Other variants for B039 DI-058 for Meter Install is not covered | Reject | The coverage is sufficient to prove component integration | Recommend close
64 | UK Power Networks |  | 93 | IF-022,Secondary recipient is blank and doesn't have LDSO though DES138 interface catalogue has LDSO as secondary recipient | Reject | The routing is consistent with that specified in the latest version of the MHHSP-DES138-Interface Catalogue | Recommend close
65 | UK Power Networks |  | 94 | IF-023,Secondary recipient is blank and doesn't have LDSO though DES138 interface catalogue has LDSO as secondary recipient | Reject | The routing is consistent with that specified in the latest version of the MHHSP-DES138-Interface Catalogue | Recommend close
66 | UK Power Networks |  | All scenario Ref# | Scenarios are based on event codes and doesn't cover different combinations and permutations for each event code, data item and market segment | Reject | In the context of CIT we're varying event codes purely with the objective of exercising DIP routing. Combinations and permutations for each event code, data item and market segment will be tested during SIT Functional phase. | Recommend close
67 | UK Power Networks |  | 188 | IF-044 test scenarios doesn't cover 'Market segment indicator' for different values- S,A,U | Actioned | We have included scenarios that cover all segments in the latest update | Recommend close
68 | UK Power Networks |  | 187 | IF-043 test scenarios doesn't cover different values and mandatory fields within B023- 'MPAN Connection type' like 'Connection type indicator' etc | Reject | Test Cases will be issued for review that elaborate on coverage of the mandatory fields | Recommend close
69 | UK Power Networks |  | 146, 147 | For IF-036,B014 & B015 covering 'meter service details' and 'data service details' are not included as test scenarios/test cases | Reject | Test Cases will be issued for review that elaborate on coverage of the mandatory fields | Recommend close
70 | UK Power Networks |  | 84,86,87,89,90,91,92 | IF-021, B023-Connection type, B045-MQID,B046-UTC settlement day,B047-UTC settlement period data | Reject | Test Cases will be issued for review that elaborate on coverage of the mandatory fields | Recommend close
71 | UK Power Networks |  |  | No scenario covering IF-003 for Migration | Reject | We have confirmed with the design team that The IF-003 is to be introduced in Interim Release 3 of the design. Test scenarios and test cases will impact assessed and updated in line with the design changes when they are issued. | Recommend close
72 | Spenergy networks |  | MHHSP-IF-005 Ref 6 to 15 inclusive | These scenarios relate to metering and in the comments it states that UMS should be included. There are no meters installed on an UMS site and we see no requirement for inclusion in these test. UMSO is not identified in the segment to be tested. | Reject | There is currently no reference to UMS | Recommend close
73 | Spenergy networks |  | MHHSP-IF-007 Ref 53 to 56 inclusive) | Currently (in practice) the Energisation is updated by the LDSO (not UMSO) to Registration service. There is no ability for the UMSO role code to send a D0139 (update to energisation) flow. | Accept | Thanks for calling this out. We are in touch with the design team to monitor this change and will update in line with revisions to the DES138 Interface Catalogue. | Recommend close
74 | CGI |  | All Events codes with whitespace, e.g. 16, 17, 20, 21, 117 etc etc This is not an exhaustive list | Event Codes in DES138 do not have any white space. | Actioned | Resolved as part of 5.2 uplift. | Recommend close
75 | CGI |  | 112, 114, 115, 116, 117 | DES138 states "Any Event & [DI-979] = "R"" is routed to SUPS (primary only) | Actioned | Resolved as part of 5.2 uplift. | Recommend close
76 | CGI |  | 109, 110, 115, 116 | DES138 v5.1.1 has removed event codes [SSC] and [ProfileClass] | Actioned | Resolved as part of 5.2 uplift. | Recommend close
77 | CGI |  | 183-186 | Should these be routed to ADSC, these are smart specific | Acknowledged | Impacts scenario Refs 183-185. The scenarios align with DES138-Interface Catalogue v5.2.1. We will pass your comments on to the design team so that they can log any errors in the DES138 as DINs and apply updates. Once these are reflected in the DES-138 we will apply updates to the CIT scenarios. | Recommend close
78 | CGI |  | 179-182 | Should these be routed to SDSC, these are Advanced specific | Actioned | This has been resolved in the latest issue of the CIT scenarios | Recommend close
79 | CGI |  | 191 | Secondary routing incorrect as per DES138, SDS should not receive this | Actioned | Resolved as part of 5.2 uplift. | Recommend close
80 | ENWL |  | General | Subject to Design decisions yet to be confirmed the sending and receipt of DIP messages between DNO to DNO roles (REGS, LDSO, UMSO) may be optional where DNO's already have existing internal systems interfaces and/or business processes sharing the same information. | Acknowledged | If the DIN resolutions results in design changes, we will update the test assets as per the standard process of maintaining consistency with the design baseline. | Recommend close
81 | Wheatley Solutions |  | 146, 147 | IF/PUB-036 is not included in the set of messages that metering service will need to receive (on the Receiving Summary by Role tab) but is listed as a message that is sent to the MS (e.g. in refs 146 and 147). | Actioned | Resolved as part of 5.2 uplift. | Recommend close
82 | Wheatley Solutions |  | 156 - 161 | IF/PUB-039 is not included in the set of messages that metering service will need to receive (on the Receiving Summary by Role tab) but is listed as a message that is sent to the MS (e.g. in refs 156 through to 161). | Actioned | Resolved as part of 5.2 uplift. | Recommend close
83 | Wheatley Solutions |  | 69 | IF/PUB-018 is not included in the set of messages that metering service will need to receive (on the Receiving Summary by Role tab) but is listed as a message that is sent to the MS (e.g. in refs 69). | Actioned | Resolved as part of 5.2 uplift. | Recommend close
84 | Wheatley Solutions |  | 5 | IF/PUB-004 is listed as an item that should be received by the MS, but this is not listed in the Interface Catalogue or End-to-end architecture document. | Reject | IF/PUB-004 is present in the latest MHHSP-DES138-Interface Catalogue; "Optional interface to allow passing of Comms Hub information" | Recommend close
86 | IH |  | 86 | We were under the impression that SDS would not be required to collect Reactive Data, we can see no requirement within any of the Programme Artifacts to date | Reject | We are unable to find an entry with this mapping; this may have been resolved in the uplift rounds since 5.0. | Recommend close
87 | CF |  | Missing | Think these tests might be missing as a receiving scenario from Data Services IF-008 (Reg Service notification of Change of Energisation Status) IF-036 (Reg Service Formal Confirmation of Appointment and MTDs) IF-037 (Reg Service notification of de-appointment) | Actioned | Resolved as part of 5.2 uplift. | Recommend close
88 | Participants #2 |  | ALL | Is the DIP Simulator intended to be used as part of these tests? If so, please confirm what version of the DIP simulator will be used in testing these components | Acknowledged | We are exploring whether the DIP Simulator can assist with removing dependency on a third party where a participant is executing a point to point CIT test. We do not yet have a definitive answer on this, or whether enhancements will need to be made to the DIP. We will keep participants posted via the working group. | Recommend close
89 | Participants #2 |  | ALL | Are ECS external catalogue reports in scope for these tests? E.g. MHHS-REP-002, MHHS-REP-002A, MHHS-REP-003, MHHS-REP-004, MHHS-REP-006, MHHS-REP-007, MHHS-REP-008, MHHS-REP-009, ELEX-REP-005, ELEX-REP-020 Our current assumption is that these are out of scope for SIT testing | Acknowledged | These reports are in-scope for SIT Functional testing and are covered in the defined SIT Functional test scenarios | Recommend close
90 | Participants #2 |  | ALL | What is the relationship, if any, between MHHS-DEL11167 and MHHS-DEL1177? | Acknowledged | We've looked at the document tracker and not been able to identify these document references; perhaps this is a typo? Could you provide links? As far as we can tell there is no relationship between the closest matches we could find (1167 Amended Design Artefacts Comment Log, 1177 9th May CWG Headline report. | Recommend close
91 | Participants #2 |  | Sending Scenarios - MHHSP-IF-022 LSS test scenarios (LSS Period Data & LSS Totals Data) | Is there a rationale for splitting the test cases? Our understanding is that one of these test cases could cover the other market segments. | Acknowledged | The rationale is to verify the correct DIP routing for all the variants specified | Recommend close
92 | Participants #2 |  | Sending Scenarios - MHHSP-IF-040 Annual Consumption | Could this scenario be split out, as the current form could be harder to pull out the data for. | Acknowledged | Data challenges can be raised in the Test Data Approach and Plan context. A practical solution may be available from the approach and actions being formulated for test data. | Recommend close
93 | Participants #2 |  | Sending Scenarios - MHHSP-IF-047 ISD | Could you confirm what the 12 test cases would cover? | Acknowledged | The test cases will demonstrate successful routing of the ISD file to All participants. The CIT test cases will elaborate further. | Recommend close
94 | Participants #2 |  | Sending Scenarios - MHHSP-IF-047 ISD | What is the expectation of data to be received for IF-047? Please clarify what will be expected to be in this file? What test cases will be created for this interface? | Acknowledged | For data content please refer to DES138 interface catalogue for details; additionally, we can confirm the format for the ISD will be a csv file. We have identified an equivalence class of tests that will deliver coverage of the routing to "All". These will be specified in the forthcoming CIT test cases. | Recommend close