## Consolidated Feedback
| Organisation: | Various |  | MHHS-DEL1334 Overarching Test Data Approach & Plan Comments Log (This Artefact)
| Constituency: | Various
| Date: | 2023-06-23 |  | Comments on artefact ''MHHS-DEL813_Overarching_Test_Data_Approach_&_Plan_v0.7"
| Anonymised: | Where requested
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
|  | Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
| Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
UPN | 1 | RECCo | 6 | 2 | Does the approach still deliver a common and fully aligned test data set for use in the industry-wide test phase if there are to be additional/later data cuts for Qualification? | No document changes required | The first data cut will align the SIT Participants only. Those are all participants going through PIT, SIT CIT, SIT Functional, SIT Non-Functional and Migration tests. They should be fully aligned during SIT and Migration. The Qualification environment won't use the same SIT Test Environments and will have an additional Data Cut which will align all the non-SIT participants. The scope of the Qualification tests are yet to be defined. After that, a Qualification Test Data Plan will be elaborated. | Proposed to close for this document review
UPN | 2 | RECCo | 6 | 2 | The Qualification preparation phase for non-SIT LDSOs is 29 Jan to 5 July 24 and the Qualification Testing activity begins on 15 July 24. We note the Programme view that a data cut for non-SIT LDSOs could be taken in Q2 2024. Welcome further discussion with the Programme on whether this provides sufficient time for non-SIT-LDSOs and Code Bodies to facilitate non-SIT LDSO Qualification Testing. | Add " Change Forecast" - Qualification will require a review of this document." | Confirm. It is likely the second Data Cut will be planned for th Qualification Preparation phase. The scope and participants involved, will dependent on the Qualification Test Plan. | Proposed to close for this document review
Siemens | 3 | RECCo | 7 | 2 | Figure 2 refers to data being allocated to parites by Code Bodies. Code Body assumption that this is an administrative task and that the SI will retain the central repositiry of data and provide access to Qualification parites, inc. non-SIT LDSOs, as required. Note that section 3.5, penultimate bullet, states that access to data requires a PKI certificate. Will this be managed by SI for each Qualification party? | No document changes required | Yes. For SIT and Non-SIT (qualification), the SI will provide an sFTP space with PKI access for Test Data transfer. The only difference between SIT and Non-SIT is that for Qualification, the SI will allocate a large volume of MPANs to the Code Body that will later allocate subsets to the qualification tests. The qualification data allocation process will require an update in a future iteration of the Qualification Approach & Plan. | Proposed to close for this document review
Siemens | 4 | RECCo | 7 | 3.1 | Suggest adding QWG to the list of groups that should read the document as this sets out the activities that will need to be conducted by Qualification parties. | Ammend "readers audience" to include Code Bodies. | Usually we do not add other Working Groups to the list. We would need to add SIT, Migration, Qualification and other working groups. This document is public in the Programme portal and the programme encourage the participants to join as many working groups they find relevant for their work. I will align with other working groups and evaluate the updating the list in a next version of this document. | Proposed to close for this document review
Siemens | 5 | RECCo | 8 | 3.4 | Typo "SIT" rather than "STI" | Typo corrected | Thanks for point out. The typo is corrected | Proposed to close for this document review
Avanade | 6 | RECCo | 8 | 3.5 | Text assumes that the UIT environment will be used for non-SIT LDSO testing. This approach has not yet been confirmed by the Programme. | Add "Change Forecast: review required when Environment Approach & Plan updates" | This section will be amended if the Test Environments approach changes. When the Qualification test plan is released/confirmed, it may require other updates to this document as well. | Proposed to close for this document review
Avanade | 7 | RECCo | 8 | 3.5 | Will only MHHS quaification parties be able to access the E2E Sandbox? If so, an alternative approach needed for EES API Users that are not Qualified parties - e.g. TPIs. | No document changes required | I will forward the query to Environments Working Group | Proposed to close for this document review
Avanade | 8 | RECCo | 9 | 5.2 | Last bullet - please amend to note that this qualification data allocation process will be set out in a future iteration on the Qualification Approach & Plan. | Ammend section: "Qualification Test Data allocation process will be further clarified in a future iteration of this document after the release of the Qualification Approach & Plan" | Thanks for point out. W e agree with this and the document will be updated in subsequent release. | Proposed to close for this document review
Avanade | 9 | RECCo | 11 | 6.1 | Section 2 states that a data cut will be required by all SIT Participants. However Section 6.1 states that EES is not required to take a data cut. As EES is a SIT participant the two starements are contradictory. Note in practice we are anticipating EES will need to take a full system back-up in order to populate the test environment. This data set will then be updated by augmented data provided by MPAS | Ammend: "EES to take the data cut" | From a Programme perspective, both approaches work well. After a bilateral call with RECCo, the Data Plan will be updated to set the preferable approach by RECCo. | Proposed to close for this document review
Avanade | 10 | RECCo | 11 | 6.1 | Note that the existing MPRS Full Mpan Refresh arrangements will need updating to take into account new MHHS Data Items and the removal of legacy data items. | No document changes required | Noted. Details on how to update the new MHHS Data Items covered by CIT Test Data Approach and SIT Functional Test Data Approach | Proposed to close for this document review
| 11 | RECCo | 11 | 6.1 | Is it possible to confrirm when the population of EES by MPRS will take place? | No document changes required | Yes - During the CIT Inerval 2 Data Preparation (Between 18th Sept and 20th October). | Proposed to close for this document review
| 12 | RECCo | 11 | 6.1 | It was mentioned in DWG that following the data cut multiple provisions of augmented data may be sent to parties. Is it planned to use an MPRS full refresh to communicate any updates to EES? Note that a full refesh would have the affect of updating all MPANs, refreshing data that has been updated via testing. | No document changes required | Yes. It is planned to have refreshs of the EES after cycles of data Augmentation. Details will be provided by CIT Test Data Plan and SIT Functional Test Data Plan. | Proposed to close for this document review
| 13 | RECCo | 13 | 6.5 | Please clarify if this is the same approach for SIT and non-SIT parites | Update wording: "allocation vs specified by" | Same approach. The only difference is that the Code Body will allocate the MPAN for each test scenario during Qualification from a large data set prepared by SI. | Proposed to close for this document review
| 14 | RECCo | 14 | 6.8 | Please clarify if this is the same approach for SIT and non-SIT parites | No document changes required | Same approach. The only difference is that the Code Body will allocate the MPAN for each test scenario during Qualification from a large data set prepared by SI. | Proposed to close for this document review
| 15 | RECCo | 15 | 6.9 | Second to last paragraph starting 'Although the expectation is....' no longer makes sense. Suggest deleting this paragraph as it's no longer required. | No document changes required | We currently are planning 2 data cuts, but we do not want to completely close the possibility of an additional one. | Proposed to close for this document review
| 16 | RECCo | 16 | 8.2 | Please clarify if this is the same approach for SIT and non-SIT parites | No document changes required | Same approach. The only difference is that the Code Body will allocate the MPAN for each test scenario during Qualification from a large data set prepared by SI. | Proposed to close for this document review
| 17 | RECCo | 17 | 9.1 | Please clarify if a DPIA is expected to be undertaken before each Data Cut is undertaken and any data shared between parties - including for Non-SIT LDSO testing and other non-SIT testing. | No document changes required | On going by Elexon. No data will be shared before DPIA and Data Sharing Agreements are signed. | Proposed to close for this document review
| 18 | RECCo | 20 | Appendix | Unclear on the reference to Info Sec Consultants
| 19 | St Clements |  | 2 | “It is the responsibility of the participant to obtain or develop appropriate means of taking and storing their original data cut, extracting the data required by the SI, loading the data cut into its test environment and updating the data with the augmented/manipulated data provided by the SI“ we believed that data would be ascertained from EES rather than MPRS. The production of data items is not included in St Clements plan and has been raised in FTIG as D014 | No updates required required to the document. Action: Risk R552 added to the Programme and will be closely tracked. | The SI will try to allocate, cleanse and prepare Test Data using as a primary source data from EES. - For CIT, it is unlikely additional data will be required. - However, for SIT Functional Tests in Q2 2024, the SI will need more enriched data from participants to prepare the necessary IF/PUB and DTS messages to populate participants' test environments. | Proposed to close in this document review. Moved to Programme Risk
| 20 | St Clements |  | Figure 1 | Figure 1 shows 19th June to 19th July, but wording below states to 10th July | Typo fixed | Thanks for point out the Type. Document will be corrected | Proposed to close
| 21 | St Clements |  | 5.2 | 5.2 Out of Scope “A test data cleansing is required prior to starting the execution of SIT and UIT tests to reduce potential errors due to data inconsistencies” Will the test data cleansing be the same process as the production data cleansing? There is a risk that data is not cleansed in the same way or same capacity by go live, leading to data inconsistencies in production. | No updates required required to the document | The Data Cleanse for SIT will not be as comprehensive as required for Production. Just the minimum required to pass the test scenarios. | Proposed to close
| 22 | St Clements |  | 5.2 | 5.2 Out of Scope “Qualification Testing data allocation - The mechanism and approach for allocating data to Qualification Testing participants is covered elsewhere.” This is an overarching test approach, so confused why this doesn’t cover Qualification testing too? | Section 2 - Execute Summary has been updated to include workflow for Non-SIT/Qualification tests. | The details for the Qualification Tests (Non-STI Participants) will be covered by a specific Qualification Test Data Plan. | Proposed to close
| 23 | St Clements |  | 6.1 | 6.1 Systems requiring data cuts – “EES – no data cut required, but EES is expected to conduct a full refresh before testing commences, based on the MPRS test data in those MPRS instances being used for the testing. As part of the initial population of test environments, the EES will be populated by the MPRS systems, which will be undertaking the SIT using the existing full MPAN refresh mechanisms.” Would EES will be updated before the extraction of data for testing and after the update to MPRS with augmented data | No updates required required to the document | Hi, - For CIT, load the data to MPRS test environment and then run a full refresh (to capture any data cleansed). Would this capture the new MHHS parameters/data items? (to be discussed/aligned) - Before the start of SIT Functional Tests (Q2 2024), it is desirable to refresh EES with the MPRS data in the Test Environment. | Proposed to close
| 24 | St Clements |  | 6.2 | 6.2 Data Cut Process – “3. The SI will avoid re-using MPANs across test phases.” Please confirm it is the intention to use the same set of data for both CIT and SIT | No updates required required to the document | Only one Data cut/backup and loaded to the CIT/SIT Functional Test Environment (environemnts info here: MHHS-DEL618 Environment Approach and Plan). However: - MPANs used for CIT won’t be re-used for SIT Functional. - If an unexpected reason arises to require the re-use, an impact analysis will be required and participants involved. | Proposed to close
| 25 | St Clements |  | 6.4 | 6.4 Test Data Creation – “D0149 Notification of Mapping Details giving Meter Technical Details” Further to our data conversation, MTD processed into MPRS will need to be back filled to MEM systems and suppliers | No updates required required to the document | Agreed. Bilateral calls in progress to define the best file format/loading | Proposed to close
| 26 | St Clements |  | 6.9 | Data Refresh and Restore - “MHHS Programme may decide to take an additional data cut if the original data source has become less usable over time.” It is not possible to apply data from a new data cut on top of the original data cut within MPRS (i.e. “data refresh”) – therefore any previous testing would be lost if moving to the new data cut. | No updates required required to the document | Agree. There is no active plan for a second data cut for SIT participants. A new data cut would mean a re-start of the test environemnt or a new instance. Any plan for a new data cut would be aligned with all SIT participants for impact analysis. | Proposed to close
| 27 | St Clements |  | 2 | Any additional cuts cannot be applied onto of the Original Data cut. If a later Data cut needs to be used in SIT the Environment will need to be re-built and the SI Custom Data Re-loaded | No updates required required to the document | Noted. Same as above | Proposed to close
| 28 | St Clements |  | 6.2 | Current CIT Plans show only a Week between the Data cut and the Extra of Data to SI. It will take longer than 1 week to transfer the Data from the customer Database then stand up the environment ready for any data extraction or loading | No updates required required to the document | On going discussion on schedule/data preparation in the bilateral calls. Risk to be raised by Cesar to the Programme risks (affecting all participants, not only MPRS) | Proposed to close
| 29 | St Clements |  | 6.2 Step 6 | Our preference is for SI Manipulated Data to be loaded into MPRS using BAU interfaces. This avoids the need for additional development. Formats for these interfaces have been shared with the Programme. | No updates required required to the document | On going discussion in the bilateral calls. Agreed to provide the content using the JSON messages/formart as described by relevant IFs. | Proposed to close
| 30 | St Clements |  |  | Will there be a further Data cut for Migration SIT? | No updates required required to the document | No. | Proposed to close
| 31 | St Clements |  | 7.2 | Registration Data needs to be obtained from EES, this is a copy of the MPRS data and is more obtainable. MPRS is not designed to be a Enquiry Service, extracting data will required custom developed code, there is no time to deliver this. | No updates required required to the document | The SI will try to allocate, cleanse and prepare Test Data using as a primary source data from EES. - For CIT, it is unlikely additional data will be required. - However, for SIT Functional Tests in Q2 2024, the SI will need more enriched data from participants to prepare the necessary IF/PUB and DTS messages to populate participants' test environments. | Proposed to close
| 32 | Callisto | 10, 15, 19 | 6, 7.2, Appendix | These three sections all relate to the provision of historical consumption data. Requirements have yet to be determined, but the document in section 6 states that DC's will not need to take a cut of data. We hold the majority of appointments in the NHH and HH DC markets and the size of a consumption data extract for our portfolio will be a significant undertaking. We would seek the earliest clarification of the requirements of the programme in this regard. I have requested a bilateral discuss, but have not yet had a response. | No updates required to the document | I confirm the historical consumption data is not required from Data Cut. All domestic consumption data will be manufactured. Document section 9.2 was updated to confirm this position. The child document CIT Test Data Plan also confirms no historical data needed from data cut/backup. For non-domestic consumption data, we recognize some participant may want to load use real consumption to allow further tests on their systems. | Proposed to close
| 33 | Participants # 1 | 11 | 6.1 | If an organisation with 3 MPIDs participates in SIT with one MPID, is it still required to take a data cut for ther 2 MPIDs at a later stage for qualification though placing reliance policy can be used for other 2 MPIDs | No changes required to the document. Update the section "Change Forecast" to include the data cut requirements for Qualification will be updated when the Qualification Test Plan is published. | The Qualification Test Plan stills in elaboration and this document is likely to require an update to update the Data Cut requirements for Qualification. We'll have more information to define the exact scope of Data Cut for Qualification and a new child document "Qualification Test Data plan" will also be produced. | Proposed to close for this document review.
| 34 | Participants # 2 | 14 | 6.7 Test Data Cleansing | "The cleansing is expected to be minimal as SI will look to exclude MPANs from testing that do not confirm to the required quality measures" Will the reasons for excluding MPANs be captured and reported? Feels it could be useful information for the wider data cleanse work that needs to be done for migration. (NB: This may have already been discussed at DWG/MWG which I don't attend; it was just a thought that occured whilst looking at the red-line text) If so, the fact it will be captured/reported could be added to the next version (plus update confirm -> conform) | Typo corrected | Noted and I agree it will be useful. During the next sessions with Data Working Group and Migration lead (John Wiggins), I will bring the topic and get insights of the better format to capture and share the "non-conform" MPANs. | Proposed to close for this document Review
| 35 | Participants # 3 | 12 | 6.2 | Figure 4 - has a swim lane for Programme Participants (SIT and non SIT) but non-SIT participants are not required to provide data in the first round. If this is the model that the programme expects to use for all subsequent data loads, then it is fine, but there should be a sentence in a footnote to explain this, otherwise it might mislead non-SIT participants into thinking that they will receive some data. | Added footnote | We expect the same process for the subsequent data cut. I will add the footnote to make it clear. Thanks for highligthing it. | Proposed to close.
| 36 | Participants # 3 | 17 | 9.1 | The section on data protection impact assessment is good, however, it should explain is that the purpose of a DPIA is to identify the risks involved in processing personal data, to which the programme should then apply appropriate safeguards. This would be better structured by making this distinction and then describing safeguards (1) real consumption will not be used as a safeguard. (2) PKI & COCO infrastructure (MHHSDEL1197 Interface Code of Connection and [REF-08] MHHS-DEL1210 Data Integration Platform Public Key | Added the purposed of DPIA in the first paragraph. | Thanks for the comment. Agree. I updated the section to properly introduce the content. | Proposed to close.
| 37 | Participants # 3 | 14 | 6.7 | This should establish a principle that distinguishes between data quality issues that are expected to be persistent (i.e. those that will not be cleansed to zero prior to migration) and those that must be addressed. This is an important distinction - as testing should include ensuring that data with a persistent data quality issue will be correctly handled by the system, and that the system appropriately rejects data (with a meaningful error message) where it is an unacceptable data quality issue. We recognise that a full list of persistent data issues will not yet have been defined (as this is part of the TMAG sponsored Data Cleanse activities) however, we think that it is important that this principle is established up front | Added paragraph: "There are data quality issues that are expected to be persistent (i.e. those that will not be cleansed to zero prior to testing) and those that must be addressed for the correct execution of tests." | I will add a paragraph to clarify the item. When the detailed SIT Functional Test Cases are released, it will be clear the tests associated to "negative"/error handling. | Proposed to close.
| 38 | Participants # 4 | 11 | 6.2, Note 3 | Perhaps note that re-use may not be possible depending on how the data was originally used. For example it might have been lost in a CoS process, so cannot then be used again by the same supplier. Similarly if an MPAN was set up to run in functional (e.g. migrated to new arrangement) with new MHHS set up then it can't be used in Migration. | No changes required to the document | Agree. The plan is that MPANs used in one test phase won't be re-used in the next phase. We understand that the participant's systems during CIT Tests may not be functionally complete and those MPANs used in the test cases may become "corrupted/unusable". Also, for Migration tests, we'll separate MPANs to not being migrated before. The note 3 is to not close completely the possibility to re-use MPANs. But, if it happens, it should be by exception. | Proposed to close
| 39 | Participants # 4 | 10 | 6.1 | Smart Metering - noted the update is to review to SIT Functional document. Can you confirm when this will be updated? We will need to know what smart metering systems will be part of Non-SIT testing so we can understand what systems we need to take data cuts of. Please also see email conversation with testing@mhhsprogramme.co.uk and Cesar Lopes on 8th June. It would be useful to understand what industry systems will be present in Non-SIT, e.g. direct connection to DCC by Suppliers to communicate read data. | Section updated: no historical data required for Smart Metering consumption. Updated section 3.3 Change forecast: this document will be updated after the Qualification Test Plan is released. | Historical domestic consumption data not required from Data Cut. Some participants may want to use non-domestic real consumption data in their tests in order to execute additional tests. For Non-SIT testing, we will update the document to provide more details after the Qualification Test Plan is released. | Proposed to close for this document review
| 40 | Participants # 4 | 16 | 8.3 | Do you have a timeline for when the data format will be available? | No changes required to the document | The functional Test Data Plan will provide details on the format. The document will be released for public Consultation Monday 10th July | Proposed to close for this document review
| 41 | Participants # 4 | 16 | 8.4 | Do you have a timeline for when the allocation format will be available? | No changes required to the document | We provided more details in the CIT Test Data Plan. But the final Allocation approach will be ready when the Detailed Test Cases are published. | Proposed to close for this document review
| 42 | Participants # 4 | 16 | 8.5 | Will information also be provided for pairing in Non-SIT testing? | No changes required to the document | The Qualification Test Plan hasn't been released yet. As soon as we get the Test Plan published, we'll be able to elaborate and provide guidelines around pairing for Non-SIT. | Proposed to close for this document review
| 43 | IMServ |  | Cell M2 | Reference to the D0354 is still being made in cell M2, Programme has already agreed to remove this | Updated | The" MHHS-DEL816 Population of Data Items for Testing" will be updated and released again containing several changes after the review. It will have another public consultation, independent of this Overarching Test Data Plan. I propose to close the item for the Overarching Test Data Plan document recognizing the spreadsheet will be updated. | Proposed to close for this document review.
| 44 | IMServ | 9 | 3.5 | Typo - "However, if required, the consumption will never be never linked to the original MPAN ..." | Corrected | Thanks
| 45 | IMServ | 14 | 6.9 | Given the change made to this section i.e. the removal of "The same data cut will then be used to load the “SIT B” Test Environment used by SIT Migration." , please clarify which data cut will be used to test SIT Migration? Will it be an extra cut or the same cut as used for SIT CIT component & SIT functional / Qualification? | No updates required to the document | No additional Data Cut planned for Migration Tests. The Migration test is a stage of SIT, similar to CIT, Functional, Non-Functional, etc. The SIT Migration tests will use the same data cut (19th August). A subset of MPANs will be left un-allocated to allow Migration Tests. No refreshes are required. However, as specified by MHHS-DEL618 Environment Approach and Plan, the Migration tests will be executed in a different test environment than the SIT CIT and SIT Functional. A Migration Test Data Plan will be produced providing more details | Proposed to close
| 46 | IMServ | 7 | 2 | Our preference is for SI Manipulated Data to be loaded into MPRS using BAU interfaces. This avoids the need for additional development. Formats for these interfaces have been shared with the Programme. |  | Agree. We are planning to use BAU and JSON files containing the same data structure. The details will be presented in the next DWGs and Functional Test Data Plan. | Proposed to close
| 47 | IMServ | 8 | 3.5 | Typo - 'Non-STI' - should be Non-SIT | Corrected. | Thanks | Proposed to close