## Cover Page
SIT CIT Test Scenarios
Document owner | Document number | Version
SI Test Team | MHHS-DEL1116 | 5.2.2
Status: | Date | Classification
Draft | 2023-08-16 | Public

## Change Control
Change Record
Date | Author | Version | Change Detail
2023-03-28 | SI Test Team | 0.1 | First draft for review by LDP
2023-04-12 | SI Test Team | 0.2 | Draft for review by SRO & Code Bodies
2023-04-17 | SI Test Team | 0.3 | Draft for review by industry
2023-07-18 | SI Test Team | 5.2 | Uplift to design Interim Release 2
2023-08-09 | SI Test Team | 5.2.1 | Additional updates based on design clarifications and participant feedback
2023-08-16 | SI Test Team | 5.2.2 | Additional updates based on design clarifications and participant feedback
Document Approval
Reviewer/Approver | Role
SI Test Team | Internal review
Chan Dabare | Approval ahead of industry review (including review by SRO Design Team)
Code Bodies | Approval ahead of industry review
SITWG | Recommendation to TMAG
TMAG | Approval
References
Reference | Documents | Publisher | Version | Additional Information
Design Interface | MHHSP-DES138-Interface Catalogue |  | v5.2.1 | MHHSP-DES138-Interface Catalogue v5.2.1
SIT Component Integration Test Approach & Plan | MHHS-DEL1258 SIT Component Integration Test Approach & Plan |  | v1.0 | SIT CIT Test Approach & Plan v1.0
Terminology
Term | Description
For terminology, see Programme Glossary on the MHHS portal

## Notes on Scenarios
SIT Component Integration SIT Component Integration Testing (SIT CIT) is described in the SIT CIT Test Approach & Plan. Please refer to this before reading the rest of this document. Component systems/services will be integrated one at a time or in small groups. SIT CIT will be conducted on a bi-lateral basis between the SI Test Team and the organisation responsible for each component being integrated, with messages being exchanged between special end-points set up by the SI Test Team and the service being integrated. Each service will be expected to receive and to send one example of each IF/PUB message relevant to it in order for that service to pass SIT CIT. This means that where the test is that a service receives a PUB message, the SI Test Team will initiate that test by sending in the relevant message from a specially created end-point. For service message receipt, the service is expected to pass the test when it has successfully received a single IF message. Where the test involves a service generating an IF then it up to that service to generate a message appropriately, triggering it from the agreed point in their service. An exception to this is where a service responds to a PUB with the generation of an IF (for example IF-005 being sent by a Metering Service then coming to the Registration Service as PUB-005 and the Registration Service responding by producing a corresponding IF-006). In this case, the test would be triggered by the SI Test Team sending an IF-005. However a Sender which has passed all its own tests will also be required to send additional messages to test the DIP routing. This will involve generating several different variations of a particular IF (see Sending Scenarios below). Notes on the sheets in this workbook: Sending Scenarios – This sheet contains a list of all the scenarios involved in verifying that: - the services can correctly generate messages and send via the DIP; AND - the DIP correctly routes the messages sent. This will involve the Sender of an IF message potentially having to send many different variations of that message in order to verify the DIP routing. For example, the Registration Service will need to generate 14 different IF-006 messages to fully test the DIP routing. The following combination of data items makes each scenario unique: - Interface (IF number) - Event Code - Data Conditions - Sender. Data Conditions means any specific conditions called out in the MHHSP-DES138-Interface Catalogue which are used to determine the routing. For example, routing for an IF-006 can depend on the Supply Start Date. Each scenario has one or more test cases associated with it. These cases are identified but full details are not given in this document – they will be the subject of a later, separate document. Typically, there is a test case for each relevant Market Segment. The Market Segments to which the scenario relates are also indicated. Sending Summary by Role – This sheet contains a PivotTable showing the number of different scenarios relating to each Role. It can be used to generate additional worksheets with each worksheet showing all the scenarios relating to an individual Role. Receiving Summary by Role – This sheet contains several PivotTables based on the Sending Scenarios sheet. There is a set of tables for each Role, listing the IF messages each one is to receive. Receipt of the message by the Role constitutes a test scenario. In this case, each scenario will have a single test case associated with it, so test cases are not mentioned. The number of test scenarios for a given Role is the sum of the Sending and the Receiving.
SIT CIT Test Approach & Plan Link

## Sending Scenarios
Ref # | Interface | Event Code | Data Conditions | Sender | Always | Primary | Secondary | Number of Always | Number of Primaries | Number of Secondaries | Number of Test Cases | Smart Segment | Advanced Segment | Unmetered Segment | Notes | Executing Test (where IF is SENT by party under test) | Baseline Version | Changed from 23/04 Issue | Change Reason | Changed from 21/07 Issue | Change Summary | Change Reason | Changed from 09/08 Issue | Change Summary | Change Reason | Impacted by Open Design Query | Comment Summary
1 | MHHSP-IF-001 | ChangeofSupplier |  | REGS | MDS, EES | SUPI | LDSO | 2 | 1 | 1 | 1 | Y |  |  | This will be for an Import MPAN which has both Export MPAN and 2 Related MPANs linked to it. | Sender sends out relevant message (up to Sender to initiate message in appropriate way) | 5.2 | [8 empty] | Y | DIN-620 (Interim Release 5) has been raised to reflect that EES will receive this information directly from CSS and will not ingest the IF-001.
2 | MHHSP-IF-001 | InitalRegistation |  | REGS | MDS, EES | SUPI | LDSO | 2 | 1 | 1 | 1 | Y |  |  | This will be for a single MPAN. | Sender sends out relevant message (up to Sender to initiate message in appropriate way) | 5.2 | [8 empty] | Y | DIN-620 (Interim Release 5) has been raised to reflect that EES will receive this information directly from CSS and will not ingest the IF-001.
3 | MHHSP-IF-002 | GainMPANInfo |  | REGS |  | SUPI |  | 0 | 1 | 0 | 1 |  |  |  | This will be for an Import MPAN which has both Export MPAN and 2 Related MPANs linked to it as well as having 2 meters on the MPAN. | Sender sends out relevant message (up to Sender to initiate message in appropriate way) | 5.2
4 | MHHSP-IF-004 | CommsHubInfo |  | MSSS |  |  | SUPC | 0 | 0 | 1 | 1 | Y |  |  |  | Sender sends out relevant message (up to Sender to initiate message in appropriate way) | 5.2 | Y | 5.2.1 impact
5 | MHHSP-IF-004 | CommsHubInfo |  | SUPS |  |  | MSSC | 0 | 0 | 1 | 1 | Y |  |  |  | Sender sends out relevant message (up to Sender to initiate message in appropriate way) | 5.2 | Y | 5.2.1 impact
6 | MHHSP-IF-005 | MeterInstall |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | This will include IHD information. |  | 5.2 |  |  | Y | Avanced Segment removed | Design clarification
7 | MHHSP-IF-005 | MeterRemoval |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Avanced Segment removed | Design clarification
8 | MHHSP-IF-005 | MeterExchange |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | This will include IHD information. |  | 5.2 |  |  | Y | Avanced Segment removed | Design clarification
9 | MHHSP-IF-005 | MeterUpdate |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | This will include MAP information in the message. |  | 5.2 |  |  | Y | Avanced Segment removed | Design clarification
10 | MHHSP-IF-005 | MeterHistoryUpdate |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | This will include meter removal information in the message. |  | 5.2 |  |  | Y | Avanced Segment removed | Design clarification
11 | MHHSP-IF-005 | MeterInstall |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Smart segment removed | Design clarification
12 | MHHSP-IF-005 | MeterRemoval |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Smart segment removed | Design clarification
13 | MHHSP-IF-005 | MeterExchange |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Smart segment removed | Design clarification
14 | MHHSP-IF-005 | MeterUpdate |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  | This will include MAP information in the message. |  | 5.2 |  |  | Y | Smart segment removed | Design clarification
15 | MHHSP-IF-005 | MeterHistoryUpdate |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  | This will include meter removal information in the message. |  | 5.2 |  |  | Y | Smart segment removed | Design clarification
41 | MHHSP-IF-006 | MeterExchange | DI-979<>'R' | REGS | EES | MSSS | SDSC, MSSC, SUPC, LDSO, SDSP, MSSP | 1 | 1 | 6 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Secondary changed from XMSP to MSSP | Design clarification Participant Feedback
42 | MHHSP-IF-006 | MeterUpdate | DI-979<>'R' | REGS | EES | MSSS | SUPC, LDSO, SDSC | 1 | 1 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 42a added for Advanced | Design clarification
42a | MHHSP-IF-006 | MeterUpdate | DI-979<>'R' | REGS | EES | MSAS | SUPC, LDSO, ADSC | 1 | 1 | 3 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
43 | MHHSP-IF-006 | MeterInstall | DI-979<>'R' | REGS | EES | MSSS | SDSC, MSSC, SUPC, LDSO, SDSP, MSSP | 1 | 1 | 6 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 43a added for Advanced | Design clarification Participant Feedback
43a | MHHSP-IF-006 | MeterInstall | DI-979<>'R' | REGS | EES | MSAS | ADSC, MSAC, SUPC, LDSO, ADSP, MSAP | 1 | 1 | 6 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
44 | MHHSP-IF-006 | MeterHistoryUpdate | DI-979<>'R' | REGS | EES | MSSS | SUPC, LDSO | 1 | 1 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 44a added for Advanced | Design clarification
44a | MHHSP-IF-006 | MeterHistoryUpdate | DI-979<>'R' | REGS | EES | MSAS | SUPC, LDSO | 1 | 1 | 2 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
45 | MHHSP-IF-006 | MeterRemoval | DI-979<>'R' | REGS | EES | MSSS | SDSC, MSSC, SUPC, LDSO, SDSP, MSSP | 1 | 1 | 6 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 45a added for Advanced | Design clarification Participant Feedback
45a | MHHSP-IF-006 | MeterRemoval | DI-979<>'R' | REGS | EES | MSAS | ADSC, MSAC, SUPC, LDSO, ADSP, MSAP | 1 | 1 | 6 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
46 | MHHSP-IF-006 | MeterInstall | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 46a added for Advanced | Design clarification
46a | MHHSP-IF-006 | MeterInstall | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
47 | MHHSP-IF-006 | MeterRemoval | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 47a added for Advanced | Design clarification
47a | MHHSP-IF-006 | MeterRemoval | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
48 | MHHSP-IF-006 | MeterExchange | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 48a added for Advanced | Design clarification
48a | MHHSP-IF-006 | MeterExchange | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
49 | MHHSP-IF-006 | MeterUpdate | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 49a added for Advanced | Design clarification
49a | MHHSP-IF-006 | MeterUpdate | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
50 | MHHSP-IF-006 | MeterHistoryUpdate | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Advanced deleted and row 50a added for Advanced | Design clarification
50a | MHHSP-IF-006 | MeterHistoryUpdate | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Advanced Segment | Design clarification
51 | MHHSP-IF-007 | EnergisationStatusChange |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Removed Adv and UM | Design clarification
51a | MHHSP-IF-007 | EnergisationStatusChange |  | MSAS |  |  | REGS | 0 | 1 | 1 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Added ref# 51a adv | Design clarification
51b | MHHSP-IF-007 | EnergisationStatusChange |  | UMSO |  |  | REGS | 0 | 0 | 1 | 1 |  |  | Y |  |  | 5.2 |  |  | Y | Added ref# 51b UM | Design clarification
52 | MHHSP-IF-007 | EnergisationStatusFailure |  | MSSS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Removed Adv and UM | Design clarification
53 | MHHSP-IF-007 | EnergisationStatusFailure |  | MSAS |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Added ref# 52a adv | Design clarification
53a | MHHSP-IF-007 | EnergisationStatusFailure |  | UMSO |  | SUPS |  | 0 | 1 | 0 | 1 |  |  | Y |  |  | 5.2 |  |  | Y | Added ref# 52b UM | Design clarification |  |  |  | Y | Design Team working with UMSO community to clarify process for Change of Energisation Status for unmetered sites. DIN-619 raised as a result; scenarios will be updated in line with DIN design outcomes.
53b | MHHSP-IF-008 | EnergisationStatusChange | DI-979 = 'A' | REGS | MDS, EES | MSSS | SUPC, SDSC, MSSC, LDSO, SDSP, MSSP | 2 | 1 | 6 | 1 | Y |  |  |  | Initiate by sending appropriate IF-007 to RS | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
57a | MHHSP-IF-008 | EnergisationStatusChange | DI-979 = 'A' | REGS | MDS, EES | MSAS | SUPC, ADSC, MSAC, LDSO, ADSP, MSAP | 2 | 1 | 6 | 1 |  | Y | [6 empty] | Y | Added Advanced Row 57a | Design clarification
57b | MHHSP-IF-008 | EnergisationStatusChange | DI-979 = 'A' | REGS | MDS, EES | UMSO | SUPC, UMSDSC, MSSC, LDSO, UMSDSP, UMSO | 2 | 1 | 7 | 1 |  |  | Y | [5 empty] | Y | Added Unnmetered Row 57b | Design clarification
58 | MHHSP-IF-008 | EnergisationStatusChange | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  | Initiate by sending appropriate IF-007 to RS | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
58a | MHHSP-IF-008 | EnergisationStatusChange | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Advanced Row 58a | Design clarification
58b | MHHSP-IF-008 | EnergisationStatusChange | DI-979='R' | REGS |  | UMSO |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added Unnmetered Row 58b | Design clarification
59 | MHHSP-IF-009 | MPANDisconnection |  | REGS | EES |  | SUPC, LDSO | 1 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Removed Adv and UM | Design clarification
59a | MHHSP-IF-009 | MPANDisconnection |  | REGS | EES |  | SUPC, LDSO | 1 | 0 | 2 | 1 |  | Y | [6 empty] | Y | Added Advanced Row 59a | Design clarification | Y | Removed Unmetered scenario | Participant feedback and Design clarification
60 | MHHSP-IF-009 | CSSDeRegistration |  | REGS | MDS, EES |  | SUPC, LDSO | 2 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Removed Adv and UM | Design clarification
60a | MHHSP-IF-009 | CSSDeRegistration |  | REGS | MDS, EES |  | SUPC, LDSO | 2 | 0 | 2 | 1 |  | Y | [6 empty] | Y | Added row 60a Advanced | Design clarification | Y | Removed Unmetered scenario | Participant feedback and Design clarification
61a | MHHSP-IF-013 | ActivePowerDefaulted & DI-015 <> 'W' | DI-015 <> W | MDS |  | SUPC, ADSS | LDSO | 0 | 2 | 1 | 1 |  | Y | [6 empty] | Y | Added row 61a Advanced | Design clarification
61b | MHHSP-IF-013 | ActivePowerDefaulted & DI-015 <> 'W' | DI-015 <> W | MDS |  | SUPC, UMSDS | LDSO | 0 | 2 | 1 | 1 |  |  | Y | [5 empty] | Y | Added row 61b Unmetered | Design clarification
62 | MHHSP-IF-013 | ActivePowerDefaulted & DI-015 = 'W' | DI-015 = W | MDS |  | SUPC, SDSS |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
63a | MHHSP-IF-014 | ActivePowerRejected | DI-015 <> W | MDS |  | SUPS, ADSS | LDSO | 0 | 2 | 1 | 1 |  | Y | [6 empty] | Y | Added row 63a Advanced | Design clarification |  |  |  | Y | Design Team clarification: the IF-014 notifies rejected IF-021s; impacts on consumption. A DIN would be needed to remove LDSO.
63b | MHHSP-IF-014 | ActivePowerRejected | DI-015 <> W | MDS |  | SUPS, UMSDSS | LDSO | 0 | 2 | 1 | 1 |  |  | Y | [5 empty] | Y | Added row 63b Unmetered | Design clarification |  |  |  | Y | Design Team clarification: the IF-014 notifies rejected IF-021s; impacts on consumption. A DIN would be needed to remove LDSO.
64 | MHHSP-IF-014 | ActivePowerRejected | DI-015 = W | MDS |  | SUPS, SDSS |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
65 | MHHSP-IF-014 | ConsumptionOnDeEnergisedMPAN |  | MDS |  | SDSS | LDSO | 0 | 1 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification |  |  |  | Y | Design Team clarification: the IF-014 notifies rejected IF-021s; impacts on consumption. A DIN would be needed to remove LDSO.
65a | MHHSP-IF-014 | ConsumptionOnDeEnergisedMPAN |  | MDS |  | ADSS | LDSO | 0 | 1 | 1 | 1 |  | Y | [6 empty] | Y | Added row 65a Advanced | Design clarification |  |  |  | Y | Design Team clarification: the IF-014 notifies rejected IF-021s; impacts on consumption. A DIN would be needed to remove LDSO.
65b | MHHSP-IF-014 | ConsumptionOnDeEnergisedMPAN |  | MDS |  | UMSDSS | LDSO | 0 | 1 | 1 | 1 |  |  | Y | [5 empty] | Y | Added row 65b Unmetered | Design clarification |  |  |  | Y | Design Team clarification: the IF-014 notifies rejected IF-021s; impacts on consumption. A DIN would be needed to remove LDSO.
66 | MHHSP-IF-015 | ConsumptionReplay |  | ADSS | DIP |  |  | 1 | 0 | 0 | 1 |  | Y |  |  | Relevant IFs are sent before commencement of this test so that there is something to replay. | 5.2 |  |  | Y
67a | MHHSP-IF-016 | ConsumptionReplayResult |  | DIP |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added row 67a Advanced and removed Smart scenario | Design clarification
68 | MHHSP-IF-018 | AddressChg |  | REGS | EES |  | SUPC, SDSC, MSSC | 1 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
68a | MHHSP-IF-018 | AddressChg |  | REGS | EES |  | SUPC, ADSC, MSAC |  | 0 | 3 | 1 |  | Y | [6 empty] | Y | Added row 68a Advanced | Design clarification
68b | MHHSP-IF-018 | AddressChg |  | REGS | EES |  | SUPC, UMSDSC, UMSO | 1 | 0 | 3 | 1 |  |  | Y | [5 empty] | Y | Added row 68b Unmetered | Design clarification
69 | MHHSP-IF-018 | DCCEnrolment |  | REGS | EES |  | SUPC | 1 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | PP Feedback
70 | MHHSP-IF-018 | GSPChg |  | REGS | MDS, EES |  | SUPC, SDSC, MSSC | 2 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
70a | MHHSP-IF-018 | GSPChg |  | REGS | MDS, EES |  | SUPC, ADSC, MSAC | 2 | 0 | 3 | 1 |  | Y | [6 empty] | Y | Added row 70a Advanced | Design clarification
70b | MHHSP-IF-018 | GSPChg |  | REGS | MDS, EES |  | SUPC, UMSDSC, UMSO | 2 | 0 | 3 | 1 |  |  | Y | [5 empty] | Y | Added row 70b Unmetered | Design clarification
71 | MHHSP-IF-018 | DOMPremInd |  | REGS | MDS, EES |  | SUPC, SDSC, MSSC, LDSO | 2 | 0 | 4 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
71a | MHHSP-IF-018 | DOMPremInd |  | REGS | MDS, EES |  | SUPC, ADSC, MSAC, LDSO | 2 | 0 | 4 | 1 |  | Y | [6 empty] | Y | Added row 71a Advanced | Design clarification
71b | MHHSP-IF-018 | DOMPremInd |  | REGS | MDS, EES |  | SUPC, UMSDSC, UMSO, LDSO | 2 | 0 | 4 | 1 |  |  | Y | [5 empty] | Y | Added row 71b Unmetered | Design clarification
72 | MHHSP-IF-018 | DUOSTariffIDChg |  | REGS | MDS, EES |  | SUPC, SDSC, MSSC | 2 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
72a | MHHSP-IF-018 | DUOSTariffIDChg |  | REGS | MDS, EES |  | SUPC, ADSC, MSAC | 2 | 0 | 3 | 1 |  | Y | [6 empty] | Y | Added row 72a Advanced | Design clarification
72b | MHHSP-IF-018 | DUOSTariffIDChg |  | REGS | MDS, EES |  | SUPC, UMSDSC, UMSO | 2 | 0 | 3 | 1 |  |  | Y | [5 empty] | Y | Added row 72b Unmetered | Design clarification
73 | MHHSP-IF-018 | EnergyDirection |  | REGS | MDS, EES |  | SUPC, SDSC, MSSC, LDSO | 2 | 0 | 4 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
73a | MHHSP-IF-018 | EnergyDirection |  | REGS | MDS, EES |  | SUPC, ADSC, MSSC, LDSO | 2 | 0 | 4 | 1 |  | Y | [6 empty] | Y | Added row 73a Advanced | Design clarification
73b | MHHSP-IF-018 | EnergyDirection |  | REGS | MDS, EES |  | SUPC, UMSDSC, UMSO, LDSO | 2 | 0 | 4 | 1 |  |  | Y | [5 empty] | Y | Added row 73b Unmetered | Design clarification
74 | MHHSP-IF-018 | MUMIndicator |  | REGS | EES |  | SUPC, SDSC, MSSC, LDSO | 1 | 0 | 4 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
74a | MHHSP-IF-018 | MUMIndicator |  | REGS | EES |  | SUPC, ADSC, MSAC, LDSO | 1 | 0 | 4 | 1 |  | Y | [6 empty] | Y | Added row 74a Advanced | Design clarification
74b | MHHSP-IF-018 | MUMIndicator |  | REGS | EES |  | SUPC, UMSDSC, UMSO, LDSO | 1 | 0 | 4 | 1 |  |  | Y | [5 empty] | Y | Added row 74b Unmetered | Design clarification
75 | MHHSP-IF-019 | LinkedImportExportCreate |  | SUPS |  |  | LDSO | 0 | 0 | 1 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | PP Feedback | Y | Removed Adv | Design clarification
75a | MHHSP-IF-019 | LinkedImportExportCreate |  | SUPS |  |  | LDSO | 0 | 0 | 1 | 1 |  | Y | [6 empty] | Y | Added row 75a Advanced | Design clarification
76 | MHHSP-IF-019 | LinkedImportExportAdd |  | SUPS |  |  | LDSO | 0 | 0 | 1 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | PP Feedback | Y | Removed Adv | Design clarification
76a | MHHSP-IF-019 | LinkedImportExportAdd |  | SUPS |  |  | LDSO | 0 | 0 | 1 | 1 |  | Y | [6 empty] | Y | Added row 76a Advanced | Design clarification
77 | MHHSP-IF-019 | LinkedImportExportRemove |  | SUPS |  |  | LDSO | 0 | 0 | 1 | 1 | Y |  |  | Include DI-120 Additional Information |  | 5.2 | Y | PP Feedback | Y | Removed Adv | Design clarification
77a | MHHSP-IF-019 | LinkedImportExportRemove |  | SUPS |  |  | LDSO | 0 | 0 | 1 | 1 |  | Y | [6 empty] | Y | Added row 77a Advanced | Design clarification
78 | MHHSP-IF-019 | RelatedCreate |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification
78a | MHHSP-IF-019 | RelatedCreate |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y | [6 empty] | Y | Added row 78a Advanced | Design clarification
79 | MHHSP-IF-019 | RelatedAdd |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | Include DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification
79a | MHHSP-IF-019 | RelatedAdd |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y | [6 empty] | Y | Added row 79a Advanced | Design clarification
80 | MHHSP-IF-019 | RelatedRemove |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification
80a | MHHSP-IF-019 | RelatedRemove |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y | [6 empty] | Y | Added row 80a Advanced | Design clarification
81 | MHHSP-IF-020 | LinkedImportExportCreate | [DI-979] = "A" | REGS | EES | SUPS, SUPL | SUPC, SDSC, MSSC, LDSO | 1 | 2 | 4 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
81b | MHHSP-IF-020 | LinkedImportExportCreate | [DI-979] = "A" | REGS | EES | SUPS, SUPL | SUPC, ADSC, MSAC, LDSO | 1 | 2 | 4 | 1 |  | Y | [6 empty] | Y | Added Adv row 81b | Design clarification
82 | MHHSP-IF-020 | LinkedImportExportAdd | [DI-979] = "A" | REGS | EES | SUPS, SUPL | SUPC, SDSC, MSSC, LDSO | 1 | 2 | 4 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
82b | MHHSP-IF-020 | LinkedImportExportAdd | [DI-979] = "A" | REGS | EES | SUPS, SUPL | SUPC, ADSC, MSAC, LDSO | 1 | 2 | 4 | 1 |  | Y | [6 empty] | Y | Added Adv row 82b | Design clarification | Y | Removed 82c | Participant feedback and design clarification
83 | MHHSP-IF-020 | LinkedImportExportRemove | [DI-979] = "A" | REGS | EES | SUPS, SUPL | SUPC, SDSC, MSSC, LDSO | 1 | 2 | 4 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Removed scenario 82e, 82d | Participant feedback and design clarification
83b | MHHSP-IF-020 | LinkedImportExportRemove | [DI-979] = "A" | REGS | EES | SUPS, SUPL | SUPC, ADSC, MSAC, LDSO | 1 | 2 | 4 | 1 |  | Y | [6 empty] | Y | Added Adv row 83b | Design clarification | Y | Removed 83a | Participant feedback and design clarification
84 | MHHSP-IF-020 | RelatedCreate | [DI-979] = "A" | REGS | EES, MDS | SUPS | SDSC, MSSC, LDSO | 2 | 1 | 3 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Removed 83e, 83d, 83c | Participant feedback and design clarification | Y | MHHS-IF-020 is out of scope for CIT from an MDS point of view, as agreed in-MHHS-DIN-84. The design change will be formalised in Interim Release 4.
84b | MHHSP-IF-020 | RelatedCreate | [DI-979] = "A" | REGS | EES, MDS | SUPS | ADSC, MSAC, LDSO | 2 | 1 | 3 | 1 |  | Y | [6 empty] | Y | Added Adv row 84b | Design clarification | Y | Removed 84a | Participant feedback and design clarification | Y | MHHS-IF-020 is out of scope for CIT from an MDS point of view, as agreed in-MHHS-DIN-84. The design change will be formalised in Interim Release 4.
85 | MHHSP-IF-020 | RelatedAdd | [DI-979] = "A" | REGS | EES, MDS | SUPS | SDSC, MSSC, LDSO | 2 | 1 | 3 | 1 | Y |  |  | Include DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Removed 84e, 84d, 84c | Participant feedback and design clarification | Y | MHHS-IF-020 is out of scope for CIT from an MDS point of view, as agreed in-MHHS-DIN-84. The design change will be formalised in Interim Release 4.
85b | MHHSP-IF-020 | RelatedAdd | [DI-979] = "A" | REGS | EES, MDS | SUPS | ADSC, MSAC, LDSO | 2 | 1 | 3 | 1 |  | Y | [6 empty] | Y | Added Adv row 85b | Design clarification | Y | Removed 85a | Participant feedback and design clarification | Y | MHHS-IF-020 is out of scope for CIT from an MDS point of view, as agreed in-MHHS-DIN-84. The design change will be formalised in Interim Release 4.
86 | MHHSP-IF-020 | RelatedRemove | [DI-979] = "A" | REGS | EES, MDS | SUPS | SDSC, MSSC, LDSO | 2 | 1 | 3 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Removed 85d, 85e, 85c | Participant feedback and design clarification | Y | MHHS-IF-020 is out of scope for CIT from an MDS point of view, as agreed in-MHHS-DIN-84. The design change will be formalised in Interim Release 4.
86b | MHHSP-IF-020 | RelatedRemove | [DI-979] = "A" | REGS | EES, MDS | SUPS | ADSC, MSAC, LDSO | 2 | 1 | 3 | 1 |  | Y | [6 empty] | Y | Added Adv row 86b | Design clarification | Y | Removed 86a and 86c | Participant feedback and design clarification | Y | MHHS-IF-020 is out of scope for CIT from an MDS point of view, as agreed in-MHHS-DIN-84. The design change will be formalised in Interim Release 4.
90 | MHHSP-IF-020 | LinkedImportExportCreate | [DI-979] = "R" | LDSO |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification | Y | Removed 86d | Participant feedback and design clarification
90a | MHHSP-IF-020 | LinkedImportExportCreate | [DI-979] = "R" | LDSO |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#090a | Design clarification | Y | Sender changed to LDSO for event code = R | Participant feedback and Design clarification
91 | MHHSP-IF-020 | LinkedImportExportAdd | [DI-979] = "R" | LDSO |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification | Y | Sender changed to LDSO for event code = R | Participant feedback and Design clarification
91a | MHHSP-IF-020 | LinkedImportExportAdd | [DI-979] = "R" | LDSO |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#091a | Design clarification | Y | Sender changed to LDSO for event code = R | Participant feedback and Design clarification
92 | MHHSP-IF-020 | LinkedImportExportRemove | [DI-979] = "R" | LDSO |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Include DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification | Y | Sender changed to LDSO for event code = R | Participant feedback and Design clarification
92a | MHHSP-IF-020 | LinkedImportExportRemove | [DI-979] = "R" | LDSO |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#092a | Design clarification | Y | Sender changed to LDSO for event code = R | Participant feedback and Design clarification
93 | MHHSP-IF-020 | RelatedCreate | [DI-979] = "R" | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification | Y | Sender changed to REGS for event code = R | Participant feedback and Design clarification
93a | MHHSP-IF-020 | RelatedCreate | [DI-979] = "R" | REGS |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#093a | Design clarification | Y | Sender changed to REGS for event code = R | Participant feedback and Design clarification
94 | MHHSP-IF-020 | RelatedAdd | [DI-979] = "R" | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Include DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification | Y | Sender changed to REGS for event code = R | Participant feedback and Design clarification
94a | MHHSP-IF-020 | RelatedAdd | [DI-979] = "R" | REGS |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#094a | Design clarification | Y | Sender changed to REGS for event code = R | Participant feedback and Design clarification
95 | MHHSP-IF-020 | RelatedRemove | [DI-979] = "R" | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Exclude DI-120 Additional Information |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification | Y | Sender changed to REGS for event code = R | Participant feedback and Design clarification
95a | MHHSP-IF-020 | RelatedRemove | [DI-979] = "R" | REGS |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#095a | Design clarification | Y | Sender changed to REGS for event code = R | Participant feedback and Design clarification
100 | MHHSP-IF-021 | ActivePower | DI-015 = W | SDSS | LSS, MDS | SUPS |  | 2 | 1 | 0 | 1 | Y |  |  | Includes Active Import + Active Export and has information covering consumption on 2 settlement days |  | 5.2 |  |  | Y | Removed Advanced and Unmetered where DI-015 = W and Removed Smart where DI-015 <> W | Participant Feedback
102 | MHHSP-IF-021 | ActivePower | DI-015 <> W | ADSS | LSS, MDS | SUPS | LDSO | 2 | 1 | 1 | 1 |  | Y |  |  |  | 5.2
104 | MHHSP-IF-021 | ReactivePower |  | ADSS |  | SUPS | LDSO | 0 | 1 | 1 | 1 |  | Y |  |  |  | 5.2 | Y | PP Feedback
105 | MHHSP-IF-021 | ActivePower | DI-015 <> W | UMSDS | LSS, MDS | SUPS | LDSO | 2 | 1 | 1 | 1 |  |  | Y | Includes information covering consumption on 2 settlement days |  | 5.2
108 | MHHSP-IF-022 | LSSPeriodData |  | LSS | SUPC, SUPS, SUPL, SDSC, SDSP, SDSS |  |  | 6 | 0 | 0 | 1 | Y |  |  | Includes at least 2 Load Shape Criteria blocks and at least two settlement periods in each one |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Removed 106, 107 | Participant feedback and Design clarification
108a | MHHSP-IF-022 | LSSPeriodData |  | LSS | SUPC, SUPS, SUPL, ADSC, ADSP, ADSS |  |  | 6 | 0 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#108a | Design clarification
108b | MHHSP-IF-022 | LSSPeriodData |  | LSS | SUPC, SUPS, SUPL, UMSDSC, UMSDSP, UMSDSS |  |  | 7 | 0 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#108b | Design clarification
109 | MHHSP-IF-023 | LSSTotalsData |  | LSS | SUPC, SUPS, SUPL, SDSC, SDSP, SDSS |  |  | 6 | 0 | 0 | 1 | Y |  |  | Includes at least 2 different Load Shape Criteria combinations within the message |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
109a | MHHSP-IF-023 | LSSTotalsData |  | LSS | SUPC, SUPS, SUPL, ADSC, ADSP, ADSS |  |  | 6 | 0 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#109a | Design clarification | Y | Unmetered segment removed, only Smart and Adv tests. | Participant feedback and Design clarification (see Design Comment Summary) |  | DIN-617 raised to add a note to the "Interface Additional Information". This is to clarify the design position with regards to IF-023 Load Shape Totals Data and IF-040 Annual Consumption Data. Whilst these are provided to all data services, it is for each Data Service to determine if/how they wish to utilise these messages or not.
110 | MHHSP-IF-024 | SNVacant |  | SUPS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Removed 109b | Participant feedback and Design clarification
110a | MHHSP-IF-024 | SNVacant |  | SUPS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#110a | Design clarification
110b | MHHSP-IF-024 | SNVacant |  | SUPS |  | UMSDSS |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#110b | Design clarification
111 | MHHSP-IF-024 | SNNoComms |  | SUPS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
111 | MHHSP-IF-024 | SNNoComms |  | SUPS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#111a | Design clarification
111 | MHHSP-IF-024 | SNNoComms |  | SUPS |  | UMSDSS |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#111b | Design clarification
112 | MHHSP-IF-024 | SNRemoteEnabled |  | SUPS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
112a | MHHSP-IF-024 | SNRemoteEnabled |  | SUPS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#112a | Design clarification
112b | MHHSP-IF-024 | SNRemoteEnabled |  | SUPS |  | UMSDSS |  | 0 | 1 | 0 | 1 |  |  | Y
113 | MHHSP-IF-024 | SNRemoteDisabled |  | SUPS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
113a | MHHSP-IF-024 | SNRemoteDisabled |  | SUPS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#113a | Design clarification
113b | MHHSP-IF-024 | SNRemoteDisabled |  | SUPS |  | UMSDSS |  | 0 | 1 | 0 | 1 |  |  | Y
114 | MHHSP-IF-024 | SNSupplierAC |  | SUPS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
114a | MHHSP-IF-024 | SNSupplierAC |  | SUPS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#114a | Design clarification
114 | MHHSP-IF-024 | SNSupplierAC |  | SUPS |  | UMSDSS |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#114b | Design clarification
115 | MHHSP-IF-025 | ConsentGranularity |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | PP Feedback
116 | MHHSP-IF-025 | IHDInfo |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | PP Feedback
117 | MHHSP-IF-025 | SMSO |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | PP Feedback | Y | Removed Adv and UM | Participant Feedback
118 | MHHSP-IF-025 | SSCandProfileClass |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  | Includes MPAN Legacy Info B0-32 |  | 5.2 | Y | 5.2.1 impact
119 | MHHSP-IF-026 | ConsentGranularity | DI-979<>'R' | REGS | EES | SUPS | SDSC | 1 | 1 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
119a | MHHSP-IF-026 | ConsentGranularity | DI-979<>'R' | REGS | EES | SUPS | ADSC | 1 | 1 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#119a | Design clarification
120 | MHHSP-IF-026 | IHDInfo | DI-979<>'R' | REGS | EES | SUPS |  | 1 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact
121 | MHHSP-IF-026 | SMSO | DI-979<>'R' | REGS | EES | SUPS | SDSC | 1 | 1 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification; participant feedback
122 | MHHSP-IF-026 | ConsentGranularity | DI-979='R' | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2
123 | MHHSP-IF-026 | IHDInfo | DI-979='R' | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2
124 | MHHSP-IF-026 | SMSO | DI-979='R' | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2
125 | MHHSP-IF-026 | SSCandProfileClass | DI-979<>'R' | REGS | EES, LSS | SUPS | SDSC, MSSC, LDSO | 2 | 1 | 3 | 1 | Y |  |  | Includes MPAN Legacy Info |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification |  |  |  | Y | MHHS-IF-026, SSC and Profile class are not in CIT scope as agreed in MHHS-DIN-415
125a | MHHSP-IF-026 | SSCandProfileClass | DI-979<>'R' | REGS | EES, LSS | SUPS | ADSC, MSAC, LDSO | 2 | 1 | 3 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#125a | Design clarification |  |  |  | Y | MHHS-IF-026, SSC and Profile class are not in CIT scope as agreed in MHHS-DIN-415
126 | MHHSP-IF-026 | SSCandProfileClass | DI-979='R' | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Includes MPAN Legacy Info |  | 5.2 | Y | 5.2.1 impact
127 | MHHSP-IF-027 | ConsumptionAmendment |  | SUPS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  | Includes Active Import + Active Export and has information covering at least 2 consumption amendments in each |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv | Design clarification
127a | MHHSP-IF-027 | ConsumptionAmendment |  | SUPS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added UM Ref#127a | Design clarification
128 | MHHSP-IF-028 | ConsumptionAmendment |  | SDSS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Includes Active Import + Active Export and has information covering at least 2 consumption amendments in each |  | 5.2
128a | MHHSP-IF-028 | ConsumptionAmendment |  | ADSS |  | SUPS |  | 0 | 1 | 0 | 1 |  | Y |  | Includes Active Import + Active Export and has information covering at least 2 consumption amendments in each |  | 5.2 |  |  | Y | Changed from Ref#129 to 128a | Design clarification
128b | MHHSP-IF-028 | ConsumptionAmendment |  | UMSDS |  | SUPS |  | 0 | 1 | 0 | 1 |  |  | Y |  |  | 5.2 |  |  | Y | Changed from Ref#130 to 128b | Design clarification |  |  |  | Y | From a design perspective, this is to provide the mechanism for consumption amendment; Elexon Working Group ratification will be needed to formally exclude Unmetered
131 | MHHSP-IF-031 | MSApp |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2
132 | MHHSP-IF-031 | DSApp |  | SUPS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2
133 | MHHSP-IF-032 | MSAPPInitialResp |  | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Response Code = Accept |  | 5.2
134 | MHHSP-IF-032 | DSAPPInitialResp |  | REGS |  | SUPS |  | 0 | 1 | 0 | 1 | Y |  |  | Response Code = Accept |  | 5.2
135 | MHHSP-IF-033 | MSAppSPRequest |  | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification; participant feedback
135a | MHHSP-IF-033 | MSAppSPRequest |  | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#135a | Design clarification; participant feedback
135b | MHHSP-IF-033 | MSAppSPRequest |  | REGS |  | UMSO |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#135b | Design clarification
136 | MHHSP-IF-033 | DSAppSPRequest |  | REGS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification; participant feedback
136a | MHHSP-IF-033 | DSAppSPRequest |  | REGS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#136a | Design clarification; participant feedback
136b | MHHSP-IF-033 | DSAppSPRequest |  | REGS |  | UMSDSS |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#136b | Design clarification; participant feedback
137 | MHHSP-IF-034 | DSAppSPResponse |  | SDSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2
137a | MHHSP-IF-034 | SDS-MDRUpdate |  | SDSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Added Adv Ref# 137a; corrected Event code "SDSMDRUpdate" to "SDS-MDRUpdate" | Design clarification; participant feedback
137b | MHHSP-IF-034 | MSAppSPResponse |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Added Adv Ref# 137b | Design clarification
137c | MHHSP-IF-034 | DSAppSPResponse |  | ADSS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Added Adv Ref# 137c | Design clarification
137d | MHHSP-IF-034 | DSAppSPResponse |  | UMSDS |  |  | REGS | 0 | 0 | 1 | 1 |  |  | Y |  |  | 5.2 |  |  | Y | Added Adv Ref# 137d | Design clarification
137e | MHHSP-IF-034 | MSAppSPResponse |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2 |  |  | Y | Added Adv Ref# 137e | Design clarification
143 | MHHSP-IF-035 | MSAppAccepted |  | REGS |  | MSSS, SUPS, |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
143a | MHHSP-IF-035 | MSAppAccepted |  | REGS |  | MSAS, SUPS, |  | 0 | 2 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#143a | Design clarification
143b | MHHSP-IF-035 | MSAppAccepted |  | REGS |  | UMSO, SUPS, |  | 0 | 2 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#143b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
144 | MHHSP-IF-035 | MSAppRejected |  | REGS |  | MSSS, SUPS, |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
144a | MHHSP-IF-035 | MSAppRejected |  | REGS |  | MSAS, SUPS, |  | 0 | 2 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#144a | Design clarification
144b | MHHSP-IF-035 | MSAppRejected |  | REGS |  | UMSO, SUPS, |  | 0 | 2 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#144b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
145 | MHHSP-IF-035 | MSAppLapsed |  | REGS |  | MSSS, SUPS, |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
145a | MHHSP-IF-035 | MSAppLapsed |  | REGS |  | MSAS, SUPS, |  | 0 | 2 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#145a | Design clarification
145b | MHHSP-IF-035 | MSAppLapsed |  | REGS |  | UMSO, SUPS, |  | 0 | 2 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#145b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
146 | MHHSP-IF-035 | DSAppAccepted |  | REGS |  | SDSS, SUPS, |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
146a | MHHSP-IF-035 | DSAppAccepted |  | REGS |  | ADSS, SUPS, |  | 0 | 2 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#146a | Design clarification
146b | MHHSP-IF-035 | DSAppAccepted |  | REGS |  | UMSDSS, SUPS, |  | 0 | 3 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#146b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
147 | MHHSP-IF-035 | DSAppRejected |  | REGS |  | SDSS, SUPS, |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
147 | MHHSP-IF-035 | DSAppRejected |  | REGS |  | ADSS, SUPS, |  | 0 | 2 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#147a | Design clarification
147 | MHHSP-IF-035 | DSAppRejected |  | REGS |  | UMSDSS, SUPS, |  | 0 | 3 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#147b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
148 | MHHSP-IF-035 | DSAppLapsed |  | REGS |  | SDSS, SUPS, |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
148a | MHHSP-IF-035 | DSAppLapsed |  | REGS |  | ADSS, SUPS, |  | 0 | 2 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#148a | Design clarification
148b | MHHSP-IF-035 | DSAppLapsed |  | REGS |  | UMSDSS, SUPS, |  | 0 | 3 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#148b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
149 | MHHSP-IF-035 | IMS-SendMTD | Created from copy of MSApp Accepted and DSApp Accepted | REGS |  | MSSC |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
149a | MHHSP-IF-035 | IMS-SendMTD | Created from copy of MSApp Accepted and DSApp Accepted | REGS |  | MSAC |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#149a | Design clarification
149b | MHHSP-IF-035 | IMS-SendMTD | Created from copy of MSApp Accepted and DSApp Accepted | REGS |  | UMSO |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#149b | Design clarification |  |  |  | Y | A single design approach has been taken across all Data and Metering Services for Service Provider Appointment – which does include the issuing of “Lapsed Notifications” in certain circumstances (e.g. Switch Cancellation). However, some Service Providers may have chosen an “Appointment Acceptance Only” type design approach, in which IF-035 is not used.
150 | MHHSP-IF-035 | SDSMDROutcome | B092.DI-979 = AC | REGS |  | SDSS, SUPC |  | 0 | 2 | 0 | 1 | Y |  |  |  |  | 5.2
151 | MHHSP-IF-035 | SDSMDROutcome | B092.DI-979 = RJ | REGS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2
152 | MHHSP-IF-035 | DCC-MDROutcome |  | REGS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2
154 | MHHSP-IF-036 | MSAppActive |  | REGS | EES | CustomSupplier, SDS, MSS, SUPL | LDSO | 1 | 4 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification; participant feedback | Y | Clarified the Primary routing targets | Design clarification
154a | MHHSP-IF-036 | MSAppActive |  | REGS | EES | CustomSupplier, ADS, MSA, SUPL | LDSO | 1 | 4 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#154a | Design clarification; participant feedback | Y | Clarified the Primary routing targets | Design clarification
154b | MHHSP-IF-036 | MSAppActive |  | REGS | EES | CustomSupplier, UMSDS, UMSO, SUPL | LDSO | 1 | 4 | 1 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#154b | Design clarification; participant feedback | Y | Clarified the Primary routing targets | Design clarification
155 | MHHSP-IF-036 | DSAppActive |  | REGS | MDS, EES | CustomSupplier, SDS, MSS, SUPL | LDSO | 2 | 4 | 1 | 1 | Y |  |  | This is for Smart and therefore includes Assigned MDR. Includes associated Export MPAN and at least 2 Related MPANs. |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification; participant feedback | Y | Clarified the Primary routing targets | Design clarification
155a | MHHSP-IF-036 | DSAppActive |  | REGS | MDS, EES | CustomSupplier, ADS, MSA, SUPL | LDSO | 2 | 4 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#155a | Design clarification; participant feedback | Y | Clarified the Primary routing targets | Design clarification
155b | MHHSP-IF-036 | DSAppActive |  | REGS | MDS, EES | CustomSupplier, UMSDS, UMSO, SUPL | LDSO | 2 | 4 | 1 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#155b | Design clarification; participant feedback | Y | Clarified the Primary routing targets | Design clarification
156 | MHHSP-IF-037 | MSDeApp |  | REGS | EES | MSSC | SUPC, LDSO | 1 | 1 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
156a | MHHSP-IF-037 | MSDeApp |  | REGS | EES | MSAC | SUPC, LDSO | 1 | 1 | 2 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#156a | Design clarification
156b | MHHSP-IF-037 | MSDeApp |  | REGS | EES | UMSO | SUPC, LDSO | 1 | 1 | 2 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#156b | Design clarification
157 | MHHSP-IF-037 | DSDeApp |  | REGS | MDS, EES | SDSC | SUPC, LDSO | 2 | 1 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
157a | MHHSP-IF-037 | DSDeApp |  | REGS | MDS, EES | ADSC | SUPC, LDSO | 2 | 1 | 2 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#157a | Design clarification
157b | MHHSP-IF-037 | DSDeApp |  | REGS | MDS, EES | UMSDSC | SUPC, LDSO | 2 | 1 | 2 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#157b | Design clarification
158 | MHHSP-IF-037 | MSDeAppUpdate |  | REGS |  | MSSC |  | 0 | 1 | 0 | 1 | Y | Y | Y |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
158a | MHHSP-IF-037 | MSDeAppUpdate |  | REGS |  | MSAC |  | 0 | 1 | 0 | 1 | [8 empty] | Y | Added Adv Ref#158a | Design clarification
158b | MHHSP-IF-037 | MSDeAppUpdate |  | REGS |  | UMSO |  | 0 | 1 | 0 | 1 | [8 empty] | Y | Added UM Ref#158b | Design clarification
159 | MHHSP-IF-037 | DSDeAppUpdate |  | REGS |  | SDSC |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
159a | MHHSP-IF-037 | DSDeAppUpdate |  | REGS |  | ADSC |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#159a | Design clarification
159b | MHHSP-IF-037 | DSDeAppUpdate |  | REGS |  | UMSDSC |  | 0 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added UM Ref#159b | Design clarification
160 | MHHSP-IF-038 | DirectContractDSAdd |  | SDSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | PP Feedback
161 | MHHSP-IF-038 | DirectContractDSAdd |  | ADSS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2 | Y | PP Feedback
161a | MHHSP-IF-038 | DirectContractDSAdd |  | UMSDS |  |  | REGS | 0 | 0 | 1 | 1 |  |  | Y
162 | MHHSP-IF-038 | DirectContractDSRemove |  | SDSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2
163 | MHHSP-IF-038 | DirectContractDSRemove |  | ADSS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2
163a | MHHSP-IF-038 | DirectContractDSRemove |  | UMSDS |  |  | REGS | 0 | 0 | 1 | 1 |  |  | Y | [5 empty] | Y | Added Unmetered scenario | Design clarification
164 | MHHSP-IF-038 | DirectContractMSAdd |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2
165 | MHHSP-IF-038 | DirectContractMSAdd |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2
166 | MHHSP-IF-038 | DirectContractMSRemove |  | MSSS |  |  | REGS | 0 | 0 | 1 | 1 | Y |  |  |  |  | 5.2
167 | MHHSP-IF-038 | DirectContractMSRemove |  | MSAS |  |  | REGS | 0 | 0 | 1 | 1 |  | Y |  |  |  | 5.2
168 | MHHSP-IF-039 | DirectContractMSAdd | DI-979='A' | REGS | EES | MSSS | SUPC | 1 | 1 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
168a | MHHSP-IF-039 | DirectContractMSAdd | DI-979='A' | REGS | EES | MSAS | SUPC | 1 | 1 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#168a | Design clarification
169 | MHHSP-IF-039 | DirectContractDSAdd | DI-979='A' | REGS | EES | SDSS | SUPC | 1 | 1 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
169a | MHHSP-IF-039 | DirectContractDSAdd | DI-979='A' | REGS | EES | ADSS | SUPC | 1 | 1 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#169a | Design clarification
169b | MHHSP-IF-039 | DirectContractDSAdd | DI-979='A' | REGS | EES | UMSDSS | SUPC | 1 | 1 | 1 |  |  |  | Y | [5 empty] | Y | Added Unmetered scenario | Design clarification
170 | MHHSP-IF-039 | DirectContractMSRemove |  | REGS | EES | MSSS |  | 1 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
170a | MHHSP-IF-039 | DirectContractMSRemove |  | REGS | EES | MSAS |  | 1 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#170a | Design clarification
171 | MHHSP-IF-039 | DirectContractDSRemove |  | REGS | EES | SDSS |  | 1 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
171a | MHHSP-IF-039 | DirectContractDSRemove |  | REGS | EES | ADSS |  | 1 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#171a | Design clarification
171b | MHHSP-IF-039 | DirectContractDSRemove |  | REGS | EES | UMSDSS |  | 1 | 1 | 0 | 1 |  |  | Y | [5 empty] | Y | Added Unmetered scenario | Design clarification
172 | MHHSP-IF-039 | DirectContractMSAdd | DI-979='R' | REGS |  | MSSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
172a | MHHSP-IF-039 | DirectContractMSAdd | DI-979='R' | REGS |  | MSAS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#172a | Design clarification
173 | MHHSP-IF-039 | DirectContractDSAdd | DI-979='R' | REGS |  | SDSS |  | 0 | 1 | 0 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
173a | MHHSP-IF-039 | DirectContractDSAdd | DI-979='R' | REGS |  | ADSS |  | 0 | 1 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#173a | Design clarification
174 | MHHSP-IF-040 | AnnualConsumption |  | MDS | EES |  | SUPC, SDSC, LDSO, REGS | 1 | 0 | 4 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification | Y | Ref #174b removed (unmetered) | Participant feedback and design team clarification (see Design Comment Summary) |  | DIN-617 raised to add a note to the "Interface Additional Information". This is to clarify the design position with regards to IF-023 Load Shape Totals Data and IF-040 Annual Consumption Data. Whilst these are provided to all data services, it is for each Data Service to determine if/how they wish to utilise these messages or not.
174a | MHHSP-IF-040 | AnnualConsumption |  | MDS | EES |  | SUPC, ADSC, LDSO, REGS | 1 | 0 | 4 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#174a | Design clarification
175 | MHHSP-IF-041 | SDS: ReadingCOS |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
176 | MHHSP-IF-041 | SDS: ReadingOnSite |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
177 | MHHSP-IF-041 | SUP: ReadingCOR |  | SUPS |  | SUPC, SUPL, SUPP, SDSC, SDSP, SDSS | LDSO | 0 | 6 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
177a | MHHSP-IF-041 | SUP: ReadingCOR |  | SUPS |  | SUPC, SUPL, SUPP, ADSC, ADSP, ADSS | LDSO | 0 | 6 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#177a; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
178 | MHHSP-IF-041 | SUP: ReadingCOS |  | SUPS |  | SUPC, SUPL, SUPP, SDSC, SDSP, SDSS | LDSO | 0 | 6 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
178a | MHHSP-IF-041 | SUP: ReadingCOS |  | SUPS |  | SUPC, SUPL, SUPP, ADSC, ADSP, ADSS | LDSO | 0 | 6 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#178a; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
179 | MHHSP-IF-041 | SUP: SupplierAgreedCOS |  | SUPS |  | SUPC, SUPL, SUPP, SDSC, SDSP, SDSS | LDSO | 0 | 6 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
179a | MHHSP-IF-041 | SUP: SupplierAgreedCOS |  | SUPS |  | SUPC, SUPL, SUPP, ADSC, ADSP, ADSS | LDSO | 0 | 6 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#179a; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
180 | MHHSP-IF-041 | SUP: ReadingOverride |  | SUPS |  | SUPC, SUPL, SUPP, SDSC, SDSP, SDSS | LDSO | 0 | 6 | 1 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
180a | MHHSP-IF-041 | SUP: ReadingOverride |  | SUPS |  | SUPC, SUPL, SUPP, ADSC, ADSP, ADSS | LDSO | 0 | 6 | 1 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#180a; Updates to event code | Design clarification; PP feedback on inconsistency with DES138
181 | MHHSP-IF-041 | DS: ReadingRemv |  | ADSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
182 | MHHSP-IF-041 | DS: ReadingInstl |  | ADSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
183 | MHHSP-IF-041 | DS: ReadingRemote |  | ADSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138 |  |  |  | Y | Clarified by the Design Team as also applying to ADSC; a DIN would need to be raised to change this.
184 | MHHSP-IF-041 | DS: ReadingEnergisationChg |  | ADSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138 |  |  |  | Y | Clarified by the Design Team as also applying to ADSC; a DIN would need to be raised to change this.
185 | MHHSP-IF-041 | DS: DSEstimate |  | ADSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138 |  |  |  | Y | Clarified by the Design Team as also applying to ADSC; a DIN would need to be raised to change this.
186 | MHHSP-IF-041 | DS: ReadingRemv |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
187 | MHHSP-IF-041 | DS: ReadingInstl |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
188 | MHHSP-IF-041 | DS: ReadingRemote |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
189 | MHHSP-IF-041 | DS: ReadingEnergisationChg |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
190 | MHHSP-IF-041 | DS: DSEstimate |  | SDSS |  |  | SUPC, LDSO | 0 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
191 | MHHSP-IF-041 | MS: ReadingRemv |  | MSAS |  |  | SUPC, ADSC, LDSO | 0 | 0 | 3 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
192 | MHHSP-IF-041 | MS: ReadingInstl |  | MSAS |  |  | SUPC, ADSC, LDSO | 0 | 0 | 3 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
193 | MHHSP-IF-041 | MS: ReadingEnergisationChg |  | MSAS |  |  | SUPC, ADSC, LDSO | 0 | 0 | 3 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
194 | MHHSP-IF-041 | MS: ReadingOnSite |  | MSAS |  |  | SUPC, ADSC, LDSO | 0 | 0 | 3 | 1 |  | Y |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
195 | MHHSP-IF-041 | MS: ReadingRemv |  | MSSS |  |  | SUPC, SDSC, LDSO | 0 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
196 | MHHSP-IF-041 | MS: ReadingInstl |  | MSSS |  |  | SUPC, SDSC, LDSO | 0 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES138
197 | MHHSP-IF-041 | MS: ReadingEnergisationChg |  | MSSS |  |  | SUPC, SDSC, LDSO | 0 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES145
198 | MHHSP-IF-041 | MS: ReadingOnSite |  | MSSS |  |  | SUPC, SDSC, LDSO | 0 | 0 | 3 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Updates to event code | PP feedback on inconsistency with DES146
199 | MHHSP-IF-043 | ConnectionTypeChange |  | REGS | MDS, EES |  | SUPC, SDSC, MSSC, LDSO | 2 | 0 | 4 | 1 | Y |  |  |  |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
199a | MHHSP-IF-043 | ConnectionTypeChange |  | REGS | MDS, EES |  | SUPC, ADSC, MSAC, LDSO | 2 | 0 | 4 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#199a | Design clarification | Y | Removed 199b (unmetered) | Participant feedback and Design clarification
200 | MHHSP-IF-044 | MarketSegementChange |  | REGS | MDS, EES |  | SUPC, LDSO | 2 | 0 | 2 | 1 | Y |  |  |  |  | 5.2 |  | 5.2.1 impact
200a | MHHSP-IF-044 | MarketSegementChange |  | REGS | MDS, EES |  | SUPC, LDSO | 2 | 0 | 2 | 1 |  | Y | [6 empty] | Y | Added Ref#200a | Design clarification | Y | Removed 200b (unmetered) | Participant feedback and Design clarification
201 | MHHSP-IF-045 | InvalidMarketSegment |  | REGS |  |  | SUPC, SDSC, MSSC | 0 | 0 | 3 | 1 | Y |  |  | REGS will need to be able to initiate generation of this message in some manner. Includes Registration Reminder Additional Information. |  | 5.2 | Y | 5.2.1 impact | Y | Removed Adv and UM | Design clarification
201a | MHHSP-IF-045 | InvalidMarketSegment |  | REGS |  |  | SUPC, ADSC, MSAC | 0 | 0 | 3 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#201a | Design clarification
202 | MHHSP-IF-045 | ConsentGranularityInvalid |  | REGS |  |  | SUPC | 0 | 0 | 1 | 1 | Y |  |  | REGS will need to be able to initiate generation of this message in some manner. Includes Registration Reminder Additional Information. |  | 5.2 | Y | 5.2.1 impact
203 | MHHSP-IF-045 | NoMSAppointed |  | REGS |  |  | SUPC | 0 | 0 | 1 | 1 | Y |  |  | REGS will need to be able to initiate generation of this message in some manner. Does not include Registration Reminder Additional Information. |  | 5.2
204 | MHHSP-IF-045 | NoDSAppointed |  | REGS |  |  | SUPC | 0 | 0 | 1 | 1 | Y |  |  | REGS will need to be able to initiate generation of this message in some manner. Does not include Registration Reminder Additional Information. |  | 5.2
205 | MHHSP-IF-047 | ISD |  | ISD | All Roles |  |  | 1 | 0 | 0 | 1 | Y |  |  | Sends Industry Standing Data to Participants |  | 5.2 |  |  | Y | Removed Adv and UM | Design clarification |  |  |  | Y | MHHS-IF-047 is used to send the ISD catalogue information from DAH to DIP, hence the verification of the same message from DAH to LSS and MDS are not covered in IF-047, they are covered in a separate Helix-Interfaces (ex: Helix-IF-001). So for CIT the scope of testing for IF-047 would be that ISD publishing catalogue has been sent from DAH to DIP
205a | MHHSP-IF-047 | ISD |  | ISD | All Roles |  |  | 1 | 0 | 0 | 1 |  | Y |  | Sends Industry Standing Data to Participants |  |  |  |  | Y | Added Adv Ref#205a | Design clarification |  |  |  | Y | MHHS-IF-047 is used to send the ISD catalogue information from DAH to DIP, hence the verification of the same message from DAH to LSS and MDS are not covered in IF-047, they are covered in a separate Helix-Interfaces (ex: Helix-IF-001). So for CIT the scope of testing for IF-047 would be that ISD publishing catalogue has been sent from DAH to DIP
205b | MHHSP-IF-047 | ISD |  | ISD | All Roles |  |  | 1 | 0 | 0 | 1 |  |  | Y | Sends Industry Standing Data to Participants |  |  |  |  | Y | Added UM Ref#205b | Design clarification |  |  |  | Y | MHHS-IF-047 is used to send the ISD catalogue information from DAH to DIP, hence the verification of the same message from DAH to LSS and MDS are not covered in IF-047, they are covered in a separate Helix-Interfaces (ex: Helix-IF-001). So for CIT the scope of testing for IF-047 would be that ISD publishing catalogue has been sent from DAH to DIP
206 | MHHSP-IF-050 | MPANCreation |  | REGS | EES |  |  | 1 | 0 | 0 | 1 | Y |  |  |  |  | 5.2 |  |  | Y | Removed Adv and UM; Removed note to 'Include one linked Export MPAN and at least 2 Related MPANs' | Design clarification; participant feedback
206a | MHHSP-IF-050 | MPANCreation |  | REGS | EES |  |  | 1 | 0 | 0 | 1 |  | Y | [6 empty] | Y | Added Adv Ref#206a | Design clarification | Y | Removed 206b (unmetered) | Participant feedback and Design clarification
207 | MHHSP-IF-050 | MPStatusChange |  | REGS | EES |  |  | 1 | 0 | 0 | 1 | Y |  |  |  |  | 5.2
208 | MHHSP-IF-050 | GreenDeal |  | REGS | EES |  |  | 1 | 0 | 0 | 1 | Y |  |  |  |  | 5.2
[8 empty] | 164 | 264 | 351 | 286 | [8 empty] | 244 |  |  | 36 |  |  | 30
Note on Q1: Sender sends out relevant message - up to Sender to initiate message in appropriate way Initiate by sending… - up to SI to initiate test using simulated endpoints

## Sending Summary By Role
SENDING
Sender | Count of Ref #
ADSS | 12
DIP | 1
ISD | 3
LDSO | 6
LSS | 5
MDS | 11
MSAS | 15
MSSS | 14
REGS | 156
SDSS | 13
SUPS | 44
UMSDS | 5
UMSO | 2
(blank)
Grand Total | 287
NOTE: Double-click on Count of Ref # to generate new sheet which lists all the relevant messages

## Data Service (hidden)
Sender | Interface | Interface Name | From | Always | Primary | Secondary | Event Code/Conditions
Data Service | MHHSP-IF-028 | Supplier Consumption Amendment Request Response | Data Service |  | Supplier |  | Consumption Element
Data Service | MHHSP-IF-034 | Service Provider Appointment Request Response | Data Service/Metering Service |  |  | REGS | DS App SP Response
Data Service | MHHSP-IF-034 | Service Provider Appointment Request Response | Data Service/Metering Service |  |  | REGS | SDS MDR Update
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact MS Add
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact DS Add
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact MS Remove
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact DS Remove
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingRemv
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingInstl
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingRemote
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingEnergisationChg, DSEstimate
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: DSEstimate
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SUPO, SDSC, SDSO | SDS: ReadingCOS,
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SUPO, SDSC, SDSO | SDS: ReadingOnSite

## LDSO Receiving Summary
LDSO Receiving Summary
Always | All Roles | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-047 |  | Grand Total |  | MHHSP-IF-001
Grand Total |  |  |  | MHHSP-IF-006
MHHSP-IF-008
MHHSP-IF-009
MHHSP-IF-013
MHHSP-IF-014
MHHSP-IF-018
MHHSP-IF-019
MHHSP-IF-020
MHHSP-IF-021
MHHSP-IF-026
MHHSP-IF-036
MHHSP-IF-037
MHHSP-IF-040
MHHSP-IF-041
MHHSP-IF-043
MHHSP-IF-044
Grand Total

## ADS Receiving Summary
ADS Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-022 |  | MHHSP-IF-013 |  | MHHSP-IF-006
MHHSP-IF-023 |  | MHHSP-IF-014 |  | MHHSP-IF-008
MHHSP-IF-047 |  | MHHSP-IF-016 |  | MHHSP-IF-018
Grand Total |  | MHHSP-IF-024 |  | MHHSP-IF-020
|  | MHHSP-IF-027 |  | MHHSP-IF-026
|  | MHHSP-IF-033 |  | MHHSP-IF-040
|  | MHHSP-IF-035 |  | MHHSP-IF-041
|  | MHHSP-IF-036 |  | MHHSP-IF-043
|  | MHHSP-IF-037 |  | MHHSP-IF-045
|  | MHHSP-IF-039 |  | Grand Total
MHHSP-IF-041
Grand Total

## LSS Receiving Summary
LSS Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-021 |  | Grand Total |  | Grand Total
MHHSP-IF-026
MHHSP-IF-047
Grand Total

## MDS Receiving Summary
MDS Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-001 |  | Grand Total |  | Grand Total
MHHSP-IF-008
MHHSP-IF-009
MHHSP-IF-018
MHHSP-IF-020
MHHSP-IF-021
MHHSP-IF-036
MHHSP-IF-037
MHHSP-IF-043
MHHSP-IF-044
MHHSP-IF-047
Grand Total

## MSA Receiving Summary
MSA Receiving Summary
Always | All Roles | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-047 |  | MHHSP-IF-006 |  | MHHSP-IF-006
Grand Total |  | MHHSP-IF-008 |  | MHHSP-IF-008
|  | MHHSP-IF-033 |  | MHHSP-IF-018
|  | MHHSP-IF-035 |  | MHHSP-IF-020
|  | MHHSP-IF-036 |  | MHHSP-IF-026
|  | MHHSP-IF-037 |  | MHHSP-IF-043
|  | MHHSP-IF-039 |  | MHHSP-IF-045
|  | Grand Total |  | Grand Total

## MSS Receiving Summary
MSS Receiving Summary
Always | All Roles | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-047 |  | MHHSP-IF-006 |  | MHHSP-IF-004
Grand Total |  | MHHSP-IF-008 |  | MHHSP-IF-006
|  | MHHSP-IF-033 |  | MHHSP-IF-008
|  | MHHSP-IF-035 |  | MHHSP-IF-018
|  | MHHSP-IF-036 |  | MHHSP-IF-020
|  | MHHSP-IF-037 |  | MHHSP-IF-026
|  | MHHSP-IF-039 |  | MHHSP-IF-043
|  | Grand Total |  | MHHSP-IF-045
Grand Total

## REGS Receiving Summary
REGS Receiving Summary
Always | All Roles | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-047 |  | Grand Total |  | MHHSP-IF-005
Grand Total |  |  |  | MHHSP-IF-007
MHHSP-IF-019
MHHSP-IF-025
MHHSP-IF-031
MHHSP-IF-034
MHHSP-IF-038
MHHSP-IF-040
Grand Total

## SDS Receiving Summary
SDS Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-022 |  | MHHSP-IF-013 |  | MHHSP-IF-006
MHHSP-IF-023 |  | MHHSP-IF-014 |  | MHHSP-IF-008
MHHSP-IF-047 |  | MHHSP-IF-024 |  | MHHSP-IF-018
Grand Total |  | MHHSP-IF-027 |  | MHHSP-IF-020
|  | MHHSP-IF-033 |  | MHHSP-IF-026
|  | MHHSP-IF-035 |  | MHHSP-IF-040
|  | MHHSP-IF-036 |  | MHHSP-IF-041
|  | MHHSP-IF-037 |  | MHHSP-IF-043
|  | MHHSP-IF-039 |  | MHHSP-IF-045
|  | MHHSP-IF-041 |  | Grand Total
Grand Total

## SUPS Receiving Summary
SUPS Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-022 |  | MHHSP-IF-001 |  | MHHSP-IF-004
MHHSP-IF-023 |  | MHHSP-IF-002 |  | MHHSP-IF-006
MHHSP-IF-047 |  | MHHSP-IF-007 |  | MHHSP-IF-008
Grand Total |  | MHHSP-IF-013 |  | MHHSP-IF-009
|  | MHHSP-IF-014 |  | MHHSP-IF-018
|  | MHHSP-IF-020 |  | MHHSP-IF-020
|  | MHHSP-IF-021 |  | MHHSP-IF-037
|  | MHHSP-IF-026 |  | MHHSP-IF-039
|  | MHHSP-IF-028 |  | MHHSP-IF-040
|  | MHHSP-IF-032 |  | MHHSP-IF-041
|  | MHHSP-IF-035 |  | MHHSP-IF-043
|  | MHHSP-IF-036 |  | MHHSP-IF-044
|  | MHHSP-IF-041 |  | MHHSP-IF-045
|  | Grand Total |  | Grand Total

## UMSDS Receiving Summary
UMSDS Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-022 |  | MHHSP-IF-013 |  | MHHSP-IF-008
MHHSP-IF-047 |  | MHHSP-IF-014 |  | MHHSP-IF-018
Grand Total |  | MHHSP-IF-024 |  | Grand Total
MHHSP-IF-033
MHHSP-IF-035
MHHSP-IF-036
MHHSP-IF-037
MHHSP-IF-039
Grand Total

## UMSO Receiving Summary
UMSO Receiving Summary
Always | All Roles | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-047 |  | MHHSP-IF-008 |  | MHHSP-IF-008
Grand Total |  | MHHSP-IF-033 |  | MHHSP-IF-018
|  | MHHSP-IF-035 |  | Grand Total
MHHSP-IF-036
MHHSP-IF-037
Grand Total

## EES Receiving Summary
EES Receiving Summary
Always | (Multiple Items) | Primary | (Multiple Items) | Secondary | (Multiple Items)
Interface |  | Interface |  | Interface
MHHSP-IF-001 |  | Grand Total |  | Grand Total
MHHSP-IF-006
MHHSP-IF-008
MHHSP-IF-009
MHHSP-IF-018
MHHSP-IF-020
MHHSP-IF-026
MHHSP-IF-036
MHHSP-IF-037
MHHSP-IF-039
MHHSP-IF-040
MHHSP-IF-043
MHHSP-IF-044
MHHSP-IF-047
MHHSP-IF-050
Grand Total