## Consolidated Tab Only
Organisation: | Various
Constituency:
Date: | 24/7/2023 to 28/7/2023 | MHHS-DEL1422 SIT CIT Test Scenarios Assurance Review Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | Participant #1 | Receiving summary by Role | XDS | MHHSP-IF-036 is missing from the summary list under data services | Actioned | We have updated the scenarios with the specific data service routing, as opposed to the "X" notation. We have also made corrections to the Receiving Summary by Role tables for the individual services that resolves this issue with regards to IF-036 | Recommend closed
2 | Participant #1 | Receiving summary by Role | XDS | MHHSP-IF-047 is duplicate across ADS, SDA and XDS is this necessary? | Actioned | We have updated the scenarios with the specific data service routing, as opposed to the "X" notation. This is now reflected in the Receiving Summary by Role sheet. | Recommend closed
3 | Participant #1 | Sending Scenarios | 135 | Requirement ref 135: Typo in Event code should be MSAppSPRequest | Actioned | This has been corrected in the latest release of the CIT scenarios | Recommend closed
4 | Participant #1 | Sending Scenarios | 136 | Requirement ref 136: Typo in Event code should be DSAppSPRequest | Actioned | This has been corrected in the latest release of the CIT scenarios | Recommend closed
5 | St Clements | Sending Scenarios | Ref: 81a to 83a Ref: 84a to 86a Ref 90 to 95 MHHSP-IF-020 | for import/export linkages:- Accepted IF-020 are from MPRS Rejected IF-020 are from LDSO for related MPANs:- Accepted IF-020 are from MPRS Rejected IF-020 are from MPRS Therefore - refs 81a, 82a & 83a are invalid - refs 84a, 85a & 86a are invalid - tests 90, 91 and 92 should be sent to LDSOs - tests 93, 94 and 95 should be sent to MPRS | Accept | The scenarios align with DES138-Interface Catalogue v5.2.1. We will pass your comments on to the design team so that they can log any errors in the DES138 as DINs and apply updates. Once these are reflected in the DES-138 we will apply updates to the CIT scenarios. | Recommend closed
6 | St Clements | Sending Scenarios | Ref 83 MHHSP-IF-020 | MPRS cannot add DI-120 Additional Information, therefore the test cases to 'include additional information' for REGS are not possible | Actioned | We have updated the Notes field to remove this reference to the DI-120 | Recommend closed
7 | St Clements | Sending Scenarios | Ref 121 MHHSP-IF-026 | SMSO is only relevant to SMART market segment | Actioned | We have removed 121a and 121b, which refer to ADV and UNMET. | Recommend closed
8 | St Clements | Sending Scenarios | Ref 168, 170 & 172 MHHSP-IF-039 | Although Direct Contact is allowable for an unmetered supply, it is not possible to change MS of UMSO, so DirectContractMSAdd & DirectContractMSRemove are not relevant to unmetered market segment? | Actioned | We have remove Unmetered scenario for Events MSAdd/Remove Row273/Ref#168b, Row276/Ref#169b. Row279/Ref#170b, Row282/ref171b, Row285/Ref#172b, Row 288/Ref#173b | Recommend closed
9 | St Clements | Sending Scenarios | Ref 125 MHHSP-IF-026 | [SSCandProfileClass] should not be relevant to unmetered market segment in MHHS world - all unmetered should be HH before MHHS starts | Actioned | We have removed 198/Ref#125b Unmetered scenario as per comments re all meters required to be half hourly | Recommend closed
10 | St Clements | Sending Scenarios | Reg 177 to 180 MHHSP-IF-041 | I do not believe that 'readings' tests are relevant to unmetered market segment | Actioned | Removed Unmetered scenario for IF-041 as per Interface Notes section and as suggested. Row 296/Ref#177b, Row299/Ref178b, Row302/Ref#179b, Row305/Ref#180b, | Recommend closed
11 | St Clements | Sending Scenarios | Ref 206 MHHSP-IF-050 | MPAN creation cannot include related MPANs. They cannot be related until a supplier has been registered. Import and Export can be added at MPAN creation. | Actioned | Column Q in V5.2.1 CIT Scenarios details 'Include one linked Export MPAN and at least 2 Related MPANs.' Interface cat states - Related/Linked MPANs cannot be grouped together at the point of MPAN creation. Grouping will always occur as a separate action after MPAN creation which will be notified on PUB-020 | Recommend closed
12 | Utilita | Notes on Scenarios tab | N.A. | It's not clear why the details of the Receiving Scenarios are not included. Presumably that’s because the SI will be triggering those whereas the Service is required to action the Sending Scenarios? Can a statement be made confirming the above? | Accept | The receiving scenario details correspond to the sending scenario details, in terms of conditions and variants, so these have not been repeated in a separate tab. Note that the test cases will be elaborated explicitly for the receiving scenarios. | Recommend closed
13 | Utilita | Receiving Summary by Role tab | N.A. | Could each role be shown on an individual tab? It would make this section easier to read | Actioned | We have split this out so each role gets its own tab | Recommend closed
14 | Utilita | Sending Scenarios tab | N.A. | In the Notes on Scenarios tab is states "Each service will be expected to receive and to send one example of each IF/PUB message relevant to it in order for that service to pass SIT CIT " Can it be made clear on the "Sending scenarios" tab which one of the examples in each message this statement refers to (I.e. which is the priority variant to send) , assuming the remaining examples are covered by the statement "However a Sender which has passed all its own tests will also be required to send additional messages to test the DIP routing." | Reject | This will vary from role to role; there is not a simple way to represent this in the sheet as currently structured. | Recommend closed
15 | Northern Powergrid |  | Sending Scenarios MHHSP-IF-020 | For the interface 'MHHSP-IF-020' The market roles mentioned under Always, Primary and Secondary columns are not sync in CIT test scenario and MHHSP DES138 v5.1.2 documents 1. As per the MHHSP DES138 v5.1.2 (Interface CatLog) - under tab '02_IF-020', the 'Always' routing shows only 'EES' - under tab 'IF_LIST', the 'Always' routing shows 'Supplier, EES' But as per CIT Test Scenario document, there are some scenarios mentioned 'Always' routing as 'EES, MDS'. 2. As per the MHHSP DES138 v5.1.2 - - under tab '02_IF-020', the 'Primary' routing shows only 'SUPS' - under tab 'IF_LIST', the 'Primary' routing shows blank column But as per CIT Test Scenario document, the 'Primary' routing column shows 'SUPS, SUPL' based on scenario. The same goes to Secondary routing, details are not in sync across all the areas. | Actioned | As part of the recent uplift we have now corrected the alignment with 5.2.1 | Recommend closed
16 | Northern Powergrid |  | Sending Scenarios tab | The Secondary routing short code is prefixed with 'X' for few of the cells which we presume represents as Smart, Advanced and Un-metered. Could you please confirm the same? Are you going to test for each of the meter type area? In this case, the 'Number of Secondaries' column count would increase. | Actioned | We have updated the scenarios to reflect the actual routing for the segment variants. | Recommend closed
17 | Northern Powergrid |  | MHHSP-IF-041 | As per the test Scenario document 'LDSO' role is present under 'secondary' routing. However as per the MHHSP DES138 v5.1.2 (Interface CatLog) and - under 'IF_LIST' tab in excel, the LDSO is not mentioned under either Always, Primary or Secondary - under '02_IF-041' tab in excel, the LDSO is present under 'Always' column. Please confirm which document is correct? All these documents should be in sync. | Actioned | The routing is now correct for this and aligns with DES138 5.2.1 | Recommend closed
18 | Northern Powergrid |  | MHHSP-IF-019 | As per the test Scenario document 'REGS' role is present under 'secondary' routing. However as per the MHHSP DES138 v5.1.2 (Interface CatLog) and - under 'IF_LIST' tab in Excel, REGS is present under Always - under '02_IF-019' tab in Excel, REGS is present under 'secondary' column. Please confirm which document is correct? All these documents should be in sync. | Reject | The routing is correct as per DES138 5.2.1 | Recommend closed
19 | IMServ | 101 |  | Reactive power test for SDS is still present, is this required? We commented previously there doesn't appear to be a requirement for this in other documents for SDS and haven't had comment responses back. | Reject | ReactivePower is specified as an event code in DES138 5.2.1. This needs to be challenged with MHHS Design and we will update in line with changes to the design baseline | Recommend closed
20 | IMServ |  |  | Receiving scenarios for XDS now have IF-008 and IF-037, but not IF-036. Is this IF out of scope although it is something we do appear to need to receive | Actioned | This has been updated in the new release of CIT Scenarios | Recommend closed
21 | IMServ |  |  | There seems to be a link embedded in the spreadsheet that doesn't update and flags a warning 'Failed to update' | Reject | We would need a reference to the specific link that is not working. Do let us now if it still not working in the latest release with a specific reference or snapshot please. | Recommend closed
22 | IMServ |  |  | Column O Ref #10 is set to Y - should this be null? | Actioned | Col O Ref#10 in scenarios 5.2.1 is blank | Recommend closed
23 | IMServ | 41 & 43 |  | Marked as having 7 secondaries but only 6 are listed, is this correct? | Actioned | Col L secondary now shows as 6 with 6 listed in col I - | Recommend closed
24 | IMServ | 45 |  | Marked as having 15 secondaries but only 6 are listed, is this correct? | Actioned | Col L secondary now shows as 6 with 6 listed in col I - | Recommend closed
25 | IMServ | 154 |  | Marked as having 5 Primaries but only 4 are listed | Actioned | Col K now shows 4 primaries with 4 listed in Col H | Recommend closed
26 | IMServ | 155 |  | Marked as having 9 primaries but only 4 are listed | Actioned | This has been updated in the new release of CIT Scenarios | Recommend closed
27 | Participant #2 | 84 to 86a |  | MHHS-IF-020 this interface is out of scope for CIT from MDS point of view as agreed in-MHHS-DIN-84 | Accept | DES138 v5.2.1 still has MDS listed for Related. A design query will need to be raised to address this. When this progresses and is changed in the DES138, we will update the scenarios inline. | Recommend closed
28 | Participant #2 | 205 |  | MHHS-IF-047 is used to send the ISD catalogue information from DAH to DIP, hence the verification of the same message from DAH to LSS and MDS are not covered in IF-047, they are covered in a separate Helix-Interfaces (ex: Helix-IF-001). So for CIT the scope of testing for IF-047 would be that ISD publishing catalogue has been sent from DAH to DIP | Accept | We will raise a query with the Design team to get a clarification of how this should be handled in CIT | Recommend closed
29 | Participant #2 | 125 |  | MHHS-IF-026, SSC and Profile class are not in CIT scope as agreed in MHHS-DIN-415 | Accept | DES138 v5.2.1 still has SSC and Profile Class listed. A design query will need to be raised to address this. When this progresses and is changed in the DES138, we will update the scenarios inline. | Recommend closed
30 | DCC | General | Test Scenarios v5.2 | All scenarios seem positive scenarios (happy path)? I'd expect to see negative scenarios in here to review errors etc. | Reject | PIT testing will address comprehensive coverage of error code generation where validation rules are breached | Recommend closed
31 | DCC | General | Test Scenarios v5.2 | Unable to see scenarios were the max number of ESME's eligible for 1 MPAN (i.e. 5 max) | Reject | This will be addressed by later phases of testing | Recommend closed
32 | DCC | General | Test Scenarios v5.2 | Should this also cover SOLR event where consumption data has been sporadic but now moving to HHS? Consumption data will be mixed | Reject | This is outside the bounds of CIT scope; we will review as part of finalising SIT Functional scenarios and test cases | Recommend closed
33 | DCC | General | Test Scenarios v5.2 | Should ENO/EIS be included in the role codes? | Reject | The design baseline, in particular the DES138 Interface Catalogue, does not specify ENO/EIS role codes. | Recommend closed
34 | DCC | General | Test Scenarios v5.2 | Should the scenarios include malformed formats of data being sent? | Reject | PIT testing will address comprehensive coverage of error code generation where validation rules are breached | Recommend closed
35 | Participant #3 | General |  | We have not received all comments back from previous review therefore are unable to confirm what responses have been given. | Actioned | We are publishing the comments and responses from the first review round | Recommend closed
36 | Participant #3 | Notes on Scenarios | Sending Scenarios | There is a reference to a document within this section - MHHSP-DES138 - Interface Catalogue, but there is no reference section and links to this document within this review. Please update the document to include the correct link to the document | Reject | The full name and version of the interface catalogue is documented in the Change Control tab, as well as a link to the Collaboration Base link. The document can be found most reliably by searching on the Programme Collaboration Base, entering the document name "MHHSP-DES138-Interface Catalogue v5.2.1" in the "Search across sites" field at the top of the page. | Recommend closed
37 | Participant #3 | Notes on Scenarios | Sending Scenarios | There is a link to the SIT CIT Test Approach and Plan within this page, please move to the references section as per all other documents produced by the programme | Reject | The link is here for convenient access when reviewing the instructions. It is also now included in the references on the Change Control tab. | Recommend closed
38 | Participant #3 | Notes on Scenarios | Sending Scenarios | Suggests full business orchestration needs to be in place for certain scenarios (e.g. IF-05, IF-06), please supply a complete list of these scenarios for all parties. Please also clarify this scenario as contradictory discussions have been held in SITWG/bi-laterals with the programme, i.e. that no business orchestration is required in CIT. Which is correct? | Reject | The Notes on Scenarios reflect the current wording in the SIT Test Approach and Plan. There should be no inference that full business orchestration is required for CIT. | Recommend closed
39 | Participant #3 | Sending Scenarios | Ref#4+5 | This flow states its optional and is a bi-lateral agreement for Comms Hub information, as per DES-138, what happens where the test participant has no business use for this process and will not be developing this interface, can this test be omitted or does the programme demand those parties undertake additional development at significant impact to the party for functionality they will not use? | Reject | Will need to validate with the code bodies the requirements for qualification and ratify any scope exclusions related to a participant's context. | Recommend closed
40 | Participant #3 | Sending Scenarios | General | Within the scenarios we are using unnecessary data due to the IF files containing the same common blocks for each scenario (IF-006). Can these scenarios be combined to reduce usage as one test will confirm the route. | Reject | We are looking to cover the routing variations associated with each event code, as well as the segment variants | Recommend closed
41 | Participant #3 | Sending Scenarios | Ref#45 | Number of Primaries and Secondaries does not match the list marked within the previous columns, please check and update the document as necessary. | Actioned | This has been corrected in the new release of CIT Scenarios | Recommend closed
42 | Participant #3 | Sending Scenarios | General | Are the scenarios mandatory, regarding Supplier functionality, e.g. if supplier does not have Smart segment are these tests needed in CIT If they are mandatory and the party does not have that segment, please clarify how the programme expects such parties undertake that testing and provides the required evidence. | Reject | Will need to validate with the code bodies the requirements for qualification and ratify any scope exclusions related to a participant's context. | Recommend closed
43 | IPA | Overall | Overall | The expected outputs against the scenarios seems to be missing suggest to provide a separate column to detail out the expected output (s) for each of the scenarios. Example: when a supplier sends out IF-001 ( change supplier ) they will be expecting a response back from the DIP which can either be an IF or PUB message or can be a simple ACK/NACK and might have and ID associated to the response. Can this be mapped against the scenarios? | Reject | The existing E2E001 End-to-End Solution Architecture, combined to with test data defined in the forthcoming test cases, specifies the relevant details. | Recommend closed
44 | IPA | Sending scenarios | IF-001 | We are not able to identify clearly the various sub/scenarios/cases and the negative scenarios corresponding the primary scenarios. Can we please add all the variations and negative scenarios which needs to be tested in order to ensure the application is tested thoroughly against the design. This will give the participants and the programme an assurance from the test design phase on covering the minimum requirements. | Reject | The test cases will be provided as a separate deliverable, with full traceability to the scenarios, and will also provide details of the data conditions to be applied. For the message sending and receipt, the full coverage of levels 1-4 validation and error messaging will be covered in PIT testing in the run up to CIT. | Recommend closed
45 | IPA | Sending scenarios |  | From reading the scenarios we feel there needs to be more clarity on test data. All the fields to test a scenario that needs to be set up/fabricated should be clearly defined and the responsibility of cleansing the data needs to be clearly defined. | Reject | Please reference the Test Data Approach and plan for details on this | Recommend closed
46 | IPA | Sending scenarios |  | There are certain scenarios e.g. IF005 / IF006 which have multiple scenarios and multiple sub scenarios. Is there any identified dependences on them for execution? Example - Ref ID 6-15 can they be run independently or do they have any interlinked dependencies? | Reject | The CIT scenarios can be run independently | Recommend closed
47 | IPA | Sending scenarios |  | Are these scenarios for suppliers only? Are we expecting a separate list of scenarios for CIT for central parties for example Helix? | Reject | A full range of participant roles and their interactions with the DIP are covered in the document as is, including Central Parties (LSS, MDS) | Recommend closed
48 | SSEN | Sending Scenarios | MHHSP-IF-039 | What is the Customer Direct Contract? This is not familiar to UMSO. A customer cannot have a direct contract with an UMSO, it must be via the DNO/iDNO. | Actioned | This has been corrected in the new release of CIT Scenarios | Recommend closed
49 | SSEN | Sending Scenarios | MHHSP-IF-007 | For Unmetered only - post receiving notification, the de-energisation is always carried out and never not actioned. Therefore this scenario is not valid. | Reject | We need to confirm that you can still process the message even if you don't not action it. | Recommend closed
50 | SSEN | Sending Scenarios | MHHS-IF-014 | This is not received by the LDSO. | Accept | The scenario aligns to the IF Catalogue v5.2.1. A query would need to be raised with the Design Team to challenge this. | Recommend closed
51 | SSEN | Sending Scenarios | MHHSP-IF-037 | This flow is currently received as a DB02. Business process suggests the IF-037 will be received if the LDSO is subscribed. What does this mean? | Reject | The scenario reflects the context, mapping and routing, as specified in the DES138 v5.2.1 for the IF-037. It may be best to raise a Design query to resolve this. | Recommend closed
52 | RECCo | Receiving Summary by role | EES | EES isn't expecting to ingest the IF-001 as this information is received direct from the CSS | Accept | Scenario for IF-01 has been authored in line with IF Catalogue 5.2.1, which EES are a recipient of the data from REGS. A query will need to be raised with Design to challenge this. | Recommend closed
53 | RECCo | Receiving Summary by role | LDSO | Please could you confirm why all the flows have been removed from LDSO always routing and moved to secondary routing under the receiving summary by role tab | Reject | This is in line with changes to the DES138 Interface Catalogue in version 5.2.1. | Recommend closed
54 | Callisto | Various | Various | Our test analyst reviewed the document and struggled to find any changes in the scenarios for IF-038 and 2 of the IF-021 ones. We are not sure if we have missed something important - please could the changes that are indicated be clarified? | Reject | We have identified the scenarios that have changed, or have been added with information on the change reason. The scenarios should be reviewed in conjunction with the Red-lined version of the DES138 Interface Catalogue v5.2.1. | Recommend closed
55 | C&C Group | N/A | Sending Scenarios | Test Scenarios 81a - 86a Appear to relate to changes that are planned for Interim Release 3 (according to the DIN Log), hence should not be included within SIT CIT which is baselined at IR2. | Actioned | We can confirm that the scenarios align with the DES138 v5.2.1, which is the Interim Release 2 baseline version | Recommend closed
56 | C&C Group | N/A | Sending Scenarios | Column P allows filtering on scenarios relating to the UMS role, this shows 76 test scenarios that are to be tested, many of those highlighted do not appear to be valid UMS tests. | Reject | Please check the current version of the scenarios. If you can identify invalid scenarios please provide specific reference numbers. We have made every effort to align with the DES138 Interface Catalogue v5.2.1. We can raise design queries where there are issues with the DES138, that have filtered through to the test scenarios. | Recommend closed
57 | C&C Group | N/A | Sending Scenarios | Columns G,H,I do not appear to show and test scenarios to be included for the UMSO Role Code, this conflicts with Column P which shows 76 such test cases (see comment C&C002) | Reject | Please double check the latest version as there are several scenarios with UDS as Always; UMSO, UDSS, UMSDS as Primary; UMSO and UDS as Secondary. | Recommend closed
58 | CGI | Sending Scenarios | 99 | As called out in MHHS-DEL1308 Systems Integration Testing (SIT) Component Integration Testing (CIT) Test Data Approach & Plan Comments Log Invalid scenario - SDSS will only send Active Power DI-015 = W for the IF-021. | Actioned | Removed Ref 099 from scenario s/sheet based on SMART = W (e.g. removal anything SDSS not = W) | Recommend closed
59 | CGI | Sending Scenarios | 101 | As called out in MHHS-DEL1308 this is an invalid scenario - SDSS will not send reactive power IF-021, this is ADSS only. | Actioned | Removed Ref 101 from scenarios (secondary routing in IF Cat is LDSO who do not receive SMART data) | Recommend closed
60 | CGI | Sending Scenarios | 102 | Should this be broken down to L/H/E, because I assume U is not valid for ADSS? | Acknowledged | The test cases will provide clarity on the breakdown of test coverage in this area | Recommend closed
61 | CGI | Sending Scenarios | 103 | As called out in MHHS-DEL1308 this is an invalid scenario - ADSS will only send Active Power DI-015 <> W for the IF-021 | Actioned | Removed ref 103 ADSS as = W incorrect | Recommend closed
62 | CGI | Sending Scenarios | 175-194 | Typo in event codes - missing colons from DES138 suggests the event codes are not what they are | Actioned | Updated to correct the event codes | Recommend closed
63 | CGI | Receiving Summary by Role | XDS | This worksheet is very confusing and hard to follow. Is XDS = ADS or SDS? XDS is not defined in DES138 | Actioned | The "X" has been replaced with a full elaboration of the routing | Recommend closed
64 | CGI | Receiving Summary by Role | XDS | Assuming XDS is both ADS and SDS, I think this implies that MHHSP-IF-016 is received by SDS. DES138 is contradictory here, the Primary Routing says XDSS, but the To Parties lists only "Advanced Data Service" and Purpose describes on Advanced Data Service. I have sent the following to the MHHS Design team: "Since v5.1.2 of DES138, the Recognised Parties has been consolidated, and the likes of ADSS has been replaced with XDSS, which I assume implies both ADS and SDS. Subsequently, in the IF-016 routing, the Primary Routing has been updated from ADSS to XDSS (implying both SDS and ADS). The “To Parties” states “Advanced Data Service” and the “Purpose/Description” only refers to the Advanced Data Service. BP003C only refers to the ADS receiving the PUB-016. The update to XDSS has resulted in the IF-016 being identified as an “XDS” recipient in the SIT CIT test scenarios. “XDS” is not defined, but again, I’m assuming XDS implies both ADS and SDS. Should the IF-016 be sent to the SDS? If so, DES138, BP003C require updates. If not, would this be clearer if the routing rules in DES138 were reverted to ADSS along with the SIT CIT test scenarios?" | Actioned | The "X" has been replaced in the CIT scenarios with a full elaboration of the routing | Recommend closed
65 | CGI | Receiving Summary by Role | XDS | MHHSP-IF-036 in either the ADS, SDS or XDS section. This could be by misunderstanding of this worksheet and the various filters. Should I be amending the filters? | Actioned | The "X" has been replaced in the CIT scenarios with a full elaboration of the routing | Recommend closed
66 | CGI | Sending Summary by Role | SDSS Ref#68 | As called out in MHHS-DEL1308 Systems Integration Testing (SIT) Component Integration Testing (CIT) Test Data Approach & Plan Comments Log Invalid scenario - SDSS will only send Active Power DI-015 = W for the IF-021. | Actioned | This change has been made and IF-021 now reflects SDSS ActivePower DI-015 = W. | Recommend closed
67 | CGI | Sending Summary by Role | SDSS Ref#70 | As called out in MHHS-DEL1308 this is an invalid scenario - SDSS will not send reactive power IF-021, this is ADSS only. | Actioned | This change has been made to the Scenario tab for IF-021 . | Recommend closed
68 | CGI | Sending Summary by Role | SDSS and ADSS | The Event Codes for IF-041 are confusing. Some are as per DES138 (e.g. DSEstimate), while others have DS Appended to them not as per DES138, for instance DSReadingEnergisationChg should be ReadingEnergisationChg | Actioned | We have updated the scenarios to be consistent with the DES138 | Recommend closed
69 | CGI | Sending Summary by Role | SDSS Ref#109 | "SDS-MDRUpdate" as per DES138 rather than "SDSMDRUpdate" | Actioned | This applies to 137a and the correction has been made | Recommend closed
70 | CGI | Sending Summary by Role | ADSS Ref#72 | As called out in MHHS-DEL1308 this is an invalid scenario - ADSS will only send Active Power DI-015 <> W for the IF-021 | Actioned | We have removed the incorrect scenario | Recommend closed
71 | CGI | Sending Summary by Role | ADSS Ref#71 | Should this be broken down to L/H/E, because I assume U is not valid for ADSS? | Acknowledged | The test cases will provide clarity on the breakdown of test coverage in this area | Recommend closed