## Theme 6
MHHS-DEL2089 - SIT Functional Themes 6 Consolidated Comments Log
Ref | Reviewer | Organisation | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject or Action | Draft Response
1 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1892 SITFTS-0855 MET Disconnect Linked.xlsx | SITFTS0855-Smart | 90 | Test suggests that IF-007 should be produced but process BP009 suggests that IF-005 etc would also be produced due to the removal of the meter. | Clarified | Design Team has confirmed that as the pyhsical meter is shared no IF-005/006 or MTDs are required
2 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1892 SITFTS-0855 MET Disconnect Linked.xlsx | SITFTS0855-Advanced | 85 | Test suggests that IF-007 should be produced but process BP009 suggests that IF-005 etc would also be produced due to the removal of the meter. | Clarified | Design Team has confirmed that as the pyhsical meter is shared no IF-005/006 or MTDs are required
3 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related (1).xlsx | SITFTS0850-Smart | 90 | Test suggests that IF-007 should be produced but process BP009 suggests that IF-005 etc would also be produced due to the removal of the meter. | Fixed | Change made to add missing messages
4 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related (1).xlsx | SITFTS0850-Traditional | 85 | Test suggests that IF-007 should be produced but process BP009 suggests that IF-005 etc would also be produced due to the removal of the meter. | Fixed | Change made to add missing messages
5 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related (1).xlsx | SITFTS0850-Advanced | 90 | Test suggests that IF-007 should be produced but process BP009 suggests that IF-005 etc would also be produced due to the removal of the meter. | Fixed | Change made to add missing messages
6 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections.xlsx | SITFTS0890- Trad Hist UPD Acc | Various | References to Metering Service use SMSC rather than MSSC | Clarified | DES138 references XMSC Metering Service – Current. The test specifies SMSC to align to design
7 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections.xlsx | SITFTS0890 Smart Hist UPD Rej | Various | References to Metering Service use SMSC rather than MSSC | Clarified | DES138 references XMSC Metering Service – Current. The test specifies SMSC to align to design
8 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections.xlsx | SITFTS0890- Trad Hist REM Rej | Various | References to Metering Service use SMSC rather than MSSC | Clarified | DES138 references XMSC Metering Service – Current. The test specifies SMSC to align to design
9 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections.xlsx | SITFTS0890 Smart Hist ADD Acc | Various | References to Metering Service use SMSC rather than MSSC | Clarified | DES138 references XMSC Metering Service – Current. The test specifies SMSC to align to design
10 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections.xlsx | SITFTS0890 Smart Hist ADD Rej | Various | References to Metering Service use SMSC rather than MSSC | Clarified | DES138 references XMSC Metering Service – Current. The test specifies SMSC to align to design
11 | Anon | Anon | Theme 6 - Meter Changes | MHHS-DEL1915 SITFTS-0915 MET Change of MAP update unsuccessful.xlsx | MHHS-DEL1915 SITFTS-0915 MET Change of MAP update unsuccessful | 75 (and others) | Test is specific to MeterExchange event code but some parties use remove/install combination instead of exchange. | Acknowledged | We will add a test case to cover this in the next batch of test cases we issue
12 | Simon Harrison | Callisto | Theme 6 - Meter Changes | Relates to testing of BP008 - Energisation |  | See comment | A recurring issue exists in 0845 (steps 125 & 130) for each tab and 0855 (steps 115 & 120) where it references current and proposed metering services. In that BP, current and proposed don't come into play". Essentially they refer to Current and Proposed MS's, but the process is about metering work taking place, not an appointment | Fixed | Redundant steps removed
13 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1890 SITFTS-0845 MET Supp Disc De-Energise during COS | SITFTS0845-Smart | 120 & 130 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Clarified | DES138 IF-008 requires routing to Current and proposed Metering service so no change required based on current design. To challenge the design, raise a DIN or design query.
14 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1890 SITFTS-0845 MET Supp Disc De-Energise during COS | SITFTS0845-Traditional | 125 & 130 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Clarified | DES138 IF-008 requires routing to Current and proposed Metering service so no change required based on current design. To challenge the design, raise a DIN or design query.
15 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1890 SITFTS-0845 MET Supp Disc De-Energise during COS | SITFTS0845-Advanced | 125 & 130 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Clarified | DES138 IF-008 requires routing to Current and proposed Metering service so no change required based on current design. To challenge the design, raise a DIN or design query.
16 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related | SITFTS0850-Smart | 115 & 120 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Fixed | Change made to remove Proposed references/steps that are not relevant to this scenario
17 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related | SITFTS0850-Traditional | 110 & 115 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Fixed | Change made to remove Proposed references/steps that are not relevant to this scenario
18 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related | SITFTS0850-Advanced | 115 & 120 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Fixed | Change made to remove Proposed references/steps that are not relevant to this scenario
19 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1892 SITFTS-0855 MET Disconnect Linked | SITFTS0855-Smart | 115 & 120 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Fixed | Change made to remove Proposed references/steps that are not relevant to this scenario
20 | Andrew Peacock | Callisto | Theme 6 - Meter Changes | MHHS-DEL1892 SITFTS-0855 MET Disconnect Linked | SITFTS0855-Advanced | 110 & 115 | Step refers to Currently Appointed and Proposed Metering Services, but that isn't relevant for this process. | Fixed | Change made to remove Proposed references/steps that are not relevant to this scenario
21 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1891 | SITFTS-0850 Smart | 25 | Reference to "CSS Update" should be to CSS Interface ID CSS01000. | Fixed
22 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1891 | SITFTS-0850 Traditional | 20 | Reference to "CSS Update" should be to CSS Interface ID CSS01000. | Fixed
23 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1891 | SITFTS-0850 Advanced | 25 | Reference to "CSS Update" should be to CSS Interface ID CSS01000. | Fixed
24 | Mahadesha Subramanyam | DCC | Theme 6 - Meter Changes | MHHS-DEL1917 | MHHS-DEL1917 SITFTS-0862 MET Change of Market Segment with Cos | N/A | Document name in the online page is MHHS-DEL 0862 instead of 1917 ? | Fixed | This has been rectified and the correct filenames should now be showing
25 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1892 | SITFTS-0855 - Smart | 220 | BP007, Step 70 is the sending of the CSS0700 notification by the Registration Service. Step 115 is the receipt of this by CSS. | Clarified | Your interpretation is correct
26 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1891 | SITFTS-0855 - Advanced | 215 | BP007, Step 70 is the sending of the CSS0700 notification by the Registration Service. Step 115 is the receipt of this by CSS. | Clarified | Your interpretation is correct
27 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1891 | SITFTS-0850 - Smart | 25 | BP010B, Step 340 is the sending of the CSS Update to CSS, Step 341 is the receipt of this update by CSS. | Clarified | Your interpretation is correct
28 | Chris Beard | DCC | Theme 6 - Meter Changes | MHHS-DEL1891 | SITFTS-0850 - Smart | 215 | BP007, Step 70 is the sending of the CSS0700 notification by the Registration Service. Step 115 is the receipt of this by CSS. | Clarified | Your interpretation is correct
29 | SG | IMServ | Theme 6 - Meter Changes | MHHS-DEL1916 SITFTS-0860 MET Change of Market Segment.cleaned & MHHS-DEL1918 SITFTS-0870 MET Connect Type Change (MS).cleaned | All | 210 | Steps are missing the meter removal flows i.e TC01 missing removal D0268 | Fixed | This has now been added on advanced meter removals
30 | SG | IMServ | Theme 6 - Meter Changes | MHHS-DEL1914 SITFTS-0910 MET Change of MAP.cleaned | All | All | The test description states change of MAP triggered by receipt of D0304 however the scenarios and steps appear to cover meter exchange coincident with change of MAP which would not be triggered by D0304. The steps themselves do not feature D0304 receipt or sending of D0303 flows which we would expect them to based on the test description. Would suggest the scenarios being tested here are not representative of the test description. | Acknowledged | We have redrafted this test case for clarity
31 | SG | IMServ | Theme 6 - Meter Changes | MHHS-DEL1894 SITFTS-0900 – MET Change of Meter successful.cleaned | SITFTS-0900 TC04 | 20 | When advanced meter is removed D0383/D0384 is not required to be sent - test step requires D0268/D0383/D0384/D0010 to be sent | Fixed | This has been updated so only D0268 & D0010 is sent
32 | Henri Naef | Kraken | Theme 6 - Meter Changes | MHHS-DEL1894 SITFTS-0900 – MET Change of Meter successful | SITFTS-0900 TC01 | 15 | Following the BP009 diagram, we would expect that following the receipt of the D0142 (or agreed API alternative in our case), we would be required to evidence the D0002/D0221 being sent to the supplier. 1. Can we assume that evidencing this is out of scope? 2. If it is in scope, can this please be added into the steps to showcase this requirement. 2a. If in scope, can we request that our API alternative to sending the D0002/D0221 is acceptable for evidencing this step? This query also applies to steps following the D0142 (or API equivalent) within the below files: [MHHS-DEL1913 SITFTS-0905 MET Change REGS Rejection] [MHHS-DEL1890 SITFTS-0845 MET Supp Disc De-Energise during COS] [MHHS-DEL1915 SITFTS-0915 MET Change of MAP update unsuccessful] [MHHS-DEL1914 SITFTS-0910 MET Change of MAP] | Clarified | These test cases are not invoking the rejection that would trigger the D0002/D0221, just the happy path so these would not apply.
33 | Jonny Moore | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SIFTS-0855-Smart and Advanced | Step 10 - 60 | There should be no requirement to 'de-link' an associated Import / Export metering system prior to Disconnection. De-linking at this point would be inocrrect as the two MPANs continue to share metering equipment. (and would fail the DNO validation in step 20) | Fixed | De-linking steps now moved to after disconnection
34 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Steps 15 - 20 | Step 880 on BP010 has the IF019 issued to the LDSO for decision, not the registration service. The LDSO then send a DB05 flow to the RS to update. | Fixed | Change made to BP010C Steps
35 | Jonny Moore | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Steps 70 - 150 / 65 - 145 | If only one Mpan of a Import/Export association is being disconnected. Physically removing / de-energising the meter is not required. (As the other MPAN will continue to require the metering equipment) This should be the turning off of the AE / AI register. Followed by a logical disconnection with the meter still in situ. | Fixed | Step definition changed from "remove physical meter" to "Turn off AE Register"
36 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Step 80 | This step is only covering the capture of the Cumulative Read. Steps needed to cover the sending of this via the DIP an the processing by the recipients - supplier, LDSO and DS | Fixed | Change made to include additional steps
37 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Step 85 | This covers the sending of the Cumulative Read but not the MTDs. An IF005 also needs to be issued to the RS as per step 55. There is then RS validation before an IF006 is issued out to the MS, Supplier, LDSO, DS and EES | Reject | Design Team has confirmed that as the pyhsical meter is shared no IF-005/006 or MTDs are required
38 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Advanced | Step 85 | For Advanced, there is also a need to send register reads via the D0268 - step 80 in the BP | Fixed | Discussion with Design confirmed no requirement to send MTD (D0268). Steps added to issue D0010, if Advanced Meter does not suppoprt Cumulative Reads.
39 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Step 90 | This step should reference de-energisation, not energisation | Fixed | Change made, as per comment, to reflect de-energisation.
40 | Jonny Moore | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Step 135 / 130 | There's no need for a proposed SDS in this test case. (No change in SDS is being processed) | Fixed | Change made
41 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0855- Smart and Advanced | Step 250 / 245 | The description in column k is misleading as the de-appointment messages are further down. This step is just receipt of the CSS02860 by the RS. | Fixed | Change made as per comment
42 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0855 | SITFTS-0850 all tabs | General | We do not believe that this scenario reflects a real world example. Associated Import / Export Metering Points are linked as they share a meter. If you wanted to disconnect an Export Metering Point you would carry out a logical disconnection following the process in BP007, without removing the meter. If the meter was also being removed then this would be progressed by the Import Supplier using the meter removal, de-energisation and disconnection process. Therefore there should be separate scenarios for import and export Metering Points | Fixed | Step definition changed from "remove physical meter" to "Turn off AE Register"
43 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | General | We do not believe the choreography reflected in this scenario is correct. For Related Metering Points, there is a requirement that the relationship is removed before the Metering Point is disconnected. There is no requirement for the relationship to be removed before a meter is removed / de-energised. Therefore, we believe the IF019 / 020 process should be included directly before the D0132 is issued to disconnect the Metering Point. | Fixed | We have clarified the correct sequencing of events with the Design team and have updated the test case accordingly. Specifically, the steps to remove the relationship have been shifted to occur before the disconnection.
44 | Jonny Moore | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | Step 20/25/20 | The message into the CSS needs defined. | Clarified | Message labelled as "RMP Asscociation"
45 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | Step 80 | This step is only covering the capture of the Cumulative Read. Steps needed to cover the sending of this via the DIP an the processing by the recipients - supplier, LDSO and DS | Fixed | Changes made to all tabs to handle reads and MTDs
46 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 advanced | Step 85 | This covers the sending of the Cumulative Read but not the MTDs. An IF005 also needs to be issued to the RS as per step 55. There is then RS validation before an IF006 is issued out to the MS, Supplier, LDSO, DS and EES | Fixed | Change made missing steps have been added
47 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | Step 85 | For Advanced, there is also a need to send register reads via the D0268 - step 80 in the BP | Fixed | Change made missing steps have been added
48 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | Step 90 | This step should reference de-energisation, not energisation | Fixed | Change made as per comment
49 | Jonny Moore | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | Change of Energisation Status | Unsure why there's a new and proposed MS/DS here. There's no change of agent triggered by the de-eng. | Fixed | Change made to update Proposed MS and DS recipients that were incorrect
50 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 traditional | Step 250 / 245 | The description in column k is misleading as the de-appointment messages are further down. This step is just receipt of the CSS02860 by the RS. | Fixed | Change made to remove misleading step
51 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | Step 85 | For Traditional, there is also a need to send register reads via the D0149/150 - step 80 in the BP | Fixed | Change made missing steps have been added
52 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS-0850 | SITFTS-0850 all tabs | General | Presumably the inclusion of scenarios with and Related Primary and Secondary is to show that the relationship needs to be broken first. In order to test this functionality there needs to be scenarios where the LDSO attempts to disconnect a secondary metering point where the relationship still exists. This is not captured in the test cases | Clarified | Goal is to remove the relationship between primary and secondaryt MPANs and to disconnnect the secondary. We have corrected the sequence of events to put the removal of the relationship to happen just before the disconnection
53 | Sarah Jones | RECCo | Theme 6 - Meter Changes | General |  |  | There are a significant number of IF005 validation rules in the DES138 (as explained in the IF005 User Guide. By missing the IF005 steps from the disconnection examples, these are not being tested at all. This is an area which could lead to significant operational issues post go live if the validation rules have not been interpreted correctly and therefore we would expect to see a number of test cases reflecting meter updates for a variety of event types and including negative testing to reflect the validation e.g. updates being made by the wrong MEM with IF006 rejections going to the MEM and the Supplier. | Clarified | Our approach top comprehensive coverage of the validation rules will comprise a combination of: 1. PIT coverage of all the rules at PP level, which we will audti and assure; 2. Risk-based coverage of a subset of the scenario examples in the user guide. We will be conducting a workshop with SRO design and assurance in the new year to define and ratify the coverage in point 2 above.
54 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0280 | General |  | We do not agree with the test cases identified. The energisation of a metering asset by the LDSO is an infrequent event, reserved large metering assets. Therefore we would only expect this to be tested for advanced, with test cases 1 and 5 amended to cover MS energisation | Fixed | This has since been amended
55 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0280 | All scenarios | 35 | The IF041 is also issued to the SDS and the LDSO | Fixed | This has since been amended
56 | Jonny Moore | RECCo | Theme 6 - Meter Changes | SITFTS0280 | SITFTS02360 - TC01 | 20 | I'm not sure this step works. The validation rule quoted is for the RS to validate a change of energisation request. For the IF-007 rejection to the Supplier the MS would populate the failure to energise / de-energise code (DI-097) | Fixed | This has been revised to an RS rejection test after discussions with design team
57 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS02360 | SITFTS02360 - TC02 | 25 | The IF041 is also issued to the SDS | Fixed | This has since been amended
58 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS02360 | SITFTS02360 - TC02 | 40 | This step reads as though the D0134 is sent from MSSC to SUPC. Suggest removing this step as this is simply repeating step 15 which triggers the work and sending the IF007 | Fixed | Agreed, this step has been removed
59 |  | RECCo | Theme 6 - Meter Changes | SITFTS02360 | SITFTS02360 - TC03 | 30 | I'm not sure this step works. The validation rule quoted is for the RS to validate a change of energisation request. For the IF-007 rejection to the Supplier the MS would populate the failure to energise / de-energise code (DI-097) | Fixed | This has been updated as a RS rejection test after discussions with design team
60 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0890 | All acceptance scenarios | 35 | The IF006 also gets issued to the DS | Reject | as per current version of DES138, this does not apply to meter history update
61 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0890 | All rejection scenarios | 30 | The IF006 rejection also gets issued to the Supplier | Fixed | This has since been amended
62 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0845 | General |  | These scenarios are a mixture of agent appointment and meter removal / disconnection. Our comments against these individual scenarios are therefore applicable | Acknowledged | We have reviewed and responded accordingly
63 | Sarah Jones | RECCo | Theme 6 - Meter Changes | General | General |  | The IF005 User Guide includes a number of meter update scenarios which have not been reflected in the published scenarios. Suggest these are tested, given the complexity of the metering update arrangements and the risk associated with inaccurate MTDs. Examples include: update Meter Id, Update data items (multiple tests for each relevant data item and combinations), extend MAP history | Clarified | Our approach top comprehensive coverage of the meter update scenarios will comprise: 1. PIT coverage of all the rules at PP level, which we will audti and assure; 2. Risk-based coverage of a subset of the scenario examples in the user guide. We will be conducting a workshop with SRO design and assurance in the new year to define and ratify the coverage in point 2 above.
64 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0910 | General |  | The overview tab explains that this is a change of MAP following receipt of the D0304. Our expectation was that this would therefore cover the change of MAP process where a D0304 is received and the Metering Service sends an IF005 MAP Id update to the RS. The actual test scenarios appear to cover a meter exchange scenraio which is triggered by the supplier requesting a meter exchange via the D0142. We have reviewed the test cases on the basis they are meant to cover a smart and advanced meter exchange. | Acknowledged | We have updated the test to change how the MAP update is triggered in the scenario
65 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0910 | TC01 | Step 15 | As flagged in previous tranches the D0142 is not sent via SDEP or email - the SDEP and email method are alternatives from using the DTN. Party testing should be based on their chosen enduring approach. | Acknowledged | These step has been removed because it is redundant following the change to the test case, as per the response to the "General" MAP query above
66 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0860 | Overview |  | The scenarios do not reference connection type and its not clear from the test cases if change of connection type is occurring. There should be a mixture of examples tested. | Clarified | This test is for Market segment change change of connection type wording has been removed connection type change can be seen as part of test SITFTS-0870
67 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0860 | All tabs | Step 10 | This process starts with the supplier requesting a change of connection type but then progresses as just a meter exchange. There needs to be a change of connection type scenario as well where the RS waits for both the change of connection type and the meter exchange details before issuing the change of market segment notification and the chnage of connection type IF043. | Clarified | This test relates to a change of connection type. This has been clarified in the test description
68 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0860 | All tabs |  | IF041 is missing from the scenarios - as a meter exchange this should be sent for smart and advanced metering assets. | Fixed | This has since been added
69 | Sarah Jones | RECCo | Theme 6 - Meter Changes | SITFTS0860 | General |  | The complexity of a change of market segment comes from the need to prospectively appoint the agent to then allow the metering update to be made whilst the agent is in the prospective queue. Suggest that there are scenarios needed to cover instances where the meter is exchanged and the agent appointment is not made so the IF005 is rejected. Also need scenarios where the connection type is updated triggering a change of market segment, but no agent appointed so existing agents are de-appointed and the IF045 is sent to notify missing agent. | Acknowledged | This is covered by SITFTS-0880
70 | Keith Donaldson | TMA Data Management Ltd | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | All Tabs |  | Data that should be under "Key Journey Events" is instead under "Test Case Title" | Fixed | Amended
71 | Keith Donaldson | TMA Data Management Ltd | Theme 6 - Meter Changes | MHHS-DEL1917 SITFTS-0862 MET Change of Market Segment with Cos | SITFTS0862 Overview |  | Test Case ID is 'SITFTS-0860 TC01' instead of 'SITFTS-0862 TC01' | Fixed | Amended
72 | Keith Donaldson | TMA Data Management Ltd | Theme 6 - Meter Changes | MHHS-DEL1913 SITFTS-0905 MET Change REGS Rejection | SITFTS-0905 TC04 | 35 | Step includes D0383 and D0384 flows, currently these are not sent to an HHDC and we can't see anything to indicate that these will be sent to an ADS in MHHS | Fixed | Amended
73 | Keith Donaldson | TMA Data Management Ltd | Theme 6 - Meter Changes | MHHS-DEL1913 SITFTS-0905 MET Change REGS Rejection | SITFTS-0905 TC06 | 35 | Step includes D0383 and D0384 flows, currently these are not sent to an HHDC and we can't see anything to indicate that these will be sent to an ADS in MHHS | Fixed | Amended
74 | Keith Donaldson | TMA Data Management Ltd | Theme 6 - Meter Changes | MHHS-DEL1914 SITFTS-0910 MET Change of MAP | SITFTS-0910 TC02 | 30 | Step includes D0383 and D0384 flows, currently these are not sent to an HHDC and we can't see anything to indicate that these will be sent to an ADS in MHHS | Fixed | Amended
75 | Keith Donaldson | TMA Data Management Ltd | Theme 6 - Meter Changes | MHHS-DEL1918 SITFTS-0870 MET Connect Type Change (MS).xlsx | SITFTS-0870 TC02 | 315 | Message is PUB-006 when should be PUB-006 | Fixed | Steps 290 - 315 have PUB-006 in error; edited to IF-036 and PUB-036 where applicable
76 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1890 SITFTS-0845 MET Supp Disc De-Energise during COS | N.A. | N.A. | Document reviewed. I have no comments to make
77 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1892 SITFTS-0855 MET Disconnect Linked | N.A. | N.A. | Document reviewed. I have no comments to make
78 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1891 SITFTS-0850 MET Disconnect Related | N.A. | N.A. | Document reviewed. I have no comments to make
79 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | SITFTS-0280 TC04 | 10 | Test Step contains two actual actions, the latter of which appears to be duplicated in Step 15 Step states "For newly created MPAN with installed meter LDSO receives D0134 from Supplier and Issues D0139 to Advanced Metering Service" Second part "... and Issues D0139 to Advanced Metering Service" appears to be covered in Step 20 Suggest the step is reworded to something like "For newly created MPAN with installed meter LDSO receives D0134 from Supplier" and leave Step 15 as it stands | Fixed | Agreed, these have been split in to separate test steps now to make it clearer who is sending and receiving
80 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | SITFTS-0280 TC04 | 10 | Message output is wrong because of the issues above. It should be D134 | Fixed | Message output column is being removed on All tests based on feedback we have received
81 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | SITFTS-0280 TC04 | 15 | Message output is wrong. It should be D139 | Fixed | Message output column is being removed on All tests based on feedback we have received
82 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | SITFTS-0280 TC05 | 10 | Test Step contains two actual actions, the latter of which appears to be duplicated in Step 15 Step states "For newly created MPAN with installed meter LDSO receives D0134 from Supplier and Issues D0139 to Advanced Metering Service" Second part "... and Issues D0139 to Advanced Metering Service" appears to be covered in Step 20 Suggest the step is reworded to something like "For newly created MPAN with installed meter LDSO receives D0134 from Supplier" and leave Step 15 as it stands | Fixed | The newly created MPAN comment was added in error and has now been removed
83 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | SITFTS-0280 TC05 | 10 | Message output is wrong because of the issues above. It should be D134 | Fixed | Message output column is being removed on All tests based on feedback we have received
84 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1887 SITFTS-0280 – MET Energisation Change | SITFTS-0280 TC05 | 15 | Message output is wrong. It should be D139 | Fixed | Message output column is being removed on All tests based on feedback we have received
85 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1888 SITFTS-0360 MET Energisation Change Fails | N.A. | N.A. | Document reviewed. I have no comments to make
86 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1893 SITFTS-0890 MET Historic Updates incl Rejections | N.A. | N.A. | Document reviewed. I have no comments to make
87 | Kev Roper | Utilita | Theme 6 - Meter Changes | MHHS-DEL1889 SITFTS-0840 MET LDSO or Cust Disconnect | N.A. | N.A. | Document reviewed. I have no comments to make