## Consolidated PP Feedback
MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log
| Reviewer to Complete | [9 empty] | Programme to complete once consultation window has closed.
Ref | Reviewer | Anonymised | Organisation | Constituency | Date | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject Or Action | Response | Status
1 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | All | All | All | Overall the Test Cases read like a process description rather than a test script. Expected outcomes should be more explicit. | Reject | Expected outcomes and what needs to be verified are listed in columns for the test | Complete
2 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 1 | In the text comment the Supplier needs to identify both the correct MS and DS. The description might be better asking the Supplier to identify the correct market segment. | Accept | Changes implemented | Complete
3 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 3+5 | In the text comment 'Registrations' should read Registration Service | Accept | Changes implemented | Complete
4 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 8 | I'm assuming this is a happy path scenario. Would the expectation be that the REGS validates the request and sends an acceptance. | Accept | Changes implemented | Complete
5 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 33 | Mention of rejection processing in what I assume is a happy path scenario seems unnecessary | Accept | Changes implemented | Complete
6 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 37-42 | Clarity is required on whether this is a same day or future dated appointment test. Would suggest separate test cases are required for each. | Reject | Prospective - This has been clarified in the Overview tab | Complete
7 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 64 | Don't think this step is required | Accept | Changes implemented | Complete
8 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 70 | Should the text in green be a test step to ensure the status is set? | Accept | Changes implemented | Complete
9 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 70 | Note EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | Accept | Changes implemented | Complete
10 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 76-78 | As this is a COA test the mention of 'for COA' adds confusion | Accept | Changes implemented | Complete
11 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | 80 | As this is a COA test reference to the D0086 is not required. | Accept | Changes implemented | Complete
12 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC01 TRAD | N/A | The above comments can be translated to the matching steps in associated test cases. (Both COA and COS) | Accept | Changes implemented | Complete
13 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 50 | Is it worth adding a test for sucessfully mapping the D0149/D0150 to the D0268. | Reject | This is an action by outgoing MOP so will be stubbed. Legacy agents are not in scope of testing. | Complete
14 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 62 & 66 | Communication of Smart Meter details not relevant for Advanced | Accept | Changes implemented | Complete
15 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 66 | Communication of Smart Meter details not relevant for Advanced | Accept | Changes implemented | Complete
16 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC04 S-NHH | 22 | Appointment of MDR test steps appear to be missing. | Reject | We believe this process is covered in the send of the IF-31. This is implicit within the step and is already being covered and does not need explicit coverage. | Complete
17 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC04 S-NHH | 58 | Reference to advanced incorrect for Smart scenario | Accept | Changes implemented | Complete
18 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 | SIT-M-FM-COA-MS-DS-TC04 S-NHH | 58 | No receipt of legacy MTDs for the MS to compare the RS MTDs with. | Accept | MTDs aren't sent for Smart Meters, so the step has been removed | Complete
19 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 | SIT-M-FM-COS-MS-DS-TC01 - Trad | 6 | New Connections are not valid for migration testing. | Accept | Changes implemented | Complete
20 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 | SIT-M-FM-COS-MS-DS-TC01 - Trad | 9+13 | EES does not receive the IF-001. Registration details are received direct from the CSS. As per approved and implemented CR028 | Accept | Noted. Will raise the requirement with Design Team to update the Migration Design document following the CR. | Complete
23 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 | SIT-M-FM-COS-MS-DS-TC01 - Trad | 18-20 | These steps do not make sense as part of a test case. | Accept | Step 18 is needed. Steps 19 & 20 removed. | Complete
24 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 | SIT-M-FM-COS-MS-DS-TC01 - Trad | 21-23 | I don't understand why the D0170 / D0215 process is being referenced as part of a migration test. I don't believe this is required. | Reject | This is part of the CoS process. | Complete
24.7857 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 | SIT-M-FM-COS-MS-DS | N/A | The above COS comments can be translated to the matching steps in associated test cases. | Accept | Changes implemented | Complete
26.0714 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 | SIT-M-FM-COS-MS-DS-TC01 - Trad | 104 | Only D0086 is required for COS NHH test cases. | Accept | Changes implemented | Complete
27.3571 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-CoA-MS-DS Overview | 4 & 5 | Would it be clearer to talk about Customer Consent Granularity rather than settlement arrangements? For example, it is not clear from the description whether SIT-M-FM-COA-MS-DS-TC04 is migration of a customer on monthly or daily consent. | Reject | SIT Functional tests are also organised in the same fashion. Changing now would be deviating from the norm. | Complete
28.6429 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC01 Trad | 52 & 54 | Why is a stub being used for the outgoing MOP in steps 52 and 54 whilst a real outgoing MOP is used in steps 48 & 49? | Reject | If a participant initiates a data flow/interface, a stub will be used to generate that data flow/interface so that the system can function correctly. If a participant receives a data flow/interface, no verification will be made as this is out of scope for migration. | Complete
29.9286 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC01 Trad | Step 57, 59, 271, 281 | Does this Test Case test handling of MTD discrepancies or not? It is unclear from the use of the phrase 'if required' whether the test intends to exercise handling of MTD discrepancies or not. If the intention is to test the handling of MTD discrepancies, these will need to be reflected in the D0149 and D0150 generated in steps 52 and 42. If the intention is to test handling of MTD discrepancies AND the happy path in which there are no discrepancies, these should feature as two separate Test Cases. In our opinion, a Test Case should describe the steps that are intended to be tested, not reproduce the entire business process on which the test is based. | Reject | Migration: These test cases only outline the 'happy path'. The handling of MTD discrepancies falls into exception handling (Theme 3) | Complete
31.2143 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC01 Trad | 76 | This test step makes reference to sending a D0151 for both primary and secondary related MPANs however no mention is made of this test involving related MPANs in the Test Case description contained in the SIT-M-FM-CoA-MS-DS Overview tab. | Accept | Changes implemented | Complete
32.5 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 6, 8, 9, 10, 15, 21, 31, 32, | This Test Case talks about 'taking the appropriate action dependant on the outcome'. It is not clear from this description whether the Test Case is testing a positive or negative outcome. If the intention is to test both, these should be documented as separate Test Cases. | Accept | Changes implemented | Complete
33.7857 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 33, 34 | This test step suggests that the Test Case needs to be run for two different types of appointment, namely: same day and prospective. If this is the case, these should be expressed as separate Test Cases. | Accept | Changes implemented | Complete
35.0714 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 50, 52 | Why is a stub being used for the outgoing MOP in steps 50 and 52 whilst a real outgoing MOP is used in steps 47? | Reject | If a participant initiates a data flow/interface, a stub will be used to generate that data flow/interface so that the system can function correctly. If a participant receives a data flow/interface, no verification will be made as this is out of scope for migration. | Complete
36.3571 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 63, 67 | It is not clear whether this Test Case will test MTD discrepancies or not. | Reject | Migration: These test cases only outline the 'happy path'. The handling of MTD discrepancies falls into exception handling (Theme 3) | Complete
37.6429 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 76, 77 | This test step makes reference to sending a D0151 for both primary and secondary related MPANs however no mention is made of this test involving related MPANs in the Test Case description contained in the SIT-M-FM-CoA-MS-DS Overview tab. | Accept | Changes implemented | Complete
38.9286 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 78, 79 | Why is a stub being used for the outgoing DC in steps 78 and 79 whilst a real outgoing MOP is used in steps 77? | Reject | If a participant initiates a data flow/interface, a stub will be used to generate that data flow/interface so that the system can function correctly. If a participant receives a data flow/interface, no verification will be made as this is out of scope for migration. | Complete
40.2143 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 6, 8, 9, 11, 15, 21, 31, 32 | This Test Step is unclear whether REGS will respond with an Accepted or Rejected Supplier Service Appointment. These are two different Test Cases. | Accept | Changes implemented | Complete
41.5 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 14 | This Test Step makes reference to the transfer of a linked MPAN. No mention is made in the overview of this Test Case requiring linked MPANs. Should an additional Test Case be added for this? | Accept | Changes implemented | Complete
42.7857 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 33, 34 | This Test Step makes reference to same day registrations and prospective registrations. It is unclear which is being tested here. It would be clearer to have two separate Test Cases to test these two different types of registration. | Accept | Changes implemented | Complete
44.0714 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 50, 52 | Why is a stub used for the Outgoing MOP when a real Outgoing MOP appears to be used in steps 46 and 47? | Reject | If a participant initiates a data flow/interface, a stub will be used to generate that data flow/interface so that the system can function correctly. If a participant receives a data flow/interface, no verification will be made as this is out of scope for migration. | Complete
45.3571 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 54, 66 | This Test Step makes reference to Smart Metering (this is an Advanced Meter Test Case). | Accept | Changes implemented | Complete
46.6429 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 74, 75 | These Test Steps make reference to primary and secondary MPANs, however, no mention is made of the Test Case requiring related MPANs in the overview. Should an additional Test Case be added for this? | Accept | Changes implemented | Complete
47.9286 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 76, 77, 79, 80 | Why do these Test Steps use a stub for the Outgoing DC whereas Test Step 75 uses an actual Outgoing DC? | Reject | If a participant initiates a data flow/interface, a stub will be used to generate that data flow/interface so that the system can function correctly. If a participant receives a data flow/interface, no verification will be made as this is out of scope for migration. | Complete
49.2143 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 6, 8, 9, 11, 15, 21, 31, 32 | It is not clear whether this Test Case is a positive or negative test (i.e. does the Supplier send the correct appointment details or incorrect appointment details. | Accept | Changes implemented | Complete
50.5 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 14 | This Test Step makes reference to linked MPANs. It is not clear from the overview that this Test Case is testing linked MPANs. | Accept | Changes implemented | Complete
51.7857 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 29 | This Test Step only appears to be valid if the meter is Advanced. However, the overview states that the Test Case relates to a NHH smart meter. | Accept | Changes implemented | Complete
53.0714 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 33, 34 | It is unclear whether this Test Case is for a same day or prospective appointment. | Reject | Prospective - Please see Overview | Complete
54.3571 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 47 | This Test Step says that, in the case of smart meters, the process ends. Since this Test Case is for a smart meter, what is the purpose of Test Steps 48 to 78? | Accept | Text clarified that process ends for the logic thread in progress. | Complete
55.6429 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 58 | This Test Step makes reference to "Advanced", however, the Test Case is for a Smart NHH meter. | Accept | Changes implemented | Complete
56.9286 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC05 - S-HH | N/A | Does "Smart HH" denote elective HH settlement? |  | Yes, it does. | Complete
58.2143 | Chris Beard | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | SIT-M-FM-COA-MS-DS-TC05 - S-HH | Various | See comments on above Test Cases | Accept | Changes implemented across CoS & CoA, as deemed correct. | Complete
59.5 | Maha | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | All test cases |  | An issue with the layout of test cases for CoS scenario. Seems like the content for all columns from ‘Trigger sending’ is shifted to the right by a column. A separate email with the screen capture is shared with MHHS testing team and raising in the comments log for tracking. | Accept | Changes implemented | Complete
60.7857 | Alan Matthews | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | All test cases |  | It is apparent that none of the CoA scenarios involve DCC systems. It is assumed that any CoA will lead to the sending of an MDR SAA to CSS so what is the rationale for not including DCC systems? | Accept. MDR SAA will be sent to CSS | They're BAU process that occur after the Migration process. AP to speak to Kevin and copy steps from SIT Functional. | Complete
62.0714 | Alan Matthews | No | DCC | Central System | 2024-02-12 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios and Test Cases | All test cases |  | DCC doesn’t appear to feature in the CoA Scenario. We would have expected these to have included the appointment of an MDR which would flow through CSS to DSP? | Accept. Appointment of MDR which will flow through CSS to DSP | AP to speak to Kevin and copy steps from SIT Functional. | Complete
63.3571 | Kev Roper | No | Utilita | Supplier | 2024-02-08 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases | N.A. | N.A. | I have reviewed the document and have no comments to make |  |  | Complete
64.6429 | Kev Roper | No | Utilita | Supplier | 2024-02-08 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | N.A. | N.A. | I have reviewed the document and have no comments to make |  |  | Complete
65.9286 | Keith Donaldson | No | TMA Data Management Ltd | Independent Agent | 2024-02-13 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 67 | Step has D0383 and D0384 flows sent to SDS, we would expect these to be sent between mops and metering services not to a DS. | Accept | Migration: Check Section 6.4.2 of the Migration Design document. There are no additional steps required to share MTDs in the case of Smart meters as they wll be transferred via the BAU MHHS process where the MTDs are transferred via the IF-036 (which is already sent as part of every migration so no additional steps required). The D0383 and D0384 are flows that are sent only in the case of the transfer of Advanced MTDs. They should not be referenced as part of the Smart tab. Change Implemented | Complete
67.2143 | Keith Donaldson | No | TMA Data Management Ltd | Independent Agent | 2024-02-13 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC05 - S-HH | 66 | Step has D0383 and D0384 flows sent to SDS, we would expect these to be sent between mops and metering services not to a DS. | Accept | Change Implemented | Complete
68.5 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview |  | Is this a COA only, or a CoS and CoA together? The overview suggests both CoS and CoA together ("coincident with a switch"), but there are no CSS interfaces? Should SUPC be SUPI? | Reject | There are 2 testcases - CoA & CoS CoA is for Change of Agents - MS + DS CoS is for Change of Supply and related Change of Agents - MS +DS) For CoA - the supplier does not change, hence SUPC is correct. | Complete
69.7857 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 8 | There should be separate tests for Accepted or Rejected. There should not be an OR in a test step. | Accept | Change implemented | Complete
71.0714 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 11 | There should be separate tests for Valid or Failed. There should not be an OR in a test step. | Accept | Change implemented | Complete
72.3571 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 16 | Is this a Linked MPAN test? | Accept | Change implemented | Complete
73.6429 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 17 | Should there be a separate test for an invalid appointment request? | Accept | Change implemented | Complete
74.9286 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 23 | There should be separate tests for Valid or Failed. There should not be an OR in a test step. | Accept | Change implemented | Complete
76.2143 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 33 | It would be a different test for rejections | Accept | Change implemented | Complete
77.5 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 34 | It would be a different test for rejections | Accept | Change implemented | Complete
78.7857 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 35/36 | This is a next day test, so is the Same Day statement valid? | Accept | Change implemented | Complete
80.0714 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 38/41 | Lapsing would be a different test | Accept | Change implemented | Complete
81.3571 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 60 | Only being sent to Supplier, but description states the other agents too. | Accept | Change implemented | Complete
82.6429 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 61 | This is a next day test, so is the Same Day statement valid? | Reject | Unable to locate referred text | Complete
83.9286 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 52-53 | Is the ordering/numbering of these steps correct? | Accept | Change implemented | Complete
85.2143 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 60/61 | Only one step for both the send and the receive, but 2 steps previously (e.g. 52/54 and 53/55) | Reject | 60 is Issue & 61 is receive | Complete
86.5 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 62/63 | New Data Service | Accept | Change implemented | Complete
87.7857 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 65 | New Metering Service | Accept | Change implemented | Complete
89.0714 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 73 | Is this a duplicate of 60, or should the detail be that the Supplier receives the D0149/D0150 | Reject | Not a duplicate because 60 is issuing MTDs and 73 is receiving MTDs. Text has been reworded to make this clearer | Complete
90.3571 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-CoA-MS-DS Overview | 76/77 | Not a related MPAN test | Accept | Change implemented | Complete
91.6429 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC02 AdvNHH |  | Is this a COA only, or a CoS and CoA together? The overview suggests both CoS and CoA together ("coincident with a switch"), but there are no CSS interfaces? Should SUPC be SUPI? | Reject | There are 2 testcases - CoA & CoS CoA is for Change of Agents - MS + DS CoS is for Change of Supply and related Change of Agents - MS +DS) For CoA - the supplier does not change, hence SUPC is correct. | Complete
92.9286 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 6 | There should be separate tests for Valid or Failed. There should not be an OR in a test step. | Accept | Change implemented | Complete
94.2143 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 9 | There should be separate tests for Valid or Failed. There should not be an OR in a test step. | Accept | Change implemented | Complete
95.5 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 14 | Linked? | Accept | Change implemented | Complete
96.7857 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 15 | Invalid should be separate test | Accept | Change implemented | Complete
98.0714 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | all | As per comments for trad | Accept | Change implemented | Complete
99.3571 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC04 - S-NHH |  | Is this a COA only, or a CoS and CoA together? The overview suggests both CoS and CoA together ("coincident with a switch"), but there are no CSS interfaces? Should SUPC be SUPI? | Accept | Change implemented | Complete
100.6429 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 75 | Are there steps missing? Does the Supplier send a D0010 to the outgoing DC, who validate it, and then send a D0010 back to Supplier? | Reject | Migration: Yes, this is the correct process and the relevant steps are included, but the initial send of the D0010 to the outgoing DC is included higher up in the process which is why you might have missed it (step 56). Test steps 75 and 77 then complete the transfer of reads process. | Complete
101.9286 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | all | As per comments for trad | Accept | Change implemented | Complete
103.2143 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COS-MS-DS-TC01 Trad | 1-23 | Columns J-Q do not align with the headers | Accept | Change implemented | Complete
104.5 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COS-MS-DS-TC01 Trad | 47 | No MDR for Trad | Accept | Change implemented | Complete
105.7857 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COS-MS-DS-TC01 Trad | 54 | Sent by DIP and should be PUB not IF | Reject | PUB-035 is being sent by DIP, as has been suggested | Complete
107.0714 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COS-MS-DS-TC01 Trad | 76/78 | Existing or new? Do they both send it? SMSC or SMSI? | Accept | Change implemented | Complete
108.3571 | Dave Webster | No | CGI | Software Provider | 2024-02-14 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases.xlsx | SIT-M-FM-COS-MS-DS-TC01 Trad | 49 | Sent to DIP only | Accept | Change implemented | Complete
109.6429 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COA-MS-DS-TC01 Trad | 44, 46, 66, 69, 72, 75, | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
110.9286 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 42, 44, 66, 69 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
112.2143 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COA-MS-DS-TC03 AdvHH | 42, 44, 60, 63 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
113.5 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COA-MS-DS-TC04 - S-NHH | 42, 44, 60, 63 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
114.7857 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2239 SIT-M-FM-CoA-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COA-MS-DS-TC05 - S-HH | 42, 44, 59, 62 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
116.0714 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC01 Trad | Columns mis match | Looks like Columns are mis matched from column J | Accepted | Changes implemented | Complete
117.3571 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC02 AdvNHH | Columns mis match | Looks like Columns are mis matched from column J | Accepted | Changes implemented | Complete
118.6429 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC02 AdvNHH | 245, 255, 280 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
119.9286 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC03 AdvHH | Columns mis match | Looks like Columns are mis matched from column J | Accepted | Changes implemented | Complete
121.2143 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC03 AdvHH | 64, 66, 85 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
122.5 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC04 - S-NHH | Columns mis match | Looks like Columns are mis matched from column J | Accepted | Changes implemented | Complete
123.7857 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC04 - S-NHH | 245, 255, 280 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
125.0714 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC05 - S-HH | Columns mis match | Looks like Columns are mis matched from column J | Accepted | Changes implemented | Complete
126.3571 | Anonymous | Yes | Anonymous | Anonymous | 2024-02-09 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC05 - S-HH | 245, 255, 280 | PUB-036 goes to UMSO. Trigger Recepient should be UMSO. | Rejected | Unmetered Tests covered in Theme 3 | Complete
127.6429 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-28 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC01 Trad | 65 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. | Accepted | Changes implemented | Complete
128.9286 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-28 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC01 Trad SIT-M-FM-COS-MS-DS-TC02 Adv NHH SIT-M-FM-COS-MS-DS-TC03 Adv HH SIT-M-FM-COS-MS-DS-TC04 Smart NHH SIT-M-FM-COS-MS-DS-TC05 Smart HH | 33 33 33 28 28 | The test cases do not reference the ISD check that the Registration Service undertakes to identify if the incoming Supplier is MHHS qualified. This should be added to the COS scenarios at test step 35. | Accepted | Changes implemented | Complete
130.2143 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-28 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC01 Trad | BP003A section | The newly added steps for communication of the MDR to CSS are only relevant for Smart Meters and should be removed from Traditional and Advanced scenarios. | Accepted | Changes implemented | Complete
131.5 | Jonny Moore | No | RECCo | Central Party / Code Manager | 2024-02-28 | Theme 1 - Forward Migration - CoA & CoS | MHHS-DEL2240 SIT-M-FM-CoS-MS-DS Test Scenarios And Test Cases | SIT-M-FM-COS-MS-DS-TC01 Trad | BP003A Step 20 | The MDR update has been covered, at the same time the Registration Service will inform the CSS of the newly appointed Metering Service. Steps for this should also be added to all the test cases for all metering types. | Accepted | Changes implemented | Complete
132.7857
134.0714
135.3571
136.6429
137.9286
139.2143
140.5
141.7857
143.0714
144.3571
145.6429
146.9286
148.2143
149.5
150.7857
152.0714
153.3571
154.6429
155.9286
157.2143
158.5
159.7857
161.0714
162.3571
163.6429
164.9286
166.2143
167.5
168.7857
170.0714

## Sheet2 (hidden)
Theme
Theme 1 - Forward Migration - CoA & CoS
Theme 2 - Reverse Migration - CoS
Theme 3 - Import/Export MPANs & Exception Handling