## Consolidated
MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log
|  |  |  | Reviewer to Complete | [5 empty] | Programme to complete once consultation window has closed.
Ref | Organisation | Constituency | Date | Reviewer | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject or Action | Response | Status
1 | Utilita | Supplier | 28.02.2024 | Kev Roper | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make
2 | Wheatley Solutions | Software Suppliers | 01.03.2024 | Stuart Atkins | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-SoS-MS-DS v0.1xlsx | SIT-M-RM-COS-MS-DS-TC03 Smart | 44 | This step suggests that the outgoing Metering Service would issue both D0149/D0150 but isn't it expected that the SMSO would only issue a 'skeleton' D0150 (as per step 45)? | Accept | Corrections made | Complete
3 | Wheatley Solutions | Software Suppliers | 01.03.2024 | Stuart Atkins | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-SoS-MS-DS v0.1xlsx | SIT-M-RM-COS-MS-DS-TC03 Smart | 49 | This step suggests that the outgoing Metering Service would issue both D0149/D0150 but isn't it expected that the SMSO would only issue a 'skeleton' D0150 (as per step 45)? | Reject | Skeleton D150 is sent only for MS and not DS | Complete
4 | Wheatley Solutions | Software Suppliers | 01.03.2024 | Stuart Atkins | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-SoS-MS-DS v0.1xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | Various | Refers to SMSO rather than AMSO | Accept | Corrections made | Complete
5 | Wheatley Solutions | Software Suppliers | 01.03.2024 | Stuart Atkins | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-SoS-MS-DS v0.1xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 53 | Incoming MOP would issue D0268 (as per step 52) - this step references D0149/D0150 | Accept | Corrections made | Complete
6 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC01 Trad & SIT-M-RM-COS-MS-DS-TC02 Adv & SIT-M-RM-COS-MS-DS-TC03 Smart | Missing | D0148 flow is missing from process step, following the D0011 | Reject | Out of scope | Complete
7 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC01 Trad | 46 | Terminology - Metering Service is used in this step when I think it should be be MOP as it refers to Legacy Arrangements | Accept | Corrections made | Complete
8 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC01 Trad | Missing | Should D0303 flow be included for completeness? | Reject | Out of scope | Complete
9 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 48 | For completeness, should D0150/D0149 sending to Supplier and LDSO also be included here? | Reject | BPM & BPD do not list this send. | Complete
10 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | All | 7, 8, 9 | 1. D0170 to LDSO and D0215 is for New Connections, as this is not a New Connection scenario does not seem relevant to test. 2. However if you are testing the D0170 to LDSO, should you also be testing the D0382 response (rejection), in place of the D0215? | Accept | Corrections made | Complete
11 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | All | Example 25 | There are several test steps that have Evidence Required? field null however there is Test Evidence notes populated in P. Can Evidence Required? be updated to reflect this so that items are not missed when filtering? | Accept | Corrections made | Complete
12 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 51 to 54 | Assumed thie field is not complete/typo - "[ReadomgCOS]?" | Accept | Corrections made | Complete
13 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | SG | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 44 | "SDS for non-smart Metering Services will send D0150 & D0149. " Think this should be MSS? Although this tab is for Smart so not sure this is relevant? | Accept | Corrections made | Complete
14 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | IH | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC02 Adv | 7 to 9 | The steps around "Metering Services will issue a D0170 to the LDSO to request Metering Technical details on a new connection" make no sense in the context of this test log since this test is on Reverse Migration | Accept | Corrections made | Complete
15 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | IH | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC02 Adv | 42 | Test Evidence should read "(1) Evidence that DIP produces a PUB-003 which is consumed by Outgoing Data Service. | Accept | Corrections made | Complete
16 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | IH | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC02 Adv | 23 to 26, 46 to 47 | Why is this being tested at all, this is out of scope for MHHS and is a BAU activity | Accept | Steps are listed for completeness | Complete
17 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | IH | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC02 Adv | 49 | Why is this being tested at all, this is out of scope for MHHS and is a BAU activity | Accept | Steps are listed for completeness | Complete
18 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | IH | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC02 Adv | 51 to 56 | Why is this being tested at all, this is out of scope for MHHS and is a BAU activity | Accept | Steps are listed for completeness | Complete
19 | IMServ Europe | Independent Supplier Agent | 01.03.2024 | IH | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC02 Adv | Missing step | For completeness, if legacy BAU steps are all being included, then the D0148 flow is missing as is the triggereing of a Proving Test | Reject | Out of scope | Complete
20 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 1 | How will this be delivered. Reverse migration is automatic where a non qualified Supplier registers an MHHS metering point. Will SIT suppliers be removed from as MHHS qaulified in ISD to allow the test to take place? | Accept | A stub will be required to initiate this step | Complete
21 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 2 | What is the reference to MPAN Enquiry Webservice covering in column H? | Reject | This is as per the BPM/BPD. Suppliers may need to use the MPAN Enquiry Web Service in order to establish criteria for taking supply. Description updated to make this clear. | Complete
22 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 2 | The registration pending notification to the Registration Service is 2800 not 1800. | Reject | It is CSS2800 as can be seen in the BP Step 70 | Complete
23 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 5 | This is in the wrong place. The pending registraton sync is covered in step 2 and should not be issued after the secured active sync. | Accept | Changes made to script | Complete
24 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 6 | This should be moved to inbetween steps 2 and 3 as it follows the pending notification | Accept | Changes made to script | Complete
25 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 7, 8 and 9 | These are irrelevant to reverse migration. There's no need to request the site technical details as these are only required for New Connections. | Accept | Changes made to script | Complete
26 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 11 | The content in column I is irrelvant as this is a reverse migration scenario so there is no choice. Suggest steps 10 and 11 are merged. | Accept | Changes made to script | Complete
27 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 12 | The reference to Site Technical Details in Column I is irrelevant. Instead the scenario needs to iclude the IF-003 via the DIP which triggers the sending of MTDs to the gaining MOA. (Included in Step 31) | Accept | Changes made to script | Complete
28 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 27-30 | These steps are not relevant as they reflect MHHS appointment arrangements which will not be applicable for the appointment of legacy agents. | Accept | Changes made to script | Complete
29 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 49 | This is a duplicate of step 46. | Reject | Step 46 is the sender step. Steps 47, 49 are the receiving steps. | Complete
30 | RECCo | Central Party / Code Body | 04.03.2024 | Sarah Jones | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 51 + 52 | These are duplicates of step 46. | Reject | These steps are on the DS side. 46 is on the MS side. | Complete
31 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 20 | The Supplier will also need to send a D0153 to appoint a DA. | Accept | This is out of scope anyway along with the other agent appointments as this is legacy | Complete
32 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 21 | A D0011 will also be required from the incoming DA. | Accept | This is out of scope anyway along with the other agent appointments as this is legacy | Complete
33 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 24 | Unsure of the reference to the 'CSS daily batch' here? Is this the MPRS updating CSS of the MOA? | Accept | Changes made to script | Complete
34 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 23+25 | The 'settlement details' requiring update should be specified. (PC, SSC, MTC, MC etc.) | Reject | Too much detail for something that is out of scope | Complete
35 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 23+25 | There is no reference to EES being updated with the legacy agents and data items via the ERDS Update File. | Reject | Too much detail for something that is out of scope | Complete
36 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Trad | 43 | The RS notification to the existing MOA of who the new MOA is seems to be missing. This should be a test step. | Reject | Too much detail for something that is out of scope | Complete
37 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Advanced | All | See above RECCo comments on the Trad test case which also apply to the Advanced test | Accept | Implemented as in Trad | Complete
38 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Advanced | 53 | The MTD flow has switched from a D0268 to D0149/D0150. Should be D0268. | Accept | Implemented as in Trad | Complete
39 | RECCo | Central Party / Code Body | 04.03.2024 | Jonny Moore | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS | Smart | All | See above RECCo comments on the Trad test case which also apply to the Advanced test | Accept | Implemented as in Trad | Complete
40 | Elexon-Helix |  | 04.03.2024 | Sailaja Puthota | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | General |  | Should we include VAS application, to test the settlements are not happening in Helix for the migrated MPAN. Please update if VAS transition functionality will be covered in another theme? | Reject | Other migration tests do not have the VAS application steps. We feel this should be added to Phase III instead. | Complete
41 | DCC | Central System | 04.03.2024 | Mahadesha Subramanyam | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC01 Trad, SIT-M-RM-COS-MS-DS-TC02 Adv and SIT-M-RM-COS-MS-DS-TC03 Smart | 3, 4 and 5 | CSS interface numbers should include a five character numerical identifier (e.g. "CSS02370"). It is shown as as four character CSS2370, CSS2860 and CSS2800. | Accept | Corrections made in script | Complete
42 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | N/A | At what point in this Test Case does the Incoming Supplier appoint its Metering Service and Data Service Agents? Step 7 has the Incoming Metering Service issuing a D0170 to the LDSO to request MTD but this doesn't appear to have been preceded by an Appointment. | Reject | More clarity required, because in Reverse Migration we don't appoint MHHS agents. Perhaps I may have misunderstood the question. | Complete
43 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 6 | The Test Description states that the Registration Service will send an IF-002 before stating that, for a reverse migration, it will send a D0170. Given this Test Case is about a reverse migration, would it not be clearer to either lead with the D0170 or, better still, remove all references to the IF-002 (which is irrelevant in the context of this Test Case)? | Accept | Corrections made in script | Complete
44 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 7 | The Test Description states that the Metering Service will issue a D0170 on a new connection. Is this Test Case testing a new connection or a Change of Supply? Assuming the latter, the reference to a new connection is, at best, superfluous and possibly confusing. | Accept | Corrections made in script | Complete
45 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 11 | I do not understand the Test Description for this step. For this to be a reverse migration Test Case, I assume the pre-requisite is an MPAN currently being settled in MHHS. Under what circumstances would a MHHS-qualified Supplier gaining an MPAN that is being operated in MHHS, decide to reverse migrate and operate it under legacy settlement? Also, why the reference to "if the MPAN is being operated under the Legacy arrangements" since an MPAN operated under MHHS arrangements is presumably a pre-requisite for this Test Case? | Accept | Corrections made in script | Complete
46 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 24 | The Trigger Sender for this Test Step is shown as the incoming Supplier. However, the Test Step is waiting for CSS to run the daily batch. Would "CSS" not be a better Trigger Sender? | Reject | Not sure this question makes sense, looking at the test case, Step 24 is different to what is being said. The Supplier initiates the switch in the CSS then the CSS sends the relevant message to the REGS | Complete
47 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 24, 26 | These two Test Steps are essentially doing the same thing but for different Agents (Metering Service and Data Service) and yet they have different Test Descriptions which is somewhat confusing. | Accept | Corrections made in script | Complete
48 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 27, 29 | These Test Descriptions discuss two possible outcomes: the switch is secured or becomes lapsed. Which outcome is being tested in this Test Case? | Accept | Corrections made in script | Complete
49 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | 50, 55 | The Trigger Sender, Interface ID, Trigger Recipient, Traceability Requirement and Evidence Required columns are incomplete for these Test Steps. | Reject | This is because there aren't any triggers/data flows/etc. | Complete
50 | DCC | Central System | 04.03.2024 | Chris Beard | Theme 2 - Reverse Migration - CoS | MHHS-DEL2316-SIT-M-RM-CoS-MS-DS v0.1 | SIT-M-RM-COS-MS-DS-TC03 Smart | N/A | On a reverse migration, do we not require the DSP to de-appoint the MDR to prevent access to the customer's meter beyond the end of their appointment? This appears to still be missing from the BPMs on which this Test Case is based, despite having been raised several times with the MHHS Design Team. | Accept | Corrections made in script | Complete
51 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC01 Trad | 34 | DS is in the description but not the recipient or validation columns | Accept | Corrections made to the script
52 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC01 Trad | 42 | This is a DS step, the validation column references the Metering Service | Accept | Corrections made to the script
53 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC01 Trad | 60 | Some confusion between steps 60 and 61 over who is sending and receiving the reads | Accept | Corrections made to the script
54 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC01 Trad | 61 | Some confusion between steps 60 and 61 over who is sending and receiving the reads | Accept | Corrections made to the script
55 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 20 | Typo in the validation column should be D0155 | Accept | Corrections made to the script
56 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 34 | DS is in the description but not the recipient or validation columns | Accept | Corrections made to the script
57 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 42 | Recipient should be ADSO | Accept | Corrections made to the script
58 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 46 | D0383/D0384 not sent to DC | Accept | Corrections made to the script
59 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 47 | D0383/D0384 not sent to DC | Accept | Corrections made to the script
60 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 51 | Steps 51 and 52 look to be the same | Accept | Step 52 merged into Step 51
61 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 52 | Steps 51 and 52 look to be the same | Accept | Step 52 merged into Step 51
62 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC02 Adv | 53 | Either a D0268 or a D0149/D0150 will be sent depending on the site, should this not be in a separate test case for sites that get a D0149/D0150 | Reject | Advanced Metering Services will send a D0268. Smart & Traditional Metering Services will send D0150 & D0149. This has been addressed in the different metering segment test cases
63 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC03 Smart | 22 | Typo in interface ID column, should be D0011 | Accept | Corrections made to the script
64 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC03 Smart | 34 | DS is in the description but not the recipient or validation columns | Accept | Corrections made to the script
65 | TMA Data Management Ltd | Independent Agent | 04.03.2024 | Keith Donaldson | Theme 2 - Reverse Migration - CoS | TMA MHHS-DEL2234 SIT Migration Test Scenarios and Test Cases Comments Log.xlsx | SIT-M-RM-COS-MS-DS-TC03 Smart | 44 | Interface ID has a repead of D0150 | Accept | Step has been changed ro reflect other comments as well.
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347

## Sheet2 (hidden)
Theme
Theme 1 - Forward Migration - CoA & CoS
Theme 2 - Reverse Migration - CoS
Theme 3 - Import/Export MPANs & Exception Handling