## Consolidated
MHHS-DEL-2234 SIT Migration Test Scenarios and Test Cases Comments Log
|  |  |  | Reviewer to Complete | [5 empty] | Programme to complete once consultation window has closed.
Ref | Organisation: | Constituency: | Date: | Reviewer | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Action | Response | Status | Comments
1 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2403 SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
2 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2390 SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
3 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2405 SIT-M-FM-CoA-InvReq v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
4 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2401 SIT-M-FM-CoA-Lapsed v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
5 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2397 SIT-M-FM-CoA - Missing Reads Deemed Reads v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
6 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2394 SIT-M-FM-CoA-MissMTD v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
7 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2404 SIT-M-FM-CoA - Rejected Appointment v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
8 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS- DEL2388 SIT-M-FM-CoA-REL-MPAN Test Scenarios And Test Cases v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
9 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2411 SIT-M-FM-CoA-SameDate v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
10 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2408 SIT-M-FM-CoA - Unmetered v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
11 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2391 SIT-M-FM-CoS-IE-MPAN Test Scenarios And Test Cases v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
12 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2407 SIT-M-FM-CoS-InvReq v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
13 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2402 SIT-M-FM-CoS-Lapsed v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
14 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2398 SIT-M-FM-CoS - Missing Reads Deemed Reads v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
15 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2395 SIT-M-FM-CoS-MissMTD v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
16 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2406 SIT-M-FM-CoS - Rejected Appointment v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
17 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2389 SIT-M-FM-CoS-REL-MPAN Test Scenarios And Test Cases v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
18 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2412 SIT-M-FM-CoS-SameDate v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
19 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2409 SIT-M-FM-CoS - Unmetered v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
20 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2400 SIT-M-RM-CoS-CancAppt v0.1 | SIT-M-RM-COS-CANCAPPT-TC01 | 135 - 150 | What is the significance of the test steps highlighted in yellow? | Accept | None. This were a reminder to make changes to the steps across the board | Complete
21 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2392 SIT-M-RM-CoS-IE-MPAN v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
22 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2399 SIT-M-RM-CoS - Missing Reads Deemed Reads v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
23 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2396 SIT-M-RM-CoS-MissMTD v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
24 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2393 SIT-M-RM-CoS-REL-MPAN v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
25 | Utilita | Supplier | 2024-03-18 | Kev Roper | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL-2410 SIT-M-RM-CoS - Unmetered v0.1 | N.A. | N.A. | I have reviewed the document and have no comments to make | Accept |  | Complete
26 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | 215 | Outgoing ADSC doesn't receive an IF-036? | Accept | Test Step corrected to reflect ADSC being published the PUB-36 | Complete
27 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | 265 | Since this scenario is COA for MS+DS, all flows being sent to the DS form the MS would be from the incoming DS not the outgoing one | Reject | The step currently is already showing AMSC sending D0268 to the ADSI. Please clarify. | Complete
28 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | 325 | AMSI not AMSC is receiving the IF-36 | Accept | Corrected AMSC to AMSI | Complete
29 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | 395 | Test not needed, this is legacy BAU so why test | Reject | Step needed for clarity & completeness. | Complete
30 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | 420 onwards | All the previous steps have talked about ADS therefore deeming a read etc would not be performed by the ADS? | Reject | We're saying that it should be performed by the outgoing data collector | Complete
31 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC01 TRAD | 310/325/345 | This step talks about Smart MTDs but the scenario is for Trad meter | Accept | Step corrected to remove reference to Smart MTDs | Complete
32 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC01 TRAD | 375 | This step isn't needed - no added value to scripts | Accept | Steps shown as End Points removed | Complete
33 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC01 TRAD | 400/430 | Should DA be added as recipient of the D0019 here for completeness? - Also issue on ANHH scenario | Reject | This is out of scope for the test. there are no data collector/aggregator. We could have added more messages but because this is out of scope anyway, it would not have made a difference. | Complete
34 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC01 TRAD | 415/445 | No step to cover the sending of the D0010 to the DS | Reject | Both these steps include the D0010 send to the DS | Complete
35 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC01 TRAD | 430 | Missing step to cover D0010 withdrawing incorrect read - also issue on ANHH scenario | Accept | Step added for Trad and ANHH tests | Complete
36 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | 305 | Step is missing D0384 which is also sent to Supplier - also issue on AHH scenario | Reject | We don't expect the D0384 to be sent. | Complete
37 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC03 AHH | 305 | Again this step talks about Smart MTDs but the scenario is for Advanced meter | Accept | Step corrected to remove reference to Smart MTDs | Complete
38 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC02 ANHH | Missing | The incoming DS obtaining the I read seems to have been omitted from this scenario but included in others on the same spreadsheet | Accept | Add 1007 for the ANHH test | Complete
39 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC04 SNHH | 310 | PUB-037 is incorrect for this step | Accept | PUB-37 reference corrected | Complete
90 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-MS-DS-IE | ANHH (and the others) | 495 | As part of the linked MPAN Processing we should ensure that the tests cover the situations where a) agents a misaligned across the association and the Export MPAN needs to be aligned b) agents are aligned so no alignment takes place. This doesn't appear to be clear in the test cases. | Accept | Notes on Overview updated to clarify. Description in the test step also clarifies what needs to happen in bold. MS & DS alignments will be different for Advanced and Smart meters. These have been defined in the test step | Complete
41 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Missing Reads Deemed Reads.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 310 | Whole steps seems wrong, talks about Smart MTDs and recipient is ADS but the scenario is Trad meter | Accept | Step corrected to remove reference to Smart MTDs and changed ADSI to SDSI | Complete
42 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Missing Reads Deemed Reads.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 395/403 | These steps seem to contradict each other, one is sending the D0010 to the Outgoing DC, and one is deeming a read where the D0010 isn't sent. If the test is to meant to cover deeming in the absence of a read step 395 is not needed | Reject | Steps 395-415 will be repeated in case of an incorrect meter reading and new meter readings will be requested. | Complete
43 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Missing Reads Deemed Reads.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 275 | Recipient stated as SMSI - scenario is for Advanced so should be AMSI | Reject | Step does say AMSI. | Complete
44 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Rejected Appointment.cleaned | SIT-M-FM-CoA-RejApt-TC01 All | 85/115 | Scenario is to test rejected appointment but both steps state appointment accepted | Accept | Steps 230 and 91 removed | Complete
45 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Rejected Appointment.cleaned | SIT-M-FM-CoA-RejApt-TC01 All |  | Test case states it covers all meter types but only Smart services are tested not Advanced in steps | Reject | The steps are common for all types of meters | Complete
46 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC03 AHH | 420 | Receipient is ADSI but comment states " Evidence that Current Supplier processes D0010/D0019 from stub; log screenshots in downstream systems." | Accept | Validation corrected to reflect ADSI instead of Current Supplier | Complete
47 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC03 AHH | ALL | Steps 420 to 440 are not correcting anything, what is the purpose of this entire test? It is definitely not " Correcting incorrect FM CoA reading" as per your intro | Reject | Steps 390 to 415 are repeated as Steps 420 to 440 in case incorrect meter readings are received. | Complete
48 | IMSERV | Ind. Agent | 2024-03-19 | IH | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | All of them | ALL | I am not prepared to review this artifact any further as it is not fit for purpose | Reject | Further responses received | Complete
49 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 7 - Supplier De-appointment MA, doesn't belong on a Metering Service requirement line. There is no concept of de-appointing an UMSO in the 1998 settlement arragements | Accept | Changes made | Complete
50 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 8 - D0170 is not used in Unmetered arrangements. This would not be a flow to tell a HHDC that Migration is occuring for UMS. | Accept | Changes made | Complete
51 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 12 - D0151 is optional, this requirement should be corrected to match BSCP520 on how a MA is de-appointed | Accept | Changes made | Complete
52 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 13 - D0170 is not used in Unmetered arrangements. This would not be a flow to tell a HHDC that Migration is occuring for UMS. | Accept | Changes made | Complete
53 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | n/a | line 32 - there is no MOP in Unmetered arrangments. This requirement is incorrect | Accept | Changes made | Complete
54 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 36 - D0170 is not used in Unmetered arrangements. | Accept | Changes made | Complete
55 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 215 | line 43 & 45 - PUB-035 is descoped from UMSDS testing. It will not be used/received by some roles. | Lee Cox | Design team has been asked this question. Awaiting response. | Pending
56 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 270 | line 58 - UMSDS receiving a PUB-036 should not be against a MS requirement | Accept | Changes made | Complete
57 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 68 & 69 - please correct UMSDS role code (to say UMSDS) | Accept | UMDS changed to UMSDS | Complete
58 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 |  | line 72 & 73 - there is no transfer of readings in Unmetered Supplies | Reject | Test is as expected. DC is using final day's data. | Complete
59 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | ALL | Much of what is wrong with the COA document, is wrong on this CoS process document too | Accept | Changes made | Complete
60 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line 16 - missing that the IF-003 is also sent to UMSO and UMSDS | Accept | Added UMSO and UMSDS to receipients. Added corresponding steps too. | Complete
61 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line24 - there is no MOP in Unmetered arrangments. An UMSO does not get a D0155 in current settlement arrangements. Needs correction of creation of a process to inform them if it is intended. | Accept |  | Complete
62 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line24 - there is no MOP in Unmetered arrangments. Should reflect MA. Needs to recognise D0155 may not be used by MA, it is bilaterally agreed between Supplier/MA | Accept | MOP changed to MA These tests are only kept for completeness. They are out of scope for SIT. | Complete
63 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line28 - there is no MOP. D0011 could be sent by a MA to Supplier, but down to any bi-lateral agreement as it is not mandatory | Accept | Changes made | Complete
64 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line 41 - why is a reference to AMSO being used for Unmetered process? | Accept | Changes made | Complete
65 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line 41 - missing UMSO as recipient | Accept | Changes made | Complete
66 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line 45 - missing UMSDS as recipient | Accept | Changes made | Complete
67 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line 48 & 49 - should be the UMSO doing this, not LDSO | Reject | We think the LDSO gets a PUB-003 as well | Complete
68 | IMSERV | Ind. Agent | 2024-03-19 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 |  | line 58 - then missing that the MA should send to the UMSO the D0389 Flow | Reject | This is out of scope of testing as MA will not be involved in testing. | Complete
69 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS-REL-MPAN.xlsx | SIT-M-RM-CoS-REL-MPAN-TC01 Trad | 95 | Although MOP/MS is out of scope (red text) - Test Description states that specific value will be used in the Contract Reference, whereas Design states that REVM will be used in the Service Reference and Service Level Reference items. | Accept | Text changed to have REVM as the specific text | Complete
70 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS-REL-MPAN.xlsx | SIT-M-RM-CoS-REL-MPAN-TC02 Adv | 95 | Although MOP/MS is out of scope (red text) - Test Description states that specific value will be used in the Contract Reference, whereas Design states that REVM will be used in the Service Reference and Service Level Reference items. | Accept | Description corrected to include REVM. | Complete
71 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS-REL-MPAN.xlsx | SIT-M-RM-CoS-REL-MPAN-TC03 SMRT | 95 | Although MOP/MS is out of scope (red text) - Test Description states that specific value will be used in the Contract Reference, whereas Design states that REVM will be used in the Service Reference and Service Level Reference items. | Accept | Description corrected to include REVM. | Complete
105 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | General COS | General | N/A | The COA comments above will generally be applicable for the COS and Reverse Migration versions of the test. | Accept | Changes that we could recognise as above have been made. | Complete
85 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | N/A | N/A | N/A | There are no test cases covering the update of ISD data when a new party is qualified. As per the Migration A&P this process is in the scope of SIT Migration and we would expect a test case to cover this off. | Accept | This shall be addressed at a later point. | Complete
86 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | N/A | N/A | N/A | All tests involving a completed migration for a Smart meter should have the MS and MDR update sent to the CSS and then onward to the DSP. | Accept | All Smart meter tests have the CSS/DCC update steps | Complete
40 | IMSERV | Ind. Agent | 2024-03-19 | SG | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings.cleaned | SIT-M_FM-COA-CORRREAD-TC01 TRAD |  | There is no step to tell the Outgoing DC that the meter read already used is incorrect and should be withdrawn. Simply the sending of an additional D0010 would not cause the DC to withdraw a valid read and validate another one (if one is already held for that same date). Note this is the case for the other scenarios on here too. | Accept | Create the same step as 118 | Complete
76 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA-Lapsed.xlsx | SIT-M-FM-COA-LAPSED-TC01 Trad | 255 | Lapsed IF-035 message not documented with a Trigger Recipient of Metering Service (Trigger Recipient missing in this step, which should presumably be the Metering Service). Similar on other tabs. | Accept | Metering Service added | Complete
77 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Rejected Appointment.xlsx | SIT-M-FM-COS-RegApt-TC01 | 195 | Should the IF-034 being sent by the Metering Service be a Rejection? This isn't clear within the test steps. | Accept | Test description corrected to rejection | Complete
78 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-Lapsed.xlsx | SIT-M-FM-COS-Lapsed-TC01 Trad | 370 | Lapsed IF-035 message not documented with a Trigger Recipient of Metering Service (Trigger Recipient missing in this step, which should presumably be the Metering Service). Similar on other tabs. | Accept | Metering Service added | Complete
79 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-Lapsed.xlsx | SIT-M-FM-COS-Lapsed-TC02 ANHH | 350 | Lapsed IF-035 message not documented with a Trigger Recipient of Metering Service (Trigger Recipient missing in this step, which should presumably be the Metering Service). Similar on other tabs. | Accept | Metering Service added | Complete
80 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-Lapsed.xlsx | SIT-M-FM-COS-Lapsed-TC03 AHH | 350 | Lapsed IF-035 message not documented with a Trigger Recipient of Metering Service (Trigger Recipient missing in this step, which should presumably be the Metering Service). Similar on other tabs. | Accept | Metering Service added | Complete
81 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-Lapsed.xlsx | SIT-M-FM-COS-Lapsed-TC04 SNHH | 320 | Lapsed IF-035 message not documented with a Trigger Recipient of Metering Service (Trigger Recipient missing in this step, which should presumably be the Metering Service). Similar on other tabs. | Accept | Metering Service added | Complete
82 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-Lapsed.xlsx | SIT-M-FM-COS-Lapsed-TC05 SHH | 320 | Lapsed IF-035 message not documented with a Trigger Recipient of Metering Service (Trigger Recipient missing in this step, which should presumably be the Metering Service). Similar on other tabs. | Accept | Metering Service added | Complete
72 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS-REL-MPAN.xlsx | SIT-M-RM-CoS-REL-MPAN-TC01 Trad | 255 | Although MOP/MS is out of scope (red text) - Incoming MOP to issue MTD flows to Incoming DC, but no D0148 provided to identify DC. | Reject | Step includes the D0010 sent to the DS. This step will not be tested in SIT-M anyway. | Complete
73 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS-REL-MPAN.xlsx | SIT-M-RM-CoS-REL-MPAN-TC02 Adv | 230 | Although MOP/MS is out of scope (red text) - Incoming MOP to issue MTD flows to Incoming DC, but no D0148 provided to identify DC. | Reject | Step includes the D0010 sent to the DS. This step will not be tested in SIT-M anyway. | Complete
74 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS-REL-MPAN.xlsx | SIT-M-RM-CoS-REL-MPAN-TC03 SMRT | 245 | Terms are confusing here as this step talks about Smart Metering Services sending D0149 / D0150. Also, would incoming MOP be able to send D0149 if it has only received a Skeleton D0150 from the outgoing MS? There also doesn't seem to be a corresponding step where Service Type is MS and the MRDs are being sent (unlike the equivalent step 230 on the Trad tab). | Reject | Incoming MOP will be able to generate D0149 from the Skeleton D0150 and the D0367 | Complete
75 | Wheatley | Software Solutions | 2024-03-19 | Stuart Atkins | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Missing Reads Deemed Reads.xlsx | SIT-M-RM-COS-DeemRead-TC01 All | 230 | Although MOP/MS is out of scope (red text) - This is a common step on a number of the spreadsheets and states the Incoming MOP will issue MTDs to Supplier, Incoming DC and LDSO. This contradicts the DEL961 Migration Design Document that states that the MTDs will only be shared with incoming Supplier and DC (not LDSO). It should be noted that the test steps are in line with the current CoS/CoA process and the Design Document deviates from this. As per previous comments there is also no D0148 mechanism to allow the Incoming MOP to identify the Incoming DC. | Reject | We believe that the MTDs get sent to the LDSO too. LDSO is listed in the BPD document, but not in the BPM. We believe the BPM is incorrect and are raising this with the Design Team. | Complete | Raised with Design Team. Awaiting response. In the meantime, we're keeping the test in line with our understanding that LDSO does get sent the MTDs.
83 | Calisto | SDS/ADS/MSS/MSA | 2024-03-19 | Dave Woodhouse (MS) | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA-REL-MPAN Test Scenarios And Test Cases | SIT-M-FM-COA-REL-MPAN-TC4 SNHH | 310 | SIT-M-FM-COA-REL-MPAN-TC4 - Step 310 has Interface ID as IF-037, should be IF-036 | Accept | Corrected to IF-036 | Complete
84 | Calisto | SDS/ADS/MSS/MSA | 2024-03-19 | Rob Adams (DS) | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA-Lapsed | SIT-M-FM-COA-LAPSED-TC01 Trad | 91 and 280 | For the CoA Lapsed scenarios, DS are listed as receiving two IF-035s - one with an Accepted message, then another with a Lapsed message. May be a valid scenario, but we understood as DS we'd only ever get one IF-035. | Reject | For Lapsed appointment scenario, the IF-035 gets sent twice - first when the appointment is accepted, and then when it lapses. | Complete
89 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-MS-DS-IE | ANHH (and the others) | 490 | The Note stating that the linked section refers to related MPANs only is not required in this test case and causes confusion. | Accept | Note has been removed | Complete
87 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-MS-DS-IE | Trad | N/A | I don't believe it is possible to have an Export Trad Meter | Accept | Traditional meters Export tests have been removed | Complete
88 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-MS-DS-IE | All | N/A | I'm assuming that these tests are for a single Import and Export MPAN in a relationship with a single Supplier and migrating at the same time. A test for an Export MPAN migrating indepently with an already migrated associated Import MPAN registered by a seperate Supplier , followed by the alignment of agents should be added. | Reject | The MPANs are always migrated separately, never together. The comment in the Overview Tab has been updated to make this clear. | Complete
92 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-InvReq | TC01 | 40 + 55 | The REGS is accepting the IF-032 in these steps. Is this an error? | Accept | The description has been corrected | Complete
91 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-InvReq | TC01 | 10 + 20 | This test case appears to be testing where an IF-031 fails the RS validation rules. As such the test should specify which error should be added into the IF-031 to trigger the failure. | Accept | Example - Trying to appoint IF-031 with a Smart Data Service for an Advanced MPAN | Complete
94 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-Missing MTDs | All | General | I'm not actually sure what additonal test steps are actually being covered here. The MTDs are being received by all parties. Are these tests actually required? | Reject | Needs further clarification. Not sure what the comment means. Please can you elaborate. | Complete
95 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-Rejected Appointment | TC01 | 85+115 | It appears both agents are accepting the appointment. As this is a rejected appointment test is this an error? | Accept | The description has been corrected | Complete
96 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-Rejected Appointment | TC01 | 120 | This step is not required if the DS is rejecting the appointment. | Accept | The description has been corrected | Complete
93 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-Lapsed | TC01 Trad | 220 | As this is a COA test I'm not sure what CSS notification is expected? - This would normaly only be applicable for a COS. | Reject | No CSS notification is expected - the text is generic. | Complete
98 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-REL-MPAN | TC1 Trad | 495 | The note around Import/Export MPANs isn't required for this test case. | Accept | The description has been corrected | Complete
99 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA Same Date | General | N/A | I can't see any difference in the test steps for these test cases from the standard COA tests. Are these tests required? | Reject | Same date appointments do not wait in the queue to be processed daily. | Complete
97 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA-REL-MPAN | All | Linked MPAN Processing | After the automatic agent appointment has been progressed the obtaining of MTDs and final reads would occur as per the Primary MPAN. This should also be included in the test case. | Reject | This is out of scope as this is BAR activity. The secondary MPAN is usually migrated last anyway. | Complete
101 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM COA-Unmetered | TC01 | General | No test step numbers in the document. | Accept | Test numbers have been added | Complete
100 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COA Same Date | General | N/A | Through the Migration Framework discussions it's been proposed that a Migration would need to have a 10WD lead time, meaning that a same day migration would not be allowed. Is this what this test case is trying to cover? If so the test cases may not be required. | Reject | The migration design supports Same Day migration | Complete
103 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-IE MPAN | TC01 | 65 | EES does not receive the IF-001. Instead data is received direct from CSS. This was confirmed in CR028 which has been implemented. This will be the case for all COS tests. | Accept | Tests have been updated | Complete
102 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM COA-Unmetered | TC01 | ??? | This is a COA test so no secured active notification would be received from CSS. | Accept | The steps have now been removed | Complete
104 | RECCo | Central Party / Code Body | 2024-03-20 | Jonny Moore | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-COS-IE MPAN | General | N/A | It would be good to include a COS test for Export only, where the associated Import is regsitered to another Supplier, followed by the agent alignment. | Accept | This has been clarified in the Overview | Complete
106 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC01 Trad | 40, 55 | Test Description says 'The REGS will accept the 'Supplier Service Appointment Request' while REGS is the trigger sender and not trigger receipient? | Accept | Description has been updated | Complete
107 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC01 Trad | 110 | Trigger sender/ receipient, Interface ID shouldn't be N/A? | Reject | This is just the internal business process that happens. So, N/A is correct | Complete
108 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC02 ANHH | 30, 45 | Test Description says 'The REGS will accept the 'Supplier Service Appointment Request' while REGS is the trigger sender and not trigger receipient? | Accept | Description has been updated | Complete
109 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC02 ANHH | 100 | Trigger sender/ receipient, Interface ID shouldn't be N/A? | Reject | This is just the internal business process that happens. So, N/A is correct | Complete
110 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC03 AHH | 30, 45 | Test Description says 'The REGS will accept the 'Supplier Service Appointment Request' while REGS is the trigger sender and not trigger receipient? | Accept | Description has been updated | Complete
111 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC03 AHH | 100 | Trigger sender/ receipient, Interface ID shouldn't be N/A? | Reject | This is just the internal business process that happens. So, N/A is correct | Complete
112 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC04 SNHH | 30, 45 | Test Description says 'The REGS will accept the 'Supplier Service Appointment Request' while REGS is the trigger sender and not trigger receipient? | Accept | Description has been updated | Complete
113 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC04 SNHH | 100 | Trigger sender/ receipient, Interface ID shouldn't be N/A? | Reject | This is just the internal business process that happens. So, N/A is correct | Complete
114 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC05 SHH | 30, 45 | Test Description says 'The REGS will accept the 'Supplier Service Appointment Request' while REGS is the trigger sender and not trigger receipient? | Accept | Description has been updated | Complete
115 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403 SIT-M-FM-CoA-Correcting Incorrect Fwdmig CoA Readings | SIT-M-FM-COA-CorrRead-TC05 SHH | 100 | Trigger sender/ receipient, Interface ID shouldn't be N/A? | Reject | This is just the internal business process that happens. So, N/A is correct | Complete
116 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390 MHHS-DEL2405 MHHS-DEL2401 MHHS-DEL2397 MHHS-DEL2394 MHHS-DEL2404 MHHS-DEL2388 MHHS-DEL2411 MHHS-DEL2391 MHHS-DEL2402 MHHS-DEL2398 MHHS-DEL2395 MHHS-DEL2406 MHHS-DEL2389 MHHS-DEL2412 | All test cases | various | See comments (Ref 1 to 10) for MHHS-DEL2403 above. The test step number may differ for the test cases in different test scenarios.. | Accept | Description has been updated | Complete
117 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390 SIT-M-FM-CoA-IE-MPAN Test Scenarios and Test Cases | All test cases | 495-550 | Test for Linked MPAN is covered under MHHS-DEL2388 (SIT-M-FM-CoA-REL-MPAN Test Scenarios and Test Cases). What is the idea of including the section 'Linked MPAN Processing' is all the test cases under this test scenario, MHHS-DEL2403? | Accept | These is an Import Export test. Test Section Name updated | Complete
118 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | General | All Test Scenarios | N/A | It would be helpful if the file name of the Test Scenario could contain the MHHS-DEL reference (as with SIT Functional Test Scenarios) | Accept | All files names have been updated | Complete
119 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | General | All Test Scenarios | N/A | The use of gratuitous blank lines and merged cells makes it extremely difficult to combine these Test Scenarios into a single spreadsheet from which proper analysis of the impact of these Test Scenarios on individual parties can be performed. For example, the use of gratuitous blank lines between Test Steps renders the filters inoperable. In the absence of a single directory of Migration Test Scenarios, it is very difficult to perform a meaningful review. | Reject | I appreciate your perspective. However, this is a personal preference. Others prefer the current method of listing. | Complete
120 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC01 Trad | 40 | Despite previous review comments on this subject, the Test Case still contains multiple paths ('All requests, Valid requests only'). When executing this Test Step, which path is the participant supposed to be following in order to obtain a pass? If the answer is 'both', this should be reflected in two separate Test Cases. | Reject | The steps only narrow down to Valid Requests after passing through the All Requests decision. Only 1 path is chosen to be progressed per testcase. | Complete
121 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC01 Trad | 100-125 | CSS figures heavily in the Test descriptions but the Trigger Senders and Recipients for these Test Steps are 'N/A'. Given that these Test Scripts will presumably be uploaded into ADO where Test Steps will be passed on according to Trigger Recipients, these fields should be populated. | Reject | These are internal steps for the REGS. Hence, n/a is correct. | Complete
122 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC01 Trad | 220 | Can we assume that, since there is no indiciation otherwise, no specific CSS intervention is required to ensure that CSS sends no notification of MS/DS appointments? | Reject | CSS isn't involved in this testcase. | Complete
123 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC01 Trad | 295, 300 | These Test Steps occur after the ENDPOINT. Do they need to be performed for a participant to complete the Test Case? | Accept | Test step has been removed | Complete
124 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC02 ANHH | 165-200 | CSS figures heavily in the Test descriptions but the Trigger Senders and Recipients for these Test Steps are 'N/A'. Given that these Test Scripts will presumably be uploaded into ADO where Test Steps will be passed on according to Trigger Recipients, these fields should be populated. | Reject | These are internal steps for the REGS. Hence, n/a is correct. | Complete
125 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC02 ANHH | 285, 290 | These Test Steps occur after the ENDPOINT. Do they need to be performed for a participant to complete the Test Case? | Accept | Test step has been removed | Complete
126 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC03 AHH | 165-200 | CSS figures heavily in the Test descriptions but the Trigger Senders and Recipients for these Test Steps are 'N/A'. Given that these Test Scripts will presumably be uploaded into ADO where Test Steps will be passed on according to Trigger Recipients, these fields should be populated. | Reject | These are internal steps for the REGS. Hence, n/a is correct. | Complete
127 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC03 AHH | 275 | This Test Step has no Trigger Sender or Recipient. It appears to be an action required of the Data Service (in this case, the SDSI). If this field remains blank, how will the Test Case be passed to the Data Service during execution in SIT? | Reject | This is just the internal business process that happens. So, N/A is correct | Complete
128 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC03 AHH | 265, 270 | SInce this Test Case is the migration of an Advanced meter, why is an SDS being appointed? | Accept | SDSI has been corrected to ADSI | Complete
129 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC04 SNHH | 170-200 | CSS figures heavily in the Test descriptions but the Trigger Senders and Recipients for these Test Steps are 'N/A'. Given that these Test Scripts will presumably be uploaded into ADO where Test Steps will be passed on according to Trigger Recipients, these fields should be populated. | Reject | These are internal steps for the REGS. Hence, n/a is correct. | Complete
130 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC04 SNHH | No Test Step reference | These Test Steps occur after the ENDPOINT. Do they need to be performed for a participant to complete the Test Case? | Accept | Test step has been removed | Complete
131 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC04 SNHH | NA | This Test Case is missing Test Steps references for the last 12 Test Steps. | Accept | Test step # have been added | Complete
132 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC04 SNHH | 165-200 | CSS figures heavily in the Test descriptions but the Trigger Senders and Recipients for these Test Steps are 'N/A'. Given that these Test Scripts will presumably be uploaded into ADO where Test Steps will be passed on according to Trigger Recipients, these fields should be populated. | Reject | These are internal steps for the REGS. Hence, n/a is correct. | Complete
133 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC05 SHH | No Test Step reference | These Test Steps occur after the ENDPOINT. Do they need to be performed for a participant to complete the Test Case? | Accept | Test step has been removed | Complete
134 | DCC | Central Systems | 2024-03-20 | Chris Beard | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401 | SIT-M-FM-COA-LAPSED-TC05 SHH | No Test Step reference | This Test Case is missing Test Steps references for the last 12 Test Steps. | Accept | Test step # have been added | Complete
135 | DCC | Central Systems | 2024-03-20 | Mahadesha Subramanyam | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390 MHHS-DEL2403 MHHS-DEL2388 MHHS-DEL2397 MHHS-DEL2401 MHHS-DEL2394 MHHS-DEL2411 MHHS-DEL2391 MHHS-DEL2402 MHHS-DEL2398 MHHS-DEL2395 MHHS-DEL2389 MHHS-DEL2399 MHHS-DEL2396 MHHS-DEL2393 MHHS-DEL2410 | All test cases | various | CSS figures heavily in the Test descriptions but the Trigger Senders and Recipients for these Test Steps are 'N/A' or blank. Given that these Test Scripts will presumably be uploaded into ADO where Test Steps will be passed on according to Trigger Recipients, these fields should be populated. See comments in Ref 24 and 28. The test step number may differ for the test cases in different test scenarios. | Reject | These are internal steps for the REGS. Hence, n/a is correct. | Complete
136 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Clean.xlsx | SIT-M-FM-COA-CorrRead-TC02 ANHH | Numerous | All references to current DS or MS in Forward Migration scenarios are incorrect since there will be no current Service. Reference could be made to outgoing DC or outgoing MO if appropriate | Accept | Changes made | Complete
137 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Clean.xlsx | SIT-M-FM-COA-CorrRead-TC02 ANHH | 415 onwards | These steps seem to be legacy BAU activity so hold no value in testing? If this is true, doesn't this make the whole test scenario redundant? | Reject | The steps describe the process of correcting incorrect readings and require to be repeated. Hence they have been mentioned for completeness. | Complete
138 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Clean.xlsx | SIT-M-FM-COA-CorrRead-TC03 AHH | 415 onwards | These steps seem to be legacy BAU activity so hold no value in testing? If this is true, doesn't this make the whole test scenario redundant? | Reject | The steps describe the process of correcting incorrect readings and require to be repeated. Hence they have been mentioned for completeness. | Complete
139 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Clean.xlsx | SIT-M-FM-COA-CorrRead-TC04 SNHH | 465 onwards | These steps seem to be legacy BAU activity so hold no value in testing? If this is true, doesn't this make the whole test scenario redundant? | Reject | The steps describe the process of correcting incorrect readings and require to be repeated. Hence they have been mentioned for completeness. | Complete
140 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Clean.xlsx | SIT-M-FM-COA-CorrRead-TC05 SHH | 465 onwards | These steps seem to be legacy BAU activity so hold no value in testing? If this is true, doesn't this make the whole test scenario redundant? | Reject | The steps describe the process of correcting incorrect readings and require to be repeated. Hence they have been mentioned for completeness. | Complete
141 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Clean.xlsx | SIT-M-FM-COA-DeemRead-TC02 ANHH |  | This test is described as 'Under this scenario a MHHS Qualified Supplier chooses to migrate a Advanced Meter (NHH) MPAN from Legacy NHH settlements to MHHS arrangements. Correcting incorrect Forward Migration COA Readings.' yet I can see no steps relating to correcting forward migration COA readings | Accept | Changes made | Complete
142 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Clean.xlsx | SIT-M-FM-COA-DeemRead-TC02 ANHH | 400 onwards | These steps seem to be legacy BAU activity so hold no value in testing? | Reject | The steps describe the process required for Deemed Read test. Hence they have been mentioned for completeness. | Complete
143 | IMServ | Ind. Agent | 2024-04-03 | IH | This dropdown doesn't work | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Clean.xlsx | SIT-M-FM-COA-DeemRead-TC03 SNHH |  |  | Reject | There is no issue mentioned here. I assume the concern is same as above. The response therefore, is also as above. The steps describe the process required for Deemed Read test. Hence they have been mentioend for completeness. | Complete
144 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2404-SIT-M-FM-CoA - Rejected Appointment - v0.2 - Clean.xlsx | SIT-M-FM-CoA-RejApt-TC01 All | 80 and 110 | These test steps must instruct the DS and MS to reject the appointment else the following steps do not deliver the intend of this test thread of "Under this scenario a MHHS Qualified Supplier chooses to migrate MPAN for all meter types MPAN from Legacy NHH settlements to MHHS arrangements but the appointment is rejected." Also the test thread is described as "This document lists both DS and MS changes for each meter segment type" yet only lists steps for the SMSI and SDSI so please clarify | Accept | Changes made | Complete
145 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390-SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases - v0.2 - Clean.xlsx | SIT-M-FM-COA-MS-DS-IE-TC01 ANHH | 255 and 265 | For added clarity it should be noted that D268/383/384 flows will be sent for both MPANs. Same for flows going to Supplier and LDSO | Accept | Changes made | Complete
146 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390-SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases - v0.2 - Clean.xlsx | SIT-M-FM-COA-MS-DS-IE-TC01 ANHH | 260 and 270 | For added clarity it should be noted that D268/383/384 flows will be received for both MPANs | Accept | Changes made | Complete
147 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390-SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases - v0.2 - Clean.xlsx | SIT-M-FM-COA-MS-DS-IE-TC01 ANHH | 500 | Outgoing MOP isn't expected to support IF-036 to de-appoint, this should be a D0151 | Reject | The Outgoing MOP will not recieve an IF-036, they will receive a D0151 from the Supplier de-appointing them. | Complete | JW: The Outgoing MOP will not recieve an IF-036, they will receive a D0151 from the Supplier de-appointing them.
148 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390-SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases - v0.2 - Clean.xlsx | SIT-M-FM-COA-MS-DS-IE-TC01 ANHH | Missing step | The termination of outgoing DC for a linked MPAN is missing | Reject | This would be the Outgoing DC receiving a D0151 from Supplier. | Complete | JW: This would be the Outgoing DC receiving a D0151 from Supplier.
149 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390-SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases - v0.2 - Clean.xlsx | SIT-M-FM-COA-MS-DS-IE-Overview | Overview | The test description appears wrong - "Under this scenario a MHHS Qualified Supplier chooses to migrate Advanced HH Import/Export MPANs from Legacy NHH settlements to MHHS arrangements." should be "Under this scenario a MHHS Qualified Supplier chooses to migrate Advanced HH Import/Export MPANs from Legacy HH settlements to MHHS arrangements."? | Accept | Changes made | Complete
150 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2390-SIT-M-FM-CoA-IE-MPAN Test Scenarios And Test Cases - v0.2 - Clean.xlsx | All of them | All steps prior to steps in the block labelled 'IE MPAN Processing' | What purpose do these serve? Shouldn't we just be checking the delta between a standard unlinked MPAN and linked ones? | Reject | You make a valid point. However, in the interest of clarity, completeness and to avoid any confusion, these steps are included. | Complete
151 | IMServ | Ind. Agent | 2024-04-03 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2401-SIT-M-FM-CoA-Lapsed - v0.2 - Clean.xlsx | SIT-M-FM-COA-LAPSED Overview | Overview | The test description appears wrong - "Under this scenario a MHHS Qualified Supplier chooses to migrate Advanced HH Import/Export MPANs from Legacy NHH settlements to MHHS arrangements." should be "Under this scenario a MHHS Qualified Supplier chooses to migrate Advanced HH Import/Export MPANs from Legacy HH settlements to MHHS arrangements."? I guess this error may be repeated elsewhere | Accept | Import/Export MPANs does not apply to the Lapsed Appointment test. But, I get your point - Changes made. | Complete
152 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 20 | Based on the answer in item Ref 68, that the MA is out of scope - this also means that given this step is for the MA, that this step should also be removed to be out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
153 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 50 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
154 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 55 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
155 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 155 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
156 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 305 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
157 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoA - Unmetered.cleaned | SIT-M-FM-COA-UNMET-TC01 | 310 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
158 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COS-UNMET-TC01 | 41 | Based on the answer in item Ref 68 for CoA, that the MA is out of scope - this also means that given this step is for the MA, that this step should also be removed to be out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
159 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COS-UNMET-TC01 | 56 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
160 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COS-UNMET-TC01 | 58 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
161 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COS-UNMET-TC01 | 147 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
162 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COS-UNMET-TC01 | 335 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
163 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-FM-CoS - Unmetered.cleaned | SIT-M-FM-COS-UNMET-TC01 | 340 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
164 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 | 95 | Based on the answer in item Ref 68 for CoA, that the MA is out of scope - this also means that given this step is for the MA, that this step should also be removed to be out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
165 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 | 100 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
166 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 | 105 | Based on the answer in item Ref 68 for CoA, that the MA is out of scope - this also means that given this step is for the MA, that this step should also be removed to be out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
167 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 | 110 | The HHDC would be out of scope as a current world agent, so this step should be removed, in the same logic as the MA being out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
168 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 | 215 | Based on the answer in item Ref 68 for CoA, that the MA is out of scope - this also means that given this step is for the MA, that this step should also be removed to be out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
169 | IMServ | Ind. Agent | 2024-04-04 | RF | Theme 3 - Import/Export MPANs & Exception Handling | SIT-M-RM-CoS - Unmetered.cleaned | SIT-M-RM-COS-UNMET-TC01 | 225 | Based on the answer in item Ref 68 for CoA, that the MA is out of scope - this also means that given this step is for the MA, that this step should also be removed to be out of scope. | Reject | Although these steps are out of scope, they are included in the interest of clarity, completeness and to avoid confusion. | Complete
170 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC01 Trad | 230 | Test step references Smart MTDs, the test scenario is for Trad so not necassary | Accept | Changes made | Complete
171 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC02 ANHH | 305 | D0384 should be added to Interface ID column as per Key Validation and Test Evidence Column. D0384 is sent to Supplier as well as D0268. | Accept | Changes made | Complete
172 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC02 ANHH | 350 | Test step references Smart MTDs, the test scenario is for Advanced so not necassary | Accept | Changes made | Complete
173 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC02 ANHH | 375 | Trigger Sender is set to SMSI this is an Advanced scenario | Accept | Changes made | Complete
174 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC03 AHH | 215 | Step for Smart Data Service and Smart MTDs when test scenario is Advanced | Accept | Changes made | Complete
175 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC03 AHH | 260 | Typo in Interface ID column D0385 should be D0384 | Accept | Changes made | Complete
176 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC03 AHH | 265 | Test Evidence column - the DS does not receive the D0383 or D0384 so should not be asked to evidence receipt of this | Accept | Changes made | Complete
177 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC03 AHH | 345 | Test step references Smart MTDs, the test scenario is for Advanced so not necassary | Accept | Changes made | Complete
178 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC04 SNHH | 250 | As the scenario is Smart and MS receives MTDs from Reg Service the outgoing MOP is not required to send MTDs to new MS. Is this whole D0170 section obselete? | Reject | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent. | Complete | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent.
179 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC05 SHH | 240 | This step seems unecassary given the scenario is Smart and there is no requirement for outgoing MOP to send MTDs | Reject | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent. | Complete | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent.
180 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC05 SHH | 255 | As above | Reject | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent. | Complete | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent.
181 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC05 SHH | 310 | LDSO is won't receive MTDs from MS to need to reconcile | Reject | As this is a Smart Meter, there are no MTDs sent | Complete | Is this is smart then no MTDs are sent
182 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC05 SHH | 350 | As above | Reject | As this is a Smart Meter, there are no MTDs sent | Complete | Is this is smart then no MTDs are sent
183 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2403-SIT-M-FM-CoA - Correcting Incorrect FwdMig CoA Readings - v0.2 - Redlined.cleaned | SIT-M-FM-COA-CorrRead-TC05 SHH | 360 | As above | Reject | As this is a Smart Meter, there are no MTDs sent | Complete | Is this is smart then no MTDs are sent
184 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2404-SIT-M-FM-CoA - Rejected Appointment - v0.2 - Redlined.cleaned | SIT-M-FM-CoA-RejApt-TC01 All |  | The test only covers Smart scenario. Although the test steps are common across market segments the actors involved are not. | Accept | Script updated to highlight which MS/DS to use for which type of test. The SMSI/AMSI and the SDSI/ADSI are the only difference. The process remains the same. | Complete
185 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 220 | Test step refers to Smart MTDs the scenario is Trad | Accept | Changes made | Complete
186 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 230 | Test step refers to Smart MTDs the scenario is Trad | Accept | Changes made | Complete
187 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 310 | Test step refers to Smart MTDs the scenario is Trad | Accept | Changes made | Complete
188 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 325 | Test step refers to Smart MTDs the scenario is Trad | Accept | Changes made | Complete
189 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC01 Trad | 345 | Test step refers to Smart MTDs the scenario is Trad | Accept | Changes made | Complete
190 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 215 | Test step refers to Smart MTDs and Smart DS the scenario is Advanced | Accept | Changes made | Complete
191 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 225 | Test step refers to Smart MTDs and Smart DS the scenario is Advanced | Accept | Changes made | Complete
192 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 265 | Test Evidence column - the DS does not receive the D0383 or D0384 so should not be asked to evidence receipt of this | Accept | Changes made | Complete
193 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 280 | Test step states Traditional scenario is Advanced | Accept | Changes made | Complete
194 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 350 | Test step refers to Smart MTDs the scenario is Advanced | Accept | Changes made | Complete
195 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC02 ANHH | 375 | Trigger Sender is set to SMSI this is an Advanced scenario | Accept | Changes made | Complete
196 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC03 SNHH | 245 | Scenario is Smart so Outgoing MOP does not need to send MTDs | Reject | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent. | Complete | The Outgoing MOP still receives a D0170 - but for Smart there is no D0150/D0149's sent.
197 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC03 SNHH | 295 | Test step for Traditional scenario is Smart so not relevant | Accept | Changes made | Complete
198 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2397-SIT-M-FM-CoA - Missing Reads Deemed Reads - v0.2 - Redlined.cleaned | SIT-M-FM-COA-DeemRead-TC03 SNHH | 360 | Scenario is Smart so no D flow MTDs sent | Accept | Changes made | Complete
199 | IMServ | Ind. Agent | 2024-04-04 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2394-SIT-M-FM-CoA-MissMTD - v0.2 - Clean | All | All | No idea what this set of tests is doing at all, that is different to previous tests, where a site migrates and new DS and MS are appointed. There is no delta relating to missing MTDs (the name of the test set seems to be suggesting this is what the test is all about but nothing else supports this supposition) | Reject | Steps 286, 288, 296 and 298 are new steps relevant to this scenario. Text has been bolded to make this more apparent. | Complete
200 | IMServ | Ind. Agent | 2024-04-04 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2394-SIT-M-FM-CoA-MissMTD - v0.2 - Clean | SIT-M-FM-COA-MS-DS-TC02 AdvNHH | 290 | The only clue here is "For missing MTDs, check EES or IF-003 to validate that meters are installed on the MPAN." but no evidence is required so what are we testing here? Also the term MTDs is unclear, | Reject | Missing MTDs means the D0268/D0150 has not been sent (Trad or Adv) or no MTDs in REGs to send in the IF-036 for Smart | Complete | Missing MTDs means the D0268/D0150 has not been sent (Trad or Ad) or no MTDs in REGs to send in the IF-036 for Smart
201 | IMServ | Ind. Agent | 2024-04-04 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2388-SIT-M-FM-CoA-REL-MPAN Test Scenarios And Test Cases - v0.2 - Clean | SIT-M-FM-COA-REL-MPAN Overview | Overview | Scenario 3 is a site migrating from legacy HH arrangements? I suspect this is wrong across a number of test cases. | Reject | Please can we have more information on this. I'm unable to find this on the Overview tab. Scenario 3 says - "Under this scenario a MHHS Qualified Supplier chooses to migrate Advanced HH Import/Export MPANs from Legacy NHH settlements to MHHS arrangements. This test is specific to Prospective Appointments only as it covers all functionality." | Complete
202 | IMServ | Ind. Agent | 2024-04-04 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2388-SIT-M-FM-CoA-REL-MPAN Test Scenarios And Test Cases - v0.2 - Clean | SIT-M-FM-COA-REL-MPAN-TC3 AHH | 345 | Reference to Smart MTDs is incorrect, this is an Advanced scenario | Accept | Changes made | Complete
203 | IMServ | Ind. Agent | 2024-04-04 | IH | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2388-SIT-M-FM-CoA-REL-MPAN Test Scenarios And Test Cases - v0.2 - Clean | SIT-M-FM-COA-REL-MPAN-TC3 AHH | 380 | I would expect this step to include reference to terminating both MPANs | Accept | Changes made | Complete | What he is saying is that there are 2 MPANs in the relationship so he would expect a D0151 de-appointment to be sent for both.
204 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2405-SIT-M-FM-CoA-InvReq - v0.2 - Redlined.cleaned | SIT-M-FM-COA-InvReq-TC01 | 40 | The REGS will accept the 'Supplier Service Appointment Request' with Rejection response - should this be reject as per purpose of test? | Accept | Changes made | Complete
205 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2405-SIT-M-FM-CoA-InvReq - v0.2 - Redlined.cleaned | SIT-M-FM-COA-InvReq-TC01 | 55 | The REGS will accept the 'Supplier Service Appointment Request' with Rejection response - should this be reject as per purpose of test? | Accept | Changes made | Complete
206 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2411-SIT-M-FM-CoA-SameDate - v0.2 - Redlined.cleaned | All |  | What is the purpose of this Test Scenario? What "exception" is this trying to prove? It reads as though happy path scenario | Reject | Same date appointments do not wait in the queue to be processed daily. | Complete
207 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2412-SIT-M-FM-CoS-SameDate - v0.2 - Clean.cleaned | All |  | What is the purpose of this Test Scenario? What "exception" is this trying to prove? It reads as though happy path scenario | Reject | Same date appointments do not wait in the queue to be processed daily. | Complete
208 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2407-SIT-M-FM-CoS-InvReq - v0.2 - Clean.cleaned | SIT-M-FM-COS-InvReq-TC01 | 45 | The REGS will accept the 'Supplier Service Appointment Request' with Rejection response - should this be reject as per purpose of test? | Accept | Changes made | Complete
209 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2407-SIT-M-FM-CoS-InvReq - v0.2 - Clean.cleaned | SIT-M-FM-COS-InvReq-TC01 | 20 | Test is to prove handling of invalid request but test step requires Supplier to send "the correct appointment details" | Accept | I assume that you mean "BP Step" instead of "Test Step" here. You've referred "Test Step" everywhere else. Changes made based on above assumption. | Complete
210 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2406-SIT-M-FM-CoS - Rejected Appointment - v0.2 - Clean.cleaned | SIT-M-FM-COS-RejApt-TC01 | 195 | Step is for MS but description states Data Service | Accept | Changes made | Complete
211 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2406-SIT-M-FM-CoS - Rejected Appointment - v0.2 - Clean.cleaned | SIT-M-FM-COS-RejApt-TC01 | 205 | Step talks about managing accepted responses, this test is for rejection | Accept | Changes made | Complete
212 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2396-SIT-M-RM-CoS-MissMTD - v0.2 - Clean.cleaned | SIT-M-RM-COS-MissMTD-TC01 TRAD | 140-150 | Terminology here, when talking about Incoming MOP (legacy) "Metering Service" is used in these steps - for clarity and consistency should Incoming MOP be used? | Accept | Changes made | Complete
213 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2396-SIT-M-RM-CoS-MissMTD - v0.2 - Clean.cleaned | All |  | This scenario is meant to be testing missing MTDs, but the steps don't actually cover where MTDs are missing. The MTDs seem to be sent and received as they would in happy path? | Reject | New steps have been added to the tests - I have set these steps in BOLD + RED font to showcase them for you. | Complete
214 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2396-SIT-M-RM-CoS-MissMTD - v0.2 - Clean.cleaned | SIT-M-RM-COS-MissMTD-TC02 ADV | 265 | Advanced Scenario with reference to D0150/D0149 - should be D0268 | Reject | The BPM/BPD design documents say D0149/D0150 | Complete
215 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2396-SIT-M-RM-CoS-MissMTD - v0.2 - Clean.cleaned | SIT-M-RM-COS-MissMTD-DS-TC03 SM | 245 | Refernce to Smart Metering Service when actually talking about legacy Incoming MOP | Reject | The BPM/BPD design documents say D0149/D0150 | Complete
216 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 | 135 | Recipient is MS - should be Incoming MOP | Accept | Changes made | Complete
217 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 | 140 | Recipient is MS - should be Incoming DC | Accept | Changes made | Complete
218 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 | 135 | As these steps are crticial to what the test scenario is trying to prove why is there no test evidence required? | Reject | The Incoming MOP is out of scope for verification. | Complete
219 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 | 140 | As these steps are crticial to what the test scenario is trying to prove why is there no test evidence required? | Reject | The Incoming DC is out of scope for verification. | Complete
220 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 | 145 | As these steps are crticial to what the test scenario is trying to prove why is there no test evidence required? | Accept | Changes made | Complete
221 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 | 150 | As these steps are crticial to what the test scenario is trying to prove why is there no test evidence required? | Accept | Changes made | Complete
222 | IMServ | Ind. Agent | 2024-04-04 | SG | Theme 3 - Import/Export MPANs & Exception Handling | MHHS-DEL2400-SIT-M-RM-CoS-CancAppt - v0.2 - Clean.cleaned | SIT-M-RM-COS-CANCAPPT-TC01 |  | No mention of Metering Service or Data Service in these tests steps? Is the test assuming they haven't been de-appointed and are therefore unaware of the failed attempt to reverse migrate? | Accept | Changes made | Complete | The CSS would send a cancellation message which would stop the Switch from occurring - so an IF-003 wouldn’t be sent because the IF-003 is only sent when a switch becomes secured. The normal CSS to REGS message flow is 1) Pending Switch then 2) Secured Switch. For a cancellation the flow is 1) Pending Switch then 2) Cancelled Switch
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347

## Sheet2 (hidden)
Theme
Theme 1 - Forward Migration - CoA & CoS
Theme 2 - Reverse Migration - CoS
Theme 3 - Import/Export MPANs & Exception Handling