## Sheet1
Organisation: | Various |  | MHHS-DEL2506 Consolidated Comments Log (This Artefact)
Constituency: | Various
Date: | 2024-04-19 |  | Comments on artefact 'MHHS-DEL2127 SIT Non-Functional Test Approach & Plan v0.4'
Anonymised: | Where requested
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete |  |  |  | Programme to complete once consultation window has closed.
Ref | Reviewer | Page | Section | Comment | Accept/Reject or Action | Response | Status
1 | C&C Group | 8 | Dependencies | We are puzzled by the references to reusing parties PIT message injection tools. Where systems are priimarily inbound from the DIP then it's difficult to understand how our message injection tools will be of any value. We do note however that reference is made to having bi-laterals with individual parties so will wait until those discussions. This is also referred to again on Page 13. | Accept | while C&C group will not be generating inbound messages to the DIP, the business processes themselves need a start point within the integrated environment, will re-word this section. This is also mentioned withon section 6.2 | Drafted
2 | C&C Group | 9/10 | In Scope | The in scope table refers to Network Operations and UMSO as being in scope for NFT, reference is made later in the table to MPRS only having 2 representative LDSOs in SIT, this restriction also applies to both of these role codes. This is further complicated that the systems are not common between the 2 parties for Network Operations. | Accept | re-worked final section to highlight the limitation in available PPs for this area | Drafted
3 | C&C Group | 10 | Test Types | Security - For the LDSO/REGS/UMSO role codes all security requirements described are delivered via the adaptor solution not the cleint apps, yet the adaptor is not mentioned as being in scope of testing | Accept | As this is SIT, the use of adapters where these are planned to be used in produciton was assumed, updated section 6.2 to additionally mention the use of DIP Adapters | Drafted
4 | C&C Group |  | General | The document makes no reference to Adaptors, yet a number (majority) of the NFR for business applications will be met by the Adaptor, in addition, for LDSOs all role codes are exempt (in effect) from NFR E2E1009 which is a key performancce metric that is met (in part) by the Adaptor. Can the document include guidance on what tests will be regarded as being met by the adaptor and which ones will be applicable to the business application. | Accept | We're aware of the CR for exemptions from NFR E2E1009 and have taken that into our assurance criteria. Re Adapter use, if these are being hosted by the PP then their activity, under load, error etc falls within the remit of the PP themselves. This is stated in both the NFT Policy and PIT guidance documents, with additional wording within section 6.2, Environment requirements within this document now | Closed
5 | Utilita | 3 | References | In the references table 4 documents are not available. 12 documents have newer versions available and 1 document is duplicated. | Accept | All document references have been updated | Closed
6 | Utilita | All Document | References | Throughout the document there are 18 cases where the Referenced document in the text does not match the referenced document in the table. | Accept | All document references have been updated | Closed
7 | Utilita | 6 | Figure 1 | The referenced documents in Tier one do not match the referenced documents table. | Accept | will update, however all other references are now in place | Open
8 | Utilita | 9 | Objectives | "objectives, and approach to both SIT Non-Functional testing, given the approach laid out within section 0." Section 0 gives no indication what the referenced section is. Occurs at other parts of the document too. | Accept | document updated to show links properly | Drafted
9 | Utilita | 10 | Scope | 2 Instances of "Error! Reference source not found." | Accept | refernces updates | Closed
10 | Utilita | 12 | Figure 2 | The second MSS box in the diagram should be MSA. | Accept | Updated | Closed
11 | Utilita | 18 | 1.1.1.3 | Reference to section 7.2 (with no link) Sections aren't numbered so no idea where this reference is for. | Accept | Updated reference | Closed | Kevin
12 | Utilita | 22 | Figure 3 | Does not show an ADO Defect Process Flow. | Accept | Figure updated and moved | Closed | Kevin
13 | Utilita | 25 | Figure 5 | SIT NFT Phases not visible | Accept | Figure updated and moved | Closed | Kevin
14 | Utilita | 25 | Preparation Schedule | "SIT Non-Functional readiness dates that all PP’s will be required to meet ahead of test execution commencement can be found below." There are no dates listed. | Accept | Figure updated and moved | Closed
15 | Utilita | 18 | 1.1.1.3 | Reference to section 7.2 (with no link) Sections aren't numbered so no idea where this reference is for. | Accept | Updated reference | Closed
16 | Utilita | 22 | Figure 3 | Does not show an ADO Defect Process Flow. | Accept | Figure updated and moved | Closed
17 | Utilita | 25 | Figure 5 | SIT NFT Phases not visible | Accept | Figure updated and moved | Closed
18 | Utilita | 25 | Preparation Schedule | "SIT Non-Functional readiness dates that all PP’s will be required to meet ahead of test execution commencement can be found below." There are no dates listed. | Accept | Figure updated and moved | Closed
19 | Utilita | 4 | References - REF-15 | "MHHS E2E003 - End-to-End Solution Architecture - Transaction Volumes" Referred document not found on MHHS SharePoint | Accept | We will check with document owners, this was release under Interim Release 5 SIT. Potentially can be released with NFTWG minutes | Open
20 | Utilita | 11 | In Scope Migration/Operational | SIT Migration is referred to be performed in SIT-B. This testing has been moved to SIT-A. Please confirm Also this section referes to a link which is having a reference error | Reject | Migration Testing in SIT-A is purely to exercise the functional areas of migration. Testing, at volume would need to be carried out during PP PIT phase, with interfaces to be targeted during NFT | Closed
21 | NAT Grid ESO | 12 | Figure 2 | Figure 2 refers to the TOM. The colour scheme of the data flows don't correspond to the colour scheme in the legend. A small point but you might want to tidy this up so they are consistent. | Accept | Diagram updated with new key | Closed
22 | DCC | 11 |  | As DCC is not a participant in NFT, and CSS does not have an instance in SIT-B, there is no true E2E testing which can be achieved in SIT-B. We therefore assume that CSS will be stubbed. | Accept | CSS has a data workaround that the programme are currently looking at with a view for using during SIT NFT | Closed
23 | SPEN | 11 | In Scope | Operational SLA's / Performance efficiency - broken link or reference is not found at end of this paragragh | Accept | document formatting has been fixed to resolve this | Closed
24 | SPEN | 11 | In Scope | Migration/Operational Choreography - broken link or reference is not found at end of this paragraph | Accept | document formatting has been fixed to resolve this | Closed
25 | Imserv | 10 | Scope | The comment 'Electralink (DTN) – no test environment for DTN exists, this area will be stubbed if/where required.' is of concern, could more detail be provided to re-assurance PPs that testing with 'stubs' provides such assurance? There will be a significant number of flows being exchanged via the DTN during Migration | Accept
26 | Imserv | 10 | Scope | Broken link here - 'Scale and scope of environments that are recommended to be utilised in this phase for NFT can be found within section Error! Reference source not found' and 'To mitigate these factors, the MHHS NFT team believes that carrying out the scheduled processing as defined within both the migration and operational choreography documents referenced within section Error! Reference source not found.' | Accept | formatting issues fixed | Drafted
27 | Imserv | 8 | assumptions | Define 'scaled PIT environment' - 10%, 50%? | Accept | This bullet is for SIT Phase 1 only, DIP & Helix. Minimum expected scaling for other phases of SIT are defined in section 6.2, Env requirements | Closed
28 | Imserv | 13 | MHHS environment requirements | Couple of the paragraphs talk about reusing Participants test harnesses that will be used in NFT PIT - but this cycle of testing will be connected to the avanade DIP? Isn't the whole point to test using the real DIP? | Reject | The test harnesses statement is for SIT Phase 1, where only central parties and DIP will be involved in execution | Closed
29 | Imserv | 15 | Phase 2 NFT SIT | 'suitably scaled volume' - where is this defined? | Accept | This will be defined within the SIT NFT Test scemarios as we have more of an understanding of the SIT-B limitations in terms of test cases and test data design
30 | Imserv | 17 | test toolsets | There are no requirements what such test toolsets should be capable of. Will the programme detail what their expectations are? At NFTWG 19/03/24 it was mentioned the programme was looking into testing toolsets - any further information available on this? | Accept | The testing toolsets that were mentioned during the NFTWG were related to PIT, w will continue to look into these, but as mentioned during the previous WG, we should mpve forward on the assumption that given the current timescales, that these will not be available. As for SIT, given the lack of DCC, there is at least the requirement for a method of injecting IF021's. To avoid manual working, this may also be the case for starting points of other messages, this will be worked further through our Test Scenario's as we collate more detail. | Closed
31 | RECCo | 5 | Executive Summary | Three stages of delivery are referenced here, however the rest of the document splits NFT into two stages. | Accept | End to End Performance stage will consist of the lifecycle processing and E2E as listed in table 1 | Closed
32 | RECCo | 10 | Scope | The section on the DCC (CSS) could be clearer. The DCC will not be able to provide a CSS instance for SIT B, so any NFT tests requiring CSS would need to be carried out in SIT A. As such my understanding is that CSS is out of scope for SIT NFT. | Accept | Correct, there is no CSS instance for SIT-B, this will be looked into in more detail re test types available during the creation of the NFT Test Scenarios and Cases | Open (tbd via Test Scenario plans)
33 | RECCo | 10 | Scope | Although Electralink is not able to provide a test environment for the DTS, test flagged flows could be used. (This approach could be required in SIT B for the Settlement element of SIT Functional) | Accept | Correct, there is no DTS instance for SIT-B, this will be looked into in more detail re test types available during the creation of the NFT Test Scenarios and Cases | Open (tbd via Test Scenario plans)
34 | RECCo | 10 | Scope | Multiple broken links 'Error! Reference Source not found' should be resolved. | Accept | document formatting issues has been fixed | Drafted
35 | RECCo | 12 | MHHS Architecture and Coverage | References to 'Section 0' look incorrect | Accept | document formatting issues has been fixed | Drafted
36 | RECCo | 13 | MHHS Environment Requirements | There's a reference to stubbing EES for the IF-021 (Consumption Data Processing). Unsure what this refers to as EES would not send or receive the IF-21. Is this for the IF-040 'Annual Consumption' interface from MDS to EES? | Accept | document amended to cover the available synthetic data plan | Drafted
37 | Helix | 13 | MHHS Environment Requirements | Context from Document : With the bulk of performance testing, at volume being carried out during the PIT NFT Phase, we would still expect there to be a suitable level of messaging concurrency utilised to provide a level of assurance to solutions during the NFT SIT tests defined within section 0 Given the lack of current knowledge of all Participants expected SIT-B environment scales (this will be determined via bi-laterals with all involved parties on the release of this document), the MHHS SI is proposing that, as a minimum, they should be scaled to 25% of the size of environment that would be expected to be implemented into production. Review comment from Nigel : Perf Testing with configuration is significantly different to production may yield unrelaible results. Assumption here is 25% is minimum as we will run production like configuration in SITB. | Accept | For SIT (Theme1) we will be setting up bi-latarals between the programme, DIP and Helix teams as a means to ensure that any tests for this part of delivery, add some form of benefit to the programme. | Open
38 | Helix | 5 | Executive Summary | Executive Summary : Page 5 of 32 Infrastructure Focused NFT, Bullet Point 3 Query : BP3 - MHHS to do these tests with DIP? Get more clarification and more specific about. Unclear about R&R. | Accept | Amended text to point to DIP side interface testing | Drafted
39 | Helix | N/A | Test Data | Generic question : Responsibility on Helix WRT Test Data Generation. More clarity would be helpful. SITB: How can we get this ready in terms of Data Generation, Data alignment and Data being cleansed after test runs are complete? We need Test Data Plan for this activity. Owner – MHHS? Who will run this task of following up with MHHS. Needs to be called out in our LOG back to MHHS | Accept | The test data requirements will become more apparent as the NFT team work through the Test Scenarios and cases. We have 3-4 options available to us as per the SIT NFT Test Data Approach document. As this is SIT, the programme will take ownership of this | Open
40 | Helix | 8 | Assumptions and Dependencies | Need more detailed inputs specific to NFR’s are required from MHHS. BP 3: How is this overlap being addressed? In terms of SITB availability. BP4: Who is going to take ownership for Data provision and helping out if there are issues? MHHS? Would this be same for NFT so that MHHS owns this action? Failure Scenarios: What are the scenarios and How are we going to add them? Based on this outcome, we are required to prepare/ask for Test Data Ask MHHS: Tools, Stubs: What is the plan from MHHS and how the connections will be established if needed. Need more clarification from MHHS. Current SIT tools for Data Consumption: Is MHHS expecting same process to be followed in SIT NFT Industry testing on SITB. | Accept | These are more aligned with monitorring solution in place on system, some have specific NFRs, others taken at best practive levels Both teams will work together to ensure no duplication of tests for the same areas MHHS Programme will take ownership of data provision as in SIT-A The bulk of the interface scenarios will be expected to be covered in PIT, an additional level of assurance is being added to SIT NFT to ensure successful processing of messages E2E post interfaces being back on-line In terms of Theme 1, this will be discussed, rest of SIT should act as production would | Open
41 | Helix | 10 | Migration/Operational Choreography | WP2 - Please clarify if it will be a similar test data creation process as per HXT1 Performance Testing? | Accept | MHHS Programme will create the synced test data for this stage of testing | Closed
42 | Helix | 10 |  | Operational SLAs/ Performance efficiency – Need more clarification around SLA's. More detailed and transparent view. Paragrapgh for reference : Operational SLAs/ Performance efficiency – Taking each Central Party and Programme Participants systems as individual components within MHHS infrastructure, scaled volume, integrated, testing to be carried out as a means of ensuring areas not under test during PIT, namely E2E interfaces and the transfer of data between them, are not detrimentally affected. Scale and scope of environments that are recommended to be utilised in this phase for NFT can be found within section Error! Reference source not found. | Reject | SLA's for processing under volume/performance testing are already known. As this would have been covered during PIT testing at 'volume' we are not expecting full loads to take place during SIT, simply assuring the effect of the physical interfaces on E2E processing | Closed
43 | Helix | 10 | Reliability/Recoverability | Reliability/Recoverability. Infrastructure and test designs for WP1, WP3 and WP4. WP2 is not storing anything and we are storing configuration on the Operator Portal and WP1/DAH, so no testing is required. Is this correct? | Accept | MHHS NFT would need to see the solution designs for this area to confirm | Open
44 | Helix | 10 | Operational SLAs/ Performance efficiency | Operational SLAs/ Performance efficiency. This Non-Functional is still ongoing, should we get it ready for 9-6 release, as that is earmarked for MHHS Cycle2. https://elxnfa.visualstudio.com/The%20Helix%20Programme/_workitems/edit/124449 Please can we clarify if there any SLAs needed to be met by WP2? | Accept | As far as MHHS NFT are aware, there are no changes to delivery plans | Closed
45 | Helix | 25 | Test Schedule | Page 25 of 32 : Can this be checked and updated by MHHS Please? | Accept | These will be further defined as MHHS NFT go through Test Scenario, Case and Data planning, also now taking into consideration Settlements testing being moved onto SIT-B | Open
46 | Callisto |  | General | Why does this document have no section numbering? There are attempts to cross reference to sections, but that doesn't work if there are no numbers? (e.g. page 12 refers to section 0?). There are some random paragraphs with reference numbers | Accept | Document formatting has been foxed | Closed
47 | Callisto | 12 | Can't say - see previous comment | Not sure why this version of the TOM has been used in the document, this is the one taken from the architecture tool in 2022 and is missing the DCC component and has added PAT in front of all the other functions. (not that I am biased as the creator of the Patrick!) | Accept | Hi Simon! The TOM has been used on all docs, so to keep with the delivery format has been sligtly alterred to suite NFT | Drafted
48 | Callisto | 22 | Figure 3 | Is missing | Accept | Document formatting has been foxed | Closed
49 | Callisto | 25 | ? | There seems to be a spurious document element before the final sentence/paragraph, has something been edited or cropped? | Accept | Document formatting has been foxed | Closed
50 | Callisto | 31 | Figure 6 | Appears to be incomplete | Accept | Document formatting has been foxed | Closed
51 | UKPN | 3 | References | REF-03 MHHS-DEL852 - Pre-Integration Test Guidance link points to the older version of PIT guidance published in August 2023 while the latest version was published end of march 2024 | Accept | References updated, there will be a new version containing Qualification and NFT updates shortly | Close
52 | UKPN | 12 | MHHS Architecture and coverage | Mention references to volume of IF-021 to be processed | Accept | Volumes will be defined alongside NFT Test Scenarios and Test Cases | Close
53 | UKPN | 13 | MHHS Environment Requirements | "the current assumption is that Smart and Traditional meter IF-021 injection will be simulated, using existing injection methods, utilised during DIP PIT to simulate SDS messaging. Registration Services, Suppliers, LDSO and EES systems will be stubbed for this phase of testing as the main focus for processing are the new systems being implemented as part of the MHHS Programme", does this mean the registration services will not be non-functionally tested for inbound IF-021 in phase 1? | Accept | Only DIP and Helix is to be exercised during the initial phase of NFT, we would also expect that NFT at voume, will be carried out by all parties during PIT. Later phases of NFT SIT will focus on scaled volume (limited by synced data) processing and interface failures | Close
54 | UKPN | 17 | Test Toolsets | Define the tentative timelines by when the peformance testing tools and test harnesses/stubs will be agreed | Accept | This will be defined in detail as the programme create the NFT Scenarios and Test Cases | Close
55 | British Gas | ALL | ALL | Please include numbered sections to help referencing. These only start at p17 in the current document under review. | Accept | Document formatting has been foxed | Closed
56 | British Gas | 4 | Executive Summary | "This document has been developed in unison.." - unison is the wrong word as it applies to singing or speach - suggest in parallel or simultaneously | Accept | wording updated | Closed
57 | British Gas | 4 | Executive Summary | via bi-lateral meetings - typo - should be "via bilateral meetings" Also p8 Dependencies - "A series of bi-lateral meetings" -> A series of bilateral meetings Also p12 - MHHS Environment Requirements - "this will be determined via bi-laterals with all involved parties" P17 - "The SI will hold a series of bi-lateral meetings" | Accept | wording corrected | Closed
58 | British Gas | 8 | Change Forecast | "are to be issued and reviewed in conjunction with each other," - word redundancy - "are to be issued and reviewed in conjunction," | Accept | wording corrected | Closed
59 | British Gas | 8 | Change Forecast | All updates to this document will follow the review and approval process outlined in section 3.2. -> section numbers are not shown in this document - see first point above | Accept | Document formatting has been foxed | Closed
60 | British Gas | 10 | Scope | Operational SLAs/ Performance efficiency section has a bad internal document reference "Error! Reference source not found" | Accept | Document formatting has been foxed | Closed
61 | British Gas | 10 | Scope | Security – NFR’s - no apostrophe required - Security – NFRs | Accept | wording corrected | Closed
62 | British Gas | 10 | Scope | Migration/Operational Choreography section has a bad internal document reference "Error! Reference source not found" | Accept | Document formatting has been foxed | Closed
63 | British Gas | 12 | MHHS Architecture and Coverage | There are 3 references here to section 0 - what is this? (i.e. "where all roles listed within section 0", & "Details of message injection and stubbed/harnessed areas to be used during this test run are detailed within section 0" & "Tests that are planned to be carried out are summarised within section 0.") | Accept | Document formatting has been foxed | Closed
64 | British Gas | 14 | Phase 1 NFT SIT | Spelling - focussing on the message journey for processing within the MHHS TOM. -> "focusing" | Accept | wording corrected | Closed
65 | British Gas | 14 | Test Approach | No mention is made of the DIP reports in this document - e.g external reports MHHS-REP-002-009 - given that CR030 has flagged that these reports are large enough to require zipping why is isn't this being covered. The internal and external reports are critical to settlement and statutory reporting - failing to consider these carries considerable risk. | Accept | We are currently defining the NFR Scenarios, analysis of this area will be carried out to determine scope within the SIT environment, given data limitations for the later phases of SIT, we would ideally want these to be included within PIT delivery, & potentially as part of NFT SIT Theme 1 dependant on start/end point analysis | Open
66 | British Gas | 17 | 1.1.1.2 | "Participant’s adopting the Placing Reliance Policy" - Participant’s - apostrophe not required | Accept | wording corrected | Closed
67 | British Gas | 18 | 1.1.1.3 Participant SIT NFT Test Readiness Report | must be signed by senior stakeholders within the participants’ organisation. - apostrophe in the wrong place - "must be signed by senior stakeholders within the participant's organisation." | Accept | wording corrected | Closed
68 | British Gas | 19 | SI Test Readiness Report | This report will form the basis on which governance approval to commence SIT Non-Functional Test execution will be sought via the MHHS Governance Framework –please see section 10.1. -> section numbers are not shown in this document - see first point above | Accept | Document formatting has been foxed | Closed
69 | British Gas | 19 | Test Execution | Test Execution - "to ensure the test can be run in an end-to-end manner." - > "to ensure the test can be run end-to-end." (grammar) | Accept | wording corrected | Closed
70 | British Gas | 21 | Test Evidence Capture | Programme participants’ own quality gate -> apostrophe in the wrong position -> Programme participant’s own quality gate | Accept | wording corrected | Closed
71 | British Gas | 22 | Defect Management | Figure 3 - ADO Defect Process Flow - process flow is not visible | Accept | Document formatting has been foxed | Closed
72 | British Gas | 24 | SI Non-Functional Test Completion Report | This report will form the basis on which governance approval of the completion of the SIT Non-Functional Test stage for both the ‘MVC’ and ‘Other SIT PP’ cohorts will be sought via the MHHS Programme Governance Framework – please see section 10.1. . -> section numbers are not shown in this document - see first point above | Accept | Document formatting has been foxed | Closed
73 | British Gas | 25 | SIT Non-Functional Test | Figure 5 - SIT NFT Phases - diagram is not visible | Accept | Document formatting has been foxed | Closed
74 | British Gas | 26 | Test Management & Organisation | "The resources below is a guideline to the types of resource" - poor grammar/ word repetition -> suggest -> The table below is a guideline to the types of resource | Accept | wording corrected | Closed
75 | British Gas | 31 | Reporting | Figure 6 - ADO Dashboards - screenshot only partially visible | Accept | Document formatting has been foxed | Closed
76 | British Gas | 4 | Reference | PIT Guidance V 2.1 is the latest available document and was published on 18th Aug 2023. No new version of PIT Guidance have been published yet and the link in the document is also pointing to V2.1 | Accepted | The latest version of PIT Guidance is to be issued shortly, containing updates for NFT & Qualification. A road map for this is in progress | Closed
77 | British Gas | 11 | Out of Scope | The document is refering to PIT Guidance V 2.1 which doesn’t have PIT guidance for NFT in detail | Accepted | The latest version of PIT Guidance is to be issued shortly, containing updates for NFT & Qualification. A road map for this is in progress | Closed
78 | British Gas | 19 | Test Entry Criteria | The document is refering to PIT Guidance V 2.1 which doesn’t have PIT guidance for NFT in detail | Accepted | The latest version of PIT Guidance is to be issued shortly, containing updates for NFT & Qualification. A road map for this is in progress | Closed
79 | RECCo | 10 | 5.1 | There is no RECCo test instance of the DTN. (The DTN is run by Electralink and is not a REC Service). As per the NFT Data A&P I would expect production instance of the DTS to be used with different test flags used to identify test flows. This is the same approach as being used in SIT Functional and SIT Migration. | Action | wording around DTN updated | Drafted
80 | RECCo | 10 | 5.1 | Both the Registration Service and MPRS are listed as being in scope. This is a duplication as both names apply to the same service. | Action | have moved all roles into the same bullet | Drafted
81 | RECCo | 10 | 5.1 | There are still a number of broken links in the document 'Error! Reference Source not found.' | Action | Document formatting has been resolved | Drafted
82 | RECCo | 13 | 6.2 | Does the new text added stating that where DIP Adaptors are utilised, these will form the end points of their segment is SIT B, mean that volume testing etc. will be only be undertaken in the adaptors? From a qualification point of view we would expect to assure that individial parties systems were able to process the required volumes and not just the adaptor. | Action | Have amended statement to class adapters as boundary points for messages, but to include message creation or processing as evidence | Drafted
83 | UKPN |  |  | Hi, The documents have been reviewed and as UK Power Networks’ previous comments have been accepted and addressed and/ or clarified, we have nothing further to add. Regards, Steve Musiol Risk & Governance Manager, Income Management, UK Power Networks Mobile: 07875 113016 Upcoming Annual Leave: 26-29 Apr, 10 May & 31 May-3 Jun. All days are inclusive
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117