## Consolidated
MHHS-DEL2676 - SIT Operational Test Cases and Test Scenarios Theme 1 Comments Log
| Reviewer to Complete | [9 empty] | Programme to complete once consultation window has closed.
Reference # | Reviewer | Organisation | Constituency | Date | Theme | Testcase | Requirements on MPRS/LDSO | Comment | *Suggested Change | *Impact of not making the Change | Action (Accep/Reject) | Response | Comment Status (Complete/Pending)
SITOPS _BR02 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | No LDSO test case for IF-007. | LDSO case to be added. | LDSO not testing energisation status changes. |  | We have included LDSO in TC08 as recipient of PUB-008. LDSO are not the senders or recipient for IF-007 | Completed
SITOPS _BR02 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | IF-018 to MS and IF-007 to MPRS have been tested in SIT Functional, I'm not sure what additonal value these test cases provide. | Review if these test cases are required | Repetition of tests. |  | The purpose of this scenario is to show that records are updated with data received via Interfaces against the respective requirements. Although these interfaces have been sent/received during SIT Functional the focus here is about maintaining and updating records with the data received | Completed
SITOPS _BR03 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | This scenario references the update of customer contact details via the IF-018. This is incorrect, the customer contact details are shared via the D0302. | Update test case to reference the D0302 for updating customer contact details. | Test case is incorrect |  | Amended Test Case in v0.2 to replace IF-018 with D0302 DTN Flow. | Completed
SITOPS_BR08 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | These test cases detail the supplier driven fault process used for trad and smart meters. The Advanced process, where an ADS would raise the D0001 to the MSA should also be included. | Add Advanced fault resolution process steps. | Full service coverage not present |  | MHHS-BR-DS-147 requirement & related tests for ADS added. | Completed
SITOPS_BR11 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | Steps 160 and 170 in both test cases are duplicates | We would propose removing step 160 | Duplicate steps present |  | Step 160 has been removed. | Completed
SITOPS_BR11 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | We're unsure how this scenario, which truncates the COA process is possible in practice. i.e. how will the RS trigger the IF-035 without the preceeding messages | Review scenario for feasability. | Scenario is unable to be completed |  | Preceeding steps added to get to the state of sending IF-035. | Completed
SITOPS_BR12 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | This scenario includes a single test case for a MS and DS. Test cases for all MS and DS types are required (Smart, Advanced and UMS) | Add required test cases | Parties not covered will not be able to test these requirements for qualification purposes. |  | Added Test Cases in v0.2 for full coverage of all relevant roles. Split DS and MS to ADS, SDS, UMSDS, MSS, MSA and UMSO | Completed
SITOPS_BR12 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | MS test case references investigating IF-006s not being received within the defined SLA, but does not describe how a party would do this. (The same applies to other test cases referencing the investigation of missing flows) | Update test case to describe the activity being undertaken. | Test requirement is unclear |  | Amended Test Case in v0.2 to include additional detail. The investigation steps are not the subject of the test, the test is looking to validate that monitoring is in place to identify where expected responses are not received. We have a step for investigation under Service Mngt but the intent is not to test the SM steps and assume the fix has been made | Completed
SITOPS_BR12 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | Supplier test case covers the IF031 being sent and IF032 not received within the SLA. Same question as above. What should they do to query the late response and is that a different query to one they would raise if they issue a consumption amendment request to the data service and do not receive a response? | Update test case to describe the activity being undertaken. | Test requirement is unclear |  | Amended Test Case in v0.2 to include additional detail. The investigation steps are not the subject of the test, the test is looking to validate that monitoring is in place to identify where expected responses are not received. We have a step for investigation under Service Mngt but the intent is not to test the SM steps and assume the fix has been made | Completed
SITOPS_BR12 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | The LDSO test case seems odd. It references the IF-020 and IF-021. These interfaces are not connected | Review test case. It potentially needs split into two seperate IF-020 and IF-021 test cases | Test case does not appear to make logical sense. |  | We have removed steps for IF-021 . The test is now looking for LDSO monitoring against PUB-020 | Completed
SITOPS_BR16 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | An LDSO test case is required here. | Add LDSO test case. | LDSO not testing DIP Errors |  | Updated in v0.2 to Include new TC05 for LDSO | Completed
SITOPS_BR16 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | It looks like this test case covers a sample of validation errors. Can this be confirmed? If this is the case what's the rationale for not testing each type of DIP error? | Provide clarity. |  |  | Lower level testing expected to have full coverage to test all validation errors. The scope for Operational Testing is a sample of these validation errors for L1-L4.
SITOPS_BR20 & BR21 | Jonny Moore | RECCo | Code Body / Central Party | 2024-06-04 | Theme 1 |  |  | These test cases appear odd. The IF-20 and IF-019 are out of order and the IF-021 and IF-013 have no relevance to the IF019/IF020 process. It could be that multiple test cases are required. | Review test case. Create multiple test cases if required. | Test case does not appear to make logical sense. |  | Test Case updated to relect IF-019 / IF-020 which satisfies both sending and receiving of messages. Other PUB steps removed | Completed
MHHS-DEL2622 SITOPS_BR12 | Chris Wood | CGI |  |  | Theme 1 |  |  | When transacting via the DIP - Presumably, this means when using the DIP to send messages? | Use plain English to better explain | Minimal, but causes confusion in understanding |  | Amended in v0.2 from transacting to sending/receiving messages/events, have left as transacting in Overview Requirement mapping cell to reflect the req desription | Completed
MHHS-DEL2634 SITOPS_BR23 | Riccardo Lampini Nigel | CGI |  |  | Theme 1 |  |  | it is not clear in the cases who is supposed to raise requests, and by which mean and exactly what may be asked for. In general, how is this different to MHHS-DEL2638 SIT_OPS_BR25 | defer scenario | test a workaround, not enduring solution. waste effort |  | Amended test case in v0.2 to include MDS as the requester and the method used to send the LSS Data to MDS. BR23 is related to a single adhoc request whereas BR25 is about Load shape data being available publicly. | Completed
MHHS-DEL2638 SIT_OPS_BR25 | Riccardo Lampini | CGI |  |  | Theme 1 |  |  | Currently in discussion with MHHS Design to understand criticality of this requirement | defer scenario | test a workaround, not enduring solution. waste effort |  | On hold | Pending
MHHS-DEL2624 SITOPS_BR01_Investigate and Resolve Issues | Participant #1 | Participant #1 |  |  |  | TC01, TC02. TC03 | LDSO to receive PUB-021, no further actions required | These 3 test cases only require us to receive a PUB message in each case with no further actions required. In the interests of efficiency during test and the testing of the actual test case, does it make sense to require the LDSO to capture evidence that it has received the file when this is not the process/item under test and will have been already covered under Functional Testing previously? In the scenario TC03 - should the UMSDS send the IF-021 to the UMSO |  |  |  | Changes made to TC01,02,03 v0.1 LDSO not required to provide evidence. TC03 - UMSO is not a recipient for PUB-021 (no update to TCs made for this part of the feedback). | Completed
MHHS-DEL2165 SIT_OPS_BR02 Manage Data on Receipt of Interfaces | Participant #1 | Participant #1 |  |  |  | TC04, | TC04 MPRS sends PUB-018 to DIP/UMSO, MPRS sends PUB-018 to DIP/MSS, TC05 MPRS send PUB-018 to DIP/MSA, TC08 MSS/DIP sends IF-007 to MPRS | This is an automated flow so are there proceeding steps to step 1 or will we be expected to create and send a file? I'm unclear on what our requirements are as an LDSO or UMSO to produce the file. |  |  |  | Test cases amended v0.2 to include proceedings steps for clarity. | Completed
MHHS-DEL2616 SIT_OPS_BR03 Manage Previous Customer Details | Participant #1 | Participant #1 |  |  |  | TC01-TC04 | MPRS to send PUB-18 | An IF-018 is an automatically triggered flow but there are no proceeding steps to indicate what is triggering the flow to be sent out? |  |  |  | Changes made to TC01,02,03,04 in v0.1 to include the proceeding steps to indicate what is triggering the flow to be sent out. | Completed
MHHS-DEL2619 SITOPS_BR04 Delete any Active DSP Schedules | Participant #1 | Participant #1 |  |  |  | TC01 | MPRS sends IF-037 | Again, this is a triggered flow so are there proceeding steps to step 1 or will we be expected to create and send a file? I'm unclear on what our requirements are as an LDSO to produce the file. |  |  |  | TC01 updated v0.2 to include all proceeding steps | Completed
MHHS-DEL2618 SITOPS_BR05 Attempted Meter Read Fail recorded | Participant #1 | Participant #1 |  |  |  | TC01 | None | No Comment |  |  |  | NA | NA
MHHS-DEL2628 SIT_OPS_BR06 Escalate where consumption on de-enerigsed MPAN | Participant #1 | Participant #1 |  |  |  | TC01-TC03 | None | Energised typo in the title of the scenario |  |  |  | Typo fixed in v0.2 | Completed
MHHS-DEL2626 SITOPS_BR08 Investigate faulty equipment. | Participant #1 | Participant #1 |  |  |  | TC01-TC03 | None | No Comment |  |  |  | NA | NA
MHHS-DEL2629 SIT_OPS_BR11 Investigate Meter Technical Details issues | Participant #1 | Participant #1 |  |  |  | TC01 MSA, TC02 MSS | MPRS to send IF/PUB files | No Comment |  |  |  | NA | NA
MHHS-DEL2622 SITOPS_BR12 Monitoring & Tracking when transacting with DIP | Participant #1 | Participant #1 |  |  |  | TC01, TC02, TC03 & TC04 (TC05 does not apply to us) | A number of steps require MPRS to monitor if messages not received in time and send/received PUB messages. TC03 is more in depth and requires execution of a process | For this scenario, as an LDSO will require an IF-019 to be sent, in order that the IF-020 can be sent. Generally speaking, the LDSO's can't send an IF-020 on its own. |  |  |  | Test case update v0.2 showing IF-019 being sent prior to IF-020 | Completed
MHHS-DEL2627 SIT_OPS_BR13 Receive notification of fault resolution for (Unmetered) Equivalent Meter | Participant #1 | Participant #1 |  |  |  | TC01, TC02, TC03 | UMSO is required to send/receive emails | I'm unclear on the benefit of scenarios that require emails to be exchanged back and forth? No system steps appear to be required on either end of the process nor is there any indication if there are scenarios which are being tested within the test case which may hinder UMSD's ability to complete the test step within the 5WD timescale. These types of operational scenarios should be covered off by our "Business Readiness" requirements under qualification |  |  |  | This scenario has been removed , there are no system steps within this scenario email only communication
MHHS-DEL2617 SITOPS_BR15 Maintain Off-Peak Declaration records | Participant #1 | Participant #1 |  |  |  | TC01 | None | No Comment |  |  |  | NA | NA
MHHS-DEL2623 SITOPS_BR16 DIP Platform error messages | Participant #1 | Participant #1 |  |  |  | TC04_Regs, (TC01-TC03 requires MPRS to send/receive file only) | To send incorrect messages and then correct and resend | Our adapter monitors the execution of messages and applies validation to those files. An incorrectly generated file cannot bypass this and be released to the DIP. On that basis the test case will be impossible to complete from the applications themselves as we cannot create incorrect files that bypass the adapter |  |  |  | The interfaces selected are to elicit a response for the validation errors, if there are system costraints preventing particular validation errors being possible then an alternative message may be selected with the validation level being tested
MHHS-DEL2620 SITOPS_BR17 Load Shape Run information storage | Participant #1 | Participant #1 |  |  |  | N/A | None | No Comment |  |  |  | NA | NA
MHHS-DEL2621 SITOPS_BR18 VAS Run number setting and VAS runs date time storage | Participant #1 | Participant #1 |  |  |  | TC01 | None | No Comment |  |  |  | NA | NA
MHHS-DEL2636 SITOPS_BR20 BUUK can sucessfully load and operate MPRS in their own infrastructure | Participant #1 | Participant #1 |  |  |  | TC01 | Number of steps which C & C will complete | Typo, successfully is spelt incorrectly in the title |  |  |  | Typo fixed in v0.2 redlined | Completed
MHHS-DEL2637 SITOPS_BR21 MPRS in SSEN target infrastructure | Participant #1 | Participant #1 |  |  |  | TC01 | None | There appear to be a number of errata on this spreadsheet, essentially combining or alternately using SSEN and BUUK. All traces of BUUK must be removed from the test case, as it applies to SSEN only. |  |  | Accept | Updated to remove BUUK and replace with SSEN in v0.2 Redlined | Completed
MHHS-DEL2630 SITOPS_BR22 Target work date confirmation for Change Conn and Change Market Seg | Participant #1 | Participant #1 |  |  |  | TC01, TC02 | A number of steps including communication with the supplier, sending and receiving of various PUB messages. TC03 does not apply to us. | I am confused as to the benefit of the steps involving LDSO's being contacted by email/telephone/web portal and the requirement for evidence for Test Case 1 in particular and then to a lesser extent TC02. I can see that the Supplier is required to evidence the communication between LDSO's and themselves but as a central party it's likely that we will be required to repeat this test case a number of times and it's unclear how this can be efficiently managed or what this really proves. I am concerned that this could potentially hold up testing for little gain. If this test step goes ahead without amendment, then it will be prudent to include either guidance or a list of contacts/method for contacting the LDSO to ensure that parties know who to contact. Would it not be more helpful for the Suppliers to have a set of deemed date changes rather than a step requiring LDSO output which may hold up their testing. As with BR13 our ability to interact with the supplier and carry out this process should be covered by our "Business Readiness" responsibilities under Qualification. |  |  |  | This scenario has been removed as there are limited system steps against existing functionality and the interfaces have been tested in SIT Functional | Completed
MHHS-DEL2634 SITOPS_BR23 LSS provides data on request (adhoc requests) | Participant #1 | Participant #1 |  |  |  | TC01 | None | No Comment |  |  |  | NA | NA
MHHS-DEL2635 SITOPS_BR24 LSS Validation Failure investigation | Participant #1 | Participant #1 |  |  |  | N/A | None | No Comment |  |  |  | NA | NA
MHHS-DEL2638 SIT_OPS_BR25 LSS provides Load Shape data that is publically accessible | Participant #1 | Participant #1 |  |  |  | N/A | None | Typo in document title publically instead of publicly |  |  | Accept | This has been fixed in v0.2 | Completed
MHHS-DEL2639 SITOPS_BR26 VAS Capture and Store Data | Participant #1 | Participant #1 |  |  |  | TC01 | None | No Comment |  |  |  | NA | NA