## Sheet1
Organisation: | Various
Constituency:
Date: |  |  |  | MHHS-DEL2751 SIT Non-Functional Test Scenarios and Test Cases Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete | [5 empty] | Programme to complete once consultation window has closed.
Ref | Reviewer | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject or Action | Response | Status
1 | Helix |  |  |  |  | Hi Team, Helix Programme has a similar feedback inputs like last time for Theme 2. We are awaiting few more feedback comments, I will share them asap. Thanks Comments : 1. The scope for NFTs seems very wide and not really focused on Non-Functional as it requires running most of the integrations and services, producing most of the reports, ec. This overlaps with the functional tests being executed for SIT Functional. There are no details yet in the scenarios, but assumption is those will come later. 2. The Theme 3 Test Cases overall feedback looks more on functional side than non-functional. Thank You Shraddha Patre | Accept | These are functional tests, but with the focus being on integration from participant to DIP interfaces to provide an additional level of assurance around participant error handling, albeit at low volumes, but with a real DIP instance available.
2 | RECCo | 3 | SITNFT-T2-100 Disconnect | 010-Smart | 57+ | The meter removal steps are ocurring after the disconnection (and de-appointment of the MS) These should be moved up to be processed prior to the disconnection. | Accept | The test cases are based on functional SIT cases, disconnection steps have been moved ahead prior to disconnection steps
3 | RECCo | 3 | SITNFT-T2-110 COM | 010 - Trad to Smart | 25 | The CSS 00200 message to update the MDR would normally be triggered within the RS/ERDS by receipt of the IF-031 to appoint a DS/MDR. Does the simulated nature of this test mean the interface is being triggered by a different method? In addition I'm not sure what NFR this trigger of the CSS 00200 is covering. | Accept | This test case is based against functional case MHHS-DEL1894 SITFTS-0900 – MET Change of Meter successful. This will be further reviewed. NFT have looked through all Qualification and SIT cases, all start at metering service for these types of BP The only NFRs being met in this theme of testing are error handling, i.e. no connectivity to DIP, and processing, albeit at low volumes
4 | RECCo | 3 | SITNFT-T2-110 COM | General | N/A | There are 6 test cases in the overview tab but only 4 detailed. | Accept | Updated to match existing cases
5 | RECCo | 3 | SITNFT-T2-110 COM | 010 - Trad to Smart + 040 Trad to Smart | N/A | In 010 the meter removal is covered by sending a D0150, but in 040 it's both the D0149 and D0150. Can you confirm the expectation? | Accept | This test case is based against functional case MHHS-DEL1894 SITFTS-0900 – MET Change of Meter successful. This will be further reviewed.
6 | RECCo | 3 | SITNFT-T2-120 (IF19-020) | General | N/A | This covers IF019 and IF020 for related MPANs but not the Import / Export MPANs which are managed by the LDSO rather than the RS. This is needed to test LDSO NFRs | Acceot | Import/Export LSO rejection added to cover this interface
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372