## Sheet1
Organisation: | Various
Constituency: | Various
Date: | 2024-06-12 |  |  | MHHS-DEL2768 SIT Non-Functional Test Scenarios Theme 2 Consolidated Comments Log
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete | [5 empty] | Programme to complete once consultation window has closed.
Ref | Reviewer | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject or Action | Response | Status
1 | Utilita Energy | Theme 2 | SITNFT-T2-020 Consumption Test Cases v0.1. SITNFT-T2-030 Settlement LSS Test Cases v0.1 SITNFT-T2-040 COSupplier Notifications Test Cases v0.1 SITNFT-T2-050 COA Notifications Test Cases v0.1 SITNFT-T2-060 COSupplier Processing Test Cases v0.1 SITNFT-T2-070 COA Processing Test Cases v0.1 | All | All | General Comment (for all scenarios) As a Non-Functional Tester I am unable to comment on the validity of the test steps themselves. But... The test cases / scenarios are presented as Functional Test scenarios. Generally such level of complexity and choreography does not lend itself to Non-Functional testing. In order for this to work detailed information about the test data requirements will be needed to ensure that receiving participants have data in the correct state. | Action | Understood, we have a more process driven summary of message processing detailed for Theme 3 which will be tailored for the Load Plan By Scenario page. In terms of data, we have a summary of the # of MPANs per process, once the data is created and moved to SIT-B we will be able to provide details of specific MPANs for use
2 | Utilita Energy | Theme 2 | SIT Non-Functional Test Scenarios Theme2 v0.1 | Processing Window Load Plan by Scenario | n/a | Both Tabs refer to Day 1 and Day 2-4. Are these the same days and just different views on the same scenarios? Or are they different scenarios in different windows? It doesn't help that one refers to IFs and the other names scenarios. | Accept | Day 1 is using the Appointment processing as seed data for days 2-4 for COA and COS processing. Day 2 appointment processing will seed Day 3 COA and COS etc etc
3 | Utilita Energy | Theme 2 | SIT Non-Functional Test Scenarios Theme2 v0.1 | Processing Window Load Plan by Scenario |  | Interface IF-064(and the rest in BP017) are optional interfaces whcih makes the testing of this possible only to those MPs who choose to implement/use it. | Accept | IF-064 isn't covered within Theme 2
4 | Utilita Energy | Theme 2 | SIT Non-Functional Test Scenarios Theme2 v0.1 | Processing Window Load Plan by Scenario |  | Interface IF/PUB-022 & IF/PUB-023 are expected to be received by all MPs and expecting the Central Systems would use throttling mechanism. It would be ideal to test this aspect at part of NFT and receipients would have a view upfront view. Raising this question because LSS test scenarios are planned for fixed one hour period(10:00 - 11:00) If this is not relevent for Theme2, please confirm in whcih Theme or which phase(i.e. PIT/SIT) is this covered? | Accept | Given the amount of available data I think testing of the throttling mechanism may be beyond the scope of themes 2 and 3. Full performance related NFRs, are expected to be covered during PIT NFT delivery
5 | Utilita Energy | Theme 2 | SITNFT-T2-060* | SITNFT-T2-060* |  | These tests are intended to cover CoS from a previous date. Cannot see IF-31 message to initiate the appointment? Are the appontment related messges missed out or have I understood it wrong? | Accept | SITNFT-T2-060 & 70 are intended to be the actual processing of COS and COA, IF-31 from the previous day will have created the appointment for processing on the day this porcess is run
6 | Elexon |  |  |  |  | We were expecting the MHHS Bi-Laterals to agree the best way to test Helix non functionally. It feels like these tests are more functional and operational. Is this the best use of testing resource when we have many performance aspects to prove before? | Accept | The approach and plan for NFT has always stated that testing, at volume and expected messaging rates is to be carried out during PIT. The NFT team have had limited time available to set-up bilaterals up to this point. As part of the PIT documentation review these are now starting to be put in place
7 | Elexon |  | SIT Non-Functional Test Scenarios - Theme 2 |  |  | Is the overall objective of these tests to prove that Helix systems can meet the Operational Choreography timelines? | Accept | In terms of processing, as above, we would expect testing at volume to be carried out during PIT, and to meet the processing/timing guidelines for within the Operational Choreography doc and E2E requirements. Theme 2 is to provide a high level view of this type of processing in an intergrated environment, although at low volumes of traffic
8 | Elexon |  | SIT Non-Functional Test Scenarios - Theme 2 | In Scope for Theme 2 (Yes) |  | Are the processes listed in Overall Process List all in scope for SIT NFT Theme 2? The test cases do not show any scenarios or steps steps to execute some of these (like MDS, for example). | Accept | This are all the processes available for IR8, and utilised to track coverage of tests for themes 2 and 3, this will be removed as it is an internal tool for the NFT Team
9 | Elexon |  | SIT Non-Functional Test Scenarios - Theme 2 |  |  | In general, there isn’t much detail on the scenarios cases to understand the full scope of the tests. There seems to be also some overlap between the SIT NFT test cases and the SIT Functional test cases. | Accept | The test cases themselves are the same as Functional, effectivly a statement of where a participants involvment in the E2E processing required to complete a business process occurs, we will update the Load Plan By Scenario to also highlight required role and interface activites
10 | Elexon |  |  |  |  | What are the Acceptance Criteria for the tests? 1. SITNFT-T2-020, 30, 40, 50, 60, 70 2. How is each testing being validated? |  | As with above statement, the criteria will be successful processing/acceptance of a message as per the test cases, & particpant provided evidence that this has occurred. Analysis of this evidence against NFRs will be carried out. NFRs against each case step will be updated to highlight this
11 | Elexon |  |  |  |  | What is the category for these tests, is it Availability, Reliability, E2E, or something else? |  | Given the volume of traffic proposed for Theme 2, this would cover Interoperability an Time behaviour based NFRs, the doucments will be updated to highlight this
12 | Elexon |  |  |  |  | It is implying that MDS and VAS will be tested, is there any validation for them? | Accept | We would need further clairty on the specific test where this is being implied? As part of this theme, we are focussing on the initial settlement run II as the end point. We would require a little more knowledge in what is required from this from the Helix team if it has been omitted from the details for the theme 2
13 | Elexon |  |  |  |  | Only impact for WP3/4 would be to provide ISD data for the LSS runs. Is publishing of the ISD catalog a pre-requisite for this testing? | Accept | As above, if this is required for publishing will work with individual participants to generated acceptable test cases/data for this processing to take place
14 | Elexon |  |  |  |  | There will be test preparation needed, when to run the tests, so that we can get our team organised to support? According to the plan, they are running from Monday, 02 September this year. | Accept | 02 September is the planned start of Theme 1 testing (DIP-->Helix). Once the schedule for this has been agreed we will provide further scedules for Themes 2 & 3 of NFT SIT
15 | Elexon |  |  |  |  | Would it be possible for our team to speak with Iain Smith to discover more about the tests? | Accept | main point of contact for the programme remains - testing@mhhsprogramme.co.uk This will be forwarded onto the NFT team to set any needed meetings up
16 | Elexon |  |  |  |  | In the "LoadPlanby Scenario" sheet, Registration data load is not mentioned, does this mean the data should be loaded as pre-requisite?, if yes, do we have a plan in place to load the data and the required attributes to start the Theme2 testing | Accept | NFT will confirm with the programme data team
17 | Elexon |  |  |  |  | In the Overall Process list for "Elexon Central systems", for theme2 scope, it was mentioned only "LSS and MDS", and in the reports only Rep002 , could you please confirm the scope is only limited to these and not have VAS and other reports | Accept | These details can be provided on the back of the discussions that need to be set-up
18 | Elexon |  |  |  |  | Are we expecting the scheduler to trigger the execution?, if yes, do we have the settlement calendar and the required run types to be executed with the settlement dates | Accept | These details can be provided on the back of the discussions that need to be set-up
19 | Elexon |  |  |  |  | In most of the LSS cases, we see that the test is to check the files are received at LSS, does this mean we need to check the files received at Helix which means at DAH in the estimated time? Or also includes the settlement run to trigger and produce the reports back to the participants | Accept | Given the volume of traffic proposed for Theme 2, the processing and generation of reports would not be a true step in the validation of these processes. They would be a useful guage, but not the actual priority of this theme. To be discussed once meetings are set-up with you
20 | Elexon |  |  |  |  | Industry Standing Data-IF47 data notification- what exactly being tested as part of NFT for the IF-47 notification? Are we expecting an IF-47 to be sent to participants as pre-requisite data requirement before theme2 starts? | Accept | This IF, as a starting point, has not featured within the functional tests that were reviewed for Theme 2, we will need to work with Helix and Data teams to determine if this is a required pre-req that can be added into the test pack
21 | EON | General |  |  |  | Test scenario for this theme doesn’t make much value as only 1000 MPANs are allocated per cohort and testing the interfaces with 100-150 MPANs wouldn’t give any benefit as its not in proportion to the actual load and its already in functional testing scope. | Accept | The number of synced MPAN data limitation is known, however, there are still a number of benefits to conducting this type of testing within an integrated environment: 1) in addition to the step by step processing of Functional SIT, where automated processes are involved, these will be utilised 2) There is no current understanding of the E2E processing implications as part of SIT-F, even at low volumes of traffic, the addition of interfaces and other systems needs to be understood (relative to how they have behaved during PIT NFT) 3) OC - as a process remains untested, theme 2 intends to cover this area
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372

## Sheet2
Theme
Theme 1 - Forward Migration - CoA & CoS
Theme 2 - Reverse Migration - CoS
Theme 3 - Import/Export MPANs & Exception Handling