## Change Log
Date | Author | Release | Reason for change
2024-11-15 | Kevin Davis | 1.0 | Inventory of test cases that have been merged, replaced, or otherwise de-scoped from the SIT Functional baseline

## Test Case List
Theme | Cycle Where Changed Occurred | Scenario Ref | Test Case Ref | Test Case Name | Context and Reason for Change (De-scoping or Consolidation)
1 - New Connections | Cycle 1 | SITFTS-0060 Create MPAN, Services not immediately appointed | SITFTS-0060 TC01 | SITFTS-0060 TC01 Smart Metered | Upstream validation in Supplier Systems means it is not possible to create the conditions for setting a Service Appointment Date before the Supply start date. The negative condition cannot be created in SIT F.
1 - New Connections | Cycle 2 | SITFTS-0090 New Connection MS Change Re-Submit | SITFTS-0060 TC01 | SITFTS-0060 TC01 Unmetered | Test unachievable due to upstream validation in Supplier Systems.
1 - New Connections | Cycle 2 | SITFTS-0090 New Connection MS Change Re-Submit | SITFTS-0090 TC02 | SITFTS-0090 TC02 Traditional Metered | Conditions can't be created by the third Party outside the Registration Service.
2 - Change of Registration | Cycle 2 | SITFTS-0980 Registration data update for Metered Indicator | SITFTS-0980 TC01 | SITFTS-0980 TC01 | PP systems can’t support the Business Process for BPM011 in SITF and cannot change the Metered Indicator.
2 - Change of Registration | Cycle 2 | SITFTS-0980 Registration data update for Metered Indicator | SITFTS-0980 TC02 | SITFTS-0980 TC02 | PP systems can’t support the Business Process for BPM011 in SITF and cannot change the Metered Indicator.
2 - Change of Registration | Cycle 2 | SITFTS-0980 Registration data update for Metered Indicator | SITFTS-0980 TC03 | SITFTS-0980 TC03 | PP systems can’t support the Business Process for BPM011 in SITF and cannot change the Metered Indicator.
2 - Change of Registration | Cycle 1 | SITFTS-1010 Registration data update for legacy data items | SITFTS-1010 TC03 | SITFTS-1010 TC03 traditional, legacy data update (Profile Class Update Only) | De-scoped as per Defect 31814, profile class and SSC cannot be updated individually, making this test unviable.
2 - Change of Registration | Cycle 1 | SITFTS-1010 Registration data update for legacy data items | SITFTS-1010 TC04 | SITFTS-1010 TC04 smart, legacy data update (SSC Update Only) | De-scoped as per Defect 31814, profile class and SSC cannot be updated individually, making this test unviable.
3 - Change of Supplier | Cycle 1 | SITFTS-0020 Change of Supplier and DS, no change of MS | SITFTS-0020 TC03 | SITFTS-0020 TC03 Unmetered | Conditions specified in the test case cannot be produced in SITF.
3 - Change of Supplier | Cycle 1 | SITFTS-0020 Change of Supplier and DS, no change of MS | SITFTS-0020 TC05 | SITFTS-0020 TC05 Smart Single | TC certified invalid in in consultation with SI and SRO design.
5 - Change of Metering | Cycle 1 | SITFTS-0105 Change of MS, no change of supplier or DS | SITFTS-0105 TC05 | SITFTS-0105 TC05 Unmetered Accepted | Descoped: Untestable in SITF as there is only oner UMSO on the pitch (can't change an unmetered MS when there is only one UMSO)
5 - Change of Metering | Cycle 1 | SITFTS-0105 Change of MS, no change of supplier or DS | SITFTS-0105 TC06 | SITFTS-0105 TC06 Unmetered Lapsed | Untestable in SITF as there is only oner UMSO on the pitch (can't change an unmetered MS when there is only one UMSO)
6 - Metering Changes | Cycle 2 | SITFTS-0862 MET Market Segment Change during COS | SITFTS-0862 TC01 | SITFTS-0862 TC01 Smart to Advanced Market Segment Change | Descoped: The design provides no mechanism for dealing with this scenario, and as Change of Segment and Change of Supplier are covered elsewhere, the intent of this test case is invalid.
6 - Metering Changes | Cycle 2 | SITFTS-0905 Change of meter - Registration Service Rejections | SITFTS-0905 TC03 | SITFTS-0905 TC03 Smart Install | TC certified invalid in in consultation with SI and SRO design.
7 - Consumption | Cycle 2 | SITFTS-0012 Consumption on Change of Supplier, no change of MS | SITFTS-0012 TC03 | SITFTS-0012 TC03 Advanced | The test runs CoS process with no consumption issued at the end; agreed superfluous with SI/SRO design.
7 - Consumption | Cycle 2 | SITFTS-0012 Consumption on Change of Supplier, no change of MS | SITFTS-0012 TC04 | SITFTS-0012 TC04 Unmetered | The test runs CoS process with no consumption issued at the end; agreed superfluous with SI/SRO design.
7 - Consumption | Cycle 2 | SITFTS-0132 Consumption on Change of Data Service, Transfer of Reads | SITFTS-0132 TC04 | SITFTS-0132 TC04 Unmetered | Invalid test case. There is no consumption adjustment on change of Unmetered Data Service.
7 - Consumption | Cycle 3 | SITFTS-0310 CONS ADS Export Estimation | SITFTS-0310 TC09 | SITFTS-0310 Advanced Meter where Check Meter data is missing (Reactive Power) | De-scoped as per defect 42822:
The purpose of scenario SITFTS-0310 is to cover the Export Standard Method (ADS Standard Estimation Methods for Export Metering Systems) and this is achieved with TC01-08. However, this TC is invalid because Export Reactive Power does not fall under the Export Standard Method. Export Reactive Power falls under the ADS Standard Methods for import Metering Systems, which is covered by scenario SITFTS-0305 Estimates consumption data where actual UTC Period Consumption is unavailable (import), specifically TC09-TC15.
7 - Consumption | Cycle 3 | SITFTS-0310 CONS ADS Export Estimation | SITFTS-0310 TC10 | SITFTS-0310 Advanced Meter where Main Meter data is missing (Reactive Power) | De-scoped as per defect 42822:
The purpose of scenario SITFTS-0310 is to cover the Export Standard Method (ADS Standard Estimation Methods for Export Metering Systems) and this is achieved with TC01-08. However, this TC is invalid because Export Reactive Power does not fall under the Export Standard Method. Export Reactive Power falls under the ADS Standard Methods for import Metering Systems, which is covered by scenario SITFTS-0305 Estimates consumption data where actual UTC Period Consumption is unavailable (import), specifically TC09-TC15.
7 - Consumption | Cycle 3 | SITFTS-0310 CONS ADS Export Estimation | SITFTS-0310 TC11 | SITFTS-0310 Advanced Meter where one UTC Period unavailable (Reactive Power) | De-scoped as per defect 42822:
The purpose of scenario SITFTS-0310 is to cover the Export Standard Method (ADS Standard Estimation Methods for Export Metering Systems) and this is achieved with TC01-08. However, this TC is invalid because Export Reactive Power does not fall under the Export Standard Method. Export Reactive Power falls under the ADS Standard Methods for import Metering Systems, which is covered by scenario SITFTS-0305 Estimates consumption data where actual UTC Period Consumption is unavailable (import), specifically TC09-TC15.
7 - Consumption | Cycle 3 | SITFTS-0310 CONS ADS Export Estimation | SITFTS-0310 TC12 | SITFTS-0310 Advanced Meter where Main and Check Meter data is unavailable (Reactive Power) | De-scoped as per defect 42822:
The purpose of scenario SITFTS-0310 is to cover the Export Standard Method (ADS Standard Estimation Methods for Export Metering Systems) and this is achieved with TC01-08. However, this TC is invalid because Export Reactive Power does not fall under the Export Standard Method. Export Reactive Power falls under the ADS Standard Methods for import Metering Systems, which is covered by scenario SITFTS-0305 Estimates consumption data where actual UTC Period Consumption is unavailable (import), specifically TC09-TC15.
7 - Consumption | Cycle 3 | SITFTS-0310 CONS ADS Export Estimation | SITFTS-0310 TC13 | SITFTS-0310 Advanced Meter with Data from MSA where Main and Check Meter data is unavailable (Reactive Power) | De-scoped as per defect 42822:
The purpose of scenario SITFTS-0310 is to cover the Export Standard Method (ADS Standard Estimation Methods for Export Metering Systems) and this is achieved with TC01-08. However, this TC is invalid because Export Reactive Power does not fall under the Export Standard Method. Export Reactive Power falls under the ADS Standard Methods for import Metering Systems, which is covered by scenario SITFTS-0305 Estimates consumption data where actual UTC Period Consumption is unavailable (import), specifically TC09-TC15.
7 - Consumption | Cycle 3 | SITFTS-0310 CONS ADS Export Estimation | SITFTS-0310 TC14 | SITFTS-0310 Advanced Meter with Data from BRP(Supplier) where Main and Check Meter data is unavailable (Reactive Power) | De-scoped as per defect 42822:
The purpose of scenario SITFTS-0310 is to cover the Export Standard Method (ADS Standard Estimation Methods for Export Metering Systems) and this is achieved with TC01-08. However, this TC is invalid because Export Reactive Power does not fall under the Export Standard Method. Export Reactive Power falls under the ADS Standard Methods for import Metering Systems, which is covered by scenario SITFTS-0305 Estimates consumption data where actual UTC Period Consumption is unavailable (import), specifically TC09-TC15.
7 - Consumption | Cycle 2 | SITFTS-0330 UMSDS validation failures of D0388 | SITFTS-0330 TC05 | SITFTS-0330 Invalid Eff From Date | Defect 32249: UMSO internal system validation will not allow sending of a D0388 file with an Effective From Date that would trigger the invalid date this test requires. Coverage of this condition would only be possible as part of an internal system test.
7 - Consumption | Cycle 1 | SITFTS-0530 Consumption IF-021 Invalid Data Rejected by LSS | SITFTS-0530 TC01 | SITFTS-0530 TC01 Smart | Replaced by and incorporated into scenario SITFTS-ST0070 Consumption for LSS Rejection and Default.
7 - Consumption | Cycle 1 | SITFTS-0530 Consumption IF-021 Invalid Data Rejected by LSS | SITFTS-0530 TC02 | SITFTS-0530 TC02 Advanced | Replaced by and incorporated into scenario SITFTS-ST0070 Consumption for LSS Rejection and Default.
7 - Consumption | Cycle 1 | SITFTS-1070 Consumption Override Readings | SITFTS-1070 TC01 | SITFTS-1070 TC01 Traditional BAU | Descoped: TC certified invalid in in consultation with SI and SRO design.
7 - Consumption | Cycle 1 | SITFTS-1070 Consumption Override Readings | SITFTS-1070 TC02 | SITFTS-1070 TC02 Adv Pre RF Calc Required | Descoped: TC certified invalid in in consultation with SI and SRO design.
7 - Consumption | Cycle 1 | SITFTS-1080 Consumption Amendment Criteria Not Met | SITFTS-1080 TC01 | SITFTS-1080 TC01 Smart Pre RF and Below Threshold | Descoped: Conditions specified in the test case cannot be produced in SITF.
7 - Consumption | Cycle 1 | SITFTS-1080 Consumption Amendment Criteria Not Met | SITFTS-1080 TC02 | SITFTS-1080 TC02 Advanced Post RF and Dispute Criteria not met | Descoped: Conditions specified in the test case cannot be produced in SITF.
7 - Consumption | Cycle 1 | SITFTS-1095 Consumption Amendment Trading Dispute | SITFTS-1095 TC01 | SITFTS-1095 TC01 Smart Post RF and Dispute Criteria met | Descoped: Conditions specified in the test case cannot be produced in SITF.
7 - Consumption | Cycle 1 | SITFTS-1100 Consumption Amendment Rejected | SITFTS-1100 TC01 | SITFTS-1100 TC01 Smart Consumption Rejected | Replaced by and incorporated into SITFTS-ST0070 Consumption for LSS Rejection and Default, TC09 Smart LS Default.
7 - Consumption | Cycle 1 | SITFTS-1100 Consumption Amendment Rejected | SITFTS-1100 TC02 | SITFTS-1100 TC02 Advanced Consumption Rejected | Replaced by and incorporated into SITFTS-ST0070 Consumption for LSS Rejection and Default, TC04 Adv LS Default.
7 - Consumption | Cycle 1 | SITFTS-1110 Consumption Amendment Accepted | SITFTS-1110 TC01 | SITFTS-1110 TC01 Smart Pre RF validation pass | Replaced by and incorporated into SITFTS-ST0055 Settlement impacted by Override Readings and Consumption Amendment.
7 - Consumption | Cycle 1 | SITFTS-1110 Consumption Amendment Accepted | SITFTS-1110 TC02 | SITFTS-1110 TC02 Advanced Pre RF validation pass | Replaced by and incorporated into SITFTS-ST0055 Settlement impacted by Override Readings and Consumption Amendment.
8 - Settlement | Cycle 2 | SITFTS-ST0005 New Connections | ST0005 TC01 | ST0005 TC01 Smart Linked | Superfluous test case. No impact on Settlement. Req covered by SITFTS-ST0030 Consumption settling normally.
8 - Settlement | Cycle 2 | SITFTS-ST0005 New Connections | ST0005 TC02 | ST0005 TC02 Trad Single | Superfluous test case. No impact on Settlement. Req covered by SITFTS-ST0030 Consumption settling normally.
8 - Settlement | Cycle 2 | SITFTS-ST0005 New Connections | ST0005 TC03 | ST0005 TC03 Advanced Single | Superfluous test case. No impact on Settlement. Req covered by SITFTS-ST0030 Consumption settling normally.
8 - Settlement | Cycle 2 | SITFTS-ST0005 New Connections | ST0005 TC04 | ST0005 TC04 Unmetered | Superfluous test case. No impact on Settlement. Req covered by SITFTS-ST0030 Consumption settling normally.
8 - Settlement | Cycle 1 | SITFTS-ST0010 New Connection / Customer Own Read supplied | ST0010 TC01 | ST0010 TC01 Trad CoR | Superfluous test case. No impact on Settlement. Req covered by SITFTS-ST0030 Consumption settling normally.
8 - Settlement | Cycle 2 | SITFTS-ST0015 Change of Energisation | ST0015 TC04 | ST0015 TC04 Adv Retro Energise | Replaced by and consolidated into SITFTS-ST0015 Change of Energisation, TC02 Retro Energise.
8 - Settlement | Cycle 2 | SITFTS-ST0015 Change of Energisation | ST0015 TC05 | ST0015 TC05 Unm Retro Energise | Replaced by and consolidated into SITFTS-ST0015 Change of Energisation, TC02 Retro Energise.
8 - Settlement | Cycle 2 | SITFTS-ST0015 Change of Energisation | ST0015 TC06 | ST0015 TC06 Smart Retro Energise | Replaced by and consolidated into SITFTS-ST0015 Change of Energisation, TC02 Retro Energise.
8 - Settlement | Cycle 2 | SITFTS-ST0015 Change of Energisation | ST0015 TC07 | ST0015 TC07 Smart Back Stop Energise | Replaced by SITFTS-ST0015 Change of Energisation, TC03 Smart Back-Stop Energise.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC01 | ST0020 TC01 Traditional | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC02 | ST0020 TC02 Advanced | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC03 | ST0020 TC03 Smart | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC04 | ST0020 TC04 Unmetered | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC05 | ST0020 TC05 Traditional Export | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC06 | ST0020 TC06 Smart Export | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs | ST0020 TC07 | ST0020 TC07 Advanced Re Estimate | Replaced by and consolidated into SITFTS-ST0020 Consumption adjustments applied in Subsequent Calendar Runs, TC01 Read Adjustments.
8 - Settlement | Cycle 2 | SITFTS-ST0025 Rollover Changed Reads | ST0025 TC01 | ST0025 TC01 Trad Rollover | Superfluous test case. No impact on Settlement. No unique req impact.
8 - Settlement | Cycle 2 | SITFTS-ST0025 Rollover Changed Reads | ST0025 TC02 | ST0025 TC02 Adv Rollover | Superfluous test case. No impact on Settlement. No unique req impact.
8 - Settlement | Cycle 2 | SITFTS-ST0025 Rollover Changed Reads | ST0025 TC03 | ST0025 TC03 Smart Changed Read | Superfluous test case. No impact on Settlement. No unique req impact.
8 - Settlement | Cycle 2 | SITFTS-ST0025 Rollover Changed Reads | ST0025 TC04 | ST0025 TC04 Adv Changed Read | Superfluous test case. No impact on Settlement. No unique req impact.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC01 | ST0030 Traditional | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC02 | ST0030 Smart Single | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC03 | ST0030 Advanced Import | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC04 | ST0030 Advanced Export | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC05 | ST0030 Smart Diff Suppliers | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC06 | ST0030 Smart Same Suppliers | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC07 | ST0030 Unmetered | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC08 | ST0030 Traditional Multi Rated | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC09 | ST0030 Advanced Reactive Power | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0030 Consumption settling normally | ST0030 TC10 | ST0030 Smart single MPAN on Monthly Consents | Replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC01 | ST0032 Smart Spring | Not possible to create conditions in SITF to cover processing of the Spring Clock Change Settlement Day with specific reference to the variation in the number of Settlement Periods. Coverage of the IF-021 consumption split has been moved to a new Consumption TC, SITFTS-0012 Consumption on Change of Supplier, no change of MS, TC10 Smart CoS with change of MS and DS, BST.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC02 | ST0032 Traditional Spring | Not possible to create conditions in SITF to cover processing of the Spring Clock Change Settlement Day with specific reference to the variation in the number of Settlement Periods. Coverage of the IF-021 consumption split has been moved to a new Consumption TC, SITFTS-0012 Consumption on Change of Supplier, no change of MS, TC10 Smart CoS with change of MS and DS, BST.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC03 | ST0032 TC03 Advanced Spring | Not possible to create conditions in SITF to cover processing of the Spring Clock Change Settlement Day with specific reference to the variation in the number of Settlement Periods. Coverage of the IF-021 consumption split has been moved to a new Consumption TC, SITFTS-0012 Consumption on Change of Supplier, no change of MS, TC08 Advanced Reactive Power CoS with change of MS and DS, BST.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC04 | ST0032 TC04 Unmetered Spring | Not possible to create conditions in SITF to cover processing of the Spring Clock Change Settlement Day with specific reference to the variation in the number of Settlement Periods. Coverage of the IF-021 consumption split has been moved to a new Consumption TC, SITFTS-0012 Consumption on Change of Supplier, no change of MS, TC09 Unmetered CoS with no change of DS - BST.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC05 | ST0032 TC05 Smart Autumn | Replaced by and consolidated into SITFTS-ST0032 Settling after Clock Changes, TC01 Settling Normally on day of change from BST to GMT.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC06 | ST0032 TC06 Traditional Autumn | Replaced by and consolidated into SITFTS-ST0032 Settling after Clock Changes, TC01 Settling Normally on day of change from BST to GMT.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC07 | ST0032 TC07 Advanced Autumn | Replaced by and consolidated into SITFTS-ST0032 Settling after Clock Changes, TC01 Settling Normally on day of change from BST to GMT.
8 - Settlement | Cycle 2 | SITFTS-ST0032 Settling during Clock Changes | ST0032 TC08 | ST0032 TC08 Unmetered Autumn | Replaced by and consolidated into SITFTS-ST0032 Settling after Clock Changes, TC01 Settling Normally on day of change from BST to GMT.
8 - Settlement | Cycle 1 | SITFTS-ST0035 Consumption settling normally | ST0035 TC01 | ST0035 TC01 Traditional | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 1 | SITFTS-ST0035 Consumption settling normally | ST0035 TC02 | ST0035 TC02 Smart | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 1 | SITFTS-ST0035 Consumption settling normally | ST0035 TC03 | ST0035 TC03 Advanced | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 1 | SITFTS-ST0035 Consumption settling normally | ST0035 TC04 | ST0035 TC04 Unmetered | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0037 Consumption settling against De-Energised MPANs | ST0037 TC01 | ST0037 TC01 Traditional | Replaced by and consolidated into SITFTS-ST0037 Consumption settling against De-Energised MPANs, TC04 Trad - Smart.
8 - Settlement | Cycle 2 | SITFTS-ST0037 Consumption settling against De-Energised MPANs | ST0037 TC05 | ST0037 TC05 Advanced A2 | Replaced by and consolidated into SITFTS-ST0037 Consumption settling against De-Energised MPANs, TC02 Consumption Settling De-Energised, Advanced.
8 - Settlement | Cycle 2 | SITFTS-ST0037 Consumption settling against De-Energised MPANs | ST0037 TC06 | ST0037 TC06 Advanced A3 | Replaced by and consolidated into SITFTS-ST0037 Consumption settling against De-Energised MPANs, TC02 Consumption Settling De-Energised, Advanced.
8 - Settlement | Cycle 2 | SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS | ST0040 TC05 | ST0040 TC05 Smart Import | SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS test cases TC05-TC08 are superfluous with no unique MHHS requirements coverage. Impact of CoS extensively covered in the other test cases, i.e.: TC01 Settlement Before and After CoS, Trad Related TC02 Settlement Before and After CoS, Smart Single TC03 Settlement Before and After CoS, Adv Single TC04 Settlement Before and After CoS, Unmetered No value added by additional data variants (Smart Import/Export, Adv Single Estimate, Smart Deemed).
8 - Settlement | Cycle 2 | SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS | ST0040 TC06 | ST0040 TC06 Smart Export | As above, superfluous test case with no unique MHHS requirements coverage. Impact of CoS extensively covered in SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS, TC01-TC04; no value added by this data variant.
8 - Settlement | Cycle 2 | SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS | ST0040 TC07 | ST0040 TC07 Adv Single Estimate | As above, superfluous test case with no unique MHHS requirements coverage. Impact of CoS extensively covered in SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS, TC01-TC04; no value added by this data variant.
8 - Settlement | Cycle 2 | SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS | ST0040 TC08 | ST0040 TC08 Smart Deemed | As above, superfluous test case with no unique MHHS requirements coverage. Impact of CoS extensively covered in SITFTS-ST0040 COS only or COS with change of Metering Service and/or Data Service where Settlement is working prior to and after the COS, TC01-TC04; no value added by this data variant.
8 - Settlement | Cycle 2 | SITFTS-ST0050 Settlement impacted by IF-024 Supplier Advisory Notifications to Data Service | ST0050 TC02 | ST0050 TC02 Smart Off Peak | Method Statement 7 does not provide for Smart Meters with SNACs. The test is invalid.
8 - Settlement | Cycle 2 | SITFTS-ST0052 UPD Domestic Premise Indicator | ST0052 TC01 | ST0052 TC01 Update for Domestic Premise Indicator smart | Superfluous test case as associated MHHS requirements are covered in existing Functional Test Cases, e.g. SITFTS-0940 Registration data update for Domestic Premise Indicator. No material Settlement impact associated with this scenario not covered elsewhere.
8 - Settlement | Cycle 2 | SITFTS-ST0052 UPD Domestic Premise Indicator | ST0052 TC02 | ST0052 TC02 Update for Domestic Premise Indicator Advanced | Superfluous test case as associated MHHS requirements are covered in existing Functional Test Cases, e.g. SITFTS-0940 Registration data update for Domestic Premise Indicator. No material Settlement impact associated with this scenario not covered elsewhere.
8 - Settlement | Cycle 2 | SITFTS-ST0053 MDS D0297 MPAN_ABMU Mapping | ST0053 TC02 | ST0053 TC02 D0297 MPAN_ABMU Mapping Advanced | Replaced by and consolidated into SITFTS-ST0053 MDS D0297 MPAN_ABMU Mapping, TC01 ABMU Normal Settlement.
8 - Settlement | Cycle 2 | SITFTS-ST0053 MDS D0297 MPAN_ABMU Mapping | ST0053 TC03 | ST0053 TC03 Rejection of D0297 MPAN_ABMU Mapping | BAU process; no residual risk not covered elsewhere.
8 - Settlement | Cycle 2 | SITFTS-ST0054 - Update DUoS Tariff Id | ST0054 TC02 | ST0054 TC02 Advanced | Replaced by and consolidated into SITFTS-ST0054 Update DUoS Tariff Id, TC01 Update DUoS Tariff ID Smart; no value added by this data variant.
8 - Settlement | Cycle 1 | SITFTS-ST0060 Consumption settling normally for Unmetered with differing characteristics | ST0060 TC01 | ST0060 TC01 UM Passive | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 1 | SITFTS-ST0060 Consumption settling normally for Unmetered with differing characteristics | ST0060 TC02 | ST0060 TC02 UM Dyn PECU Mult MPAN | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 1 | SITFTS-ST0060 Consumption settling normally for Unmetered with differing characteristics | ST0060 TC03 | ST0060 TC03 UM Dyn PECU Sing MPAN | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 1 | SITFTS-ST0060 Consumption settling normally for Unmetered with differing characteristics | ST0060 TC04 | ST0060 TC04 UM Dyn CMS Data | Critical scope coverage (data variants) replaced by and consolidated into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
8 - Settlement | Cycle 2 | SITFTS-ST0070 LSS Reject and Default | ST0070 TC01 | ST0070 TC01 Smart Reject | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0070 LSS Reject and Default | ST0070 TC02 | ST0070 TC02 Advanced Reject | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0070 LSS Reject and Default | ST0070 TC03 | ST0070 TC03 Trad LS Default | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0070 LSS Reject and Default | ST0070 TC06 | ST0070 TC06 Trad Variance | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0070 LSS Reject and Default | ST0070 TC07 | ST0070 TC07 Adv Variance | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0070 LSS Reject and Default | ST0070 TC08 | ST0070 TC08 Unmetered Variance | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0075 MDS Reject IF-021 | ST0075 TC01 | ST0075 TC01 Smart Reject | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0075 MDS Reject IF-021 | ST0075 TC02 | ST0075 TC02 Advanced Reject | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0075 MDS Reject IF-021 | ST0075 TC03 | ST0075 TC03 Unmetered Reject 1 | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0075 MDS Reject IF-021 | ST0075 TC04 | ST0075 TC04 Unmetered Reject 2 | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0075 MDS Reject IF-021 | ST0075 TC05 | ST0075 TC05 Smart Consumption Amendment Reject | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0075 MDS Reject IF-021 | ST0075 TC06 | ST0075 TC06 Advanced Consumption Amendment Reject | Not possible to create the conditions for this TC in SITF - PP systems cannot issue invalid data.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC01 | ST0090 TC01 Traditional AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC02 | ST0090 TC02 Smart Single AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC03 | ST0090 TC03 Advanced Import AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC04 | ST0090 TC04 Advanced Export AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC05 | ST0090 TC05 Unmetered AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC06 | ST0090 TC06 Traditional E7 AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC07 | ST0090 TC07 New Connection Smart Linked AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC08 | ST0090 TC08 New Connection Advanced Single AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC09 | ST0090 TC09 Energised Smart Single AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 2 | SITFTS-ST0090 Annual Consumption | ST0090 TC10 | ST0090 TC10 Energised Advanced Single AC | Replaced by and consolidated into a new TC: ST0090 TC01 Annual Consumption.
8 - Settlement | Cycle 1 | SITFTS-ST0099 Settlement LDSO to Supplier Reports REP-900 [E-BILL] and REP-901 [Aggregated DUoS Charges] | ST0099 TC01 | ST0099 TC01 Reports | Coverage merged into SITFTS-ST0030 Consumption settling normally, TC01 Settling Normally.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC01 | SITFTS-0410 TC01 MSS Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC02 | SITFTS-0410 TC02 MSA Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC03 | SITFTS-0410 TC03 UMSO Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC04 | SITFTS-0410 TC04 SDS Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC05 | SITFTS-0410 TC05 ADS Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC06 | SITFTS-0410 TC06 UMSDS Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC07 | SITFTS-0410 TC07 REGS Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC08 | SITFTS-0410 TC08 SUP Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC09 | SITFTS-0410 TC09 LDSO Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0410 Invalid download | SITFTS-0410 TC10 | SITFTS-0410 TC10 EES Invalid download individual entity | Replaced by and merged into a single test case SITFTS-0410 TC01 ISD Data Download Fails, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC01 | SITFTS-0420 TC01 MSS ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC02 | SITFTS-0420 TC02 MSA ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC03 | SITFTS-0420 TC03 UMSO ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC04 | SITFTS-0420 TC04 SDS ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC05 | SITFTS-0420 TC05 ADS ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC06 | SITFTS-0420 TC06 UMSDS ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC07 | SITFTS-0420 TC07 REGS ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC08 | SITFTS-0420 TC08 SUP ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC09 | SITFTS-0420 TC09 LDSO ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0420 ISD Data Access - Previous ISD version | SITFTS-0420 TC10 | SITFTS-0420 TC10 EES ISD previous version | Replaced by and merged into a single test case SITFTS-0420 TC01 ISD previous version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC01 | SITFTS-0425 TC02 MSA ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC02 | SITFTS-0425 TC02 MSA ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC03 | SITFTS-0425 TC03 UMSO ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC04 | SITFTS-0425 TC04 SDS ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC05 | SITFTS-0425 TC05 ADS ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC06 | SITFTS-0425 TC06 UMSDS ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC07 | SITFTS-0425 TC07 REGS ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC08 | SITFTS-0425 TC08 SUP ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC09 | SITFTS-0425 TC09 LDSO ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.
9 - ISD | Cycle 1 | SITFTS-0425 ISD Data access - Human-readable form | SITFTS-0425 TC10 | SITFTS-0425 TC10 EES ISD human readable version | Replaced by and merged into a single test case SITFTS-0425 TC01 ISD human-readable version, with validation steps for each role.