## Consolidated Log
MHHS-DEL3522 - SIT Operational Theme 3 (Batch 2) Supplementary Test Cases Consolidated Comments Log
*Organisation: | Various |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Comment Owner Anonymised: | No
*Date: | 2025-03-04
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner
To be populated by the Programme | Input the Ref # of the area of the document you are commenting on | Succinctly state the comment and the basis for the concern | Provide detail of the change or action required to resolve the comment | Provide a rationale for the change detailing the impact or materiality as a result of not making the recommended change | Provide the name of person providing the comment | Action (Accept/Reject) | Response | Comment Status (Complete/Pending)
| SITOP-DIP06 v0.4 | This test appears far more limited than the earlier version and does not reference revocation of certificates or checks with code bodies to ensure there are no live metering points registered to the organisation that would be stranded if the DIP User access is removed. These are important controls and we believe operational testing should ensure the full process is in place | Re-introduce wider operational checks to ensure the required controls are built into the process. | If the wider checks are not captured in the test there is a risk that these are not built into the process which would not align to code drafting and would introduce an operational risk. | RECCo | Accept | As all the detail to include the extra checks you mentioned have not yet been agreed. At this stage the programme can only really test the technical aspects of the off-boarding process. | Pending
| OPC007_COA | The scenario includes steps for the RS to send the D0170 to the losing MOP but these appear after the issuing of the IF036. The D0170 should be sent after the IF035 as set out in the business process. | Move the steps relating to the D0170 so they come after the IF035 appointment acceptance | If the tests are not amended and the RS sends the D0170 after the IF036 it would be inconsistent with the MHHS Design and may caouse delaying in the sending of MTDs in live operations | RECCo | Accept | Req has come from other participants to review whether the Requirements have previously been tested. SITF team are currently reviewing and if correct we will be approaching Code Bodies to descope this from Operational Testing. | Pending
| OPC007_COA | Overview page refers to traditional, but the test case is Advanced | Update the overview page to reflect the test case | The overview page should reflect the test scenarios to avoid confusion | RECCo | Accept | Will correct but please see above. | Complete.
| OPC007_COA | There appears to be a lack of clarity around which MOA sends the MTDs. Step 52 suggests the current MS (AMSC) sending the MTDs as a result of the MS appointment. This should be the existing MOP as a result of the DS appointments and / or the new MS (AMSI) as a result of the MS appointment | We would appreciate a discussion with the programme to fully understand who should send the MTDs in a migration i.e. whether both the losing MOP and Gaining MS send to the Gaining DS and what happens if the MS and DS appointments are not progressed in parallel | Operational issues that may impact migration if its not clear when the MTDs should be sent | RECCo | Accept | Req has come from other participants to review whether the Requirements have previously been tested. SITF team are currently reviewing and if correct we will be approaching Code Bodies to descope this from Operational Testing. | Pending
| OPC007_COA | Step 55 states that the MS should check the EES or the IF-003 if MTDs are missing. The IF-003 is only sent for reverse migration so not valid in this scenario | Remove reference to the IF-003 | Erroneous steps, likely to cause testing issues | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC007_COA | Step 57 has no message - as this is sending the correct details, it should reference the D0268 | Add reference to D0268 | Lack of clarity | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC007_COA | This scenario is meant to cover missing MTDs, but the MTDs are actually being sent? | Remove steps where the MTDs are sent before the missing MTD test steps | You wouldnt be testing missing MTDs if the MTDs are actually sent | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC008_COS | Steps 17 and 18 refer to a new connection and are not relevant for a CoS scenario | Remove steps 17 and 18 | Erroneous steps, likely to cause testing issues | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC008_COS | There appears to be a lack of clarity around which MOA sends the MTDs. Step 74 suggests the current MS (AMSC) sending the MTDs as a result of the MS appointment. This should be the existing MOP as a result of the DS appointments and / or the new MS (AMSI) as a result of the MS appointment | We would appreciate a discussion with the programme to fully understand who should send the MTDs in a migration i.e. whether both the losing MOP and Gaining MS send to the Gaining DS and what happens if the MS and DS appointments are not progressed in parallel | Operational issues that may impact migration if its not clear when the MTDs should be sent | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC008_COS | Step 93 states that the MS should check the EES or the IF-003 if MTDs are missing. The IF-003 is only sent for reverse migration so not valid in this scenario | Remove reference to the IF-003 | Erroneous steps, may cause testing issues | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC008_COS | The scenario includes steps for the RS to send the D0170 to the losing MOP but these appear after the issuing of the IF036. The D0170 should be sent after the IF035 as set out in the business process. | Move the steps relating to the D0170 so they come after the IF035 appointment acceptance | If the tests are not amended and the RS sends the D0170 after the IF036 it would be inconsistent with the MHHS Design and may caouse delaying in the sending of MTDs in live operations | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC008_COS | This scenario is meant to cover missing MTDs, but the MTDs are actually being sent? | Remove steps where the MTDs are sent before the missing MTD test steps | You wouldnt be testing missing MTDs if the MTDs are actually sent | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC009_RM | Step 19 evidence states MOP will create the D0205. This should be the Supplier. | Amend evidence column to refer to the Supplier sending the D0205 | Erroneous steps, may cause testing issues | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC009_RM | Step 20 also covers the D0205 but refers to awaiting CSS. Should the text align to step 22 | Review and correct text | Lack of clarity | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC009_RM | Step 45 is unclear. It suggests the step is receipt of MTDs but the evidence states the SMSO is producing the D0149 / 150. For a smart reverse migration, this should be a skeleton D0150 to the mop and supplier and its not clear how this is a missing MTD scenario as the MTDs are being sent. | Review and correct text | Lack of clarity | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
| OPC009_RM | Step 1018 evidence suggests the MS sends the D0367 which is not correct | Amend evidence column to refer to the Supplier sending the D0367 | Lack of clarity | RECCo | Reject | These Test Cases were taken through Interna and Industy review whilst under the remit of Migrations. Since they have moved to Operations no changes have been made but as per the potentially descoping mentioned above, I will wait for confirmation they remain in scope before addressing the script errors (Thy will need Migration Team to review and confirm changes). | Pending
1 | MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successful Supplemental v0.4 - Clean; MHHS-DEL3463_SITOPS_DIP06_DIP Offboarding Technical Supplemental v0.1 Clean | Are we going to do execution in production DIP portal or Test DIP portal. Want Clarification on environment | Need confirmation | n/a | Mihir Mistry | Accept | All Operational Testing will be done in Test (SITB) environment. | Complete.
2 | MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successful Supplemental v0.4 - Clean; MHHS-DEL3463_SITOPS_DIP06_DIP Offboarding Technical Supplemental v0.1 Clean | We believe detailed Test Cases of Theme 3 Batch 2 will be uploaded in ADO. Any expected date for upload of Test case in ADO | Need confirmation | n/a | Mihir Mistry | Accept | This should be done in next few week, ideally in time for the DITL session 26/03/25) | Complete.
| MHHS-DEL3313_SITOPS_OPC007_COA v0.72; MHHS-DEL3319_SITOPS_OPC008_COS v0.6; MHHS-DEL3320_SITOPS_OPC009_RM_COS v0.7 | Utilita's Market roles are Supplier services & Metering Services. Kindly confirm that Utilita is only responsible to execute the test steps marked as SUPC for the column, Service Producing Trigger (column I) and Service Recipient/Processor of Input/Trigger (Column K) | Need confirmation | n/a | Mihir Mistry | Accept | Please note these scenarios may potentially be descoped as functionality has been proven. Await confirmation from Code Bodies. | Pending
| MHHS-DEL3313_SITOPS_OPC007_COA v0.72; MHHS-DEL3319_SITOPS_OPC008_COS v0.6; MHHS-DEL3320_SITOPS_OPC009_RM_COS v0.7 | It looks like these Test Cases are already covered as part of SIT Non-Functional Theme 2: Lifecycle Processing and E2E and SIT Functional phase.so what is the difference between these two scenarios/Test cases. What would be objective of these test scenarios to be included in SIT OPS Theme 3 Batch 2 | Need confirmation | n/a | Mihir Mistry | Accept | Agreed and potentially may be descoped - Please see above. | Pending
1 | Theme 3 – Batch 2 MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successfully V0.2 | SITOps_DIP01_DIP Onboarding successful supplemental v0.4 clean & redlined (DEL2699) |  |  | Ellen Crawford | Reject | Apologies but cant find a question? | Pending
2 | Theme 3 – Batch 2 MHHS-DEL3235 SITOPS_DIP02_DIP Onboard error handling V0.2 | SITOPS_DIP02_DIP Onboard error handling V0.3 redline (DEL3235) |  |  | Ellen Crawford | Reject | Apologies but cant find a question? | Pending
3 | Theme 3 – Batch 2 MHHS-DEL2701 SITOPS_DIP03_DIP participant in-life Certificate Renewal V0.2 | Is this scenario not required? Demonstrated practically in SIT-F in November? |  |  | Ellen Crawford | Reject | Could you provide test case Ref# of where this has been executed as part of SITF Iand I can review and forward onto Cde Bodies to confirm. | Pending
4 | Theme 3 – Batch 2 MHHS-DEL2702 SITOPS_DIP04_DIP in-life Certificate Re-Issue V0.1 | Is this scenario not required? Demonstrated practically in SIT-F in November? |  |  | Ellen Crawford | Reject | Could you provide test case Ref# of where this has been executed as part of SITF Iand I can review and forward onto Cde Bodies to confirm. | Pending
5 | Theme 3 – Batch 2 MHHS-DEL2703 SITOPS_DIP05_DIP In-life changes to DIP User Privileges V0.1 | Is this scenario not required? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
6 | Theme 3 – Batch 2 MHHS-DEL2704 SITOPS_DIP06_DIP Offboard of a Participant V0.2 | SITOPS_DIP06_DIP Offboard of a Participant V0.4 redline (DEL2704) SITOPS_DIP06_DIP Offboard Technical Supplmental v0.1 clean (DEL3463) |  |  | Ellen Crawford | Reject | Apologies but cant find a question? | Pending
7 | Theme 3 – Batch 2 MHHS-DEL3236 SITOPS_DIP07_DIP In-Life qualification V0.2 | Is this scenario not required? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
8 | Theme 3 – Batch 2 MHHS-DEL3237 SITOPS DIP08 - DIP Reporting/Audit V0.2 | Is this scenario not required? Is this going to be covered by DIP training/what available to PPs? |  |  | Ellen Crawford | Accept | Im not aware of any formal Training sessions managed by the Programme, but I have reached out to DIP Management to see if this is somthing they could provided. | Complete.
9 | Theme 3 – Batch 2 MHHS-DEL3044 SITOPS DIP09 - Participant backoff and retry in the event of comms failure V0.2 | Is this scenario not required? Is this now covered by SIT-NFT? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
10 | Theme 3 – Batch 2 MHHS-DEL3045 SITOPS DIP10 - Communication failure send IF messages V0.2 | Is this scenario not required? Is this now covered by SIT-NFT or having proven retries in SIT-F? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
11 | Theme 3 – Batch 2 MHHS-DEL3257 SITOPS_DIP11_DIP Domain Re-verification successful V0.1 | Is this scenario not required? Demonstrated practically in SIT-F in November? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
12 | Theme 3 – Batch 2 MHHS-DEL3234 SITOPS_BCDR01_Business Continuity and Disaster Recovered V0.1 | Is this scenario not required? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
13 | Theme 3 - Batch 2 DIP06 TC03 – Remove Role from a User | Is this scenario not required? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
14 | Theme 3 - Batch 2 DIP07 TCO2 - Future dates effective date | Is this scenario not required? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
15 | Theme 3 - Batch 2 DIP08 TC07 - DIP generated report | Is this scenario not required? |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
16 | Supplementary 20/2/25-4/3/25 | SITOPS_OC007 COA v0.72 (DEL3313) - removed from migration & included in SIT-Ops |  |  | Ellen Crawford | Reject | We believe Operationally it hasnt been tested, even though it may have functionally been proven. | Complete.
17 | Supplementary 20/2/25-4/3/25 | SITOPS_OC008 COS v0.6 (DEL3319) - removed from migration & included in SIT-Ops |  |  | Ellen Crawford | Accept | Cant see a question but it may resolve your issue but this may be descoped as feedback received is this functionality has been proven in SITF testing and may not be required. | Pending
18 | Supplementary 20/2/25-4/3/25 | SITOPS_OC009 RM COS v0.7 (DEL3320) - removed from migration & included in SIT-Ops |  |  | Ellen Crawford | Accept | Cant see a question but it may resolve your issue but this may be descoped as feedback received is this functionality has been proven in SITF testing and may not be required. | Pending

## RECCo
MHHS-DEL2676 - SIT Operational Test Cases and Test Scenarios Comments Log
*Organisation: | RECCo |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency: | Code Body
*Comment Owner Anonymised: | No
*Date: | 2025-03-03
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner
To be populated by the Programme | Input the Ref # of the area of the document you are commenting on | Succinctly state the comment and the basis for the concern | Provide detail of the change or action required to resolve the comment | Provide a rationale for the change detailing the impact or materiality as a result of not making the recommended change | Provide the name of person providing the comment
| SITOP-DIP06 v0.4 | This test appears far more limited than the earlier version and does not reference revocation of certificates or checks with code bodies to ensure there are no live metering points registered to the organisation that would be stranded if the DIP User access is removed. These are important controls and we believe operational testing should ensure the full process is in place | Re-introduce wider operational checks to ensure the required controls are built into the process. | If the wider checks are not captured in the test there is a risk that these are not built into the process which would not align to code drafting and would introduce an operational risk. | RECCo
| OPC007_COA | The scenario includes steps for the RS to send the D0170 to the losing MOP but these appear after the issuing of the IF036. The D0170 should be sent after the IF035 as set out in the business process. | Move the steps relating to the D0170 so they come after the IF035 appointment acceptance | If the tests are not amended and the RS sends the D0170 after the IF036 it would be inconsistent with the MHHS Design and may caouse delaying in the sending of MTDs in live operations | RECCo
| OPC007_COA | Overview page refers to traditional, but the test case is Advanced | Update the overview page to reflect the test case | The overview page should reflect the test scenarios to avoid confusion | RECCo
| OPC007_COA | There appears to be a lack of clarity around which MOA sends the MTDs. Step 52 suggests the current MS (AMSC) sending the MTDs as a result of the MS appointment. This should be the existing MOP as a result of the DS appointments and / or the new MS (AMSI) as a result of the MS appointment | We would appreciate a discussion with the programme to fully understand who should send the MTDs in a migration i.e. whether both the losing MOP and Gaining MS send to the Gaining DS and what happens if the MS and DS appointments are not progressed in parallel | Operational issues that may impact migration if its not clear when the MTDs should be sent | RECCo
| OPC007_COA | Step 55 states that the MS should check the EES or the IF-003 if MTDs are missing. The IF-003 is only sent for reverse migration so not valid in this scenario | Remove reference to the IF-003 | Erroneous steps, likely to cause testing issues | RECCo
| OPC007_COA | Step 57 has no message - as this is sending the correct details, it should reference the D0268 | Add reference to D0268 | Lack of clarity | RECCo
| OPC007_COA | This scenario is meant to cover missing MTDs, but the MTDs are actually being sent? | Remove steps where the MTDs are sent before the missing MTD test steps | You wouldnt be testing missing MTDs if the MTDs are actually sent | RECCo
| OPC008_COS | Steps 17 and 18 refer to a new connection and are not relevant for a CoS scenario | Remove steps 17 and 18 | Erroneous steps, likely to cause testing issues | RECCo
| OPC008_COS | There appears to be a lack of clarity around which MOA sends the MTDs. Step 74 suggests the current MS (AMSC) sending the MTDs as a result of the MS appointment. This should be the existing MOP as a result of the DS appointments and / or the new MS (AMSI) as a result of the MS appointment | We would appreciate a discussion with the programme to fully understand who should send the MTDs in a migration i.e. whether both the losing MOP and Gaining MS send to the Gaining DS and what happens if the MS and DS appointments are not progressed in parallel | Operational issues that may impact migration if its not clear when the MTDs should be sent | RECCo
| OPC008_COS | Step 93 states that the MS should check the EES or the IF-003 if MTDs are missing. The IF-003 is only sent for reverse migration so not valid in this scenario | Remove reference to the IF-003 | Erroneous steps, may cause testing issues | RECCo
| OPC008_COS | The scenario includes steps for the RS to send the D0170 to the losing MOP but these appear after the issuing of the IF036. The D0170 should be sent after the IF035 as set out in the business process. | Move the steps relating to the D0170 so they come after the IF035 appointment acceptance | If the tests are not amended and the RS sends the D0170 after the IF036 it would be inconsistent with the MHHS Design and may caouse delaying in the sending of MTDs in live operations | RECCo
| OPC008_COS | This scenario is meant to cover missing MTDs, but the MTDs are actually being sent? | Remove steps where the MTDs are sent before the missing MTD test steps | You wouldnt be testing missing MTDs if the MTDs are actually sent | RECCo
| OPC009_RM | Step 19 evidence states MOP will create the D0205. This should be the Supplier. | Amend evidence column to refer to the Supplier sending the D0205 | Erroneous steps, may cause testing issues | RECCo
| OPC009_RM | Step 20 also covers the D0205 but refers to awaiting CSS. Should the text align to step 22 | Review and correct text | Lack of clarity | RECCo
| OPC009_RM | Step 45 is unclear. It suggests the step is receipt of MTDs but the evidence states the SMSO is producing the D0149 / 150. For a smart reverse migration, this should be a skeleton D0150 to the mop and supplier and its not clear how this is a missing MTD scenario as the MTDs are being sent. | Review and correct text | Lack of clarity | RECCo
| OPC009_RM | Step 1018 evidence suggests the MS sends the D0367 which is not correct | Amend evidence column to refer to the Supplier sending the D0367 | Lack of clarity | RECCo

## Utilita
MHHS-DEL2676 - SIT Operational Test Cases and Test Scenarios Comments Log
*Organisation: | Utilita(UEL) |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency: | Supplier and Metring Service
*Comment Owner Anonymised: | No
*Date: | 2025-02-25
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner
1 | MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successful Supplemental v0.4 - Clean; MHHS-DEL3463_SITOPS_DIP06_DIP Offboarding Technical Supplemental v0.1 Clean | Are we going to do execution in production DIP portal or Test DIP portal. Want Clarification on environment | Need confirmation | n/a | Mihir Mistry
2 | MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successful Supplemental v0.4 - Clean; MHHS-DEL3463_SITOPS_DIP06_DIP Offboarding Technical Supplemental v0.1 Clean | We believe detailed Test Cases of Theme 3 Batch 2 will be uploaded in ADO. Any expected date for upload of Test case in ADO | Need confirmation | n/a | Mihir Mistry
| MHHS-DEL3313_SITOPS_OPC007_COA v0.72; MHHS-DEL3319_SITOPS_OPC008_COS v0.6; MHHS-DEL3320_SITOPS_OPC009_RM_COS v0.7 | Utilita's Market roles are Supplier services & Metering Services. Kindly confirm that Utilita is only responsible to execute the test steps marked as SUPC for the column, Service Producing Trigger (column I) and Service Recipient/Processor of Input/Trigger (Column K) | Need confirmation | n/a | Mihir Mistry
| MHHS-DEL3313_SITOPS_OPC007_COA v0.72; MHHS-DEL3319_SITOPS_OPC008_COS v0.6; MHHS-DEL3320_SITOPS_OPC009_RM_COS v0.7 | It looks like these Test Cases are already covered as part of SIT Non-Functional Theme 2: Lifecycle Processing and E2E and SIT Functional phase.so what is the difference between these two scenarios/Test cases. What would be objective of these test scenarios to be included in SIT OPS Theme 3 Batch 2 | Need confirmation | n/a | Mihir Mistry

## EonNext
MHHS-DEL2676 - SIT Operational Test Cases and Test Scenarios Comments Log
*Organisation: | Eon Next |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Comment Owner Anonymised: | No
*Date: | 2025-02-25
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner
1 | Theme 3 – Batch 2 MHHS-DEL2699 SITOPS_DIP01_DIP Onboarding successfully V0.2 | SITOps_DIP01_DIP Onboarding successful supplemental v0.4 clean & redlined (DEL2699)
2 | Theme 3 – Batch 2 MHHS-DEL3235 SITOPS_DIP02_DIP Onboard error handling V0.2 | SITOPS_DIP02_DIP Onboard error handling V0.3 redline (DEL3235)
3 | Theme 3 – Batch 2 MHHS-DEL2701 SITOPS_DIP03_DIP participant in-life Certificate Renewal V0.2 | Is this scenario not required? Demonstrated practically in SIT-F in November?
4 | Theme 3 – Batch 2 MHHS-DEL2702 SITOPS_DIP04_DIP in-life Certificate Re-Issue V0.1 | Is this scenario not required? Demonstrated practically in SIT-F in November?
5 | Theme 3 – Batch 2 MHHS-DEL2703 SITOPS_DIP05_DIP In-life changes to DIP User Privileges V0.1 | Is this scenario not required?
6 | Theme 3 – Batch 2 MHHS-DEL2704 SITOPS_DIP06_DIP Offboard of a Participant V0.2 | SITOPS_DIP06_DIP Offboard of a Participant V0.4 redline (DEL2704) SITOPS_DIP06_DIP Offboard Technical Supplmental v0.1 clean (DEL3463)
7 | Theme 3 – Batch 2 MHHS-DEL3236 SITOPS_DIP07_DIP In-Life qualification V0.2 | Is this scenario not required?
8 | Theme 3 – Batch 2 MHHS-DEL3237 SITOPS DIP08 - DIP Reporting/Audit V0.2 | Is this scenario not required? Is this going to be covered by DIP training/what available to PPs?
9 | Theme 3 – Batch 2 MHHS-DEL3044 SITOPS DIP09 - Participant backoff and retry in the event of comms failure V0.2 | Is this scenario not required? Is this now covered by SIT-NFT?
10 | Theme 3 – Batch 2 MHHS-DEL3045 SITOPS DIP10 - Communication failure send IF messages V0.2 | Is this scenario not required? Is this now covered by SIT-NFT or having proven retries in SIT-F?
11 | Theme 3 – Batch 2 MHHS-DEL3257 SITOPS_DIP11_DIP Domain Re-verification successful V0.1 | Is this scenario not required? Demonstrated practically in SIT-F in November?
12 | Theme 3 – Batch 2 MHHS-DEL3234 SITOPS_BCDR01_Business Continuity and Disaster Recovered V0.1 | Is this scenario not required?
13 | Theme 3 - Batch 2 DIP06 TC03 – Remove Role from a User | Is this scenario not required?
14 | Theme 3 - Batch 2 DIP07 TCO2 - Future dates effective date | Is this scenario not required?
15 | Theme 3 - Batch 2 DIP08 TC07 - DIP generated report | Is this scenario not required?
16 | Supplementary 20/2/25-4/3/25 | SITOPS_OC007 COA v0.72 (DEL3313) - removed from migration & included in SIT-Ops
17 | Supplementary 20/2/25-4/3/25 | SITOPS_OC008 COS v0.6 (DEL3319) - removed from migration & included in SIT-Ops
18 | Supplementary 20/2/25-4/3/25 | SITOPS_OC009 RM COS v0.7 (DEL3320) - removed from migration & included in SIT-Ops